## Waste
PCD Ref | Project No. | Title | Total Forecast (January 2026) (£m) | Total Forecast (April 2026) (£m) | % difference | Commentary
Gated Scheme - NO PCD | M184 | Beckton STW SPG | 277.02 | 349.14 | 26% | Gated scheme - Date reflects our most recent quarterly gated submission
PCDWW35 | K035.01 | Bexley WTW – Alleviation of Low Flows (W | 85.41 | 8.03 | -91% | AMP7 methodology change
PCDWW35 (Contributor) | K561.01 | LF Mitigation London - Upper Cray Restoration | 1.64 | 0.54 | -67% | AMP7 methodology change
PCDWW35 | K560.04 | LF Mitigation TV - RIVER RESTORATION PROJECTS - CHESS | 0.71 | 0.41 | -42% | Change in solution
PCDWW35 | K036.01 | Hawridge - Alleviation of Low Flows | 52.98 | 97.33 | 84% | Data Error
PCDWW35 | K561.01 | LF Mitigation London - Upper Cray Restoration | 1.24 | 0.54 | -56% | AMP7 methodology change
PCDWW35 | K561.02 | LF Mitigation London - Upper Darent Restoration - SUNDRIDGE PUMPING STATION | 1.24 | 3.38 | 172% | AMP7 methodology change
PCDWW35 | K561.03 | LF Mitigation London - Upper Darent Restoration - WESTERHAM HILL PS | 1.24 | 0.11 | -91% | AMP7 methodology change
PCDWW35 | J009 | Guildford STW Relocation Delivery | 179.71 | 118.24 | -34% | AMP7 methodology change
PCDWW35 | J568 | East Hyde AMP7 Growth | 95.13 | 16.9 | -82% | AMP7 methodology change
PCDWW35 | J971.01 | Kingston Bagpuize STW Growth and Quality | 27.17 | 6.95 | -74% | AMP7 methodology change
PCDWW35 | J983 | Haslemere STW Early Procurement | 4.22 | 25.87 | 513% | AMP7 methodology change
PCDWW35 | J988.01 | Harpenden STW Flow compliance and Low P | 64.89 | 22.94 | -65% | AMP7 methodology change
PCDWW35 | J991.01 | Burstow STW Growth & Flow Compliance | 29.63 | 26.55 | -10% | AMP7 methodology change
PCDWW35 | K104.01 | Bordon Flow Compliance | 72.29 | 52.08 | -28% | Programme level efficiency
PCDWW35 | K245.01 | Oxford STW AMP 7 | 232.68 | 77.71 | -67% | AMP7 methodology change
PCDWW35 | K298.01 | Maple Lodge STW Quality AMP7 New Permit | 258.62 | 105.89 | -59% | Programme level efficiency
PCDWW35 | K298.01 | Maple Lodge STW Quality AMP7 New Permit | 133.23 | 105.89 | -21% | Programme level efficiency
PCDWW35 | K444.01 | WWNI Alton STW P-removal | 19.31 | 88.95 | 361% | Data Error
PCDWW35 | K444.04 | WWNI Fleet STW P-removal | 22.3 | 1.8 | -92% | Data Error
PCDWW35 | L477.01 | Brentwood STW WAAP and P-Removal | 19.24 | 9.77 | -49% | AMP7 methodology change
PCDWW35 | L516.01 | Farnham STW WAAP and P-Removal | 24.79 | 18.66 | -25% | AMP7 methodology change
PCDWW35 | K672.01 | WWNI Ripley STW G2G and Low P | 28.54 | 22.64 | -21% | AMP7 methodology change
PCDWW35 | K759.01 | WWNI Watlington STW FTFT & Low P | 4.64 | 7.46 | 61% | Change in solution
PCDWW35 | K831.01 | WWNI Thornwood STW G2G & P-removal | 12.99 | 6.91 | -47% | AMP7 methodology change
PCDWW35 | K936.01 | Stansted Mountfitchet STW Growth & Low P | 23.73 | 13.75 | -42% | AMP7 methodology change
PCDWW35 | L470.01 | Theydon Bois STW WAAP and P-Removal | 26.84 | 20.82 | -22% | AMP7 methodology change
PCDWW35 | L483.01 | Burghfield STW WAAP and P-Removal | 24.24 | 17.09 | -30% | AMP7 methodology change
PCDWW35 | L484.01 | Waddesdon STW WAAP and P-Removal | 15.6 | 10.34 | -34% | AMP7 methodology change
PCDWW35 | L487.01 | Shamley Green STW WAAP & P-Removal | 19.62 | 7.57 | -61% | AMP7 methodology change
PCDWW35 | L511.01 | North Weald STW PRemoval&Flow Compliance | 29.85 | 9.8 | -67% | AMP7 methodology change
PCDWW35 | L514.01 | Wisley STW G2G and P-Removal | 43.78 | 13.07 | -70% | AMP7 methodology change
PCDWW35 | L696.01 | Marsh Gibbon STW Low P | 1.05 | 1.68 | 60% | Change in solution
PCDWW35 | L700.01 | South Leigh STW Low P | 1.14 | 1.54 | 35% | Change in solution
PCDWW35 | L745.01 | Holmwood STW WAAP and P-Removal | 17.93 | 12.99 | -28% | AMP7 methodology change
PCDWW35 | K932.01 | BENTLEY STW | 2.16 | 0.09 | -96% | Data Error - scheme completed
PCDWW35 | L697 | Lewknor STW Low P | 5.5 | 4.73 | -14% | Programme level efficiency
PCDWW35 | K649.01 | WWNI Mill Green STW G2G and Low P | 15.52 | 9.69 | -38% | AMP7 methodology change
PCDWW27 | M100 | Arborfield STW - AMP8 Growth | 43.38 | 33.33 | -23% | Methodology
PCDWW12 | M167 | BASILDON PARK STW | 1.36 | 1.58 | 16% | Methodology
PCDWW27 | M102 | Cassington STW - AMP8 Growth | 20.34 | 22.49 | 11% | Data Error
PCDWW12 | L873 | CHALGROVE STW | 14.49 | 10.85 | -25% | Programme level efficiency
PCDWW12 | M201 | CODICOTE CSO | 1.67 | 1.86 | 11% | Methodology
PCDWW27 | L670 | Culham STW - AMP8 Growth | 26.78 | 8.47 | -68% | Methodology
PCDWW12 | M168 | HEADLEY STW 08TW101402d | 1.28 | 1.43 | 11% | Methodology
PCDWW30 | UBA8.SEW.S39567, UBA8.SEW.S42128, UBA8.SEW.S42127, M423 | IED scheme 8 Camberley STC | 17.82 | 21.97 | 23% | Change in solution
PCDWW30 | M369, J568 | IED scheme 14 East Hyde STC | 14.65 | 19.15 | 31% | Refining scope at East Hyde (to best align with compliance requirements)
PCDWW30 | M358 | IED scheme 20 Reading STC | 1.35 | 1.67 | 24% | We now have real prices and are about to go into delivery
PCDWW18 | L620 | INV4 Sites Storm Overflow Programme | 33.68 | 14.06 | -58% | Methodology
PCDWW12 | M160 | LECKHAMPSTEAD STW | 2.82 | 2.45 | -13% | Methodology
PCDWW12 | L840 | MARSH GIBBON STW | 1.35 | 0.96 | -29% | Change in solution
PCDWW18 | UBA8.SEW.S39057 | Phosphorus Investigations | 1.97 | 2.47 | 25% | Refinement of need
PCDWW18 | UBA8.SEW.S38655 | PR24 WINEP Ammonia Investigations | 0.8 | 0.47 | -41% | Methodology
PCDWW18 | M146 | WWNI PR24 WINEP WFD SW Investigations | 2.63 | 3.75 | 43% | Cost refinement following detail design and on-site surveys
PCDWW18 | M147 | PR24 WINEP SSSI Investigations | 2.53 | 2.06 | -19% | Cost refinement following detail design and on-site surveys
PCDWW3 | M490 | PR24 WINEP UMON6d | 6.27 | 0 | -100% | Data Error
PCDWW18 | L891 | Pr24 WINEP Wallingford Beach Bathing Water study | 0.3 | 0.22 | -24% | Methodology
PCDWW12 | UBA8.SEW.S40809 | WATLINGTON STW | 0 | 0 | -100% | Methodology
PCDWW3 | M490 | WINEP Emergency Overflows monitoring | 4.27 | 0.4 | -91% | Data Error
PCDWW18 | M420 | Wolvercote Stream Bathing Water Invest | 3.26 | 0.25 | -92% | Methodology
PCDWW10 | L837 | Chertsey STW - 08TW100157a, Chertsey STW - 08TW100886a | 27.64 | 21.54 | -22% | Cost refinement following detail design and on-site surveys
PCDWW10 | M319 | Iver (North) STW - 08TW100159a | 2.26 | 2.62 | 16% | Complexity of solution due to onsite condition and multiple drivers
PCDWW7 | L837 | Chertsey STW AMP8 WINEP Low P and Chem | 58.74 | 45.77 | -22% | Cost refinement following detail design and on-site surveys
PCDWW10 | UBA8.SEW.S38072 | Chieveley STW - 08TW100859a | 1.01 | 1.97 | 96% | Methodology
PCDWW10 | UBA8.SEW.S38508 | East Shefford STW - 08TW100860a | 0 | 0 | -100% | Methodology
PCDWW10 | M299 | Charlton-on-Otmoor STW - 08TW100861a | 3.85 | 7.12 | 85% | Complexity of solution due to onsite condition and multiple drivers
PCDWW10 | UBA8.SEW.S39552 | Appleton STW - 08TW100863a | 6.94 | 3.55 | -49% | Methodology
PCDWW10 | M100 | Arborfield STW - 08TW100864a | 11.94 | 9.04 | -24% | Methodology
PCDWW10 | K435 | Banbury STW - 08TW100869a | 33.81 | 26.44 | -22% | Programme level efficiency
PCDWW10 | M429 | Chadlington STW - 08TW100883a | 3.55 | 10.39 | 193% | Complexity of solution due to onsite condition and multiple drivers
PCDWW10 | L838 | Chalgrove STW - 08TW100884a | 6.02 | 7.92 | 32% | Methodology
PCDWW10 | M374 | Crawley STW - 08TW100893a | 33.71 | 37.14 | 10% | Methodology
PCDWW10 | L670 | Culham STW - 08TW100897a | 8.73 | 13.99 | 60% | Methodology
PCDWW10 | UBA8.SEW.S38978 | Culworth STW - 08TW100898a | 3.17 | 3.52 | 11% | Methodology
PCDWW10 | M179 | Didcot STW - 08TW100899a | 18.9 | 23.3 | 23% | Methodology
PCDWW10 | M188 | Hogsmill STW - 08TW100910a, Hogsmill 'B' STW - 08TW100220 | 67.06 | 44.39 | -34% | Programme level efficiency
PCDWW10 | M242 | Little Compton STW - 08TW100916a | 3.38 | 3.89 | 15% | Methodology
PCDWW10 | M603 | Little Milton STW - 08TW100917a | 3.68 | 4.06 | 10% | Methodology
PCDWW10 | K563 | Middleton Cheney STW - 08TW100919a | 12.89 | 6.24 | -52% | Programme level efficiency
PCDWW10 | K540 | Milton-Under-Wychwood STW - 08TW100922a | 5.92 | 4.58 | -23% | Methodology
PCDWW10 | M457 | Priors Marston STW - 08TW100926a | 0 | 5.6 | 100% | Mapping issue in project for Jan submission
PCDWW10 | M180 | Reading STW - 08TW100928a | 54.52 | 37.56 | -31% | Methodology
PCDWW10 | M467 | Sandhurst STW - 08TW100930a | 10.53 | 11.78 | 12% | Methodology
PCDWW10 | M085 | Silchester STW - 08TW100934a | 16.1 | 9.78 | -39% | Methodology
PCDWW10 | K222 | Slough STW - 08TW100935a | 34.52 | 16.56 | -0.52 | Programme level efficiency
PCDWW10 | M181 | Swindon STW - 08TW100939a | 53.31 | 39.81 | -0.25 | Programme level efficiency
PCDWW10 | M297 | Tring STW - 08TW100942a | 6.67 | 13.45 | 1.02 | Methodology
PCDWW10 | M246 | Witney STW - 08TW100949a | 14.92 | 3.51 | -0.76 | Methodology
PCDWW10 | M602 | Hanwell STW - 08TW100956a | 3.39 | 3.74 | 0.1 | Methodology
PCDWW10 | M241 | Aston Le Walls STW - 08TW100960a | 2.35 | 2.7 | 0.15 | Methodology
PCDWW10 | M464 | Abbess Roding STW - 08TW100967a | 4.75 | 5.27 | 0.11 | Methodology
PCDWW5 | UBA8.SEW.S39218 | Newmans Lane SPS | 1.55 | 2.22 | 0.43 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39216 | ANDOVERSFORD STW | 4.35 | 4.99 | 0.15 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S40747 | Briff Lane (Bucklebury) STW | 2.65 | 3.39 | 0.28 | Methodology
PCDWW4 | UBA8.SEW.S40747 | Briff Lane (Bucklebury) STW | 2.87 | 3.29 | 0.15 | Methodology
PCDWW5 | UBA8.SEW.S39212 | BLEDINGTON STW | 3.38 | 4.06 | 0.2 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39211 | BLETCHINGDON STW | 3.59 | 4.37 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39188 | CHURT SPS | 5.97 | 7.35 | 0.23 | Methodology
PCDWW5 | UBA8.SEW.S39177 | BRICKENDON STW | 1.14 | 1.96 | 0.72 | Methodology
PCDWW5b | M534 | BURGHFIELD STW | 19.19 | 5.8 | -0.7 | Methodology
PCDWW5 | M534 | BURGHFIELD STW | 3.39 | 1.5 | -0.56 | Methodology
PCDWW5 | UBA8.SEW.S39171 | CHADLINGTON STW | 4.48 | 5.11 | 0.14 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39169 | CHAPEL ROW (Berks) STW | 2.16 | 3.15 | 0.46 | Methodology
PCDWW5 | UBA8.SEW.S39168 | CHARLTON-ON-OTMOOR STW | 3.63 | 4.1 | 0.13 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39163 | COMBE STW | 2.25 | 2.97 | 0.32 | Methodology
PCDWW4 | M531 | Compton (Berks) STW | 3.67 | 6.25 | 0.7 | Methodology
PCDWW5 | M528 | CRONDALL STW | 5.08 | 8.56 | 0.69 | Methodology
PCDWW4 | M528 | CRONDALL STW | 3.83 | 1.25 | -0.67 | Methodology
PCDWW5 | UBA8.SEW.S39159 | CUDDINGTON STW | 3.82 | 4.45 | 0.16 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S38361 | STONEBRIDGE SSO, BROCKHAM CSO | 5.11 | 6.37 | 0.25 | Methodology
PCDWW5 | UBA8.SEW.S39155 | EAST GRAFTON STW | 0.83 | 1.58 | 0.9 | Methodology
PCDWW5b | M545 | EAST SHEFFORD STW | 12.81 | 4.68 | -0.63 | Methodology
PCDWW5 | M545 | EAST SHEFFORD STW | 3.01 | 11 | 2.66 | Methodology
PCDWW5 | UBA8.SEW.S39153 | EYDON STW | 1.41 | 1.89 | 0.34 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | M235 | Fyfield (Wilts) STW | 11.24 | 16.13 | 0.43 | Methodology
PCDWW4 | M235 | Fyfield (Wilts) STW | 3.95 | 5.56 | 0.41 | Methodology
PCDWW5 | UBA8.SEW.S39149 | GRENDON UNDERWOOD STW | 4.08 | 5.5 | 0.35 | Methodology
PCDWW5 | UBA8.SEW.S39148 | HAMPSTEAD NORREYS STW | 2.92 | 3.36 | 0.15 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39147 | HAMSTEAD MARSHALL STW | 1.28 | 2.01 | 0.57 | Methodology
PCDWW5 | UBA8.SEW.S39146 | HANWELL STW | 4.72 | 5.39 | 0.14 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S40746 | CHARLBURY STW | 4.27 | 5.01 | 0.17 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S38366 | Horley (Surrey) STW | 12.68 | 15.31 | 0.21 | Methodology
PCDWW5 | UBA8.SEW.S40745 | FINSTOCK STW | 2.4 | 3.6 | 0.5 | Methodology
PCDWW5 | UBA8.SEW.S39141 | HORTON-CUM-STUDLEY STW | 2.97 | 3.67 | 0.23 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39140 | HUNGERFORD STW | 1.66 | 2.41 | 0.45 | Methodology
PCDWW5 | UBA8.SEW.S38557 | Ironsbottom (Sidlow) STW | 3.37 | 4.7 | 0.39 | Methodology
PCDWW5 | UBA8.SEW.S39136 | LITTLE COMPTON STW | 2.46 | 3.35 | 0.36 | Methodology
PCDWW5 | M237 | MARKYATE STW | 13.48 | 17.29 | 0.28 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S40743 | HUCKERS LANE (SELBOURNE) SPS | 3.07 | 3.68 | 0.2 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39127 | SOUTH LEIGH STW | 2.03 | 2.76 | 0.36 | Methodology
PCDWW5b | M233 | STANDLAKE STW | 2.87 | 4.79 | 0.67 | Methodology
PCDWW5 | M233 | STANDLAKE STW | 3.65 | 3 | -0.18 | Methodology
PCDWW5 | UBA8.SEW.S39124 | Stewkley STW | 4.69 | 5.25 | 0.12 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39121 | THERFIELD STW | 5.84 | 6.98 | 0.2 | Methodology
PCDWW5 | UBA8.SEW.S39119 | THORNWOOD STW | 3.91 | 4.53 | 0.16 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39116 | WADDESDON STW | 4.74 | 5.36 | 0.13 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39115 | Weston (Herts) STW | 2.98 | 3.77 | 0.27 | Methodology
PCDWW5 | UBA8.SEW.S39113 | WHITWELL STW | 3.79 | 4.46 | 0.18 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39112 | Widford and wareside STW | 2.95 | 3.66 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39111 | WILLINGALE STW | 1.45 | 1.91 | 0.32 | Methodology
PCDWW5 | UBA8.SEW.S39110 | WINGRAVE STW | 3.67 | 4.34 | 0.18 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39109 | BEECH HALL CRESCENT, WALTHAMSTOW CSO | 3.39 | 4.16 | 0.23 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39108 | SOUTH PARK, ILFORD CSO | 3.61 | 4.21 | 0.17 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39107 | RAY LODGE ROAD (RAY PARK 1) CSO | 3.43 | 4.03 | 0.18 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39106 | Prospect road , woodford CSO (Monkhams Lane) | 3.23 | 3.93 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39105 | WORCESTER CRESCENT CSO | 3.33 | 3.87 | 0.16 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39103 | MULBERRY COURT, HALL ROAD CSO | 3.43 | 4.2 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39102 | LONGBRIDGE ROAD CSO | 3.23 | 3.93 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39101 | HIGH ROAD, WOODFORD CSO | 3.22 | 4.12 | 0.28 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39100 | AUCKLAND ROAD STORM TANKS SPS | 3.09 | 3.73 | 0.21 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39099 | BROOK WAY, CHIGWELL CSO | 3.23 | 3.93 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39098 | REDBRIDGE LANE WEST, WANSTEAD CSO | 3.17 | 3.87 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39096 | ROAD A3, ROEHAMPTON VALE CSO | 3.44 | 4.21 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S38550 | STREATHAM STORM RELIEF CSO B | 8.11 | 13.4 | 0.65 | Methodology
PCDWW5 | UBA8.SEW.S38373 | STREATHAM VALE STORM RELIEF CSO | 3 | 3.89 | 0.3 | Methodology
PCDWW5 | UBA8.SEW.S39093 | CROFTON ROAD, SUNNYDALE CSO | 3.22 | 3.93 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S38357 | OUTSIDE 135 LEESIDE CRESCENT (FORMERLY BROOKSIDE ROAD, GOLDERS GREEN) | 4.65 | 6.04 | 0.3 | Methodology
PCDWW5 | UBA8.SEW.S39090 | HONEYPOT LANE (Winchester Avenue) CSO | 3.36 | 4.05 | 0.21 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39088 | DAINTRY CLOSE CSO | 3.23 | 3.93 | 0.21 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39087 | ABBESS RODING STW | 2.51 | 3.08 | 0.23 | Methodology
PCDWW5 | UBA8.SEW.S39209 | HOLYBOURNE SPS | 3.29 | 3.92 | 0.19 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39205 | WARDINGTON SPS | 3.38 | 4.06 | 0.2 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39204 | Rusper Stw | 3.14 | 3.8 | 0.21 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39203 | CROPREDY STW | 3.66 | 4.33 | 0.18 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | M547 | EAST GARSTON SPS | 2.83 | 4.06 | 0.43 | Methodology
PCDWW5 | UBA8.SEW.S39200 | COBHAM BRIDGE, ADJ COBHAM PS CSO | 3.17 | 3.73 | 0.18 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW4 | UBA8.SEW.S39197 | HAMBLEDEN STW | 2.41 | 2.98 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39195 | WEALDBRIDGE, NORTH WEALD SPS | 3.04 | 3.63 | 0.19 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39194 | CASSINGTON STW | 9.65 | 11.22 | 0.16 | Methodology
PCDWW4 | UBA8.SEW.S39194 | CASSINGTON STW | 13.33 | 14.96 | 0.12 | Methodology
PCDWW5 | UBA8.SEW.S39192 | Selborne STW | 2.29 | 2.92 | 0.28 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | M527 | SEVENHAMPTON VILLAGE STW | 3.21 | 4.1 | 0.28 | Methodology
PCDWW5 | UBA8.SEW.S39190 | HADHAM MILL SPS | 3.04 | 3.63 | 0.2 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39189 | WINTERBOURNE STW | 1.14 | 2.03 | 0.78 | Methodology
PCDWW5 | UBA8.SEW.S38372 | STREATHAM STORM RELIEF CSO E | 3.52 | 4.67 | 0.33 | Methodology
PCDWW5 | UBA8.SEW.S39182 | ALICIA AVENUE CSO | 3.17 | 3.86 | 0.22 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39181 | CHIGWELL ROAD, WOODFORD GREEN 08TW101100a | 3.17 | 3.95 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39180 | CHIGWELL ROAD, WOODFORD GREEN 08TW101101a | 3.17 | 3.95 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39179 | CHIGWELL ROAD, WOODFORD GREEN 08TW101102a | 3.17 | 3.95 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39178 | CHIGWELL ROAD, WOODFORD GREEN 08TW101103a | 3.17 | 3.95 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39176 | CHIGWELL ROAD, WOODFORD GREEN 08TW101104a | 3.17 | 3.95 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39175 | CHIGWELL ROAD, WOODFORD GREEN 08TW101105a | 3.17 | 3.95 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39174 | CHIGWELL ROAD, WOODFORD GREEN 08TW101106a | 3.17 | 3.95 | 0.24 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S39173 | CHIGWELL ROAD, WOODFORD GREEN 08TW101107a | 3.06 | 3.84 | 0.25 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5b | UBA8.SEW.S38363 | Burstow STW | 13.75 | 16.14 | 0.17 | Methodology
PCDWW5 | UBA8.SEW.S38363 | Burstow STW | 8.07 | 9.62 | 0.19 | Methodology
PCDWW10 | M247 | Thame STW - 08TW101889a | 7.62 | 9.19 | 0.21 | Methodology
PCDWW10 | M373 | Basingstoke STW - 09TW100022a | 21.28 | 23.56 | 0.11 | Methodology
PCDWW10 | M465 | Berkhamsted STW - 09TW100023a | 8.62 | 9.62 | 0.12 | Methodology
PCDWW10 | L892 | Chobham STW - 09TW100028a | 13.02 | 9.14 | -0.3 | Cost refinement following detail design and on-site surveys
PCDWW10 | M238 | Mill Green STW - 09TW100035a | 9.58 | 12.7 | 0.33 | Methodology
PCDWW10 | M245 | High Wycombe STW - 08TW101485a | 1.77 | 0 | -1 | No build solution
PCDWW10 | M109 | Rye Meads STW - 09TW100046a | 109.14 | 175.58 | 0.61 | Complexity of solution due to onsite condition and multiple drivers
PCDWW10 | M118 | Weybridge STW - 09TW100049a | 10.19 | 32.32 | 2.17 | Complexity of solution due to onsite condition and multiple drivers
PCDWW5 | UBA8.SEW.S41337 | SNAKES LANE CSO | 3.44 | 0 | -1 | Methodology
PCDWW5 | M581 | Bampton STW | 4.83 | 9.64 | 0.99 | Methodology
PCDWW4 | M581 | Bampton STW | 6.96 | 3.28 | -0.53 | Methodology
PCDWW5 | UBA8.SEW.S39214 | BARKWAY STW | 1.59 | 2.25 | 0.42 | Methodology
PCDWW5 | UBA8.SEW.S41575 | FARNHAM STW | 3.36 | 4.06 | 0.21 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S41499 | Constable's Piece (Beckley) STW | 3.22 | 3.83 | 0.19 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S41156 | NEW STORM TANKS AT CASCADE ROAD | 4.05 | 4.74 | 0.17 | Methodology - Apportionment of investigative costs back to scheme (M138)
PCDWW5 | UBA8.SEW.S41490 | LITTLE MILTON STW | 3.21 | 3.9 | 0.21 | Methodology - Apportionment of investigative costs back to scheme (M138)

## Water
PCD Ref | Project No. | Title | Total Forecast (January 2026) (£m) | Total Forecast (April 2026) (£m) | % difference | Commentary
Gated scheme - NO PCD | UBA8.WAT.S41877 | PR24 SEMD - ESS/OT | 14.833 | 31.5552 | 112.7% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | UBA8.WAT.S41876 | PR24 SEMD - Patrol and Response | 40.2668 | 3.374 | -91.62% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | L827 | SEMD - CAT 3-5 | 81.916 | 73.2602 | -10.57% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M321 | 3185, 3186, 3187 | 24.792 | 21.2543 | -14.27% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M323 | 3179 | 11.3779 | 8.9605 | -21.25% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M325 | 3210, 3211 | 17.2257 | 15.3331 | -10.99% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M328 | 3170 | 10.4122 | 22.5116 | 116.2% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M332 | 3190, 3191, 3192 | 29.3286 | 25.8742 | -11.78% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M333 | 3072 | 10.938 | 9.7605 | -10.77% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M364 | 3164 | 52.291 | 45.597 | -12.8% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M365 | 3200 | 41.8392 | 36.6068 | -12.51% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M370 | 3300 | 56.5305 | 49.4261 | -12.57% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M371 | 3165 | 35.5381 | 31.7243 | -10.73% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M372 | 3166 | 41.6042 | 36.8687 | -11.38% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | M586 | SEMD AMC – System and Sites CNI Pack 11 | 9.0441 | 5.0167 | -44.53% | Gated scheme - Date reflects our most recent quarterly gated submission
Gated scheme - NO PCD | UBA8.WAT.S40977 | Coppermills UV Treatment Design Work | 4.9109 | 4.1175 | -16.16% | Gated scheme - Date reflects our most recent quarterly gated submission
PCDW12 | UBA8.WAT.S39396, UBA8.WAT.S39404, UBA8.WAT.S39405, UBA8.WAT.S39406, UBA8.WAT.S39407, UBA8.WAT.S39408, UBA8.WAT.S39409, UBA8.WAT.S40145, UBA8.WAT.S40147, UBA8.WAT.S40148, UBA8.WAT.S40149, UBA8.WAT.S40151, UBA8.WAT.S40152, UBA8.WAT.S42275, UBA8.WAT.S39412, UBA8.WAT.S39413, UBA8.WAT.S39419, UBA8.WAT.S39428, UBA8.WAT.S39429 | Metering Programme | 385.775 | 462.9915 | 20.02% | Change in solution
PCDW11a | UBA8.WAT.S36984 | WRMP19_ML_ Didcot Raw Water Purchase | 20.4894 | 18.1751 | -11.3% | Contractual issues
PCDWW32 | M252 | Guildford Power Resilience | 3.1255 | 5.1555 | 64.95% | Lack of internal resourcing
PCDW5 | L875 | PR24 WINEP ED Bradfield | 2.2108 | 1.9542 | -11.61% | Methodology
PCDW8 | M221 | WINEP AMP8 Catchment Management Schemes – Drinking Water Protected Areas (DrWPA) | 0.98726 | 0.56822 | -42.44% | Programme level efficiency
PCDW8 | M171 | Implemetning company - wide INNS plan | 0.73724 | 0.33409 | -54.68% | Programme level efficiency
PCDW8 | M046 | Low Flow & Env Destination Inv & Eels | 5.1198 | 8.882 | 73.48% | Methodology
PCDW5 | L874 | PR24 WINEP ED Netley Mill Sustainability | 15.3953 | 2.004 | -86.98% | Methodology
PCDW11a | M213, M470, M469, M468 | WRMP'24 Ml/d | 48.7919 | 43.8641 | -10.1% | Programme level efficiency
PCDW8 | UBA8.WAT.S40116 | PR24 WINEP New gauge investigation | 1.1251 | 0.93029 | -17.32% | Methodology
PCDW5 | L898 | River Restoration (RR) LND | 5.2766 | 7.5978 | 43.99% | Methodology
PCDW5 | UBA8.WAT.S37803 | PR24 WINEP SWELLS | 2.4595 | 2.0279 | -17.55% | Methodology
PCDW5 | M592 | WINEP Nrt New River Wells Chinnor licenc | 0.0039518 | 0.10249 | 2493% | Methodology