## Cover
Cover
PR24 Delivery Plan Tables
| Model code | PR24DP
| Version number: | 3
| File name: | Thames Water - AMP8 Delivery Plan - Data Tables (for Website).xlsx
| Date: | 2026-08-13
| For enquiries please contact: | PR24ofwat.gov.uk
| Instructions: | See below.
Changes since previous published model:
Please see Change log sheet for changes common for all companies. We also have included company specific change logs.
With red the changes we made in tables based on companies' feedback.
Tables
Please note that we will collect the input values as given. The number of decimal places stated is for our database visual view. With respect to the colours shown in the baseline tables, we note that: • If there is a cell which contains a formula and is performing a calculation on the cell(s) inside its formula using information from another sheet, it is pink. • If there is a cell which contains a formula and is performing a calculation on the cell(s) inside its formula, it is blue. We have set out in the guidance document the assumptions we used to calculate the PCD output and expenditure delivery profiles for the baseline tables. We expect companies to use our profiles for the baseline tables in their delivery plan submission. For PCDs where we have not provided a baseline profile but reported only the target output or allowed total expenditure (totex) at year 5 of AMP, we ask companies to provide profiled annual output and totex values in their deliver plans (commentary). We also ask companies to provide the assumptions used to derive these profiles in their delivery plans.
Price base for financial data
We set out the price base of any financial data in the related submission tables guidance document. The price base for financial information is 2022-23 base year prices indexed using the financial year average Consumer Price Index (including housing costs), that is, 2022-23 prices FYA (CPIH deflated).
Submissions
Your completed spreadsheet should be uploaded to your company's area of our SharePoint DCS website. We provide a link to this website below. Please upload the tables we have requested by 12 August 2025 to the folder, "Delivery Plan Data Capture" and the 2025-26 Q# sub Folders. If you require any assistance with this, please contact PR24ofwat.gov.uk.
Links to data capture site
<Data Capture site>
Links to additional information / guidance
<Delivery Plan Guidance>
Summary:
This file sets out the data we are seeking to collect through delivery plans. This collates data on outturn and forecast delivery and expenditure data in relation to the Price Control Deliverables (PCD) and interim milestones. It also requests data at scheme level for enhanced engagement, large gated, water resilience and high-profile enhancement schemes. This data will allow us and stakeholders to understand the progress that companies are making towards achieving their PCD targets and delivering their PR24 programme.
Companies should use this template to submit their delivery plan tables data. The common format of this template will allow us to process the data provided by companies effectively. Please do not make any undue alterations to our template as you populate it.
Contents:
Industry_Query log: includes our response to main issues raised by all companies.
Company name_Query log: includes our response to main issues raised by a specific company.
Industry_Change log: includes our changes to the template applicable to all companies.
Company name_Change log: includes our company specific changes.
F_Inputs_BIO5: pulls the bioresources raw output data from Ofwat's database. Where possible, it calculates output percentages on a cumulative basis. These are further used to derive the PCD enhancement output delivery profile in the DPWW1 sheet.
F_Inputs_CWW20: pulls the wastewater raw output data from Ofwat's database. Where possible it calculates output percentages on a cumulative basis. These are further used to derive the PCD enhancement output delivery profile in the DPWW1 sheet.
F_Inputs_WW_EXP: pulls the wastewater raw expenditure data from Ofwat's database. Where possible it calculates expenditure percentages on a cumulative basis. These are further used to derive the PCD enhancement expenditure delivery profile in the DPWW2 sheet.
F_Inputs_W_EXP: pulls the water raw expenditure data from Ofwat's database. Where possible it calculates expenditure percentages on a cumulative basis. These are further used to derlive the PCD enhancement expenditure delivery in the DPW2 sheet.
F_Inputs_NRF: pulls the water and wastewater network infrastructure reinforcement data from Ofwat's database. It calculates the expenditure percentages on a cumulative basis. These are further used to derive the PCD enhancement expenditure profile in the DPB2 sheet.
PCD list: provides the list of PCDs for each company for base, wastewater and water enhancement expenditure.
Calcs_Net zero: where possible provides the output profile for net zero PCD schemes across companies and calculates cumulative PCD allowed total enhancement expenditure. This information is then used in the DPWW1 and DPWW2 sheets.
Calcs_Supply: where possible it calculates expenditure percentages for supply schemes (base overlap, high medium, low and very low) on a cumulative basis. These are further used to derive the PCD enhancement expenditure delivery profile in the DPW2 sheet.
DPB1, DPW1 and DPWW1: request companies to provide the number of units of PCD output delivered against each PCD output line. For Base PCDs, we have common and bespoke PCDs outputs (DPB1_ADD)
DPB2, DPW2 and DPWW2 request companies to provide expenditure associated with PCD output for each PCD output line. For Base PCDs, we have common and bespoke PCDs expenditure (DPB2_ADD).
DPWW3 and DPW3: presents interim milestones for a number of PCD output lines and request companies to provide the profile of the number of schemes at each stage gate.
DPWW4 and DPW4: requests data at scheme level for enhanced engagement, large gated, and critical high-profile enhancement schemes.
DPWW5: requests data at scheme level for Growth at Sewage Treatment Works Schemes (excluding critical high-profile projects).
DPW5: requests data at scheme level for Water resilience schemes (excluding critical high-profile projects).
Quality assurance:
This model has been subject to Ofwat internal quality assurance.
Disclaimer:
This model is part of our final determinations setting out the price, service, and incentive package for water companies for the period 2025-30. It should be read together with the other documents and information that we have published as part of our consultation.

## Industry_Change logs
May template changes - applied to all companies
Sheet | PCD ref | Line description | PCD Output Description | Changes
DPB2 | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals expenditure | Use the PCD output profile from DBP1
DPB2 | PCDB1b | Mains renewals - asset health adjustment | Base asset health adjustment renewals expenditure | Use the PCD output profile from DBP1
DPB2 | PCDB1c | Mains renewals - enhancement leakage | Enhancement leakage renewals expenditure | Use the PCD output profile from DBP1
DPB2 | PCDB3a | Water network reinforcement | Water network reinforcement expenditure | Use the expenditure profile from F_Inputs_NRF
DPB2 | PCDB3b | Wastewater network reinforcement | Wastewater network reinforcement expenditure | Use the expenditure profile from F_Inputs_NRF
DPWW1 | PCDWW27 | Growth to Sewerage Treatment Works | Added Process Capacity in PE | Replaced with Nr
DPWW1 | PCDWW34 | Greenhouse gas reduction (net zero) | tCO2e | Replaced with tonnes
DPWW1, DPWW2, DPWW3 | PCDWW34 | Greenhouse gas reduction (net zero) | Number of hectares | Deleted and pasted to DPW1, DPW2 and DPW3 sheets.
DPWW1,DWW3 | PCDWW34 | Greenhouse gas reduction (net zero) | tCO2e | Combined tCO2e with the number of sites - one line of expenditure and one line for IM.
DPWW1,DWW3 | PCDWW34 | Greenhouse gas reduction (net zero) | Number of sites
DPWW2 | PCDWW6 | Storm Overflow - Screens | Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions | Replaced with Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions
DPW1 | PCDW12 | Metering | All | Rounded meter numbers where needed. Reported in 0 decimal points
DPW2 | PCDWW32 | W Resilience CC Uplift | Spend on scheme as a % of allowance | Use the enhancement aggregator cost file to generate an expenditure delivery profile for AMP8.
DPW2 | PCDW11b | Supply interconnectors | WAFU Benefit | Use the enhancement aggregator cost file to generate an expenditure delivery profile for AMP8.
DPW2 | PCDW16b | Resilience Interconnector | All | Use the enhancement aggregator cost file to generate an expenditure delivery profile for AMP8.
DPW2 | PCDW16c | Resilience | All | Use the enhancement aggregator cost file to generate an expenditure delivery profile for AMP8.
DPW2 | PCDW5 | Water framework directive obligations |  | Use the enhancement aggregator cost file to generate an expenditure delivery profile for AMP8.
DPW2 | PCDW12 | Metering | New installations | Updated the values of the non-delivery PCD payment column
DPW2 | PCDW12 | Metering | Household meter upgrades | Updated the values of the non-delivery PCD payment column
DPW2 | PCDW12 | Metering | Non household meter upgrades | Updated the values of the non-delivery PCD payment column
DPW2 | PCDW12 | Metering | Large bulk meters | Updated the values of the non-delivery PCD payment column
DPW2 | PCDW12 | Metering | Small bulk meters | Updated the values of the non-delivery PCD payment column
DPW2 | PCDW12 | Metering | All | Use the PCD output profile from DPW1 sheet
DPWW4, DPW4 |  |  |  | Added drop-down list of primary reasons for delay
DPWW4, DPW4 |  |  |  | Added the word 'cumulative' on column headings AD and AE and baseline and forecast expenditure annual profiles column headings.
DPWW4, DPW4 |  |  |  | Added a new column 'High-profile scheme (Y/N)' and a drop-down list
DPWW4 |  |  |  | Added drop down list on the Type of scheme (enhanced engagement, large gated and delivery mechanism) column
DPW4 |  |  |  | Added drop down list on the Type of scheme (enhanced engagement, large gated, resilience) column
DPW3 |  |  |  | To avoid confusion we deleted the grey out areas. Format is now consistent with DPWW3. It includes the list of water PCDs for which we ask for an IM.
June template changes - applied to all companies
Sheet | PCD ref | Line description | PCD Output Description | Changes
DPW3 |  |  |  | We have added a pre-2025-26 column
DPW1 | PCDWW34 | Greenhouse gas reduction (net zero) | tCO2e | Added a new row
DPWW3, DPW3 |  |  |  | Updated the structure of template
DPWW4, DPW4 |  |  |  | Headings/dropw down list have been updated and columns have been added
DPWW5, DPW5 |  |  |  | New table has been updated
DPWW1, DPW1 |  |  |  | Update annual baseline output profile where we did not have a profile before
DPW2 | PCDW11a | Supply | WAFU Benefit | Update baseline expenditure profile
DPW2 | PCDW12 | Metering | Connected meters | Update Baseline PCD allowance for connected meters by multiplying the existing non-delivery payment rate of connected meters with an updated number of connected meters (sum of new installations, household and non-household meter upgrades, small and large bulk meters)
DPW1 | PCDW17b | Cyber | Legal instruments | Updated baseline output profile
DPW1 | PCDW17a | SEMD | Legal instruments | Updated baseline output profile
DPW2 | PCDW8 | Water WINEP/NEP Investigations | Water WINEP/NEP Investigations | Expanded the formula to include pre-AMP8 years
DPW2 | PCDW14, PCDW13 | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | Provide an expenditure profile for years where this has not been previously populated (ie. where cells were previously blank). Thus, we do not have any missing annual expenditure profile data.
DPW1 | PCDW14, PCDW13 | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | Where possible expand the number till end of AMP9 so that there is a AMP9 output target
July template changes - applied to all companies
Sheet | PCD ref | Line description | PCD Output Description | Changes
DPW2 | PCDW14, PCDW13 | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | Use the enhancement aggregator cost file to generate an expenditure delivery profile for AMP8.
DPB1,DPW(W)1 | All |  |  | Added Blue RAG rating

## TMS_Change log
TMS_Change log
Change summary
| Company | Sheet | PCD ref | Line description | PCD Output Description | Changes
| TMS | DPWW1 | PCDWW35 | PR19 WINEP Carryover actions | Number of schemes | Updated baseline output profile. 3 actions were incorrectly populated in 2024-25.
| TMS | DPW2 | PCDW17a | SEMD | Legal instruments | Removed large gated allowance
| TMS | DPW2 | n/a | Total PCD and non - total enhancement expenditure | n/a | Corrected calc to remove total supply benefit

## Industry_Query logs
Delivery Plan
|  |  | Company query | Ofwat response
Query number | Sheet | PCD ref
1 | DPWW1/DPWW2 | PCDWW2b Continuous river water quality monitoring | DPWW1 – the Ofwat assumed profile is logical, however, we believe the baseline plan needs to consider the initial trail period that will impact a consistent profile across the AMP, especially across year 1 and 2. DPWW2 – given the updated baseline plan, we have updated the baseline expenditure profile. This closely aligns with the assumptions Ofwat made but including some additional expenditure early on. | We follow a consistent approach across all companies to setting PCD output and expenditure delivery profiles. If you have a different view of the baseline profile please use the outturn/forecast tables to set out your view and explain the reasons for this as part of your commentary in your May submission. Based on this we will consider resetting the baseline output and expenditure profiles ahead of the July delivery plan submission. We will not consider resetting output profiles for areas where time incentives apply.
2 | DPWW1 | PCDWW3 MCERTs monitoring of emergency overflows at sewage pumping stations | DPWW1 – the Ofwat assumed profile is logical, however, we have a baseline plan agreed by the EA for all monitor types. This is to enable all monitors to be MCERT’d and then signed off by the EA. There is a recognition from the EA that due to other monitors being certified early in AMP8, this is an acceptable profile for UMON_6. The initial trail period that will impact a consistent profile across the AMP, especially in year 1.
3 | DPWW1 | PCDWW18 Wastewater Investigations | DPWW1 – the Ofwat assumed profile is logical, however, we believe the baseline plan needs to reflect the fact that all of the investigations just need to be completed by year 2. The majority require hydraulic and water quality modelling, which take significant time to complete. Although these are ongoing it is not realistic to complete a significant number in year, including agreement from the EA, when the full process is yet to be agreed.
4 | DPWW2 | PCDWW25b BIO WINEP Sludge Treatment – Other | DPWW2 – the Ofwat assumed expenditure profile is logical, however, given that the technology is relatively new for the industry, further feasibility and planning will need to take place, altering the baseline expenditure profile further towards the end of the AMP.
5 |  | PCDWW30 IED | DPWW2 - the Ofwat assumed expenditure profile is logical, however, given that the EA is yet to confirm the final requirements for compliance with the IED, our expenditure profile will be slower at the beginning of the AMP to deal with this uncertainty. This will alter the expenditure profile further towards the end of the AMP.
6 | DPW1, DPW2 |  | We ask for clarity as to whether the totals for AMP9 should include AMP8 data. The pre-populated tables are inconsistent on this point. For example, the outputs in table DPW1 for legal instruments (PCDW14, PCDW13) do not show a carry over into AMP9 but the financial tables do (DPW2). | Yes, the totals for AMP9 should include AMP8 delivery as we want reporting to be on a cumulative basis. The PCD output profile for water quality was pre-populated incorrectly, thus the confusion. We have corrected this error and agreed with your approach (second option).
7 | DPW1 & DPWW1 | PCDW8 & PCDWW18 WINEP Investigations | Ofwat pre-populated the annual delivery profile for WINEP investigations for wastewater but not for water. We would be grateful if Ofwat could confirm whether it expects companies to submit an annual profile for WINEP investigations, regardless of the profile published in the PCD model, or whether it expects companies to only include the profile as per the PCD model, which would only show the total number of investigations complete by 2029-30. | We do not have information on how to populate the annual delivery profile for WINEP investigations for water. We expect companies to include an annual profile for WINEP investigations. We therefore now include the following statement in the cover sheet of the updated delivery plan table template: For PCDs where we have not provided a baseline profile but reported only the target output or allowed total expenditure (totex) at year 5 of AMP8 or at year 5 of AMP9, we ask companies to provide profiled annual output and totex values in their deliver plans. These should be reported for both baseline and outturn & forecast tables. We also ask companies to provide the assumptions used to derive these profiles as part of their commentary in their delivery plan submission.
8 | DPB1, DPB2 | PCDB3a PCDB3b Network Reinforcement | Network Reinforcement For network reinforcement, we note that although the PCD is included in the expenditure tables (DPB2), there is no output included in the output tables (DPB1). We will add a delivery profile for these schemes in our draft submission in May. | As per the PCD appendix, there is no output related to network reinforcement expenditure in the output tables (DPB1). We monitor network reinforcement expenditure only in the expenditure table (DPB2). We provide a baseline expenditure profile based on business plan profile.
9 | DPB2, DPB2_ADD DPWW2 | PCDB1a (example) Mains Renewals (base) | Mains Renewals (base) In the pre-populated data tables we note that for some PCDs, Ofwat’s expenditure profile only shows the cumulative total for the end of an AMP, whereas for other PCDs the expenditure profile is based on an annual profile. We ask Ofwat to clarify its guidance on whether or not companies are expected to complete a planned delivery profile for investments lines where Ofwat have only provided a total AMP cumulative value. | We provide a baseline expenditure profile based on the PCD output profile. We expect companies to include an annual profile for network reinforcement. To clarify this we therefore included the following statement in the cover sheet of the updated DP table template: For PCDs where we have not provided a baseline profile but reported only the target output or allowed total expenditure (totex) at year 5 of AMP8 or at year 5 of AMP9, we ask companies to provide profiled annual output and totex values in their deliver plans. These should be reported in both baseline and outturn & forecast tables. We also ask companies to provide the assumptions used to derive these profiles in their delivery plans.
10 | DPWW1 | PCDWW25a Sludge Treatment (Thickening and dewatering) | Sludge Treatment (Thickening and Dewatering) We believe there is a mistake in the pre-populated tables for PCDWW25a (Sludge thickening and dewatering). The pre-populated table has a profile starting in 2025/26 where-as you our business plan delivery profile in BIO5 should be used which starts in 2026/27 (below). | You are correct. There is a formula error. We have now corrected this for all companies.
11 | DPW1 | PCDW12 Metering | Metering. The pre-populated profiles are broadly correct however, these appear to be created from an expenditure profile which creates some unintended consequences, eg, 13,273.5 new meters in 2025/26. We recommend the output profile should be based on the PCD model. | We use the PCD output profile from the published PCD model. We agree with your suggestion, so we have rounded the meter numbers for all companies. Please also note that in the updated delivery plan table template we changed the metering expenditure delivery profile. This is now based on the PCD output profile.
12 | DPW1 | PCDW12 Metering | For the Non delivery PCD payments, we have noted a misalignment between the pre-populated data (which matched the payments listed in the final determination metering model PR24CA32) and the latest version of the Water Supply and Demand Balance PCD model (published February 2025). | Your are correct. We will use the updated payment rates for the different metering categories using the updated PCD model. We have now corrected this error for all companies
13 |  | PCDW11b: Supply Interconnectors PCDW16c: Reservoir safety improvements PCDWW32: Water resilience climate change uplift | Use the enhancement costs aggregator model for the PCDs in column E. Although the delivery is in AMP9 expenditure incurs in AMP8 as well. For water resilience climate change uplift, the water resilience profile from the enhancement costs aggregator model has been used. | We will use the enhancement costs aggregator model to derive an AMP8 expenditure delivery profile for supply interconnectors, resilience and resilience interconnectors. We apply this approach to all companies.
14 |  | PCDWW34: Net Zero - GHG/Carbon PCDWW34: Peatlands | For the following 2 PCDs, the expenditure profile does not match the enhancement costs aggregator model, so we propose that it is updated. For PCDWW34: Net Zero - GHG/Carbon, DPWW2 presents expenditure for tCO2e and number of sites as separate lines (DPWW2.43 and DPWW2.44). While we recognise that Ofwat has applied a percentage split to calculate non-delivery payment rates, expenditure will not be incurred separately for tCO2e and number of sites, so we have presented this information as 1 line. | In the enhancement costs aggregator model the expenditure percentages were calculated using both wastewater and water expenditure. The total (water and wastewater) enhancement expenditure for net zero in the enhancement costs aggregator over the whole period matches with the one reported in the deliver plan (please see the allowed PCD totex in year 2029-30). However, based on your subsequent comments on peatland restoration expenditure we moved the PCDWW34 for peatland restoration to water tables because it is for water price control. We agree with your proposal to report one expenditure line for tCO2eq and number of sites. The interim milestone in DPWW3 has one line as well. The updated template reflects this change.
15 |  | Treatment of PCDWW34 Peatland Restoration DPWW3.18, DPWW2.45, DPWW1.58 | This component of PCDWW34 is for peatland restoration and forms part of the water price control. We have moved the lines DPWW3.18, DPWW2.45, DPWW1.58 from the wastewater table 1, 2 and 3 to the water equivalents. | Based on your subsequent comments on peatland restoration expenditure we moved the PCDWW34 for peatland restoration to water tables as it relates to the water price control.
16 |  | PCDWW4: Increase flow to full treatment PCDWW5: Storm Overflows PCDWW5b: WINEP Storm Overflows – Wetlands | For the following 3 PCDs, the total storm overflow expenditure profile has been used but the 3 PCDs have individual spend profiles. We propose that the individual business plan profiles are applied to each PCD to more closely reflect forecast expenditure as the total of these PCDs is over £1bn. | Companies have allocated components of storm overflows e.g. Flow to full treatment, storm overflows, screens, wetlands etc across all storm overflows lines. Therefore it is not possible to split these expenditure lines out from the CWW3 lines and derive an accurate expenditure profile. We consider that our approach to use the combined storm overflows enhancement expenditure for the different areas of storm overflows expenditure will allow us to draw a baseline for all companies on a consistent basis. We are not making further changes at this stage. Please provide your view of the expenditure profile in the outturn & forecast tables and provide commentary explaining difference to our proposed baseline. We will consider amending baseline for final delivery plan.
17 |  | PCDW12: Metering | The allowance is split between base and enhancement, but the expenditure profile applied is only for enhancement. We propose that the base cost aggregator profile is applied for the base expenditure portion. | In the updated template we use the PCD output profile to derive expenditure profile for different metering categories.
18 | DPWW2/DPW2 |  | We have identified a potential issue with the total enhancement expenditure calculations in tabs ‘DPW2’ and ‘DPWW2’. In tab ‘DPW2’, the metering PCD (PCDW12) is comprised of both base and enhancement expenditure therefore when non-PCD enhancement is added in DPW2.43, the total in DPW2.44 will exceed the water enhancement allowance due to the inclusion of the base component of the metering PCD. This issue also applies to tab ‘DPWW2’ where the enhancement component of the sewer mains renewals PCD (PCDB2) is not included in DPWW2 therefore when non-PCD enhancement is added in DPWW2.46, the total in DPWW2.47 will be less than the wastewater enhancement allowance due to the exclusion of the enhancement component of the sewer mains renewals PCD. | We understand this issue and expect the companies to inform us for any variance between PCD and non PCD expenditure in their delivery plan. We will consider adding a reconciliation line in the table for companies to provide this variance. We will update our guidance document to clarify this.
19 |  | DPWW1.27 Volume of Sludge Storage delivered | We note you have used the delivery profile from BIO5 however the table currently shows our year 2 target in year 1, bringing our whole programme forward a year. | We have corrected this error for all companies.
20 | F_Inputs_BIO5 | DPWW1.28 Sludge Storage (Cake pads) | For cake pads, that seems to be an error as F_Inputs_BIO5 has the value in 26/27 but the DPWW1 calcs it in 25/26. This also does not match the PCD which has the deliverable only in 29/30 | We have corrected this error for all companies.
21 | DPWW2 | DPWW2.43, 44 Net zero | While the monetary value included in the PCD for our wastewater net zero enhancement schemes is per our cost table CWW22. This has now been split into sites and carbon benefit delivered. Costs will be incurred as indicated however the carbon benefits will lag the investment and accrue across the AMP. There will be no carbon benefit in AMP8 year 1 as an example of how this cost allocation would not be applicable in practice. We understand the split of funding based on site delivery at 75% and carbon benefit at 25%, but not how this can be evidenced for the latter to the timeframes indicated. The carbon benefit will not be fully resolved until the end of the AMP. As the schemes cannot be delivered without the funding allowed, we propose that monies are allocated each year as set in CWW22 and final adjustment be applied at the end of year 5 based on the outturn performance (the cumulative benefit in AMP). That performance to be tracked separately against a defined baseline (which would be set early in AMP8 year 2 following the required 12 months monitoring period). If Ofwat wanted greater granularity for this area, we'd propose splitting expenditure between CH4 and N2O schemes rather than between sites and carbon benefit. | We use the enhancement aggregator cost model to derive the PCD allowed totex delivery profile for net zero. The PCD allowed totex in year 2029-30 matches with the one in the enhancement aggregator cost model (please see the total value over the whole period). We agree with your proposal on reporting one expenditure line for tCO2eq and number of sites. The interim miletone table in DPWW3 has one line as well. The updated template reflects this change. We also moved the PCD related to peatland restoration to water as it is for water price control.
22 | DPWW2 | DPWW2.42 PR19 WINEP Carryover | Ofwat assume flat profile (£36m/5 per year). We have last delivery date of 31/3/2027, so would not expect expenditure beyond yr2. | Companies have different delivery dates for PR19 WINEP Carryover schemes across AMP8. For consistency purposes, we assumed a flat profile for all companies across the whole AMP8 as stated in the PR24 FD past delivery and PR24 FD PCD documents. This is the reason why the enhancement aggregator cost file has a flat profile for all companies across all years of AMP8. Please provide your view of the baseline expenditure profile in the outturn & forecast tables. We will consider whether to reset the baseline profile after draft delivery plan submissions.
23 |  | PCDW12 | Update non-delivery PCD rates for New installations, Household meter upgrades, Non-household meter upgrades. For simplicity, we suggest that meter unit rates x output volumes should be used to set annual totex values in the delivery plan. | We have corrected the non-delivery payments for all companies using the updated PCD model. Also, we will use the PCD output profile to derive the delivery profile for metering expenditure.
24 |  |  | For PCDs where Ofwat has reported the total totex in year 5, please could you confirm would you like us to provide profiled annual totex values in our May submission. | For PCDs where we have not provided a baseline profile but reported only the target output or allowed total expenditure (totex) at year 5 of AMP8 or at year 5 of AMP9, we ask companies to provide profiled annual output and totex values in their deliver plans. These should be reported in both baseline and outturn & forecast tables. We also ask companies to provide the assumptions used to derive these profiles in their delivery plans.
|  |  | Company query | Ofwat response
Query number | Sheet | PCD ref
25 |  | PCDW12 Metering | IM for metering: •metering doesn’t meet the criteria that Ofwat has set for the purpose of IM reporting to monitor progress for back-ended delivery profiles, • the PCD has a yearly delivery profile and the current reporting requirement for DPW1 & 2 is sufficiently detailed to capture progress and hold companies to account. | There is no interim milestone reporting for this PCD as indicated by N/A in the table of section 4.3 of our delivery plan guidance. This line in table DPW3 should therefore not be populated. Please also note that the updated DP template removes this line from the DPW3 table.
26 |  | PCDW8 Water WINEP Investigations | The level of detailed required for DPW1 & 2 is sufficient to capture the details required for progress against this PCD and the additional requirements for DPW3 will not add value or confidence in delivery to customers.
27 |  | PCDW15 Lead | The lead PCD has a consistent delivery profile that spans over the AMP and the current reporting requirement for DPW1 & 2 is significant and detailed enough to capture its progress and hold companies to the correct level of accountability. Its inclusion in DPW3 seems over burdensome and does not give any additional benefits to the customers.
28 |  |  | IM Completion: It is not clear from the delivery plan guidance when a company achieves the PCD output in period, whether it then has to continue reporting on the PCD in the following updates. In the PR24 delivery plan workshop, it was mentioned that the level of reporting could be reduced over the AMP if companies remain on track and that the marginal reporting benefit does not increase towards the end of the AMP. We suggest that Ofwat updates its delivery plan guidance to provide further information on the process for completing PCDs in period and provide an incentive for companies in the form of potentially relaxed requirements given the successful delivery of PCDs in line with the baseline plan. | Where companies complete a PCD we do not expect them to update reporting for this PCD in subsequent progress reports. Companies however should keep the values for these PCDs in subsequent delivery plan progress reports to enable us to compare against other companies on a consistent basis.
29 |  |  | We encourage Ofwat to consider annual milestone rather than quarterly dates for tables DPW3 and DPWW3. Our July Delivery Plan baseline submission will include some indicative milestones generated backwards from our deliverable dates in our PR24 Final Determination. These will be produced at project level and is intended to provide an indicative view of the programme as a whole. However, we are concerned that showing information to customers at quarterly resolution provides a false sense of accuracy at this early stage. | Companies have to deliver a significant step up in investment compared to PR19. Given the deliverability challenges that companies are likely to face we are enhancing the transparency of what companies will deliver and increase the frequency at which we collect delivery data. This will allow us, stakeholders and other regulators to have early sight of any delivery issues and consider taking action in a timely manner. The quarterly interim milestones will allow us to identify slippage that is greater than 3 months but smaller than a year. We will consider whether to move to six monthly or annual milestones for later years of the AMP as part of our annual delivery reviews.
30 |  | PCDWW32 | Interim milestones for PCDWW32 are missing from DPWW3 but the water equivalent is included in DPW3. | We do not track progress for wastewater climate change uplift using intnerim milestones.
31 |  | Delayed schemes: reason categories | Would Ofwat support the addition of a commentary field within each of the DPW3 and DPWW3 tables? This would provide the opportunity for companies to provide further clarity. For example, a reason category ‘Change in solution (IM2)’, would often be due to one of the other categories, e.g. ‘Land and planning permission’, or ‘Programme level efficiency’. Similarly, ‘Programme level efficiency’ may be chosen where a scheme is combined with another driver to minimise costs overall to customers; the additional commentary field could be used to provide context for such changes. | We consider that companies can provide comments for the reasons delayed in their commentary within the delivery plan as set out in our delivery plan guidance document. We will consider adding a commentary column within each of DPW3 and DPWW3 tables after the submission of draft delivery plans.
32 |  | Wastewater investigations | How do the interim milestones map out when considering schemes that deliver investigations? The IM definitions look to map out to asset delivery processes. We welcome some further guidance for Interim milestones relating to investigation schemes. | We are not requiring companies to report interim milestones for wastewater investigations - please see Table DPWW3: Wastewater Enhancement PCD interim milestones in our guidance document.
33 |  |  | For interim milestones and cost profiles do Ofwat require this to be cumulative or a count of in quarter / year deliverables? | For interim milestones we expect a count of schemes require this reporting to be on a cumulative basis. Thus, by year 5 we expect to see 100% of the schemes at IM6. Our delivery plan guidance (p.13) states that the number of schemes at each stage should include both outturn and forecasts. Companies should provide the outturn number of schemes at each scheme for the quarters within the reporting year and previous years. In our guidance document we provide tables with worked examples (please see pp.15-16).
|  |  | Company query | Ofwat response
Query number | Sheet | PCD ref
34 |  |  | The company wants Ofwat to provide definition/guidance on what we mean by schemes “which are of particular interest for relevant stakeholders”. | We are asking companies to set out the list of schemes that you consider as high profile for your stakeholders. We have now included a column in tables DPW4 and DPWW4 so that companies can identify if the scheme is a high-profile scheme or not. Please provide commentary on the reasons why you consider these schemes as high-profile. If required, we may consider providing further guidance on the criteria for identifying high profile schemes for final delivery plans. Please also note that in tables DPW4 and DPWW4 the 'type of scheme' column has an updated drop down list; enhanced engagement, large gated and delivery mechanism schemes.
35 |  |  | It is currently unclear how "spend to date" (column AD) and "forecast expenditure" (column AE) should be populated at each half-yearly progress report. We would welcome clarification of whether expenditure in column AD should be spend to the end of the previous full year, spend to date including the first half of the current year, or total spend including 6 months forecast for the second half of the current year to align to DPW(W)2. We would also welcome clarification in relation to column AE. It is unclear from the guidance and table labelling whether baseline and forecast expenditure profiles at scheme level are cumulative or not. We assume they are for consistency with DPW(W)2. We would welcome clarification of this in the guidance document and column heading in the tables. It is unclear how we should populate scheme level tables DPW(W)4 where there is an approved scheme substitution before the first agreed re-baselining date of 01/04/27 (reference guidance section 2.3, P13). In such a case, we propose to add the scheme to DPW(W)4 and complete the forecast columns but leave the baseline columns blank. One additional scheme would be reported in DPW(W)3 and the scheme being substituted would be reported against stage 7 (in DPW(W)3) and IM7 (in DPW(W)4). Column S of DPW4 asks for 'Current interim milestone' whereas column S of DPWW4 asks for 'Current stage'. We assume these should be consistent and would welcome clarification. | Spend to date (column AD) should be populated at each half-yearly progress report by including the spend from the previous years of the price control period and spend to date in the first half of the current year. Forecast expenditure to complete the scheme (column AE) should include the total outstanding forecast expenditure to complete scheme. This shoudl exclude the expenditure reported in column AD, ie spend to date. The sum of AE and AD should provide the total scheme expenditure. The spend in columns AD and AE should be reported on a cumulative basis. The baseline and forecast expenditure profiles at scheme level should be reported on cumulative basis as suggested in the column headings. We will also clarify this in our guidance document. We agree with your proposal on how to report a substitution scheme in the DPW(W)3 and DPW(W)4 sheets. Column S in DPWW4 is now renamed 'Current interim Milestone' to be consistent with DPW4.
36 |  |  | Does Ofwat require companies to report Wastewater resilience schemes in a similar way, perhaps in DPWW4? | Companies are not required to report wastewater resilience schemes in DPWW4.
37 |  |  | To support comparison of company plans and ensure full compliance with the reporting requirement, will Ofwat provide a definition of ‘High-profile’ schemes? | We asking companies to set out the list of schemes that you consider as high profile for your stakeholders. We have now included a column in tables DPW4 and DPWW4 so that companies can identify if the scheme is a high-profile scheme or not. Please provide commentary on the reasons why you consider these schemes as high-profile. If required, we may consider providing further guidance on the criteria for identifying high profile schemes for final delivery plans. Please also note that in tables DPW4 and DPWW4 the 'type of scheme' column has an updated drop down list; enhanced engagement, large gated and delivery mechanism schemes in table DPWW4 and nhanced engagement, large gated and resilience schemes in table DPW4
|  |  | Company query | Ofwat response
Query number | Sheet | PCD ref
38 | DPWW2 | PCDWW5b & PCDWW6 Storm Overflows Scheme level & Screen Only | Storm Overflows Scheme Level & Screen Only It appears the line description and output description have been interchanged, i.e. screen - to - number and wetland – to – wetland area. | We have corrected this error.
39 | HDD_DPB1_ADD & HDD_DPB2_ADD | PCDB5 Supply Interruptions CAC, PCDB6 Reservoir Maintenance | Errors in line descriptions | We have corrected this error.
40 |  | PCDW14 Metering | Error in decimal point | We have corrected this error. We ask companies to report the number of meters in 0 decimal points.
41 | DPW3 |  | In table DPW3 (column MO), the ‘DP Reference’ values state WW in the line references for this table, rather than W, as this table relates to water. | We have corrected this error.
42 |  | Metering PCD definition (Guidance section 4.1, P28) | The line definition for DPW1.19 Meter replacements is meters replaced on a 'like-for-like' basis. Our Business Plan is predicated on us replacing basic meters with an AMR meter upgrade i.e. all replacements are upgrades. The PCD has been populated from PR24 Business Plan table CW7 which defines CW7.9/10 as "renewals" which include like for like and replacement of an existing meter with a different type of meter; CW7.11/13 as "replacement of basic meter with smart meter". The current definition of DPW1.19 would give rise to zero replacements. We request that the definition be corrected. | Given that meter upgrades are funded partly through enhancement allowances and base allowances we expect you to report upgrades to AMR against lines DPW1.15, DPW1.16 and DPW1.19. If all of your meter replacements are upgrades to AMR then we would expect the sum of upgrades reported against lines DPW1.15 and DPW.16 to match those reported against DPW1.19.
43 |  | Greenhouse gas reduction (net zero) tCO2e(DPWW1.56) | For PCDWW34 greenhouse gas reduction, the unit value is shown as (000s) it should be (Nr or Tonnes). | We have corrected this error.
44 |  | Table DPB2 – ‘PCD Output Description’ (column F) | For lines DPB2.1 to DPB2.3, ‘in kilometres’ should be replaced with ‘expenditure’. | We have corrected this error.
45 |  | Table DPW4 (cells AR5:AV5) | This section is labelled ‘Baseline expenditure profile (£m)’ instead of ‘Forecast expenditure profile (£m)’. | We have corrected this error.
46 |  | DPWW2, PCDWW6 – Storm Overflow – Screens | Tab DPWW2, PCDWW6 – Storm Overflow – Screens: We believe that the PCD Output Description in cell G17, 'Wetland area delivered', should read 'Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions'. Question – We request Ofwat to review the description above with a view to correcting if appropriate. | We have corrected this error.
47 | DPWW1 | Growth to Sewerage Treatment Works | Believe there to be a decimal point missing in 9807 figure. Units are 000's. | We have corrected this error by replacing 000s with Nr
48 | DPWW1 | DPWW1.56 Greenhouse gas reduction (net zero) | Unit changes between tables Calc_Net Zero & DPWW1 - Figures are shown in wrong units (tCO2e) but needs to be in 000's. Values need to be divided by 1000 to be correct | We changed the unit of measurement from 000s to tonnes.
49 | DPWW1 | DPW1.10 Continuous river water quality monitoring (CWQM) | Numbers look right but PCD was just a yr5 figure with requirement we start in yr1. Should this then be in there? It should be in our forecast line | We mapped the PCD output profile based on CWW_20. We consider our approach is appropriate. Note that this does not change our approach to how PCDs work - we will continue to apply PCD claw-back only if output target is not delivered by the end of 2029-30.
50 | DPWW2 | DPW1.10 Continuous river water quality monitoring (CWQM) | Numbers look right but PCD was just a yr5 figure with requirement we start in yr1. Should this then be in there? It should be in our forecast line | We mapped the PCD allowed totex delivery profile based on the enhancement aggregator cost file. We consider our approach is appropriate. Note that this does not change our approach to how PCDs work - we will continue to apply PCD claw-back only if output target is not delivered by the end of 2029-30.
51 | DPWW1 | CPWW1.23 WINEP Investigations (wastewater) | Numbers do not match source and showing incorrect profile | We checked the updated PCD model and our numbers in the Delivery Plan are correct.
52 | DPW2 | DPW2.21-25 Water Supply and Demand Balance - WAFU Benefit | The costs do not match the allowance in the FD and the timing is not correct. | We checked the updated PCD model and the number is unchanged. We used the PCD related FD allowance. This may not match the total allowance set in final determinations for this enhancement line due to large gated schemes not having a PCD.
53 | DPB1 | DPB2.3-4 Network reinforcement - Wastewater | We notice that network reinforcement is include in DPB2 for PCDB3a and 3b but not included in DPB1 for the base PCD outputs. We belive this to be an error and would assume that it should be present in DPB1. | There is no PCD output for network reinforcement. Please see Base PCD excel file and PR24 FD appendix.
54 | All lines |  | Decimal places shown are not consistent with stated tolerance | We address dps issues where needed.
55 | All lines |  | Suggest showing column J on DPW2 in £000s rather than £m as units are too small to be accurately represented in £m | We consider it is appropriate to retain the current format so that we can compare across companies on a consistent basis.
56 |  | PDCW15 | The Final Determination made an allowance for atypical costs associated with Schools and Nurseries (see page 168 of PR24 final determinations: Expenditure allowances - Enhancement cost modelling appendix). But the Delivery Plan table refers only to “Schools”. Can this be amended to avoid “Schools and Nurseries” to reflect the FD and avoid any subsequent confusion. | Yes, we will amend the definition of this PCD output in the guidance document.
57 | DPW1/DPW2/DPW3 |  | All include PCDWW32 which is a Wastewater PCD and appears to have an incorrect line description. It is included in tables DPWW1/DPWW2 with what looks like the right line description | PCDWW32 is the PCD for climate change uplift. We use the same PCD reference for both water and wastewater related climate change uplift outputs and expenditure.
58 | DPWW1/DPWW2/DPWW3 |  | PCDWW5b inconsistent output descriptions used across the different tables | DPWW2 tracks the expenditure, whereas DPWW3 tracks the number of schemes. DPWW1 has the number of schemes and wetland area delivered.
59 | DPWW1/DPWW2 |  | PCDWW6 inconsistent output descriptions used across the different tables | We have now corrected this error.
60 | DPWW2/DPWW3 |  | PCDWW9 appears to have the wrong output description because it is a copy of the line description. In table DPWW1 there are 2x outputs against PCDWW9 so should these tables also list 2x outputs against this PCD? | DPWW2 includes total overall expenditure against PCDWW9. We do not split expenditure allowance between number of schemes and PE because the same expenditure is used to deliver both output types. DPWW3 tracks the number of schemes for all PCD areas.
61 | DPWW1/DPWW2 |  | there are PCDs missing from DPWW2 that are in DPWW1 e.g. PCDWW5. There are fewer rows in DPWW2 than DPWW1. | Please see delivery plan guidance document where we set out reason for this. In DPWW2 there are fewer lines because for some PCDs we do not split expenditure by output type where the split is artificial.
62 | DPW1/DPW2 |  | there are inconsistent PCD refs and output descriptions e.g. DPW1 PCDW12=Large bulk meters but DPW2 PCDW12= Non household meter upgrades - looks like some incorrect copying down on the metering PCDs | We have now corrected this error for all companies.
63 |  |  | The assurers and company's own RAG's are filled in. Do they need to be at this stage given this is baseline? Have the inputs been assured? | The RAG rating is for the companies to fill in. It is not related to the pre-populated data.The RAG from the assurer is only required for the July submissions. We expect companies to fill in and update their own RAG rating in each submission.
|  |  | Company query | Ofwat response
Query number | Sheet | PCD ref
64 |  |  | Timing and alignment with Annual Performance Reports (APRs): We do not support the need for draft reports in May ahead of the final report in July each year. This is not something that is done for company APRs and therefore it does not seem necessary here. Ofwat have not provided information on what the May submission will be used for or the benefits that a draft submission brings. Therefore, we recommend that the May requirement is removed or made optional.Remove May submission. | Companies have to deliver a significant step up in investment compared to PR19. Given the deliverability challenges that companies are likely to face we are enhancing the transparency of what companies will deliver and increase the frequency at which we collect delivery data. This will allow us, stakeholders and other regulators to have early sight of any delivery issues and consider taking action in a timely manner. We will consider less frequent reporting for later years of the AMP for companies showing good progress against PCD targets as part of our annual delivery reviews.
65 |  | RAG ratings | ‘Amber’ and ‘Red’ categories both refer to ‘meet requirements by 30 June 2030’. We believe that a tolerance of 90 working days should be applied; this would ensure that a delay of, in extremis, a single day, which forces delivery into the next quarter, does not precipitate the application of a non-delivery penalty. Question - We request Ofwat to clarify the definition with respect to the application of non-delivery penalties and request a 90 working days tolerance control limit be applied. | The RAG information will be used for monitoring purposes rather than for the application of PCDs. This is to identify the PCD areas that are at risk of not being met. We set out our approach to PCDs in section 4.7.2 of PR24 final determinations: expenditure allowances.
66 |  | RAG ratings | We note the guidance on RAG ratings. Question – We request Ofwat to confirm whether the timely delivery against the PCD time profile requirement as set out in PR24-final-determinations-Expenditure-allowances-1.pdf should continue to be provided in addition to the restated performance RAG rating for each PCD. | Yes, we confirm that the timely delivery against the PCD time profile requirement as set out in PR24-final-determinations-Expenditure-allowances-1.pdf (please see Table 1 at pages 20-21) should continue to be provided in addition to the restated performance RAG rating for each PCD. As stated above, the RAG information is for monitoring information purposes rather than for the application of PCDs.
67 |  | Commentaries | We would expect to provide commentaries. However, there would seem to be some overlap with APR commentaries and narratives. To minimise resource effort, we would propose to only include a single narrative on PCD outputs and expenditure, in particular. Question – We request Ofwat to confirm whether and how PCD commentaries will be integrated into the APR. | As stated in our delivery plan document, we want to understand the main risks that companies are facing in delivering their PR24 enhancement programme. As part of their delivery plan submission we expect companies to identify these risks and set out the actions they are undertaking, or planning to undertake, to mitigate those risks. As we go through the price control period companies are likely to make changes to their programmes. We expect companies to provide commentary within their delivery plan submission to explain these changes where they are material. We identify the material changes where we expect companies to provide additional commentary in section 2.5. As stated in our delivery plan guidance document, we will consider removing any unnecessary duplication in future APRs and update our guidance to reflect our latest view of definition of terms for similar output metrics. You can cross refer to your commentary in delivery plans in your APRs where appropriate.
68 |  | Commentaries | We would seek to also comment on where we may be ‘ahead’ of the baseline programme. External reporting on companies’ delivery progress should be balanced and recognise successes where evidenced, despite the focus on programme slippage, as per categories listed. Question – Will Ofwat recognise performance where favourable to baseline, in the same way as it will for performance adverse to baseline? | We welcome companies commenting where they may be 'ahead' of the baseline programme in the delivery plans. In our public facing anual delivery reports we will report on the progress that companies are making in delivering PR24 and will highlight both early delivery and late delivery. Companies can earn time incentive payments where they deliver outputs on time in areas where time incentives apply.
69 |  |  | We welcome the additional visibility of delivery which the delivery plan brings. However, we question the need for a May submission ahead of the final assured July submission, which in effect creates three submissions per annum rather than two. For the May submission we will need to use draft outturn figures, as these will not have been approved and assured as part of the APR process at this time. It is not clear why Ofwat requires a May submission and how it intends to use this. We suggest alignment with the annual return process, with one fully assured end of year submission. This will reduce the burden for both Ofwat and companies. | Companies have to deliver a significant step up in investment compared to PR19. Given the deliverability challenges that companies are likely to face we are enhancing the transparency of what companies will deliver and increase the frequency at which we collect delivery data. This will allow us, stakeholders and other regulators to have early sight of any delivery issues and consider taking action in a timely manner. We will consider less frequent reporting for later years of the AMP for companies showing good progress against PCD targets as part of our annual delivery reviews.
70 |  |  | We also ask Ofwat to reconsider the need for quarterly interim milestones. Given the delivery plan reports on half year and full year delivery, we think the use of half year milestones will provide sufficient level of visibility whilst simplifying the delivery plan tables. | Companies have to deliver a significant step up in investment compared to PR19. Given the deliverability challenges that companies are likely to face we are enhancing the transparency of what companies will deliver and increase the frequency at which we collect delivery data. This will allow us, stakeholders and other regulators to have early sight of any delivery issues and consider taking action in a timely manner. The quarterly interim milestones will allow us to identify slippage that is greater than 3 months but smaller than a year. We will consider whether to move to six monthly or annual milestones for later years of the AMP as part of our annual delivery reviews.

## F_Inputs_BIO5
F_Inputs_BIO5
|  | PCD_Delivery_BIO5 |  | Run on 08 Feb 2025 19:14 | [12 empty] | Delivery profile (no cumulative basis) | [6 empty] | Delivery profile (cumulative basis)
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | Line description | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Latest | Latest | Latest | Latest | Latest | Latest | Latest | Latest
TMS | BIO5_001_PR24 | Bioresources data - Tonnes of dry solids treated via main sludge treatment | ttds/yr | Price Review 2024 | [8 empty] | 0
TMS | BIO5_002_PR24 | Bioresources data - Tonnes of dry solids undertaking thickening/dewatering | ttds/yr | Price Review 2024 | [8 empty] | 0
TMS | BIO5_003_PR24 | Bioresources data - Additional sludge storage - tank volume (pre-thickening/pre-dewatering/untreated sludge) | m3 | Price Review 2024 | [8 empty] | 0
TMS | BIO5_004_PR24 | Bioresources data - Additional sludge storage - tank volume (thickened/dewatered/treated sludge) | m3 | Price Review 2024 | [8 empty] | 0
TMS | BIO5_005_PR24 | Bioresources data - Additional sludge storage - cake pads/bays area or equivalent (cake) | m2 | Price Review 2024 | [8 empty] | 0
TMS | BIO5_006_PR24 | Bioresources data - Total number of sludge treatment schemes providing sludge storage | nr | Price Review 2024 | [8 empty] | 0
TMS | BIO5_007_PR24 | Bioresources data - Total number of sludge treatment schemes providing sludge thickening and dewatering | nr | Price Review 2024 | [8 empty] | 0
TMS | BIO5_008_PR24 | Bioresources data - Total number of sludge treatment schemes providing main sludge treatment enhancement | nr | Price Review 2024 | [8 empty] | 0
TMS | BIO5_009_PR24 | Bioresources data - Volume of sludge processed via thickening or dewatering | m3 | Price Review 2024 | [8 empty] | 0
TMS | BIO5_010_PR24 | Bioresources data - Landbank availability | % | Price Review 2024 | [8 empty] | 0
TMS | BIO5_011_PR24 | Sludge management/sludge treatment/ Bioresources cost driver - Additional Line 1; Sludge management/sludge treatment/ Bioresources cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | BIO5_012_PR24 | Sludge management/sludge treatment/ Bioresources cost driver - Additional Line 2; Sludge management/sludge treatment/ Bioresources cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | BIO5_013_PR24 | Sludge management/sludge treatment/ Bioresources cost driver - Additional Line 3; Sludge management/sludge treatment/ Bioresources cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | BIO5_014_PR24 | Sludge management/sludge treatment/ Bioresources cost driver - Additional Line 4; Sludge management/sludge treatment/ Bioresources cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | BIO5_015_PR24 | Sludge management/sludge treatment/ Bioresources cost driver - Additional Line 5; Sludge management/sludge treatment/ Bioresources cost driver | define | Price Review 2024 | [8 empty] | 0

## F_Inputs_CWW20
F_Inputs_CWW20
|  | PCD_Delivery_CWW20 |  | Run on 08 Feb 2025 18:57 |  |  |  | id | 29824 | [7 empty] | Delivery profile (no cumulative basis) | [6 empty] | Delivery profile (cumulative basis)
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | Line description | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Latest | Latest | Latest | Latest | Latest | Latest | Latest | Latest
TMS | BN1603_PR24 | Sewage treatment data - Current population equivalent served by STWs | 000s | Price Review 2024 | 15315.6881 | 15428.746 | 15703.1633 | 15862.1033 | 16007.7033 | 16139.9833 | 16266.3333 | 16369.7433 | 111777.7756
TMS | S4030_PR24 | Sewage treatment data - Current population equivalent served by STWs with tightened/new P permits | 000s | Price Review 2024 | 0 | 0 | 1928.0372 | 0.63339 | 108.0848 | 0 | 0 | 4335.4613 | 6372.2168
TMS | S4023_PR24 | Sewage treatment data - Current population equivalent served by STWs with tightened/new N permits | 000s | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | S4024_PR24 | Sewage treatment data - Current population equivalent served by STWs with tightened/new sanitary parameter permits | 000s | Price Review 2024 | 1.55 | 3.705 | 492.7286 | 96.4878 | 339.2075 | 0 | 0 | 60.4214 | 992.5502
TMS | S4025_PR24 | Sewage treatment data - Current population equivalent served by STWs with tightened/new microbiological standards | 000s | Price Review 2024 | 0 | 0 | 0 | 41.7563 | 0 | 0 | 0 | 0 | 41.7563
TMS | S4027_PR24 | Sewage treatment data - Population equivalent served by STWs with enhanced treatment capacity | 000s | Price Review 2024 | 0 | 62.247 | 129.485 | 14.706 | 239.396 | 491.592 | 14.864 | 112.424 | 1064.714
TMS | S4031_PR24 | Sewage treatment data - Current population equivalent served by STWs with tightened/new permits for chemicals / hazardous substances | 000s | Price Review 2024 | 661.1864 | 0 | 16.2648 | 0 | 6588.014 | 0 | 0 | 264.7884 | 6869.0672
TMS | CWW20_008_PR24 | Sewage treatment data - Current population equivalent served by septic tank replacement projects | 000s | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_009_PR24 | Sewage treatment data - Number of new wetland treatment solutions for tightened sanitary or nutrient (N or P) permits | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
TMS | CWW20_010_PR24 | Sewage treatment data - Total area of new wetlands for tightened sanitary or nutrient (N or P) permits | ha | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1704 | 0.1704
TMS | CWW20_011_PR24 | Sewage treatment data - Total number of septic tank replacement projects | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_012_PR24 | Sewage treatment data - Total number of STW outfall screens | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | S4032_PR24 | Sewage treatment data - Cumulative shortfall in FFT addressed by WINEP / NEP schemes to increase STW capacity | l/s | Price Review 2024 | 121 | 155.7 | 6.23 | 507.2 | 13 | 215.4 | 74 | 511 | 1482.53
TMS | CWW20_014_PR24 | Sewage treatment data - Additional storm tank capacity provided at STWs - grey infrastructure | m3 | Price Review 2024 | 816.4 | 349.4 | 2614.8 | 4489 | 849 | 27750.9 | 572 | 55891.0132 | 92516.1132
TMS | CWW20_015_PR24 | Sewage treatment data - Additional volume of effective storm storage at STWs - nature based/green solution | m3 | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 69193.81 | 69193.81
TMS | CWW20_016_PR24 | Sewage treatment data - Total number of STW sites where additional storage has been delivered | nr | Price Review 2024 | 4 | 4 | 8 | 4 | 2 | 7 | 2 | 67 | 94
TMS | CWW20_017_PR24 | Sewage treatment data - Number of STW sites where additional storage has been delivered with pumping | nr | Price Review 2024 | 4 | 0 | 8 | 3 | 2 | 7 | 3 | 67 | 90
TMS | CWW20_018_PR24 | Sewage treatment data - Number of STW sites benefitting from green infrastructure replacing the need for storm tank storage | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 54
TMS | CWW20_019_PR24 | Sewage treatment data - Total number of schemes with tightened / new P permits (met by biological treatment) | nr | Price Review 2024 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 7 | 11
TMS | CWW20_020_PR24 | Sewage treatment data - Total number of schemes with tightened / new P permits (met by chemical treatment) | nr | Price Review 2024 | 1 | 2 | 5 | 13 | 18 | 17 | 13 | 99 | 167
TMS | CWW20_021_PR24 | Sewage treatment data - Total number of schemes with tightened / new N permits (met by biological treatment) | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_022_PR24 | Sewage treatment data - Total number of schemes with tightened / new N permits (met by chemical treatment) | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_023_PR24 | Sewage treatment data - Total number of schemes with tightened/new sanitary parameter permits | nr | Price Review 2024 | 1 | 1 | 3 | 3 | 18 | 0 | 1 | 5 | 31
TMS | CWW20_024_PR24 | Sewage treatment data - Total number of schemes with tightened/new microbiological standards (UV, ozone etc) | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
TMS | CWW20_025_PR24 | Sewage treatment data - Total number of STWs with microbiological treatment - new and existing (UV, ozone etc) | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4
TMS | CWW20_026_PR24 | Sewage treatment data - Total number of schemes with tightened/new chemicals/hazardous substances permits | nr | Price Review 2024 | 11 | 1 | 1 | 0 | 1 | 22 | 0 | 73 | 98
TMS | CWW20_027_PR24 | Sewage treatment data - Total number of schemes with new chemical dosing installations | nr | Price Review 2024 | 0 | 3 | 5 | 15 | 20 | 16 | 14 | 96 | 169
TMS | CWW20_029_PR24 | Sewage treatment data - Total number of schemes with new tertiary solids removal | nr | Price Review 2024 | 0 | 5 | 3 | 11 | 13 | 15 | 12 | 101 | 160
TMS | CWW20_030_PR24 | Sewage treatment data - Volume to water treated through tertiary solids removal (m3/day) | m3/day | Price Review 2024 | 0 | 23880.64 | 24556.44 | 69203.92 | 235305.1525 | 212866.14 | 209416.24 | 2185787.9636 | 2961016.4962
TMS | CWW20_031_PR24 | Sewage treatment data - Total number of N-TAL trials | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3
TMS | CWW20_032_PR24 | Sewage treatment data - Number of STW flow monitors installed | nr | Price Review 2024 | 28 | 40 | 55 | 35 | 1 | 2 | 0 | 1 | 134
TMS | CWW20_033_PR24 | Sewage treatment data - Number of STW flow monitoring schemes requiring permit changes only | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2
TMS | CWW20_034_PR24 | Sewage treatment data - Number of STW flow monitoring schemes requiring simple meter installations | nr | Price Review 2024 | 12 | 25 | 37 | 35 | 0 | 2 | 0 | 1 | 100
TMS | CWW20_035_PR24 | Sewage treatment data - Number of STW flow monitoring schemes requiring complex civils installations | nr | Price Review 2024 | 16 | 15 | 18 | 0 | 1 | 0 | 0 | 0 | 34
TMS | CWW20_036_PR24 | Network / Storm overflow data - Additional volume of network storage at CSOs etc to reduce spill frequency - grey infrastructure | m3 | Price Review 2024 | 0 | 0 | 0 | 0 | 500 | 0 | 0 | 67529 | 68029
TMS | CWW20_037_PR24 | Network / Storm overflow data - Additional volume of effective network storage to reduce CSO spill frequency - nature based/green solution | m3 | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6 | 6
TMS | CWW20_038_PR24 | Network / Storm overflow data - Number of individual sites delivering additional network storage - grey infrastructure | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 40
TMS | CWW20_039_PR24 | Network / Storm overflow data - Number of individual sites delivering additional network storage - grey infrastructure - which include pumping | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 40 | 41
TMS | CWW20_041_PR24 | Network / Storm overflow data - Surface water separation drainage area removed | m2 | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 235200 | 235200
TMS | CWW20_042_PR24 | Network / Storm overflow data - Total number of surface water separation schemes to reduce storm overflows | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 53
TMS | CWW20_043_PR24 | Network / Storm overflow data - Sustainable drainage / attenuation schemes (green) area removed / attenuated | m2 | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 252447 | 252447
TMS | CWW20_044_PR24 | Network / Storm overflow data - Total number of sustainable drainage / attenuation schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 53 | 53
TMS | CWW20_045_PR24 | Network / Storm overflow data - Flow rate diverted to reduce storm overflow spills | l/s | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 466.606 | 466.606
TMS | CWW20_046_PR24 | Network / Storm overflow data - Total number of sewer flow management / control schemes to reduce storm overflow spills | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65 | 65
TMS | CWW20_047_PR24 | Network / Storm overflow data - Total storm overflow spill volume avoided | m3/year | Price Review 2024 | 13948.2453 | 40361.0059 | 2660888.8333 | 216139.9767 | 35092 | 526457.2423 | 12176.292 | 2449010.1623 | 5940125.5126
TMS | CWW20_048_PR24 | Network / Storm overflow data - Total number of new storm overflow screens installed | nr | Price Review 2024 | 3 | 3 | 4 | 1 | 1 | 0 | 0 | 60 | 69
TMS | CWW20_049_PR24 | Network / Storm overflow data - Number of continuous water quality monitor installations | nr | Price Review 2024 | 0 | 0 | 0 | 63 | 63 | 63 | 63 | 62 | 314
TMS | CWW20_050_PR24 | Network / Storm overflow data - Number of new MCERTs event duration monitors installed at SPS emergency overflows | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74 | 74 | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
TMS | CWW20_051_PR24 | Network / Storm overflow data - Number of new MCERTs flow monitors (PFF) installed at SPSs with combined emergency and storm overflows. | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 232 | 0 | 0 | 65 | 297 | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils | 0% | 0% | 0% | 78.11% | 0% | 0% | 21.89% | 0% | 0% | 0% | 78.11% | 78.11% | 78.11% | 100%
TMS | CWW20_052_PR24 | Network / Storm overflow data - Number of event duration monitors installed (to include at STWs and in network) | nr | Price Review 2024 | 60 | 16 | 3 | 237 | 1 | 2 | 0 | 0 | 259
TMS | CWW20_053_PR24 | Network / Storm overflow data - Number of event duration monitoring schemes requiring permit changes only (at STWs and in network) | nr | Price Review 2024 | 0 | 0 | 0 | 237 | 0 | 0 | 0 | 0 | 237
TMS | CWW20_054_PR24 | Network / Storm overflow data - Number of event duration monitoring schemes requiring simple meter installations (at STWs and in network) | nr | Price Review 2024 | 54 | 14 | 3 | 0 | 0 | 2 | 0 | 0 | 19
TMS | CWW20_055_PR24 | Network / Storm overflow data - Number of event duration monitoring schemes requiring complex civils installations (at STWs and in network) | nr | Price Review 2024 | 6 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 3
TMS | CWW20_056_PR24 | Network / Storm overflow data - Total number of storm overflow discharge relocation schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_057_PR24 | Network / Storm overflow data - Total number of schemes to increase combined or trunk sewer capacity to reduce storm overflow spills | nr | Price Review 2024 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 4 | 5
TMS | CWW20_058_PR24 | Network / Storm overflow data - Total number of infiltration management schemes to reduce storm overflow spills | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 35 | 35
TMS | CWW20_059_PR24 | Network / Storm overflow data - Length of new rising main installed to reduce storm overflow spills (km) | km | Price Review 2024 | 0 | 1.41 | 0 | 0.035 | 0 | 0 | 0 | 0 | 1.445
TMS | CWW20_060_PR24 | Network / Storm overflow data - Total length of sewer installed to reduce storm overflow spills (km) | km | Price Review 2024 | 0 | 0.31 | 0 | 0.02 | 0 | 0 | 0 | 2.3 | 2.63
TMS | CWW20_061_PR24 | Other data - Number of WINEP/NEP investigations - desk-based studies only | nr | Price Review 2024 | 0 | 0 | 0 | 152 | 0 | 0 | 0 | 0 | 152
TMS | CWW20_062_PR24 | Other data - Number of WINEP/NEP investigations - survey, monitoring or simple modelling | nr | Price Review 2024 | 0 | 0 | 5 | 0 | 150 | 25 | 0 | 0 | 180
TMS | CWW20_063_PR24 | Other data - Number of WINEP/NEP investigations - multiple surveys and/or monitoring locations, and/or complex modelling | nr | Price Review 2024 | 8 | 0 | 0 | 2 | 2 | 128 | 0 | 0 | 132
TMS | CWW20_064_PR24 | Other data - Total number of WINEP/NEP investigations | nr | Price Review 2024 | 8 | 0 | 5 | 154 | 152 | 153 | 0 | 0 | 464 | Number of satisfactorily completed WINEP / NEP investigations - all categories | 0% | 1.078% | 33.19% | 32.76% | 32.97% | 0% | 0% | 0% | 1.078% | 34.27% | 67.03% | 100% | 100% | 100%
TMS | CWW20_065_PR24 | Other data - Total number of catchment management chemical source control schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_066_PR24 | Other data - Total number of catchment management nutrient balancing schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_067_PR24 | Other data - Total number of catchment management catchment permitting schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_068_PR24 | Other data - Total number of catchment management habitat restoration schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 2
TMS | CWW20_069_PR24 | Other data - Number of river connectivity schemes (fish passes etc) | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_070_PR24 | Other data - Number of marine conservation zones (new and existing) | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_071_PR24 | Other data - Total number of contribution to 3rd party WINEP/NEP schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1
TMS | CWW20_072_PR24 | Other data - Total number of 25 yr Environment Plan schemes | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | CWW20_073_PR24 | Other data - Additional line 1; wastewater network+ cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | CWW20_074_PR24 | Other data - Additional line 2; wastewater network+ cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | CWW20_075_PR24 | Other data - Additional line 3; wastewater network+ cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | CWW20_076_PR24 | Other data - Additional line 4; wastewater network+ cost driver | define | Price Review 2024 | [8 empty] | 0
TMS | CWW20_077_PR24 | Other data - Additional line 5; wastewater network+ cost driver | define | Price Review 2024 | [8 empty] | 0

## F_Inputs_WW_EXP
F_Inputs_WW_EXP |  | PR24CA14_Waste_Enh_out
Acronym | Reference | Item description | Unit | Model | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | Line description | Delivery profile (no cumulative basis) | [6 empty] | Delivery profile (cumulative basis)
[14 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
TMS | PR24CA14_WW_TOTAL_ENHANCEMENT_ALLOW_TOT | PR24 final wastewater enhancement totex allowance- total enhancement expenditure | £m | Price review 2024 | 0 | 0 | 431.5116 | 575.5733 | 735.1155 | 1106.0967 | 1752.592 | 4600.8891
TMS | PR24CA14_WW_EDM_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Event duration monitoring at intermittent discharges expenditure | £m | Price review 2024 | 0 | 0 | 1.6268 | 0 | 0 | 0 | 0 | 1.6268
TMS | PR24CA14_WW_FLOW_MONITORING_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Flow monitoring at sewage treatment works expenditure | £m | Price review 2024 | 0 | 0 | 14.0996 | 26.1634 | 0 | 0 | 0.86136 | 41.1243 | Flow monitoring at sewage treatment works; (WINEP/NEP) | 0% | 0% | 34.29% | 63.62% | 0% | 0% | 2.095% | 0% | 0% | 34.29% | 97.91% | 97.91% | 97.91% | 100%
TMS | PR24CA14_WW_CWQM_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Continuous river water quality monitoring expenditure | £m | Price review 2024 | 0 | 0 | 8.3145 | 8.2706 | 8.2198 | 8.1591 | 7.9779 | 40.9419 | Continuous river water quality monitoring (CWQM) | 0% | 0% | 20.31% | 20.2% | 20.08% | 19.93% | 19.49% | 0% | 0% | 20.31% | 40.51% | 60.59% | 80.51% | 100%
TMS | PR24CA14_WW_MCERTS_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - MCERTs monitoring at emergency sewage pumping station overflows expenditure | £m | Price review 2024 | 0 | 0 | 3.72 | 3.7169 | 0.92744 | 0.46263 | 0.46197 | 9.2889 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | 0% | 0% | 40.05% | 40.01% | 9.984% | 4.98% | 4.973% | 0% | 0% | 40.05% | 80.06% | 90.05% | 95.03% | 100%
TMS | PR24CA14_WW_FFT_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Increase flow to full treatment expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_CSO_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - combined storm overflow expenditure | £m | Price review 2024 | 0 | 0 | 25.7765 | 24.8417 | 98.1103 | 200.6767 | 369.2681 | 718.6733 | Storm overflows | 0% | 0% | 3.587% | 3.457% | 13.65% | 27.92% | 51.38% | 0% | 0% | 3.587% | 7.043% | 20.69% | 48.62% | 100%
TMS | PR24CA14_WW_CHEMICAL_REMOVAL_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Treatment for chemical removal expenditure | £m | Price review 2024 | 0 | 0 | 0.41649 | 0.27855 | 19.6843 | 48.652 | 121.171 | 190.2023 | Treatment for chemical removal (WINEP/NEP) | 0% | 0% | 0.219% | 0.1465% | 10.35% | 25.58% | 63.71% | 0% | 0% | 0.219% | 0.3654% | 10.71% | 36.29% | 100%
TMS | PR24CA14_WW_CHEMICAL_INV_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Chemicals and emerging contaminants monitoring, investigations, options appraisals expenditure | £m | Price review 2024 | 0 | 0 | 1.7352 | 2.5733 | 2.7288 | 0.082612 | 0.083046 | 7.203
TMS | PR24CA14_WW_N_REMOVAL_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Treatment for total nitrogen removal expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_NTAL_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Nitrogen technically achievable limit monitoring, investigation or options appraisal expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 15.0433 | 0.40062 | 0.39891 | 15.8429
TMS | PR24CA14_WW_P_REMOVAL_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Treatment for phosphorus removal expenditure | £m | Price review 2024 | 0 | 0 | 26.1686 | 38.0745 | 167.5887 | 362.8746 | 588.5094 | 1183.2158 | P-removal | 0% | 0% | 2.212% | 3.218% | 14.16% | 30.67% | 49.74% | 0% | 0% | 2.212% | 5.43% | 19.59% | 50.26% | 100%
TMS | PR24CA14_WW_NUT_SAN_DETS_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Treatment for nutrients (N or P) and / or sanitary determinands, nature based solution expenditure | £m | Price review 2024 | 0 | 0 | 0.1034 | 0.32984 | 0.66885 | 0.95606 | 0.042585 | 2.1007 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | 0% | 0% | 4.922% | 15.7% | 31.84% | 45.51% | 2.027% | 0% | 0% | 4.922% | 20.62% | 52.46% | 97.97% | 100%
TMS | PR24CA14_WW_SANITARY_PARAM_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Treatment for tightening of sanitary parameters expenditure | £m | Price review 2024 | 0 | 0 | 31.5783 | 29.9921 | 0.6218 | 0.69041 | 6.111 | 68.9935 | Treatment for tightening of sanitary parameters | 0% | 0% | 45.77% | 43.47% | 0.9012% | 1.001% | 8.857% | 0% | 0% | 45.77% | 89.24% | 90.14% | 91.14% | 100%
TMS | PR24CA14_WW_CHEM_SOURCE_CON_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Catchment management - chemicals source control expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_NUT_BALANCING_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Catchment management - nutrient balancing expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_CATCHMENT_PERMIT_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Catchment management - catchment permitting expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Catchment solutions - Catchment Permitting (WINEP/NEP) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_HABITAT_REST_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Catchment management - habitat restoration expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_MICRO_TREATMENT_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Microbiological treatment - bathing waters, coastal and inland expenditure | £m | Price review 2024 | 0 | 0 | 1.864 | 1.862 | 1.9054 | 1.9467 | 1.9439 | 9.5219 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | 0% | 0% | 19.58% | 19.55% | 20.01% | 20.44% | 20.41% | 0% | 0% | 19.58% | 39.13% | 59.14% | 79.59% | 100%
TMS | PR24CA14_WW_SEPTIC_TANK_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Septic tank expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Septic tank replacements - treatment solution; (WINEP/NEP) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_FISH_SCREENS_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Fish outfall screens expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_25YR_EP_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - 25 year environment plan expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25 year environment plan; (WINEP/NEP) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_INVESTIGATIONS_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Investigations expenditure | £m | Price review 2024 | 0 | 0 | 17.1646 | 15.9329 | 6.2612 | 0.86799 | 0.13617 | 40.3628 | WINEP Investigations (wastewater) | 0% | 0% | 42.53% | 39.47% | 15.51% | 2.15% | 0.3374% | 0% | 0% | 42.53% | 82% | 97.51% | 99.66% | 100%
TMS | PR24CA14_WW_THIRD_PARTY_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Contribution to third party schemes under WINEP/NEP only (not covered elsewhere) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0.0017624 | 0.065604 | 0.093861 | 0.16123
TMS | PR24CA14_WW_RIVER_CONNECT_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - River connectivity (e.g. for fish passage) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_REST_MANAGEMENT_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Restoration management (marine conservation zones etc) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_ACCESS_AMENITY_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Access and amenity for WINEP/NEP only (not covered elsewhere) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_ADVANCED_WINEP_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Advanced WINEP (not covered elsewhere) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Advanced WINEP | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_SLUDGE_TANK_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Sludge storage -Tanks expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sludge storage -Tanks | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_SLUDGE_CAKE_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Sludge storage - Cake expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sludge storage (cake pads) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_SLUDGE_ANAEROBIC_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Sludge treatment - Anaerobic digestion and/or advanced anaerobic digestion expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_SLUDGE_THICKENING_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Sludge treatment - Thickening and/or dewatering expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sludge thickening and dewatering | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_SLUDGE_OTHER_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Sludge treatment -Other expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Sludge treatment (Other) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_SLUDGE_INV_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - WINEP/NEP - Sludge investigations and monitoring (NEP only) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_GROWTH_STW_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Growth at sewage treatment works (excluding sludge treatment) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 52.7731 | 123.8385 | 176.6116 | Growth to Sewerage Treatment Works | 0% | 0% | 0% | 0% | 0% | 29.88% | 70.12% | 0% | 0% | 0% | 0% | 0% | 29.88% | 100%
TMS | PR24CA14_WW_FIRSTTIME_SEWERAGE_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - First time sewerage expenditure | £m | Price review 2024 | 0 | 0 | 1.3951 | 1.2394 | 2.51 | 2.1343 | 2.245 | 9.5238 | Number of connected properties served by S101A schemes | 0% | 0% | 14.65% | 13.01% | 26.36% | 22.41% | 23.57% | 0% | 0% | 14.65% | 27.66% | 54.02% | 76.43% | 100%
TMS | PR24CA14_WW_ODOUR_NUISANCE_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Odour and other nuisance expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_RESILIENCE_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Resilience expenditure | £m | Price review 2024 | 0 | 0 | 1.2546 | 0.97073 | 4.8794 | 8.1595 | 15.939 | 31.2031 | Climate change uplift | 0% | 0% | 4.021% | 3.111% | 15.64% | 26.15% | 51.08% | 0% | 0% | 4.021% | 7.132% | 22.77% | 48.92% | 100%
TMS | PR24CA14_WW_SEMD_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Security - SEMD expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_WW_CYBER_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Security - cyber expenditure | £m | Price review 2024 | 0 | 0 | 15.597 | 13.071 | 12.345 | 13.5739 | 12.6642 | 67.2511
TMS | PR24CA14_WW_NET_ZERO_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Greenhouse gas reduction (net zero) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Greenhouse gas reduction (net zero) | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_WW_FREEFORM_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Freeform lines expenditure | £m | Price review 2024 | 0 | 0 | 138.773 | 183.6591 | 137.8438 | 128.1303 | 161.5939 | 750
TMS | PR24CA14_WW_IED_ALLOW_TOT | PR24 final wastewater enhancement totex allowances - Industrial Emissions Directive (IED) expenditure | £m | Price review 2024 | 0 | 0 | 18.5794 | 18.0479 | 44.2213 | 71.938 | 137.705 | 290.4916 | Bioresources - IED and Reg changes | 0% | 0% | 6.396% | 6.213% | 15.22% | 24.76% | 47.4% | 0% | 0% | 6.396% | 12.61% | 27.83% | 52.6% | 100%
TMS | PR24CA103_WW_WINEPCARRYOVER_ALLOW_TOT | PR24 final wastewater enhancement totex allowance- WINEP carryover expenditure | £m | Price review 2024 | 0 | 0 | 181.2061 | 181.2061 | 181.2061 | 181.2061 | 181.2061 | 906.0305 | PR19 WINEP Carryover actions | 0% | 0% | 20% | 20% | 20% | 20% | 20% | 0% | 0% | 20% | 40% | 60% | 80% | 100%
TMS | PR24CA103_WW_GRCARRYOVER_ALLOW_TOT | PR24 final wastewater enhanceme totex allowance - GR carryover expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | PR19 Green recovery carryover | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | C_PR24CA14_ENH_WW_ASSESSED | Total amount assessed - Wastewater - Totex | £m | Price review 2024 | [7 empty] | 0 | Storm Overflow - Wetland | 0% | 0% | 3.587% | 3.457% | 13.65% | 27.92% | 51.38% | 0% | 0% | 3.587% | 7.043% | 20.69% | 48.62% | 100%
TMS | PR24QA_PR24CA14_OUT1 | Date & Time for Model - PR24CA14 | Text | Price Review 2024 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | 0 | Storm Overflow - Screens | 0% | 0% | 3.587% | 3.457% | 13.65% | 27.92% | 51.38% | 0% | 0% | 3.587% | 7.043% | 20.69% | 48.62% | 100%
TMS | PR24QA_PR24CA14_OUT2 | Name of Model - PR24CA14 | Text | Price Review 2024 | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | 0 | Flow to Full Treatment | 0% | 0% | 3.587% | 3.457% | 13.65% | 27.92% | 51.38% | 0% | 0% | 3.587% | 7.043% | 20.69% | 48.62% | 100%
TMS | PR24QA_PR24CA14_OUT3 | F_Inputs time stamp - PR24CA14 | Text | Price Review 2024 | Run on 15 Nov 2024 11:32 | Run on 15 Nov 2024 11:32 | Run on 15 Nov 2024 11:32 | Run on 15 Nov 2024 11:32 | Run on 15 Nov 2024 11:32 | Run on 15 Nov 2024 11:32 | Run on 15 Nov 2024 11:32 | 0
TMS | PR24QA_PR24CA14_OUT4 | Model override switch for - PR24CA14 | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## F_Inputs_W_EXP
F_Inputs_W_EXP |  | PR24CA14_Water_Enh_out
Acronym | Reference | Item description | Unit | Model | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total |  |  |  | Delivery profile (no cumulative basis) |  |  |  |  | Delivery profile (cumulative basis)
Company | [12 empty] | Line description | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
TMS | PR24CA14_W_TOTAL_ENHANCEMENT_ALLOW_TOT | PR24 final water enhancement totex allowance- total enhancement expenditure | £m | Price review 2024 | 0 | 0 | 406.3022 | 462.3106 | 499.6301 | 500.8419 | 717.4422 | 2586.5271
TMS | PR24CA14_W_BIODIVERSITY_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - biodiversity and conservation expenditure | £m | Price review 2024 | 0 | 0 | 3.7419 | 3.737 | 3.7292 | 3.7179 | 3.7098 | 18.6358 | Biodiversity and Conservation hectares | 0% | 0% | 20.08% | 20.05% | 20.01% | 19.95% | 19.91% | 0% | 0% | 20.08% | 40.13% | 60.14% | 80.09% | 100%
TMS | PR24CA14_W_EELS_SCREENS_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - eels and fish screens expenditure | £m | Price review 2024 | 0 | 0 | 0.1128 | 0.53226 | 0.50731 | 0.50538 | 0 | 1.6578 | Biodiversity and Conservation kilometres | 0% | 0% | 20.08% | 20.05% | 20.01% | 19.95% | 19.91% | 0% | 0% | 20.08% | 40.13% | 60.14% | 80.09% | 100%
TMS | PR24CA14_W_EELS_PASSES_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - eels and fish passes expenditure | £m | Price review 2024 | 0 | 0 | 2.1341 | 2.3353 | 3.4907 | 3.302 | 1.9308 | 13.1929
TMS | PR24CA14_W_INNS_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - invasive non-native species expenditure | £m | Price review 2024 | 0 | 0 | 2.0191 | 2.0172 | 2.0137 | 2.0072 | 2.0031 | 10.0602
TMS | PR24CA14_W_DWPA_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - drinking water protected areas expenditure | £m | Price review 2024 | 0 | 0 | 2.218 | 2.2148 | 2.2106 | 2.2039 | 2.199 | 11.0464 | Drinking Water Protected Areas | 0% | 0% | 20.08% | 20.05% | 20.01% | 19.95% | 19.91% | 0% | 0% | 20.08% | 40.13% | 60.14% | 80.09% | 100%
TMS | PR24CA14_W_WFD_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - water framework directive expenditure | £m | Price review 2024 | 0 | 0 | 1.1098 | 2.6264 | 5.1112 | 8.9631 | 29.7207 | 47.5311 | Water Framework Directive interconnector | 0% | 0% | 2.335% | 5.526% | 10.75% | 18.86% | 62.53% | 0% | 0% | 2.335% | 7.861% | 18.61% | 37.47% | 100%
TMS | PR24CA14_W_DISCHARGE_MONITOR_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - trade effluent discharge flow monitoring expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_W_25YR_EP_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - 25 year environment plan expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_W_INVESTIGATIONS_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - investigations expenditure | £m | Price review 2024 | 0 | 0 | 5.5946 | 6.0152 | 1.9931 | 1.973 | 1.8643 | 17.4402 | Water WINEP/NEP Investigations | 0% | 0% | 32.08% | 34.49% | 11.43% | 11.31% | 10.69% | 0% | 0% | 32.08% | 66.57% | 78% | 89.31% | 100%
TMS | PR24CA14_W_WETLAND_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP/NEP - wetland creation expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_W_SUPPLY_ALLOW_TOT | PR24 final water enhancement totex allowance- Supply-demand balance - supply expenditure | £m | Price review 2024 | 0 | 0 | 17.1938 | 22.8752 | 30.9153 | 36.6363 | 76.9038 | 184.5245 | Supply | 0% | 0% | 9.318% | 12.4% | 16.75% | 19.85% | 41.68% | 0% | 0% | 9.318% | 21.71% | 38.47% | 58.32% | 100%
TMS | PR24CA14_W_SUPPLY_INTER_ALLOW_TOT | PR24 final water enhancement totex allowance- Supply-demand balance - supply interconnectors expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Supply interconnectors | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_W_LEAKAGE_ALLOW_TOT | PR24 final water enhancement totex allowance- Supply-demand balance - leakage expenditure | £m | Price review 2024 | 0 | 0 | 32.9489 | 32.1782 | 30.6545 | 30.5581 | 30.4903 | 156.8301
TMS | PR24CA14_W_DEMAND_ALLOW_TOT | PR24 final water enhancement totex allowance- Supply-demand balance - demand expenditure | £m | Price review 2024 | 0 | 0 | 11.1841 | 11.1712 | 11.1481 | 11.1133 | 11.0881 | 55.7048 | Efficiency
TMS | PR24CA14_W_SRO_ALLOW_TOT | PR24 final water enhancement totex allowance- Supply-demand balance - strategic resource options expenditure | £m | Price review 2024 | 0 | 0 | 44.2339 | 45.6303 | 50.0091 | 69.8581 | 250.2053 | 459.9367
TMS | PR24CA14_W_METERING_ALLOW_TOT | PR24 final water enhancement totex allowance- Metering - metering expenditure | £m | Price review 2024 | 0 | 0 | 57.4149 | 53.9054 | 54.1267 | 54.2575 | 54.4487 | 274.1532 | Metering | 0% | 0% | 20.94% | 19.66% | 19.74% | 19.79% | 19.86% | 0% | 0% | 20.94% | 40.61% | 60.35% | 80.14% | 100%
TMS | PR24CA14_W_TOC_ALLOW_TOT | PR24 final water enhancement totex allowance- water quality improvements - taste, odour and colour expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_W_RWD_ALLOW_TOT | PR24 final water enhancement totex allowance- water quality improvements - raw water deterioration expenditure | £m | Price review 2024 | 0 | 0 | 1.9777 | 2.8686 | 3.1746 | 1.8494 | 0.65352 | 10.5238 | Raw Water Deterioration and Taste, Odour and Colour | 0% | 0% | 18.79% | 27.26% | 30.17% | 17.57% | 6.21% | 0% | 0% | 18.79% | 46.05% | 76.22% | 93.79% | 100%
TMS | PR24CA14_W_LEAD_ALLOW_TOT | PR24 final water enhancement totex allowance- water quality improvements - lead expenditure | £m | Price review 2024 | 0 | 0 | 12.5238 | 19.5973 | 21.1564 | 20.9952 | 17.5295 | 91.8022 | Lead | 0% | 0% | 13.64% | 21.35% | 23.05% | 22.87% | 19.09% | 0% | 0% | 13.64% | 34.99% | 58.04% | 80.91% | 100%
TMS | PR24CA14_W_RESILIENCE_INTER_ALLOW_TOT | PR24 final water enhancement totex allowance- resilience interconnectors expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Resilience Interconnector | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
TMS | PR24CA14_W_RESILIENCE_ALLOW_TOT | PR24 final water enhancement totex allowance- resilience expenditure | £m | Price review 2024 | 0 | 0 | 57.941 | 105.787 | 103.76 | 107.2965 | 98.4542 | 473.2387 | Resilience | 0% | 0% | 12.24% | 22.35% | 21.93% | 22.67% | 20.8% | 0% | 0% | 12.24% | 34.6% | 56.52% | 79.2% | 100%
TMS | PR24CA14_W_SEMD_ALLOW_TOT | PR24 final water enhancement totex allowance- security SEMD expenditure | £m | Price review 2024 | 0 | 0 | 4.5006 | 6.4086 | 8.7095 | 15.6654 | 20.2963 | 55.5805 | SEMD | 0% | 0% | 8.097% | 11.53% | 15.67% | 28.19% | 36.52% | 0% | 0% | 8.097% | 19.63% | 35.3% | 63.48% | 100%
TMS | PR24CA14_W_CYBER_ALLOW_TOT | PR24 final water enhancement totex allowance- security cyber expenditure | £m | Price review 2024 | 0 | 0 | 10.3864 | 8.7064 | 8.2138 | 9.0301 | 8.4237 | 44.7604 | Cyber | 0% | 0% | 23.2% | 19.44% | 18.35% | 20.18% | 18.83% | 0% | 0% | 23.2% | 42.64% | 60.99% | 81.17% | 100%
TMS | PR24CA14_W_RESERVOIR_SAFETY_ALLOW_TOT | PR24 final water enhancement totex allowance- reservoir safety expenditure | £m | Price review 2024 | 0 | 0 | 1.6248 | 2.1303 | 2.6324 | 2.6238 | 1.1077 | 10.119
TMS | PR24CA14_W_NET_ZERO_ALLOW_TOT | PR24 final water enhancement totex allowance- Greenhouse gas reduction (net zero) expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PR24CA14_W_FREEFORM_ALLOW_TOT | PR24 final water enhancement totex allowance- freeform line expenditure | £m | Price review 2024 | 0 | 0 | 117.3243 | 111.456 | 135.9562 | 98.1679 | 86.2956 | 549.2
TMS | PR24CA103_W_WINEPCARRYOVER_ALLOW_TOT | PR24 final water enhancement totex allowance- WINEP carryover expenditure | £m | Price review 2024 | 0 | 0 | 20.1178 | 20.1178 | 20.1178 | 20.1178 | 20.1178 | 100.5889
TMS | PR24CA104_W_GRCARRYOVER_ALLOW_TOT | PR24 final water enhancement totex allowance- Green recovery carryover expenditure | £m | Price review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | C_PR24CA14_ENH_W_ASSESSED | Total amount assessed - Water - Totex | £m | Price review 2024 | [7 empty] | 0 | W Resilience CC Uplift | 0% | 0% | 12.24% | 22.35% | 21.93% | 22.67% | 20.8% | 0% | 0% | 12.24% | 34.6% | 56.52% | 79.2% | 100%
TMS | PR24QA_PR24CA14_OUT1 | Date & Time for Model - PR24CA14 | Text | Price Review 2024 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | […]10/02/2025 15:12:52 | 0 | Water Framework Directive actions | 0% | 0% | 2.335% | 5.526% | 10.75% | 18.86% | 62.53% | 0% | 0% | 2.335% | 7.861% | 18.61% | 37.47% | 100%
TMS | PR24QA_PR24CA14_OUT2 | Name of Model - PR24CA14 | Text | Price Review 2024 | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | PR24-FD-CA14-Enhancement-costs-aggregator-model-2.xlsx | 0
TMS | PR24QA_PR24CA14_OUT3 | F_Inputs time stamp - PR24CA14 | Text | Price Review 2024 | Run on 17 Nov 2024 17:43 | Run on 17 Nov 2024 17:43 | Run on 17 Nov 2024 17:43 | Run on 17 Nov 2024 17:43 | Run on 17 Nov 2024 17:43 | Run on 17 Nov 2024 17:43 | Run on 17 Nov 2024 17:43 | 0
TMS | PR24QA_PR24CA14_OUT4 | Model override switch for - PR24CA14 | nr | Price Review 2024 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## F_Inputs_NRF
F_Inputs_NRF | [5 empty] | id | 30265
|  | Network Reinforcement |  | Run on 17 Apr 2025 13:44
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total |  |  |  | Delivery profile (no cumulative basis) |  |  |  |  | Delivery profile (cumulative basis)
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024 | Price Review 2024
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data | Run 11 - PR24 FD Data |  | Line description | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
Company Acronym | Item Code | Item Description | Item Unit | Item Table Suite | Latest | Latest | Latest | Latest | Latest | Latest | Latest
TMS | B0201DSITDWNC | Infrastructure network reinforcement - Capex - Treated water distribution | £m | Price Review 2024 | 22.365 | 32.397 | 37.81 | 37.457 | 37.497 | 37.279 | 36.938 | 186.981
TMS | B0201DSITDWNO | Infrastructure network reinforcement - Opex - Treated water distribution | £m | Price Review 2024 | 0.081 | 0.039 | 0.127 | 0.131 | 0.132 | 0.138 | 0.144 | 0.672 | Water network reinforcement |  |  | 20.22% | 20.03% | 20.05% | 19.94% | 19.76% | 0% | 0% | 20.22% | 40.25% | 60.3% | 80.24% | 100%
TMS | B0200DSISWCWWC | Infrastructure network reinforcement - Capex - Combined | £m | Price Review 2024 | 23.079 | 33.998 | 24.972 | 24.869 | 24.78 | 24.697 | 24.615 | 123.933
TMS | B0200DSISWCWWO | Infrastructure network reinforcement - Opex - Combined | £m | Price Review 2024 | 0.07 | 0.064 | 0.074 | 0.075 | 0.074 | 0.079 | 0.08 | 0.382 | Wastewater network reinforcement |  |  | 20.15% | 20.07% | 19.99% | 19.93% | 19.86% | 0% | 0% | 20.15% | 40.21% | 60.21% | 80.14% | 100%

## PCD List
PCD List
| MODEL | PCD | ANH | SVE | TMS | SRN | WSX | SWB | NES | HDD | WSH | NWT | YKY | MODEL | PCD | Line description | PCD Output | ANH | SVE | TMS | SRN | WSX | SWB | NES | HDD | WSH | NWT | YKY | AFW | BRL | PRT | SSC | SEW | SES | MODEL | PCD | Line description | PCD Output | ANH | SVE | TMS | SRN | WSX | SWB | NES | HDD | WSH | NWT | YKY | AFW | BRL | PRT | SSC | SEW | SES
| PR24CA110 Wastewater flow and monitoring | PCDWW2a |  |  |  | Y | [7 empty] | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals in kilometres | bar: ANH to SES
|  | PCDWW2a | [12 empty] | PCDB1b | Mains renewals - asset health adjustment | Base asset health adjustment renewals in kilometres | bar: ANH; TMS to WSX; NES; WSH; YKY; SEW
|  | PCDWW2b | Y | Y |  |  | Y | Y | Y |  |  | Y | Y |  | PCDB1c | Mains renewals - enhancement leakage | Enhancement leakage renewals in kilometres | [17 empty] | PR24CA106 Water WINEP | PCDW1 | Biodiversity and Conservation | Hectares of environmental improvement | [9 empty] | Y |  |  |  |  | Y | bar: ANH to SVE; SRN; NES; NWT; BRL; SEW
|  | PCDWW3 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y |  | PCDB1d | Mains renewals - enhancement water quality | Enhancement water quality renewals in kilometres | [18 empty] | PCDW1 | Biodiversity and Conservation | Kilometres of environmental improvement | [14 empty] | Y | bar: BRL
| PR24CA115 Wastewater Other Storm Overflow | PCDWW5b |  |  | Y | Y | Y |  |  |  | Y |  |  |  | PCDB4 | Water softening | Water softening target | [18 empty] | PCDW4 | Drinking Water Protected Areas | No Deterioration and Implementation actions | [15 empty] | Y | bar: SES
|  | PCDWW6 | Y |  |  | Y |  | Y | [6 empty] | PCDB5 | Supply interruptions | Increased storage at Higher Berse DSR | [18 empty] | PCDW5 | Water Framework Directive interconnector | Length of WFD interconnector |  | Y | Y | [8 empty] | Y | bar: HDD
| PR24CA111 Wastewater Treatment | PCDWW7 |  | Y | Y | [9 empty] | PCDB5 | Supply interruptions | Trunk main | [18 empty] | PCDW5 | Water Framework Directive actions | Other WFD actions |  | Y | Y | [8 empty] | Y | bar: HDD
|  | PCDWW9 | Y |  |  | Y | Y | [7 empty] | PCDB4 | Water softening | Softening equipment at Kenley WTW​ | [18 empty] | PCDW8 | Water WINEP/NEP Investigations | Water WINEP/NEP Investigations | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | bar: SES
|  | PCDWW11 | [5 empty] | Y | [6 empty] | PCDB4 | Water softening | Other capex investment​ | [17 empty] | PR24CA108 Water quality | PCDW14, PCDW13 | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | Y | Y | Y | Y | Y | Y | Y |  | Y | Y | Y | Y | Y | Y | Y | Y | Y | bar: SES
|  | PCDWW13a | [6 empty] | Y | [5 empty] | PCDB3 | Water network reinforcement | Water network reinforcement | [18 empty] | PCDW15 | Lead communication | Lead communication pipes replaced/relined | Y |  | Y | Y | Y | Y | Y | Y |  | Y | Y |  | Y | Y | Y |  | Y | bar: ANH to AFW; PRT to SEW
|  | PCDWW14 | Y | [11 empty] | PCDB6 | Reservoir maintenance | Reservoir maintenance | [18 empty] | PCDW15 | Lead external non school | Lead external supply pipes replaced/relined - Non-schools | Y |  | Y | Y | Y | Y | Y | Y |  | Y | Y |  | Y | Y | Y |  | Y | bar: HDD
|  | PCDWW15 | [7 empty] | Y |  |  |  |  | PCDB2 | Sewer pumping mains | Base wholesale wastewater model funded renewals | [18 empty] | PCDW15 | Lead external school | Lead external supply pipes replaced/relined - Schools | Y |  | Y | Y | Y | Y | Y | Y |  | Y | Y |  | Y | Y | Y |  | Y | bar: WSH to NWT
|  | PCDWW17 | [6 empty] | Y | [5 empty] | PCDB2 | Sewer pumping mains | Pollution incidents schemes | [18 empty] | PCDW15 | Lead internal non school | Lead internal supply pipes replaced/relined - Non-schools | Y |  | Y | Y | Y | Y | Y | Y |  | Y | Y |  | Y | Y | Y |  | Y | bar: WSH
| PR24CA112 Wastewater Other WINEP | PCDWW18 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y |  | PCDB3 | Wastewater Network reinforcement | Wastewater network reinforcement | [18 empty] | PCDW15 | Lead internal school | Lead internal supply pipes replaced/relined - Schools | Y |  | Y | Y | Y | Y | Y | Y |  | Y | Y |  | Y | Y | Y |  | Y | bar: ANH to SWB; HDD; NWT to YKY
|  | PCDWW23a | Y | [11 empty] | PCDB7 | Flood management | Unit of area discounnted from the combined network | [17 empty] | PR24CA109 Water Resilience and Security | PCDWW32 | W Resilience CC Uplift | Spend on scheme as a % of allowance | Y | Y | Y | Y | Y |  | Y | Y | Y | Y | Y | Y |  | Y | Y |  | Y | bar: YKY
|  | PCDWW23b | [9 empty] | Y |  |  | PCDB7 | Flood management | Blue Green corridors | [17 empty] | PR24CA107 Water Supply and Demand Balance | PCDW12 | Metering new | New installations | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | bar: YKY
| PR24CA114 Wastewater Bioresources | PCDWW24a | [8 empty] | Y |  |  |  | PCDB7 | Flood management | Pumping stations | [18 empty] | PCDW12 | Metering household upgrades | Household meter upgrades | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | bar: YKY
|  | PCDWW24b | Y |  |  | Y | Y |  | Y |  |  |  | Y | [22 empty] | PCDW12 | Metering non household upgrades | Non household meter upgrades | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | PCDWW25a | [5 empty] | Y | [5 empty] | Total PCD outputs |  |  |  | 5 | 4 | 4 | 5 | 4 | 3 | 4 | 6 | 5 | 5 | 7 | 2 | 3 | 2 | 2 | 4 | 4 |  | PCDW12 | Large bulk meters | Large bulk meters |  |  | Y
|  | PCDWW25b |  | Y | [31 empty] | PCDW12 | Small bulk meters | Small bulk meters |  |  | Y
|  | PCDWW25b |  | Y | [31 empty] | PCDW12 | Metering replacement | Meter Replacements | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
|  | PCDWW30 | Y | Y | Y | Y | Y | Y |  |  | Y | Y | Y | [22 empty] | PCDW12 | Metering connected | Connected meters | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
| PR24CA116 Wastewater Other | PCDWW32 | Y | Y | Y | Y | Y |  | Y | Y | Y | Y | Y | [22 empty] | PCDW11a | Supply | WAFU Benefit [Base Overlap Schemes] | Y | Y | Y | Y |  | Y | Y |  |  |  | Y | Y |  |  | Y
|  | PCDWW32b | [9 empty] | Y | [23 empty] | PCDW11a | Supply | WAFU Benefit [Medium] | Y | Y | Y | Y |  | Y | Y |  |  |  | Y | Y |  |  | Y
|  | PCDWW32d |  |  |  | Y | [29 empty] | PCDW11a | Supply | WAFU Benefit [Low] | Y | Y | Y | Y |  | Y | Y |  |  |  | Y | Y |  |  | Y
|  | PCDWW32e |  | Y | [31 empty] | PCDW11a | Supply | WAFU Benefit [Very Low] | Y | Y | Y | Y |  | Y | Y |  |  |  | Y | Y |  |  | Y
|  | PCDWW32f | [9 empty] | Y | [23 empty] | PCDW11a | Supply | WAFU Benefit [Total] | Y | Y | Y | Y |  | Y | Y |  |  |  | Y | Y |  |  | Y
|  | PCDWW32g | [6 empty] | Y | [26 empty] | PCDW11b | Supply interconnectors | WAFU Benefit | Y | Y |  | Y |  | Y | Y |  | Y |  |  | Y
|  | PCDWW29 | [5 empty] | Y | [27 empty] | PCDW11b | Supply interconnectors | Pipeline length | Y | Y |  | Y |  | Y | Y |  | Y |  |  | Y
| PR24CA117 WINEP and GER Carryover | PCDWW36 | [9 empty] | Y | [22 empty] | PR24CA109 Water Resilience and Security | PCDW9 | Efficiency | Water demand savings (benefit) |  |  |  |  | Y | Y | [5 empty] | Y |  | Y |  | Y
|  | PCDWW36 | [9 empty] | Y | [23 empty] | PCDW16b | Resilience Interconnector | Length of resilience interconnector | Y | Y |  |  |  | Y |  |  | Y | [5 empty] | Y | Y
| PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | [22 empty] | PCDW16b | Resilience Interconnector | Crossing connections improvement | [8 empty] | Y
| PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y |  | Y |  | Y | Y |  | Y | Y | Y | Y | [22 empty] | PCDW16b | Resilience Interconnector | Additional storage at reservoirs | [11 empty] | Y |  |  | Y
| PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | [22 empty] | PCDW16b | Resilience Interconnector | Reservoir bypass | [16 empty] | Y
| PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | [22 empty] | PCDW16a | Resilience | Number of water treatment works with new equipment | [6 empty] | Y
| PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Y | Y | Y | Y | Y | Y |  | Y | Y | Y | [22 empty] | PCDW16a | Resilience | Upgrade works at water treatment works |  |  |  | Y
| PR24CA117 WINEP and GER Carryover | PCDWW35 | Y |  | Y | Y | Y |  | Y |  |  | Y | Y | [22 empty] | PCDW16a | Resilience | Service reservoirs with new enhanced bypass provision | [13 empty] | Y
| PR24CA118 Net Zero | PCDWW34 | Y | Y |  |  | Y |  |  | Y | Y | Y | Y | [22 empty] | PCDW16a | Resilience | Installation of new equipment | [15 empty] | Y
| PR24PCD119-PR19-ODI-PCDs | PR19PCD-1 | [6 empty] | Y | [26 empty] | PCDW16a | Resilience | Ml of additional service reservoir storage at service reservoirs | [15 empty] | Y
|  | PR19PCD-2 |  |  |  |  | Y | [28 empty] | PCDW16a | Resilience | Ml/d of peak week production capacity of additional process stream | [15 empty] | Y
|  | PR19PCD-8 | [10 empty] | Y | [22 empty] | PCDW16c | Resilience | Number of raw water reservoirs with the delivery of specified safety improvements |  |  |  | Y |  |  | Y | Y | Y | Y
[36 empty] | PCDW16c | Resilience | Reservoirs - spend on MITIOS (Measures in the Interest of Safety) | [9 empty] | Y
| Total PCD outputs |  | 17 | 14 | 12 | 15 | 16 | 13 | 14 | 9 | 12 | 17 | 14 | [22 empty] | PCDW17b | Cyber | Legal instruments | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y | Y
[36 empty] | PCDW17a | SEDM | Legal instruments | Y | Y | Y | Y | Y | Y | Y |  | Y | Y | Y | Y | Y | Y | Y | Y | Y
[35 empty] | PR24CA118 Net Zero | PCDWW34 | Greenhouse gas reduction (net zero) | tCO2e | [8 empty] | Y | Y
[35 empty] | PR24CA118 Net Zero | PCDWW34 | Greenhouse gas reduction (net zero) | Number of hectares | [8 empty] | Y | Y
[35 empty] | PR24PCD119-PR19-ODI-PCDs | PR19PCD-4 | Internal connection delivery | WAFU Benefit | Y
[36 empty] | PR19PCD-10 | Strategic Main | Number of months delay to delivery of programme | [15 empty] | Y
[36 empty] | PR19PCD-9 | Alderney WTW | Number of months delay to delivery of scheme | [5 empty] | Y
[36 empty] | PR19PCD-7 | Water network improvement programme | Number of months delay to programme (Newport Zone DWR-2019-00004) | [8 empty] | Y
[36 empty] | PR19PCD-7 | Water network improvement programme | Number of months delay to programme (Newport Zone West DWR-2019-00005) | [8 empty] | Y
[36 empty] | PR19PCD-7 | Water network improvement programme | Number of months delay to programme (Barry / Sully Zone DWR-2019-00001) | [8 empty] | Y
[35 empty] | Total PCD outputs |  |  |  | 24 | 20 | 24 | 24 | 16 | 24 | 24 | 14 | 20 | 20 | 20 | 21 | 14 | 17 | 24 | 16 | 16

## Calcs_Net zero
Calcs_Net zero
PCD output & expenditure - Net Zero
| Company name | PCD Model | PCD Ref | PCD Output Description | Units | DPs | PCD output target (cumulative) |  |  |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | Allowed totex (cumulative)
[7 empty] | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 |  | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
| ANH | PR24CA118 Net Zero | PCDWW34 | Liquor Recovery | tCO2e | 3 | 0 | 0 | 0 | 0 | 287.5 | 0.0124 |  |  |  |  | 3.5649
| ANH | PR24CA118 Net Zero | PCDWW34 | Containment | tCO2e | 3 | 0 | 0 | 116 | 348 | 1027 | 0.0010977 |  |  |  |  | 1.1274
| ANH | PR24CA118 Net Zero | PCDWW34 | MABR | tCO2e | 3 | 0 | 0 | 268.232 | 73.272 | 655.672 | 0.017323 |  |  |  |  | 11.3585
| ANH | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide Abatement | tCO2e | 3 | 0 | 0 | 90.125 | 881.85 | 2543.15 | 0.00092386 |  |  |  |  | 2.3495
| ANH | PR24CA118 Net Zero | PCDWW34 | Liquor treatment plant | Nr Sites | 0 |  |  |  |  | 1 | 10.6946 |  |  |  |  | 10.6946
| ANH | PR24CA118 Net Zero | PCDWW34 | Tank covers and odour control measures | Nr Sites | 0 |  |  |  |  | 3 | 1.1274 |  |  |  |  | 3.3821
| ANH | PR24CA118 Net Zero | PCDWW34 | Membrane Aerated Biofilm Reactors | Nr Sites | 0 |  |  |  |  | 5 | 6.8151 |  |  |  |  | 34.0754
| ANH | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide Abatement | Nr Sites | 0 |  |  |  |  | 9 | 0.78326 |  |  |  |  | 7.0493
| WSH | PR24CA118 Net Zero | PCDWW34 | Net Zero Carbon Strategy | tCO2e | 3 | 3874 | 7748 | 11623 | 15498 | 19372 | 0.00044634 |  |  |  |  | 8.6465
| WSH | PR24CA118 Net Zero | PCDWW34 | Peatland Restoration | tCO2e | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| WSH | PR24CA118 Net Zero | PCDWW34 | Net Zero Carbon Strategy | Nr Sites | 0 |  |  |  |  | 30 | 0.86465 |  |  |  |  | 25.9394
| WSH | PR24CA118 Net Zero | PCDWW34 | Peatland Restoration | Nr Hectares | 0 |  |  |  |  | 2000 | 0.0066851 |  |  |  |  | 13.3703
| HDD | PR24CA118 Net Zero | PCDWW34 | GHG emissions reduction | tCO2e | 3 | 0 | 0 | 137.13 | 274.265 | 411.39 | 0.00051796 |  |  |  |  | 0.21308
| HDD | PR24CA118 Net Zero | PCDWW34 | Digital Twin with Cover and Treat | Nr Sites | 0 |  |  |  |  | 1 | 0.63925 |  |  |  |  | 0.63925
| SVE | PR24CA118 Net Zero | PCDWW34 | Cover & Treat | tCO2e | 3 | 0 | 0 | 2010.388 | 6144.459 | 19618.18 | 0.0011575 |  |  |  |  | 22.7082
| SVE | PR24CA118 Net Zero | PCDWW34 | ASP Intensification | tCO2e | 3 | 0 | 0 | 2200.349 | 6601.047 | 13202.094 | 0.0019277 |  |  |  |  | 25.45
| SVE | PR24CA118 Net Zero | PCDWW34 | Digital Twin | tCO2e | 3 | 0 | 0 | 1337.931 | 4013.794 | 8027.589 | 0.0016243 |  |  |  |  | 13.0392
| SVE | PR24CA118 Net Zero | PCDWW34 | Active Gas Capture | tCO2e | 3 | 0 | 0 | 1359 | 4078 | 8156 | 0.0010676 |  |  |  |  | 8.7076
| SVE | PR24CA118 Net Zero | PCDWW34 | Process Optimisation | tCO2e | 3 | 0 | 0 | 8984.727 | 17969.453 | 26954.18 | 8.1323e-05 |  |  |  |  | 2.192
| SVE | PR24CA118 Net Zero | PCDWW34 | Cover & Treat | Nr Sites | 0 |  |  |  |  | 23 | 2.9619 |  |  |  |  | 68.1247
| SVE | PR24CA118 Net Zero | PCDWW34 | ASP Intensification | Nr Sites | 0 |  |  |  |  | 7 | 10.9071 |  |  |  |  | 76.3499
| SVE | PR24CA118 Net Zero | PCDWW34 | Digital Twin | Nr Sites | 0 |  |  |  |  | 32 | 1.2224 |  |  |  |  | 39.1177
| SVE | PR24CA118 Net Zero | PCDWW34 | Active Gas Capture | Nr Sites | 0 |  |  |  |  | 18 | 1.4513 |  |  |  |  | 26.1227
| SVE | PR24CA118 Net Zero | PCDWW34 | Process Optimisation | Nr Sites | 0 |  |  |  |  | 105 | 0.062628 |  |  |  |  | 6.576
| UUW | PR24CA118 Net Zero | PCDWW34 | Net Zero Catchment Strategy | tCO2e | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0
| UUW | PR24CA118 Net Zero | PCDWW34 | Process Emissions | tCO2e | 3 | 0 | 0 | 12541.041 | 37623.123 | 62705.206 | 0.00013425 |  |  |  |  | 8.4182
| UUW | PR24CA118 Net Zero | PCDWW34 | Peatland Restoration | tCO2e | 3 | 0 | 0 | 0 | 0 | 13227 | 0.00037867 |  |  |  |  | 5.0087
| UUW | PR24CA118 Net Zero | PCDWW34 | Net Zero Catchment Strategy | Nr Sites | 0 |  |  |  |  | 1 | 1.0031 |  |  |  |  | 1.0031
| UUW | PR24CA118 Net Zero | PCDWW34 | Process Emissions | Nr Sites | 0 |  |  |  |  | 17 | 1.4856 |  |  |  |  | 25.2544
| UUW | PR24CA118 Net Zero | PCDWW34 | Peatland Restoration | Nr Hectares | 0 |  |  |  |  | 1494 | 0.010058 |  |  |  |  | 15.026
| WSX | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide - Standard | tCO2e | 3 | 0 | 0 | 652.74 | 1305.5 | 1978 | 0.00010561 |  |  |  |  | 0.2089
| WSX | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide - NZ | tCO2e | 3 | 0 | 0 | 294.492 | 589 | 892.4 | 0.0003764 |  |  |  |  | 0.3359
| WSX | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide - Standard | Nr Sites | 0 |  |  |  |  | 7 | 0.089527 |  |  |  |  | 0.62669
| WSX | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide - NZ | Nr Sites | 0 |  |  |  |  | 13 | 0.077515 |  |  |  |  | 1.0077
| YKY | PR24CA118 Net Zero | PCDWW34 | Methane Reduction | tCO2e | 3 | 0 | 5397 | 19300 | 33203 | 47106 | 5.2316e-05 |  |  |  |  | 2.4644
| YKY | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide Reduction | tCO2e | 3 | 0 | 2500 | 7000 | 12418 | 17836 | 0.00018223 |  |  |  |  | 3.2503
| YKY | PR24CA118 Net Zero | PCDWW34 | Methane Reduction | Nr Sites | 0 |  |  |  |  | 9 | 0.82146 |  |  |  |  | 7.3932
| YKY | PR24CA118 Net Zero | PCDWW34 | Nitrous Oxide Reduction | Nr Sites | 0 |  |  |  |  | 13 | 0.75007 |  |  |  |  | 9.7509

## Calcs_Supply
|  |  |  | Capital expenditure (£m) | [6 empty] | Opex costs (£m) | [5 empty] | TOTEX (£m) | [5 empty] | Cumulative TOTEX (£m) | [5 empty] | AMP8 Profile expenditure (%) | [8 empty] | Cumulative AMP8 allowances (Post FS) (£m)
|  |  |  | pre-2025-26 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | After 2029-30 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | After 2029-30 | pre-2025-26 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | pre-2025-26 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | pre-2025-26 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | AMP8 allowances | FS adjustment | AMP8 allowances Post FS | pre-2025-26 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30
ANH | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 0.15785 | 5.6281 | 10.2374 | 26.6473 | 56.9006 | 42.6734 | 0 | 0 | 0 | 0 | 0 | 0.87959 | 40.4612 | 0.15785 | 5.6281 | 10.2374 | 26.6473 | 56.9006 | 43.553 | 0.15785 | 5.786 | 16.0234 | 42.6707 | 99.5713 | 143.1243 | 0.1103% | 4.043% | 11.2% | 29.81% | 69.57% | 100% | 150.9095 | 0.97387 | 146.9667 | 0.16209 | 5.9413 | 16.4536 | 43.8162 | 102.2444 | 146.9667
ANH | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97387 | 0
ANH | Medium | Medium | WAFU Benefit [Medium] | 5.8451 | 7.5478 | 11.1999 | 8.754 | 3.1073 | 0 | 0 | 0.0955 | 0.191 | 0.40777 | 0.69018 | 0.75583 | 17.3841 | 5.8451 | 7.6433 | 11.3909 | 9.1618 | 3.7975 | 0.75583 | 5.8451 | 13.4884 | 24.8793 | 34.0411 | 37.8386 | 38.5944 | 15.14% | 34.95% | 64.46% | 88.2% | 98.04% | 100% | 49.7306 | 0.97387 | 48.4312 | 7.3349 | 16.9263 | 31.2205 | 42.7174 | 47.4828 | 48.4312
ANH | Low | Low | WAFU Benefit [Low] | 0 | 2.249 | 4.262 | 3.8194 | 0.9448 | 0 | 0 | 0 | 0.0028628 | 0.027389 | 0.056241 | 0.063429 | 1.4589 | 0 | 2.249 | 4.2649 | 3.8468 | 1.001 | 0.063429 | 0 | 2.249 | 6.5139 | 10.3607 | 11.3618 | 11.4252 | 0% | 19.68% | 57.01% | 90.68% | 99.44% | 100% | 2.9048 | 0.97387 | 2.8289 | 0 | 0.55686 | 1.6128 | 2.5653 | 2.8132 | 2.8289
ANH | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97387 | 0
NES | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 9 | 20.555 | 20.555 | 20.555 | 20.879 | 11.879 | 0 | 0 | 0 | 0 | 0 | 0 | 5.744 | 9 | 20.555 | 20.555 | 20.555 | 20.879 | 11.879 | 9 | 29.555 | 50.11 | 70.665 | 91.544 | 103.423 | 8.702% | 28.58% | 48.45% | 68.33% | 88.51% | 100% | 103.423 | 0.98083 | 101.4402 | 8.8275 | 28.9884 | 49.1493 | 69.3102 | 89.7889 | 101.4402
NES | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.98083 | 0
NES | Medium | Medium | WAFU Benefit [Medium] | 1.632 | 17.784 | 17.784 | 0 | 0 | 0 | 0 | 0 | 0 | 1.566 | 1.566 | 1.566 | 1.566 | 1.632 | 17.784 | 17.784 | 1.566 | 1.566 | 1.566 | 1.632 | 19.416 | 37.2 | 38.766 | 40.332 | 41.898 | 3.895% | 46.34% | 88.79% | 92.52% | 96.26% | 100% | 39.7209 | 0.98083 | 38.9594 | 1.5175 | 18.0542 | 34.5909 | 36.047 | 37.5032 | 38.9594
NES | Low | Low | WAFU Benefit [Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.98083 | 0
NES | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.98083 | 0
SVE | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 29.3 | 27.368 | 36.878 | 57.118 | 59.518 | 8.328 | 0 | 0 | 0 | 0 | 0 | 1.2617 | 5.155 | 29.3 | 27.368 | 36.878 | 57.118 | 59.518 | 9.5897 | 29.3 | 56.668 | 93.546 | 150.664 | 210.182 | 219.7717 | 13.33% | 25.78% | 42.57% | 68.55% | 95.64% | 100% | 188.6369 | 0.97858 | 184.597 | 24.6105 | 47.5982 | 78.5738 | 126.55 | 176.5421 | 184.597
SVE | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97858 | 0
SVE | Medium | Medium | WAFU Benefit [Medium] | 1.31 | 1.701 | 0 | 0 | 0 | 0 | 0 | 0 | 0.429 | 0.429 | 0.429 | 0.429 | 0.429 | 1.31 | 1.701 | 0.429 | 0.429 | 0.429 | 0.429 | 1.31 | 3.011 | 3.44 | 3.869 | 4.298 | 4.727 | 27.71% | 63.7% | 72.77% | 81.85% | 90.92% | 100% | 38.0923 | 0.97858 | 37.2765 | 10.3305 | 23.7444 | 27.1274 | 30.5105 | 33.8935 | 37.2765
SVE | Low | Low | WAFU Benefit [Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97858 | 0
SVE | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97858 | 0
SWB | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 0 | 3.793 | 2.866 | 11.463 | 11.463 | 2.866 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5274 | 0 | 3.793 | 2.866 | 11.463 | 11.463 | 2.866 | 0 | 3.793 | 6.659 | 18.122 | 29.585 | 32.451 | 0% | 11.69% | 20.52% | 55.84% | 91.17% | 100% | 8.9827 | 0.97556 | 8.7632 | 0 | 1.0243 | 1.7982 | 4.8937 | 7.9892 | 8.7632
SWB | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97556 | 0
SWB | Medium | Medium | WAFU Benefit [Medium] | 0 | 0 | 0 | 0.718 | 1.167 | 3.499 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1852 | 0 | 0 | 0 | 0.718 | 1.167 | 3.499 | 0 | 0 | 0 | 0.718 | 1.885 | 5.384 | 0% | 0% | 0% | 13.34% | 35.01% | 100% | 3.9721 | 0.97556 | 3.875 | 0 | 0 | 0 | 0.51677 | 1.3567 | 3.875
SWB | Low | Low | WAFU Benefit [Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97556 | 0
SWB | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97556 | 0
SRN | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 0 | 14.1893 | 22.1098 | 23.7617 | 23.7617 | 7.9206 | 85.8673 | 0 | 0 | 0 | 0 | 0 | 0.00039113 | 0 | 14.1893 | 22.1098 | 23.7617 | 23.7617 | 7.9206 | 0 | 14.1893 | 36.2991 | 60.0608 | 83.8225 | 91.7431 | 0% | 15.47% | 39.57% | 65.47% | 91.37% | 100% | 16.6908 | 0.97659 | 16.3 | 0 | 2.521 | 6.4493 | 10.671 | 14.8928 | 16.3
SRN | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97659 | 0
SRN | Medium | Medium | WAFU Benefit [Medium] | 0 | 8.8726 | 11.1862 | 2.1208 | 17.5278 | 17.4596 | 24.7312 | 0 | 0 | 0.15233 | 0.15233 | 0.15233 | 0.75028 | 0 | 8.8726 | 11.1862 | 2.2731 | 17.6801 | 17.6119 | 0 | 8.8726 | 20.0588 | 22.3319 | 40.012 | 57.6239 | 0% | 15.4% | 34.81% | 38.75% | 69.44% | 100% | 75.8322 | 0.97659 | 74.0566 | 0 | 11.4028 | 25.7789 | 28.7003 | 51.4222 | 74.0566
SRN | Low | Low | WAFU Benefit [Low] | 0 | 18.6917 | 2.0957 | 4.6585 | 6.7959 | 5.2468 | 7.5551 | 1.46e-05 | 1.46e-05 | 0.11365 | 0.11365 | 0.11365 | 1.0391 | 0 | 18.6917 | 2.0957 | 4.7721 | 6.9095 | 5.3605 | 0 | 18.6917 | 20.7874 | 25.5596 | 32.4691 | 37.8295 | 0% | 49.41% | 54.95% | 67.57% | 85.83% | 100% | 20.8634 | 0.97659 | 20.3749 | 0 | 10.0673 | 11.196 | 13.7663 | 17.4877 | 20.3749
SRN | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97659 | 0
TMS | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97198 | 0
TMS | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97198 | 0
TMS | Medium | Medium | WAFU Benefit [Medium] | 0 | 5.397 | 8.928 | 17.025 | 16.418 | 14.217 | 0 | 0 | 0 | 0.042 | 0.134 | 0.441 | 0.447 | 0 | 5.397 | 8.928 | 17.067 | 16.552 | 14.658 | 0 | 5.397 | 14.325 | 31.392 | 47.944 | 62.602 | 0% | 8.621% | 22.88% | 50.15% | 76.59% | 100% | 82.4606 | 0.97198 | 80.1504 | 0 | 6.9099 | 18.3405 | 40.1917 | 61.3835 | 80.1504
TMS | Low | Low | WAFU Benefit [Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.118 | 3.163 | 3.21 | 3.256 | 3.304 | 0 | 0 | 3.118 | 3.163 | 3.21 | 3.256 | 3.304 | 0 | 3.118 | 6.281 | 9.491 | 12.747 | 16.051 | 0% | 19.43% | 39.13% | 59.13% | 79.42% | 100% | 16.051 | 0.97198 | 15.6013 | 0 | 3.0306 | 6.105 | 9.2251 | 12.3899 | 15.6013
TMS | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97198 | 0
YKY | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.96251 | 0
YKY | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.96251 | 0
YKY | Medium | Medium | WAFU Benefit [Medium] | 0.47744 | 1.2596 | 5.3276 | 4.1866 | 0.89006 | 0.89006 | 74.1611 | 0 | 0.14259 | 0.28519 | 0.28519 | 0.28519 | 2.661 | 0.47744 | 1.2596 | 5.4702 | 4.4718 | 1.1753 | 1.1753 | 0.47744 | 1.737 | 7.2072 | 11.679 | 12.8543 | 14.0295 | 3.403% | 12.38% | 51.37% | 83.25% | 91.62% | 100% | 27.2075 | 0.96251 | 26.1875 | 0.89119 | 3.2423 | 13.453 | 21.8001 | 23.9938 | 26.1875
YKY | Low | Low | WAFU Benefit [Low] | 0.49 | 3.8595 | 10.1464 | 6.6127 | 0 | 0 | 0 | 0 | 0 | 1.1536 | 2.3072 | 2.3072 | 2.3072 | 0.49 | 3.8595 | 10.1464 | 7.7663 | 2.3072 | 2.3072 | 0.49 | 4.3495 | 14.496 | 22.2622 | 24.5695 | 26.8767 | 1.823% | 16.18% | 53.94% | 82.83% | 91.42% | 100% | 10.6532 | 0.96251 | 10.2538 | 0.18694 | 1.6594 | 5.5304 | 8.4933 | 9.3736 | 10.2538
YKY | Very Low | Very Low | WAFU Benefit [Very Low] | 0.020992 | 0.003991 | 0.003991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.020992 | 0.003991 | 0.003991 | 0 | 0 | 0 | 0.020992 | 0.024983 | 0.028974 | 0.028974 | 0.028974 | 0.028974 | 72.45% | 86.23% | 100% | 100% | 100% | 100% | 0.021306 | 0.96251 | 0.020508 | 0.014858 | 0.017683 | 0.020508 | 0.020508 | 0.020508 | 0.020508
AFW | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97816 | 0
AFW | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97816 | 0
AFW | Medium | Medium | WAFU Benefit [Medium] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.97816 | 0
AFW | Low | Low | WAFU Benefit [Low] | 0 | 3.3443 | 0 | 0 | 1.8028 | 0 | 0 | 0.89685 | 0.89685 | 0.89685 | 0.89685 | 1.4948 | 0 | 0 | 4.2412 | 0.89685 | 0.89685 | 2.6996 | 1.4948 | 0 | 4.2412 | 5.138 | 6.0349 | 8.7345 | 10.2292 | 0% | 41.46% | 50.23% | 59% | 85.39% | 100% | 10.6532 | 0.97816 | 10.4205 | 0 | 4.3205 | 5.2341 | 6.1477 | 8.8978 | 10.4205
AFW | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 4.006 | 0 | 0 | 0 | 0 | 0 | 0 | 0.47 | 0.47 | 0 | 0 | 0 | 0 | 4.006 | 0.47 | 0 | 0 | 0 | 0 | 4.006 | 4.476 | 0% | 0% | 0% | 0% | 89.5% | 100% | 2.3437 | 0.97816 | 2.2925 | 0 | 0 | 0 | 0 | 2.0518 | 2.2925
SSC | Base-overlap schemes | Treatment | WAFU Benefit [Base Overlap Schemes] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.84175 | 0
SSC | High | High |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.84175 | 0
SSC | Medium | Medium | WAFU Benefit [Medium] | 0 | 0.288 | 0.673 | 0.962 | 0 | 0 | 0 | 0 | 0 | 0.027 | 0 | 0 | 0 | 0 | 0.288 | 0.673 | 0.989 | 0 | 0 | 0 | 0.288 | 0.961 | 1.95 | 1.95 | 1.95 | 0% | 14.77% | 49.28% | 100% | 100% | 100% | 1.5888 | 0.84175 | 1.3374 | 0 | 0.19752 | 0.6591 | 1.3374 | 1.3374 | 1.3374
SSC | Low | Low | WAFU Benefit [Low] | 0.17 | 1.379 | 1.379 | 3.748 | 2.961 | 2.961 | 0 | 0 | 0 | 0 | 0 | 0 | 57.953 | 0.17 | 1.379 | 1.379 | 3.748 | 2.961 | 2.961 | 0.17 | 1.549 | 2.928 | 6.676 | 9.637 | 12.598 | 1.349% | 12.3% | 23.24% | 52.99% | 76.5% | 100% | 18.4655 | 0.84175 | 15.5434 | 0.20975 | 1.9112 | 3.6126 | 8.2368 | 11.8901 | 15.5434
SSC | Very Low | Very Low | WAFU Benefit [Very Low] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0.84175 | 0

## DPB1
DPB1 | [39 empty] | Ofwat Bon Numbers
DPB
Base PCD outputs
Header | Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | PCD output (cumulative) - Target | [10 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP reference |  | PCD output (cumulative) - Target | [10 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Performance
[8 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%)
Start_Data | [7 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [7 empty] | Start_BON | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals in kilometres | km | 3 |  | 73.2344 | 170.8802 | 292.9374 | 390.5832 | 488.229 | [5 empty] | 488.229 | 0 |  | 78.0343 | 170.9263 | 273.0143 | 379.0233 | 488.3793 | [5 empty] | 488.3793 | 0 | 100% |  | Amber | Green | DPB1.1 |  | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE_T | PCD_DPB1_MRBASE_T | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_OT | PCD_DPB1_MRBASE_OT | PCD_DPB1_MRBASE_P | PCD_DPB1_MRBASE_P
|  |  | PCDB1b | Mains renewals - asset health adjustment | Base asset health adjustment renewals in kilometres | km | 3 |  | 9.1088 | 21.2538 | 36.4351 | 48.5801 | 60.7251 | [5 empty] | 60.7251 | 0 |  | 7.424 | 23.141 | 35.637 | 48.837 | 62.637 | [5 empty] | 62.637 | 0 | 103.1% |  | Amber | Green | DPB1.2 |  | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH_T | PCD_DPB1_MRAH_T | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_OT | PCD_DPB1_MRAH_OT | PCD_DPB1_MRAH_P | PCD_DPB1_MRAH_P
|  |  | PCDB1c | Mains renewals - enhancement leakage | Enhancement leakage renewals in kilometres | km | 3 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPB1.3 |  | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA_T | PCD_DPB1_MRENHLEA_T | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_OT | PCD_DPB1_MRENHLEA_OT | PCD_DPB1_MRENHLEA_P | PCD_DPB1_MRENHLEA_P

## DPB2
DPB2 | [40 empty] | Ofwat Bon Numbers
DPB
Base PCD expenditure
Header | Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance
[9 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%)
Start_Data | [8 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [6 empty] | Start_BON | 2025-30 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals expenditure | £m | 3 |  |  | 55.5668 | 129.656 | 222.2674 | 296.3565 | 370.4457 | [5 empty] | 370.4457 | 0 |  | 86.3121 | 208.6979 | 335.6396 | 472.7817 | 612.5975 | [5 empty] | 612.5975 | 0 | 165.4% |  | DPB2.1 |  |  | PCD_DPB2_MR_BASE_NP | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE_T | PCD_DPB2_MR_BASE_T | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_OT | PCD_DPB2_MR_BASE_OT | PCD_DPB2_MR_BASE_P | PCD_DPB2_MR_BASE_P
|  |  | PCDB1b | Mains renewals - asset health adjustment | Base asset health adjustment renewals expenditure | £m | 3 |  |  | 10.5203 | 24.5474 | 42.0812 | 56.1083 | 70.1354 | [5 empty] | 70.1354 | 0 |  | 14.6163 | 34.0702 | 51.7424 | 71.7946 | 93.613 | [5 empty] | 93.613 | 0 | 133.5% |  | DPB2.2 |  |  | PCD_DPB2_MR_AH_NP | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH_T | PCD_DPB2_MR_AH_T | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_OT | PCD_DPB2_MR_AH_OT | PCD_DPB2_MR_AH_P | PCD_DPB2_MR_AH_P
|  |  | PCDB1c | Mains renewals - enhancement leakage | Enhancement leakage renewals expenditure | £m | 3 | [6 empty] | 0 | [5 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPB2.3 |  |  | PCD_DPB2_MR_ENHLEA_NP | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA_T | PCD_DPB2_MR_ENHLEA_T | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_OT | PCD_DPB2_MR_ENHLEA_OT | PCD_DPB2_MR_ENHLEA_P | PCD_DPB2_MR_ENHLEA_P
|  |  | PCDB3a | Water network reinforcement | Water network reinforcement expenditure | £m | 3 |  |  | 31.5204 | 62.7508 | 94.0153 | 125.1037 | 155.9137 | [5 empty] | 155.9137 | 0 |  | 28.1695 | 66.4617 | 92.9814 | 123.1365 | 157.2182 | [5 empty] | 157.2182 | 0 | 100.8% |  | DPB2.4 |  |  | PCD_DPB2_WN_RFT_NP | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT_T | PCD_DPB2_WN_RFT_T | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_OT | PCD_DPB2_WN_RFT_OT | PCD_DPB2_WN_RFT_P | PCD_DPB2_WN_RFT_P
|  |  | PCDB3b | Wastewater network reinforcement | Wastewater network reinforcement expenditure | £m | 3 |  |  | 24.5146 | 48.9294 | 73.2562 | 97.5065 | 121.6776 | [5 empty] | 121.6776 | 0 |  | 18.1407 | 56.8485 | 79.009 | 99.9376 | 122.8328 | [5 empty] | 122.8328 | 0 | 100.9% |  | DPB2.5 |  |  | PCD_DPB2_WWN_RFT_NP | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT_T | PCD_DPB2_WWN_RFT_T | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_OT | PCD_DPB2_WWN_RFT_OT | PCD_DPB2_WWN_RFT_P | PCD_DPB2_WWN_RFT_P
[38 empty] | End_Data | [30 empty] | End_BON

## TMS_DPB1_ADD
TMS_DPB1_ADD | [38 empty] | Ofwat Bon Numbers
TMS
Base PCD outputs
| Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | PCD output (cumulative) - Target | [10 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP reference | [11 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Outturn & Forecast) | [11 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Outturn & Forecast)
[8 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 | AMP8 |  |  |  |  | AMP9
[8 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [7 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
|  | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals in kilometres - Thames Valley | km | 3 | AMP8 2025-26: 33.6878; AMP8 2026-27: 78.6049; AMP8 2027-28: 134.7512; AMP8 2028-29: 179.6683; AMP8 2029-30: 224.5854 | 224.5854 | 0 |  | 24.8141 | 69.2321 | 126.2311 | 175.2331 | 225.2231 | [5 empty] | 225.2231 | 0 | 100.3% |  | Amber | Green | DPB1.1
|  |  | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals in kilometres - London | km | 3 | AMP8 2025-26: 39.5466; AMP8 2026-27: 92.2753; AMP8 2027-28: 158.1862; AMP8 2028-29: 210.9149; AMP8 2029-30: 263.6437 | 263.6437 | 0 |  | 53.2202 | 101.6942 | 146.7832 | 203.7902 | 263.1562 | [5 empty] | 263.1562 | 0 | 99.82% |  | Amber | Green | DPB1.1

## TMS_DPB2_ADD
TMS_DPB2_ADD | [37 empty] | Ofwat Bon Numbers
TMS
Base PCD expenditure
| Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference | [11 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Outturn & Forecast) | [11 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast)
[9 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 | AMP8 |  |  |  |  | AMP9
[9 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [5 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
|  | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals expenditure - Thames Valley | £m | 3 |  | AMP8 2029-30: 65.9462 | 65.9462 | 0 |  | 12.7043 | 55.0052 | 113.8168 | 163.3221 | 210.9016 | [5 empty] | 210.9016 | 0 | 319.8% |  | DPB2.1
|  |  | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals expenditure - London | £m | 3 |  | AMP8 2029-30: 304.4995 | 304.4995 | 0 |  | 73.6078 | 153.6927 | 221.8228 | 309.4596 | 401.6959 | [5 empty] | 401.6959 | 0 | 131.9% |  | DPB2.1

## DPWW1
Ofwat Bon Numbers
Enhancement PCD output - wastewater - Programme level
Header | Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | PCD output (cumulative) - Target | [10 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP reference |  |  | PCD output (cumulative) - Target` | [10 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Performance
[9 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  |  |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%)
Start_Data | [8 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [8 empty] | Start_BON | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA110 Wastewater flow and monitoring | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring permits only or simple schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.1 |  |  | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS_T | PCD_DPWW1_FMS_T | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_OT | PCD_DPWW1_FMS_OT | PCD_DPWW1_FMS_P | PCD_DPWW1_FMS_P
| TMS |  | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring complex schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.2 |  |  | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC_T | PCD_DPWW1_FMC_T | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_OT | PCD_DPWW1_FMC_OT | PCD_DPWW1_FMC_P | PCD_DPWW1_FMC_P
| TMS |  | PCDWW2b | 0 | Continuous river water quality monitoring (CWQM) | Continuous river water quality monitoring (CWQM) | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.3 |  |  | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM_T | PCD_DPWW1_CWQM_T | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_OT | PCD_DPWW1_CWQM_OT | PCD_DPWW1_CWQM_P | PCD_DPWW1_CWQM_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only | Nr | 0 |  | 0 | 26 | 26 | 26 | 26 | [5 empty] | 26 | 0 | [5 empty] | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 38.46% |  | Green | Green | DPWW1.4 |  |  | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1_T | PCD_DPWW1_SPSO1_T | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_OT | PCD_DPWW1_SPSO1_OT | PCD_DPWW1_SPSO1_P | PCD_DPWW1_SPSO1_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.5 |  |  | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2_T | PCD_DPWW1_SPSO2_T | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_OT | PCD_DPWW1_SPSO2_OT | PCD_DPWW1_SPSO2_P | PCD_DPWW1_SPSO2_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.6 |  |  | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3_T | PCD_DPWW1_SPSO3_T | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_OT | PCD_DPWW1_SPSO3_OT | PCD_DPWW1_SPSO3_P | PCD_DPWW1_SPSO3_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils | Nr | 0 |  | 0 | 17.1852 | 17.1852 | 17.1852 | 22 | [5 empty] | 22 | 0 | [5 empty] | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 38 | 172.7% |  | Green | Green | DPWW1.7 |  |  | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4_T | PCD_DPWW1_SPSO4_T | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_OT | PCD_DPWW1_SPSO4_OT | PCD_DPWW1_SPSO4_P | PCD_DPWW1_SPSO4_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.8 |  |  | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5_T | PCD_DPWW1_SPSO5_T | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_OT | PCD_DPWW1_SPSO5_OT | PCD_DPWW1_SPSO5_P | PCD_DPWW1_SPSO5_P
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes | Nr | 0 |  | 0 | 0 | 0 | 3 | 6 | [5 empty] | 6 | 0 |  |  |  |  | 2 | 2 | 3 | 3 | 6 | 6 | 6 | 2 | 6 | 33.33% |  | Red | Red | DPWW1.9 |  |  | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1_T | PCD_DPWW1_SOFW1_T | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_OT | PCD_DPWW1_SOFW1_OT | PCD_DPWW1_SOFW1_P | PCD_DPWW1_SOFW1_P
| TMS |  | PCDWW5b | Y | Storm Overflow - Wetland | Wetland area delivered | ha | 0 |  | 0 | 0 | 0 | 2.83 | 7.931 | [5 empty] | 7.931 | 0 |  |  |  |  | 2.361 | 2.361 | 2.83 | 2.83 | 7.931 | 7.931 | 7.931 | 2.361 | 7.931 | 29.77% |  | Red | Red | DPWW1.10 |  |  | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2_T | PCD_DPWW1_SOFW2_T | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_OT | PCD_DPWW1_SOFW2_OT | PCD_DPWW1_SOFW2_P | PCD_DPWW1_SOFW2_P
| TMS |  | PCDWW6 | 0 | Storm Overflow - Screens | Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.11 |  |  | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS_T | PCD_DPWW1_SOFS_T | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_OT | PCD_DPWW1_SOFS_OT | PCD_DPWW1_SOFS_P | PCD_DPWW1_SOFS_P
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Total number of schemes with a treatment solution delivered to meet compliance | Nr | 0 |  | 0 | 0 | 0 | 0 | 7 | [5 empty] | 7 | 0 | [6 empty] | 3 | 4 | 5 | 7 | 7 |  | 7 |  |  | Red | Red | DPWW1.12 |  |  | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1_T | PCD_DPWW1_TCR1_T | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_OT | PCD_DPWW1_TCR1_OT | PCD_DPWW1_TCR1_P | PCD_DPWW1_TCR1_P
| TMS |  | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Population equivalent served by schemes with a treatment solution being delivered to meet compliance | Nr | 0 |  | 0 | 0 | 0 | 0 | 243105 | [5 empty] | 243105 | 0 | [6 empty] | 17473 | 33539 | 113791 | 243105 | 243105 |  | 243105 |  |  | Red | Red | DPWW1.13 |  |  | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2_T | PCD_DPWW1_TCR2_T | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_OT | PCD_DPWW1_TCR2_OT | PCD_DPWW1_TCR2_P | PCD_DPWW1_TCR2_P
| TMS |  | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Total number of schemes delivered to meet compliance | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.14 |  |  | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1_T | PCD_DPWW1_TNR1_T | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_OT | PCD_DPWW1_TNR1_OT | PCD_DPWW1_TNR1_P | PCD_DPWW1_TNR1_P
| TMS |  | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Population equivalent served by schemes delivered to meet compliance | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.15 |  |  | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2_T | PCD_DPWW1_TNR2_T | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_OT | PCD_DPWW1_TNR2_OT | PCD_DPWW1_TNR2_P | PCD_DPWW1_TNR2_P
| TMS |  | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Total number of site treatment solutions delivered to meet compliance | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.16 |  |  | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL_T | PCD_DPWW1_NBS_SOL_T | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_OT | PCD_DPWW1_NBS_SOL_OT | PCD_DPWW1_NBS_SOL_P | PCD_DPWW1_NBS_SOL_P
| TMS |  | PCDWW13a | 0 | Catchment solutions (WINEP/NEP) | Total number of CNB solutions delivered to meet compliance (allowance/7) | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.17 |  |  | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1_T | PCD_DPWW1_CS1_T | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_OT | PCD_DPWW1_CS1_OT | PCD_DPWW1_CS1_P | PCD_DPWW1_CS1_P
| TMS |  | PCDWW13a | 0 | Catchment solutions (WINEP/NEP) | Total number of CP solutions delivered to meet compliance (allowance/6) | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.18 |  |  | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2_T | PCD_DPWW1_CS2_T | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_OT | PCD_DPWW1_CS2_OT | PCD_DPWW1_CS2_P | PCD_DPWW1_CS2_P
| TMS |  | PCDWW14 |  | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.19 |  |  | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1_T | PCD_DPWW1_MBT1_T | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_OT | PCD_DPWW1_MBT1_OT | PCD_DPWW1_MBT1_P | PCD_DPWW1_MBT1_P
| TMS |  | PCDWW14 |  | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Current population equivalent served by STWs with tightened/new microbiological standards | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.20 |  |  | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2_T | PCD_DPWW1_MBT2_T | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_OT | PCD_DPWW1_MBT2_OT | PCD_DPWW1_MBT2_P | PCD_DPWW1_MBT2_P
| TMS |  | PCDWW15 | 0 | Septic tank replacements - treatment solution; (WINEP/NEP) | Total number of septic tank replacement or flow diversion schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.21 |  |  | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR_T | PCD_DPWW1_STR_T | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_OT | PCD_DPWW1_STR_OT | PCD_DPWW1_STR_P | PCD_DPWW1_STR_P
| TMS |  | PCDWW17 | 0 | 25 year environment plan; (WINEP/NEP) | Number of schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.22 |  |  | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP_T | PCD_DPWW1_25EP_T | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_OT | PCD_DPWW1_25EP_OT | PCD_DPWW1_25EP_P | PCD_DPWW1_25EP_P
| TMS | PR24CA112 Wastewater Other WINEP | PCDWW18 | Y | WINEP Investigations (wastewater) | Number of satisfactorily completed WINEP / NEP investigations - all categories | Nr | 0 |  | 147.6918 | 288.8815 | 431 | 431 | 431 | [5 empty] | 431 | 0 |  |  | 366 | 421 | 421 | 426 | 427 | 427 | 427 | 427 | 427 | 426 | 427 | 98.84% |  | Amber | Amber | DPWW1.23 |  |  | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG_T | PCD_DPWW1_WINIVG_T | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_OT | PCD_DPWW1_WINIVG_OT | PCD_DPWW1_WINIVG_P | PCD_DPWW1_WINIVG_P
| TMS |  | PCDWW23a | 0 | Advanced WINEP | Number of restoration plans developed and designed | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.24 |  |  | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1_T | PCD_DPWW1_ADWIN1_T | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_OT | PCD_DPWW1_ADWIN1_OT | PCD_DPWW1_ADWIN1_P | PCD_DPWW1_ADWIN1_P
| TMS |  | PCDWW23a | 0 | Advanced WINEP | Partnership funding | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.25 |  |  | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2_T | PCD_DPWW1_ADWIN2_T | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_OT | PCD_DPWW1_ADWIN2_OT | PCD_DPWW1_ADWIN2_P | PCD_DPWW1_ADWIN2_P
| TMS |  | PCDWW23b | 0 | Advanced WINEP | Equivalent storage avoided | m3 | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.26 |  |  | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3_T | PCD_DPWW1_ADWIN3_T | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_OT | PCD_DPWW1_ADWIN3_OT | PCD_DPWW1_ADWIN3_P | PCD_DPWW1_ADWIN3_P
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24a | 0 | Sludge storage -Tanks | Volume of Sludge Storage delivered | m3 | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.27 |  |  | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT_T | PCD_DPWW1_SSTT_T | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_OT | PCD_DPWW1_SSTT_OT | PCD_DPWW1_SSTT_P | PCD_DPWW1_SSTT_P
| TMS |  | PCDWW24b | 0 | Sludge storage (cake pads) | Sludge Storage area delivered | m2 | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.28 |  |  | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP_T | PCD_DPWW1_SSCP_T | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_OT | PCD_DPWW1_SSCP_OT | PCD_DPWW1_SSCP_P | PCD_DPWW1_SSCP_P
| TMS |  | PCDWW25a | 0 | Sludge thickening and dewatering | Tonnes of dry solids/ year | ttds/yr | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.29 |  |  | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW_T | PCD_DPWW1_STDW_T | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_OT | PCD_DPWW1_STDW_OT | PCD_DPWW1_STDW_P | PCD_DPWW1_STDW_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge throughput Dryer/Pelletiser installed plant capacity | ttds/yr | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.30 |  |  | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1_T | PCD_DPWW1_STOTH1_T | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_OT | PCD_DPWW1_STOTH1_OT | PCD_DPWW1_STOTH1_P | PCD_DPWW1_STOTH1_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge Throughput P Recovery installed plant capacity | 000m3/month | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.31 |  |  | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2_T | PCD_DPWW1_STOTH2_T | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_OT | PCD_DPWW1_STOTH2_OT | PCD_DPWW1_STOTH2_P | PCD_DPWW1_STOTH2_P
| TMS |  | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of sites achieving IED compliance | Nr | 0 | 25 | 0 | 2 | 2 | 5 | 25 | [5 empty] | 25 | 0 |  |  | 1 | 1 | 1 | 2 | 2 | 7 | 15 | 19 | 21 | 2 | 21 | 8% |  | Red | Red | DPWW1.32 |  |  | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED_T | PCD_DPWW1_BIO_IED_T | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_OT | PCD_DPWW1_BIO_IED_OT | PCD_DPWW1_BIO_IED_P | PCD_DPWW1_BIO_IED_P
| TMS | PR24CA116 Wastewater Other | PCDWW32 | Y | Climate change uplift | Spend on schemes for power and flood resilience delivered: | % | 0 |  | 3.6303 | 11.8661 | 25.9213 | 60.893 | 100 | [5 empty] | 100 | 0 | 0 | 0.94269 | 2.9226 | 14.503 | 84.6168 | 90.4548 | 91.4265 | 91.4265 | 91.4265 | 91.4265 | 91.4265 | 90.4548 | 91.4265 | 90.45% |  | Red | Red | DPWW1.33 |  |  | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP_T | PCD_DPWW1_CCUP_T | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_OT | PCD_DPWW1_CCUP_OT | PCD_DPWW1_CCUP_P | PCD_DPWW1_CCUP_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Crosby Rising Main | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.34 |  |  | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1_T | PCD_DPWW1_CER1_T | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_OT | PCD_DPWW1_CER1_OT | PCD_DPWW1_CER1_P | PCD_DPWW1_CER1_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Halcroft Cottages Sewer | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.35 |  |  | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2_T | PCD_DPWW1_CER2_T | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_OT | PCD_DPWW1_CER2_OT | PCD_DPWW1_CER2_P | PCD_DPWW1_CER2_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | London Road Terrace Sewer | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.36 |  |  | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3_T | PCD_DPWW1_CER3_T | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_OT | PCD_DPWW1_CER3_OT | PCD_DPWW1_CER3_P | PCD_DPWW1_CER3_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Rhodes Business Park Sewer | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.37 |  |  | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4_T | PCD_DPWW1_CER4_T | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_OT | PCD_DPWW1_CER4_OT | PCD_DPWW1_CER4_P | PCD_DPWW1_CER4_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Leyland WwTW | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.38 |  |  | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5_T | PCD_DPWW1_CER5_T | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_OT | PCD_DPWW1_CER5_OT | PCD_DPWW1_CER5_P | PCD_DPWW1_CER5_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Bowdon WwTW | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.39 |  |  | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6_T | PCD_DPWW1_CER6_T | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_OT | PCD_DPWW1_CER6_OT | PCD_DPWW1_CER6_P | PCD_DPWW1_CER6_P
| TMS |  | PCDWW32d | 0 | Infiltration | Total length (in metre) of sewer effectively sealed / lined | m | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.40 |  |  | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF_T | PCD_DPWW1_INF_T | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_OT | PCD_DPWW1_INF_OT | PCD_DPWW1_INF_P | PCD_DPWW1_INF_P
| TMS |  | PCDWW32e | 0 | WW Partnership Funding | spend on schemes for power and flood resilience delivered: | % | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.41 |  |  | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1_T | PCD_DPWW1_WWPF1_T | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_OT | PCD_DPWW1_WWPF1_OT | PCD_DPWW1_WWPF1_P | PCD_DPWW1_WWPF1_P
| TMS |  | PCDWW32e | 0 | WW Partnership Funding | Minimum number of schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.42 |  |  | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2_T | PCD_DPWW1_WWPF2_T | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_OT | PCD_DPWW1_WWPF2_OT | PCD_DPWW1_WWPF2_P | PCD_DPWW1_WWPF2_P
| TMS |  | PCDWW32f | 0 | Rainwater management | Total storage volume provided via SuDS solutions | Cubic metre | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.43 |  |  | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1_T | PCD_DPWW1_RRM1_T | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_OT | PCD_DPWW1_RRM1_OT | PCD_DPWW1_RRM1_P | PCD_DPWW1_RRM1_P
| TMS |  | PCDWW32f | 0 | Rainwater management | Completion of named schemes | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.44 |  |  | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2_T | PCD_DPWW1_RRM2_T | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_OT | PCD_DPWW1_RRM2_OT | PCD_DPWW1_RRM2_P | PCD_DPWW1_RRM2_P
| TMS |  | PCDWW32g | 0 | Flood and power | Flooding resilience scheme unit rate | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.45 |  |  | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2_T | PCD_DPWW1_FP2_T | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_OT | PCD_DPWW1_FP2_OT | PCD_DPWW1_FP2_P | PCD_DPWW1_FP2_P
| TMS |  | PCDWW32g | 0 | Flood and power | Power resilience scheme unit rate | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.46 |  |  | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3_T | PCD_DPWW1_FP3_T | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_OT | PCD_DPWW1_FP3_OT | PCD_DPWW1_FP3_P | PCD_DPWW1_FP3_P
| TMS |  | PCDWW29 | 0 | First time sewerage | Number of connected properties served by S101A schemes | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.47 |  |  | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS_T | PCD_DPWW1_FTS_T | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_OT | PCD_DPWW1_FTS_OT | PCD_DPWW1_FTS_P | PCD_DPWW1_FTS_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW36 | 0 | PR19 Green recovery carryover | Storage in the network close to Nuttall Road combined sewer overflow | m3 | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.48 |  |  | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1_T | PCD_DPWW1_GRC1_T | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_OT | PCD_DPWW1_GRC1_OT | PCD_DPWW1_GRC1_P | PCD_DPWW1_GRC1_P
| TMS |  | PCDWW36 | 0 | PR19 Green recovery carryover | Storm tank capacity at Bury wastewater treatment works | m3 | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.49 |  |  | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2_T | PCD_DPWW1_GRC2_T | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_OT | PCD_DPWW1_GRC2_OT | PCD_DPWW1_GRC2_P | PCD_DPWW1_GRC2_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows | Equivalent storage | m3 | 3 |  | 0 | 10557.9405 | 73905.5835 | 126695.286 | 211158.81 | [5 empty] | 211158.81 | 0 |  |  | 3462.4 | 25124.73 | 69755.31 | 113903.52 | 176066.19 | 185919.23 | 211158.81 | 211158.81 | 211158.81 | 113903.52 | 211158.81 | 53.94% |  | Red | Red | DPWW1.50 |  |  | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES_T | PCD_DPWW1_SOFES_T | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_OT | PCD_DPWW1_SOFES_OT | PCD_DPWW1_SOFES_P | PCD_DPWW1_SOFES_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | litres per second | l/s | 3 |  | 0 | 66.965 | 468.755 | 803.58 | 1339.3 | [5 empty] | 1339.3 | 0 |  |  | 12.6 | 39.8 | 66.3 | 253.7 | 505.9 | 555.9 | 1339.3 | 1339.3 | 1339.3 | 253.7 | 1339.3 | 18.94% |  | Red | Red | DPWW1.51 |  |  | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT_T | PCD_DPWW1_FTFT_T | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_OT | PCD_DPWW1_FTFT_OT | PCD_DPWW1_FTFT_P | PCD_DPWW1_FTFT_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Population equivalent served | 000s | 3 |  | 0 | 0 | 992.4325 | 2381.8379 | 3969.7299 | [5 empty] | 3969.7299 | 0 |  | 13.0146 | 13.0146 | 13.0146 | 22.2501 | 866.1171 | 1623.1382 | 2838.9477 | 3478.1102 | 3969.3453 | 3969.7301 | 866.1171 | 3969.7301 | 21.82% |  | Red | Red | DPWW1.52 |  |  | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL_T | PCD_DPWW1_PRMVL_T | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_OT | PCD_DPWW1_PRMVL_OT | PCD_DPWW1_PRMVL_P | PCD_DPWW1_PRMVL_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Added Process Capacity in PE | Nr | 3 |  | 0 | 0 | 0 | 3630.8805 | 93769.523 | [5 empty] | 93769.523 | 0 | [5 empty] | 24093.9665 | 38053.5445 | 57349.2977 | 93769.5209 | 93769.5209 | 93769.5209 | 24093.9665 | 93769.5209 | 25.69% |  | Red | Red | DPWW1.53 |  |  | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW_T | PCD_DPWW1_GSTW_T | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_OT | PCD_DPWW1_GSTW_OT | PCD_DPWW1_GSTW_P | PCD_DPWW1_GSTW_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Population equivalent served | 000s | 3 |  | 55.0287 | 137.9683 | 231.0587 | 491.4389 | 492.7439 | [5 empty] | 492.7439 | 0 |  | 63.3417 | 63.3417 | 156.4322 | 167.7582 | 414.7444 | 415.1494 | 415.2211 | 492.7439 | 492.7439 | 492.7439 | 414.7444 | 492.7439 | 84.17% |  | Red | Red | DPWW1.54 |  |  | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP_T | PCD_DPWW1_TTSP_T | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_OT | PCD_DPWW1_TTSP_OT | PCD_DPWW1_TTSP_P | PCD_DPWW1_TTSP_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes | Nr | 0 |  | 27 | 34 | 55 | 62 | 66 | [5 empty] | 66 | 0 | 9 | 20 | 25 | 35 | 53 | 62 | 65 | 66 | 66 | 66 | 66 | 62 | 66 | 93.94% |  | Red | Red | DPWW1.55 |  |  | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA_T | PCD_DPWW1_PR19WINCA_T | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_OT | PCD_DPWW1_PR19WINCA_OT | PCD_DPWW1_PR19WINCA_P | PCD_DPWW1_PR19WINCA_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | tCO2e | tonnes | 3 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.56 |  |  | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1_T | PCD_DPWW1_GGR1_T | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_OT | PCD_DPWW1_GGR1_OT | PCD_DPWW1_GGR1_P | PCD_DPWW1_GGR1_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of sites | Nr | 0 | [11 empty] | 0 | 0 | [17 empty] | DPWW1.57 |  |  | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2_T | PCD_DPWW1_GGR2_T | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_OT | PCD_DPWW1_GGR2_OT | PCD_DPWW1_GGR2_P | PCD_DPWW1_GGR2_P
[40 empty] | End_Data | [29 empty] | End_BON

## DPWW2
DPWW2 | [41 empty] | Ofwat Bon Numbers
Enhancement PCD expenditure - wastewater - Programme level
Header | Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance
[10 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%)
Start_Data | [9 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [6 empty] | Start_BON | 2025-30 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA110 Wastewater flow and monitoring | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring permits only or simple schemes delivered | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.1 |  |  | PCD_DPWW2_FMS_NP | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS_T | PCD_DPWW2_FMS_T | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_OT | PCD_DPWW2_FMS_OT | PCD_DPWW2_FMS_P | PCD_DPWW2_FMS_P
| TMS |  | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring complex schemes delivered | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.2 |  |  | PCD_DPWW2_FMC_NP | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC_T | PCD_DPWW2_FMC_T | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_OT | PCD_DPWW2_FMC_OT | PCD_DPWW2_FMC_P | PCD_DPWW2_FMC_P
| TMS |  | PCDWW2b | 0 | Continuous river water quality monitoring (CWQM) | Continuous river water quality monitoring (CWQM) | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.3 |  |  | PCD_DPWW2_CWQM_NP | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM_T | PCD_DPWW2_CWQM_T | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_OT | PCD_DPWW2_CWQM_OT | PCD_DPWW2_CWQM_P | PCD_DPWW2_CWQM_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only | £m | 3 | 0.14293 |  | 1.4883 | 2.9753 | 3.3463 | 3.5314 | 3.7162 | [5 empty] | 3.7162 | 0 | 0 | 0.14561 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 10.75% |  | DPWW2.4 |  |  | PCD_DPWW2_SPSO1_NP | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1_T | PCD_DPWW2_SPSO1_T | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_OT | PCD_DPWW2_SPSO1_OT | PCD_DPWW2_SPSO1_P | PCD_DPWW2_SPSO1_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.5 |  |  | PCD_DPWW2_SPSO2_NP | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2_T | PCD_DPWW2_SPSO2_T | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_OT | PCD_DPWW2_SPSO2_OT | PCD_DPWW2_SPSO2_P | PCD_DPWW2_SPSO2_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.6 |  |  | PCD_DPWW2_SPSO3_NP | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3_T | PCD_DPWW2_SPSO3_T | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_OT | PCD_DPWW2_SPSO3_OT | PCD_DPWW2_SPSO3_P | PCD_DPWW2_SPSO3_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils | £m | 3 | 0.25331 |  | 2.2317 | 4.4616 | 5.018 | 5.2956 | 5.5727 | [5 empty] | 5.5727 | 0 | 0 | 0.14561 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 7.166% |  | DPWW2.7 |  |  | PCD_DPWW2_SPSO4_NP | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4_T | PCD_DPWW2_SPSO4_T | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_OT | PCD_DPWW2_SPSO4_OT | PCD_DPWW2_SPSO4_P | PCD_DPWW2_SPSO4_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.8 |  |  | PCD_DPWW2_SPSO5_NP | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5_T | PCD_DPWW2_SPSO5_T | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_OT | PCD_DPWW2_SPSO5_OT | PCD_DPWW2_SPSO5_P | PCD_DPWW2_SPSO5_P
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes | £m | 3 |  |  | 2.2636 | 4.445 | 13.0605 | 30.6829 | 63.11 | [5 empty] | 63.11 | 0 | 0 | 0.19208 | 0.68705 | 5.5111 | 23.7075 | 47.6612 | 47.8735 | 47.9257 | 47.9257 | 47.9257 | 47.9257 | 47.6612 | 47.9257 | 75.52% |  | DPWW2.9 |  |  | PCD_DPWW2_SOFW1_NP | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1_T | PCD_DPWW2_SOFW1_T | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_OT | PCD_DPWW2_SOFW1_OT | PCD_DPWW2_SOFW1_P | PCD_DPWW2_SOFW1_P
| TMS |  | PCDWW6 | 0 | Storm Overflow - Screens | Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.10 |  |  | PCD_DPWW2_SOFW2_NP | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2_T | PCD_DPWW2_SOFW2_T | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_OT | PCD_DPWW2_SOFW2_OT | PCD_DPWW2_SOFW2_P | PCD_DPWW2_SOFW2_P
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Treatment for chemical removal (WINEP/NEP) | £m | 3 |  |  | 0.41431 | 0.69141 | 20.2728 | 68.6705 | 189.2081 | [5 empty] | 189.2081 | 0 | 0 | 10.6741 | 25.3715 | 39.3939 | 65.7745 | 101.0777 | 121.6611 | 144.0868 | 156.2303 | 158.2824 | 158.7503 | 101.0777 | 158.7503 | 53.42% |  | DPWW2.11 |  |  | PCD_DPWW2_TCR1_NP | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1_T | PCD_DPWW2_TCR1_T | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_OT | PCD_DPWW2_TCR1_OT | PCD_DPWW2_TCR1_P | PCD_DPWW2_TCR1_P
| TMS |  | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Treatment for total nitrogen removal (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.12 |  |  | PCD_DPWW2_TNR1_NP | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1_T | PCD_DPWW2_TNR1_T | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_OT | PCD_DPWW2_TNR1_OT | PCD_DPWW2_TNR1_P | PCD_DPWW2_TNR1_P
| TMS |  | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Total number of site treatment solutions delivered to meet compliance | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.13 |  |  | PCD_DPWW2_NBS_SOL_NP | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL_T | PCD_DPWW2_NBS_SOL_T | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_OT | PCD_DPWW2_NBS_SOL_OT | PCD_DPWW2_NBS_SOL_P | PCD_DPWW2_NBS_SOL_P
| TMS |  | PCDWW13a | 0 | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP) | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.14 |  |  | PCD_DPWW2_CS1_NP | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1_T | PCD_DPWW2_CS1_T | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_OT | PCD_DPWW2_CS1_OT | PCD_DPWW2_CS1_P | PCD_DPWW2_CS1_P
| TMS |  | PCDWW13a | 0 | Catchment solutions - Catchment Permitting (WINEP/NEP) | Catchment solutions - Catchment Permitting (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.15 |  |  | PCD_DPWW2_CS2_NP | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2_T | PCD_DPWW2_CS2_T | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_OT | PCD_DPWW2_CS2_OT | PCD_DPWW2_CS2_P | PCD_DPWW2_CS2_P
| TMS |  | PCDWW14 |  | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.16 |  |  | PCD_DPWW2_MBT1_NP | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1_T | PCD_DPWW2_MBT1_T | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_OT | PCD_DPWW2_MBT1_OT | PCD_DPWW2_MBT1_P | PCD_DPWW2_MBT1_P
| TMS |  | PCDWW15 | 0 | Septic tank replacements - treatment solution; (WINEP/NEP) | Total number of septic tank replacement or flow diversion schemes delivered | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.17 |  |  | PCD_DPWW2_STR_NP | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR_T | PCD_DPWW2_STR_T | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_OT | PCD_DPWW2_STR_OT | PCD_DPWW2_STR_P | PCD_DPWW2_STR_P
| TMS |  | PCDWW17 | 0 | 25 year environment plan; (WINEP/NEP) | Number of schemes delivered | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.18 |  |  | PCD_DPWW2_25EP_NP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP_T | PCD_DPWW2_25EP_T | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_OT | PCD_DPWW2_25EP_OT | PCD_DPWW2_25EP_P | PCD_DPWW2_25EP_P
| TMS | PR24CA112 Wastewater Other WINEP | PCDWW18 | Y | WINEP Investigations (wastewater) | Number of satisfactorily completed WINEP / NEP investigations - all categories | £m | 3 | 0.09365 |  | 17.1647 | 33.0977 | 39.359 | 40.227 | 40.3631 | [5 empty] | 40.3631 | 0 | 0 | 0.39325 | 23.1961 | 25.8478 | 28.4627 | 29.3644 | 29.3644 | 29.3644 | 29.3644 | 29.3644 | 29.3644 | 29.3644 | 29.3644 | 72.75% |  | DPWW2.19 |  |  | PCD_DPWW2_WINIVG_NP | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG_T | PCD_DPWW2_WINIVG_T | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_OT | PCD_DPWW2_WINIVG_OT | PCD_DPWW2_WINIVG_P | PCD_DPWW2_WINIVG_P
| TMS |  | PCDWW23a | 0 | Advanced WINEP | Advanced WINEP | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.20 |  |  | PCD_DPWW2_ADWIN1_NP | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1_T | PCD_DPWW2_ADWIN1_T | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_OT | PCD_DPWW2_ADWIN1_OT | PCD_DPWW2_ADWIN1_P | PCD_DPWW2_ADWIN1_P
| TMS |  | PCDWW23b | 0 | Advanced WINEP | Equivalent storage avoided | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.21 |  |  | PCD_DPWW2_ADWIN2_NP | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2_T | PCD_DPWW2_ADWIN2_T | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_OT | PCD_DPWW2_ADWIN2_OT | PCD_DPWW2_ADWIN2_P | PCD_DPWW2_ADWIN2_P
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24a | 0 | Sludge storage -Tanks | Volume of Sludge Storage delivered | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.22 |  |  | PCD_DPWW2_SSTT_NP | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT_T | PCD_DPWW2_SSTT_T | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_OT | PCD_DPWW2_SSTT_OT | PCD_DPWW2_SSTT_P | PCD_DPWW2_SSTT_P
| TMS |  | PCDWW24b | 0 | Sludge storage (cake pads) | Sludge Storage area delivered | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.23 |  |  | PCD_DPWW2_SSCP_NP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP_T | PCD_DPWW2_SSCP_T | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_OT | PCD_DPWW2_SSCP_OT | PCD_DPWW2_SSCP_P | PCD_DPWW2_SSCP_P
| TMS |  | PCDWW25a | 0 | Sludge thickening and dewatering | Tonnes of dry solids/ year | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.24 |  |  | PCD_DPWW2_STDW_NP | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW_T | PCD_DPWW2_STDW_T | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_OT | PCD_DPWW2_STDW_OT | PCD_DPWW2_STDW_P | PCD_DPWW2_STDW_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge throughput Dryer/Pelletiser installed plant capacity | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.25 |  |  | PCD_DPWW2_STOTH1_NP | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1_T | PCD_DPWW2_STOTH1_T | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_OT | PCD_DPWW2_STOTH1_OT | PCD_DPWW2_STOTH1_P | PCD_DPWW2_STOTH1_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge Throughput P Recovery installed plant capacity | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.26 |  |  | PCD_DPWW2_STOTH2_NP | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2_T | PCD_DPWW2_STOTH2_T | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_OT | PCD_DPWW2_STOTH2_OT | PCD_DPWW2_STOTH2_P | PCD_DPWW2_STOTH2_P
| TMS |  | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of sites achieving IED compliance | £m | 3 |  |  | 18.5794 | 36.6273 | 80.8486 | 152.7866 | 290.4916 | [5 empty] | 290.4916 | 0 | 0 | 2.6857 | 20.1125 | 51.1926 | 111.1971 | 187.1411 | 252.7659 | 298.1067 | 370.7528 | 417.3658 | 427.1801 | 187.1411 | 427.1801 | 64.42% |  | DPWW2.27 |  |  | PCD_DPWW2_BIO_IED_NP | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED_T | PCD_DPWW2_BIO_IED_T | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_OT | PCD_DPWW2_BIO_IED_OT | PCD_DPWW2_BIO_IED_P | PCD_DPWW2_BIO_IED_P
| TMS | PR24CA116 Wastewater Other | PCDWW32 | Y | Climate change uplift | Spend on schemes for power and flood resilience delivered: | £m | 3 | 0.31203 |  | 1.2546 | 2.2253 | 7.1047 | 15.2641 | 31.2031 | [5 empty] | 31.2031 | 0 | 0 | 0.29415 | 0.91193 | 4.5254 | 26.4031 | 28.2247 | 28.5279 | 28.5279 | 28.5279 | 28.5279 | 28.5279 | 28.2247 | 28.5279 | 90.45% |  | DPWW2.28 |  |  | PCD_DPWW2_CCUP_NP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP_T | PCD_DPWW2_CCUP_T | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_OT | PCD_DPWW2_CCUP_OT | PCD_DPWW2_CCUP_P | PCD_DPWW2_CCUP_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Coastal Erosion Risk | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.29 |  |  | PCD_DPWW2_CER1_NP | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1_T | PCD_DPWW2_CER1_T | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_OT | PCD_DPWW2_CER1_OT | PCD_DPWW2_CER1_P | PCD_DPWW2_CER1_P
| TMS |  | PCDWW32d | 0 | Infiltration | Total length (in metre) of sewer effectively sealed / lined | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.30 |  |  | PCD_DPWW2_INF_NP | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF_T | PCD_DPWW2_INF_T | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_OT | PCD_DPWW2_INF_OT | PCD_DPWW2_INF_P | PCD_DPWW2_INF_P
| TMS |  | PCDWW32e | 0 | WW Partnership Funding | WW Partnership Funding | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.31 |  |  | PCD_DPWW2_WWPF1_NP | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1_T | PCD_DPWW2_WWPF1_T | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_OT | PCD_DPWW2_WWPF1_OT | PCD_DPWW2_WWPF1_P | PCD_DPWW2_WWPF1_P
| TMS |  | PCDWW32f | 0 | Rainwater management | Rainwater management | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.32 |  |  | PCD_DPWW2_RRM_NP | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM_T | PCD_DPWW2_RRM_T | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_OT | PCD_DPWW2_RRM_OT | PCD_DPWW2_RRM_P | PCD_DPWW2_RRM_P
| TMS |  | PCDWW32g | 0 | Flood and power | Flooding resilience scheme unit rate | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.33 |  |  | PCD_DPWW2_FP_NP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP_T | PCD_DPWW2_FP_T | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_OT | PCD_DPWW2_FP_OT | PCD_DPWW2_FP_P | PCD_DPWW2_FP_P
| TMS |  | PCDWW32g | 0 | Flood and power | Power resilience scheme unit rate | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.34 |  |  | PCD_DPWW2_FP1_NP | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1_T | PCD_DPWW2_FP1_T | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_OT | PCD_DPWW2_FP1_OT | PCD_DPWW2_FP1_P | PCD_DPWW2_FP1_P
| TMS |  | PCDWW29 | 0 | First time sewerage | Number of connected properties served by S101A schemes | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.35 |  |  | PCD_DPWW2_FTS_NP | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS_T | PCD_DPWW2_FTS_T | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_OT | PCD_DPWW2_FTS_OT | PCD_DPWW2_FTS_P | PCD_DPWW2_FTS_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW36 | 0 | PR19 Green recovery carryover | PR19 Green recovery carryover | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.36 |  |  | PCD_DPWW2_PR19GRC_NP | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC_T | PCD_DPWW2_PR19GRC_T | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_OT | PCD_DPWW2_PR19GRC_OT | PCD_DPWW2_PR19GRC_P | PCD_DPWW2_PR19GRC_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows | Equivalent storage | £m | 3 |  |  | 18.7044 | 36.7306 | 107.9232 | 253.5419 | 521.4971 | [5 empty] | 521.4971 | 0 | 0 | 13.4138 | 50.6767 | 135.2456 | 364.8899 | 539.5852 | 551.8582 | 552.9837 | 552.9837 | 552.9837 | 552.9837 | 539.5852 | 552.9837 | 103.5% |  | DPWW2.37 |  |  | PCD_DPWW2_SOFES_NP | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES_T | PCD_DPWW2_SOFES_T | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_OT | PCD_DPWW2_SOFES_OT | PCD_DPWW2_SOFES_P | PCD_DPWW2_SOFES_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | litres per second | £m | 3 |  |  | 4.8532 | 9.5304 | 28.0025 | 65.7859 | 135.3115 | [5 empty] | 135.3115 | 0 | 0 | 1.0869 | 3.5764 | 12.8964 | 64.2148 | 124.4539 | 129.8484 | 130.356 | 130.356 | 130.356 | 130.356 | 124.4539 | 130.356 | 91.98% |  | DPWW2.38 |  |  | PCD_DPWW2_FTFT_NP | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT_T | PCD_DPWW2_FTFT_T | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_OT | PCD_DPWW2_FTFT_OT | PCD_DPWW2_FTFT_P | PCD_DPWW2_FTFT_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Population equivalent served | £m | 3 |  |  | 26.1686 | 64.2431 | 231.8319 | 594.7064 | 1183.2158 | [5 empty] | 1183.2158 | 0 | 0 | 24.7863 | 111.3063 | 272.2784 | 719.9538 | 993.7957 | 1154.123 | 1248.6534 | 1272.5443 | 1278.3424 | 1278.9117 | 993.7957 | 1278.9117 | 83.99% |  | DPWW2.39 |  |  | PCD_DPWW2_PRMVL_NP | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL_T | PCD_DPWW2_PRMVL_T | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_OT | PCD_DPWW2_PRMVL_OT | PCD_DPWW2_PRMVL_P | PCD_DPWW2_PRMVL_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Added Process Capacity in PE | £m | 3 |  |  | 0 | 0 | 0 | 51.664 | 172.9 | [5 empty] | 172.9 | 0 | 0 | 4.3122 | 28.7012 | 74.6741 | 196.1264 | 280.1188 | 339.8374 | 387.2904 | 432.5825 | 432.7223 | 432.7223 | 280.1188 | 432.7223 | 162% |  | DPWW2.40 |  |  | PCD_DPWW2_GSTW_NP | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW_T | PCD_DPWW2_GSTW_T | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_OT | PCD_DPWW2_GSTW_OT | PCD_DPWW2_GSTW_P | PCD_DPWW2_GSTW_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Population equivalent served | £m | 3 |  |  | 31.5783 | 61.5704 | 62.1922 | 62.8826 | 68.9935 | [5 empty] | 68.9935 | 0 | 0 | 15.4167 | 28.5308 | 40.8871 | 67.0129 | 77.4824 | 79.9768 | 82.0272 | 83.5591 | 83.9328 | 84.0064 | 77.4824 | 84.0064 | 112.3% |  | DPWW2.41 |  |  | PCD_DPWW2_TTSP_NP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP_T | PCD_DPWW2_TTSP_T | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_OT | PCD_DPWW2_TTSP_OT | PCD_DPWW2_TTSP_P | PCD_DPWW2_TTSP_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes | £m | 3 |  |  | 201.3239 | 402.6477 | 603.9716 | 805.2955 | 1006.6194 | [5 empty] | 1006.6194 | 0 | 134.4761 | 194.337 | 323.7492 | 552.1707 | 776.6019 | 923.2801 | 983.6342 | 1026.3073 | 1035.1271 | 1035.1271 | 1035.1271 | 923.2801 | 1035.1271 | 91.72% |  | DPWW2.42 |  |  | PCD_DPWW2_PR19WINCA_NP | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA_T | PCD_DPWW2_PR19WINCA_T | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_OT | PCD_DPWW2_PR19WINCA_OT | PCD_DPWW2_PR19WINCA_P | PCD_DPWW2_PR19WINCA_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | tCO2e/Number of sites | £m | 3 | [12 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPWW2.43 |  |  | PCD_DPWW2_GGR1_NP | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1_T | PCD_DPWW2_GGR1_T | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_OT | PCD_DPWW2_GGR1_OT | PCD_DPWW2_GGR1_P | PCD_DPWW2_GGR1_P
[21 empty] | 0 | 0 | [11 empty] | 0 | 0
| 0 |  |  |  | Total other non - PCD enhancement wastewater/bioresources expenditure, totex | Total other non - PCD enhancement wastewater/bioresources expenditure, totex | £m | 3 | [12 empty] | 0 | 0 | 186.902 | 443.3964 | 667.0377 | 981.281 | 1201.9849 | 1647.8499 | 1843.189 | 1880.4465 | 1899.7175 | 1921.407 | 1927.5534 | 1647.8499 | 1927.5534 |  |  | DPWW2.44 |  |  | PCD_DPWW2_OTH1_NP | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1_T | PCD_DPWW2_OTH1_T | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_OT | PCD_DPWW2_OTH1_OT | PCD_DPWW2_OTH1_P | PCD_DPWW2_OTH1_P
| 0 |  |  |  | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex | £m | 3 |  |  | 326.0249 | 659.2458 | 1202.9312 | 2150.3344 | 3712.2023 | 0 | 0 | 0 | 0 | 0 | 3712.2023 | 0 | 321.3781 | 711.2799 | 1284.656 | 2196.7027 | 3647.1281 | 4980.8339 | 5563.4584 | 5856.8748 | 6040.47 | 6117.1363 | 6134.2077 | 4980.8339 | 6134.2077 | 134.2% |  | DPWW2.45 |  |  | PCD_DPWW2_OTH2_NP | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2_T | PCD_DPWW2_OTH2_T | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_OT | PCD_DPWW2_OTH2_OT | PCD_DPWW2_OTH2_P | PCD_DPWW2_OTH2_P
[39 empty] | End_Data | [30 empty] | End_BON

## DPWW3
DPWW3
Interim Milestones - Wastewater - Programme level
| Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | Number of Schemes (Nr) | [21 empty] | Total number of schemes with a 90+ day delay for any given IM | Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category | [10 empty] | DP reference |  |  | Number of Schemes (Nr) | IM1 has yet to be achieved | [20 empty] | Total number of schemes with a 90+ day delay for any given IM | Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category
Data_Start | [9 empty] | Pre 2025-26 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 |  | Lack of internal resourcing | Lack of supply chain resourcing | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency |  |  | BON_Start | Constant | 2024-25 Q4 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | Conatant | Lack of internal resourcing | Lack of supply chain resourcing | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 0 | Nr | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | PCD_DPWW3_SOW1 | PCD_DPWW3_SOW1_NR | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_DLY | PCD_DPWW3_SOW1_DIR | PCD_DPWW3_SOW1_DSCR | PCD_DPWW3_SOW1_DCS | PCD_DPWW3_SOW1_DSCS | PCD_DPWW3_SOW1_DPP | PCD_DPWW3_SOW1_DTPI | PCD_DPWW3_SOW1_DCI | PCD_DPWW3_SOW1_DSI | PCD_DPWW3_SOW1_DER | PCD_DPWW3_SOW1_RS | PCD_DPWW3_SOW1_DPLE
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 1 | Nr | 0 |  | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S1 |  | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_DLY_S1 | PCD_DPWW3_SOW1_DIR_S1 | PCD_DPWW3_SOW1_DSCR_S1 | PCD_DPWW3_SOW1_DCS_S1 | PCD_DPWW3_SOW1_DSCS_S1 | PCD_DPWW3_SOW1_DPP_S1 | PCD_DPWW3_SOW1_DTPI_S1 | PCD_DPWW3_SOW1_DCI_S1 | PCD_DPWW3_SOW1_DSI_S1 | PCD_DPWW3_SOW1_DER_S1 | PCD_DPWW3_SOW1_RS_S1 | PCD_DPWW3_SOW1_DPLE_S1
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S2 |  | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_DLY_S2 | PCD_DPWW3_SOW1_DIR_S2 | PCD_DPWW3_SOW1_DSCR_S2 | PCD_DPWW3_SOW1_DCS_S2 | PCD_DPWW3_SOW1_DSCS_S2 | PCD_DPWW3_SOW1_DPP_S2 | PCD_DPWW3_SOW1_DTPI_S2 | PCD_DPWW3_SOW1_DCI_S2 | PCD_DPWW3_SOW1_DSI_S2 | PCD_DPWW3_SOW1_DER_S2 | PCD_DPWW3_SOW1_RS_S2 | PCD_DPWW3_SOW1_DPLE_S2
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S3 |  | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_DLY_S3 | PCD_DPWW3_SOW1_DIR_S3 | PCD_DPWW3_SOW1_DSCR_S3 | PCD_DPWW3_SOW1_DCS_S3 | PCD_DPWW3_SOW1_DSCS_S3 | PCD_DPWW3_SOW1_DPP_S3 | PCD_DPWW3_SOW1_DTPI_S3 | PCD_DPWW3_SOW1_DCI_S3 | PCD_DPWW3_SOW1_DSI_S3 | PCD_DPWW3_SOW1_DER_S3 | PCD_DPWW3_SOW1_RS_S3 | PCD_DPWW3_SOW1_DPLE_S3
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 1 | [12 empty] | DPWW3.1 |  | _S4 |  | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_DLY_S4 | PCD_DPWW3_SOW1_DIR_S4 | PCD_DPWW3_SOW1_DSCR_S4 | PCD_DPWW3_SOW1_DCS_S4 | PCD_DPWW3_SOW1_DSCS_S4 | PCD_DPWW3_SOW1_DPP_S4 | PCD_DPWW3_SOW1_DTPI_S4 | PCD_DPWW3_SOW1_DCI_S4 | PCD_DPWW3_SOW1_DSI_S4 | PCD_DPWW3_SOW1_DER_S4 | PCD_DPWW3_SOW1_RS_S4 | PCD_DPWW3_SOW1_DPLE_S4
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | [12 empty] | DPWW3.1 |  | _S5 |  | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_DLY_S5 | PCD_DPWW3_SOW1_DIR_S5 | PCD_DPWW3_SOW1_DSCR_S5 | PCD_DPWW3_SOW1_DCS_S5 | PCD_DPWW3_SOW1_DSCS_S5 | PCD_DPWW3_SOW1_DPP_S5 | PCD_DPWW3_SOW1_DTPI_S5 | PCD_DPWW3_SOW1_DCI_S5 | PCD_DPWW3_SOW1_DSI_S5 | PCD_DPWW3_SOW1_DER_S5 | PCD_DPWW3_SOW1_RS_S5 | PCD_DPWW3_SOW1_DPLE_S5
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 1 | [10 empty] | 1 | DPWW3.1 |  | _S6 |  | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_DLY_S6 | PCD_DPWW3_SOW1_DIR_S6 | PCD_DPWW3_SOW1_DSCR_S6 | PCD_DPWW3_SOW1_DCS_S6 | PCD_DPWW3_SOW1_DSCS_S6 | PCD_DPWW3_SOW1_DPP_S6 | PCD_DPWW3_SOW1_DTPI_S6 | PCD_DPWW3_SOW1_DCI_S6 | PCD_DPWW3_SOW1_DSI_S6 | PCD_DPWW3_SOW1_DER_S6 | PCD_DPWW3_SOW1_RS_S6 | PCD_DPWW3_SOW1_DPLE_S6
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S7 |  | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_DLY_S7 | PCD_DPWW3_SOW1_DIR_S7 | PCD_DPWW3_SOW1_DSCR_S7 | PCD_DPWW3_SOW1_DCS_S7 | PCD_DPWW3_SOW1_DSCS_S7 | PCD_DPWW3_SOW1_DPP_S7 | PCD_DPWW3_SOW1_DTPI_S7 | PCD_DPWW3_SOW1_DCI_S7 | PCD_DPWW3_SOW1_DSI_S7 | PCD_DPWW3_SOW1_DER_S7 | PCD_DPWW3_SOW1_RS_S7 | PCD_DPWW3_SOW1_DPLE_S7
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [12 empty] | DPWW3.1 |  | _ST |  | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_DLY_ST | PCD_DPWW3_SOW1_DIR_ST | PCD_DPWW3_SOW1_DSCR_ST | PCD_DPWW3_SOW1_DCS_ST | PCD_DPWW3_SOW1_DSCS_ST | PCD_DPWW3_SOW1_DPP_ST | PCD_DPWW3_SOW1_DTPI_ST | PCD_DPWW3_SOW1_DCI_ST | PCD_DPWW3_SOW1_DSI_ST | PCD_DPWW3_SOW1_DER_ST | PCD_DPWW3_SOW1_RS_ST | PCD_DPWW3_SOW1_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | PCD_DPWW3_TCR1 | PCD_DPWW3_TCR1_NR | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_DLY | PCD_DPWW3_TCR1_DIR | PCD_DPWW3_TCR1_DSCR | PCD_DPWW3_TCR1_DCS | PCD_DPWW3_TCR1_DSCS | PCD_DPWW3_TCR1_DPP | PCD_DPWW3_TCR1_DTPI | PCD_DPWW3_TCR1_DCI | PCD_DPWW3_TCR1_DSI | PCD_DPWW3_TCR1_DER | PCD_DPWW3_TCR1_RS | PCD_DPWW3_TCR1_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 7 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | _S1 |  | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_DLY_S1 | PCD_DPWW3_TCR1_DIR_S1 | PCD_DPWW3_TCR1_DSCR_S1 | PCD_DPWW3_TCR1_DCS_S1 | PCD_DPWW3_TCR1_DSCS_S1 | PCD_DPWW3_TCR1_DPP_S1 | PCD_DPWW3_TCR1_DTPI_S1 | PCD_DPWW3_TCR1_DCI_S1 | PCD_DPWW3_TCR1_DSI_S1 | PCD_DPWW3_TCR1_DER_S1 | PCD_DPWW3_TCR1_RS_S1 | PCD_DPWW3_TCR1_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | _S2 |  | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_DLY_S2 | PCD_DPWW3_TCR1_DIR_S2 | PCD_DPWW3_TCR1_DSCR_S2 | PCD_DPWW3_TCR1_DCS_S2 | PCD_DPWW3_TCR1_DSCS_S2 | PCD_DPWW3_TCR1_DPP_S2 | PCD_DPWW3_TCR1_DTPI_S2 | PCD_DPWW3_TCR1_DCI_S2 | PCD_DPWW3_TCR1_DSI_S2 | PCD_DPWW3_TCR1_DER_S2 | PCD_DPWW3_TCR1_RS_S2 | PCD_DPWW3_TCR1_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | _S3 |  | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_DLY_S3 | PCD_DPWW3_TCR1_DIR_S3 | PCD_DPWW3_TCR1_DSCR_S3 | PCD_DPWW3_TCR1_DCS_S3 | PCD_DPWW3_TCR1_DSCS_S3 | PCD_DPWW3_TCR1_DPP_S3 | PCD_DPWW3_TCR1_DTPI_S3 | PCD_DPWW3_TCR1_DCI_S3 | PCD_DPWW3_TCR1_DSI_S3 | PCD_DPWW3_TCR1_DER_S3 | PCD_DPWW3_TCR1_RS_S3 | PCD_DPWW3_TCR1_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 5 | 6 | 6 | 5 | [12 empty] | DPWW3.2 |  | _S4 |  | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_DLY_S4 | PCD_DPWW3_TCR1_DIR_S4 | PCD_DPWW3_TCR1_DSCR_S4 | PCD_DPWW3_TCR1_DCS_S4 | PCD_DPWW3_TCR1_DSCS_S4 | PCD_DPWW3_TCR1_DPP_S4 | PCD_DPWW3_TCR1_DTPI_S4 | PCD_DPWW3_TCR1_DCI_S4 | PCD_DPWW3_TCR1_DSI_S4 | PCD_DPWW3_TCR1_DER_S4 | PCD_DPWW3_TCR1_RS_S4 | PCD_DPWW3_TCR1_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | [12 empty] | DPWW3.2 |  | _S5 |  | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_DLY_S5 | PCD_DPWW3_TCR1_DIR_S5 | PCD_DPWW3_TCR1_DSCR_S5 | PCD_DPWW3_TCR1_DCS_S5 | PCD_DPWW3_TCR1_DSCS_S5 | PCD_DPWW3_TCR1_DPP_S5 | PCD_DPWW3_TCR1_DTPI_S5 | PCD_DPWW3_TCR1_DCI_S5 | PCD_DPWW3_TCR1_DSI_S5 | PCD_DPWW3_TCR1_DER_S5 | PCD_DPWW3_TCR1_RS_S5 | PCD_DPWW3_TCR1_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | _S6 |  | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_DLY_S6 | PCD_DPWW3_TCR1_DIR_S6 | PCD_DPWW3_TCR1_DSCR_S6 | PCD_DPWW3_TCR1_DCS_S6 | PCD_DPWW3_TCR1_DSCS_S6 | PCD_DPWW3_TCR1_DPP_S6 | PCD_DPWW3_TCR1_DTPI_S6 | PCD_DPWW3_TCR1_DCI_S6 | PCD_DPWW3_TCR1_DSI_S6 | PCD_DPWW3_TCR1_DER_S6 | PCD_DPWW3_TCR1_RS_S6 | PCD_DPWW3_TCR1_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | _S7 |  | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_DLY_S7 | PCD_DPWW3_TCR1_DIR_S7 | PCD_DPWW3_TCR1_DSCR_S7 | PCD_DPWW3_TCR1_DCS_S7 | PCD_DPWW3_TCR1_DSCS_S7 | PCD_DPWW3_TCR1_DPP_S7 | PCD_DPWW3_TCR1_DTPI_S7 | PCD_DPWW3_TCR1_DCI_S7 | PCD_DPWW3_TCR1_DSI_S7 | PCD_DPWW3_TCR1_DER_S7 | PCD_DPWW3_TCR1_RS_S7 | PCD_DPWW3_TCR1_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [12 empty] | DPWW3.2 |  | _ST |  | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_DLY_ST | PCD_DPWW3_TCR1_DIR_ST | PCD_DPWW3_TCR1_DSCR_ST | PCD_DPWW3_TCR1_DCS_ST | PCD_DPWW3_TCR1_DSCS_ST | PCD_DPWW3_TCR1_DPP_ST | PCD_DPWW3_TCR1_DTPI_ST | PCD_DPWW3_TCR1_DCI_ST | PCD_DPWW3_TCR1_DSI_ST | PCD_DPWW3_TCR1_DER_ST | PCD_DPWW3_TCR1_RS_ST | PCD_DPWW3_TCR1_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | PCD_DPWW3_TNR1 | PCD_DPWW3_TNR1_NR | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_DLY | PCD_DPWW3_TNR1_DIR | PCD_DPWW3_TNR1_DSCR | PCD_DPWW3_TNR1_DCS | PCD_DPWW3_TNR1_DSCS | PCD_DPWW3_TNR1_DPP | PCD_DPWW3_TNR1_DTPI | PCD_DPWW3_TNR1_DCI | PCD_DPWW3_TNR1_DSI | PCD_DPWW3_TNR1_DER | PCD_DPWW3_TNR1_RS | PCD_DPWW3_TNR1_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S1 |  | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_DLY_S1 | PCD_DPWW3_TNR1_DIR_S1 | PCD_DPWW3_TNR1_DSCR_S1 | PCD_DPWW3_TNR1_DCS_S1 | PCD_DPWW3_TNR1_DSCS_S1 | PCD_DPWW3_TNR1_DPP_S1 | PCD_DPWW3_TNR1_DTPI_S1 | PCD_DPWW3_TNR1_DCI_S1 | PCD_DPWW3_TNR1_DSI_S1 | PCD_DPWW3_TNR1_DER_S1 | PCD_DPWW3_TNR1_RS_S1 | PCD_DPWW3_TNR1_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S2 |  | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_DLY_S2 | PCD_DPWW3_TNR1_DIR_S2 | PCD_DPWW3_TNR1_DSCR_S2 | PCD_DPWW3_TNR1_DCS_S2 | PCD_DPWW3_TNR1_DSCS_S2 | PCD_DPWW3_TNR1_DPP_S2 | PCD_DPWW3_TNR1_DTPI_S2 | PCD_DPWW3_TNR1_DCI_S2 | PCD_DPWW3_TNR1_DSI_S2 | PCD_DPWW3_TNR1_DER_S2 | PCD_DPWW3_TNR1_RS_S2 | PCD_DPWW3_TNR1_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S3 |  | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_DLY_S3 | PCD_DPWW3_TNR1_DIR_S3 | PCD_DPWW3_TNR1_DSCR_S3 | PCD_DPWW3_TNR1_DCS_S3 | PCD_DPWW3_TNR1_DSCS_S3 | PCD_DPWW3_TNR1_DPP_S3 | PCD_DPWW3_TNR1_DTPI_S3 | PCD_DPWW3_TNR1_DCI_S3 | PCD_DPWW3_TNR1_DSI_S3 | PCD_DPWW3_TNR1_DER_S3 | PCD_DPWW3_TNR1_RS_S3 | PCD_DPWW3_TNR1_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S4 |  | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_DLY_S4 | PCD_DPWW3_TNR1_DIR_S4 | PCD_DPWW3_TNR1_DSCR_S4 | PCD_DPWW3_TNR1_DCS_S4 | PCD_DPWW3_TNR1_DSCS_S4 | PCD_DPWW3_TNR1_DPP_S4 | PCD_DPWW3_TNR1_DTPI_S4 | PCD_DPWW3_TNR1_DCI_S4 | PCD_DPWW3_TNR1_DSI_S4 | PCD_DPWW3_TNR1_DER_S4 | PCD_DPWW3_TNR1_RS_S4 | PCD_DPWW3_TNR1_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S5 |  | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_DLY_S5 | PCD_DPWW3_TNR1_DIR_S5 | PCD_DPWW3_TNR1_DSCR_S5 | PCD_DPWW3_TNR1_DCS_S5 | PCD_DPWW3_TNR1_DSCS_S5 | PCD_DPWW3_TNR1_DPP_S5 | PCD_DPWW3_TNR1_DTPI_S5 | PCD_DPWW3_TNR1_DCI_S5 | PCD_DPWW3_TNR1_DSI_S5 | PCD_DPWW3_TNR1_DER_S5 | PCD_DPWW3_TNR1_RS_S5 | PCD_DPWW3_TNR1_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S6 |  | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_DLY_S6 | PCD_DPWW3_TNR1_DIR_S6 | PCD_DPWW3_TNR1_DSCR_S6 | PCD_DPWW3_TNR1_DCS_S6 | PCD_DPWW3_TNR1_DSCS_S6 | PCD_DPWW3_TNR1_DPP_S6 | PCD_DPWW3_TNR1_DTPI_S6 | PCD_DPWW3_TNR1_DCI_S6 | PCD_DPWW3_TNR1_DSI_S6 | PCD_DPWW3_TNR1_DER_S6 | PCD_DPWW3_TNR1_RS_S6 | PCD_DPWW3_TNR1_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S7 |  | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_DLY_S7 | PCD_DPWW3_TNR1_DIR_S7 | PCD_DPWW3_TNR1_DSCR_S7 | PCD_DPWW3_TNR1_DCS_S7 | PCD_DPWW3_TNR1_DSCS_S7 | PCD_DPWW3_TNR1_DPP_S7 | PCD_DPWW3_TNR1_DTPI_S7 | PCD_DPWW3_TNR1_DCI_S7 | PCD_DPWW3_TNR1_DSI_S7 | PCD_DPWW3_TNR1_DER_S7 | PCD_DPWW3_TNR1_RS_S7 | PCD_DPWW3_TNR1_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _ST |  | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_DLY_ST | PCD_DPWW3_TNR1_DIR_ST | PCD_DPWW3_TNR1_DSCR_ST | PCD_DPWW3_TNR1_DCS_ST | PCD_DPWW3_TNR1_DSCS_ST | PCD_DPWW3_TNR1_DPP_ST | PCD_DPWW3_TNR1_DTPI_ST | PCD_DPWW3_TNR1_DCI_ST | PCD_DPWW3_TNR1_DSI_ST | PCD_DPWW3_TNR1_DER_ST | PCD_DPWW3_TNR1_RS_ST | PCD_DPWW3_TNR1_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | PCD_DPWW3_NBS_SOL | PCD_DPWW3_NBS_SOL_NR | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_DLY | PCD_DPWW3_NBS_SOL_DIR | PCD_DPWW3_NBS_SOL_DSCR | PCD_DPWW3_NBS_SOL_DCS | PCD_DPWW3_NBS_SOL_DSCS | PCD_DPWW3_NBS_SOL_DPP | PCD_DPWW3_NBS_SOL_DTPI | PCD_DPWW3_NBS_SOL_DCI | PCD_DPWW3_NBS_SOL_DSI | PCD_DPWW3_NBS_SOL_DER | PCD_DPWW3_NBS_SOL_RS | PCD_DPWW3_NBS_SOL_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S1 |  | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_DLY_S1 | PCD_DPWW3_NBS_SOL_DIR_S1 | PCD_DPWW3_NBS_SOL_DSCR_S1 | PCD_DPWW3_NBS_SOL_DCS_S1 | PCD_DPWW3_NBS_SOL_DSCS_S1 | PCD_DPWW3_NBS_SOL_DPP_S1 | PCD_DPWW3_NBS_SOL_DTPI_S1 | PCD_DPWW3_NBS_SOL_DCI_S1 | PCD_DPWW3_NBS_SOL_DSI_S1 | PCD_DPWW3_NBS_SOL_DER_S1 | PCD_DPWW3_NBS_SOL_RS_S1 | PCD_DPWW3_NBS_SOL_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S2 |  | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_DLY_S2 | PCD_DPWW3_NBS_SOL_DIR_S2 | PCD_DPWW3_NBS_SOL_DSCR_S2 | PCD_DPWW3_NBS_SOL_DCS_S2 | PCD_DPWW3_NBS_SOL_DSCS_S2 | PCD_DPWW3_NBS_SOL_DPP_S2 | PCD_DPWW3_NBS_SOL_DTPI_S2 | PCD_DPWW3_NBS_SOL_DCI_S2 | PCD_DPWW3_NBS_SOL_DSI_S2 | PCD_DPWW3_NBS_SOL_DER_S2 | PCD_DPWW3_NBS_SOL_RS_S2 | PCD_DPWW3_NBS_SOL_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S3 |  | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_DLY_S3 | PCD_DPWW3_NBS_SOL_DIR_S3 | PCD_DPWW3_NBS_SOL_DSCR_S3 | PCD_DPWW3_NBS_SOL_DCS_S3 | PCD_DPWW3_NBS_SOL_DSCS_S3 | PCD_DPWW3_NBS_SOL_DPP_S3 | PCD_DPWW3_NBS_SOL_DTPI_S3 | PCD_DPWW3_NBS_SOL_DCI_S3 | PCD_DPWW3_NBS_SOL_DSI_S3 | PCD_DPWW3_NBS_SOL_DER_S3 | PCD_DPWW3_NBS_SOL_RS_S3 | PCD_DPWW3_NBS_SOL_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S4 |  | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_DLY_S4 | PCD_DPWW3_NBS_SOL_DIR_S4 | PCD_DPWW3_NBS_SOL_DSCR_S4 | PCD_DPWW3_NBS_SOL_DCS_S4 | PCD_DPWW3_NBS_SOL_DSCS_S4 | PCD_DPWW3_NBS_SOL_DPP_S4 | PCD_DPWW3_NBS_SOL_DTPI_S4 | PCD_DPWW3_NBS_SOL_DCI_S4 | PCD_DPWW3_NBS_SOL_DSI_S4 | PCD_DPWW3_NBS_SOL_DER_S4 | PCD_DPWW3_NBS_SOL_RS_S4 | PCD_DPWW3_NBS_SOL_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S5 |  | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_DLY_S5 | PCD_DPWW3_NBS_SOL_DIR_S5 | PCD_DPWW3_NBS_SOL_DSCR_S5 | PCD_DPWW3_NBS_SOL_DCS_S5 | PCD_DPWW3_NBS_SOL_DSCS_S5 | PCD_DPWW3_NBS_SOL_DPP_S5 | PCD_DPWW3_NBS_SOL_DTPI_S5 | PCD_DPWW3_NBS_SOL_DCI_S5 | PCD_DPWW3_NBS_SOL_DSI_S5 | PCD_DPWW3_NBS_SOL_DER_S5 | PCD_DPWW3_NBS_SOL_RS_S5 | PCD_DPWW3_NBS_SOL_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S6 |  | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_DLY_S6 | PCD_DPWW3_NBS_SOL_DIR_S6 | PCD_DPWW3_NBS_SOL_DSCR_S6 | PCD_DPWW3_NBS_SOL_DCS_S6 | PCD_DPWW3_NBS_SOL_DSCS_S6 | PCD_DPWW3_NBS_SOL_DPP_S6 | PCD_DPWW3_NBS_SOL_DTPI_S6 | PCD_DPWW3_NBS_SOL_DCI_S6 | PCD_DPWW3_NBS_SOL_DSI_S6 | PCD_DPWW3_NBS_SOL_DER_S6 | PCD_DPWW3_NBS_SOL_RS_S6 | PCD_DPWW3_NBS_SOL_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S7 |  | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_DLY_S7 | PCD_DPWW3_NBS_SOL_DIR_S7 | PCD_DPWW3_NBS_SOL_DSCR_S7 | PCD_DPWW3_NBS_SOL_DCS_S7 | PCD_DPWW3_NBS_SOL_DSCS_S7 | PCD_DPWW3_NBS_SOL_DPP_S7 | PCD_DPWW3_NBS_SOL_DTPI_S7 | PCD_DPWW3_NBS_SOL_DCI_S7 | PCD_DPWW3_NBS_SOL_DSI_S7 | PCD_DPWW3_NBS_SOL_DER_S7 | PCD_DPWW3_NBS_SOL_RS_S7 | PCD_DPWW3_NBS_SOL_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _ST |  | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_DLY_ST | PCD_DPWW3_NBS_SOL_DIR_ST | PCD_DPWW3_NBS_SOL_DSCR_ST | PCD_DPWW3_NBS_SOL_DCS_ST | PCD_DPWW3_NBS_SOL_DSCS_ST | PCD_DPWW3_NBS_SOL_DPP_ST | PCD_DPWW3_NBS_SOL_DTPI_ST | PCD_DPWW3_NBS_SOL_DCI_ST | PCD_DPWW3_NBS_SOL_DSI_ST | PCD_DPWW3_NBS_SOL_DER_ST | PCD_DPWW3_NBS_SOL_RS_ST | PCD_DPWW3_NBS_SOL_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | PCD_DPWW3_MBT1 | PCD_DPWW3_MBT1_NR | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_DLY | PCD_DPWW3_MBT1_DIR | PCD_DPWW3_MBT1_DSCR | PCD_DPWW3_MBT1_DCS | PCD_DPWW3_MBT1_DSCS | PCD_DPWW3_MBT1_DPP | PCD_DPWW3_MBT1_DTPI | PCD_DPWW3_MBT1_DCI | PCD_DPWW3_MBT1_DSI | PCD_DPWW3_MBT1_DER | PCD_DPWW3_MBT1_RS | PCD_DPWW3_MBT1_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S1 |  | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_DLY_S1 | PCD_DPWW3_MBT1_DIR_S1 | PCD_DPWW3_MBT1_DSCR_S1 | PCD_DPWW3_MBT1_DCS_S1 | PCD_DPWW3_MBT1_DSCS_S1 | PCD_DPWW3_MBT1_DPP_S1 | PCD_DPWW3_MBT1_DTPI_S1 | PCD_DPWW3_MBT1_DCI_S1 | PCD_DPWW3_MBT1_DSI_S1 | PCD_DPWW3_MBT1_DER_S1 | PCD_DPWW3_MBT1_RS_S1 | PCD_DPWW3_MBT1_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S2 |  | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_DLY_S2 | PCD_DPWW3_MBT1_DIR_S2 | PCD_DPWW3_MBT1_DSCR_S2 | PCD_DPWW3_MBT1_DCS_S2 | PCD_DPWW3_MBT1_DSCS_S2 | PCD_DPWW3_MBT1_DPP_S2 | PCD_DPWW3_MBT1_DTPI_S2 | PCD_DPWW3_MBT1_DCI_S2 | PCD_DPWW3_MBT1_DSI_S2 | PCD_DPWW3_MBT1_DER_S2 | PCD_DPWW3_MBT1_RS_S2 | PCD_DPWW3_MBT1_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S3 |  | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_DLY_S3 | PCD_DPWW3_MBT1_DIR_S3 | PCD_DPWW3_MBT1_DSCR_S3 | PCD_DPWW3_MBT1_DCS_S3 | PCD_DPWW3_MBT1_DSCS_S3 | PCD_DPWW3_MBT1_DPP_S3 | PCD_DPWW3_MBT1_DTPI_S3 | PCD_DPWW3_MBT1_DCI_S3 | PCD_DPWW3_MBT1_DSI_S3 | PCD_DPWW3_MBT1_DER_S3 | PCD_DPWW3_MBT1_RS_S3 | PCD_DPWW3_MBT1_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S4 |  | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_DLY_S4 | PCD_DPWW3_MBT1_DIR_S4 | PCD_DPWW3_MBT1_DSCR_S4 | PCD_DPWW3_MBT1_DCS_S4 | PCD_DPWW3_MBT1_DSCS_S4 | PCD_DPWW3_MBT1_DPP_S4 | PCD_DPWW3_MBT1_DTPI_S4 | PCD_DPWW3_MBT1_DCI_S4 | PCD_DPWW3_MBT1_DSI_S4 | PCD_DPWW3_MBT1_DER_S4 | PCD_DPWW3_MBT1_RS_S4 | PCD_DPWW3_MBT1_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S5 |  | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_DLY_S5 | PCD_DPWW3_MBT1_DIR_S5 | PCD_DPWW3_MBT1_DSCR_S5 | PCD_DPWW3_MBT1_DCS_S5 | PCD_DPWW3_MBT1_DSCS_S5 | PCD_DPWW3_MBT1_DPP_S5 | PCD_DPWW3_MBT1_DTPI_S5 | PCD_DPWW3_MBT1_DCI_S5 | PCD_DPWW3_MBT1_DSI_S5 | PCD_DPWW3_MBT1_DER_S5 | PCD_DPWW3_MBT1_RS_S5 | PCD_DPWW3_MBT1_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S6 |  | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_DLY_S6 | PCD_DPWW3_MBT1_DIR_S6 | PCD_DPWW3_MBT1_DSCR_S6 | PCD_DPWW3_MBT1_DCS_S6 | PCD_DPWW3_MBT1_DSCS_S6 | PCD_DPWW3_MBT1_DPP_S6 | PCD_DPWW3_MBT1_DTPI_S6 | PCD_DPWW3_MBT1_DCI_S6 | PCD_DPWW3_MBT1_DSI_S6 | PCD_DPWW3_MBT1_DER_S6 | PCD_DPWW3_MBT1_RS_S6 | PCD_DPWW3_MBT1_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S7 |  | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_DLY_S7 | PCD_DPWW3_MBT1_DIR_S7 | PCD_DPWW3_MBT1_DSCR_S7 | PCD_DPWW3_MBT1_DCS_S7 | PCD_DPWW3_MBT1_DSCS_S7 | PCD_DPWW3_MBT1_DPP_S7 | PCD_DPWW3_MBT1_DTPI_S7 | PCD_DPWW3_MBT1_DCI_S7 | PCD_DPWW3_MBT1_DSI_S7 | PCD_DPWW3_MBT1_DER_S7 | PCD_DPWW3_MBT1_RS_S7 | PCD_DPWW3_MBT1_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _ST |  | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_DLY_ST | PCD_DPWW3_MBT1_DIR_ST | PCD_DPWW3_MBT1_DSCR_ST | PCD_DPWW3_MBT1_DCS_ST | PCD_DPWW3_MBT1_DSCS_ST | PCD_DPWW3_MBT1_DPP_ST | PCD_DPWW3_MBT1_DTPI_ST | PCD_DPWW3_MBT1_DCI_ST | PCD_DPWW3_MBT1_DSI_ST | PCD_DPWW3_MBT1_DER_ST | PCD_DPWW3_MBT1_RS_ST | PCD_DPWW3_MBT1_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | PCD_DPWW3_SSCP | PCD_DPWW3_SSCP_NR | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_DLY | PCD_DPWW3_SSCP_DIR | PCD_DPWW3_SSCP_DSCR | PCD_DPWW3_SSCP_DCS | PCD_DPWW3_SSCP_DSCS | PCD_DPWW3_SSCP_DPP | PCD_DPWW3_SSCP_DTPI | PCD_DPWW3_SSCP_DCI | PCD_DPWW3_SSCP_DSI | PCD_DPWW3_SSCP_DER | PCD_DPWW3_SSCP_RS | PCD_DPWW3_SSCP_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S1 |  | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_DLY_S1 | PCD_DPWW3_SSCP_DIR_S1 | PCD_DPWW3_SSCP_DSCR_S1 | PCD_DPWW3_SSCP_DCS_S1 | PCD_DPWW3_SSCP_DSCS_S1 | PCD_DPWW3_SSCP_DPP_S1 | PCD_DPWW3_SSCP_DTPI_S1 | PCD_DPWW3_SSCP_DCI_S1 | PCD_DPWW3_SSCP_DSI_S1 | PCD_DPWW3_SSCP_DER_S1 | PCD_DPWW3_SSCP_RS_S1 | PCD_DPWW3_SSCP_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S2 |  | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_DLY_S2 | PCD_DPWW3_SSCP_DIR_S2 | PCD_DPWW3_SSCP_DSCR_S2 | PCD_DPWW3_SSCP_DCS_S2 | PCD_DPWW3_SSCP_DSCS_S2 | PCD_DPWW3_SSCP_DPP_S2 | PCD_DPWW3_SSCP_DTPI_S2 | PCD_DPWW3_SSCP_DCI_S2 | PCD_DPWW3_SSCP_DSI_S2 | PCD_DPWW3_SSCP_DER_S2 | PCD_DPWW3_SSCP_RS_S2 | PCD_DPWW3_SSCP_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S3 |  | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_DLY_S3 | PCD_DPWW3_SSCP_DIR_S3 | PCD_DPWW3_SSCP_DSCR_S3 | PCD_DPWW3_SSCP_DCS_S3 | PCD_DPWW3_SSCP_DSCS_S3 | PCD_DPWW3_SSCP_DPP_S3 | PCD_DPWW3_SSCP_DTPI_S3 | PCD_DPWW3_SSCP_DCI_S3 | PCD_DPWW3_SSCP_DSI_S3 | PCD_DPWW3_SSCP_DER_S3 | PCD_DPWW3_SSCP_RS_S3 | PCD_DPWW3_SSCP_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S4 |  | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_DLY_S4 | PCD_DPWW3_SSCP_DIR_S4 | PCD_DPWW3_SSCP_DSCR_S4 | PCD_DPWW3_SSCP_DCS_S4 | PCD_DPWW3_SSCP_DSCS_S4 | PCD_DPWW3_SSCP_DPP_S4 | PCD_DPWW3_SSCP_DTPI_S4 | PCD_DPWW3_SSCP_DCI_S4 | PCD_DPWW3_SSCP_DSI_S4 | PCD_DPWW3_SSCP_DER_S4 | PCD_DPWW3_SSCP_RS_S4 | PCD_DPWW3_SSCP_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S5 |  | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_DLY_S5 | PCD_DPWW3_SSCP_DIR_S5 | PCD_DPWW3_SSCP_DSCR_S5 | PCD_DPWW3_SSCP_DCS_S5 | PCD_DPWW3_SSCP_DSCS_S5 | PCD_DPWW3_SSCP_DPP_S5 | PCD_DPWW3_SSCP_DTPI_S5 | PCD_DPWW3_SSCP_DCI_S5 | PCD_DPWW3_SSCP_DSI_S5 | PCD_DPWW3_SSCP_DER_S5 | PCD_DPWW3_SSCP_RS_S5 | PCD_DPWW3_SSCP_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S6 |  | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_DLY_S6 | PCD_DPWW3_SSCP_DIR_S6 | PCD_DPWW3_SSCP_DSCR_S6 | PCD_DPWW3_SSCP_DCS_S6 | PCD_DPWW3_SSCP_DSCS_S6 | PCD_DPWW3_SSCP_DPP_S6 | PCD_DPWW3_SSCP_DTPI_S6 | PCD_DPWW3_SSCP_DCI_S6 | PCD_DPWW3_SSCP_DSI_S6 | PCD_DPWW3_SSCP_DER_S6 | PCD_DPWW3_SSCP_RS_S6 | PCD_DPWW3_SSCP_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S7 |  | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_DLY_S7 | PCD_DPWW3_SSCP_DIR_S7 | PCD_DPWW3_SSCP_DSCR_S7 | PCD_DPWW3_SSCP_DCS_S7 | PCD_DPWW3_SSCP_DSCS_S7 | PCD_DPWW3_SSCP_DPP_S7 | PCD_DPWW3_SSCP_DTPI_S7 | PCD_DPWW3_SSCP_DCI_S7 | PCD_DPWW3_SSCP_DSI_S7 | PCD_DPWW3_SSCP_DER_S7 | PCD_DPWW3_SSCP_RS_S7 | PCD_DPWW3_SSCP_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _ST |  | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_DLY_ST | PCD_DPWW3_SSCP_DIR_ST | PCD_DPWW3_SSCP_DSCR_ST | PCD_DPWW3_SSCP_DCS_ST | PCD_DPWW3_SSCP_DSCS_ST | PCD_DPWW3_SSCP_DPP_ST | PCD_DPWW3_SSCP_DTPI_ST | PCD_DPWW3_SSCP_DCI_ST | PCD_DPWW3_SSCP_DSI_ST | PCD_DPWW3_SSCP_DER_ST | PCD_DPWW3_SSCP_RS_ST | PCD_DPWW3_SSCP_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | PCD_DPWW3_STOTH1 | PCD_DPWW3_STOTH1_NR | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_DLY | PCD_DPWW3_STOTH1_DIR | PCD_DPWW3_STOTH1_DSCR | PCD_DPWW3_STOTH1_DCS | PCD_DPWW3_STOTH1_DSCS | PCD_DPWW3_STOTH1_DPP | PCD_DPWW3_STOTH1_DTPI | PCD_DPWW3_STOTH1_DCI | PCD_DPWW3_STOTH1_DSI | PCD_DPWW3_STOTH1_DER | PCD_DPWW3_STOTH1_RS | PCD_DPWW3_STOTH1_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S1 |  | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_DLY_S1 | PCD_DPWW3_STOTH1_DIR_S1 | PCD_DPWW3_STOTH1_DSCR_S1 | PCD_DPWW3_STOTH1_DCS_S1 | PCD_DPWW3_STOTH1_DSCS_S1 | PCD_DPWW3_STOTH1_DPP_S1 | PCD_DPWW3_STOTH1_DTPI_S1 | PCD_DPWW3_STOTH1_DCI_S1 | PCD_DPWW3_STOTH1_DSI_S1 | PCD_DPWW3_STOTH1_DER_S1 | PCD_DPWW3_STOTH1_RS_S1 | PCD_DPWW3_STOTH1_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S2 |  | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_DLY_S2 | PCD_DPWW3_STOTH1_DIR_S2 | PCD_DPWW3_STOTH1_DSCR_S2 | PCD_DPWW3_STOTH1_DCS_S2 | PCD_DPWW3_STOTH1_DSCS_S2 | PCD_DPWW3_STOTH1_DPP_S2 | PCD_DPWW3_STOTH1_DTPI_S2 | PCD_DPWW3_STOTH1_DCI_S2 | PCD_DPWW3_STOTH1_DSI_S2 | PCD_DPWW3_STOTH1_DER_S2 | PCD_DPWW3_STOTH1_RS_S2 | PCD_DPWW3_STOTH1_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S3 |  | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_DLY_S3 | PCD_DPWW3_STOTH1_DIR_S3 | PCD_DPWW3_STOTH1_DSCR_S3 | PCD_DPWW3_STOTH1_DCS_S3 | PCD_DPWW3_STOTH1_DSCS_S3 | PCD_DPWW3_STOTH1_DPP_S3 | PCD_DPWW3_STOTH1_DTPI_S3 | PCD_DPWW3_STOTH1_DCI_S3 | PCD_DPWW3_STOTH1_DSI_S3 | PCD_DPWW3_STOTH1_DER_S3 | PCD_DPWW3_STOTH1_RS_S3 | PCD_DPWW3_STOTH1_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S4 |  | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_DLY_S4 | PCD_DPWW3_STOTH1_DIR_S4 | PCD_DPWW3_STOTH1_DSCR_S4 | PCD_DPWW3_STOTH1_DCS_S4 | PCD_DPWW3_STOTH1_DSCS_S4 | PCD_DPWW3_STOTH1_DPP_S4 | PCD_DPWW3_STOTH1_DTPI_S4 | PCD_DPWW3_STOTH1_DCI_S4 | PCD_DPWW3_STOTH1_DSI_S4 | PCD_DPWW3_STOTH1_DER_S4 | PCD_DPWW3_STOTH1_RS_S4 | PCD_DPWW3_STOTH1_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S5 |  | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_DLY_S5 | PCD_DPWW3_STOTH1_DIR_S5 | PCD_DPWW3_STOTH1_DSCR_S5 | PCD_DPWW3_STOTH1_DCS_S5 | PCD_DPWW3_STOTH1_DSCS_S5 | PCD_DPWW3_STOTH1_DPP_S5 | PCD_DPWW3_STOTH1_DTPI_S5 | PCD_DPWW3_STOTH1_DCI_S5 | PCD_DPWW3_STOTH1_DSI_S5 | PCD_DPWW3_STOTH1_DER_S5 | PCD_DPWW3_STOTH1_RS_S5 | PCD_DPWW3_STOTH1_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S6 |  | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_DLY_S6 | PCD_DPWW3_STOTH1_DIR_S6 | PCD_DPWW3_STOTH1_DSCR_S6 | PCD_DPWW3_STOTH1_DCS_S6 | PCD_DPWW3_STOTH1_DSCS_S6 | PCD_DPWW3_STOTH1_DPP_S6 | PCD_DPWW3_STOTH1_DTPI_S6 | PCD_DPWW3_STOTH1_DCI_S6 | PCD_DPWW3_STOTH1_DSI_S6 | PCD_DPWW3_STOTH1_DER_S6 | PCD_DPWW3_STOTH1_RS_S6 | PCD_DPWW3_STOTH1_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S7 |  | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_DLY_S7 | PCD_DPWW3_STOTH1_DIR_S7 | PCD_DPWW3_STOTH1_DSCR_S7 | PCD_DPWW3_STOTH1_DCS_S7 | PCD_DPWW3_STOTH1_DSCS_S7 | PCD_DPWW3_STOTH1_DPP_S7 | PCD_DPWW3_STOTH1_DTPI_S7 | PCD_DPWW3_STOTH1_DCI_S7 | PCD_DPWW3_STOTH1_DSI_S7 | PCD_DPWW3_STOTH1_DER_S7 | PCD_DPWW3_STOTH1_RS_S7 | PCD_DPWW3_STOTH1_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _ST |  | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_DLY_ST | PCD_DPWW3_STOTH1_DIR_ST | PCD_DPWW3_STOTH1_DSCR_ST | PCD_DPWW3_STOTH1_DCS_ST | PCD_DPWW3_STOTH1_DSCS_ST | PCD_DPWW3_STOTH1_DPP_ST | PCD_DPWW3_STOTH1_DTPI_ST | PCD_DPWW3_STOTH1_DCI_ST | PCD_DPWW3_STOTH1_DSI_ST | PCD_DPWW3_STOTH1_DER_ST | PCD_DPWW3_STOTH1_RS_ST | PCD_DPWW3_STOTH1_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | PCD_DPWW3_STOTH2 | PCD_DPWW3_STOTH2_NR | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_DLY | PCD_DPWW3_STOTH2_DIR | PCD_DPWW3_STOTH2_DSCR | PCD_DPWW3_STOTH2_DCS | PCD_DPWW3_STOTH2_DSCS | PCD_DPWW3_STOTH2_DPP | PCD_DPWW3_STOTH2_DTPI | PCD_DPWW3_STOTH2_DCI | PCD_DPWW3_STOTH2_DSI | PCD_DPWW3_STOTH2_DER | PCD_DPWW3_STOTH2_RS | PCD_DPWW3_STOTH2_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S1 |  | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_DLY_S1 | PCD_DPWW3_STOTH2_DIR_S1 | PCD_DPWW3_STOTH2_DSCR_S1 | PCD_DPWW3_STOTH2_DCS_S1 | PCD_DPWW3_STOTH2_DSCS_S1 | PCD_DPWW3_STOTH2_DPP_S1 | PCD_DPWW3_STOTH2_DTPI_S1 | PCD_DPWW3_STOTH2_DCI_S1 | PCD_DPWW3_STOTH2_DSI_S1 | PCD_DPWW3_STOTH2_DER_S1 | PCD_DPWW3_STOTH2_RS_S1 | PCD_DPWW3_STOTH2_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S2 |  | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_DLY_S2 | PCD_DPWW3_STOTH2_DIR_S2 | PCD_DPWW3_STOTH2_DSCR_S2 | PCD_DPWW3_STOTH2_DCS_S2 | PCD_DPWW3_STOTH2_DSCS_S2 | PCD_DPWW3_STOTH2_DPP_S2 | PCD_DPWW3_STOTH2_DTPI_S2 | PCD_DPWW3_STOTH2_DCI_S2 | PCD_DPWW3_STOTH2_DSI_S2 | PCD_DPWW3_STOTH2_DER_S2 | PCD_DPWW3_STOTH2_RS_S2 | PCD_DPWW3_STOTH2_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S3 |  | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_DLY_S3 | PCD_DPWW3_STOTH2_DIR_S3 | PCD_DPWW3_STOTH2_DSCR_S3 | PCD_DPWW3_STOTH2_DCS_S3 | PCD_DPWW3_STOTH2_DSCS_S3 | PCD_DPWW3_STOTH2_DPP_S3 | PCD_DPWW3_STOTH2_DTPI_S3 | PCD_DPWW3_STOTH2_DCI_S3 | PCD_DPWW3_STOTH2_DSI_S3 | PCD_DPWW3_STOTH2_DER_S3 | PCD_DPWW3_STOTH2_RS_S3 | PCD_DPWW3_STOTH2_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S4 |  | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_DLY_S4 | PCD_DPWW3_STOTH2_DIR_S4 | PCD_DPWW3_STOTH2_DSCR_S4 | PCD_DPWW3_STOTH2_DCS_S4 | PCD_DPWW3_STOTH2_DSCS_S4 | PCD_DPWW3_STOTH2_DPP_S4 | PCD_DPWW3_STOTH2_DTPI_S4 | PCD_DPWW3_STOTH2_DCI_S4 | PCD_DPWW3_STOTH2_DSI_S4 | PCD_DPWW3_STOTH2_DER_S4 | PCD_DPWW3_STOTH2_RS_S4 | PCD_DPWW3_STOTH2_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S5 |  | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_DLY_S5 | PCD_DPWW3_STOTH2_DIR_S5 | PCD_DPWW3_STOTH2_DSCR_S5 | PCD_DPWW3_STOTH2_DCS_S5 | PCD_DPWW3_STOTH2_DSCS_S5 | PCD_DPWW3_STOTH2_DPP_S5 | PCD_DPWW3_STOTH2_DTPI_S5 | PCD_DPWW3_STOTH2_DCI_S5 | PCD_DPWW3_STOTH2_DSI_S5 | PCD_DPWW3_STOTH2_DER_S5 | PCD_DPWW3_STOTH2_RS_S5 | PCD_DPWW3_STOTH2_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S6 |  | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_DLY_S6 | PCD_DPWW3_STOTH2_DIR_S6 | PCD_DPWW3_STOTH2_DSCR_S6 | PCD_DPWW3_STOTH2_DCS_S6 | PCD_DPWW3_STOTH2_DSCS_S6 | PCD_DPWW3_STOTH2_DPP_S6 | PCD_DPWW3_STOTH2_DTPI_S6 | PCD_DPWW3_STOTH2_DCI_S6 | PCD_DPWW3_STOTH2_DSI_S6 | PCD_DPWW3_STOTH2_DER_S6 | PCD_DPWW3_STOTH2_RS_S6 | PCD_DPWW3_STOTH2_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S7 |  | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_DLY_S7 | PCD_DPWW3_STOTH2_DIR_S7 | PCD_DPWW3_STOTH2_DSCR_S7 | PCD_DPWW3_STOTH2_DCS_S7 | PCD_DPWW3_STOTH2_DSCS_S7 | PCD_DPWW3_STOTH2_DPP_S7 | PCD_DPWW3_STOTH2_DTPI_S7 | PCD_DPWW3_STOTH2_DCI_S7 | PCD_DPWW3_STOTH2_DSI_S7 | PCD_DPWW3_STOTH2_DER_S7 | PCD_DPWW3_STOTH2_RS_S7 | PCD_DPWW3_STOTH2_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _ST |  | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_DLY_ST | PCD_DPWW3_STOTH2_DIR_ST | PCD_DPWW3_STOTH2_DSCR_ST | PCD_DPWW3_STOTH2_DCS_ST | PCD_DPWW3_STOTH2_DSCS_ST | PCD_DPWW3_STOTH2_DPP_ST | PCD_DPWW3_STOTH2_DTPI_ST | PCD_DPWW3_STOTH2_DCI_ST | PCD_DPWW3_STOTH2_DSI_ST | PCD_DPWW3_STOTH2_DER_ST | PCD_DPWW3_STOTH2_RS_ST | PCD_DPWW3_STOTH2_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 0 | Nr | 0 | 25 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.9 |  | PCD_DPWW3_BIO_IED | PCD_DPWW3_BIO_IED_NR | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_DLY | PCD_DPWW3_BIO_IED_DIR | PCD_DPWW3_BIO_IED_DSCR | PCD_DPWW3_BIO_IED_DCS | PCD_DPWW3_BIO_IED_DSCS | PCD_DPWW3_BIO_IED_DPP | PCD_DPWW3_BIO_IED_DTPI | PCD_DPWW3_BIO_IED_DCI | PCD_DPWW3_BIO_IED_DSI | PCD_DPWW3_BIO_IED_DER | PCD_DPWW3_BIO_IED_RS | PCD_DPWW3_BIO_IED_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 1 | Nr | 0 |  | 2 | 24 | 24 | 22 | 22 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 18 | 18 | 10 | 9 | [12 empty] | DPWW3.9 |  | _S1 |  | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_DLY_S1 | PCD_DPWW3_BIO_IED_DIR_S1 | PCD_DPWW3_BIO_IED_DSCR_S1 | PCD_DPWW3_BIO_IED_DCS_S1 | PCD_DPWW3_BIO_IED_DSCS_S1 | PCD_DPWW3_BIO_IED_DPP_S1 | PCD_DPWW3_BIO_IED_DTPI_S1 | PCD_DPWW3_BIO_IED_DCI_S1 | PCD_DPWW3_BIO_IED_DSI_S1 | PCD_DPWW3_BIO_IED_DER_S1 | PCD_DPWW3_BIO_IED_RS_S1 | PCD_DPWW3_BIO_IED_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 2 | Nr | 0 |  | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 9 | [12 empty] | DPWW3.9 |  | _S2 |  | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_DLY_S2 | PCD_DPWW3_BIO_IED_DIR_S2 | PCD_DPWW3_BIO_IED_DSCR_S2 | PCD_DPWW3_BIO_IED_DCS_S2 | PCD_DPWW3_BIO_IED_DSCS_S2 | PCD_DPWW3_BIO_IED_DPP_S2 | PCD_DPWW3_BIO_IED_DTPI_S2 | PCD_DPWW3_BIO_IED_DCI_S2 | PCD_DPWW3_BIO_IED_DSI_S2 | PCD_DPWW3_BIO_IED_DER_S2 | PCD_DPWW3_BIO_IED_RS_S2 | PCD_DPWW3_BIO_IED_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | [12 empty] | DPWW3.9 |  | _S3 |  | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_DLY_S3 | PCD_DPWW3_BIO_IED_DIR_S3 | PCD_DPWW3_BIO_IED_DSCR_S3 | PCD_DPWW3_BIO_IED_DCS_S3 | PCD_DPWW3_BIO_IED_DSCS_S3 | PCD_DPWW3_BIO_IED_DPP_S3 | PCD_DPWW3_BIO_IED_DTPI_S3 | PCD_DPWW3_BIO_IED_DCI_S3 | PCD_DPWW3_BIO_IED_DSI_S3 | PCD_DPWW3_BIO_IED_DER_S3 | PCD_DPWW3_BIO_IED_RS_S3 | PCD_DPWW3_BIO_IED_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 2 | [12 empty] | DPWW3.9 |  | _S4 |  | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_DLY_S4 | PCD_DPWW3_BIO_IED_DIR_S4 | PCD_DPWW3_BIO_IED_DSCR_S4 | PCD_DPWW3_BIO_IED_DCS_S4 | PCD_DPWW3_BIO_IED_DSCS_S4 | PCD_DPWW3_BIO_IED_DPP_S4 | PCD_DPWW3_BIO_IED_DTPI_S4 | PCD_DPWW3_BIO_IED_DCI_S4 | PCD_DPWW3_BIO_IED_DSI_S4 | PCD_DPWW3_BIO_IED_DER_S4 | PCD_DPWW3_BIO_IED_RS_S4 | PCD_DPWW3_BIO_IED_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.9 |  | _S5 |  | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_DLY_S5 | PCD_DPWW3_BIO_IED_DIR_S5 | PCD_DPWW3_BIO_IED_DSCR_S5 | PCD_DPWW3_BIO_IED_DCS_S5 | PCD_DPWW3_BIO_IED_DSCS_S5 | PCD_DPWW3_BIO_IED_DPP_S5 | PCD_DPWW3_BIO_IED_DTPI_S5 | PCD_DPWW3_BIO_IED_DCI_S5 | PCD_DPWW3_BIO_IED_DSI_S5 | PCD_DPWW3_BIO_IED_DER_S5 | PCD_DPWW3_BIO_IED_RS_S5 | PCD_DPWW3_BIO_IED_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | [12 empty] | DPWW3.9 |  | _S6 |  | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_DLY_S6 | PCD_DPWW3_BIO_IED_DIR_S6 | PCD_DPWW3_BIO_IED_DSCR_S6 | PCD_DPWW3_BIO_IED_DCS_S6 | PCD_DPWW3_BIO_IED_DSCS_S6 | PCD_DPWW3_BIO_IED_DPP_S6 | PCD_DPWW3_BIO_IED_DTPI_S6 | PCD_DPWW3_BIO_IED_DCI_S6 | PCD_DPWW3_BIO_IED_DSI_S6 | PCD_DPWW3_BIO_IED_DER_S6 | PCD_DPWW3_BIO_IED_RS_S6 | PCD_DPWW3_BIO_IED_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.9 |  | _S7 |  | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_DLY_S7 | PCD_DPWW3_BIO_IED_DIR_S7 | PCD_DPWW3_BIO_IED_DSCR_S7 | PCD_DPWW3_BIO_IED_DCS_S7 | PCD_DPWW3_BIO_IED_DSCS_S7 | PCD_DPWW3_BIO_IED_DPP_S7 | PCD_DPWW3_BIO_IED_DTPI_S7 | PCD_DPWW3_BIO_IED_DCI_S7 | PCD_DPWW3_BIO_IED_DSI_S7 | PCD_DPWW3_BIO_IED_DER_S7 | PCD_DPWW3_BIO_IED_RS_S7 | PCD_DPWW3_BIO_IED_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | [12 empty] | DPWW3.9 |  | _ST |  | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_DLY_ST | PCD_DPWW3_BIO_IED_DIR_ST | PCD_DPWW3_BIO_IED_DSCR_ST | PCD_DPWW3_BIO_IED_DCS_ST | PCD_DPWW3_BIO_IED_DSCS_ST | PCD_DPWW3_BIO_IED_DPP_ST | PCD_DPWW3_BIO_IED_DTPI_ST | PCD_DPWW3_BIO_IED_DCI_ST | PCD_DPWW3_BIO_IED_DSI_ST | PCD_DPWW3_BIO_IED_DER_ST | PCD_DPWW3_BIO_IED_RS_ST | PCD_DPWW3_BIO_IED_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 0 | Nr | 0 | 106 | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.10 |  | PCD_DPWW3_SOES | PCD_DPWW3_SOES_NR | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_DLY | PCD_DPWW3_SOES_DIR | PCD_DPWW3_SOES_DSCR | PCD_DPWW3_SOES_DCS | PCD_DPWW3_SOES_DSCS | PCD_DPWW3_SOES_DPP | PCD_DPWW3_SOES_DTPI | PCD_DPWW3_SOES_DCI | PCD_DPWW3_SOES_DSI | PCD_DPWW3_SOES_DER | PCD_DPWW3_SOES_RS | PCD_DPWW3_SOES_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 1 | Nr | 0 |  | 103 | 103 | 105 | 105 | 106 | 98 | 90 | 47 | 28 | 23 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.10 |  | _S1 |  | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_DLY_S1 | PCD_DPWW3_SOES_DIR_S1 | PCD_DPWW3_SOES_DSCR_S1 | PCD_DPWW3_SOES_DCS_S1 | PCD_DPWW3_SOES_DSCS_S1 | PCD_DPWW3_SOES_DPP_S1 | PCD_DPWW3_SOES_DTPI_S1 | PCD_DPWW3_SOES_DCI_S1 | PCD_DPWW3_SOES_DSI_S1 | PCD_DPWW3_SOES_DER_S1 | PCD_DPWW3_SOES_RS_S1 | PCD_DPWW3_SOES_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 55 | 69 | 67 | 47 | 26 | 20 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.10 |  | _S2 |  | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_DLY_S2 | PCD_DPWW3_SOES_DIR_S2 | PCD_DPWW3_SOES_DSCR_S2 | PCD_DPWW3_SOES_DCS_S2 | PCD_DPWW3_SOES_DSCS_S2 | PCD_DPWW3_SOES_DPP_S2 | PCD_DPWW3_SOES_DTPI_S2 | PCD_DPWW3_SOES_DCI_S2 | PCD_DPWW3_SOES_DSI_S2 | PCD_DPWW3_SOES_DER_S2 | PCD_DPWW3_SOES_RS_S2 | PCD_DPWW3_SOES_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 11 | 42 | 62 | 62 | 33 | 18 | 14 | 5 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.10 |  | _S3 |  | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_DLY_S3 | PCD_DPWW3_SOES_DIR_S3 | PCD_DPWW3_SOES_DSCR_S3 | PCD_DPWW3_SOES_DCS_S3 | PCD_DPWW3_SOES_DSCS_S3 | PCD_DPWW3_SOES_DPP_S3 | PCD_DPWW3_SOES_DTPI_S3 | PCD_DPWW3_SOES_DCI_S3 | PCD_DPWW3_SOES_DSI_S3 | PCD_DPWW3_SOES_DER_S3 | PCD_DPWW3_SOES_RS_S3 | PCD_DPWW3_SOES_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 8 | 36 | 50 | 50 | 58 | 54 | 33 | 26 | 17 | [12 empty] | DPWW3.10 |  | _S4 |  | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_DLY_S4 | PCD_DPWW3_SOES_DIR_S4 | PCD_DPWW3_SOES_DSCR_S4 | PCD_DPWW3_SOES_DCS_S4 | PCD_DPWW3_SOES_DSCS_S4 | PCD_DPWW3_SOES_DPP_S4 | PCD_DPWW3_SOES_DTPI_S4 | PCD_DPWW3_SOES_DCI_S4 | PCD_DPWW3_SOES_DSI_S4 | PCD_DPWW3_SOES_DER_S4 | PCD_DPWW3_SOES_RS_S4 | PCD_DPWW3_SOES_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 15 | 16 | [12 empty] | DPWW3.10 |  | _S5 |  | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_DLY_S5 | PCD_DPWW3_SOES_DIR_S5 | PCD_DPWW3_SOES_DSCR_S5 | PCD_DPWW3_SOES_DCS_S5 | PCD_DPWW3_SOES_DSCS_S5 | PCD_DPWW3_SOES_DPP_S5 | PCD_DPWW3_SOES_DTPI_S5 | PCD_DPWW3_SOES_DCI_S5 | PCD_DPWW3_SOES_DSI_S5 | PCD_DPWW3_SOES_DER_S5 | PCD_DPWW3_SOES_RS_S5 | PCD_DPWW3_SOES_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 5 | 8 | 11 | 16 | 28 | 33 | 42 | 43 | 49 | 56 | 65 | 73 | 14 | [10 empty] | 14 | DPWW3.10 |  | _S6 |  | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_DLY_S6 | PCD_DPWW3_SOES_DIR_S6 | PCD_DPWW3_SOES_DSCR_S6 | PCD_DPWW3_SOES_DCS_S6 | PCD_DPWW3_SOES_DSCS_S6 | PCD_DPWW3_SOES_DPP_S6 | PCD_DPWW3_SOES_DTPI_S6 | PCD_DPWW3_SOES_DCI_S6 | PCD_DPWW3_SOES_DSI_S6 | PCD_DPWW3_SOES_DER_S6 | PCD_DPWW3_SOES_RS_S6 | PCD_DPWW3_SOES_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.10 |  | _S7 |  | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_DLY_S7 | PCD_DPWW3_SOES_DIR_S7 | PCD_DPWW3_SOES_DSCR_S7 | PCD_DPWW3_SOES_DCS_S7 | PCD_DPWW3_SOES_DSCS_S7 | PCD_DPWW3_SOES_DPP_S7 | PCD_DPWW3_SOES_DTPI_S7 | PCD_DPWW3_SOES_DCI_S7 | PCD_DPWW3_SOES_DSI_S7 | PCD_DPWW3_SOES_DER_S7 | PCD_DPWW3_SOES_RS_S7 | PCD_DPWW3_SOES_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | [12 empty] | DPWW3.10 |  | _ST |  | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_DLY_ST | PCD_DPWW3_SOES_DIR_ST | PCD_DPWW3_SOES_DSCR_ST | PCD_DPWW3_SOES_DCS_ST | PCD_DPWW3_SOES_DSCS_ST | PCD_DPWW3_SOES_DPP_ST | PCD_DPWW3_SOES_DTPI_ST | PCD_DPWW3_SOES_DCI_ST | PCD_DPWW3_SOES_DSI_ST | PCD_DPWW3_SOES_DER_ST | PCD_DPWW3_SOES_RS_ST | PCD_DPWW3_SOES_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 0 | Nr | 0 | 17 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.11 |  | PCD_DPWW3_FTFT | PCD_DPWW3_FTFT_NR | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_DLY | PCD_DPWW3_FTFT_DIR | PCD_DPWW3_FTFT_DSCR | PCD_DPWW3_FTFT_DCS | PCD_DPWW3_FTFT_DSCS | PCD_DPWW3_FTFT_DPP | PCD_DPWW3_FTFT_DTPI | PCD_DPWW3_FTFT_DCI | PCD_DPWW3_FTFT_DSI | PCD_DPWW3_FTFT_DER | PCD_DPWW3_FTFT_RS | PCD_DPWW3_FTFT_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 1 | Nr | 0 |  | 16 | 16 | 17 | 17 | 17 | 16 | 13 | 8 | 7 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.11 |  | _S1 |  | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_DLY_S1 | PCD_DPWW3_FTFT_DIR_S1 | PCD_DPWW3_FTFT_DSCR_S1 | PCD_DPWW3_FTFT_DCS_S1 | PCD_DPWW3_FTFT_DSCS_S1 | PCD_DPWW3_FTFT_DPP_S1 | PCD_DPWW3_FTFT_DTPI_S1 | PCD_DPWW3_FTFT_DCI_S1 | PCD_DPWW3_FTFT_DSI_S1 | PCD_DPWW3_FTFT_DER_S1 | PCD_DPWW3_FTFT_RS_S1 | PCD_DPWW3_FTFT_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 8 | 7 | 8 | 6 | 7 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.11 |  | _S2 |  | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_DLY_S2 | PCD_DPWW3_FTFT_DIR_S2 | PCD_DPWW3_FTFT_DSCR_S2 | PCD_DPWW3_FTFT_DCS_S2 | PCD_DPWW3_FTFT_DSCS_S2 | PCD_DPWW3_FTFT_DPP_S2 | PCD_DPWW3_FTFT_DTPI_S2 | PCD_DPWW3_FTFT_DCI_S2 | PCD_DPWW3_FTFT_DSI_S2 | PCD_DPWW3_FTFT_DER_S2 | PCD_DPWW3_FTFT_RS_S2 | PCD_DPWW3_FTFT_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 6 | 5 | 4 | 4 | 5 | 3 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.11 |  | _S3 |  | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_DLY_S3 | PCD_DPWW3_FTFT_DIR_S3 | PCD_DPWW3_FTFT_DSCR_S3 | PCD_DPWW3_FTFT_DCS_S3 | PCD_DPWW3_FTFT_DSCS_S3 | PCD_DPWW3_FTFT_DPP_S3 | PCD_DPWW3_FTFT_DTPI_S3 | PCD_DPWW3_FTFT_DCI_S3 | PCD_DPWW3_FTFT_DSI_S3 | PCD_DPWW3_FTFT_DER_S3 | PCD_DPWW3_FTFT_RS_S3 | PCD_DPWW3_FTFT_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 7 | 7 | 8 | 10 | 12 | 9 | 8 | 5 | [12 empty] | DPWW3.11 |  | _S4 |  | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_DLY_S4 | PCD_DPWW3_FTFT_DIR_S4 | PCD_DPWW3_FTFT_DSCR_S4 | PCD_DPWW3_FTFT_DCS_S4 | PCD_DPWW3_FTFT_DSCS_S4 | PCD_DPWW3_FTFT_DPP_S4 | PCD_DPWW3_FTFT_DTPI_S4 | PCD_DPWW3_FTFT_DCI_S4 | PCD_DPWW3_FTFT_DSI_S4 | PCD_DPWW3_FTFT_DER_S4 | PCD_DPWW3_FTFT_RS_S4 | PCD_DPWW3_FTFT_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | [12 empty] | DPWW3.11 |  | _S5 |  | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_DLY_S5 | PCD_DPWW3_FTFT_DIR_S5 | PCD_DPWW3_FTFT_DSCR_S5 | PCD_DPWW3_FTFT_DCS_S5 | PCD_DPWW3_FTFT_DSCS_S5 | PCD_DPWW3_FTFT_DPP_S5 | PCD_DPWW3_FTFT_DTPI_S5 | PCD_DPWW3_FTFT_DCI_S5 | PCD_DPWW3_FTFT_DSI_S5 | PCD_DPWW3_FTFT_DER_S5 | PCD_DPWW3_FTFT_RS_S5 | PCD_DPWW3_FTFT_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 5 | 7 | 7 | 9 | [12 empty] | DPWW3.11 |  | _S6 |  | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_DLY_S6 | PCD_DPWW3_FTFT_DIR_S6 | PCD_DPWW3_FTFT_DSCR_S6 | PCD_DPWW3_FTFT_DCS_S6 | PCD_DPWW3_FTFT_DSCS_S6 | PCD_DPWW3_FTFT_DPP_S6 | PCD_DPWW3_FTFT_DTPI_S6 | PCD_DPWW3_FTFT_DCI_S6 | PCD_DPWW3_FTFT_DSI_S6 | PCD_DPWW3_FTFT_DER_S6 | PCD_DPWW3_FTFT_RS_S6 | PCD_DPWW3_FTFT_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.11 |  | _S7 |  | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_DLY_S7 | PCD_DPWW3_FTFT_DIR_S7 | PCD_DPWW3_FTFT_DSCR_S7 | PCD_DPWW3_FTFT_DCS_S7 | PCD_DPWW3_FTFT_DSCS_S7 | PCD_DPWW3_FTFT_DPP_S7 | PCD_DPWW3_FTFT_DTPI_S7 | PCD_DPWW3_FTFT_DCI_S7 | PCD_DPWW3_FTFT_DSI_S7 | PCD_DPWW3_FTFT_DER_S7 | PCD_DPWW3_FTFT_RS_S7 | PCD_DPWW3_FTFT_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | [12 empty] | DPWW3.11 |  | _ST |  | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_DLY_ST | PCD_DPWW3_FTFT_DIR_ST | PCD_DPWW3_FTFT_DSCR_ST | PCD_DPWW3_FTFT_DCS_ST | PCD_DPWW3_FTFT_DSCS_ST | PCD_DPWW3_FTFT_DPP_ST | PCD_DPWW3_FTFT_DTPI_ST | PCD_DPWW3_FTFT_DCI_ST | PCD_DPWW3_FTFT_DSI_ST | PCD_DPWW3_FTFT_DER_ST | PCD_DPWW3_FTFT_RS_ST | PCD_DPWW3_FTFT_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 0 | Nr | 0 | 98 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.12 |  | PCD_DPWW3_PRMVL | PCD_DPWW3_PRMVL_NR | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_DLY | PCD_DPWW3_PRMVL_DIR | PCD_DPWW3_PRMVL_DSCR | PCD_DPWW3_PRMVL_DCS | PCD_DPWW3_PRMVL_DSCS | PCD_DPWW3_PRMVL_DPP | PCD_DPWW3_PRMVL_DTPI | PCD_DPWW3_PRMVL_DCI | PCD_DPWW3_PRMVL_DSI | PCD_DPWW3_PRMVL_DER | PCD_DPWW3_PRMVL_RS | PCD_DPWW3_PRMVL_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 1 | Nr | 0 |  | 89 | 87 | 88 | 85 | 82 | 76 | 61 | 25 | 18 | 7 | 5 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPWW3.12 |  | _S1 |  | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_DLY_S1 | PCD_DPWW3_PRMVL_DIR_S1 | PCD_DPWW3_PRMVL_DSCR_S1 | PCD_DPWW3_PRMVL_DCS_S1 | PCD_DPWW3_PRMVL_DSCS_S1 | PCD_DPWW3_PRMVL_DPP_S1 | PCD_DPWW3_PRMVL_DTPI_S1 | PCD_DPWW3_PRMVL_DCI_S1 | PCD_DPWW3_PRMVL_DSI_S1 | PCD_DPWW3_PRMVL_DER_S1 | PCD_DPWW3_PRMVL_RS_S1 | PCD_DPWW3_PRMVL_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 2 | Nr | 0 |  | 3 | 5 | 3 | 4 | 6 | 11 | 24 | 57 | 58 | 64 | 51 | 26 | 8 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.12 |  | _S2 |  | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_DLY_S2 | PCD_DPWW3_PRMVL_DIR_S2 | PCD_DPWW3_PRMVL_DSCR_S2 | PCD_DPWW3_PRMVL_DCS_S2 | PCD_DPWW3_PRMVL_DSCS_S2 | PCD_DPWW3_PRMVL_DPP_S2 | PCD_DPWW3_PRMVL_DTPI_S2 | PCD_DPWW3_PRMVL_DCI_S2 | PCD_DPWW3_PRMVL_DSI_S2 | PCD_DPWW3_PRMVL_DER_S2 | PCD_DPWW3_PRMVL_RS_S2 | PCD_DPWW3_PRMVL_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 1 | 3 | 3 | 4 | 3 | 5 | 7 | 10 | 10 | 21 | 40 | 43 | 24 | 8 | 4 | 3 | 3 | 1 | 0 | 0 | [12 empty] | DPWW3.12 |  | _S3 |  | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_DLY_S3 | PCD_DPWW3_PRMVL_DIR_S3 | PCD_DPWW3_PRMVL_DSCR_S3 | PCD_DPWW3_PRMVL_DCS_S3 | PCD_DPWW3_PRMVL_DSCS_S3 | PCD_DPWW3_PRMVL_DPP_S3 | PCD_DPWW3_PRMVL_DTPI_S3 | PCD_DPWW3_PRMVL_DCI_S3 | PCD_DPWW3_PRMVL_DSI_S3 | PCD_DPWW3_PRMVL_DER_S3 | PCD_DPWW3_PRMVL_RS_S3 | PCD_DPWW3_PRMVL_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 2 | 1 | 3 | 3 | 3 | 6 | 11 | 15 | 22 | 37 | 61 | 75 | 79 | 71 | 64 | 49 | 33 | 16 | [12 empty] | DPWW3.12 |  | _S4 |  | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_DLY_S4 | PCD_DPWW3_PRMVL_DIR_S4 | PCD_DPWW3_PRMVL_DSCR_S4 | PCD_DPWW3_PRMVL_DCS_S4 | PCD_DPWW3_PRMVL_DSCS_S4 | PCD_DPWW3_PRMVL_DPP_S4 | PCD_DPWW3_PRMVL_DTPI_S4 | PCD_DPWW3_PRMVL_DCI_S4 | PCD_DPWW3_PRMVL_DSI_S4 | PCD_DPWW3_PRMVL_DER_S4 | PCD_DPWW3_PRMVL_RS_S4 | PCD_DPWW3_PRMVL_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 5 | 7 | 13 | 21 | 38 | 54 | 45 | [12 empty] | DPWW3.12 |  | _S5 |  | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_DLY_S5 | PCD_DPWW3_PRMVL_DIR_S5 | PCD_DPWW3_PRMVL_DSCR_S5 | PCD_DPWW3_PRMVL_DCS_S5 | PCD_DPWW3_PRMVL_DSCS_S5 | PCD_DPWW3_PRMVL_DPP_S5 | PCD_DPWW3_PRMVL_DTPI_S5 | PCD_DPWW3_PRMVL_DCI_S5 | PCD_DPWW3_PRMVL_DSI_S5 | PCD_DPWW3_PRMVL_DER_S5 | PCD_DPWW3_PRMVL_RS_S5 | PCD_DPWW3_PRMVL_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 6 | Nr | 0 |  | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 9 | 9 | 9 | 10 | 36 | 2 | [11 empty] | DPWW3.12 |  | _S6 |  | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_DLY_S6 | PCD_DPWW3_PRMVL_DIR_S6 | PCD_DPWW3_PRMVL_DSCR_S6 | PCD_DPWW3_PRMVL_DCS_S6 | PCD_DPWW3_PRMVL_DSCS_S6 | PCD_DPWW3_PRMVL_DPP_S6 | PCD_DPWW3_PRMVL_DTPI_S6 | PCD_DPWW3_PRMVL_DCI_S6 | PCD_DPWW3_PRMVL_DSI_S6 | PCD_DPWW3_PRMVL_DER_S6 | PCD_DPWW3_PRMVL_RS_S6 | PCD_DPWW3_PRMVL_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.12 |  | _S7 |  | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_DLY_S7 | PCD_DPWW3_PRMVL_DIR_S7 | PCD_DPWW3_PRMVL_DSCR_S7 | PCD_DPWW3_PRMVL_DCS_S7 | PCD_DPWW3_PRMVL_DSCS_S7 | PCD_DPWW3_PRMVL_DPP_S7 | PCD_DPWW3_PRMVL_DTPI_S7 | PCD_DPWW3_PRMVL_DCI_S7 | PCD_DPWW3_PRMVL_DSI_S7 | PCD_DPWW3_PRMVL_DER_S7 | PCD_DPWW3_PRMVL_RS_S7 | PCD_DPWW3_PRMVL_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | [12 empty] | DPWW3.12 |  | _ST |  | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_DLY_ST | PCD_DPWW3_PRMVL_DIR_ST | PCD_DPWW3_PRMVL_DSCR_ST | PCD_DPWW3_PRMVL_DCS_ST | PCD_DPWW3_PRMVL_DSCS_ST | PCD_DPWW3_PRMVL_DPP_ST | PCD_DPWW3_PRMVL_DTPI_ST | PCD_DPWW3_PRMVL_DCI_ST | PCD_DPWW3_PRMVL_DSI_ST | PCD_DPWW3_PRMVL_DER_ST | PCD_DPWW3_PRMVL_RS_ST | PCD_DPWW3_PRMVL_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 0 | Nr | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.13 |  | PCD_DPWW3_GSTW | PCD_DPWW3_GSTW_NR | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_DLY | PCD_DPWW3_GSTW_DIR | PCD_DPWW3_GSTW_DSCR | PCD_DPWW3_GSTW_DCS | PCD_DPWW3_GSTW_DSCS | PCD_DPWW3_GSTW_DPP | PCD_DPWW3_GSTW_DTPI | PCD_DPWW3_GSTW_DCI | PCD_DPWW3_GSTW_DSI | PCD_DPWW3_GSTW_DER | PCD_DPWW3_GSTW_RS | PCD_DPWW3_GSTW_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 1 | Nr | 0 |  | 15 | 15 | 15 | 14 | 14 | 10 | 9 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.13 |  | _S1 |  | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_DLY_S1 | PCD_DPWW3_GSTW_DIR_S1 | PCD_DPWW3_GSTW_DSCR_S1 | PCD_DPWW3_GSTW_DCS_S1 | PCD_DPWW3_GSTW_DSCS_S1 | PCD_DPWW3_GSTW_DPP_S1 | PCD_DPWW3_GSTW_DTPI_S1 | PCD_DPWW3_GSTW_DCI_S1 | PCD_DPWW3_GSTW_DSI_S1 | PCD_DPWW3_GSTW_DER_S1 | PCD_DPWW3_GSTW_RS_S1 | PCD_DPWW3_GSTW_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 1 | 1 | 5 | 5 | 11 | 10 | 9 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.13 |  | _S2 |  | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_DLY_S2 | PCD_DPWW3_GSTW_DIR_S2 | PCD_DPWW3_GSTW_DSCR_S2 | PCD_DPWW3_GSTW_DCS_S2 | PCD_DPWW3_GSTW_DSCS_S2 | PCD_DPWW3_GSTW_DPP_S2 | PCD_DPWW3_GSTW_DTPI_S2 | PCD_DPWW3_GSTW_DCI_S2 | PCD_DPWW3_GSTW_DSI_S2 | PCD_DPWW3_GSTW_DER_S2 | PCD_DPWW3_GSTW_RS_S2 | PCD_DPWW3_GSTW_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 5 | 5 | 4 | 5 | 5 | 5 | 1 | 1 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.13 |  | _S3 |  | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_DLY_S3 | PCD_DPWW3_GSTW_DIR_S3 | PCD_DPWW3_GSTW_DSCR_S3 | PCD_DPWW3_GSTW_DCS_S3 | PCD_DPWW3_GSTW_DSCS_S3 | PCD_DPWW3_GSTW_DPP_S3 | PCD_DPWW3_GSTW_DTPI_S3 | PCD_DPWW3_GSTW_DCI_S3 | PCD_DPWW3_GSTW_DSI_S3 | PCD_DPWW3_GSTW_DER_S3 | PCD_DPWW3_GSTW_RS_S3 | PCD_DPWW3_GSTW_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 6 | 9 | 10 | 14 | 13 | 13 | 8 | 6 | 3 | [12 empty] | DPWW3.13 |  | _S4 |  | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_DLY_S4 | PCD_DPWW3_GSTW_DIR_S4 | PCD_DPWW3_GSTW_DSCR_S4 | PCD_DPWW3_GSTW_DCS_S4 | PCD_DPWW3_GSTW_DSCS_S4 | PCD_DPWW3_GSTW_DPP_S4 | PCD_DPWW3_GSTW_DTPI_S4 | PCD_DPWW3_GSTW_DCI_S4 | PCD_DPWW3_GSTW_DSI_S4 | PCD_DPWW3_GSTW_DER_S4 | PCD_DPWW3_GSTW_RS_S4 | PCD_DPWW3_GSTW_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 6 | 4 | [12 empty] | DPWW3.13 |  | _S5 |  | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_DLY_S5 | PCD_DPWW3_GSTW_DIR_S5 | PCD_DPWW3_GSTW_DSCR_S5 | PCD_DPWW3_GSTW_DCS_S5 | PCD_DPWW3_GSTW_DSCS_S5 | PCD_DPWW3_GSTW_DPP_S5 | PCD_DPWW3_GSTW_DTPI_S5 | PCD_DPWW3_GSTW_DCI_S5 | PCD_DPWW3_GSTW_DSI_S5 | PCD_DPWW3_GSTW_DER_S5 | PCD_DPWW3_GSTW_RS_S5 | PCD_DPWW3_GSTW_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 8 | 1 | [11 empty] | DPWW3.13 |  | _S6 |  | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_DLY_S6 | PCD_DPWW3_GSTW_DIR_S6 | PCD_DPWW3_GSTW_DSCR_S6 | PCD_DPWW3_GSTW_DCS_S6 | PCD_DPWW3_GSTW_DSCS_S6 | PCD_DPWW3_GSTW_DPP_S6 | PCD_DPWW3_GSTW_DTPI_S6 | PCD_DPWW3_GSTW_DCI_S6 | PCD_DPWW3_GSTW_DSI_S6 | PCD_DPWW3_GSTW_DER_S6 | PCD_DPWW3_GSTW_RS_S6 | PCD_DPWW3_GSTW_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.13 |  | _S7 |  | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_DLY_S7 | PCD_DPWW3_GSTW_DIR_S7 | PCD_DPWW3_GSTW_DSCR_S7 | PCD_DPWW3_GSTW_DCS_S7 | PCD_DPWW3_GSTW_DSCS_S7 | PCD_DPWW3_GSTW_DPP_S7 | PCD_DPWW3_GSTW_DTPI_S7 | PCD_DPWW3_GSTW_DCI_S7 | PCD_DPWW3_GSTW_DSI_S7 | PCD_DPWW3_GSTW_DER_S7 | PCD_DPWW3_GSTW_RS_S7 | PCD_DPWW3_GSTW_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | [12 empty] | DPWW3.13 |  | _ST |  | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_DLY_ST | PCD_DPWW3_GSTW_DIR_ST | PCD_DPWW3_GSTW_DSCR_ST | PCD_DPWW3_GSTW_DCS_ST | PCD_DPWW3_GSTW_DSCS_ST | PCD_DPWW3_GSTW_DPP_ST | PCD_DPWW3_GSTW_DTPI_ST | PCD_DPWW3_GSTW_DCI_ST | PCD_DPWW3_GSTW_DSI_ST | PCD_DPWW3_GSTW_DER_ST | PCD_DPWW3_GSTW_RS_ST | PCD_DPWW3_GSTW_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 0 | Nr | 0 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.14 |  | PCD_DPWW3_TTSP | PCD_DPWW3_TTSP_NR | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_DLY | PCD_DPWW3_TTSP_DIR | PCD_DPWW3_TTSP_DSCR | PCD_DPWW3_TTSP_DCS | PCD_DPWW3_TTSP_DSCS | PCD_DPWW3_TTSP_DPP | PCD_DPWW3_TTSP_DTPI | PCD_DPWW3_TTSP_DCI | PCD_DPWW3_TTSP_DSI | PCD_DPWW3_TTSP_DER | PCD_DPWW3_TTSP_RS | PCD_DPWW3_TTSP_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 1 | Nr | 0 |  | 17 | 15 | 15 | 10 | 9 | 9 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.14 |  | _S1 |  | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_DLY_S1 | PCD_DPWW3_TTSP_DIR_S1 | PCD_DPWW3_TTSP_DSCR_S1 | PCD_DPWW3_TTSP_DCS_S1 | PCD_DPWW3_TTSP_DSCS_S1 | PCD_DPWW3_TTSP_DPP_S1 | PCD_DPWW3_TTSP_DTPI_S1 | PCD_DPWW3_TTSP_DCI_S1 | PCD_DPWW3_TTSP_DSI_S1 | PCD_DPWW3_TTSP_DER_S1 | PCD_DPWW3_TTSP_RS_S1 | PCD_DPWW3_TTSP_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 2 | Nr | 0 |  | 4 | 3 | 3 | 6 | 6 | 1 | 2 | 4 | 5 | 9 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.14 |  | _S2 |  | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_DLY_S2 | PCD_DPWW3_TTSP_DIR_S2 | PCD_DPWW3_TTSP_DSCR_S2 | PCD_DPWW3_TTSP_DCS_S2 | PCD_DPWW3_TTSP_DSCS_S2 | PCD_DPWW3_TTSP_DPP_S2 | PCD_DPWW3_TTSP_DTPI_S2 | PCD_DPWW3_TTSP_DCI_S2 | PCD_DPWW3_TTSP_DSI_S2 | PCD_DPWW3_TTSP_DER_S2 | PCD_DPWW3_TTSP_RS_S2 | PCD_DPWW3_TTSP_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 1 | 1 | 3 | 1 | 6 | 5 | 3 | 2 | 0 | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.14 |  | _S3 |  | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_DLY_S3 | PCD_DPWW3_TTSP_DIR_S3 | PCD_DPWW3_TTSP_DSCR_S3 | PCD_DPWW3_TTSP_DCS_S3 | PCD_DPWW3_TTSP_DSCS_S3 | PCD_DPWW3_TTSP_DPP_S3 | PCD_DPWW3_TTSP_DTPI_S3 | PCD_DPWW3_TTSP_DCI_S3 | PCD_DPWW3_TTSP_DSI_S3 | PCD_DPWW3_TTSP_DER_S3 | PCD_DPWW3_TTSP_RS_S3 | PCD_DPWW3_TTSP_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 4 | 5 | 7 | 3 | 3 | 3 | 6 | 10 | 10 | 8 | 8 | 7 | 3 | 2 | [12 empty] | DPWW3.14 |  | _S4 |  | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_DLY_S4 | PCD_DPWW3_TTSP_DIR_S4 | PCD_DPWW3_TTSP_DSCR_S4 | PCD_DPWW3_TTSP_DCS_S4 | PCD_DPWW3_TTSP_DSCS_S4 | PCD_DPWW3_TTSP_DPP_S4 | PCD_DPWW3_TTSP_DTPI_S4 | PCD_DPWW3_TTSP_DCI_S4 | PCD_DPWW3_TTSP_DSI_S4 | PCD_DPWW3_TTSP_DER_S4 | PCD_DPWW3_TTSP_RS_S4 | PCD_DPWW3_TTSP_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 10 | 5 | [12 empty] | DPWW3.14 |  | _S5 |  | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_DLY_S5 | PCD_DPWW3_TTSP_DIR_S5 | PCD_DPWW3_TTSP_DSCR_S5 | PCD_DPWW3_TTSP_DCS_S5 | PCD_DPWW3_TTSP_DSCS_S5 | PCD_DPWW3_TTSP_DPP_S5 | PCD_DPWW3_TTSP_DTPI_S5 | PCD_DPWW3_TTSP_DCI_S5 | PCD_DPWW3_TTSP_DSI_S5 | PCD_DPWW3_TTSP_DER_S5 | PCD_DPWW3_TTSP_RS_S5 | PCD_DPWW3_TTSP_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 14 | [12 empty] | DPWW3.14 |  | _S6 |  | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_DLY_S6 | PCD_DPWW3_TTSP_DIR_S6 | PCD_DPWW3_TTSP_DSCR_S6 | PCD_DPWW3_TTSP_DCS_S6 | PCD_DPWW3_TTSP_DSCS_S6 | PCD_DPWW3_TTSP_DPP_S6 | PCD_DPWW3_TTSP_DTPI_S6 | PCD_DPWW3_TTSP_DCI_S6 | PCD_DPWW3_TTSP_DSI_S6 | PCD_DPWW3_TTSP_DER_S6 | PCD_DPWW3_TTSP_RS_S6 | PCD_DPWW3_TTSP_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.14 |  | _S7 |  | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_DLY_S7 | PCD_DPWW3_TTSP_DIR_S7 | PCD_DPWW3_TTSP_DSCR_S7 | PCD_DPWW3_TTSP_DCS_S7 | PCD_DPWW3_TTSP_DSCS_S7 | PCD_DPWW3_TTSP_DPP_S7 | PCD_DPWW3_TTSP_DTPI_S7 | PCD_DPWW3_TTSP_DCI_S7 | PCD_DPWW3_TTSP_DSI_S7 | PCD_DPWW3_TTSP_DER_S7 | PCD_DPWW3_TTSP_RS_S7 | PCD_DPWW3_TTSP_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | [12 empty] | DPWW3.14 |  | _ST |  | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_DLY_ST | PCD_DPWW3_TTSP_DIR_ST | PCD_DPWW3_TTSP_DSCR_ST | PCD_DPWW3_TTSP_DCS_ST | PCD_DPWW3_TTSP_DSCS_ST | PCD_DPWW3_TTSP_DPP_ST | PCD_DPWW3_TTSP_DTPI_ST | PCD_DPWW3_TTSP_DCI_ST | PCD_DPWW3_TTSP_DSI_ST | PCD_DPWW3_TTSP_DER_ST | PCD_DPWW3_TTSP_RS_ST | PCD_DPWW3_TTSP_DPLE_ST
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 0 | Nr | 0 | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | PCD_DPWW3_PR19WINCA | PCD_DPWW3_PR19WINCA_NR | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_DLY | PCD_DPWW3_PR19WINCA_DIR | PCD_DPWW3_PR19WINCA_DSCR | PCD_DPWW3_PR19WINCA_DCS | PCD_DPWW3_PR19WINCA_DSCS | PCD_DPWW3_PR19WINCA_DPP | PCD_DPWW3_PR19WINCA_DTPI | PCD_DPWW3_PR19WINCA_DCI | PCD_DPWW3_PR19WINCA_DSI | PCD_DPWW3_PR19WINCA_DER | PCD_DPWW3_PR19WINCA_RS | PCD_DPWW3_PR19WINCA_DPLE
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 1 | Nr | 0 |  | 4 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S1 |  | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_DLY_S1 | PCD_DPWW3_PR19WINCA_DIR_S1 | PCD_DPWW3_PR19WINCA_DSCR_S1 | PCD_DPWW3_PR19WINCA_DCS_S1 | PCD_DPWW3_PR19WINCA_DSCS_S1 | PCD_DPWW3_PR19WINCA_DPP_S1 | PCD_DPWW3_PR19WINCA_DTPI_S1 | PCD_DPWW3_PR19WINCA_DCI_S1 | PCD_DPWW3_PR19WINCA_DSI_S1 | PCD_DPWW3_PR19WINCA_DER_S1 | PCD_DPWW3_PR19WINCA_RS_S1 | PCD_DPWW3_PR19WINCA_DPLE_S1
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 2 | Nr | 0 |  | 42 | 41 | 37 | 31 | 28 | 22 | 19 | 10 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S2 |  | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_DLY_S2 | PCD_DPWW3_PR19WINCA_DIR_S2 | PCD_DPWW3_PR19WINCA_DSCR_S2 | PCD_DPWW3_PR19WINCA_DCS_S2 | PCD_DPWW3_PR19WINCA_DSCS_S2 | PCD_DPWW3_PR19WINCA_DPP_S2 | PCD_DPWW3_PR19WINCA_DTPI_S2 | PCD_DPWW3_PR19WINCA_DCI_S2 | PCD_DPWW3_PR19WINCA_DSI_S2 | PCD_DPWW3_PR19WINCA_DER_S2 | PCD_DPWW3_PR19WINCA_RS_S2 | PCD_DPWW3_PR19WINCA_DPLE_S2
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 3 | Nr | 0 |  | 1 | 3 | 4 | 5 | 5 | 10 | 7 | 9 | 8 | 4 | 4 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S3 |  | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_DLY_S3 | PCD_DPWW3_PR19WINCA_DIR_S3 | PCD_DPWW3_PR19WINCA_DSCR_S3 | PCD_DPWW3_PR19WINCA_DCS_S3 | PCD_DPWW3_PR19WINCA_DSCS_S3 | PCD_DPWW3_PR19WINCA_DPP_S3 | PCD_DPWW3_PR19WINCA_DTPI_S3 | PCD_DPWW3_PR19WINCA_DCI_S3 | PCD_DPWW3_PR19WINCA_DSI_S3 | PCD_DPWW3_PR19WINCA_DER_S3 | PCD_DPWW3_PR19WINCA_RS_S3 | PCD_DPWW3_PR19WINCA_DPLE_S3
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 4 | Nr | 0 |  | 12 | 13 | 15 | 19 | 13 | 15 | 22 | 29 | 33 | 37 | 37 | 35 | 34 | 31 | 22 | 19 | 14 | 11 | 11 | 9 | 3 | [12 empty] | DPWW3.15 |  | _S4 |  | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_DLY_S4 | PCD_DPWW3_PR19WINCA_DIR_S4 | PCD_DPWW3_PR19WINCA_DSCR_S4 | PCD_DPWW3_PR19WINCA_DCS_S4 | PCD_DPWW3_PR19WINCA_DSCS_S4 | PCD_DPWW3_PR19WINCA_DPP_S4 | PCD_DPWW3_PR19WINCA_DTPI_S4 | PCD_DPWW3_PR19WINCA_DCI_S4 | PCD_DPWW3_PR19WINCA_DSI_S4 | PCD_DPWW3_PR19WINCA_DER_S4 | PCD_DPWW3_PR19WINCA_RS_S4 | PCD_DPWW3_PR19WINCA_DPLE_S4
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S5 |  | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_DLY_S5 | PCD_DPWW3_PR19WINCA_DIR_S5 | PCD_DPWW3_PR19WINCA_DSCR_S5 | PCD_DPWW3_PR19WINCA_DCS_S5 | PCD_DPWW3_PR19WINCA_DSCS_S5 | PCD_DPWW3_PR19WINCA_DPP_S5 | PCD_DPWW3_PR19WINCA_DTPI_S5 | PCD_DPWW3_PR19WINCA_DCI_S5 | PCD_DPWW3_PR19WINCA_DSI_S5 | PCD_DPWW3_PR19WINCA_DER_S5 | PCD_DPWW3_PR19WINCA_RS_S5 | PCD_DPWW3_PR19WINCA_DPLE_S5
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 6 | Nr | 0 |  | 9 | 9 | 10 | 11 | 20 | 20 | 20 | 20 | 23 | 25 | 26 | 30 | 33 | 36 | 45 | 49 | 54 | 57 | 57 | 59 | 65 | 11 |  |  | 4 +3 TBC as these are PCDWW35 CONTRIBUTOR |  |  | 1 | [5 empty] | DPWW3.15 |  | _S6 |  | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_DLY_S6 | PCD_DPWW3_PR19WINCA_DIR_S6 | PCD_DPWW3_PR19WINCA_DSCR_S6 | PCD_DPWW3_PR19WINCA_DCS_S6 | PCD_DPWW3_PR19WINCA_DSCS_S6 | PCD_DPWW3_PR19WINCA_DPP_S6 | PCD_DPWW3_PR19WINCA_DTPI_S6 | PCD_DPWW3_PR19WINCA_DCI_S6 | PCD_DPWW3_PR19WINCA_DSI_S6 | PCD_DPWW3_PR19WINCA_DER_S6 | PCD_DPWW3_PR19WINCA_RS_S6 | PCD_DPWW3_PR19WINCA_DPLE_S6
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S7 |  | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_DLY_S7 | PCD_DPWW3_PR19WINCA_DIR_S7 | PCD_DPWW3_PR19WINCA_DSCR_S7 | PCD_DPWW3_PR19WINCA_DCS_S7 | PCD_DPWW3_PR19WINCA_DSCS_S7 | PCD_DPWW3_PR19WINCA_DPP_S7 | PCD_DPWW3_PR19WINCA_DTPI_S7 | PCD_DPWW3_PR19WINCA_DCI_S7 | PCD_DPWW3_PR19WINCA_DSI_S7 | PCD_DPWW3_PR19WINCA_DER_S7 | PCD_DPWW3_PR19WINCA_RS_S7 | PCD_DPWW3_PR19WINCA_DPLE_S7
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | [12 empty] | DPWW3.15 |  | _ST |  | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_DLY_ST | PCD_DPWW3_PR19WINCA_DIR_ST | PCD_DPWW3_PR19WINCA_DSCR_ST | PCD_DPWW3_PR19WINCA_DCS_ST | PCD_DPWW3_PR19WINCA_DSCS_ST | PCD_DPWW3_PR19WINCA_DPP_ST | PCD_DPWW3_PR19WINCA_DTPI_ST | PCD_DPWW3_PR19WINCA_DCI_ST | PCD_DPWW3_PR19WINCA_DSI_ST | PCD_DPWW3_PR19WINCA_DER_ST | PCD_DPWW3_PR19WINCA_RS_ST | PCD_DPWW3_PR19WINCA_DPLE_ST
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | PCD_DPWW3_GGR1 | PCD_DPWW3_GGR1_NR | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_DLY | PCD_DPWW3_GGR1_DIR | PCD_DPWW3_GGR1_DSCR | PCD_DPWW3_GGR1_DCS | PCD_DPWW3_GGR1_DSCS | PCD_DPWW3_GGR1_DPP | PCD_DPWW3_GGR1_DTPI | PCD_DPWW3_GGR1_DCI | PCD_DPWW3_GGR1_DSI | PCD_DPWW3_GGR1_DER | PCD_DPWW3_GGR1_RS | PCD_DPWW3_GGR1_DPLE
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S1 |  | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_DLY_S1 | PCD_DPWW3_GGR1_DIR_S1 | PCD_DPWW3_GGR1_DSCR_S1 | PCD_DPWW3_GGR1_DCS_S1 | PCD_DPWW3_GGR1_DSCS_S1 | PCD_DPWW3_GGR1_DPP_S1 | PCD_DPWW3_GGR1_DTPI_S1 | PCD_DPWW3_GGR1_DCI_S1 | PCD_DPWW3_GGR1_DSI_S1 | PCD_DPWW3_GGR1_DER_S1 | PCD_DPWW3_GGR1_RS_S1 | PCD_DPWW3_GGR1_DPLE_S1
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S2 |  | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_DLY_S2 | PCD_DPWW3_GGR1_DIR_S2 | PCD_DPWW3_GGR1_DSCR_S2 | PCD_DPWW3_GGR1_DCS_S2 | PCD_DPWW3_GGR1_DSCS_S2 | PCD_DPWW3_GGR1_DPP_S2 | PCD_DPWW3_GGR1_DTPI_S2 | PCD_DPWW3_GGR1_DCI_S2 | PCD_DPWW3_GGR1_DSI_S2 | PCD_DPWW3_GGR1_DER_S2 | PCD_DPWW3_GGR1_RS_S2 | PCD_DPWW3_GGR1_DPLE_S2
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S3 |  | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_DLY_S3 | PCD_DPWW3_GGR1_DIR_S3 | PCD_DPWW3_GGR1_DSCR_S3 | PCD_DPWW3_GGR1_DCS_S3 | PCD_DPWW3_GGR1_DSCS_S3 | PCD_DPWW3_GGR1_DPP_S3 | PCD_DPWW3_GGR1_DTPI_S3 | PCD_DPWW3_GGR1_DCI_S3 | PCD_DPWW3_GGR1_DSI_S3 | PCD_DPWW3_GGR1_DER_S3 | PCD_DPWW3_GGR1_RS_S3 | PCD_DPWW3_GGR1_DPLE_S3
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S4 |  | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_DLY_S4 | PCD_DPWW3_GGR1_DIR_S4 | PCD_DPWW3_GGR1_DSCR_S4 | PCD_DPWW3_GGR1_DCS_S4 | PCD_DPWW3_GGR1_DSCS_S4 | PCD_DPWW3_GGR1_DPP_S4 | PCD_DPWW3_GGR1_DTPI_S4 | PCD_DPWW3_GGR1_DCI_S4 | PCD_DPWW3_GGR1_DSI_S4 | PCD_DPWW3_GGR1_DER_S4 | PCD_DPWW3_GGR1_RS_S4 | PCD_DPWW3_GGR1_DPLE_S4
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S5 |  | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_DLY_S5 | PCD_DPWW3_GGR1_DIR_S5 | PCD_DPWW3_GGR1_DSCR_S5 | PCD_DPWW3_GGR1_DCS_S5 | PCD_DPWW3_GGR1_DSCS_S5 | PCD_DPWW3_GGR1_DPP_S5 | PCD_DPWW3_GGR1_DTPI_S5 | PCD_DPWW3_GGR1_DCI_S5 | PCD_DPWW3_GGR1_DSI_S5 | PCD_DPWW3_GGR1_DER_S5 | PCD_DPWW3_GGR1_RS_S5 | PCD_DPWW3_GGR1_DPLE_S5
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S6 |  | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_DLY_S6 | PCD_DPWW3_GGR1_DIR_S6 | PCD_DPWW3_GGR1_DSCR_S6 | PCD_DPWW3_GGR1_DCS_S6 | PCD_DPWW3_GGR1_DSCS_S6 | PCD_DPWW3_GGR1_DPP_S6 | PCD_DPWW3_GGR1_DTPI_S6 | PCD_DPWW3_GGR1_DCI_S6 | PCD_DPWW3_GGR1_DSI_S6 | PCD_DPWW3_GGR1_DER_S6 | PCD_DPWW3_GGR1_RS_S6 | PCD_DPWW3_GGR1_DPLE_S6
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S7 |  | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_DLY_S7 | PCD_DPWW3_GGR1_DIR_S7 | PCD_DPWW3_GGR1_DSCR_S7 | PCD_DPWW3_GGR1_DCS_S7 | PCD_DPWW3_GGR1_DSCS_S7 | PCD_DPWW3_GGR1_DPP_S7 | PCD_DPWW3_GGR1_DTPI_S7 | PCD_DPWW3_GGR1_DCI_S7 | PCD_DPWW3_GGR1_DSI_S7 | PCD_DPWW3_GGR1_DER_S7 | PCD_DPWW3_GGR1_RS_S7 | PCD_DPWW3_GGR1_DPLE_S7
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _ST |  | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_DLY_ST | PCD_DPWW3_GGR1_DIR_ST | PCD_DPWW3_GGR1_DSCR_ST | PCD_DPWW3_GGR1_DCS_ST | PCD_DPWW3_GGR1_DSCS_ST | PCD_DPWW3_GGR1_DPP_ST | PCD_DPWW3_GGR1_DTPI_ST | PCD_DPWW3_GGR1_DCI_ST | PCD_DPWW3_GGR1_DSI_ST | PCD_DPWW3_GGR1_DER_ST | PCD_DPWW3_GGR1_RS_ST | PCD_DPWW3_GGR1_DPLE_ST
[44 empty] | Data_End | [35 empty] | BON_End

## DPWW4
DPWW4
Scheme-level data - Wastewater - Enhanced engagement, Large gated and Critical High-profile schemes
| Company | Scheme name | Scheme ID | WINEP ID | Line description | PCD ref | Type of scheme (retained/dropped/added) | Name of the substituted scheme | Original regulatory date | Current regulatory date | Interim milestone completion dates - Baseline | [6 empty] | Current interim milestone | Interim milestone completion dates - Forecast | [6 empty] | Primary reson for delay where IM date moves more than 90 days later than baseline | Spend to date (£m) - cumulative | Forecast expenditure to complete scheme (£m) - cumulative | Forecast outturn cost (£m) | % Spend to date | Baseline expenditure profile (£m) - cumulative | [7 empty] | Forecast expenditure profile (£m) - cumulative | [7 empty] | Critical high profile (Yes/No) | Type of scheme (enhanced engagement, large gated, delivery mechanism, other) | AMP
[31 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9
[11 empty] | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 |  | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 | [5 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total
| TMS | Beckton STW SPG | M184 |  | Gated scheme - NO PCD | Gated scheme - NO PCD | Retained |  |  |  | 2025-09-08 | 2029-01-11 | 2031-03-31 | 2032-07-01 | 2035-06-30 | 2036-03-31 |  | IM2 | 2025-09-08 | 2025-12-09 | 2028-05-31 | 2029-07-31 | 2033-09-30 | 2033-09-30 |  |  | 1.3806 | 351.156 | 352.5366 | 0.3916% |  |  | 3.2134 | 6.4269 | 12.4922 | 27.6355 | 68.545 | 277.023 | 0 | 0 | 1.3806 | 4.2086 | 10.4236 | 44.2236 | 93.5266 | 352.5366 | No | Large gated | AMP8
| TMS | Phosphorus Investigations | UBA8.SEW.S39057 | 08TW100198a, 08TW100197a | WINEP Investigations (wastewater) | PCDWW18 | Dropped |  | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  | IM6 | 2024-06-19 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 0 | 0 | 0 | #DIV/0! |  |  |  | 1.4632 | 3.3919 | 3.8597 | 3.8597 | 3.8597 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | WWNI PR24 WINEP WFD SW Investigations | M146 | 08TW100196a, 08TW100186a | WINEP Investigations (wastewater) | PCDWW18 | Dropped | UBA8.SEW.S38654 | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  | IM6 | 2024-06-10 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 | 2025-08-22 |  | 0 | 0 | 0 | #DIV/0! |  |  | 1.4338 | 2.8677 | 4.3015 | 4.3015 | 4.3015 | 4.3015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | Bexley WTW – Alleviation of Low Flows (W | K035.01 | KSL00046 | River restoration to improve flow conditions in the lower Cray | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-03-25 | 2021-05-26 | 2025-06-30 | 2026-01-05 | 2030-06-13 | 2030-05-29 |  | IM4 | 2020-03-25 | 2021-05-26 | 2025-05-16 | 2025-12-23 | 2030-06-04 | 2030-05-24 |  |  | 6.5679 | 1.4657 | 8.0336 | 81.75% | 5.5566 | 6.4673 | 10.786 | 44.971 | 71.7926 | 82.0305 | 83.9824 | 85.4069 | 5.3275 | 6.4711 | 6.5679 | 6.9211 | 7.3426 | 7.72 | 8.0027 | 8.0336 | No | Other | AMP7
| TMS | Bexley WTW – Alleviation of Low Flows (W | K035.01 | KSL00044 | Closure of the North Orpington abstraction to protect the environment in the river Cray. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-03-25 | 2021-05-26 | 2025-06-30 | 2026-01-05 | 2030-06-13 | 2030-05-29 |  | IM4 | 2020-03-25 | 2021-05-26 | 2025-05-16 | 2025-12-23 | 2030-06-04 | 2030-05-24 |  |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | LF Mitigation London - Upper Cray Restoration | K561.01 | KSL00046 | River restoration to improve flow conditions in the lower Cray | PCDWW35 (Contributor) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  | Change in solution | 0.54088 | 0 | 0.54088 | 100% | 0.53301 | 0.54088 | 0.79977 | 0.90408 | 1.6759 | 1.906 | 1.9142 | 1.9142 | 0.53301 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | No | Other | AMP7
| TMS | West Wickham WTW Crypto & Turbidity | L659.01 | KSL00044 | Closure of the North Orpington abstraction to protect the environment in the river Cray. | PCDWW35 (Contributor) | Retained |  | 2024-12-22 | 2024-12-22 | 2024-04-16 | 2025-02-19 | 2026-05-29 | 2026-12-14 | 2029-02-21 | 2028-12-04 |  | IM2 | 2024-04-16 | 2025-02-19 | 2026-10-29 | 2027-05-12 | 2029-02-21 | 2030-05-24 |  | Change in solution | 1.3708 | 10.0809 | 11.4516 | 11.97% |  | 0.30318 | 1.7982 | 2.9618 | 8.9769 | 11.4174 | 11.5439 | 11.5439 | 0 | 0.30318 | 1.3708 | 2.4515 | 7.1719 | 11.3246 | 11.4516 | 11.4516 | No | Other | AMP7
| TMS | Shortlands Borehole Output | K609.01 | KSL00044 | Closure of the North Orpington abstraction to protect the environment in the river Cray. | PCDWW35 (Contributor) | Retained |  | 2024-12-22 | 2024-12-22 | 2021-09-22 | 2022-11-23 | 2025-12-23 | 2026-06-24 | 2027-06-07 | 2027-10-01 |  | IM4 | 2021-09-22 | 2022-11-23 | 2026-02-16 | 2026-03-13 | 2028-03-06 | 2030-05-24 |  | Change in solution | 1.2222 | 5.5417 | 6.7638 | 18.07% | 0.36597 | 0.42222 | 0.59999 | 3.2874 | 3.4013 | 3.4109 | 3.4109 | 3.4109 | 0.36597 | 0.42222 | 1.2222 | 4.4411 | 6.7496 | 6.7638 | 6.7638 | 6.7638 | No | Other | AMP7
| TMS | LF Mitigation TV - Continue the river restoration work from AMP7 for Farmoor (Oxford Water Course) | K560.01 | THM00759 | River restoration to improve environmental resiliance on the Oxford Watercourses. | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2025-10-24 | 2025-11-14 | 2027-02-08 | 2027-02-02 |  | IM4 | 2020-05-13 | 2022-03-16 | 2025-05-29 | 2026-05-01 | 2027-02-08 | 2026-12-02 |  |  | 0.24185 | 2.0384 | 2.2803 | 10.61% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.23393 | 0.21361 | 0.24185 | 0.54476 | 2.1848 | 2.2803 | 2.2803 | 2.2803 | No | Other | AMP7
| TMS | LF Mitigation TV - Continue the river restoration work from AMP7 for Pangbourne on the Sulham Brook | K560.02 | THM00758 | River restoration to improve environmental resiliance on the Sulham Brook. | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2025-04-01 | 2025-08-15 | 2026-06-19 | 2026-05-31 |  | IM6 | 2020-05-13 | 2022-03-16 | 2025-01-20 | 2025-04-14 | 2026-05-06 | 2026-03-31 |  |  | 0.5434 | 0 | 0.5434 | 100% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.23393 | 0.21361 | 0.5434 | 0.5434 | 0.5434 | 0.5434 | 0.5434 | 0.5434 | No | Other | AMP7
| TMS | LF Mitigation TV - Continue the river restoration work from AMP7 for Pann Mill | K560.03 | THM00760 | River restoration to improve environmental resiliance on the river Wye | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2027-08-23 | 2028-01-10 | 2029-01-18 | 2028-12-26 |  | IM2 | 2020-05-13 | 2022-03-16 | 2027-11-29 | 2028-04-18 | 2029-04-27 | 2029-02-08 |  |  | 0.11004 | 0 | 0.11004 | 100% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.12051 | 0.11004 | 0.11004 | 0.11004 | 0.11004 | 0.11004 | 0.11004 | 0.11004 | No | Other | AMP7
| TMS | LF Mitigation TV - RIVER RESTORATION PROJECTS - CHESS | K560.04 | HNL00095 | River restoration to improve environmental resiliance on the river Chess | PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2020-05-13 | 2022-03-16 | 2022-03-16 | 2025-03-28 | 2026-06-19 | 2026-05-31 |  | IM6 | 2020-05-13 | 2022-03-16 | 2022-03-16 | 2025-03-28 | 2026-07-28 | 2026-02-27 |  |  | 0.41096 | 0 | 0.41096 | 100% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.12051 | 0.11004 | 0.41096 | 0.41096 | 0.41096 | 0.41096 | 0.41096 | 0.41096 | No | Other | AMP7
| TMS | Fish passage at Fobney Turbine House | K558.01 | THM00690 | Improving fish passage on the river Kennet at the turbine house structure. | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-12-31 | 2025-12-31 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-10-24 | 2027-04-21 | 2027-05-31 |  | IM3 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2026-11-27 | 2027-12-16 | 2027-11-25 |  | Third party interface | 1.6854 | 4.5031 | 6.1885 | 27.23% | 0.95533 | 1.5282 | 4.6307 | 9.1237 | 9.1237 | 9.1237 | 9.1237 | 9.1237 | 0.95533 | 1.5282 | 1.6854 | 2.7131 | 6.1885 | 6.1885 | 6.1885 | 6.1885 | No | Other | AMP7
| TMS | Fish passage at Glenfield Gate weir on the Cherwell d/s of Grimsbury Reservoir abstraction | K558.02 | THM00691 | Improving fish passage on the river Cherwell at Glenfield Gate | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2020-05-13 | 2023-06-01 | 2023-06-01 | 2025-08-14 | 2027-06-17 | 2027-05-31 |  | IM4 | 2020-05-13 | 2023-06-01 | 2023-06-01 | 2026-03-30 | 2027-06-17 | 2027-03-31 |  |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | Fish Passage at River Pang at Pangbourne WTW | K558.03 | THM00692 | Improving fish passage on the river Pang at Pang Water Treatment Works | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-08-14 | 2027-06-17 | 2027-05-31 |  | IM4 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2026-04-30 | 2027-06-17 | 2027-03-31 |  |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | Fish Passage on the River Thames at Tangier Mill | K558.04 | THM00694 | Improving fish passage on the river Thames at Tangier Mill | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-09-01 | 2027-06-17 | 2027-05-31 |  | IM4 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2026-04-30 | 2027-06-17 | 2027-11-25 |  | Third party interface | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | Hawridge - Alleviation of Low Flows | K036.01 | HNL00092 | Closure of the abstraction at Hawridge in the Chess catchment | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-25 | 2021-05-27 | 2026-11-20 | 2027-08-12 | 2029-11-01 | 2029-11-10 |  | IM2 | 2020-02-25 | 2021-05-27 | 2027-10-29 | 2028-10-24 | 2032-02-06 | 2031-12-08 |  | Third party interface | 3.1428 | 94.1921 | 97.3349 | 3.229% | 2.3504 | 2.7251 | 4.8787 | 7.8833 | 15.0822 | 34.1807 | 52.9793 | 52.9793 | 2.3504 | 2.7251 | 3.1428 | 4.235 | 10.8169 | 25.1043 | 38.4005 | 97.3349 | No | Other | AMP7
| TMS | Hogsmill Biodiversity (WINEP) | L443.01 | KSL00092 | Improving habitat for water voles on riparian habitat around the Hogsmill STW discharge | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-09-26 | 2023-06-20 | 2024-12-06 | 2026-02-09 | 2027-01-20 | 2027-02-11 |  | IM4 | 2019-09-26 | 2023-06-20 | 2024-12-06 | 2026-05-27 | 2027-01-20 | 2026-12-11 |  |  | 1.199 | 2.079 | 3.2779 | 36.58% | 0.12331 | 0.46117 | 1.0298 | 2.7626 | 2.7626 | 2.7626 | 2.7626 | 2.7626 | 0.12332 | 0.46117 | 1.199 | 3.2779 | 3.2779 | 3.2779 | 3.2779 | 3.2779 | No | Other | AMP7
| TMS | Nitrates Reduction Lee (Rye Meads) | K562.01 | HNL00262 | Reduction in nitrates in Rye Meads STW effluent discharge to improve water quality at lower Lee abstraction points | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-02 | 2023-03-22 | 2026-04-13 | 2027-01-29 | 2030-06-20 | 2030-07-01 |  | IM3 | 2020-11-02 | 2023-03-22 | 2026-03-25 | 2027-01-29 | 2030-06-20 | 2030-05-01 |  |  | 1.6125 | 33.6271 | 35.2396 | 4.576% | 0.5656 | 1.0386 | 1.626 | 3.0789 | 7.0648 | 19.6442 | 23.832 | 24.2611 | 0.5656 | 1.0386 | 1.6125 | 5.1352 | 17.8499 | 30.3349 | 33.5408 | 35.2396 | No | Other | AMP7
| TMS | Lower Lee River Improvements | K559.01 | HNL00096 | River restoration and improvements to fish passage in the Lower lee to improve environmental resilience | PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2021-05-04 | 2022-01-25 | 2026-10-07 | 2027-02-11 | 2029-04-27 | 2029-02-15 |  | IM2 | 2021-05-04 | 2022-01-25 | 2026-10-07 | 2027-02-11 | 2029-04-27 | 2028-12-15 |  |  | 1.15 | 9.0968 | 10.2468 | 11.22% | 0.45493 | 0.46531 | 0.7329 | 1.3518 | 6.1089 | 10.1286 | 10.188 | 10.2071 | 0.45493 | 0.46531 | 1.15 | 1.8837 | 5.8455 | 10.1682 | 10.2275 | 10.2468 | No | Other | AMP7
| TMS | LF Mitigation London - Upper Cray Restoration | K561.01 | KSL00401 | River restoration to improve environmental resilience on the river Cray. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 0.54088 | 0 | 0.54088 | 100% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.53301 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | 0.54088 | No | Other | AMP7
| TMS | LF Mitigation London - Upper Darent Restoration - SUNDRIDGE PUMPING STATION | K561.02 | KSL00045 | River restoration to improve environmental resilience on the river Darent. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 0.15144 | 3.2261 | 3.3775 | 4.484% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.1066 | 0.10818 | 0.15144 | 0.21931 | 2.5435 | 3.3522 | 3.3775 | 3.3775 | No | Other | AMP7
| TMS | LF Mitigation London - Upper Darent Restoration - WESTERHAM HILL PS | K561.03 | KSL00049 | River restoration to improve environmental resilience on the river Darent. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 0.10818 | 0 | 0.10818 | 100% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.1066 | 0.10818 | 0.10818 | 0.10818 | 0.10818 | 0.10818 | 0.10818 | 0.10818 | No | Other | AMP7
| TMS | LF Mitigation London - Wandle Restoration - BRANTWOOD ROAD, CROYDON | K561.04 | KSL00047 | River restoration to improve environmental resilience on the river Wandle | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 0.11664 | 1.0754 | 1.192 | 9.785% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.1066 | 0.10818 | 0.11664 | 0.13927 | 0.91399 | 1.1836 | 1.192 | 1.192 | No | Other | AMP7
| TMS | LF Mitigation London - Wandle Restoration - WADDON PUMPING STATION - WELLS & BOREHOLES | K561.05 | KSL00048 | River restoration to improve environmental resilience on the river Wandle | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 0.11664 | 1.0754 | 1.192 | 9.785% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.1066 | 0.10818 | 0.11664 | 0.13927 | 0.91399 | 1.1836 | 1.192 | 1.192 | No | Other | AMP7
| TMS | Guildford STW Relocation Delivery | J009 | THM00529 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2026-03-31 | 2019-05-01 | 2019-05-01 | 2021-07-30 | 2022-10-26 | 2027-07-19 | 2026-11-30 |  | IM4 | 2019-05-01 | 2019-05-01 | 2021-07-30 | 2022-10-26 | 2027-10-08 | 2027-07-28 |  |  | 116.8653 | 1.3754 | 118.2407 | 98.84% | 65.6567 | 114.8098 | 143.8678 | 171.6955 | 171.7153 | 171.7153 | 171.7153 | 171.7153 | 65.6567 | 114.8098 | 116.8653 | 117.8247 | 118.2407 | 118.2407 | 118.2407 | 118.2407 | Yes | Other | AMP7
| TMS | East Hyde AMP7 Growth | J568 | HNL00214 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-21 | 2021-03-24 | 2026-09-30 | 2026-09-30 | 2028-11-30 | 2029-04-28 |  | IM2 | 2020-02-21 | 2021-03-24 | 2026-09-30 | 2027-02-02 | 2030-03-31 | 2030-03-31 |  | Contract Programme | 3.8589 | 13.0435 | 16.9024 | 22.83% | 2.1912 | 3.0533 | 9.1299 | 29.6892 | 62.8351 | 105.01 | 105.01 | 105.01 | 2.1912 | 3.0533 | 3.8589 | 6.4017 | 10.7285 | 14.8606 | 16.9024 | 16.9024 | Yes | Other | AMP7
| TMS | Kingston Bagpuize STW Growth and Quality | J971.01 | FLO01277 | Storm Tank | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-03-31 | 2024-12-22 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2026-08-16 |  | IM6 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2026-07-01 |  |  | 2.6948 | 0.67043 | 3.3652 | 80.08% | 1.097 | 2.1709 | 4.8346 | 6.2199 | 6.2478 | 6.2478 | 6.2478 | 6.2478 | 1.097 | 2.1709 | 2.6948 | 3.2449 | 3.3652 | 3.3652 | 3.3652 | 3.3652 | No | Other | AMP7
| TMS | Kingston Bagpuize STW Growth and Quality | J971.01 | THM00536 | Ammonia | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2027-07-28 |  | IM4 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2027-05-28 |  |  | 4.2663 | 2.6817 | 6.9481 | 61.4% | 4.388 | 8.6836 | 19.3382 | 24.8794 | 24.9912 | 24.9912 | 24.9912 | 24.9912 | 1.097 | 2.1709 | 4.2663 | 6.467 | 6.9481 | 6.9481 | 6.9481 | 6.9481 | No | Other | AMP7
| TMS | Dorking STW Storm Compliance | J982.01 | FLO01261 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-08-21 | 2020-01-21 | 2023-03-17 | 2024-05-09 | 2025-12-23 | 2025-10-20 |  | IM6 | 2019-08-21 | 2020-01-21 | 2023-03-17 | 2024-05-09 | 2025-12-16 | 2025-08-20 |  |  | 9.5749 | 0.066763 | 9.6417 | 99.31% | 2.1319 | 7.4179 | 10.1379 | 10.1418 | 10.1418 | 10.1418 | 10.1418 | 10.1418 | 2.1319 | 7.4179 | 9.5749 | 9.6417 | 9.6417 | 9.6417 | 9.6417 | 9.6417 | No | Other | AMP7
| TMS | Haslemere STW Early Procurement | J983.01 | THM00531 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-08-21 | 2021-11-24 | 2025-11-17 | 2026-01-19 | 2028-01-06 | 2028-01-09 |  | IM4 | 2019-08-21 | 2021-11-24 | 2025-07-25 | 2026-01-09 | 2028-01-06 | 2027-11-09 |  |  | 6.7287 | 19.1404 | 25.8692 | 26.01% | 1.115 | 3.3418 | 4.9119 | 20.5348 | 26.5252 | 27.3685 | 27.3685 | 27.3685 | 1.115 | 3.3418 | 6.7287 | 15.4032 | 25.847 | 25.8692 | 25.8692 | 25.8692 | No | Other | AMP7
| TMS | Cranleigh STW Flow Compliance &P-Removal | J984.01 | THM00514 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-09-11 | 2028-09-14 | 2028-09-27 |  | IM2 | 2019-06-18 | 2025-05-22 | 2027-03-23 | 2027-04-21 | 2028-11-22 | 2028-10-04 |  |  | 1.2591 | 24.5725 | 25.8316 | 4.874% | 0.57152 | 0.83409 | 1.6437 | 8.8481 | 22.3196 | 26.4894 | 27.2042 | 27.2042 | 0.57455 | 0.8385 | 1.2591 | 3.2364 | 11.1385 | 20.6857 | 25.8316 | 25.8316 | No | Other | AMP7
| TMS | Cranleigh STW Flow Compliance &P-Removal | J984.01 | THM00659 | P - Green | This part of the AMP7 project is not PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-09-11 | 2028-09-14 | 2028-09-27 |  | IM2 | 2019-06-18 | 2025-05-22 | 2027-03-23 | 2027-04-21 | 2028-11-22 | 2028-10-04 |  |  | 1.1597 | 18.7653 | 19.9249 | 5.82% | 0.43645 | 0.63697 | 1.2552 | 6.757 | 17.0448 | 20.2291 | 20.775 | 20.775 | 0.57455 | 0.8385 | 1.1597 | 2.6697 | 8.7043 | 15.9952 | 19.9249 | 19.9249 | No | Other | AMP7
| TMS | Heath Lake SSSI Enhancements | J985.01 | THM00074 | Phosphorous | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-09-26 | 2020-01-21 | 2025-06-16 | 2025-08-22 | 2026-11-13 | 2026-12-08 |  | IM4 | 2019-09-26 | 2020-01-21 | 2025-04-30 | 2026-01-19 | 2026-10-16 | 2026-08-20 |  |  | 2.3774 | 4.9284 | 7.3058 | 32.54% | 0.61877 | 0.88896 | 2.8243 | 8.4432 | 8.5892 | 8.5892 | 8.5892 | 8.5892 | 0.71615 | 0.98634 | 2.3774 | 7.2802 | 7.3058 | 7.3058 | 7.3058 | 7.3058 | No | Other | AMP7
| TMS | Harpenden STW Flow compliance and Low P | J988.01 | HNL00215 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-09-09 | 2021-09-22 | 2025-08-01 | 2026-01-02 | 2028-06-30 | 2028-05-30 |  | IM4 | 2020-09-09 | 2021-09-14 | 2026-04-30 | 2026-05-31 | 2029-06-30 | 2028-08-31 |  |  | 6.0081 | 16.9339 | 22.942 | 26.19% | 1.5291 | 3.3785 | 9.8025 | 31.5062 | 54.2955 | 61.074 | 61.074 | 61.074 | 1.5291 | 3.3785 | 6.0081 | 11.3214 | 19.0728 | 22.0236 | 22.942 | 22.942 | No | Other | AMP7
| TMS | Burstow STW Growth & Flow Compliance | J991.01 | KSL00235 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-02-20 | 2021-04-21 | 2021-12-03 | 2022-07-21 | 2026-02-03 | 2026-01-11 |  | IM6 | 2019-02-20 | 2021-04-21 | 2021-12-03 | 2022-07-21 | 2026-05-19 | 2026-03-31 |  |  | 26.3264 | 0.22424 | 26.5507 | 99.16% | 14.8499 | 24.9506 | 29.608 | 29.608 | 29.608 | 29.608 | 29.608 | 29.608 | 14.8499 | 24.9506 | 26.3264 | 26.5507 | 26.5507 | 26.5507 | 26.5507 | 26.5507 | No | Other | AMP7
| TMS | WINEP FtFT Witney STW | K081.01 | FLO01303 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2020-09-30 | 2021-12-23 | 2023-04-21 | 2026-01-29 | 2025-11-23 |  | IM6 | 2019-06-18 | 2020-09-30 | 2021-12-23 | 2023-04-21 | 2026-02-27 | 2025-11-25 |  |  | 17.984 | 0.40759 | 18.3916 | 97.78% | 6.6023 | 12.8604 | 17.9357 | 17.9357 | 17.9357 | 17.9357 | 17.9357 | 17.9357 | 6.6023 | 12.8604 | 17.984 | 18.3916 | 18.3916 | 18.3916 | 18.3916 | 18.3916 | No | Other | AMP7
| TMS | Shutford STW - G2G Flow Compliance | K082.01 | THM00554 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-20 | 2022-09-21 | 2024-07-01 | 2024-08-12 | 2026-03-23 | 2026-03-06 |  | IM6 | 2020-02-20 | 2022-09-21 | 2024-07-01 | 2024-08-12 | 2026-07-31 | 2026-01-15 |  |  | 10.8988 | 0.33917 | 11.238 | 96.98% | 1.1141 | 6.1621 | 12.5366 | 12.7038 | 12.7038 | 12.7038 | 12.7038 | 12.7038 | 1.1141 | 6.1621 | 10.8988 | 11.202 | 11.238 | 11.238 | 11.238 | 11.238 | No | Other | AMP7
| TMS | Bordon Flow Compliance | K104.01 | THM00497 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-27 | 2021-12-03 | 2025-11-21 | 2025-12-22 | 2031-10-20 | 2028-09-28 |  | IM4 | 2020-02-27 | 2021-12-03 | 2025-11-28 | 2025-12-22 | 2028-12-20 | 2028-07-28 |  |  | 5.7519 | 46.3272 | 52.0791 | 11.04% | 2.16 | 3.607 | 5.7065 | 13.0282 | 30.4227 | 47.7853 | 59.2638 | 63.2304 | 2.16 | 3.607 | 5.7519 | 7.0717 | 12.6068 | 29.0089 | 45.5721 | 52.0791 | No | Other | AMP7
| TMS | Slough STW WW Quality AMP7 New Permit | K222.01 | THM00672 and THM00099 | Ammonia and FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2020-11-30 | 2024-02-28 | 2025-05-30 | 2026-04-30 | 2029-05-31 | 2029-06-30 |  | IM3 | 2020-11-30 | 2024-02-28 | 2025-11-18 | 2027-04-18 | 2029-12-18 | 2029-11-19 |  |  | 3.8754 | 0 | 3.8754 | 100% | 3.0856 | 3.8754 | 8.4705 | 27.0134 | 51.4712 | 75.1243 | 75.8345 | 75.8345 | 3.0856 | 3.8754 | 3.8754 | 3.8754 | 3.8754 | 3.8754 | 3.8754 | 3.8754 | No | Other | AMP7
| TMS | Oxford STW AMP 7 | K245.01 | FLO01287 and THM00722 | FTFT and Ammonia | PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2021-04-30 | 2022-01-31 | 2025-12-31 | 2027-03-30 | 2032-03-30 | 2032-02-29 |  | IM3 | 2024-09-18 | 2024-10-03 | 2025-12-11 | 2027-05-28 | 2030-03-31 | 2029-12-24 |  |  | 12.7282 | 64.9839 | 77.712 | 16.38% | 7.935 | 10.8054 | 14.5077 | 37.4351 | 77.4519 | 118.5384 | 160.2726 | 282.4933 | 7.9349 | 10.8054 | 12.7282 | 17.5828 | 33.4695 | 54.57 | 76.4598 | 77.712 | No | Other | AMP7
| TMS | Maple Lodge STW Quality AMP7 New Permit | K298.01 | HNL00234 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2025-03-31 | 2024-12-22 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-12-31 | 2030-11-30 |  | IM3 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-09-30 | 2030-03-29 |  |  | 5.6403 | 100.2472 | 105.8875 | 5.327% | 0.73363 | 1.5186 | 3.2798 | 10.8929 | 36.7689 | 73.2689 | 109.4839 | 132.222 | 1.4673 | 3.0372 | 5.6403 | 13.3091 | 36.7824 | 66.922 | 94.496 | 105.8875 | Yes | Other | AMP7
| TMS | Maple Lodge STW Quality AMP7 New Permit | K298.01 | HNL00192 | Storm Tank | PCDWW35 | Retained |  | 2024-12-22 | 2025-03-31 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-12-31 | 2030-11-30 |  | IM3 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-09-30 | 2030-03-29 |  |  | 0 | 0 | 0 | #DIV/0! | 0.37793 | 0.78232 | 1.6896 | 5.6115 | 18.9416 | 37.7446 | 56.4008 | 68.1144 | [8 empty] | Yes | Other | AMP7
| TMS | Croughton STW P-Removal | K428.01 | THM00660 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2025-03-31 | 2021-01-21 | 2021-06-23 | 2025-09-30 | 2025-10-01 | 2026-10-22 | 2026-10-25 |  | IM6 | 2021-01-21 | 2021-06-23 | 2026-01-09 | 2026-01-13 | 2026-11-16 | 2026-03-05 |  |  | 1.5416 | 0.12921 | 1.6708 | 92.27% | 0.69881 | 1.2221 | 2.5222 | 3.2881 | 3.3067 | 3.3113 | 3.3113 | 3.3113 | 0.69881 | 1.2221 | 1.5416 | 1.6708 | 1.6708 | 1.6708 | 1.6708 | 1.6708 | No | Other | AMP7
| TMS | Banbury STW FTFT and Low P | K435.01 | THM00088 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-15 | 2026-03-20 | 2026-06-26 | 2029-04-03 | 2029-05-29 |  | IM2 | 2019-06-18 | 2026-03-19 | 2026-09-24 | 2027-02-19 | 2029-07-18 | 2029-03-29 |  |  | 0.77096 | 0 | 0.77096 | 100% | 0.6596 | 0.77096 | 1.5166 | 3.3602 | 7.1484 | 9.1462 | 9.2602 | 9.3217 | 0.65961 | 0.77096 | 0.77096 | 0.77096 | 0.77096 | 0.77096 | 0.77096 | 0.77096 | No | Other | AMP7
| TMS | Banbury STW FTFT and Low P | K435.01 | THM00078 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Dropped |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-15 | 2026-03-20 | 2026-06-26 | 2029-04-03 | 2029-05-29 |  | IM6 | 2019-06-18 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | WWNI Therfield STW Storm Tank & Low P | K440.01 | HNL00219 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2024-12-22 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-05-14 | 2027-05-22 |  | IM4 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-06-16 | 2027-04-26 |  |  | 7.2776 | 4.2175 | 11.4951 | 63.31% | 1.5159 | 3.8484 | 10.6087 | 15.127 | 15.8579 | 15.8579 | 15.8579 | 15.8579 | 1.5159 | 3.8484 | 7.2776 | 10.9651 | 11.4951 | 11.4951 | 11.4951 | 11.4951 | No | Other | AMP7
| TMS | WWNI Therfield STW Storm Tank & Low P | K440.01 | FLO01297 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2025-03-31 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-05-14 | 2027-05-22 |  | IM4 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-06-16 | 2027-04-26 |  |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | WWNI Alton STW P-removal | K444.01 | THM00575 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-06-17 | 2025-11-24 | 2026-07-20 | 2028-02-24 | 2028-02-20 |  | IM2 | 2021-01-26 | 2021-06-17 | 2026-07-22 | 2026-08-18 | 2028-03-16 | 2028-01-18 |  |  | 1.4569 | 17.7623 | 19.2192 | 7.581% | 0.99719 | 1.0903 | 1.3811 | 5.8933 | 12.1094 | 12.1678 | 12.1741 | 12.1741 | 0.99719 | 1.0903 | 1.4569 | 3.9784 | 11.88 | 18.9622 | 19.2192 | 19.2192 | No | Other | AMP7
| TMS | WWNI Fleet STW P-removal | K444.04 | THM00096 | FTFT | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-07-21 | 2026-09-01 | 2026-10-22 | 2030-11-01 | 2030-11-03 |  | IM3 | 2019-06-18 | 2021-07-21 | 2026-06-01 | 2026-10-22 | 2030-05-30 | 2030-03-26 |  |  | 1.9694 | 12.4856 | 14.455 | 13.62% | 0.67178 | 1.7968 | 2.5919 | 3.2586 | 8.846 | 26.5872 | 45.7786 | 54.2318 | 0.67254 | 1.7988 | 1.9694 | 2.5298 | 5.3686 | 9.6678 | 13.421 | 14.455 | No | Other | AMP7
| TMS | WWNI Fleet STW P-removal | K444.04 | THM00599 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-06-18 | 2021-07-21 | 2026-09-01 | 2026-10-22 | 2030-11-01 | 2030-11-03 |  | IM3 | 2019-06-18 | 2021-07-21 | 2026-06-01 | 2026-10-22 | 2030-05-30 | 2030-03-26 |  |  | 2.6317 | 60.9591 | 63.5908 | 4.138% | 0.27546 | 0.73675 | 1.0628 | 1.3362 | 3.6272 | 10.9018 | 18.771 | 22.2372 | 0.67254 | 1.7988 | 2.6317 | 5.368 | 19.2279 | 40.2179 | 58.5425 | 63.5908 | No | Other | AMP7
| TMS | Bourton on the Water STW FTFT & St. Tank | K445.01 | FLO01241 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2026-06-01 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2027-11-30 | 2027-08-06 |  | Third party interface | 20.4632 | 4.4782 | 24.9414 | 82.05% | 8.6974 | 16.9054 | 26.5415 | 27.3071 | 27.3071 | 27.3071 | 27.3071 | 27.3071 | 8.6974 | 16.9054 | 20.4632 | 23.5533 | 24.9414 | 24.9414 | 24.9414 | 24.9414 | No | Other | AMP7
| TMS | Bourton on the Water STW FTFT & St. Tank | K445.01 | FLO01242 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2026-06-01 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2027-11-30 | 2027-08-06 |  | Change in solution | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | WWNI Bampton STW FTFT | K450.01 | FLO01235 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-06-30 | 2026-04-09 | 2026-04-23 | 2028-03-20 | 2028-03-17 |  | IM2 | 2019-06-18 | 2021-06-30 | 2026-12-10 | 2026-12-18 | 2028-09-06 | 2028-07-04 |  | Contractual issues | 1.0185 | 7.9596 | 8.9781 | 11.34% | 0.27335 | 0.52918 | 0.92041 | 3.2872 | 5.4674 | 5.5037 | 5.5037 | 5.5037 | 0.27335 | 0.52917 | 1.0185 | 1.9387 | 5.8846 | 8.9571 | 8.9781 | 8.9781 | No | Other | AMP7
| TMS | WWNI Fairford STW FTFT | K452.01 | THM00095 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2023-04-20 | 2026-04-01 | 2026-04-16 | 2027-12-09 | 2028-01-17 |  | IM2 | 2019-06-18 | 2023-04-20 | 2026-08-11 | 2026-09-10 | 2028-03-10 | 2028-02-17 |  | Change in solution | 1.1998 | 10.8442 | 12.044 | 9.961% | 0.47775 | 0.67996 | 1.409 | 8.2911 | 12.1138 | 12.2216 | 12.2216 | 12.2216 | 0.47775 | 0.67996 | 1.1998 | 2.9235 | 8.369 | 12.044 | 12.044 | 12.044 | No | Other | AMP7
| TMS | WWNI Cricklade STW FTFT & Storm Tank | K455.01 | FLO01257 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2024-11-30 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-11-30 | 2026-11-30 |  | IM4 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-09-11 | 2026-07-10 |  |  | 5.1473 | 0.17326 | 5.3206 | 96.74% | 2.0403 | 3.2269 | 6.4141 | 6.4141 | 6.4141 | 6.4141 | 6.4141 | 6.4141 | 2.0403 | 3.2269 | 5.1473 | 5.3206 | 5.3206 | 5.3206 | 5.3206 | 5.3206 | No | Other | AMP7
| TMS | WWNI Cricklade STW FTFT & Storm Tank | K455.01 | FLO01256 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2024-11-30 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-11-30 | 2026-11-30 |  | IM6 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-09-11 | 2025-12-31 |  |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | Blackbirds STW Quality AMP7 New Permit | K537.01 | HNL00233 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-09-30 | 2025-10-23 | 2026-09-01 | 2027-04-14 | 2029-10-12 | 2029-09-27 |  | IM2 | 2021-09-30 | 2026-05-21 | 2027-01-26 | 2027-09-03 | 2030-03-08 | 2029-12-14 |  |  | 0.54565 | 46.8229 | 47.3686 | 1.152% |  |  | 0.92294 | 2.3492 | 8.7269 | 11.9754 | 12.204 | 12.204 | 0 | 0 | 0.54565 | 7.0827 | 13.8182 | 17.4605 | 20.8441 | 47.3686 | No | Other | AMP7
| TMS | WWNI Milton Under Wychwood STW FTFT | K540.01 | FLO01283 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-25 | 2024-12-20 | 2025-01-29 | 2026-09-10 | 2026-09-08 |  | IM4 | 2019-06-18 | 2021-08-25 | 2024-12-20 | 2025-01-29 | 2027-07-16 | 2026-08-27 |  |  | 4.6852 | 1.7236 | 6.4088 | 73.11% | 0.35489 | 1.6235 | 8.3004 | 9.2782 | 9.2782 | 9.2782 | 9.2782 | 9.2782 | 0.35488 | 1.6235 | 4.6852 | 5.4905 | 5.9554 | 6.4088 | 6.4088 | 6.4088 | No | Other | AMP7
| TMS | WWNI Drayton STW FTFT Storm Tank & G2G | K543.01 | THM00105 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2026-07-24 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2027-05-27 | 2027-03-12 |  |  | 9.785 | 4.099 | 13.884 | 70.48% | 2.4221 | 5.7593 | 16.337 | 16.9375 | 16.9375 | 16.9375 | 16.9375 | 16.9375 | 2.4221 | 5.7593 | 9.785 | 12.958 | 13.884 | 13.884 | 13.884 | 13.884 | No | Other | AMP7
| TMS | WWNI Drayton STW FTFT Storm Tank & G2G | K543.01 | THM00094 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2026-07-24 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2027-05-27 | 2027-03-12 |  |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | WWNI Cirencester STW FtFT & Storm Tank | K552.01 | FLO01254 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2026-03-24 | 2026-04-27 |  | IM4 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2027-01-08 | 2026-12-02 |  |  | 21.107 | 2.161 | 23.268 | 90.71% | 11.7339 | 18.731 | 27.664 | 27.664 | 27.664 | 27.664 | 27.664 | 27.664 | 11.7339 | 18.731 | 21.107 | 23.268 | 23.268 | 23.268 | 23.268 | 23.268 | No | Other | AMP7
| TMS | WWNI Cirencester STW FtFT & Storm Tank | K552.01 | THM00093 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2026-03-24 | 2026-04-27 |  | IM4 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2027-01-08 | 2026-12-02 |  |  | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | Brentwood STW WAAP and P-Removal | L477.01 | HNL00207 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2023-12-01 | 2025-01-23 | 2026-01-21 | 2026-05-13 | 2027-12-13 | 2027-08-12 |  | IM2 | 2020-11-30 | 2025-01-23 | 2027-05-28 | 2027-12-07 | 2029-07-18 | 2029-05-03 |  |  | 0.27133 | 9.4977 | 9.769 | 2.777% | 0.64784 | 0.45843 | 3.1567 | 6.6653 | 8.1014 | 8.3889 | 8.3889 | 8.3889 | 0 | 0.025715 | 0.27133 | 1.3684 | 3.7136 | 8.3623 | 9.5376 | 9.769 | No | Other | AMP7
| TMS | Farnham STW WAAP and P-Removal | L516.01 | THM00598 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-02-22 | 2024-04-17 | 2025-12-23 | 2026-01-26 | 2028-02-08 | 2028-02-01 |  | IM2 | 2022-02-22 | 2024-04-17 | 2027-04-20 | 2027-04-26 | 2029-04-25 | 2029-02-21 |  |  | 4.6717 | 13.9836 | 18.6553 | 25.04% |  | 3.6592 | 6.454 | 17.9818 | 25.0097 | 25.1532 | 25.1561 | 25.1561 | 0 | 3.6592 | 4.6717 | 5.934 | 12.3211 | 18.4561 | 18.627 | 18.6553 | No | Other | AMP7
| TMS | WWNI LITTLE HALLINGBURY STW P-removal | L478.01 | HNL00227 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2023-05-15 | 2021-10-26 | 2025-09-22 | 2025-10-10 | 2027-04-26 | 2027-04-15 |  | IM2 | 2023-05-15 | 2024-06-17 | 2026-06-26 | 2026-07-27 | 2027-12-01 | 2027-09-24 |  |  | 0.97946 | 8.426 | 9.4054 | 10.41% | 0.66337 | 0.024487 | 2.5236 | 5.266 | 5.4567 | 5.4697 | 5.4697 | 5.4697 | 0 | 0.40107 | 0.97946 | 5.5095 | 9.2631 | 9.4054 | 9.4054 | 9.4054 | No | Other | AMP7
| TMS | WWNI Barkway STW P-removal | L742.01 | HNL00221 | P - Amber in Plan | PCDWW35 | Retained |  |  | 2024-12-22 | 2019-05-22 | 2021-06-01 | 2024-09-10 | 2024-12-23 | 2025-06-10 | 2025-06-28 |  | IM6 | 2019-05-22 | 2021-06-01 | 2024-09-10 | 2024-12-23 | 2026-04-15 | 2025-09-30 |  |  | 3.5195 | 0.28063 | 3.8002 | 92.62% |  | 2.7127 | 2.7566 | 2.7566 | 2.7566 | 2.7566 | 2.7566 | 2.7566 | 0 | 2.7127 | 3.5195 | 3.8002 | 3.8002 | 3.8002 | 3.8002 | 3.8002 | No | Other | AMP7
| TMS | WWNI Upper Heyford STW FTFT | K568.01 | FLO01272 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-31 | 2023-07-03 | 2023-09-04 | 2025-12-01 | 2025-12-24 |  | IM6 | 2019-06-18 | 2021-08-31 | 2023-07-03 | 2023-09-04 | 2026-07-28 | 2026-02-13 |  |  | 1.0157 | 0.23492 | 1.2507 | 81.22% | 0.48303 | 0.60577 | 1.2767 | 1.2767 | 1.2767 | 1.2767 | 1.2767 | 1.2767 | 0.48303 | 0.60577 | 1.0157 | 1.2507 | 1.2507 | 1.2507 | 1.2507 | 1.2507 | No | Other | AMP7
| TMS | Takeley STW WAAP | K645.01 | HNL00228 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2024-12-22 | 2019-07-17 | 2024-04-17 | 2025-08-27 | 2025-09-29 | 2026-06-30 | 2026-05-31 |  | IM6 | 2019-07-17 | 2024-04-17 | 2025-08-27 | 2025-10-01 | 2026-09-28 | 2025-12-25 |  |  | 1.0247 | 1.2423 | 2.2669 | 45.2% | 0.10754 | 0.35881 | 2.0795 | 2.6664 | 2.7295 | 2.7295 | 2.7295 | 2.7295 | 0.10754 | 0.35881 | 1.0247 | 2.2669 | 2.2669 | 2.2669 | 2.2669 | 2.2669 | No | Other | AMP7
| TMS | WWNI Henley STW FTFT | K650.01 | FLO01271 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-10-26 | 2024-09-23 | 2024-11-29 | 2026-12-21 | 2026-11-30 |  | IM6 | 2019-06-18 | 2021-10-26 | 2024-09-23 | 2024-11-29 | 2027-02-12 | 2026-04-30 |  |  | 7.5093 | 1.3946 | 8.904 | 84.34% | 0.49833 | 2.2467 | 6.6364 | 10.9205 | 10.9274 | 10.9274 | 10.9274 | 10.9274 | 0.49832 | 2.2467 | 7.5093 | 8.8986 | 8.904 | 8.904 | 8.904 | 8.904 | No | Other | AMP7
| TMS | WWNI Ripley STW G2G and Low P | K672.01 | THM00550 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-08-31 | 2027-06-01 | 2027-09-06 | 2030-08-22 | 2030-08-27 |  | IM2 | 2021-01-26 | 2021-08-31 | 2026-07-27 | 2026-11-02 | 2029-07-26 | 2029-05-31 |  |  | 1.2465 | 21.3951 | 22.6416 | 5.505% | 0.71281 | 0.7802 | 1.3056 | 4.0288 | 5.3092 | 11.3709 | 22.9 | 28.1078 | 0.71281 | 0.7802 | 1.2465 | 3.6198 | 9.8109 | 20.5382 | 22.6416 | 22.6416 | No | Other | AMP7
| TMS | WWNI Leatherhead STW FTFT | K676.01 | KSL00279 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-22 | 2026-03-26 | 2026-10-16 | 2028-09-11 | 2028-09-24 |  | IM2 | 2019-06-18 | 2025-08-21 | 2027-03-23 | 2027-04-21 | 2028-10-13 | 2028-08-21 |  |  | 2.0414 | 21.7231 | 23.7645 | 8.59% | 1.0108 | 1.4754 | 2.72 | 8.0963 | 22.0738 | 26.6002 | 27.3439 | 27.3439 | 1.0108 | 1.4754 | 2.0414 | 5.2394 | 13.628 | 19.9115 | 23.7645 | 23.7645 | No | Other | AMP7
| TMS | WWNI Woking STW Storm Tank & Low P | K677.01 | THM00572 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2025-03-31 | 2024-12-22 | 2019-06-18 | 2025-04-17 | 2026-02-25 | 2026-09-15 | 2028-08-17 | 2028-08-29 |  | IM2 | 2019-06-18 | 2025-05-22 | 2027-03-23 | 2027-04-21 | 2028-10-23 | 2028-09-04 |  |  | 2.0841 | 55.2154 | 57.2995 | 3.637% | 1.1682 | 1.5629 | 2.9275 | 15.0309 | 46.6105 | 56.1092 | 57.2772 | 57.2772 | 1.1705 | 1.566 | 2.0841 | 6.2609 | 23.7018 | 43.1446 | 57.2995 | 57.2995 | No | Other | AMP7
| TMS | WWNI Woking STW Storm Tank & Low P | K677.01 | THM00109 | Storm Tank | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2025-03-31 | 2019-06-18 | 2025-04-17 | 2026-02-25 | 2026-09-15 | 2028-08-17 | 2028-08-29 |  | IM2 | 2019-06-18 | 2025-05-22 | 2027-03-23 | 2027-04-21 | 2028-10-23 | 2028-09-04 |  |  | 1.6516 | 9.1157 | 10.7673 | 15.34% | 0.19286 | 0.25803 | 0.48331 | 2.4815 | 7.6951 | 9.2633 | 9.4561 | 9.4561 | 1.1705 | 1.566 | 1.6516 | 2.3411 | 5.2205 | 8.4304 | 10.7673 | 10.7673 | No | Other | AMP7
| TMS | Moreton in Marsh STW G2G & Storm Tank | K758.01 | FLO01284 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2022-03-03 | 2026-06-22 | 2026-09-07 | 2029-04-06 | 2029-03-31 |  | IM2 | 2019-06-18 | 2025-12-18 | 2027-01-07 | 2027-08-24 | 2030-04-08 | 2030-02-04 |  |  | 0.61251 | 1.9274 | 2.5399 | 24.12% | 0.44262 | 0.52056 | 0.87961 | 2.5917 | 6.076 | 8.9395 | 10.2495 | 10.262 | 0.44262 | 0.52056 | 0.61251 | 1.0281 | 1.6351 | 2.0525 | 2.3219 | 2.5399 | No | Other | AMP7
| TMS | WWNI Watlington STW FTFT & Low P | K759.01 | THM00567 | P - Amber in Plan | PCDWW35 | Retained |  | 2025-03-31 | 2024-12-22 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-04-22 | 2027-06-18 | 2027-03-29 |  | IM4 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-07-22 | 2027-07-26 | 2027-04-27 |  |  | 4.0197 | 3.4405 | 7.4601 | 53.88% | 0.16874 | 0.49298 | 2.0472 | 4.2807 | 4.4948 | 4.6556 | 4.6556 | 4.6556 | 0.16828 | 0.49165 | 4.0197 | 7.2235 | 7.4601 | 7.4601 | 7.4601 | 7.4601 | No | Other | AMP7
| TMS | WWNI Watlington STW FTFT & Low P | K759.01 | FLO01298 | FTFT | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2025-03-31 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-04-22 | 2027-06-18 | 2027-03-29 |  | IM4 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-07-22 | 2027-07-26 | 2027-04-27 |  |  | 2.654 | 2.1087 | 4.7627 | 55.72% | 0.28608 | 0.8358 | 3.4709 | 7.2575 | 7.6206 | 7.8932 | 7.8932 | 7.8932 | 0.16828 | 0.49165 | 2.654 | 4.6176 | 4.7627 | 4.7627 | 4.7627 | 4.7627 | No | Other | AMP7
| TMS | WWNI Hogsmill STW Storm Tank | K760.01 | FLO01273 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2025-04-17 | 2026-01-02 | 2026-06-22 | 2028-02-24 | 2028-03-06 |  | IM2 | 2019-06-18 | 2025-04-17 | 2026-12-22 | 2027-03-31 | 2028-07-14 | 2028-05-25 |  |  | 2.5877 | 64.2716 | 66.8594 | 3.87% | 1.3482 | 1.8856 | 5.1258 | 30.9349 | 53.5305 | 55.4749 | 55.8855 | 55.8855 | 1.3482 | 1.8856 | 2.5877 | 11.0367 | 30.4705 | 54.4116 | 66.8594 | 66.8594 | No | Other | AMP7
| TMS | WWNI Thornwood STW G2G & P-removal | K831.01 | HNL00209 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2023-12-12 | 2026-02-02 | 2026-05-11 | 2027-11-17 | 2027-11-08 |  | IM2 | 2020-10-06 | 2023-12-12 | 2027-02-26 | 2027-10-28 | 2029-06-15 | 2029-04-04 |  |  | 1.0047 | 5.9103 | 6.915 | 14.53% | 0.63992 | 0.72021 | 1.6697 | 6.7834 | 12.2121 | 13.2103 | 13.2103 | 13.2103 | 0.63992 | 0.72021 | 1.0047 | 1.2885 | 1.7487 | 6.5789 | 6.8853 | 6.915 | No | Other | AMP7
| TMS | WWNI Earlswood (Reigate) STW FtFT | K934.01 | FLO01264 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2022-06-22 | 2024-08-06 | 2025-02-14 | 2028-06-16 | 2028-07-10 |  | IM4 | 2019-06-18 | 2022-06-22 | 2024-08-06 | 2025-02-14 | 2028-06-16 | 2028-05-10 |  |  | 11.1237 | 2.6051 | 13.7289 | 81.02% | 2.0765 | 6.7791 | 10.9032 | 12.8193 | 13.2451 | 13.2451 | 13.2451 | 13.2451 | 2.0765 | 6.7791 | 11.1237 | 12.9216 | 13.6971 | 13.7289 | 13.7289 | 13.7289 | No | Other | AMP7
| TMS | Stansted Mountfitchet STW Growth & Low P | K936.01 | HNL00225 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-10-17 | 2022-03-31 | 2025-10-06 | 2026-07-01 | 2028-03-27 | 2028-02-24 |  | IM4 | 2019-10-17 | 2022-03-31 | 2025-11-25 | 2026-02-02 | 2028-03-27 | 2027-12-24 |  |  | 2.3699 | 11.3844 | 13.7544 | 17.23% | 0.86162 | 2.2187 | 4.3912 | 11.7381 | 25.3252 | 33.688 | 48.9948 | 48.9948 | 0.86163 | 2.2187 | 2.3699 | 8.6186 | 13.7544 | 13.7544 | 13.7544 | 13.7544 | No | Other | AMP7
| TMS | WWNI Chieveley STW Low P & DWF | K982.01 | THM00065 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2021-05-26 | 2023-06-15 | 2026-05-20 | 2026-06-02 | 2027-07-28 | 2027-07-27 |  | IM2 | 2021-05-26 | 2023-06-15 | 2027-01-22 | 2027-01-26 | 2028-04-19 | 2028-02-16 |  | Contractual issues | 0.41445 | 3.5399 | 3.9544 | 10.48% | 0.14588 | 0.16792 | 1.4098 | 9.2869 | 11.3127 | 11.5515 | 11.5515 | 11.5515 | 0.14588 | 0.16792 | 0.41445 | 0.8556 | 2.7104 | 3.679 | 3.9544 | 3.9544 | No | Other | AMP7
| TMS | WWNI Wingrave Compliance First & Low P | K984.01 | THM00570 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-02-22 | 2022-06-08 | 2024-01-31 | 2024-04-19 | 2026-01-13 | 2025-12-22 |  | IM6 | 2022-02-22 | 2022-06-08 | 2024-01-31 | 2024-04-19 | 2026-03-23 | 2026-01-30 |  |  | 9.0944 | 0.21272 | 9.3071 | 97.71% | 1.1748 | 6.7826 | 9.9564 | 10.0604 | 10.0604 | 10.0604 | 10.0604 | 10.0604 | 1.1748 | 6.7826 | 9.0944 | 9.3071 | 9.3071 | 9.3071 | 9.3071 | 9.3071 | No | Other | AMP7
| TMS | WWNI Chinnor STW Pollutions scope | L040.01 | FLO01251 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2024-11-30 | 2022-02-22 | 2022-06-08 | 2025-07-18 | 2025-08-11 | 2026-05-29 | 2026-07-05 |  | IM6 | 2022-02-22 | 2022-06-08 | 2026-01-16 | 2026-01-16 | 2027-04-16 | 2026-05-05 |  |  | 1.9722 | 3.5164 | 5.4886 | 35.93% | 0.5386 | 0.89122 | 2.9042 | 5.4054 | 5.4054 | 5.4054 | 5.4054 | 5.4054 | 0.5386 | 0.89122 | 1.9722 | 5.4141 | 5.4886 | 5.4886 | 5.4886 | 5.4886 | No | Other | AMP7
| TMS | Faringdon Storm and Siphon | L057.01 | FLO01267 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2022-09-23 | 2024-06-28 | 2025-05-02 | 2026-05-13 | 2026-05-06 |  | IM4 | 2019-06-18 | 2022-09-23 | 2024-06-28 | 2025-07-21 | 2026-10-14 | 2026-07-31 |  |  | 5.4942 | 0.8768 | 6.371 | 86.24% | 0.57167 | 1.7141 | 6.1584 | 6.327 | 6.3293 | 6.3293 | 6.3293 | 6.3293 | 0.57166 | 1.7141 | 5.4942 | 6.3692 | 6.371 | 6.371 | 6.371 | 6.371 | No | Other | AMP7
| TMS | Theydon Bois STW WAAP and P-Removal | L470.01 | HNL00213 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-09-01 | 2023-11-23 | 2025-08-13 | 2025-11-05 | 2027-05-14 | 2027-05-03 |  | IM2 | 2022-09-01 | 2023-11-23 | 2026-06-25 | 2026-07-09 | 2030-05-16 | 2030-02-22 |  | Change in solution | 2.9453 | 17.8733 | 20.8186 | 14.15% | 1.0093 | 2.4226 | 6.0581 | 15.4866 | 16.5314 | 16.7478 | 16.7478 | 16.7478 | 1.0093 | 2.4226 | 2.9453 | 5.5521 | 11.1351 | 17.0868 | 19.8992 | 20.8186 | No | Other | AMP7
| TMS | Hatfield Heath STW WAAP and P-Removal | L473.01 | HNL00229 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2021-10-26 | 2025-04-17 | 2025-09-11 | 2027-10-26 | 2027-10-16 |  | IM6 | 2020-10-06 | 2021-10-26 | 2025-05-22 | 2025-10-23 | 2028-01-17 | 2025-04-30 |  |  | 5.3006 | 5.835 | 11.1356 | 47.6% | 2.319 | 3.3629 | 8.8249 | 14.2199 | 17.7941 | 17.8886 | 17.8886 | 17.8886 | 2.319 | 3.3629 | 5.3006 | 8.8367 | 11.0893 | 11.1356 | 11.1356 | 11.1356 | No | Other | AMP7
| TMS | Burghfield STW WAAP and P-Removal | L483.01 | THM00587 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2022-06-22 | 2025-10-27 | 2025-11-26 | 2027-07-13 | 2027-06-14 |  | IM3 | 2021-01-26 | 2022-06-22 | 2026-06-18 | 2026-07-16 | 2028-03-03 | 2027-11-22 |  |  | 2.7813 | 14.3077 | 17.089 | 16.28% | 0.37305 | 1.8872 | 4.8945 | 19.5316 | 22.9281 | 23.0751 | 23.0751 | 23.0751 | 0.37305 | 1.8872 | 2.7813 | 7.9101 | 14.5256 | 16.839 | 17.089 | 17.089 | No | Other | AMP7
| TMS | Waddesdon STW WAAP and P-Removal | L484.01 | THM00564 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-06-23 | 2025-04-17 | 2025-04-30 | 2026-12-09 | 2026-11-15 |  | IM4 | 2020-11-30 | 2021-06-23 | 2025-04-08 | 2025-04-30 | 2028-05-15 | 2028-02-15 |  | Contract Programme | 3.0688 | 7.2713 | 10.34 | 29.68% | 1.0074 | 1.7382 | 7.4806 | 13.5188 | 14.189 | 14.189 | 14.189 | 14.189 | 1.0074 | 1.7382 | 3.0688 | 8.4069 | 10.3357 | 10.34 | 10.34 | 10.34 | No | Other | AMP7
| TMS | Shamley Green STW WAAP & P-Removal | L487.01 | THM00552 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-10-17 | 2024-02-01 | 2025-09-19 | 2026-01-02 | 2028-09-20 | 2028-08-29 |  | IM4 | 2022-10-17 | 2024-02-01 | 2025-12-24 | 2026-01-21 | 2028-10-23 | 2028-08-01 |  |  | 2.7551 | 4.8151 | 7.5703 | 36.39% | 0.86505 | 2.2826 | 4.3774 | 11.2679 | 19.744 | 20.9933 | 21.0714 | 21.0714 | 0.86505 | 2.2826 | 2.7551 | 4.562 | 7.0383 | 7.5502 | 7.5703 | 7.5703 | No | Other | AMP7
| TMS | North Weald STW PRemoval&Flow Compliance | L511.01 | HNL00208 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2023-12-01 | 2026-04-07 | 2026-06-09 | 2028-01-26 | 2028-01-29 |  | IM2 | 2020-11-30 | 2023-12-01 | 2027-02-26 | 2028-01-31 | 2030-09-04 | 2030-07-12 |  |  | 0.99426 | 8.8086 | 9.8029 | 10.14% | 0.1777 | 0.75095 | 1.8038 | 9.7648 | 27.3132 | 29.839 | 29.8402 | 29.8402 | 0.1777 | 0.75095 | 0.99426 | 1.5999 | 1.7134 | 4.7876 | 9.4864 | 9.8029 | No | Other | AMP7
| TMS | Wisley STW G2G and P-Removal | L514.01 | THM00571 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2025-01-23 | 2026-02-26 | 2026-06-30 | 2028-09-19 | 2028-09-06 |  | IM2 | 2021-01-26 | 2025-01-23 | 2026-12-22 | 2027-02-26 | 2029-03-21 | 2029-01-05 |  |  | 1.3698 | 11.6987 | 13.0684 | 10.48% |  | 0.95462 | 4.4751 | 17.2536 | 37.4528 | 44.0721 | 44.152 | 44.152 | 0 | 0.95462 | 1.3698 | 2.0883 | 6.9881 | 13.0061 | 13.0575 | 13.0684 | No | Other | AMP7
| TMS | Weston on the Green STW Low P | L692.01 | THM00569 | P - Amber in Plan | PCDWW35 | Retained |  |  | 2024-12-22 | 2020-11-30 | 2021-08-31 | 2025-08-04 | 2025-11-04 | 2027-09-03 | 2027-05-31 |  | IM6 | 2020-11-30 | 2021-08-31 | 2025-10-30 | 2025-11-06 | 2027-09-03 | 2026-03-31 |  | Contract Programme | 2.641 | 7.5206 | 10.1616 | 25.99% |  | 1.2319 | 2.501 | 7.9669 | 10.3502 | 11.1374 | 11.1374 | 11.1374 | 0 | 1.2319 | 2.641 | 8.1291 | 10.0289 | 10.1616 | 10.1616 | 10.1616 | No | Other | AMP7
| TMS | Boxford STW Low P | L693.01 | THM00064 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-11-24 | 2025-08-18 | 2025-11-26 | 2028-02-07 | 2027-12-29 |  | IM4 | 2019-06-18 | 2021-11-24 | 2025-10-30 | 2025-10-31 | 2028-02-07 | 2027-10-29 |  |  | 2.9645 | 6.8146 | 9.7792 | 30.31% |  | 1.2518 | 2.4369 | 7.7375 | 9.7091 | 10.0701 | 10.0701 | 10.0701 | 0 | 1.2518 | 2.9645 | 8.2007 | 9.7792 | 9.7792 | 9.7792 | 9.7792 | No | Other | AMP7
| TMS | Blunsdon STW Low P | L694.01 | THM00585 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-11-24 | 2025-08-18 | 2025-09-23 | 2027-07-06 | 2027-03-18 |  | IM4 | 2020-11-30 | 2021-11-24 | 2025-07-17 | 2025-07-31 | 2027-07-06 | 2027-01-18 |  |  | 4.4298 | 3.126 | 7.5559 | 58.63% |  | 1.4749 | 2.8341 | 7.5306 | 8.6561 | 8.8424 | 8.8424 | 8.8424 | 0 | 1.4749 | 4.4298 | 7.2973 | 7.5559 | 7.5559 | 7.5559 | 7.5559 | No | Other | AMP7
| TMS | Barford St Michael STW Low P | L695.01 | THM00494 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-06-23 | 2024-09-02 | 2024-11-19 | 2025-10-22 | 2025-06-30 |  | IM6 | 2020-11-30 | 2021-06-23 | 2024-09-02 | 2024-11-19 | 2027-06-24 | 2026-03-05 |  |  | 1.6878 | 0.99356 | 2.6814 | 62.95% |  | 1.6643 | 2.6068 | 2.7987 | 2.7987 | 2.7987 | 2.7987 | 2.7987 | 0 | 1.6643 | 1.6878 | 2.6814 | 2.6814 | 2.6814 | 2.6814 | 2.6814 | No | Other | AMP7
| TMS | Marsh Gibbon STW Low P | L696.01 | THM00543 | P - Amber in Plan | PCDWW35 | Retained |  |  | 2024-12-22 | 2020-11-30 | 2021-06-23 | 2024-08-05 | 2024-08-15 | 2025-04-30 | 2025-06-30 |  | IM6 | 2020-11-30 | 2021-06-23 | 2024-08-05 | 2024-08-15 | 2027-07-26 | 2026-02-05 |  |  | 1.5132 | 0.16476 | 1.678 | 90.18% |  | 0.704 | 2.5176 | 2.7695 | 2.7695 | 2.7695 | 2.7695 | 2.7695 | 0 | 0.704 | 1.5132 | 1.678 | 1.678 | 1.678 | 1.678 | 1.678 | No | Other | AMP7
| TMS | Dorton STW Low P | L698.01 | THM00520 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2022-07-22 | 2025-08-18 | 2025-09-24 | 2027-06-24 | 2027-03-29 |  | IM4 | 2021-01-26 | 2022-07-22 | 2025-07-17 | 2025-07-31 | 2027-06-24 | 2027-01-29 |  |  | 4.0185 | 2.195 | 6.2135 | 64.67% |  | 1.2741 | 2.7921 | 6.1582 | 6.4041 | 6.4135 | 6.4135 | 6.4135 | 0 | 1.2741 | 4.0185 | 6.0764 | 6.2135 | 6.2135 | 6.2135 | 6.2135 | No | Other | AMP7
| TMS | Tetsworth STW Low P | L699.01 | THM00562 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-09-22 | 2025-08-18 | 2025-09-30 | 2027-07-20 | 2027-06-15 |  | IM4 | 2020-11-30 | 2021-09-22 | 2025-09-30 | 2025-10-31 | 2028-05-04 | 2028-01-28 |  |  | 2.1409 | 4.8937 | 7.0346 | 30.43% |  | 1.2625 | 2.6775 | 5.5686 | 5.9118 | 5.9327 | 5.9327 | 5.9327 | 0 | 1.2625 | 2.1409 | 5.9396 | 7.0346 | 7.0346 | 7.0346 | 7.0346 | No | Other | AMP7
| TMS | South Leigh STW Low P | L700.01 | THM00558 | P - Amber in Plan | PCDWW35 | Retained |  |  | 2024-12-22 | 2020-11-30 | 2022-07-20 | 2024-10-02 | 2024-10-02 | 2025-09-10 | 2025-06-30 |  | IM6 | 2020-11-30 | 2022-07-20 | 2024-10-02 | 2024-10-02 | 2027-08-04 | 2026-02-05 |  |  | 1.1756 | 0.36802 | 1.5436 | 76.16% |  | 0.69778 | 1.6093 | 1.857 | 1.857 | 1.857 | 1.857 | 1.857 | 0 | 0.69778 | 1.1756 | 1.5436 | 1.5436 | 1.5436 | 1.5436 | 1.5436 | No | Other | AMP7
| TMS | Stanton Harcourt STW Low P | L701.01 | THM00561 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-07 | 2021-11-24 | 2024-09-16 | 2024-09-11 | 2025-09-11 | 2025-05-21 |  | IM6 | 2020-12-07 | 2021-11-24 | 2024-09-16 | 2024-09-11 | 2026-06-12 | 2026-03-05 |  |  | 0.87639 | 0.26053 | 1.1369 | 77.08% |  | 0.83239 | 1.3103 | 1.7396 | 1.7396 | 1.7396 | 1.7396 | 1.7396 | 0 | 0.83239 | 0.87639 | 1.1369 | 1.1369 | 1.1369 | 1.1369 | 1.1369 | No | Other | AMP7
| TMS | Weston (Herts) STW Low P | L702.01 | HNL00217 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2024-09-18 | 2026-03-05 | 2026-05-18 | 2028-05-17 | 2028-04-09 |  | IM2 | 2020-11-30 | 2024-09-18 | 2026-10-07 | 2026-12-09 | 2028-09-14 | 2028-06-12 |  | Change in solution | 1.6017 | 6.3862 | 7.9879 | 20.05% |  | 1.4261 | 2.5964 | 5.0232 | 9.3334 | 9.6315 | 9.6422 | 9.6422 | 0 | 1.4261 | 1.6017 | 2.6311 | 7.2707 | 7.7991 | 7.9879 | 7.9879 | No | Other | AMP7
| TMS | Bishops Stortford STW Low P | L703.01 | HNL00226 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-12-20 | 2026-02-05 | 2026-05-12 | 2028-08-15 | 2028-07-02 |  | IM2 | 2020-11-30 | 2021-12-20 | 2026-10-07 | 2026-10-27 | 2029-02-06 | 2028-10-17 |  | Contractual issues | 2.9368 | 7.0587 | 9.9955 | 29.38% |  | 2.7882 | 3.7284 | 5.8298 | 11.5314 | 11.9655 | 12.1761 | 12.1761 | 0 | 2.7882 | 2.9368 | 3.8027 | 8.2395 | 9.6146 | 9.9322 | 9.9955 | No | Other | AMP7
| TMS | Hartley Wintney STW Low P | L704.01 | THM00602 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-06-23 | 2026-01-09 | 2026-05-12 | 2028-01-21 | 2027-11-29 |  | IM2 | 2021-01-26 | 2021-06-23 | 2026-09-22 | 2026-12-07 | 2028-08-21 | 2028-05-04 |  |  | 2.4661 | 4.5773 | 7.0435 | 35.01% |  | 2.3342 | 3.5253 | 6.9626 | 9.5545 | 9.7611 | 9.789 | 9.789 | 0 | 2.3342 | 2.4661 | 3.5684 | 6.578 | 6.8685 | 7.0435 | 7.0435 | No | Other | AMP7
| TMS | Godalming STW Low P | L705.01 | THM00525 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-06-23 | 2026-01-09 | 2026-04-13 | 2028-10-25 | 2028-09-12 |  | IM4 | 2021-01-26 | 2021-06-23 | 2025-11-24 | 2026-04-21 | 2028-10-18 | 2028-07-05 |  |  | 3.6595 | 17.6652 | 21.3247 | 17.16% |  | 2.1319 | 2.8794 | 5.4993 | 12.935 | 13.6416 | 13.948 | 13.948 | 0 | 2.1319 | 3.6595 | 10.8305 | 18.1211 | 21.3247 | 21.3247 | 21.3247 | No | Other | AMP7
| TMS | Hockford STW Low P | L706.01 | THM00754 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2024-09-18 | 2026-04-08 | 2026-07-14 | 2028-10-24 | 2028-09-04 |  | IM3 | 2021-01-26 | 2024-09-18 | 2026-02-18 | 2026-07-13 | 2028-10-23 | 2028-07-03 |  |  | 1.5897 | 18.9206 | 20.5103 | 7.751% |  | 0.75416 | 1.3176 | 2.1967 | 6.7416 | 7.2535 | 7.4816 | 7.4816 | 0 | 0.75417 | 1.5897 | 6.8654 | 14.4642 | 20.1198 | 20.5103 | 20.5103 | No | Other | AMP7
| TMS | Merstham STW Low P | L707.01 | KSL00234 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-03-05 | 2026-07-14 | 2028-07-17 | 2028-06-05 |  | IM3 | 2020-10-06 | 2024-09-18 | 2026-05-05 | 2026-07-20 | 2027-07-08 | 2027-03-31 |  |  | 1.8665 | 1.5375 | 3.404 | 54.83% |  | 1.5543 | 2.4411 | 3.9438 | 8.5288 | 8.6719 | 8.6793 | 8.6793 | 0 | 1.5543 | 1.8665 | 3.404 | 3.404 | 3.404 | 3.404 | 3.404 | No | Other | AMP7
| TMS | Elstead STW Low P | L708.01 | THM00521 | P - Amber in Plan | PCDWW35 | Retained |  |  | 2024-12-22 | 2020-11-30 | 2021-06-17 | 2025-09-18 | 2026-01-07 | 2027-06-11 | 2027-04-16 |  | IM6 | 2020-11-30 | 2021-06-17 | 2024-10-15 | 2024-10-15 | 2026-04-14 | 2025-12-25 |  |  | 2.2484 | 0.31673 | 2.5652 | 87.65% |  | 2.1323 | 3.891 | 8.8036 | 9.6662 | 9.7326 | 9.7326 | 9.7326 | 0 | 2.1323 | 2.2484 | 2.5652 | 2.5652 | 2.5652 | 2.5652 | 2.5652 | No | Other | AMP7
| TMS | Stanford Rivers STW Low P | L709.01 | HNL00212 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2025-05-22 | 2026-07-31 | 2026-11-25 | 2029-06-19 | 2029-05-01 |  | IM1 | 2020-11-30 | 2026-09-17 | 2027-07-27 | 2028-03-09 | 2030-09-25 | 2030-02-07 |  | Change in solution | 0.34005 | 10.6938 | 11.0338 | 3.082% |  | 0.1349 | 0.48672 | 1.4039 | 7.0733 | 11.4759 | 11.6215 | 11.6424 | 0 | 0.1349 | 0.34005 | 0.37775 | 1.1593 | 4.1752 | 10.5918 | 11.0338 | No | Other | AMP7
| TMS | Manuden STW Low P | L710.01 | HNL00224 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-01-09 | 2026-02-03 | 2028-07-13 | 2028-05-27 |  | IM4 | 2020-10-06 | 2024-09-18 | 2026-01-29 | 2026-02-17 | 2028-07-27 | 2028-03-24 |  |  | 2.4679 | 12.7556 | 15.2234 | 16.21% |  | 1.5648 | 2.8467 | 6.3543 | 10.7468 | 10.9817 | 11.1535 | 11.1535 | 0 | 1.5648 | 2.4679 | 8.0234 | 14.555 | 14.9387 | 15.2234 | 15.2234 | No | Other | AMP7
| TMS | Moreton STW Low P | L711.01 | HNL00210 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-02-26 | 2026-06-11 | 2028-06-14 | 2028-05-03 |  | IM2 | 2020-10-06 | 2024-09-18 | 2026-08-26 | 2026-10-22 | 2028-10-26 | 2028-07-20 |  | Change in solution | 1.1469 | 12.5572 | 13.7041 | 8.369% |  | 0.67295 | 1.672 | 2.8065 | 5.7047 | 5.8457 | 5.9479 | 5.9479 | 0 | 0.67295 | 1.1469 | 3.2886 | 11.4308 | 13.5459 | 13.7041 | 13.7041 | No | Other | AMP7
| TMS | Standon STW Low P | L712.01 | HNL00222 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2024-09-18 | 2025-09-09 | 2026-04-07 | 2027-11-22 | 2027-10-04 |  | IM3 | 2020-11-30 | 2024-09-18 | 2026-06-15 | 2026-09-07 | 2028-03-29 | 2027-12-03 |  |  | 0.54933 | 9.1772 | 9.7265 | 5.648% |  | 0.46753 | 1.4383 | 7.6375 | 9.9942 | 10.3093 | 10.3093 | 10.3093 | 0 | 0.46753 | 0.54933 | 4.4869 | 9.3401 | 9.6117 | 9.7265 | 9.7265 | No | Other | AMP7
| TMS | Epping (Fiddlers Hamlet) STW Low P | L713.01 | HNL00252 | P - Green | PCDWW35 | Retained |  |  | 2026-05-12 | 2020-10-06 | 2021-11-24 | 2026-04-08 | 2026-07-28 | 2029-02-21 | 2028-12-25 |  | IM2 | 2020-10-06 | 2021-11-24 | 2026-10-07 | 2026-12-02 | 2029-07-03 | 2026-04-30 |  |  | 2.3498 | 3.7724 | 6.1222 | 38.38% |  | 2.2409 | 3.1145 | 4.1756 | 11.0197 | 12.7694 | 12.8915 | 12.9229 | 0 | 2.2409 | 2.3498 | 2.7089 | 4.4349 | 5.9281 | 6.0328 | 6.1222 | No | Other | AMP7
| TMS | Epping (Fiddlers Hamlet) STW Low P | L713.01 | HNL00211 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2021-11-24 | 2026-04-08 | 2026-07-28 | 2029-02-21 | 2028-12-25 |  | IM2 | 2020-10-06 | 2021-11-24 | 2026-10-07 | 2026-12-02 | 2029-07-03 | 2029-02-07 |  | Change in solution | 0 | 0 | 0 | #DIV/0! | [16 empty] | No | Other | AMP7
| TMS | Braughing STW Low P | L718.01 | HNL00220 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2024-09-18 | 2026-01-09 | 2026-03-12 | 2028-03-22 | 2028-02-01 |  | IM2 | 2020-11-30 | 2024-09-18 | 2026-06-26 | 2026-08-18 | 2028-08-30 | 2028-05-16 |  |  | 2.6701 | 17.9871 | 20.6572 | 12.93% |  | 1.8837 | 2.5862 | 6.5879 | 9.9963 | 10.1959 | 10.2736 | 10.2736 | 0 | 1.8837 | 2.6701 | 4.8227 | 11.3905 | 17.2274 | 20.6572 | 20.6572 | No | Other | AMP7
| TMS | Clavering STW Low P | L719.01 | HNL00223 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-02-05 | 2026-05-12 | 2028-08-15 | 2028-07-02 |  | IM4 | 2020-10-06 | 2024-09-18 | 2026-03-06 | 2026-04-13 | 2028-06-19 | 2028-03-01 |  |  | 2.0025 | 5.6235 | 7.626 | 26.26% |  | 1.6471 | 2.4936 | 4.4242 | 9.661 | 9.9556 | 10.123 | 10.123 | 0 | 1.6471 | 2.0025 | 4.4838 | 7.3295 | 7.4956 | 7.626 | 7.626 | No | Other | AMP7
| TMS | Holmwood STW WAAP and P-Removal | L745.01 | KSL00233 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2024-06-01 | 2024-05-31 | 2026-01-23 | 2026-03-20 | 2028-06-15 | 2028-05-30 |  | IM2 | 2024-06-01 | 2024-06-01 | 2027-01-06 | 2027-01-29 | 2029-02-01 | 2028-11-14 |  |  | 2.9419 | 10.0483 | 12.9902 | 22.65% |  | 2.1297 | 3.5227 | 9.9999 | 17.9597 | 18.1565 | 18.2204 | 18.2204 | 0 | 2.1297 | 2.9419 | 3.7621 | 9.7822 | 12.9475 | 12.9822 | 12.9902 | No | Other | AMP7
| TMS | Cholsey - FtFT & ST | K098.01 | FLO01252 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2023-03-31 | 2019-06-18 | 2020-11-25 | 2021-11-18 | 2022-03-30 | 2025-02-28 | 2025-07-30 |  | IM5 | 2019-06-18 | 2020-11-25 | 2021-11-18 | 2022-03-30 | 2025-03-21 | 2026-08-28 |  | Change in solution | 8.2547 | 0.21847 | 8.4731 | 97.42% | 7.6259 | 8.1363 | 8.1873 | 8.1873 | 8.1873 | 8.1873 | 8.1873 | 8.1873 | 7.6259 | 8.1363 | 8.2547 | 8.4731 | 8.4731 | 8.4731 | 8.4731 | 8.4731 | No | Other | AMP7
| TMS | BENTLEY STW | K932.01 | THM00581 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2000-01-01 | 2021-04-21 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | IM6 | 2000-01-01 | 2021-04-21 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  |  | 0.089187 | 0 | 0.089187 | 100% | 0.085236 | 0.089187 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 0.085236 | 0.089187 | 0.089187 | 0.089187 | 0.089187 | 0.089187 | 0.089187 | 0.089187 | No | Other | AMP7
| TMS | WINEP - Catchment Management | K360 | HNL00087 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 0.75008 | 0 | 0.75008 | 100% | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.28725 | 0.72279 | 0.75008 | 0.75008 | 0.75008 | 0.75008 | 0.75008 | 0.75008 | No | Other | AMP7
| TMS | WINEP - Catchment Management | K360 | HNL00088 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 0 | 0 | 0 | #DIV/0! | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | [8 empty] | No | Other | AMP7
| TMS | WINEP - Catchment Management | K360 | HNL00089 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 0 | 0 | 0 | #DIV/0! | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | [8 empty] | No | Other | AMP7
| TMS | WINEP - Catchment Management | K360 | HNL00090 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 0 | 0 | 0 | #DIV/0! | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | [8 empty] | No | Other | AMP7
| TMS | WINEP - Catchment Management | K360 | HNL00094 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 0 | 0 | 0 | #DIV/0! | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | [8 empty] | No | Other | AMP7
| TMS | Lewknor STW Low P | L697 | THM00538 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2000-01-01 | 2023-02-23 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | IM6 | 2000-01-01 | 2023-02-23 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  |  | 3.1145 | 1.6148 | 4.7293 | 65.86% |  | 1.2123 | 3.2942 | 5.4546 | 5.501 | 5.501 | 5.501 | 5.501 | 0 | 1.2123 | 3.1145 | 4.6071 | 4.7293 | 4.7293 | 4.7293 | 4.7293 | No | Other | AMP7
| TMS | BRENTWOOD SEWAGE TREATMENT WORKS | K556.03 | HNL00253 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2026-05-12 | 2025-03-31 | 2000-01-01 | 2021-08-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | IM6 | 2000-01-01 | 2021-08-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | Partial completion of scope in line with Jan forecast, remaining scope is ongoing. | 0.048449 | 0 | 0.048449 | 100% | 0.23849 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.23849 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | No | Other | AMP7
| TMS | WWNI Mill Green STW G2G and Low P | K649.01 | HNL00216 | P - Amber NOT in Plan | PCDWW35 | Retained |  |  | 2024-12-22 | 2021-01-26 | 2021-08-26 | 2024-06-28 | 2025-04-22 | 2027-05-12 | 2027-05-19 |  | IM6 | 2021-01-26 | 2021-08-26 | 2024-06-28 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | Data Error | 7.6698 | 2.0224 | 9.6922 | 79.13% | 1.1428 | 4.9906 | 14.004 | 19.1132 | 19.1182 | 19.1182 | 19.1182 | 19.1182 | 1.1428 | 4.9906 | 7.6698 | 9.5603 | 9.6922 | 9.6922 | 9.6922 | 9.6922 | No | Other | AMP7
| TMS | Andoversford STW - AMP8 Growth | M287 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40433 |  |  | 2024-10-16 | 2025-07-16 | 2026-05-18 | 2026-12-07 | 2028-11-15 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2030-03-31 |  |  | 0.1736 | 5.5782 | 5.7518 | 3.018% |  |  |  | 0.42451 | 1.3644 | 3.2303 | 5.6492 | 5.7598 | 0 | 0 | 0.1736 | 0.62348 | 1.1502 | 4.254 | 5.6941 | 5.7518 | No | Other | AMP8
| TMS | Arborfield STW - AMP8 Growth | M100 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S38253 |  |  | 2024-10-16 | 2026-03-10 | 2027-04-25 | 2027-10-30 | 2029-12-11 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-05-21 | 2027-01-18 | 2027-12-23 | 2030-02-05 | 2031-03-31 |  |  | 0.66902 | 32.6638 | 33.3329 | 2.007% |  |  | 2.3846 | 6.8297 | 10.9268 | 26.033 | 42.2986 | 43.5312 | 0 | 0 | 0.66902 | 7.5333 | 11.1267 | 24.9308 | 32.8703 | 33.3329 | No | Other | AMP8
| TMS | BASILDON PARK STW | M167 | 08TW101402a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41639 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-04-22 | 2027-02-08 | 2027-08-23 | 2028-12-13 | 2030-03-31 |  | IM2 | 2024-06-19 | 2025-12-18 | 2026-06-29 | 2027-01-11 | 2028-05-02 | 2030-03-31 |  |  | 0.11639 | 1.4672 | 1.5836 | 7.349% |  |  | 0.20569 | 0.38176 | 0.71707 | 1.1472 | 1.36 | 1.3853 | 0 | 0 | 0.11639 | 0.27571 | 0.43633 | 1.4707 | 1.5836 | 1.5836 | No | Other | AMP8
| TMS | Bicester STW - AMP8 Growth | M106 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40437 |  |  | 2024-10-16 | 2029-11-13 | 2030-07-06 | 2030-10-02 | 2032-03-31 | 2033-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-05-09 | 2028-12-14 | 2034-11-30 | 2033-03-31 |  |  | 0.74634 | 89.616 | 90.3623 | 0.8259% |  |  |  |  | 4.4523 | 15.8167 | 39.9032 | 92.0895 | 0 | 0 | 0.74634 | 1.5391 | 3.569 | 17.9142 | 36.4136 | 90.3623 | No | Other | AMP8
| TMS | Blunsdon STW - AMP8 Growth | M230 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S38261 |  |  | 2024-10-16 | 2026-03-07 | 2027-02-11 | 2027-08-25 | 2028-12-15 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-09-28 | 2028-04-10 | 2029-08-01 | 2030-03-31 |  |  | 0.079674 | 10.6144 | 10.694 | 0.745% |  |  | 0.45022 | 1.5224 | 2.6785 | 6.5562 | 10.4728 | 10.7345 | 0 | 0 | 0.079674 | 1.2163 | 2.5725 | 9.3424 | 10.6021 | 10.694 | No | Other | AMP8
| TMS | BRACKNELL STW | L842 | 08TW101384a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  | IM2 | 2024-09-18 | 2025-06-19 | 2026-12-02 | 2027-04-22 | 2033-12-20 | 2033-03-31 |  |  | 2.0538 | 16.6729 | 18.7266 | 10.97% |  |  | 0.55758 | 5.1774 | 8.7958 | 11.6309 | 13.5572 | 19.4123 | 0 | 0 | 2.0538 | 3.4342 | 4.4054 | 8.6838 | 12.696 | 18.7266 | Yes | Other | AMP8
| TMS | Cassington STW - AMP8 Growth | M102 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40428 |  |  | 2024-10-16 | 2028-03-10 | 2029-01-17 | 2029-08-01 | 2031-03-07 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-05-21 | 2027-03-31 | 2027-10-07 | 2029-05-21 | 2031-09-30 |  |  | 0.25677 | 22.2328 | 22.4896 | 1.142% |  |  |  |  | 1.1707 | 3.6894 | 8.5945 | 20.5832 | 0 | 0 | 0.25677 | 2.2208 | 9.2521 | 21.796 | 22.3865 | 22.4896 | Yes | Other | AMP8
| TMS | Chalgrove STW - AMP8 Growth | L838 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  | IM1 | 2024-09-18 | 2026-07-16 | 2026-12-16 | 2027-07-05 | 2029-11-08 | 2030-03-31 |  |  | 0.21669 | 28.8398 | 29.0564 | 0.7458% |  | 0.00021146 | -0.043602 | 1.2169 | 3.7057 | 16.0056 | 26.5289 | 27.1218 | 0 | 0 | 0.21669 | 5.3583 | 12.073 | 25.3543 | 28.7918 | 29.0564 | No | Other | AMP8
| TMS | CHALGROVE STW | L873 | 08TW101387a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | L838 | 2026-03-31 | 2026-03-31 | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  | IM6 | 2024-09-18 | 2024-10-21 | 2025-05-01 | 2025-05-08 | 2026-05-08 | 2026-03-31 |  |  | 2.5225 | 8.3294 | 10.852 | 23.24% |  | 8.1855e-05 | -0.016878 | 0.47106 | 1.4345 | 6.1957 | 10.2693 | 10.4988 | 0 | 0 | 2.5225 | 4.5545 | 6.7348 | 9.9545 | 10.7878 | 10.852 | No | Other | AMP8
| TMS | Chipping Norton STW - AMP8 Growth | M105 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S38259 |  |  | 2024-10-16 | 2025-07-04 | 2026-05-16 | 2026-12-13 | 2028-11-20 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-06-18 | 2027-04-27 | 2027-11-03 | 2029-08-10 | 2030-03-31 |  |  | 0.07744 | 8.8838 | 8.9612 | 0.8642% |  |  |  | 0.79873 | 2.1712 | 5.3299 | 8.6908 | 8.809 | 0 | 0 | 0.07744 | 0.9497 | 3.3766 | 8.1675 | 8.8589 | 8.9612 | No | Other | AMP8
| TMS | CODICOTE CSO | M201 | 08TW101402j | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41663 | 2030-03-31 | 2030-03-31 | 2024-11-19 | 2026-09-15 | 2029-03-18 | 2029-11-09 | 2032-11-22 | 2034-03-31 |  | IM1 | 2024-06-19 | 2026-12-17 | 2027-10-15 | 2028-05-02 | 2030-08-06 | 2034-03-31 |  |  | 0.02192 | 1.8334 | 1.8553 | 1.181% |  |  |  |  | 0.094369 | 0.19134 | 0.25272 | 1.6957 | 0 | 0 | 0.02192 | 0.1882 | 0.55972 | 0.92505 | 1.7989 | 1.8553 | No | Other | AMP8
| TMS | WINEP – WFD GW Investigations​ | M148 | 08TW100280a, 08TW100280d, 08TW100280f, 08TW100280g, 08TW100280e, 08TW100280c, 08TW100280h, 08TW100280b | WINEP Investigations (wastewater) | PCDWW18 | Retained | UBA8.SEW.S38859, UBA8.SEW.S38862, UBA8.SEW.S38864, UBA8.SEW.S38863, UBA8.SEW.S38861, UBA8.SEW.S38860, UBA8.SEW.S38858, UBA8.SEW.S38857 | 2027-04-30 | 2027-04-30 | 2024-07-17 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  | IM2 | 2024-07-17 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 |  |  | 0.42633 | 4.3058 | 4.7322 | 9.009% |  |  | 1.0771 | 4.0076 | 4.8324 | 4.876 | 4.9196 | 4.9196 | 0 | 0 | 0.42633 | 3.8629 | 4.7322 | 4.7322 | 4.7322 | 4.7322 | No | Other | AMP8
| TMS | Continuos Water Quality Monitoring WCQM | L798 | 08TW101406a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-03-31 | 2023-04-03 | 2023-05-27 | 2023-05-31 | 2024-12-15 | 2030-03-31 |  | IM1 | 2024-07-17 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 |  |  | 0.06626 | 1.2855 | 1.3518 | 4.902% |  | 0.18586 | 0.32256 | 0.46114 | 0.68908 | 1.1838 | 1.4652 | 1.4652 | 0 | 0 | 0.06626 | 0.1138 | 0.45666 | 0.92054 | 1.3518 | 1.3518 | No | Other | AMP8
| TMS | CULHAM STW | L481 | 08TW101393a, 08TW101392a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S40712 | 2026-03-31 | 2026-03-31 | 2024-09-18 | 2024-09-18 | 2024-09-24 | 2024-11-20 | 2026-03-22 | 2027-03-31 |  | IM6 | 2024-10-30 | 2025-04-23 | 2025-04-30 | 2025-06-26 | 2026-10-26 | 2026-03-31 |  |  | 9.115 | 2.3624 | 11.4774 | 79.42% | [8 empty] | 0 | 0 | 9.115 | 11.4774 | 11.4774 | 11.4774 | 11.4774 | 11.4774 | No | Other | AMP8
| TMS | Culham STW - AMP8 Growth | L670 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40429 |  |  | 2024-09-18 | 2029-09-18 | 2029-09-25 | 2029-11-21 | 2031-03-23 | 2032-03-31 |  | IM2 | 2022-02-22 | 2025-11-20 | 2026-09-14 | 2027-02-15 | 2029-07-18 | 2032-03-31 |  |  | 0.11535 | 8.352 | 8.4673 | 1.362% |  |  | 0.049082 | 1.1553 | 2.1996 | 6.0072 | 15.5058 | 27.2596 | 0 | 0 | 0.11535 | 1.0992 | 3.1942 | 5.7077 | 7.423 | 8.4673 | No | Other | AMP8
| TMS | Didcot STW - AMP8 Growth | J954, M179 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40439, UBA8.SEW.S38256 |  |  | 2024-10-16 | 2028-08-30 | 2029-04-16 | 2030-04-04 | 2032-03-22 | 2033-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-05-16 | 2028-12-13 | 2034-03-09 | 2033-03-31 |  | Methodology - Change from LGP to LBE | 0.57324 | 87.0589 | 87.6321 | 0.6541% | 0.003609 | -0.013809 | -0.013809 | 0.75285 | 4.1004 | 7.2539 | 10.8618 | 92.6593 | 0 | 0 | 0.57324 | 1.1913 | 5.3998 | 8.766 | 9.1404 | 87.6321 | Yes | Enhanced engagement | AMP8
| TMS | FARNHAM STW | UBA8.SEW.S39086 | 08TW100174a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  | IM6 | 2024-10-16 | 2027-03-22 | 2027-10-27 | 2028-05-31 | 2030-04-03 | 2026-03-31 |  |  | 0 | 0 | 0 | #DIV/0! | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | HANNINGTON (HANTS) STW | M162 | 08TW101402b | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41632 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-05-19 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  | IM1 | 2024-06-19 | 2027-05-20 | 2028-02-17 | 2028-08-29 | 2029-12-14 | 2030-03-31 |  |  | 0.061115 | 4.334 | 4.3951 | 1.391% |  |  | 0.59362 | 1.2195 | 2.6805 | 4.1094 | 4.2769 | 4.3183 | 0 | 0 | 0.061115 | 0.36579 | 0.83835 | 4.0455 | 4.3951 | 4.3951 | No | Other | AMP8
| TMS | HANNINGTON (WILTS) STW | M161 | 08TW101402c | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41633 | 2026-03-31 | 2026-03-31 | 2025-04-25 | 2028-03-01 | 2028-09-26 | 2028-12-26 | 2029-12-10 | 2031-03-31 |  | IM2 | 2024-06-19 | 2025-12-18 | 2026-06-29 | 2026-10-09 | 2027-07-21 | 2031-03-31 |  |  | 0.26095 | 3.0993 | 3.3603 | 7.766% |  |  | 0.19125 | 0.5152 | 0.81617 | 1.6273 | 2.7701 | 3.2638 | 0 | 0 | 0.26095 | 1.9813 | 3.2825 | 3.3603 | 3.3603 | 3.3603 | No | Other | AMP8
| TMS | HEADLEY STW 08TW100164a | M342 | 08TW100164a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S38438 | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2024-10-16 | 2025-05-17 | 2025-12-12 | 2027-11-21 | 2029-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-10-15 | 2028-05-02 | 2029-08-20 | 2029-03-31 |  |  | 0 | 7.0758 | 7.0758 | 0% |  |  | 0.7578 | 1.7051 | 4.4694 | 6.6623 | 6.7198 | 6.7436 | 0 | 0 | 0 | 0.17152 | 2.0927 | 6.3749 | 6.998 | 7.0758 | No | Other | AMP8
| TMS | HEADLEY STW 08TW101402d | M168 | 08TW101402d | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41634 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-02-27 | 2026-07-02 | 2026-11-04 | 2031-07-03 | 2031-03-31 |  | IM1 | 2024-06-19 | 2026-12-17 | 2027-10-15 | 2028-05-02 | 2029-08-20 | 2031-03-31 |  |  | 0.042475 | 1.3872 | 1.4297 | 2.971% |  |  | 0.19239 | 0.34125 | 0.52146 | 0.82472 | 1.1131 | 1.3043 | 0 | 0 | 0.042475 | 0.17195 | 0.44712 | 1.2992 | 1.4138 | 1.4297 | No | Other | AMP8
| TMS | HIGHWORTH EASTROP CSO | M200 | 08TW101402k | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S40798 | 2026-03-31 | 2026-03-31 | 2024-06-19 | 2025-07-08 | 2026-05-16 | 2026-12-09 | 2028-11-19 | 2030-03-31 |  | IM1 | 2024-06-19 | 2027-04-15 | 2028-01-24 | 2028-08-02 | 2029-11-20 | 2030-03-31 |  |  | 0.077794 | 1.9275 | 2.0053 | 3.879% |  |  | 0.11242 | 0.33017 | 0.68389 | 1.7775 | 2.0152 | 2.0365 | 0 | 0 | 0.077794 | 0.16827 | 0.30675 | 1.3127 | 2.0053 | 2.0053 | No | Other | AMP8
| TMS | Highworth STW - AMP8 Growth | M224 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S38245 |  |  | 2024-10-16 | 2028-02-29 | 2029-02-11 | 2029-08-26 | 2030-12-15 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-04-15 | 2027-12-15 | 2028-11-20 | 2030-03-15 | 2032-03-31 |  |  | 0.062606 | 11.1807 | 11.2433 | 0.5568% |  |  |  |  | 0.46875 | 1.585 | 2.7887 | 11.1764 | 0 | 0 | 0.062606 | 0.47718 | 1.5759 | 4.5743 | 11.0182 | 11.2433 | No | Other | AMP8
| TMS | IED scheme 1 Aylesbury STC | UBA8.SEW.S42154, UBA8.SEW.S39555, UBA8.SEW.S42156, UBA8.SEW.S42155 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-03-30 | 2029-08-22 | 2030-04-22 | 2031-09-22 | 2032-03-31 |  | IM1 | 2025-05-15 | 2029-04-06 | 2029-10-04 | 2030-05-08 | 2032-02-11 | 2032-03-31 |  |  | 0.059064 | 22.2544 |  |  |  |  | 2.2955 | 5.2273 | 8.5328 | 12.951 | 18.0301 | 22.8271 | 0 | 0 | 0.059064 | 5.0918 | 12.5338 | 17.7025 | 21.9986 | 22.3135 | No | Other | AMP8
| TMS | IED scheme 2 Banbury STC | UBA8.SEW.S39557, UBA8.SEW.S42152, UBA8.SEW.S42150 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-04-29 | 2029-10-18 | 2030-06-18 | 2031-09-18 | 2032-03-31 |  | IM1 | 2025-05-15 | 2029-04-06 | 2029-10-23 | 2030-05-24 | 2031-12-24 | 2032-03-31 |  |  | 0.059064 | 15.9136 |  |  |  |  | 1.2904 | 2.986 | 4.6741 | 7.3898 | 11.1345 | 15.8068 | 0 | 0 | 0.059064 | 1.7959 | 5.371 | 10.7834 | 15.635 | 15.9726 | No | Other | AMP8
| TMS | IED scheme 3 Basingstoke STC | UBA8.SEW.S42146, UBA8.SEW.S39559, UBA8.SEW.S42147 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-07-15 | 2030-09-20 | 2030-12-03 | 2032-10-27 | 2033-03-31 |  | IM1 | 2025-05-15 | 2030-12-03 | 2031-06-30 | 2032-01-28 | 2034-05-11 | 2033-03-31 |  |  | 0.059064 | 24.1207 |  |  |  |  | 0.87478 | 2.1728 | 3.2801 | 5.3108 | 7.3415 | 23.9648 | 0 | 0 | 0.059064 | 1.6136 | 4.6449 | 20.9566 | 24.0629 | 24.1798 | No | Other | AMP8
| TMS | IED scheme 4 Beckton THP STC | UBA8.SEW.S39604, UBA8.SEW.S42142 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-09-25 | 2029-12-03 | 2030-08-01 | 2032-01-01 | 2032-03-31 |  | IM1 | 2025-05-15 | 2029-12-04 | 2030-06-28 | 2031-01-28 | 2032-10-29 | 2032-03-31 |  |  | 0.059064 | 4.5962 |  |  |  |  | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 1.2033 | 4.5428 | 0 | 0 | 0.059064 | 0.37339 | 0.984 | 4.0638 | 4.6352 | 4.6553 | No | Other | AMP8
| TMS | IED scheme 5 Beddington STC | UBA8.SEW.S42138, UBA8.SEW.S39561, UBA8.SEW.S42139 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-08-14 | 2030-10-22 | 2031-04-10 | 2032-09-09 | 2033-03-31 |  | IM1 | 2025-05-15 | 2030-12-05 | 2031-07-02 | 2032-01-30 | 2033-11-14 | 2033-03-31 |  |  | 0.059064 | 9.6015 |  |  |  |  | 1.1217 | 2.207 | 3.7231 | 5.1486 | 5.1486 | 9.5166 | 0 | 0 | 0.059064 | 0.58235 | 1.6418 | 5.5535 | 9.0752 | 9.6606 | No | Other | AMP8
| TMS | IED scheme 6 Bishops Stortford STC | UBA8.SEW.S42134, UBA8.SEW.S39563, UBA8.SEW.S42136, UBA8.SEW.S42135 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-03-30 | 2030-08-21 | 2031-04-21 | 2032-09-20 | 2033-03-31 |  | IM1 | 2025-05-15 | 2030-02-01 | 2030-08-21 | 2031-03-21 | 2033-01-11 | 2033-03-31 |  |  | 0.059064 | 16.131 |  |  |  |  | 1.2873 | 2.9838 | 4.6689 | 7.4672 | 10.3887 | 16.0042 | 0 | 0 | 0.059064 | 0.14482 | 1.8742 | 5.2152 | 11.4793 | 16.1901 | No | Other | AMP8
| TMS | IED scheme 7 Bracknell STC | UBA8.SEW.S42130, UBA8.SEW.S39565, UBA8.SEW.S42132, UBA8.SEW.S42131 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-12-24 | 2032-03-02 | 2032-09-02 | 2035-01-30 | 2035-03-31 |  | IM1 | 2025-05-15 | 2030-12-03 | 2031-06-30 | 2032-01-28 | 2033-11-16 | 2035-03-31 |  |  | 0.059064 | 15.7232 |  |  |  |  | 0.88527 | 1.2077 | 1.4894 | 1.7689 | 2.5915 | 15.5993 | 0 | 0 | 0.059064 | 0.14049 | 1.5112 | 4.1269 | 11.4185 | 15.7823 | No | Other | AMP8
| TMS | IED scheme 8 Camberley STC | UBA8.SEW.S39567, UBA8.SEW.S42128, UBA8.SEW.S42127, M423 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained | L902, UBA8.SEW.S42126 | 2025-03-31 | 2025-03-31 | 2024-09-30 | 2026-05-30 | 2026-10-26 | 2027-04-28 | 2028-12-25 | 2032-03-31 |  | IM1 | 2024-09-30 | 2026-06-18 | 2028-04-26 | 2028-11-02 | 2030-11-27 | 2032-03-31 |  |  | 0.059064 | 21.9151 |  |  |  |  | 0.028042 | 0.12931 | 0.24542 | 0.43964 | 1.2953 | 18.1643 | 0 | 0 | 0.059064 | 1.9379 | 6.026 | 12.6005 | 20.522 | 21.9742 | No | Other | AMP8
| TMS | IED scheme 9 Chertsey STC | UBA8.SEW.S42122, UBA8.SEW.S39569, UBA8.SEW.S42123 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-07-17 | 2030-09-24 | 2031-03-27 | 2033-08-23 | 2034-03-31 |  | IM1 | 2025-05-15 | 2029-12-04 | 2030-06-28 | 2031-01-28 | 2032-10-27 | 2034-03-31 |  |  | 0.059064 | 10.6615 |  |  |  |  | 0.21576 | 0.58469 | 0.58469 | 0.58469 | 1.559 | 10.5605 | 0 | 0 | 0.059064 | 0.14049 | 0.71444 | 2.2164 | 7.6853 | 10.7205 | No | Other | AMP8
| TMS | IED scheme 10 Crawley STC | UBA8.SEW.S39571, UBA8.SEW.S42119, UBA8.SEW.S42118 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-08-14 | 2029-10-22 | 2030-06-20 | 2031-08-22 | 2032-03-31 |  | IM1 | 2025-05-15 | 2029-12-04 | 2030-06-28 | 2031-01-28 | 2032-08-02 | 2032-03-31 |  |  | 0.059064 | 5.5284 |  |  |  |  | 0.68343 | 1.2291 | 1.7199 | 2.5867 | 3.802 | 5.4643 | 0 | 0 | 0.059064 | 0.14049 | 0.29579 | 1.0118 | 3.3757 | 5.5874 | No | Other | AMP8
| TMS | IED scheme 11 Crossness STC | UBA8.SEW.S42114, UBA8.SEW.S39606, UBA8.SEW.S42115 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-12-11 | 2030-02-18 | 2030-10-17 | 2036-07-15 | 2037-03-31 |  | IM1 | 2025-05-15 | 2029-12-04 | 2030-06-28 | 2031-01-28 | 2033-05-16 | 2037-03-31 |  |  | 0.059064 | 22.2298 |  |  |  |  | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 2.7649 | 22.0744 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 1.7874 | 4.8349 | 22.2888 | No | Other | AMP8
| TMS | IED scheme 12 Deephams STC | UBA8.SEW.S42110, UBA8.SEW.S39573, UBA8.SEW.S42112, UBA8.SEW.S42111 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-03-30 | 2030-06-07 | 2030-11-07 | 2032-10-06 | 2033-03-31 |  | IM1 | 2025-05-15 | 2029-11-30 | 2030-06-26 | 2031-01-24 | 2033-05-11 | 2033-03-31 |  |  | 0.059064 | 26.913 |  |  |  |  | 4.0534 | 10.0069 | 15.5003 | 16.4544 | 17.3325 | 26.986 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.65748 | 2.522 | 26.9721 | No | Other | AMP8
| TMS | IED scheme 13 Didcot STC | UBA8.SEW.S39575, UBA8.SEW.S42108, UBA8.SEW.S42107, UBA8.SEW.S42106 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-09-24 | 2031-12-02 | 2032-06-03 | 2034-10-31 | 2035-03-31 |  | IM2 | 2025-05-15 | 2025-12-24 | 2027-01-29 | 2028-01-31 | 2031-01-29 | 2035-03-31 |  |  | 0.059064 | 18.2542 |  |  |  |  | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.7985 | 18.3508 | 0 | 0 | 0.059064 | 0.80482 | 1.3831 | 3.5704 | 11.8017 | 18.3132 | No | Other | AMP8
| TMS | IED scheme 14 East Hyde STC | M369, J568 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained | UBA8.SEW.S42102, UBA8.SEW.S39577, UBA8.SEW.S42103, UBA8.SEW.S42104 | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2028-01-12 | 2028-03-21 | 2028-11-17 | 2030-01-21 | 2030-03-31 |  | IM2 | 2020-02-21 | 2021-03-24 | 2026-09-30 | 2027-02-02 | 2030-03-31 | 2030-03-31 |  |  | 1.1332 | 18.0132 |  |  |  |  | 2.3273 | 4.9479 | 8.5022 | 13.1421 | 16.7627 | 16.9986 | 0 | 0 | 1.1332 | 4.605 | 10.3741 | 15.8836 | 19.1464 | 19.1464 | No | Other | AMP8
| TMS | IED scheme 15 Hogsmill STC | UBA8.SEW.S42098, UBA8.SEW.S39579, UBA8.SEW.S42099 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-08-13 | 2030-10-21 | 2031-06-20 | 2032-09-20 | 2033-03-31 |  | IM1 | 2025-05-15 | 2030-12-03 | 2031-06-30 | 2032-01-28 | 2033-09-15 | 2033-03-31 |  |  | 0.059064 | 9.4888 |  |  |  |  | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.1648 | 9.3866 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 2.0174 | 9.5479 | No | Other | AMP8
| TMS | IED scheme 16 Long Reach STC | UBA8.SEW.S42094, UBA8.SEW.S39581 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-09-30 | 2030-12-06 | 2031-08-06 | 2032-10-07 | 2033-03-31 |  | IM1 | 2025-05-15 | 2030-12-03 | 2031-06-30 | 2032-01-28 | 2033-08-15 | 2033-03-31 |  |  | 0.059064 | 3.321 |  |  |  |  | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 0.57541 | 3.2666 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 0.9591 | 3.38 | No | Other | AMP8
| TMS | IED scheme 17 Maple Lodge STC | UBA8.SEW.S42090, UBA8.SEW.S39584, UBA8.SEW.S42092, UBA8.SEW.S42091 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-10-21 | 2031-12-29 | 2032-06-30 | 2039-12-30 | 2040-03-31 |  | IM1 | 2025-05-15 | 2030-12-03 | 2031-06-30 | 2032-01-28 | 2034-03-24 | 2040-03-31 |  |  | 0.059064 | 41.6892 |  |  |  |  | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 2.0814 | 41.3886 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 1.6445 | 41.7482 | No | Other | AMP8
| TMS | IED scheme 18 Mogden STC | UBA8.SEW.S39587, UBA8.SEW.S42087, UBA8.SEW.S42086 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-12-13 | 2031-02-20 | 2031-10-21 | 2036-08-04 | 2037-03-31 |  | IM1 | 2025-05-15 | 2029-12-04 | 2030-06-28 | 2031-01-28 | 2032-11-15 | 2037-03-31 |  |  | 0.059064 | 11.0448 |  |  |  |  | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.2374 | 10.9223 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 0.80313 | 11.1039 | No | Other | AMP8
| TMS | IED scheme 19 Oxford STC | UBA8.SEW.S39589, UBA8.SEW.S42083, UBA8.SEW.S42082 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-12-13 | 2030-02-20 | 2030-10-21 | 2034-01-12 | 2034-03-31 |  | IM1 | 2025-05-15 | 2029-12-04 | 2030-06-28 | 2031-01-28 | 2032-10-29 | 2034-03-31 |  |  | 0.059064 | 14.7041 |  |  |  |  | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.7127 | 14.6242 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 0.67619 | 14.7632 | No | Other | AMP8
| TMS | IED scheme 20 Reading STC | M358 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained | UBA8.SEW.S42078, L903 | 2025-03-31 | 2025-03-31 | 2024-09-30 | 2025-08-31 | 2025-11-11 | 2026-04-15 | 2027-03-04 | 2027-03-31 |  | IM2 | 2024-12-05 | 2025-11-20 | 2026-05-07 | 2026-06-05 | 2027-05-25 | 2027-03-31 |  |  | 0.19402 | 1.4775 |  |  |  |  | 0.70322 | 1.2082 | 1.3721 | 1.3721 | 1.3721 | 1.3721 | 0 | 0 | 0.19402 | 0.60262 | 1.1155 | 1.1419 | 1.6715 | 1.6715 | No | Other | AMP8
| TMS | IED scheme 21 Riverside STC | UBA8.SEW.S42074, UBA8.SEW.S39594 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-04-12 | 2030-06-20 | 2031-02-18 | 2032-07-20 | 2033-03-31 |  | IM1 | 2025-05-15 | 2029-12-04 | 2030-06-28 | 2031-01-28 | 2032-11-05 | 2033-03-31 |  |  | 0.059064 | 4.0345 |  |  |  |  | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 0.69966 | 3.9713 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 0.66769 | 4.0936 | No | Other | AMP8
| TMS | IED scheme 22 Rye Meads STC | UBA8.SEW.S42070, UBA8.SEW.S39596, UBA8.SEW.S42072, UBA8.SEW.S42071 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2034-06-02 | 2034-08-10 | 2035-02-12 | 2037-09-14 | 2038-03-31 |  | IM1 | 2025-05-15 | 2030-12-03 | 2031-06-30 | 2032-01-28 | 2034-07-27 | 2038-03-31 |  |  | 0.059064 | 40.9317 |  |  |  |  | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 0.58469 | 40.6175 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 0.67619 | 40.9908 | No | Other | AMP8
| TMS | IED scheme 23 Slough STC | UBA8.SEW.S39598, UBA8.SEW.S42068, UBA8.SEW.S42067, UBA8.SEW.S42066 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-04-29 | 2031-01-22 | 2031-09-22 | 2033-08-20 | 2034-03-31 |  | IM1 | 2025-05-15 | 2030-04-05 | 2030-10-24 | 2031-05-29 | 2032-09-27 | 2034-03-31 |  |  | 0.059064 | 28.4088 |  |  |  |  | 2.2799 | 5.2978 | 8.5224 | 13.5173 | 18.758 | 28.34 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.14049 | 0.67619 | 28.4678 | No | Other | AMP8
| TMS | IED scheme 24 Swindon STC | UBA8.SEW.S39600, UBA8.SEW.S42064, UBA8.SEW.S42062 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-03-31 | 2031-06-06 | 2032-02-04 | 2034-01-03 | 2034-03-31 |  | IM1 | 2025-05-15 | 2030-12-03 | 2031-06-30 | 2032-01-28 | 2034-05-31 | 2034-03-31 |  |  | 0.059064 | 22.463 |  |  |  |  | 2.1822 | 4.0575 | 6.5478 | 9.5734 | 11.7379 | 22.2663 | 0 | 0 | 0.059064 | 0.59337 | 1.1775 | 2.1495 | 7.1523 | 22.5221 | No | Other | AMP8
| TMS | IED scheme 25 Wargrave STC | UBA8.SEW.S42058, UBA8.SEW.S39602, UBA8.SEW.S42060, UBA8.SEW.S42059 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-01-24 | 2031-04-03 | 2031-12-02 | 2033-05-03 | 2033-03-31 |  | IM1 | 2025-05-15 | 2029-04-06 | 2029-10-23 | 2030-05-24 | 2032-03-17 | 2033-03-31 |  |  | 0.059064 | 15.0752 |  |  |  |  | 1.1111 | 3.0821 | 5.0476 | 7.919 | 10.517 | 14.9872 | 0 | 0 | 0.059064 | 0.14049 | 0.14049 | 0.65247 | 2.0039 | 15.1343 | No | Other | AMP8
| TMS | INV4 Sites Storm Overflow Programme | L620 | 08TW101108ft, 08TW101108ui, 08TW101108ni, 08TW101108uc, 08TW101108aa, 08TW101108it, 08TW101108es, 08TW101108ot, 08TW101108ac, 08TW101108nj, 08TW101108ad, 08TW101108do, 08TW101108nk, 08TW101108rm, 08TW101108nl, 08TW101108ta, 08TW101108uf, 08TW101108us, 08TW101108os, 08TW101108qa, 08TW101108ol, 08TW101108tt, 08TW101108ed, 08TW101108cv, 08TW101108tw, 08TW101108ae, 08TW101108pt, 08TW101108ag, 08TW101108pv, 08TW101108fv, 08TW101108rk, 08TW101108ah, 08TW101108tb, 08TW101108ai, 08TW101108tc, 08TW101108iv, 08TW101108om, 08TW101108nm, 08TW101108ix, 08TW101108iz, 08TW101108hd, 08TW101108ep, 08TW101108cb, 08TW101108ak, 08TW101108ja, 08TW101108no, 08TW101108gb, 08TW101108dp, 08TW101108nn, 08TW101108fw, 08TW101108al, 08TW101108fx, 08TW101108dx, 08TW101108pf, 08TW101108rb, 08TW101108pg, 08TW101108gr, 08TW101108am, 08TW101108td, 08TW101108np, 08TW101108an, 08TW101108ao, 08TW101108ap, 08TW101108jk, 08TW101108nc, 08TW101108nb, 08TW101108na, 08TW101108mz, 08TW101108my, 08TW101108mx, 08TW101108mw, 08TW101108mv, 08TW101108fk, 08TW101108aq, 08TW101108nq, 08TW101108uq, 08TW101108te, 08TW101108nr, 08TW101108fl, 08TW101108jo, 08TW101108jm, 08TW101108ar, 08TW101108gg, 08TW101108ou, 08TW101108rh, 08TW101108jq, 08TW101108at, 08TW101108gm, 08TW101108qe, 08TW101108jr, 08TW101108qz, 08TW101108js, 08TW101108ns, 08TW101108uk, 08TW101108ud, 08TW101108el, 08TW101108qf, 08TW101108ny, 08TW101108rc, 08TW101108au, 08TW101108fh, 08TW101108pi, 08TW101108hi, 08TW101108hj, 08TW101108fo, 08TW101108nt, 08TW101108ez, 08TW101108nu, 08TW101108gd, 08TW101108aw, 08TW101108tz, 08TW101108jx, 08TW101108jw, 08TW101108jy, 08TW101108dz, 08TW101108tf, 08TW101108gf, 08TW101108ba, 08TW101108kb, 08TW101108bd, 08TW101108ew, 08TW101108tg, 08TW101108ul, 08TW101108ut, 08TW101108uu, 08TW101108uv, 08TW101108uw, 08TW101108ux, 08TW101108uy, 08TW101108uz, 08TW101108dm, 08TW101108ke, 08TW101108up, 08TW101108nw, 08TW101108ei, 08TW101108be, 08TW101108gj, 08TW101108cc, 08TW101108bf, 08TW101108uh, 08TW101108kf, 08TW101108th, 08TW101108qg, 08TW101108kj, 08TW101108et, 08TW101108nx, 08TW101108kk, 08TW101108tu, 08TW101108bg, 08TW101108du, 08TW101108ey, 08TW101108pj, 08TW101108pk, 08TW101108bh, 08TW101108ue, 08TW101108ko, 08TW101108ti, 08TW101108re, 08TW101108gx, 08TW101108gh, 08TW101108bk, 08TW101108bl, 08TW101108ev, 08TW101108bm, 08TW101108bn, 08TW101108qi, 08TW101108gk, 08TW101108rf, 08TW101108of, 08TW101108ks, 08TW101108dn, 08TW101108or, 08TW101108fc, 08TW101108op, 08TW101108dl, 08TW101108ee, 08TW101108bo, 08TW101108fu, 08TW101108kt, 08TW101108fd, 08TW101108bp, 08TW101108bq, 08TW101108gu, 08TW101108hp, 08TW101108br, 08TW101108ku, 08TW101108bs, 08TW101108nz, 08TW101108oq, 08TW101108pn, 08TW101108po, 08TW101108pp, 08TW101108ex, 08TW101108dk, 08TW101108ri, 08TW101108on, 08TW101108dj, 08TW101108qk, 08TW101108oa, 08TW101108eg, 08TW101108pq, 08TW101108ky, 08TW101108ua, 08TW101108bu, 08TW101108di, 08TW101108lb, 08TW101108ff, 08TW101108tj, 08TW101108bv, 08TW101108bw, 08TW101108rg, 08TW101108rj, 08TW101108qs, 08TW101108ql, 08TW101108dh, 08TW101108va, 08TW101108dt, 08TW101108dg, 08TW101108dr, 08TW101108bb, 08TW101108fg, 08TW101108fp, 08TW101108ub, 08TW101108eh, 08TW101108bx, 08TW101108ds, 08TW101108by, 08TW101108ca, 08TW101108bz, 08TW101108ro, 08TW101108qw, 08TW101108qx, 08TW101108lf, 08TW101108lg, 08TW101108ps, 08TW101108li, 08TW101108de, 08TW101108lj, 08TW101108lk, 08TW101108nv, 08TW101108ug, 08TW101108gp, 08TW101108ab, 08TW101108ln, 08TW101108gq, 08TW101108cd, 08TW101108dc, 08TW101108lo, 08TW101108pw, 08TW101108rl, 08TW101108fi, 08TW101108eo, 08TW101108ob, 08TW101108tk, 08TW101108lq, 08TW101108lr, 08TW101108bc, 08TW101108lv, 08TW101108dv, 08TW101108un, 08TW101108fq, 08TW101108ek, 08TW101108da, 08TW101108gs, 08TW101108eq, 08TW101108tx, 08TW101108cz, 08TW101108hx, 08TW101108fm, 08TW101108ce, 08TW101108cy, 08TW101108oc, 08TW101108dq, 08TW101108gl, 08TW101108fs, 08TW101108ef, 08TW101108dw, 08TW101108ia, 08TW101108mb, 08TW101108ga, 08TW101108cf, 08TW101108az, 08TW101108cg, 08TW101108gv, 08TW101108gw, 08TW101108qn, 08TW101108od, 08TW101108ch, 08TW101108ic, 08TW101108mf, 08TW101108ty, 08TW101108tl, 08TW101108em, 08TW101108cx, 08TW101108gc, 08TW101108cw, 08TW101108ej, 08TW101108mi, 08TW101108mj, 08TW101108cj, 08TW101108ck, 08TW101108cm, 08TW101108ie, 08TW101108qo, 08TW101108df, 08TW101108ax, 08TW101108vb, 08TW101108gz, 08TW101108ih, 08TW101108ii, 08TW101108ij, 08TW101108ik, 08TW101108if, 08TW101108dy, 08TW101108ig, 08TW101108ea, 08TW101108fb, 08TW101108cn, 08TW101108qt, 08TW101108co, 08TW101108oe, 08TW101108cu, 08TW101108cp, 08TW101108cq, 08TW101108fj, 08TW101108cr, 08TW101108ml, 08TW101108mm, 08TW101108jl, 08TW101108fa, 08TW101108ra, 08TW101108ur, 08TW101108gn, 08TW101108tm, 08TW101108og, 08TW101108fz, 08TW101108rp, 08TW101108tn, 08TW101108oo, 08TW101108qp, 08TW101108mq, 08TW101108gi, 08TW101108tv, 08TW101108fn, 08TW101108to, 08TW101108ip, 08TW101108eb, 08TW101108oh, 08TW101108iq, 08TW101108qq, 08TW101108oi, 08TW101108cs, 08TW101108ct, 08TW101108tp, 08TW101108ms, 08TW101108mt, 08TW101108ci, 08TW101108tq, 08TW101108gy, 08TW101108qr, 08TW101108pz, 08TW101108tr, 08TW101108db, 08TW101108ts, 08TW101108ec, 08TW101108gt | WINEP Investigations (wastewater) | PCDWW18 | Retained | UBA8.SEW.S39995 | 2027-04-30 | 2027-04-30 | 2025-06-03 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-03-31 |  | IM1 | 2024-10-16 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 |  |  | -0.94307 | 15.0045 |  |  |  | 9.7663 | 24.3546 | 33.978 | 33.978 | 33.978 | 33.978 | 33.978 | 0 | 0 | -0.94307 | 14.0614 | 14.0614 | 14.0614 | 14.0614 | 14.0614 | No | Other | AMP8
| TMS | LECKHAMPSTEAD STW | M160 | 08TW101402e | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41635 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  | IM2 | 2024-06-19 | 2025-12-18 | 2026-06-26 | 2026-09-28 | 2027-07-08 | 2030-03-31 |  |  | 0.13362 | 2.3178 |  |  |  |  | 0.16973 | 0.45671 | 0.7639 | 2.2324 | 2.8311 | 2.865 | 0 | 0 | 0.13362 | 1.7187 | 2.4514 | 2.4514 | 2.4514 | 2.4514 | No | Other | AMP8
| TMS | Lots Road SPS Electrical Upgrade | L883 |  | Climate change uplift | PCDWW32 | Retained |  |  |  | 2025-04-01 | 2026-08-19 | 2027-04-27 | 2027-08-24 | 2030-07-15 | 2030-04-25 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-09-03 | 2028-01-06 | 2029-01-30 | 2030-04-26 |  |  | 0.29415 | 28.2338 |  |  |  |  | 1.1328 | 3.7026 | 8.0883 | 19.0005 | 27.9044 | 28.6246 | 0 | 0 | 0.29415 | 0.91193 | 4.5254 | 26.4031 | 28.2247 | 28.5279 | No | Other | AMP8
| TMS | MAIDENHEAD STW | M110 | 08TW100165a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S37931 | 2027-03-31 | 2027-03-31 | 2022-09-23 | 2022-09-24 | 2024-03-02 | 2024-09-12 | 2026-12-09 | 2028-03-31 |  | IM1 | 2024-09-18 | 2026-09-17 | 2028-02-24 | 2028-09-05 | 2030-12-02 | 2028-03-31 |  |  | 0.012118 | 1.8507 |  |  |  |  | 0.47046 | 1.8284 | 2.0786 | 2.0939 | 2.0939 | 2.0939 | 0 | 0 | 0.012118 | 0.099436 | 0.19853 | 0.43195 | 1.6509 | 1.8628 | No | Other | AMP8
| TMS | MARSH GIBBON STW | L840 | 08TW101398a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-09-18 | 2024-09-18 | 2025-04-30 | 2025-06-20 | 2025-12-13 | 2027-03-31 |  | IM6 | 2024-09-18 | 2024-10-16 | 2025-12-10 | 2026-01-30 | 2026-06-05 | 2026-03-31 |  |  | 0.37645 | 0.5846 |  |  |  | 9.193e-07 | 0.88119 | 1.3564 | 1.3648 | 1.3648 | 1.3648 | 1.3648 | 0 | 0 | 0.37645 | 0.96105 | 0.96105 | 0.96105 | 0.96105 | 0.96105 | No | Other | AMP8
| TMS | Moreton in Marsh STW - AMP8 Growth | M091 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S39487 |  |  | 2024-10-16 | 2025-10-16 | 2026-05-16 | 2026-12-14 | 2028-11-24 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-06-18 | 2027-04-27 | 2027-11-03 | 2029-03-28 | 2029-12-31 |  |  | 0.032719 | 7.1355 |  |  |  |  | 0.094183 | 1.925 | 4.4442 | 7.1804 | 7.3679 | 7.5002 | 0 | 0 | 0.032719 | 1.0105 | 3.2375 | 7.0119 | 7.1225 | 7.1682 | Yes | Other | AMP8
| TMS | OXFORD STW | K245 | 08TW100166a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2024-03-31 | 2025-03-31 | 2021-04-30 | 2022-01-31 | 2025-12-31 | 2027-03-30 | 2032-03-30 | 2032-02-29 |  | IM3 | 2024-09-18 | 2024-10-03 | 2025-11-12 | 2027-05-28 | 2030-03-31 | 2030-03-31 |  |  | 0.074917 | 2.532 |  |  |  |  | 0.21438 | 0.55319 | 1.1445 | 1.7517 | 2.3684 | 4.1745 | 0 | 0 | 0.074917 | 0.26407 | 0.88306 | 1.7052 | 2.5581 | 2.6069 | Yes | Other | AMP8
| TMS | PANGBOURNE STW | M251 | 08TW100176a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S38523 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-04-18 | 2026-02-11 | 2026-08-25 | 2027-12-16 | 2029-03-31 |  | IM1 | 2024-10-16 | 2027-02-18 | 2027-11-17 | 2028-06-05 | 2029-08-09 | 2029-03-31 |  |  | 0.00072778 | 2.1392 |  |  |  |  | 0.17756 | 0.54956 | 1.5018 | 2.169 | 2.1887 | 2.1941 | 0 | 0 | 0.00072778 | 0.21329 | 0.52192 | 1.8045 | 2.1214 | 2.1399 | No | Other | AMP8
| TMS | Phosphorus Investigations | UBA8.SEW.S39057 | 08TW100204a, 08TW100202a, 08TW100201a, 08TW100203a, 08TW100200a, 08TW100199a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  | IM1 | 2024-06-19 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 |  |  | 0 | 2.4669 | [5 empty] | 1.4632 | 3.3919 | 3.8597 | 3.8597 | 3.8597 | 0 | 0 | 0 | 0 | 0.50409 | 2.0185 | 2.4669 | 2.4669 | No | Other | AMP8
| TMS | PR24 WINEP Ammonia Investigations | UBA8.SEW.S38655 | 08TW100180a, 08TW100178a, 08TW100179a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  | IM1 | 2024-06-19 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 |  |  | 0 | 0.47362 |  |  |  |  | 0.40442 | 0.80883 | 1.2132 | 1.2132 | 1.2132 | 1.2132 | 0 | 0 | 0 | 0 | 0.09531 | 0.47362 | 0.47362 | 0.47362 | No | Other | AMP8
| TMS | WWNI PR24 WINEP WFD SW Investigations | M146 | 08TW100193a, 08TW100189a, 08TW100188a, 08TW100185a, 08TW100184a, 08TW100183a, 08TW100182a, 08TW100195a, 08TW100191a, 08TW100190a, 08TW100187a | WINEP Investigations (wastewater) | PCDWW18 | Retained | UBA8.SEW.S38654 | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  | IM1 | 2024-06-10 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 | 2027-06-30 |  |  | 0.45293 | 3.2996 |  |  |  |  | 1.4338 | 2.8677 | 4.3015 | 4.3015 | 4.3015 | 4.3015 | 0 | 0 | 0.45293 | 3.275 | 3.7526 | 3.7526 | 3.7526 | 3.7526 | No | Other | AMP8
| TMS | PR24 WINEP SSSI Investigations | M147 | 08TW100152a, 08TW100149a, 08TW101463a, 08TW101459a | WINEP Investigations (wastewater) | PCDWW18 | Retained | UBA8.SEW.S38661, UBA8.SEW.S38569, UBA8.SEW.S40785, UBA8.SEW.S40789 | 2027-04-30 | 2027-04-30 | 2024-07-17 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  | IM1 | 2024-07-17 | 2029-06-30 | 2029-06-30 | 2029-06-30 | 2029-06-30 | 2029-06-30 |  | 4 outputs (one of the four delayed due to delivery partner capacity, remaining 3 scheduled to complete on time). | 0.15889 | 1.8981 |  |  |  |  | 1.5816 | 1.676 | 1.7705 | 1.7705 | 1.7705 | 1.7705 | 0 | 0 | 0.15889 | 1.414 | 1.7766 | 2.0349 | 2.057 | 2.057 | No | Other | AMP8
| TMS | PR24 WINEP UMON6d | M490 | 08TW100734a, 08TW100734b, 08TW100734c, 08TW100734e, 08TW100734f, 08TW100734g, 08TW100734h, 08TW100734i, 08TW100734j, 08TW100734k, 08TW100734l, 08TW100734m, 08TW100734n, 08TW100734o, 08TW100734p, 08TW100734q, 08TW100734r, 08TW100734s, 08TW100734t, 08TW100734u, 08TW100734v, 08TW100734w, 08TW100734x, 08TW100734y, 08TW100734z, 08TW100734aa, 08TW100734ab, 08TW100734ac, 08TW100734ad, 08TW100734ae, 08TW100734af, 08TW100734ag, 08TW100734ah, 08TW100734ai, 08TW100734aj, 08TW100734ak, 08TW100734al, 08TW100734am | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | PCDWW3 | Retained | UBA8.SEW.S40421B | 2030-03-31 | 2030-03-31 |  | 2030-05-12 | 2030-06-14 | 2031-01-13 | 2032-11-19 | 2034-03-31 |  | IM1 | 2025-10-23 | 2026-11-27 | 2027-07-27 | 2028-02-24 | 2030-05-31 | 2030-03-31 |  |  | 0.14561 | 0.25371 | [8 empty] | 0.3124 | 6.3935 | 0 | 0 | 0.14561 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | No | Other | AMP8
| TMS | SHIRBURN STW | M165 | 08TW101402f | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41636 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2028-05-19 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  | IM1 | 2024-06-19 | 2027-05-20 | 2028-02-17 | 2028-08-29 | 2029-12-14 | 2032-03-31 |  |  | 0.11681 | 3.0331 |  |  |  |  | 0.16961 | 0.34121 | 0.45857 | 0.72701 | 1.4634 | 3.0859 | 0 | 0 | 0.11681 | 0.25926 | 0.73161 | 2.8878 | 3.1499 | 3.1499 | No | Other | AMP8
| TMS | Stansted Mountifitchet STW- AMP8 Growth | M232 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40435, UBA8.SEW.S38269 |  |  | 2024-11-20 | 2030-03-04 | 2031-02-09 | 2031-08-26 | 2032-12-14 | 2034-03-31 |  | IM1 | 2024-11-20 | 2026-11-19 | 2028-09-28 | 2029-04-26 | 2032-03-24 | 2033-03-31 |  |  | 0.29009 | 26.1888 | [8 empty] | 0.45598 | 25.8918 | 0 | 0 | 0.29009 | 1.2304 | 3.0127 | 6.6594 | 11.8878 | 26.4789 | No | Other | AMP8
| TMS | TEMPLE GUITING STW | M164 | 08TW101402g | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41637 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2027-05-19 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  | IM1 | 2024-06-19 | 2027-05-20 | 2028-02-17 | 2028-08-29 | 2029-12-14 | 2031-03-31 |  |  | 0.17392 | 4.1303 |  |  |  |  | 0.27136 | 0.68577 | 1.0997 | 2.2819 | 3.7545 | 4.2987 | 0 | 0 | 0.17392 | 0.36107 | 0.82908 | 4.0977 | 4.3043 | 4.3043 | No | Other | AMP8
| TMS | Thame STW - AMP8 Growth | M247 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S38270 |  |  | 2024-10-16 | 2029-04-01 | 2030-02-09 | 2030-08-22 | 2031-12-07 | 2033-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-10-12 | 2028-04-26 | 2029-08-15 | 2029-09-30 |  |  | 0.45547 | 34.1113 | [6 empty] | 0.10014 | 0.36109 | 13.3284 | 34.617 | 0 | 0 | 0.45547 | 2.0236 | 9.0805 | 29.2663 | 34.0908 | 34.5668 | No | Other | AMP8
| TMS | Pr24 WINEP Wallingford Beach Bathing Water study | L891 | 08TW100264a | WINEP Investigations (wastewater) | PCDWW18 | Retained | UBA8.SEW.S38660 | 2027-04-30 | 2027-04-30 | 2024-11-19 | 2026-04-20 | 2027-09-28 | 2028-05-18 | 2031-06-04 | 2031-03-31 |  | IM1 | 2024-11-19 | 2031-03-31 | 2031-03-31 | 2031-03-31 | 2031-03-31 | 2031-03-31 |  |  | 0.2231 | 0 |  |  |  |  | 0.014623 | 0.036441 | 0.063612 | 0.13601 | 0.22007 | 0.24307 | 0 | 0 | 0.2231 | 0.2231 | 0.2231 | 0.2231 | 0.2231 | 0.2231 | No | Other | AMP8
| TMS | Wantage STW - AMP8 Growth | M182 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40436, UBA8.SEW.S38271, UBA8.SEW.S41830 |  |  | 2024-10-16 | 2025-11-18 | 2027-06-20 | 2027-12-19 | 2029-11-17 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-05-09 | 2028-12-12 | 2031-03-26 | 2030-03-31 |  |  | 0.50041 | 38.664 |  |  |  |  | 0.71864 | 1.3768 | 5.6892 | 29.5346 | 39.5557 | 39.71 | 0 | 0 | 0.50041 | 1.2832 | 2.9878 | 11.3656 | 36.6566 | 39.1644 | No | Other | AMP8
| TMS | WATLINGTON STW | UBA8.SEW.S40809 | 08TW101401a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-02-17 | 2025-02-17 | 2025-06-13 | 2026-01-16 | 2027-11-21 | 2029-03-31 |  | IM6 | 2024-10-16 | 2025-02-17 | 2025-06-13 | 2026-01-16 | 2026-03-31 | 2026-03-31 |  |  | 0 | 0 | [6 empty] | 1.91e-06 | 8.44e-06 | 8.44e-06 | 8.44e-06 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | WELFORD STW | M163 | 08TW101402h | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41638 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-05-19 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  | IM2 | 2024-06-19 | 2025-12-18 | 2026-06-26 | 2026-10-02 | 2027-07-14 | 2030-03-31 |  |  | 0.12946 | 2.3466 |  |  |  |  | 0.16645 | 0.42065 | 0.77438 | 2.2632 | 2.5952 | 2.6226 | 0 | 0 | 0.12946 | 1.2755 | 2.4509 | 2.476 | 2.476 | 2.476 | No | Other | AMP8
| TMS | Wheatley STW - AMP8 Growth | M286 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained | UBA8.SEW.S40434 |  |  | 2024-10-16 | 2025-07-23 | 2026-05-17 | 2026-12-12 | 2028-11-20 | 2030-03-31 |  | IM1 | 2024-10-16 | 2027-03-18 | 2028-01-19 | 2028-07-28 | 2029-11-15 | 2029-09-30 |  |  | 0.062812 | 17.2902 |  |  |  |  | 0.9995 | 3.3341 | 7.8398 | 16.5647 | 17.2567 | 17.4037 | 0 | 0 | 0.062812 | 0.94488 | 3.0657 | 11.0158 | 17.1624 | 17.353 | No | Other | AMP8
| TMS | WINEP Emergency Overflows monitoring | M490 | 08TW100733b, 08TW100733c, 08TW100733d, 08TW100733e, 08TW100733f, 08TW100733g, 08TW100733h, 08TW100733i, 08TW100733j, 08TW100733k | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | PCDWW3 | Retained | UBA8.SEW.S40131 | 2030-03-31 | 2030-03-31 | 2025-06-30 | 2029-10-29 | 2030-06-13 | 2031-01-11 | 2032-11-19 | 2034-03-31 |  | IM1 | 2025-10-23 | 2026-10-02 | 2027-06-01 | 2027-12-22 | 2030-05-31 | 2030-03-31 |  |  | 0.14561 | 0.25371 | [8 empty] | 0.21279 | 4.355 | 0 | 0 | 0.14561 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | No | Other | AMP8
| TMS | Wolvercote Stream Bathing Water Invest | M420 | 08TW100262a | WINEP Investigations (wastewater) | PCDWW18 | Retained | UBA8.SEW.S38659 | 2027-04-30 | 2027-04-30 |  | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 |  | IM1 | 2024-11-19 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  | Investigation forecasting completion in line with Jan forecast, extended sampling programme required following investigation which will continue until April forecast | 0.0088041 | 0.23704 |  |  |  |  | 0.13733 | 0.27465 | 0.27465 | 0.27465 | 0.27465 | 0.27465 | 0 | 0 | 0.0088041 | 0.24584 | 0.24584 | 0.24584 | 0.24584 | 0.24584 | No | Other | AMP8
| TMS | WOLVERTON COMMON STW | M166 | 08TW101402i | Treatment for tightening of sanitary parameters | PCDWW12 | Retained | UBA8.SEW.S41640 | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2027-04-14 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  | IM2 | 2024-06-19 | 2025-12-18 | 2026-06-26 | 2026-10-02 | 2027-07-14 | 2031-03-31 |  |  | 0.12676 | 1.1664 | [6 empty] | 0.074159 | 0.19954 | 0.37061 | 1.2567 | 0 | 0 | 0.12676 | 0.58959 | 1.2785 | 1.2932 | 1.2932 | 1.2932 | No | Other | AMP8
| TMS | Wokingham STW WINEP8 Cypermethrin | M523 | 08TW100102a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained | UBA8.SEW.S40653 | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2026-11-29 | 2028-02-20 | 2028-08-15 | 2030-11-13 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-07-15 | 2028-05-05 | 2028-11-10 | 2030-03-07 | 2032-03-31 |  |  | 0 | 18.1924 | [5 empty] | 0.51808 | 2.5068 | 4.4523 | 10.925 | 17.7999 | 0 | 0 | 0 | 0 | 2.2218 | 6.6153 | 18.0167 | 18.1924 | No | Delivery Mechanism | AMP8
| TMS | Chertsey STW - 08TW100157a, Chertsey STW - 08TW100886a | L837 | 08TW100157a/08TW100886a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-09-18 | 2024-09-18 | 2024-09-25 | 2024-11-09 | 2032-11-23 | 2034-03-31 |  | IM4 | 2024-09-18 | 2025-04-17 | 2025-09-16 | 2025-10-03 | 2034-02-17 | 2034-03-31 |  |  | 2.6615 | 18.8754 |  |  |  |  | 0.47062 | 2.083 | 7.6538 | 14.6616 | 17.0494 | 28.9768 | 0 | 0 | 2.6615 | 6.3959 | 6.5896 | 6.5918 | 7.2547 | 21.5369 | No | Delivery Mechanism | AMP8
| TMS | Chipping Norton STW - 08TW100158a, Chipping Norton STW - 08TW100888a | M105 | 08TW100158a/08TW100888a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38836 | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2026-01-12 | 2026-11-21 | 2027-05-30 | 2029-03-06 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-06-18 | 2027-04-27 | 2027-11-03 | 2029-08-10 | 2030-03-31 |  |  | 0.0982 | 11.2654 |  |  |  |  | 0.12578 | 0.36344 | 4.9528 | 8.9478 | 10.8128 | 11.1559 | 0 | 0 | 0.0982 | 1.2043 | 4.2818 | 10.3571 | 11.2339 | 11.3636 | No | Other | AMP8
| TMS | Iver (North) STW - 08TW100159a | M319 | 08TW100159a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38386 | 2030-05-13 | 2030-05-13 | 2024-11-20 | 2027-04-14 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  | IM1 | 2024-11-20 | 2026-12-17 | 2027-10-15 | 2028-05-02 | 2029-08-20 | 2031-03-31 |  |  | 0.11128 | 2.5071 | [6 empty] | 0.27137 | 0.59334 | 1.6745 | 2.2917 | 0 | 0 | 0.11128 | 0.37892 | 0.94207 | 2.3824 | 2.5921 | 2.6183 | No | Other | AMP8
| TMS | Maidenhead STW - 08TW100160a, Maidenhead STW - 08TW100921a | M110 | 08TW100160a/08TW100921a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38931 | 2030-05-13 | 2030-05-13 | 2024-09-18 | 2028-09-23 | 2030-03-02 | 2030-09-12 | 2032-12-08 | 2034-03-31 |  | IM1 | 2024-09-18 | 2026-09-17 | 2028-02-24 | 2028-09-05 | 2030-12-02 | 2034-03-31 |  |  | 0.18985 | 28.9935 | [8 empty] | 1.1967 | 27.4465 | 0 | 0 | 0.18985 | 1.5578 | 3.1103 | 6.7671 | 25.8635 | 29.1834 | No | Delivery Mechanism | AMP8
| TMS | Highworth STW - 08TW100162a, Highworth STW - 08TW100909a | M224 | 08TW100162a/08TW100909a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38984 | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2026-02-28 | 2027-02-11 | 2027-08-26 | 2028-12-14 | 2030-03-31 |  | IM1 | 2024-10-16 | 2027-04-15 | 2027-12-15 | 2028-11-20 | 2030-03-15 | 2030-03-31 |  |  | 0.043506 | 7.7697 |  |  |  |  | 0.47379 | 1.6853 | 3.9313 | 7.6843 | 7.8434 | 7.9014 | 0 | 0 | 0.043506 | 0.3316 | 1.0951 | 3.1787 | 7.6567 | 7.8132 | No | Other | AMP8
| TMS | Easthampstead Park STW - 08TW100163a, Easthampstead Park STW - 08TW100901a | M239 | 08TW100163a/08TW100901a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38827 | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2028-04-18 | 2029-02-11 | 2029-08-25 | 2030-12-16 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-11-19 | 2027-09-14 | 2028-03-27 | 2029-07-18 | 2032-03-31 |  |  | 0 | 7.726 | [6 empty] | 0.44455 | 1.2706 | 2.6301 | 7.8286 | 0 | 0 | 0 | 0.52112 | 1.5917 | 6.8951 | 7.6611 | 7.726 | No | Delivery Mechanism | AMP8
| TMS | Heyford STW - 08TW100217a | M243 | 08TW100217a | P-removal | PCDWW10 | Retained | UBA8.SEW.S40986 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-05-06 | 2028-02-09 | 2028-08-18 | 2029-12-06 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-06-18 | 2027-03-18 | 2027-09-28 | 2029-01-22 | 2031-03-31 |  |  | 0.046845 | 5.7481 | [6 empty] | 0.35014 | 1.2454 | 2.9052 | 5.8392 | 0 | 0 | 0.046845 | 0.91107 | 2.9003 | 5.7325 | 5.7949 | 5.7949 | No | Delivery Mechanism | AMP8
| TMS | Grendon Underwood STW - 08TW100218a | M250 | 08TW100218a | P-removal | PCDWW10 | Retained | UBA8.SEW.S40987 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-04-18 | 2026-02-11 | 2026-08-25 | 2027-12-16 | 2029-03-31 |  | IM1 | 2024-10-16 | 2026-11-19 | 2027-09-14 | 2028-03-27 | 2029-07-18 | 2029-03-31 |  |  | 0.0013275 | 2.1838 |  |  |  |  | 0.14079 | 0.54538 | 1.3925 | 2.2041 | 2.2229 | 2.2314 | 0 | 0 | 0.0013275 | 0.2987 | 0.55181 | 1.9633 | 2.1675 | 2.1852 | No | Other | AMP8
| TMS | Chertsey STW AMP8 WINEP Low P and Chem | L837 | 08TW100474a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-09-18 | 2024-09-18 | 2024-09-25 | 2024-11-09 | 2032-11-23 | 2034-03-31 |  | IM4 | 2024-09-18 | 2025-04-17 | 2025-09-16 | 2025-10-03 | 2034-02-17 | 2034-03-31 |  |  | 5.6556 | 40.1103 |  |  |  |  | 1.0001 | 4.4263 | 16.2643 | 31.1559 | 36.2301 | 61.5758 | 0 | 0 | 5.6556 | 13.5913 | 14.0029 | 14.0075 | 15.4163 | 45.7659 | No | Delivery Mechanism | AMP8
| TMS | Gerrards Cross STW Cypermethrin - IMP | L676 | 08TW100479a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained | UBA8.SEW.S40608 | 2027-03-31 | 2027-03-31 | 2024-11-20 | 2026-01-01 | 2027-02-14 | 2027-08-17 | 2029-11-15 | 2031-03-31 |  | IM1 | 2022-02-22 | 2026-06-19 | 2027-04-29 | 2027-07-16 | 2029-02-13 | 2031-03-31 |  |  | 0.0127 | 12.4923 | [5 empty] | 0.69402 | 1.9544 | 3.3651 | 8.5504 | 12.3354 | 0 | 0 | 0.0127 | 2.3479 | 6.3068 | 11.7444 | 12.4725 | 12.505 | No | Delivery Mechanism | AMP8
| TMS | Milton under Wychwood STW WINEP P | M094 | 08TW100489a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained | UBA8.SEW.S40203 | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2025-11-08 | 2027-02-19 | 2027-08-15 | 2029-11-12 | 2031-03-31 |  | IM4 | 2024-10-16 | 2028-04-20 | 2029-01-23 | 2029-08-02 | 2031-08-28 | 2031-03-31 |  |  | 0.0065673 | 9.8439 | [5 empty] | 0.5668 | 1.5983 | 2.9168 | 7.3133 | 9.9263 | 0 | 0 | 0.0065673 | 0.0065673 | 0.51564 | 1.1036 | 3.6832 | 9.8505 | No | Delivery Mechanism | AMP8
| TMS | Chieveley STW - 08TW100859a | UBA8.SEW.S38072 | 08TW100859a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2029-03-31 | 2029-03-31 | 2029-03-31 | 2029-03-31 |  | IM1 | 2024-10-16 | 2026-12-08 | 2027-07-26 | 2027-12-10 | 2028-12-14 | 2029-03-31 |  |  | 0 | 1.9663 |  |  |  |  | 0.82971 | 3.7 | 3.9016 | 3.9252 | 3.9252 | 3.9252 | 0 | 0 | 0 | 0 | 0.088921 | 0.35653 | 0.62434 | 1.9663 | No | Other | AMP8
| TMS | East Shefford STW - 08TW100860a | UBA8.SEW.S38508 | 08TW100860a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-17 | 2025-11-23 | 2026-06-21 | 2027-01-17 | 2028-11-22 | 2030-03-31 |  | IM1 | 2024-10-16 | 2027-03-08 | 2027-10-27 | 2028-05-31 | 2030-04-03 | 2030-03-31 |  |  | 0 | 0 | [6 empty] | 8.58e-07 | 8.58e-07 | 8.58e-07 | 8.58e-07 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | Charlton-on-Otmoor STW - 08TW100861a | M299 | 08TW100861a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39049 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-08-22 | 2030-05-16 | 2030-12-11 | 2032-11-19 | 2034-03-31 |  | IM1 | 2024-10-16 | 2027-03-18 | 2028-01-19 | 2028-07-25 | 2029-11-12 | 2034-03-31 |  |  | 0.080954 | 7.0405 | [8 empty] | 0.16117 | 3.8917 | 0 | 0 | 0.080954 | 0.63278 | 0.89578 | 4.367 | 7.0672 | 7.1214 | No | Delivery Mechanism | AMP8
| TMS | Aldershot STW - 08TW100862a | M120 | 08TW100862a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38954 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-07-06 | 2028-10-14 | 2029-05-01 | 2031-03-09 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-08-20 | 2027-12-02 | 2028-06-20 | 2030-04-26 | 2032-03-31 |  |  | 0.24995 | 13.4919 | [6 empty] | 0.52565 | 1.8328 | 4.1999 | 12.7817 | 0 | 0 | 0.24995 | 1.0721 | 3.9249 | 7.466 | 13.4043 | 13.7419 | No | Delivery Mechanism | AMP8
| TMS | Appleton STW - 08TW100863a | UBA8.SEW.S39552 | 08TW100863a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-10-16 | 2025-12-23 | 2026-12-27 | 2027-07-28 | 2030-10-28 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-09-15 | 2027-07-27 | 2028-02-21 | 2030-01-30 | 2032-03-31 |  |  | 0 | 3.5483 | [6 empty] | 0.42376 | 1.5073 | 3.5161 | 7.067 | 0 | 0 | 0 | 0 | 0.41915 | 1.4941 | 3.4869 | 3.5483 | No | Delivery Mechanism | AMP8
| TMS | Arborfield STW - 08TW100864a | M100 | 08TW100864a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39006 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-03-10 | 2026-04-25 | 2026-10-30 | 2028-12-11 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-05-21 | 2027-01-18 | 2027-12-23 | 2030-02-05 | 2030-03-31 |  |  | 0.18143 | 8.858 |  |  |  |  | 0.66968 | 1.9337 | 3.7402 | 9.274 | 11.8264 | 11.9786 | 0 | 0 | 0.18143 | 2.0429 | 3.0174 | 6.7609 | 8.914 | 9.0394 | No | Other | AMP8
| TMS | Ascot STW - 08TW100865a | M158 | 08TW100865a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39004 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-05-13 | 2028-04-17 | 2028-10-30 | 2029-12-12 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-08-20 | 2027-07-06 | 2028-01-18 | 2029-02-27 | 2031-03-31 |  |  | 0.16267 | 13.2192 | [6 empty] | 0.81712 | 2.188 | 5.4784 | 13.4404 | 0 | 0 | 0.16267 | 1.4187 | 4.3605 | 13.1029 | 13.3739 | 13.3819 | No | Delivery Mechanism | AMP8
| TMS | Ash Vale STW - 08TW100866a | M121 | 08TW100866a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39056 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-10-06 | 2029-01-14 | 2029-08-01 | 2031-03-10 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-08-20 | 2027-12-02 | 2028-06-20 | 2029-11-20 | 2032-03-31 |  |  | 0.15902 | 11.6894 | [6 empty] | 0.10115 | 1.6127 | 3.6397 | 10.988 | 0 | 0 | 0.15902 | 1.026 | 3.6403 | 8.714 | 11.588 | 11.8484 | No | Delivery Mechanism | AMP8
| TMS | Banbury STW - 08TW100869a | K435 | 08TW100869a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38967 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-05-04 | 2029-11-29 | 2030-02-05 | 2033-01-27 | 2034-03-31 |  | IM2 | 2019-06-18 | 2026-03-19 | 2026-09-24 | 2027-02-19 | 2029-07-18 | 2034-03-31 |  |  | 0.5445 | 25.8991 | [8 empty] | 1.1942 | 27.4266 | 0 | 0 | 0.5445 | 2.9125 | 8.9313 | 15.9381 | 23.1976 | 26.4435 | No | Delivery Mechanism | AMP8
| TMS | Bicester STW - 08TW100872a | M106 | 08TW100872a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38939 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-28 | 2029-02-22 | 2029-08-19 | 2031-11-23 | 2033-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-05-09 | 2028-12-14 | 2034-11-30 | 2033-03-31 |  |  | 0.16383 | 19.6718 | [6 empty] | 0.65025 | 2.2424 | 4.8095 | 20.012 | 0 | 0 | 0.16383 | 0.33785 | 0.78345 | 3.9324 | 7.9932 | 19.8356 | No | Delivery Mechanism | AMP8
| TMS | Bledington STW - 08TW100873a | M482 | 08TW100873a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39023 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2025-06-15 | 2026-01-09 | 2027-11-16 | 2029-03-31 |  | IM1 | 2024-10-16 | 2027-05-20 | 2028-03-07 | 2028-09-15 | 2030-01-10 | 2029-03-31 |  |  | 0.04123 | 1.9702 |  |  |  |  | 0.12828 | 0.49692 | 1.2687 | 2.0082 | 2.0254 | 2.0331 | 0 | 0 | 0.04123 | 0.096778 | 0.2478 | 1.0299 | 2.0114 | 2.0114 | No | Other | AMP8
| TMS | Bletchingdon STW - 08TW100874a | M103 | 08TW100874a | P-removal | PCDWW10 | Retained | UBA8.SEW.S41885 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-10-18 | 2028-04-10 | 2028-10-02 | 2030-12-11 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-09-17 | 2027-08-05 | 2028-02-17 | 2030-03-21 | 2032-03-31 |  |  | 0.11991 | 9.2923 | [6 empty] | 0.083241 | 1.3335 | 2.6643 | 8.9596 | 0 | 0 | 0.11991 | 1.7222 | 4.1864 | 6.9362 | 9.1811 | 9.4122 | No | Delivery Mechanism | AMP8
| TMS | Bloxham STW - 08TW100875a | M293 | 08TW100875a | P-removal | PCDWW10 | Retained | UBA8.SEW.S41908 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-08-10 | 2028-02-22 | 2029-06-14 | 2030-03-31 |  |  | 0.041569 | 6.5245 |  |  |  |  | 0.40076 | 1.4255 | 3.3253 | 6.4998 | 6.6344 | 6.6835 | 0 | 0 | 0.041569 | 0.72255 | 1.9819 | 6.1714 | 6.4997 | 6.5661 | No | Other | AMP8
| TMS | Bourton-on-the-Water STW - 08TW100877a | L956 | 08TW100877a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-10-16 | 2026-02-11 | 2026-12-07 | 2027-05-13 | 2030-03-07 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-08-20 | 2027-06-15 | 2027-11-19 | 2030-09-13 | 2031-03-31 |  |  | 0.51758 | 6.0029 |  |  |  | 0.013552 | 0.16088 | 1.2595 | 3.2942 | 5.9721 | 6.6022 | 6.6497 | 0 | 0 | 0.51758 | 1.3442 | 2.1186 | 4.0945 | 6.1786 | 6.5204 | No | Other | AMP8
| TMS | Broadwell STW - 08TW100879a | M304 | 08TW100879a | P-removal | PCDWW10 | Retained | UBA8.SEW.S41886 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-30 | 2028-09-13 | 2029-03-15 | 2030-11-21 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2032-03-31 |  |  | 0.11559 | 11.6093 | [6 empty] | 0.099271 | 1.5828 | 3.5722 | 10.7842 | 0 | 0 | 0.11559 | 0.88338 | 2.7293 | 8.8173 | 11.586 | 11.7249 | No | Delivery Mechanism | AMP8
| TMS | Byfield STW - 08TW100880a | M229 | 08TW100880a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38843 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-24 | 2028-05-17 | 2028-12-05 | 2030-11-14 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-05-20 | 2028-02-15 | 2028-08-24 | 2029-12-12 | 2032-03-31 |  |  | 0.080939 | 6.0162 | [6 empty] | 0.24907 | 0.86353 | 2.0673 | 5.7479 | 0 | 0 | 0.080939 | 0.36738 | 1.2168 | 3.6351 | 6.013 | 6.0971 | No | Delivery Mechanism | AMP8
| TMS | Camberley STW - 08TW100881a | M265 | 08TW100881a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39052 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-04 | 2028-02-09 | 2028-08-25 | 2029-12-14 | 2031-03-31 |  | IM1 | 2024-10-16 | 2027-11-18 | 2028-10-25 | 2029-05-11 | 2030-08-30 | 2031-03-31 |  |  | 0 | 34.01 | [5 empty] | 1.409 | 4.4087 | 9.8371 | 24.6211 | 30.5409 | 0 | 0 | 0 | 0.11602 | 1.6444 | 13.2442 | 34.01 | 34.01 | No | Delivery Mechanism | AMP8
| TMS | Chacombe STW - 08TW100882a | M227 | 08TW100882a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38841 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-18 | 2029-02-11 | 2029-08-25 | 2030-12-16 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-11-19 | 2027-09-14 | 2028-03-27 | 2029-07-18 | 2032-03-31 |  |  | 0.048067 | 5.6565 | [6 empty] | 0.23043 | 0.76656 | 1.5261 | 5.3169 | 0 | 0 | 0.048067 | 0.59542 | 1.6968 | 5.1427 | 5.6493 | 5.7046 | No | Delivery Mechanism | AMP8
| TMS | Chadlington STW - 08TW100883a | M429 | 08TW100883a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39016 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-22 | 2029-05-16 | 2029-12-11 | 2031-11-20 | 2033-03-31 |  | IM1 | 2024-10-16 | 2027-02-18 | 2027-11-16 | 2028-06-02 | 2029-09-20 | 2033-03-31 |  |  | 0.11465 | 10.278 | [8 empty] | 0.14997 | 3.6212 | 0 | 0 | 0.11465 | 0.52525 | 0.81818 | 7.5462 | 10.3639 | 10.3926 | No | Delivery Mechanism | AMP8
| TMS | Chalgrove STW - 08TW100884a | L838 | 08TW100884a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  | IM1 | 2024-09-18 | 2026-07-16 | 2026-12-16 | 2027-07-05 | 2029-11-08 | 2030-03-31 |  |  | 0.059098 | 7.8654 |  |  |  | 4.7749e-05 | -0.0098457 | 0.27478 | 0.83678 | 3.6142 | 5.9904 | 6.1243 | 0 | 0 | 0.059098 | 1.4613 | 3.2926 | 6.9148 | 7.8523 | 7.9245 | No | Other | AMP8
| TMS | Charlbury STW - 08TW100885a | UBA8.SEW.S39024 | 08TW100885a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2026-06-15 | 2027-01-09 | 2028-11-17 | 2030-03-31 |  | IM1 | 2024-10-16 | 2027-03-18 | 2027-10-27 | 2028-05-31 | 2030-04-03 | 2030-03-31 |  |  | 0 | 1.973 |  |  |  |  | 0.00053337 | 0.34498 | 0.73189 | 1.946 | 2.1481 | 2.1696 | 0 | 0 | 0 | 0 | 0.54016 | 1.7446 | 1.9451 | 1.973 | No | Other | AMP8
| TMS | Chinnor STW - 08TW100887a | M244 | 08TW100887a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38991 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-04-18 | 2028-02-11 | 2028-08-24 | 2029-12-15 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-11-19 | 2027-09-14 | 2028-03-27 | 2029-07-18 | 2031-03-31 |  |  | 0 | 7.3768 | [6 empty] | 0.45147 | 1.6059 | 3.746 | 7.5291 | 0 | 0 | 0 | 0.048937 | 1.8442 | 6.6253 | 7.3168 | 7.3768 | No | Other | AMP8
| TMS | Church Hanborough STW - 08TW100889a | M222 | 08TW100889a | P-removal | PCDWW10 | Retained | UBA8.SEW.S41884 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-08-31 | 2026-02-21 | 2026-08-14 | 2028-11-19 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-10-12 | 2028-04-26 | 2029-08-15 | 2030-03-31 |  |  | 0.094958 | 13.1871 |  |  |  |  | 0.73289 | 2.1454 | 3.9314 | 9.8618 | 13.2776 | 13.4569 | 0 | 0 | 0.094958 | 1.2126 | 3.0628 | 11.2785 | 13.1593 | 13.282 | No | Other | AMP8
| TMS | Cirencester STW - 08TW100890a | M107 | 08TW100890a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38929 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-19 | 2029-07-27 | 2029-12-05 | 2030-12-11 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-11-19 | 2027-10-12 | 2028-02-18 | 2029-02-23 | 2032-03-31 |  |  | 0.10148 | 13.4198 | [6 empty] | 0.83259 | 2.2294 | 5.5822 | 13.6948 | 0 | 0 | 0.10148 | 0.89502 | 4.3248 | 13.2636 | 13.4667 | 13.5212 | No | Delivery Mechanism | AMP8
| TMS | Crawley STW - 08TW100893a | M374 | 08TW100893a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38969 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-02-24 | 2026-02-21 | 2026-08-19 | 2028-11-21 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2030-03-31 |  |  | 0 | 37.1437 |  |  |  |  | 2.1034 | 6.0121 | 12.5549 | 29.9945 | 36.599 | 37.0499 | 0 | 0 | 0 | 0.47612 | 5.7623 | 27.1816 | 36.5871 | 37.1437 | No | Other | AMP8
| TMS | Cuddesdon STW - 08TW100895a | UBA8.SEW.S39028 | 08TW100895a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-08-22 | 2027-05-16 | 2027-12-11 | 2029-11-19 | 2031-03-31 |  | IM1 | 2024-10-16 | 2028-01-19 | 2028-11-30 | 2029-07-02 | 2031-06-05 | 2031-03-31 |  |  | 0 | 3.502 | [6 empty] | 0.14355 | 0.52132 | 1.2478 | 3.4662 | 0 | 0 | 0 | 0 | 0.15996 | 0.65757 | 1.7118 | 3.502 | No | Delivery Mechanism | AMP8
| TMS | Cuddington STW - 08TW100896a | UBA8.SEW.S38990 | 08TW100896a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2028-07-03 | 2029-05-01 | 2029-11-20 | 2031-10-29 | 2032-03-31 |  |  | 0 | 5.0232 | [6 empty] | 0.20582 | 0.74749 | 1.7891 | 4.97 | 0 | 0 | 0 | 0 | 0.10662 | 0.59788 | 1.4557 | 5.0232 | No | Delivery Mechanism | AMP8
| TMS | Culham STW - 08TW100897a | L670 | 08TW100897a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38909 | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2026-03-01 | 2026-12-24 | 2027-06-24 | 2029-03-23 | 2030-03-31 |  | IM2 | 2022-02-22 | 2025-11-20 | 2026-09-14 | 2027-02-15 | 2029-07-18 | 2030-03-31 |  |  | 0.19058 | 13.7989 |  |  |  |  | 0.53224 | 1.8932 | 4.4162 | 8.6322 | 8.8109 | 8.8761 | 0 | 0 | 0.19058 | 1.8161 | 5.2773 | 9.4302 | 12.2641 | 13.9895 | No | Other | AMP8
| TMS | Culworth STW - 08TW100898a | UBA8.SEW.S38978 | 08TW100898a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2030-08-22 | 2031-05-16 | 2031-12-11 | 2033-11-19 | 2035-03-31 |  | IM1 | 2024-10-16 | 2031-04-25 | 2032-01-16 | 2032-08-09 | 2034-05-30 | 2035-03-31 |  |  | 0 | 3.5203 | [6 empty] | 7.606e-05 | 0.013764 | 0.080135 | 3.2383 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.5203 | No | Delivery Mechanism | AMP8
| TMS | Didcot STW - 08TW100899a | M179 | 08TW100899a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38821 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-30 | 2029-04-16 | 2030-04-04 | 2032-03-22 | 2033-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-05-16 | 2028-12-13 | 2034-03-09 | 2033-03-31 |  |  | 0.1536 | 23.1422 | [6 empty] | 0.16234 | 0.35622 | 0.7502 | 19.5996 | 0 | 0 | 0.1536 | 0.31791 | 1.4366 | 2.3314 | 2.4309 | 23.2958 | No | Delivery Mechanism | AMP8
| TMS | Dorking STW - 08TW100900a | M231 | 08TW100900a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39050 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-04 | 2028-02-09 | 2028-08-25 | 2029-12-14 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-09-17 | 2027-05-21 | 2027-10-01 | 2029-10-03 | 2031-03-31 |  |  | 0.054803 | 12.21 | [5 empty] | 0.74889 | 2.0053 | 5.021 | 11.9771 | 12.3181 | 0 | 0 | 0.054803 | 1.384 | 3.9344 | 10.6671 | 12.1434 | 12.2648 | No | Other | AMP8
| TMS | Esher STW - 08TW100902a | M264 | 08TW100902a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39496 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-02-21 | 2028-02-03 | 2028-08-20 | 2029-12-08 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-12-02 | 2028-06-20 | 2029-10-08 | 2031-03-31 |  |  | 0.092632 | 33.9205 | [5 empty] | 1.4487 | 4.5328 | 10.114 | 25.3142 | 31.4007 | 0 | 0 | 0.092632 | 0.88561 | 6.8462 | 25.2135 | 33.6282 | 34.0132 | No | Delivery Mechanism | AMP8
| TMS | Finstock STW - 08TW100903a | M302 | 08TW100903a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39015 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-06 | 2026-05-22 | 2026-12-07 | 2028-11-17 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-12-02 | 2028-06-15 | 2029-10-03 | 2030-03-31 |  |  | 0.035597 | 5.9617 |  |  |  |  | 0.35997 | 1.2804 | 2.9868 | 5.8383 | 5.9591 | 6.0032 | 0 | 0 | 0.035597 | 0.38985 | 1.1677 | 4.4261 | 5.938 | 5.9972 | No | Other | AMP8
| TMS | Great Milton STW - 08TW100905a | M298 | 08TW100905a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39029 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-12-02 | 2028-06-20 | 2029-10-08 | 2032-03-31 |  |  | 0.12764 | 3.7606 | [6 empty] | 0.14821 | 0.53828 | 1.2884 | 3.579 | 0 | 0 | 0.12764 | 0.62327 | 0.89695 | 2.8886 | 3.8417 | 3.8882 | No | Delivery Mechanism | AMP8
| TMS | Greatworth STW - 08TW100906a | M223 | 08TW100906a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38908 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-05-12 | 2027-02-06 | 2027-08-17 | 2028-12-11 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-09-17 | 2027-07-13 | 2028-01-25 | 2029-05-16 | 2030-03-31 |  |  | 0.089436 | 4.3929 |  |  |  |  | 0.15579 | 0.59885 | 1.1237 | 3.1395 | 4.4353 | 4.4931 | 0 | 0 | 0.089436 | 0.64659 | 1.2801 | 4.3607 | 4.4572 | 4.4823 | No | Other | AMP8
| TMS | Haddenham STW - 08TW100907a | M294 | 08TW100907a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38987 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-08-10 | 2028-02-22 | 2029-06-14 | 2032-03-31 |  |  | 0.036562 | 8.7756 | [6 empty] | 0.1701 | 0.69323 | 2.0277 | 8.6157 | 0 | 0 | 0.036562 | 0.88279 | 2.4501 | 8.2733 | 8.7248 | 8.8122 | No | Delivery Mechanism | AMP8
| TMS | Henley STW - 08TW100908a | M098 | 08TW100908a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38842 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-05-29 | 2028-12-10 | 2029-05-15 | 2029-12-08 | 2031-03-31 |  | IM2 | 2024-10-16 | 2026-03-19 | 2026-10-05 | 2027-01-04 | 2028-02-08 | 2031-03-31 |  |  | 0.098631 | 7.4083 | [8 empty] | 2.1146 | 7.2008 | 0 | 0 | 0.098631 | 2.058 | 4.0874 | 6.9354 | 7.5069 | 7.5069 | No | Delivery Mechanism | AMP8
| TMS | Hogsmill STW - 08TW100910a, Hogsmill 'B' STW - 08TW100220 | M188 | 08TW100910a/08TW100220 | P-removal | PCDWW10 | Retained | UBA8.SEW.S38959 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-27 | 2028-04-06 | 2028-08-16 | 2030-12-11 | 2032-03-31 |  | IM1 | 2025-06-05 | 2026-12-17 | 2028-01-17 | 2028-05-31 | 2030-08-16 | 2032-03-31 |  |  | 0.27 | 44.1204 | [6 empty] | 0.7788 | 1.6008 | 19.4909 | 66.99 | 0 | 0 | 0.27 | 1.1841 | 1.7553 | 1.7553 | 13.0139 | 44.3904 | Yes | Delivery Mechanism | AMP8
| TMS | Horley (Surrey) STW - 08TW100911a | M263 | 08TW100911a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38945 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-10-12 | 2028-04-26 | 2029-08-15 | 2032-03-31 |  |  | 0.059918 | 14.8103 | [6 empty] | 0.8114 | 2.2907 | 4.1811 | 14.3041 | 0 | 0 | 0.059918 | 0.8584 | 4.2205 | 13.5277 | 14.7398 | 14.8702 | No | Delivery Mechanism | AMP8
| TMS | Leatherhead STW - 08TW100914a | M375 | 08TW100914a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38970 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-02-26 | 2028-02-22 | 2028-08-19 | 2030-11-22 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-12-02 | 2028-02-09 | 2029-06-01 | 2032-03-31 |  |  | 0.24098 | 18.2677 | [6 empty] | 1.051 | 3.0041 | 6.2734 | 18.513 | 0 | 0 | 0.24098 | 0.67716 | 4.9888 | 17.8858 | 18.4297 | 18.5087 | No | Delivery Mechanism | AMP8
| TMS | Little Compton STW - 08TW100916a | M242 | 08TW100916a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39025 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-05-19 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-06-18 | 2027-03-18 | 2027-09-28 | 2029-01-22 | 2032-03-31 |  |  | 0.041108 | 3.8447 | [6 empty] | 0.14181 | 0.51503 | 1.2327 | 3.4244 | 0 | 0 | 0.041108 | 0.64084 | 2.0901 | 3.8395 | 3.8858 | 3.8858 | No | Delivery Mechanism | AMP8
| TMS | Little Milton STW - 08TW100917a | M603 | 08TW100917a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38796 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-06-28 | 2028-05-17 | 2028-12-13 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-09-16 | 2028-07-14 | 2029-01-26 | 2030-05-20 | 2032-03-31 |  |  | 0.00031576 | 4.0596 | [6 empty] | 0.16257 | 0.54081 | 1.0766 | 3.7511 | 0 | 0 | 0.00031576 | 0.20536 | 0.58826 | 1.2069 | 3.9617 | 4.0599 | No | Delivery Mechanism | AMP8
| TMS | Longborough STW - 08TW100918a | M303 | 08TW100918a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39027 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2032-03-31 |  |  | 0.035391 | 3.7403 | [6 empty] | 0.14416 | 0.52354 | 1.2531 | 3.481 | 0 | 0 | 0.035391 | 0.26265 | 0.877 | 2.8387 | 3.7308 | 3.7756 | No | Delivery Mechanism | AMP8
| TMS | Middleton Cheney STW - 08TW100919a | K563 | 08TW100919a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38975 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2026-06-28 | 2027-01-19 | 2028-12-10 | 2030-03-31 |  | IM2 | 2025-02-27 | 2025-10-23 | 2026-06-30 | 2026-10-29 | 2029-12-12 | 2030-03-31 |  |  | 0.22808 | 6.0108 |  |  |  |  | 0.27326 | 0.99242 | 2.3754 | 6.1163 | 6.545 | 6.5985 | 0 | 0 | 0.22808 | 1.0528 | 3.0283 | 5.2548 | 5.9258 | 6.2389 | No | Other | AMP8
| TMS | Milton-Under-Wychwood STW - 08TW100922a | K540 | 08TW100922a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38888 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-12 | 2026-05-07 | 2026-11-18 | 2028-12-14 | 2030-03-31 |  | IM4 | 2024-10-16 | 2028-04-20 | 2029-01-23 | 2029-08-02 | 2031-08-28 | 2030-03-31 |  |  | 2.9275 | 1.6481 | [5 empty] | 0.47253 | 1.2119 | 4.0875 | 5.9359 | 6.0184 | 0 | 0 | 2.9275 | 3.6976 | 4.1421 | 4.5756 | 4.5756 | 4.5756 | No | Other | AMP8
| TMS | Moreton-in-Marsh STW - 08TW100923a | M091 | 08TW100923a | P-removal | PCDWW10 | Retained | UBA8.SEW.S41910 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-02-04 | 2027-01-10 | 2027-07-25 | 2028-12-13 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-06-18 | 2027-04-27 | 2027-11-03 | 2029-03-28 | 2030-03-31 |  |  | 0.041643 | 9.0815 |  |  |  |  | 0.58171 | 2.0691 | 4.8267 | 9.4346 | 9.6299 | 9.7012 | 0 | 0 | 0.041643 | 1.286 | 4.1205 | 8.9242 | 9.065 | 9.1232 | Yes | Other | AMP8
| TMS | Oxford STW - 08TW100924a | K245 | 08TW100924a | P-removal | PCDWW10 | Retained |  | 2024-03-31 | 2025-03-31 | 2021-04-30 | 2022-01-31 | 2025-12-31 | 2027-03-30 | 2032-03-30 | 2032-02-29 |  | IM3 | 2024-09-18 | 2024-10-03 | 2025-11-12 | 2027-05-28 | 2030-03-31 | 2030-03-31 |  |  | 1.1293 | 38.1678 |  |  |  |  | 3.2317 | 8.3389 | 17.2529 | 26.4051 | 35.7017 | 62.9271 | 0 | 0 | 1.1293 | 3.9807 | 13.3116 | 25.7048 | 38.5616 | 39.2971 | Yes | Delivery Mechanism | AMP8
| TMS | Princes Risborough STW - 08TW100925a | M249 | 08TW100925a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38936 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-03-04 | 2029-02-09 | 2029-08-26 | 2030-12-15 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-10-12 | 2028-04-26 | 2029-08-15 | 2032-03-31 |  |  | 0.23697 | 8.1214 | [6 empty] | 0.33485 | 1.2161 | 2.9107 | 8.0857 | 0 | 0 | 0.23697 | 0.87824 | 1.9283 | 7.0906 | 8.2724 | 8.3583 | No | Delivery Mechanism | AMP8
| TMS | Priors Marston STW - 08TW100926a | M457 | 08TW100926a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38896 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-10-25 | 2026-06-14 | 2027-01-17 | 2028-11-19 | 2030-03-31 |  | IM1 | 2025-08-21 | 2026-10-22 | 2027-08-10 | 2028-02-22 | 2029-06-14 | 2032-03-31 |  | Data Error | 0.039788 | 5.5607 | [10 empty] | 0 | 0 | 0.039788 | 0.62062 | 0.97804 | 5.2755 | 5.5723 | 5.6005 | No | Other | AMP8
| TMS | Reading STW - 08TW100928a | M180 | 08TW100928a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38971 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-02-27 | 2027-09-08 | 2028-10-15 | 2031-03-30 | 2032-03-31 |  | IM2 | 2024-10-16 | 2025-11-20 | 2028-05-23 | 2028-12-22 | 2033-03-07 | 2032-03-31 |  |  | 0.83683 | 36.725 | [5 empty] | 0.60826 | 1.3497 | 3.9717 | 22.5515 | 53.2557 | 0 | 0 | 0.83683 | 1.7168 | 3.1307 | 13.0747 | 22.3028 | 37.5619 | No | Delivery Mechanism | AMP8
| TMS | Great Rollright STW - 08TW100929a | M306 | 08TW100929a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39026 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-02-18 | 2028-01-05 | 2028-07-14 | 2029-11-01 | 2032-03-31 |  |  | 0.018152 | 3.5308 | [6 empty] | 0.1356 | 0.49245 | 1.1787 | 3.2742 | 0 | 0 | 0.018152 | 0.38955 | 0.76279 | 2.435 | 3.5042 | 3.5489 | No | Delivery Mechanism | AMP8
| TMS | Sandhurst STW - 08TW100930a | M467 | 08TW100930a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39054 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-08-29 | 2030-09-13 | 2031-03-15 | 2032-11-20 | 2034-03-31 |  | IM1 | 2024-10-16 | 2027-04-15 | 2028-01-26 | 2028-08-04 | 2029-11-22 | 2034-03-31 |  |  | 0 | 11.781 | [8 empty] | 0.098905 | 10.7445 | 0 | 0 | 0 | 0.25679 | 1.5788 | 7.3556 | 11.5871 | 11.781 | No | Delivery Mechanism | AMP8
| TMS | Sherborne St John STW - 08TW100932a | M122 | 08TW100932a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39053 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-08-03 | 2026-11-01 | 2027-05-17 | 2029-03-09 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-07-16 | 2027-10-15 | 2028-05-02 | 2030-02-20 | 2030-03-31 |  |  | 0.073248 | 3.7087 |  |  |  |  | 0.032377 | 0.53713 | 1.2663 | 3.2386 | 3.4647 | 3.4929 | 0 | 0 | 0.073248 | 0.47472 | 1.3581 | 2.5848 | 3.6914 | 3.782 | No | Other | AMP8
| TMS | Shrivenham STW - 08TW100933a | M089 | 08TW100933a | P-removal | PCDWW10 | Retained | UBA8.SEW.S41911 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-06-03 | 2028-05-08 | 2028-11-20 | 2029-12-10 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-09-17 | 2027-04-27 | 2027-11-03 | 2029-01-30 | 2031-03-31 |  |  | 0.16915 | 16.7485 | [6 empty] | 1.0531 | 3.3371 | 9.2985 | 16.5008 | 0 | 0 | 0.16915 | 1.2839 | 7.3372 | 16.5939 | 16.8714 | 16.9176 | No | Delivery Mechanism | AMP8
| TMS | Silchester STW - 08TW100934a | M085 | 08TW100934a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38955 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-06-29 | 2027-01-10 | 2027-05-28 | 2029-01-07 | 2030-03-31 |  | IM3 | 2024-10-16 | 2026-01-22 | 2026-03-16 | 2026-05-11 | 2028-09-27 | 2030-03-31 |  |  | 0.79273 | 8.9857 | [5 empty] | 0.82155 | 2.3491 | 5.7644 | 9.3982 | 9.5261 | 0 | 0 | 0.79273 | 3.6446 | 6.2485 | 9.0512 | 9.7785 | 9.7785 | No | Other | AMP8
| TMS | Slough STW - 08TW100935a | K222 | 08TW100935a | P-removal | PCDWW10 | Retained |  | 2025-03-31 | 2025-03-31 | 2020-11-30 | 2024-02-28 | 2025-05-30 | 2026-04-30 | 2029-05-31 | 2029-06-30 |  | IM3 | 2020-11-30 | 2024-02-28 | 2025-11-18 | 2027-04-18 | 2029-12-18 | 2029-12-31 |  | Original timeline not deliverable due to delivery partner resourcing. | 0.51727 | 16.0453 |  |  |  |  | 3.6302 | 11.5772 | 22.0591 | 32.1961 | 32.5005 | 32.5005 | 0 | 0 | 0.51727 | 2.4073 | 7.4792 | 13.0567 | 16.5625 | 16.5625 | No | Other | AMP8
| TMS | Swindon STW - 08TW100939a | M181 | 08TW100939a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38926 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-09-03 | 2026-06-05 | 2027-03-07 | 2030-11-29 | 2032-03-31 |  | IM1 | 2024-09-30 | 2026-09-17 | 2027-09-03 | 2028-03-16 | 2030-03-22 | 2032-03-31 |  |  | 0.46429 | 39.3417 |  |  |  |  | 0.14602 | 0.42467 | 0.64438 | 8.672 | 27.4178 | 51.7629 | 0 | 0 | 0.46429 | 1.4378 | 1.96 | 12.1546 | 21.3807 | 39.806 | Yes | Delivery Mechanism | AMP8
| TMS | Towersey STW - 08TW100941a | M307 | 08TW100941a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39030 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2032-03-31 |  |  | 0.11182 | 3.6434 | [6 empty] | 0.14314 | 0.51986 | 1.2443 | 3.4565 | 0 | 0 | 0.11182 | 0.51533 | 0.87701 | 2.8249 | 3.7107 | 3.7552 | No | Delivery Mechanism | AMP8
| TMS | Tring STW - 08TW100942a | M297 | 08TW100942a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38932 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2032-03-31 |  |  | 0.088113 | 13.3662 | [6 empty] | 0.2785 | 1.0114 | 2.4209 | 6.725 | 0 | 0 | 0.088113 | 0.62888 | 1.6955 | 9.578 | 13.3677 | 13.4544 | No | Delivery Mechanism | AMP8
| TMS | Wash Water STW - 08TW100946a | L897 | 08TW100946a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2023-05-12 | 2023-05-13 | 2023-11-05 | 2024-05-08 | 2024-12-15 | 2026-03-31 |  | IM3 | 2024-10-16 | 2024-12-02 | 2025-05-27 | 2026-04-28 | 2026-11-16 | 2030-03-31 |  |  | 0.48503 | 8.7604 |  |  |  |  | 9.8874 | 9.9824 | 9.9824 | 9.9824 | 9.9824 | 9.9824 | 0 | 0 | 0.48503 | 9.1537 | 9.2454 | 9.2454 | 9.2454 | 9.2454 | No | Other | AMP8
| TMS | White Waltham STW - 08TW100947a | M119 | 08TW100947a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39002 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-02-07 | 2028-08-16 | 2030-05-23 | 2032-03-31 |  |  | 0.099166 | 6.2836 | [6 empty] | 0.24806 | 0.9009 | 2.1563 | 5.99 | 0 | 0 | 0.099166 | 0.47167 | 1.1271 | 3.0654 | 6.1951 | 6.3828 | No | Delivery Mechanism | AMP8
| TMS | Widford STW - 08TW100948a | M317 | 08TW100948a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38952 | 2030-03-31 | 2030-03-31 | 2024-11-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  | IM1 | 2024-11-16 | 2026-12-17 | 2027-10-15 | 2028-05-02 | 2029-08-20 | 2030-03-31 |  |  | 0.075309 | 5.3669 |  |  |  |  | 0.32723 | 1.164 | 2.7152 | 5.3073 | 5.4171 | 5.4572 | 0 | 0 | 0.075309 | 0.42885 | 1.3025 | 4.8944 | 5.4004 | 5.4423 | No | Other | AMP8
| TMS | Witney STW - 08TW100949a | M246 | 08TW100949a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38802 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-31 | 2028-02-07 | 2028-08-15 | 2029-12-10 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-10-12 | 2028-04-26 | 2029-08-15 | 2031-03-31 |  |  | 0 | 3.5067 | [5 empty] | 0.093253 | 0.2497 | 7.9791 | 14.6332 | 15.1279 | 0 | 0 | 0 | 0.012983 | 0.64171 | 2.7115 | 3.2926 | 3.5067 | No | Delivery Mechanism | AMP8
| TMS | Ash Ridge (Wokingham) STW - 08TW100950a | M460 | 08TW100950a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39007 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-02-25 | 2026-02-21 | 2026-08-19 | 2028-11-21 | 2030-03-31 |  | IM1 | 2024-10-16 | 2027-04-15 | 2028-01-26 | 2028-08-04 | 2030-03-22 | 2030-03-31 |  |  | 0 | 10.6972 |  |  |  |  | 0.60024 | 1.7156 | 3.5827 | 8.5594 | 10.4441 | 10.5728 | 0 | 0 | 0 | 0.12114 | 1.4395 | 5.5623 | 10.4837 | 10.6972 | No | Other | AMP8
| TMS | Ashendon STW - 08TW100953a | M484 | 08TW100953a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39551 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-11-29 | 2025-06-16 | 2026-01-09 | 2027-11-18 | 2029-03-31 |  | IM1 | 2024-10-16 | 2027-05-20 | 2028-03-07 | 2028-09-15 | 2030-01-10 | 2029-03-31 |  |  | 0.044905 | 1.6085 |  |  |  |  | 0.015548 | 0.29297 | 0.74207 | 1.6349 | 1.6674 | 1.6768 | 0 | 0 | 0.044905 | 0.095893 | 0.19918 | 0.84398 | 1.6534 | 1.6534 | No | Other | AMP8
| TMS | Buckland STW - 08TW100954a | M291 | 08TW100954a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38806 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-14 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-07-16 | 2027-01-28 | 2027-06-14 | 2028-09-08 | 2031-09-30 |  |  | 0.1057 | 3.5023 | [6 empty] | 0.14932 | 0.49672 | 0.98886 | 3.4453 | 0 | 0 | 0.1057 | 0.60241 | 2.8513 | 3.5597 | 3.608 | 3.608 | No | Delivery Mechanism | AMP8
| TMS | Farnborough STW - 08TW100955a | M483 | 08TW100955a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38976 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-08-22 | 2027-05-16 | 2027-12-11 | 2029-11-19 | 2031-03-31 |  | IM1 | 2024-10-16 | 2027-05-20 | 2028-03-07 | 2028-09-15 | 2030-01-10 | 2031-03-31 |  |  | 0.043236 | 3.393 | [6 empty] | 0.13978 | 0.50765 | 1.2151 | 3.3753 | 0 | 0 | 0.043236 | 0.19551 | 0.39181 | 1.7402 | 3.4362 | 3.4362 | No | Delivery Mechanism | AMP8
| TMS | Hanwell STW - 08TW100956a | M602 | 08TW100956a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38915 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-08-19 | 2028-06-19 | 2028-12-22 | 2030-04-18 | 2032-03-31 |  |  | 0 | 3.7352 | [6 empty] | 0.031523 | 0.53008 | 1.2521 | 3.4531 | 0 | 0 | 0 | 0.18516 | 0.567 | 1.2203 | 3.6764 | 3.7352 | No | Delivery Mechanism | AMP8
| TMS | Mollington STW - 08TW100957a | M477 | 08TW100957a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38974 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-10-27 | 2028-05-12 | 2029-08-31 | 2032-03-31 |  |  | 0.0020347 | 3.5376 | [6 empty] | 0.14268 | 0.51818 | 1.2403 | 3.4453 | 0 | 0 | 0.0020347 | 0.61016 | 0.75934 | 2.8865 | 3.5147 | 3.5397 | No | Delivery Mechanism | AMP8
| TMS | Warmington STW - 08TW100959a | M476 | 08TW100959a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38973 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-10-27 | 2028-05-12 | 2029-08-31 | 2032-03-31 |  |  | 0.0017205 | 3.5143 | [6 empty] | 0.14173 | 0.51474 | 1.232 | 3.4225 | 0 | 0 | 0.0017205 | 0.60919 | 0.7552 | 2.8671 | 3.4912 | 3.516 | No | Delivery Mechanism | AMP8
| TMS | Aston Le Walls STW - 08TW100960a | M241 | 08TW100960a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39031 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-05-19 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-05-21 | 2027-02-18 | 2027-08-31 | 2028-12-15 | 2031-03-31 |  |  | 0.037359 | 2.6676 | [6 empty] | 0.09886 | 0.40908 | 1.0508 | 2.3863 | 0 | 0 | 0.037359 | 0.5569 | 1.6268 | 2.6726 | 2.705 | 2.705 | No | Delivery Mechanism | AMP8
| TMS | Abbess Roding STW - 08TW100967a | M464 | 08TW100967a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38981 | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-11-20 | 2027-04-15 | 2028-01-13 | 2028-07-24 | 2030-03-21 | 2032-03-31 |  |  | 0 | 5.2736 | [6 empty] | 0.20017 | 0.72695 | 1.74 | 4.8334 | 0 | 0 | 0 | 0.12114 | 0.75461 | 2.8209 | 5.1687 | 5.2736 | No | Delivery Mechanism | AMP8
| TMS | Newmans Lane SPS | UBA8.SEW.S39218 | 08TW100976a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2026-03-31 18:20 | 2026-06-27 | 2026-08-22 | 2026-11-21 | 2027-03-31 |  | IM1 | 2024-11-06 | 2026-06-01 | 2027-02-22 | 2027-12-20 | 2029-01-18 | 2027-12-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 2.1009 |  |  |  |  | 0.041273 | 1.6949 | 1.6949 | 1.6949 | 1.6949 | 1.6949 | 0 | 0 | 0.11692 | 0.4247 | 1.0583 | 2.1093 | 2.2063 | 2.2178 | No | Other | AMP8
| TMS | ANDOVERSFORD STW | UBA8.SEW.S39216 | 08TW100978a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2025-12-17 19:14 | 2026-06-15 13:27 | 2026-10-13 09:37 | 2027-08-09 | 2028-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2029-11-28 | 2029-09-30 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 4.8755 |  |  |  |  | 0.24526 | 3.2528 | 4.8219 | 4.8219 | 4.8219 | 4.8219 | 0 | 0 | 0.11692 | 0.4182 | 1.1772 | 3.6257 | 4.9924 | 4.9924 | No | Other | AMP8
| TMS | Briff Lane (Bucklebury) STW | UBA8.SEW.S40747 | 08TW100980a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-08-19 09:17 | 2028-03-06 01:42 | 2028-07-17 04:39 | 2029-06-15 | 2030-03-31 |  | IM1 | 2024-07-03 | 2027-07-22 | 2028-06-28 | 2029-01-12 | 2030-01-29 | 2029-06-30 |  |  | 0.087687 | 3.2985 | [5 empty] | 0.060273 | 1.0116 | 2.7932 | 3.1648 | 3.1648 | 0 | 0 | 0.087687 | 0.31365 | 0.50932 | 1.0537 | 3.3476 | 3.3862 | No | Other | AMP8
| TMS | Briff Lane (Bucklebury) STW | UBA8.SEW.S40747 | 08TW100980a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-08-19 09:17 | 2028-03-06 01:42 | 2028-07-17 04:39 | 2029-06-15 | 2030-03-31 |  | IM1 | 2024-07-03 | 2027-07-22 | 2028-06-28 | 2029-01-12 | 2030-01-29 | 2029-06-30 |  |  | 0.029229 | 3.2571 | [5 empty] | 0.065296 | 1.0959 | 3.026 | 3.4285 | 3.4285 | 0 | 0 | 0.029229 | 0.10455 | 0.16977 | 0.7595 | 3.2445 | 3.2864 | No | Other | AMP8
| TMS | BENTLEY STW | UBA8.SEW.S39213 | 08TW100981a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2029-03-30 03:39 | 2029-09-10 11:03 | 2029-11-05 11:03 | 2030-02-23 | 2030-03-31 |  | IM1 | 2024-08-28 | 2027-11-18 | 2028-10-31 | 2029-05-21 | 2030-09-06 | 2030-03-31 |  |  | 0.077944 | 3.3779 | [6 empty] | 0.077669 | 2.2109 | 3.3985 | 3.3985 | 0 | 0 | 0.077944 | 0.2788 | 0.45273 | 0.50944 | 2.7276 | 3.4558 | No | Other | AMP7
| TMS | BENTLEY STW | UBA8.SEW.S39213 | 08TW100981a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2029-03-30 03:39 | 2029-09-10 11:03 | 2029-11-05 11:03 | 2030-02-23 | 2030-03-31 |  | IM1 | 2024-08-28 | 2027-11-18 | 2028-10-31 | 2029-05-21 | 2030-09-06 | 2030-03-31 |  |  | 0.038972 | 5.7645 | [6 empty] | 0.14424 | 4.106 | 6.3116 | 6.3116 | 0 | 0 | 0.038972 | 0.1394 | 0.22637 | 0.33168 | 4.4511 | 5.8035 | No | Other | AMP7
| TMS | BLEDINGTON STW | UBA8.SEW.S39212 | 08TW100982a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-03-23 | 2027-03-22 | 2027-12-13 | 2030-12-09 | 2031-03-31 |  | IM1 | 2024-07-31 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2029-10-31 | 2030-12-31 |  |  | 0.11692 | 3.9415 |  |  |  |  | 0.10641 | 0.78894 | 1.4283 | 2.2897 | 3.1511 | 3.784 | 0 | 0 | 0.11692 | 0.4182 | 1.3497 | 3.2108 | 4.0584 | 4.0584 | No | Other | AMP8
| TMS | BLETCHINGDON STW | UBA8.SEW.S39211 | 08TW100983a | Storm overflows | PCDWW5 | Retained |  | 2028-03-31 | 2028-03-31 | 2024-07-17 | 2025-10-22 00:04 | 2026-10-06 | 2027-06-29 | 2030-06-25 | 2031-03-31 |  | IM1 | 2024-07-17 | 2026-08-20 | 2027-07-27 | 2028-02-10 | 2029-08-02 | 2030-06-30 |  |  | 0.11692 | 4.2516 |  |  |  |  | 0.21504 | 1.0612 | 2.433 | 3.2681 | 3.9101 | 4.0631 | 0 | 0 | 0.11692 | 0.4182 | 1.3484 | 3.9488 | 4.3336 | 4.3685 | No | Other | AMP8
| TMS | BODDINGTON STW | UBA8.SEW.S39199 | 08TW100985a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-12-17 14:25 | 2027-10-07 01:20 | 2028-06-29 01:20 | 2031-03-08 | 2031-03-31 |  | IM1 | 2024-06-26 | 2026-09-17 | 2027-07-27 | 2028-02-10 | 2029-12-03 | 2031-03-31 |  |  | 0.11692 | 5.1539 | [5 empty] | 0.20891 | 1.1948 | 2.923 | 4.0602 | 5.1276 | 0 | 0 | 0.11692 | 0.4182 | 1.3091 | 4.0293 | 5.2708 | 5.2708 | No | Other | AMP8
| TMS | CHURT SPS | UBA8.SEW.S39188 | 08TW100986a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-11-19 10:45 | 2027-11-18 10:45 | 2028-07-01 09:44 | 2031-01-26 | 2031-03-31 |  | IM1 | 2024-07-31 | 2026-09-01 | 2027-05-19 | 2028-03-20 | 2029-04-13 | 2028-03-31 |  |  | 0.11692 | 7.2321 | [5 empty] | 0.42722 | 2.7165 | 4.5111 | 6.0089 | 7.3444 | 0 | 0 | 0.11692 | 0.4182 | 1.3875 | 7.2146 | 7.3164 | 7.349 | No | Other | AMP8
| TMS | BRICKENDON STW | UBA8.SEW.S39177 | 08TW100987a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2026-03-31 18:20 | 2026-06-27 | 2026-08-22 | 2026-11-21 | 2027-03-31 |  | IM1 | 2024-07-03 | 2026-07-24 | 2027-06-30 | 2028-01-14 | 2029-08-03 | 2029-12-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 1.8439 |  |  |  |  | 0.40358 | 1.4112 | 1.4112 | 1.4112 | 1.4112 | 1.4112 | 0 | 0 | 0.11692 | 0.4182 | 0.81985 | 1.8173 | 1.9532 | 1.9608 | No | Other | AMP8
| TMS | BURGHFIELD STW | M534 | 08TW100988a | Storm Overflow - Wetland | PCDWW5b | Retained | UBA8.SEW.S39172 | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 02:33 | 2029-01-19 02:33 | 2029-10-12 02:33 | 2032-09-09 | 2033-03-31 |  | IM1 | 2024-06-26 | 2027-11-18 | 2028-10-10 | 2029-04-25 | 2030-08-14 | 2032-09-30 |  |  | 0.029229 | 5.774 | [6 empty] | 1.1225 | 5.7479 | 12.2513 | 23.7955 | 0 | 0 | 0.029229 | 0.10455 | 2.2004 | 5.7087 | 5.7985 | 5.8033 | No | Delivery Mechanism | AMP8
| TMS | BURGHFIELD STW | M534 | 08TW100988a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39172 | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 02:33 | 2029-01-19 02:33 | 2029-10-12 02:33 | 2032-09-09 | 2033-03-31 |  | IM1 | 2024-06-26 | 2027-11-18 | 2028-10-10 | 2029-04-25 | 2030-08-14 | 2032-09-30 |  |  | 0.087687 | 1.4158 | [6 empty] | 0.1981 | 1.0143 | 2.162 | 4.1992 | 0 | 0 | 0.087687 | 0.31365 | 0.86767 | 1.4868 | 1.5026 | 1.5035 | No | Delivery Mechanism | AMP8
| TMS | CHADLINGTON STW | UBA8.SEW.S39171 | 08TW100989a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2028-01-21 07:16 | 2028-07-10 05:05 | 2028-11-01 03:38 | 2029-08-13 | 2030-03-31 |  | IM1 | 2024-08-28 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2030-05-14 | 2029-09-30 |  |  | 0.11692 | 4.9956 | [6 empty] | 0.26409 | 3.8854 | 4.9618 | 4.9618 | 0 | 0 | 0.11692 | 0.4182 | 1.2284 | 2.9964 | 5.072 | 5.1125 | No | Other | AMP8
| TMS | CHAPEL ROW (Berks) STW | UBA8.SEW.S39169 | 08TW100991a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-10-21 07:13 | 2028-02-09 05:03 | 2028-04-23 03:36 | 2028-10-25 | 2029-03-31 |  | IM1 | 2024-06-19 | 2026-11-02 | 2027-09-24 | 2028-04-10 | 2029-04-27 | 2027-12-31 |  |  | 0.11692 | 3.0332 | [5 empty] | 0.048008 | 0.94665 | 2.7209 | 2.7209 | 2.7209 | 0 | 0 | 0.11692 | 0.4182 | 0.94505 | 3.0914 | 3.1393 | 3.1501 | No | Other | AMP8
| TMS | CHARLTON-ON-OTMOOR STW | UBA8.SEW.S39168 | 08TW100992a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2026-01-21 23:11 | 2026-08-24 11:25 | 2027-01-14 11:35 | 2028-01-07 | 2028-03-31 |  | IM1 | 2024-08-28 | 2027-04-22 | 2028-02-28 | 2028-09-11 | 2029-09-26 | 2028-09-30 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.029229 | 7.7608 |  |  |  |  | 0.41133 | 4.778 | 8.5103 | 8.5103 | 8.5103 | 8.5103 | 0 | 0 | 0.029229 | 0.10455 | 0.18493 | 4.4405 | 7.79 | 7.79 | No | Other | AMP8
| TMS | CHARLTON-ON-OTMOOR STW | UBA8.SEW.S39168 | 08TW100992a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2026-01-21 23:11 | 2026-08-24 11:25 | 2027-01-14 11:35 | 2028-01-07 | 2028-03-31 |  | IM1 | 2024-08-28 | 2027-04-22 | 2028-02-28 | 2028-09-11 | 2029-09-26 | 2028-09-30 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.087687 | 4.0076 |  |  |  |  | 0.19357 | 2.2485 | 4.0048 | 4.0048 | 4.0048 | 4.0048 | 0 | 0 | 0.087687 | 0.31365 | 0.51646 | 2.5191 | 4.0953 | 4.0953 | No | Other | AMP8
| TMS | CHINNOR STW | UBA8.SEW.S39167 | 08TW100993a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-12-17 18:21 | 2028-12-15 18:21 | 2029-09-07 18:21 | 2032-08-28 | 2033-03-31 |  | IM1 | 2024-10-16 | 2027-11-18 | 2028-10-31 | 2029-05-21 | 2030-08-01 | 2032-09-30 |  |  | 0.087687 | 10.8288 | [6 empty] | 0.48086 | 2.1417 | 4.5323 | 11.4455 | 0 | 0 | 0.087687 | 0.31365 | 0.50932 | 0.68596 | 8.9967 | 10.9165 | No | Delivery Mechanism | AMP8
| TMS | CHINNOR STW | UBA8.SEW.S39167 | 08TW100993a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-12-17 18:21 | 2028-12-15 18:21 | 2029-09-07 18:21 | 2032-08-28 | 2033-03-31 |  | IM1 | 2024-10-16 | 2027-11-18 | 2028-10-31 | 2029-05-21 | 2030-08-01 | 2032-09-30 |  |  | 0.029229 | 9.0059 | [6 empty] | 0.40962 | 1.8244 | 3.8608 | 9.7499 | 0 | 0 | 0.029229 | 0.10455 | 0.16977 | 0.32024 | 7.3998 | 9.0351 | No | Delivery Mechanism | AMP8
| TMS | COMBE STW | UBA8.SEW.S39163 | 08TW100997a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-10-21 15:41 | 2027-04-11 01:23 | 2027-08-03 07:50 | 2028-05-15 | 2029-03-31 |  | IM1 | 2024-07-31 | 2027-05-20 | 2028-03-28 | 2028-10-10 | 2029-10-25 | 2028-06-30 |  |  | 0.11692 | 2.8487 |  |  |  |  | 0.042323 | 0.41336 | 2.2718 | 2.5158 | 2.5158 | 2.5158 | 0 | 0 | 0.11692 | 0.4182 | 0.68092 | 1.816 | 2.9426 | 2.9656 | No | Other | AMP8
| TMS | Compton (Berks) STW | M531 | 08TW100998a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39162 | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-11-20 | 2027-11-19 | 2028-08-11 | 2031-08-08 | 2032-03-31 |  | IM1 | 2024-07-10 | 2027-08-19 | 2028-06-19 | 2028-12-22 | 2030-04-18 | 2031-09-30 |  |  | 0.058458 | 7.3161 | [5 empty] | 0.50463 | 1.8182 | 4.288 | 6.2889 | 8.7423 | 0 | 0 | 0.058458 | 0.24069 | 1.319 | 3.0706 | 7.2784 | 7.3745 | No | Delivery Mechanism | AMP8
| TMS | Compton (Berks) STW | M531 | 08TW100998a | Flow to Full Treatment | PCDWW4 | Retained | UBA8.SEW.S39162 | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-11-20 | 2027-11-19 | 2028-08-11 | 2031-08-08 | 2032-03-31 |  | IM1 | 2024-07-10 | 2027-08-19 | 2028-06-19 | 2028-12-22 | 2030-04-18 | 2031-09-30 |  |  | 0.058458 | 6.1877 | [5 empty] | 0.24855 | 0.89553 | 2.112 | 3.0975 | 4.3059 | 0 | 0 | 0.058458 | 0.2091 | 0.33955 | 1.9486 | 6.15 | 6.2461 | No | Delivery Mechanism | AMP8
| TMS | CRONDALL STW | M528 | 08TW101000a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39160 | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2026-08-19 21:45 | 2027-04-30 03:13 | 2027-10-15 22:52 | 2028-12-11 | 2029-03-31 |  | IM1 | 2024-10-23 | 2027-08-19 | 2028-06-19 | 2028-12-22 | 2030-04-18 | 2028-12-31 |  |  | 0.087687 | 8.4694 |  |  |  |  | 0.096712 | 1.0133 | 3.5081 | 5.3115 | 5.3115 | 5.3115 | 0 | 0 | 0.087687 | 3.0544 | 3.3142 | 5.5335 | 8.4909 | 8.5571 | No | Other | AMP8
| TMS | CRONDALL STW | M528 | 08TW101000a | Flow to Full Treatment | PCDWW4 | Retained | UBA8.SEW.S39160 | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2026-08-19 21:45 | 2027-04-30 03:13 | 2027-10-15 22:52 | 2028-12-11 | 2029-03-31 |  | IM1 | 2024-10-23 | 2027-08-19 | 2028-06-19 | 2028-12-22 | 2030-04-18 | 2028-12-31 |  |  | 0.029229 | 1.2192 |  |  |  |  | 0.072958 | 0.7644 | 2.6465 | 4.0069 | 4.0069 | 4.0069 | 0 | 0 | 0.029229 | 0.10455 | 0.16977 | 0.91391 | 1.2411 | 1.2484 | No | Other | AMP8
| TMS | CUDDINGTON STW | UBA8.SEW.S39159 | 08TW101001a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2028-02-18 04:57 | 2028-10-11 13:04 | 2029-03-18 02:28 | 2030-04-16 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2030-09-12 | 2030-03-31 |  |  | 0.11692 | 4.3321 | [6 empty] | 0.15331 | 1.9631 | 4.1641 | 4.2731 | 0 | 0 | 0.11692 | 0.4182 | 1.3325 | 2.4468 | 4.2046 | 4.449 | No | Other | AMP8
| TMS | STONEBRIDGE SSO, BROCKHAM CSO | UBA8.SEW.S38361 | 08TW101003a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-03-17 15:13 | 2028-08-14 12:27 | 2029-01-11 09:40 | 2030-09-26 | 2031-03-31 |  | IM1 | 2024-10-23 | 2026-12-17 | 2027-09-17 | 2028-07-21 | 2030-04-29 | 2030-09-30 |  |  | 0.11692 | 6.2555 | [6 empty] | 0.17063 | 2.4773 | 5.033 | 6.2667 | 0 | 0 | 0.11692 | 0.4182 | 1.4768 | 3.293 | 6.21 | 6.3724 | No | Other | AMP8
| TMS | EAST GRAFTON STW | UBA8.SEW.S39155 | 08TW101005a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-03-17 06:20 | 2028-07-20 14:02 | 2028-10-12 03:10 | 2029-05-09 | 2030-03-31 |  | IM1 | 2024-10-23 | 2027-09-23 | 2028-08-22 | 2029-03-08 | 2030-08-23 | 2029-06-30 |  |  | 0.11692 | 1.4588 | [6 empty] | 0.027663 | 0.91562 | 1.0735 | 1.0735 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 0.80897 | 1.446 | 1.5758 | No | Other | AMP8
| TMS | EAST SHEFFORD STW | M545 | 08TW101006a | Storm Overflow - Wetland | PCDWW5b | Retained | UBA8.SEW.S39154 | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  | IM1 | 2024-10-23 | 2026-04-23 | 2027-03-01 | 2027-09-13 | 2029-05-04 | 2032-09-30 |  |  | 0.029229 | 4.651 | [6 empty] | 0.4556 | 1.6859 | 3.7493 | 13.7669 | 0 | 0 | 0.029229 | 0.10455 | 0.26198 | 2.661 | 4.6073 | 4.6803 | No | Delivery Mechanism | AMP8
| TMS | EAST SHEFFORD STW | M545 | 08TW101006a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39154 | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  | IM1 | 2024-10-23 | 2026-04-23 | 2027-03-01 | 2027-09-13 | 2029-05-04 | 2032-09-30 |  |  | 0.087687 | 10.9108 | [6 empty] | 0.10687 | 0.39545 | 0.87948 | 3.2293 | 0 | 0 | 0.087687 | 0.31365 | 5.581 | 10.3823 | 10.9814 | 10.9985 | No | Delivery Mechanism | AMP8
| TMS | EYDON STW | UBA8.SEW.S39153 | 08TW101007a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-09-16 16:20 | 2028-01-23 04:14 | 2028-04-17 20:10 | 2028-11-18 | 2029-03-31 |  | IM1 | 2024-07-03 | 2026-12-01 | 2027-11-02 | 2028-05-22 | 2029-06-07 | 2028-03-31 |  |  | 0.087687 | 1.8018 | [5 empty] | 0.029305 | 0.34976 | 1.52 | 1.52 | 1.52 | 0 | 0 | 0.087687 | 0.31365 | 0.74867 | 1.7912 | 1.8786 | 1.8895 | No | Other | AMP8
| TMS | EYDON STW | UBA8.SEW.S39153 | 08TW101007a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-09-16 16:20 | 2028-01-23 04:14 | 2028-04-17 20:10 | 2028-11-18 | 2029-03-31 |  | IM1 | 2024-07-03 | 2026-12-01 | 2027-11-02 | 2028-05-22 | 2029-06-07 | 2028-03-31 |  |  | 0.029229 | 1.8971 | [5 empty] | 0.037297 | 0.44515 | 1.9345 | 1.9345 | 1.9345 | 0 | 0 | 0.029229 | 0.10455 | 0.4744 | 1.8013 | 1.9125 | 1.9264 | No | Other | AMP8
| TMS | Fyfield (Wilts) STW | M235 | 08TW101008a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39152 | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-08-21 | 2028-08-19 | 2029-05-12 | 2032-05-08 | 2033-03-31 |  | IM1 | 2025-09-30 | 2026-09-17 | 2027-05-25 | 2027-11-30 | 2029-03-26 | 2027-06-30 |  |  | 0.379 | 15.7519 | [6 empty] | 0.61305 | 1.7456 | 4.8497 | 11.4498 | 0 | 0 | 0.379 | 2.1004 | 5.9405 | 14.1338 | 14.215 | 16.1309 | No | Delivery Mechanism | AMP8
| TMS | Fyfield (Wilts) STW | M235 | 08TW101008a | Flow to Full Treatment | PCDWW4 | Retained | UBA8.SEW.S39152 | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-08-21 | 2028-08-19 | 2029-05-12 | 2032-05-08 | 2033-03-31 |  | IM1 | 2025-09-30 | 2026-09-17 | 2027-05-25 | 2027-11-30 | 2029-03-26 | 2027-06-30 |  |  | 0.11466 | 5.4454 | [6 empty] | 0.2154 | 0.61331 | 1.704 | 4.0229 | 0 | 0 | 0.11466 | 0.67179 | 1.9797 | 4.8584 | 4.8869 | 5.5601 | No | Delivery Mechanism | AMP8
| TMS | Gerrards Cross STW | UBA8.SEW.S39151 | 08TW101009a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2025-10-23 | 2026-10-22 | 2027-07-15 | 2030-07-11 | 2031-03-31 |  | IM1 | 2024-07-10 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2030-04-11 | 2030-06-30 |  |  | 0.077944 | 13.4337 |  |  |  |  | 0.9653 | 5.1675 | 8.2029 | 10.8638 | 13.5248 | 14.3682 | 0 | 0 | 0.077944 | 0.2788 | 0.557 | 6.7127 | 13.274 | 13.5116 | No | Other | AMP8
| TMS | Gerrards Cross STW | UBA8.SEW.S39151 | 08TW101009a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2025-10-23 | 2026-10-22 | 2027-07-15 | 2030-07-11 | 2031-03-31 |  | IM1 | 2024-07-10 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2030-04-11 | 2030-06-30 |  |  | 0.038972 | 10.448 |  |  |  |  | 0.75845 | 4.0602 | 6.4451 | 8.5358 | 10.6266 | 11.2893 | 0 | 0 | 0.038972 | 0.1394 | 0.30829 | 5.1449 | 10.3002 | 10.4869 | No | Other | AMP8
| TMS | GRENDON UNDERWOOD STW | UBA8.SEW.S39149 | 08TW101011a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-03-31 04:16 | 2027-09-16 06:31 | 2027-11-11 06:31 | 2028-03-03 | 2028-03-31 |  | IM1 | 2024-07-03 | 2027-02-18 | 2027-12-23 | 2028-07-13 | 2030-03-13 | 2030-12-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 5.3849 |  |  |  |  | 0.15802 | 2.524 | 5.3423 | 5.3072 | 5.3072 | 5.3072 | 0 | 0 | 0.11692 | 0.4182 | 0.98107 | 2.9578 | 5.4411 | 5.5018 | No | Other | AMP8
| TMS | HAMPSTEAD NORREYS STW | UBA8.SEW.S39148 | 08TW101012a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-01-21 12:41 | 2027-01-20 12:41 | 2027-09-12 19:21 | 2029-04-23 | 2029-03-31 |  | IM6 | 2024-07-10 | 2027-02-18 | 2027-12-23 | 2028-07-13 | 2030-02-06 | 2029-03-31 |  |  | 0.029229 | 8.7016 |  |  |  |  | 0.36579 | 3.3929 | 6.6018 | 9.2733 | 9.5598 | 9.5598 | 0 | 0 | 0.029229 | 0.10455 | 0.27833 | 4.0752 | 8.7308 | 8.7308 | No | Other | AMP8
| TMS | HAMPSTEAD NORREYS STW | UBA8.SEW.S39148 | 08TW101012a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-01-21 12:41 | 2027-01-20 12:41 | 2027-09-12 19:21 | 2029-04-23 | 2029-03-31 |  | IM6 | 2024-07-10 | 2027-02-18 | 2027-12-23 | 2028-07-13 | 2030-02-06 | 2029-03-31 |  |  | 0.087687 | 3.2753 |  |  |  |  | 0.12193 | 1.131 | 2.2006 | 3.0911 | 3.1866 | 3.1866 | 0 | 0 | 0.087687 | 0.31365 | 0.54551 | 1.8111 | 3.363 | 3.363 | No | Other | AMP8
| TMS | HAMSTEAD MARSHALL STW | UBA8.SEW.S39147 | 08TW101013a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2027-12-16 18:19 | 2028-02-29 11:27 | 2028-04-25 11:27 | 2028-08-28 | 2029-03-31 |  | IM1 | 2024-07-31 | 2027-03-18 | 2028-02-09 | 2028-08-22 | 2029-09-07 | 2028-09-30 |  |  | 0.11692 | 1.8966 | [5 empty] | 0.025401 | 0.51087 | 1.4685 | 1.4685 | 1.4685 | 0 | 0 | 0.11692 | 0.4182 | 0.69717 | 1.5427 | 2.0039 | 2.0135 | No | Other | AMP8
| TMS | HANWELL STW | UBA8.SEW.S39146 | 08TW101014a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2028-02-18 09:09 | 2028-05-30 13:37 | 2028-08-06 16:35 | 2029-01-24 | 2029-03-31 |  | IM1 | 2024-06-19 | 2028-01-20 | 2028-11-22 | 2029-06-13 | 2030-06-28 | 2028-12-31 |  |  | 0.11692 | 5.2778 | [6 empty] | 0.243 | 5.1867 | 5.1867 | 5.1867 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 1.112 | 4.8272 | 5.3947 | No | Other | AMP8
| TMS | CHARLBURY STW | UBA8.SEW.S40746 | 08TW101016a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2028-01-21 21:40 | 2029-01-19 21:40 | 2029-09-24 22:20 | 2031-06-07 | 2032-03-31 |  | IM1 | 2024-08-28 | 2027-09-23 | 2028-08-22 | 2029-03-08 | 2030-07-26 | 2031-06-30 |  |  | 0.11692 | 4.8944 | [6 empty] | 0.18852 | 0.79148 | 2.8991 | 4.7654 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 1.5601 | 4.5228 | 5.0113 | No | Delivery Mechanism | AMP8
| TMS | Horley (Surrey) STW | UBA8.SEW.S38366 | 08TW101017a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2030-07-10 | 2032-09-30 |  |  | 0.11692 | 15.1892 | [6 empty] | 0.6732 | 1.8205 | 4.8534 | 16.0956 | 0 | 0 | 0.11692 | 0.4182 | 1.6437 | 7.1122 | 14.6857 | 15.3062 | No | Delivery Mechanism | AMP8
| TMS | FINSTOCK STW | UBA8.SEW.S40745 | 08TW101018a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2028-02-18 23:58 | 2029-02-16 23:58 | 2029-11-09 23:58 | 2031-11-17 | 2032-03-31 |  | IM1 | 2024-07-10 | 2027-01-21 | 2027-11-24 | 2028-06-14 | 2030-08-12 | 2031-12-31 |  |  | 0.11692 | 3.4819 | [6 empty] | 0.079963 | 0.71524 | 1.3505 | 2.656 | 0 | 0 | 0.11692 | 0.4182 | 1.0871 | 1.9477 | 3.4058 | 3.5988 | No | Delivery Mechanism | AMP8
| TMS | HORTON-CUM-STUDLEY STW | UBA8.SEW.S39141 | 08TW101019a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2027-01-21 23:39 | 2027-06-03 14:09 | 2027-08-30 23:50 | 2028-04-08 | 2028-03-31 |  | IM1 | 2024-07-10 | 2027-02-18 | 2027-12-23 | 2028-07-13 | 2029-07-30 | 2028-12-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 3.5509 | [5 empty] | 0.21088 | 3.2388 | 3.2898 | 3.2898 | 3.2898 | 0 | 0 | 0.11692 | 0.4182 | 0.85841 | 3.0677 | 3.6442 | 3.6678 | No | Other | AMP8
| TMS | HUNGERFORD STW | UBA8.SEW.S39140 | 08TW101020a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-17 12:12 | 2028-09-15 12:12 | 2029-06-08 12:12 | 2032-03-08 | 2032-03-31 |  | IM1 | 2024-11-06 | 2027-10-21 | 2028-09-22 | 2029-04-11 | 2030-04-26 | 2028-03-31 |  |  | 0.11692 | 2.2963 | [5 empty] | 0.033326 | 0.27355 | 0.43567 | 0.86376 | 1.9384 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 0.99823 | 2.3952 | 2.4132 | No | Delivery Mechanism | AMP8
| TMS | Ironsbottom (Sidlow) STW | UBA8.SEW.S38557 | 08TW101021a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-04-21 10:31 | 2028-11-18 11:12 | 2029-01-13 11:12 | 2029-07-09 | 2030-03-31 |  | IM1 | 2024-11-06 | 2027-10-22 | 2028-09-22 | 2029-04-11 | 2030-08-27 | 2029-06-30 |  |  | 0.11692 | 4.58 | [6 empty] | 0.098989 | 3.2715 | 3.9766 | 3.9766 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 0.91749 | 3.9831 | 4.6969 | No | Other | AMP8
| TMS | LITTLE COMPTON STW | UBA8.SEW.S39136 | 08TW101023a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2029-03-29 22:05 | 2029-09-14 13:38 | 2029-11-09 13:38 | 2030-03-02 | 2030-03-31 |  | IM1 | 2024-07-10 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2029-08-29 | 2030-03-31 |  |  | 0.11692 | 3.2333 | [6 empty] | 0.092326 | 1.9525 | 2.9827 | 2.941 | 0 | 0 | 0.11692 | 0.4182 | 1.037 | 2.8726 | 3.3261 | 3.3502 | No | Other | AMP8
| TMS | LITTLE HALLINGBURY STW | UBA8.SEW.S39135 | 08TW101024a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-12-16 07:13 | 2027-09-23 07:27 | 2028-03-28 15:37 | 2029-07-10 | 2030-03-31 |  | IM1 | 2024-06-26 | 2027-04-23 | 2028-02-28 | 2028-09-11 | 2030-01-02 | 2029-06-30 |  |  | 0.11692 | 6.522 |  |  |  |  | 0.11296 | 2.0526 | 3.4955 | 5.875 | 6.5574 | 6.5574 | 0 | 0 | 0.11692 | 0.4182 | 0.72269 | 3.3449 | 6.5622 | 6.6389 | No | Other | AMP8
| TMS | MARKYATE STW | M237 | 08TW101025a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39134 | 2030-03-31 | 2030-03-31 | 2024-07-17 | 2026-07-22 07:31 | 2027-07-21 07:31 | 2028-04-12 07:31 | 2030-11-11 | 2031-03-31 |  | IM1 | 2025-09-30 | 2027-08-19 | 2028-04-04 | 2028-10-13 | 2030-07-02 | 2030-12-31 |  |  | 1.2812 | 16.0043 |  |  |  |  | 0.60043 | 1.8879 | 5.4113 | 9.0256 | 12.7772 | 14.3424 | 0 | 0 | 1.2812 | 3.6057 | 3.8666 | 9.1981 | 17.1655 | 17.2856 | No | Other | AMP8
| TMS | HUCKERS LANE (SELBOURNE) SPS | UBA8.SEW.S40743 | 08TW101030a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-06-24 03:17 | 2028-06-22 03:17 | 2028-09-29 01:34 | 2029-11-14 | 2030-03-31 |  | IM1 | 2024-11-06 | 2027-07-22 | 2028-03-21 | 2029-01-24 | 2030-05-22 | 2029-12-31 |  |  | 0.11692 | 3.5588 | [5 empty] | 0.067154 | 0.86881 | 2.5824 | 3.2967 | 3.2967 | 0 | 0 | 0.11692 | 0.4182 | 0.68427 | 1.3902 | 3.5754 | 3.6757 | No | Other | AMP8
| TMS | SOUTH LEIGH STW | UBA8.SEW.S39127 | 08TW101032a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2028-07-21 05:09 | 2029-03-07 23:12 | 2029-05-04 09:43 | 2029-09-25 | 2030-03-31 |  | IM1 | 2024-06-19 | 2027-05-20 | 2028-03-28 | 2028-10-10 | 2030-07-11 | 2029-09-30 |  |  | 0.11692 | 2.6412 | [6 empty] | 0.045295 | 1.0763 | 2.287 | 2.287 | 0 | 0 | 0.11692 | 0.4182 | 0.68007 | 1.1576 | 2.6188 | 2.7581 | No | Other | AMP8
| TMS | STANDLAKE STW | M233 | 08TW101033a | Storm Overflow - Wetland | PCDWW5b | Retained | UBA8.SEW.S40422 | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2025-12-18 | 2026-12-17 | 2027-09-09 | 2030-09-05 | 2031-03-31 |  | IM1 | 2024-11-06 | 2026-10-19 | 2027-05-05 | 2028-03-06 | 2030-01-31 | 2030-09-30 |  |  | 0.016702 | 4.7692 |  |  |  |  | 0.16904 | 0.85948 | 1.6493 | 2.3558 | 3.0624 | 3.4035 | 0 | 0 | 0.016702 | 0.059743 | 2.2459 | 4.2743 | 4.7732 | 4.7859 | No | Other | AMP8
| TMS | STANDLAKE STW | M233 | 08TW101033a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S40422 | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2025-12-18 | 2026-12-17 | 2027-09-09 | 2030-09-05 | 2031-03-31 |  | IM1 | 2024-11-06 | 2026-10-19 | 2027-05-05 | 2028-03-06 | 2030-01-31 | 2030-09-30 |  |  | 0.10021 | 2.8974 |  |  |  |  | 0.21514 | 1.0939 | 2.0991 | 2.9983 | 3.8976 | 4.3317 | 0 | 0 | 0.10021 | 0.35846 | 1.6891 | 2.734 | 2.9911 | 2.9976 | No | Other | AMP8
| TMS | Stewkley STW | UBA8.SEW.S39124 | 08TW101035a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 22:54 | 2028-11-04 23:14 | 2029-05-15 23:27 | 2030-09-08 | 2031-03-31 |  | IM1 | 2024-06-26 | 2026-11-19 | 2027-11-02 | 2028-05-22 | 2030-08-23 | 2030-09-30 |  |  | 0.11692 | 5.1294 | [6 empty] | 0.19351 | 1.4774 | 3.752 | 5.0252 | 0 | 0 | 0.11692 | 0.4182 | 0.94765 | 2.3613 | 4.8927 | 5.2464 | No | Other | AMP8
| TMS | STONE STW | UBA8.SEW.S39123 | 08TW101036a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-08-19 02:26 | 2028-08-17 02:26 | 2029-05-10 02:26 | 2031-04-19 | 2031-03-31 |  | IM1 | 2024-06-26 | 2027-07-22 | 2028-06-28 | 2029-01-12 | 2030-01-29 | 2031-03-31 |  |  | 0.087687 | 6.023 | [5 empty] | 0.11112 | 0.43036 | 1.6855 | 3.8583 | 6.1619 | 0 | 0 | 0.087687 | 0.31365 | 0.50932 | 1.4178 | 6.0544 | 6.1107 | No | Delivery Mechanism | AMP8
| TMS | STONE STW | UBA8.SEW.S39123 | 08TW101036a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-08-19 02:26 | 2028-08-17 02:26 | 2029-05-10 02:26 | 2031-04-19 | 2031-03-31 |  | IM1 | 2024-06-26 | 2027-07-22 | 2028-06-28 | 2029-01-12 | 2030-01-29 | 2031-03-31 |  |  | 0.029229 | 6.457 | [5 empty] | 0.12531 | 0.4853 | 1.9007 | 4.3508 | 6.9485 | 0 | 0 | 0.029229 | 0.10455 | 0.16977 | 1.1942 | 6.4227 | 6.4862 | No | Delivery Mechanism | AMP8
| TMS | TAKELEY STW | UBA8.SEW.S39122 | 08TW101037a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 05:34 | 2028-11-15 13:30 | 2029-06-03 02:47 | 2030-10-15 | 2031-03-31 |  | IM1 | 2024-06-26 | 2026-12-17 | 2027-11-02 | 2028-05-22 | 2030-06-21 | 2030-09-30 |  |  | 0.11692 | 8.7787 | [6 empty] | 0.42838 | 3.4066 | 6.5679 | 9.0413 | 0 | 0 | 0.11692 | 0.4182 | 1.1623 | 4.0801 | 8.6279 | 8.8957 | No | Other | AMP8
| TMS | THERFIELD STW | UBA8.SEW.S39121 | 08TW101038a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-01-21 00:41 | 2026-10-09 08:19 | 2026-12-13 16:14 | 2027-05-26 | 2028-03-31 |  | IM1 | 2024-06-26 | 2027-07-22 | 2028-06-28 | 2029-01-12 | 2030-04-02 | 2028-06-30 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 6.86 |  |  |  |  | 0.41036 | 5.5552 | 6.9279 | 6.9279 | 6.9279 | 6.9279 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 1.5472 | 6.9031 | 6.9769 | No | Other | AMP8
| TMS | THORNWOOD STW | UBA8.SEW.S39119 | 08TW101040a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2028-03-30 18:20 | 2028-06-26 | 2028-08-21 | 2028-11-20 | 2029-03-31 |  | IM1 | 2024-07-03 | 2026-12-17 | 2027-09-17 | 2028-07-21 | 2029-08-14 | 2028-12-31 |  |  | 0.11692 | 4.4123 | [6 empty] | 0.2924 | 4.2377 | 4.2377 | 4.2377 | 0 | 0 | 0.11692 | 0.4182 | 0.86948 | 3.5258 | 4.5011 | 4.5292 | No | Other | AMP8
| TMS | WADDESDON STW | UBA8.SEW.S39116 | 08TW101043a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2028-01-21 23:06 | 2029-01-19 23:06 | 2029-10-12 23:06 | 2031-09-01 | 2032-03-31 |  | IM1 | 2024-06-19 | 2026-12-17 | 2027-11-02 | 2028-05-22 | 2030-05-23 | 2031-09-30 |  |  | 0.11692 | 5.2417 | [6 empty] | 0.20624 | 2.1825 | 3.0169 | 5.1494 | 0 | 0 | 0.11692 | 0.4182 | 0.95428 | 2.7234 | 5.2479 | 5.3586 | No | Delivery Mechanism | AMP8
| TMS | Weston (Herts) STW | UBA8.SEW.S39115 | 08TW101044a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-10-21 06:36 | 2028-05-15 04:37 | 2028-09-30 03:18 | 2029-09-10 | 2030-03-31 |  | IM1 | 2024-06-19 | 2027-07-23 | 2028-06-28 | 2029-01-12 | 2030-01-29 | 2029-09-30 |  |  | 0.11692 | 3.6519 | [5 empty] | 0.058757 | 0.9706 | 2.2086 | 3.3989 | 3.3989 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 1.1802 | 3.7378 | 3.7689 | No | Other | AMP8
| TMS | WHEATLEY STW | UBA8.SEW.S39114 | 08TW101045a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-01-03 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-09-24 | 2028-04-10 | 2029-05-29 | 2032-12-31 |  |  | 0.11692 | 11.0078 | [6 empty] | 0.36514 | 1.4918 | 3.0773 | 11.5003 | 0 | 0 | 0.11692 | 0.4182 | 1.3683 | 10.5863 | 11.0728 | 11.1248 | No | Delivery Mechanism | AMP8
| TMS | WHITWELL STW | UBA8.SEW.S39113 | 08TW101046a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2027-09-16 12:00 | 2028-04-19 22:48 | 2028-09-11 06:00 | 2029-09-07 | 2030-03-31 |  | IM1 | 2024-07-10 | 2026-12-17 | 2027-11-02 | 2028-05-22 | 2030-06-21 | 2029-09-30 |  |  | 0.11692 | 4.3476 | [5 empty] | 0.07894 | 1.2654 | 3.4796 | 4.1654 | 4.1654 | 0 | 0 | 0.11692 | 0.4182 | 0.9017 | 2.246 | 4.3412 | 4.4645 | No | Other | AMP8
| TMS | Widford and wareside STW | UBA8.SEW.S39112 | 08TW101047a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-02-18 09:29 | 2028-09-03 06:38 | 2029-01-13 04:45 | 2029-12-09 | 2030-03-31 |  | IM1 | 2024-11-06 | 2026-06-09 | 2027-04-29 | 2027-11-09 | 2028-11-23 | 2026-12-31 |  |  | 0.11692 | 3.547 | [6 empty] | 0.11839 | 1.3339 | 3.3261 | 3.3261 | 0 | 0 | 0.11692 | 0.4182 | 1.7629 | 3.6639 | 3.6639 | 3.6639 | No | Other | AMP8
| TMS | WILLINGALE STW | UBA8.SEW.S39111 | 08TW101048a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-01-20 01:25 | 2028-08-01 17:48 | 2028-12-09 12:43 | 2029-10-30 | 2030-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-11-02 | 2028-05-22 | 2030-07-19 | 2029-09-30 |  |  | 0.077944 | 1.8311 | [6 empty] | 0.075914 | 0.85182 | 1.6024 | 1.6024 | 0 | 0 | 0.077944 | 0.2788 | 0.53837 | 1.0247 | 1.8313 | 1.9091 | No | Other | AMP8
| TMS | WILLINGALE STW | UBA8.SEW.S39111 | 08TW101048a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-01-20 01:25 | 2028-08-01 17:48 | 2028-12-09 12:43 | 2029-10-30 | 2030-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-11-02 | 2028-05-22 | 2030-07-19 | 2029-09-30 |  |  | 0.038972 | 3.2821 | [6 empty] | 0.16132 | 1.8101 | 3.4052 | 3.4052 | 0 | 0 | 0.038972 | 0.1394 | 0.40834 | 1.4418 | 3.1558 | 3.3211 | No | Other | AMP8
| TMS | WINGRAVE STW | UBA8.SEW.S39110 | 08TW101049a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2026-07-22 09:20 | 2027-04-12 06:32 | 2027-10-05 04:40 | 2028-12-18 | 2029-03-31 |  | IM1 | 2024-07-03 | 2027-01-21 | 2027-11-24 | 2028-06-14 | 2030-01-08 | 2028-12-31 |  |  | 0.11692 | 4.2197 |  |  |  |  | 0.083494 | 1.6293 | 2.5489 | 4.025 | 4.025 | 4.025 | 0 | 0 | 0.11692 | 0.4182 | 0.86046 | 2.684 | 4.3012 | 4.3366 | No | Other | AMP8
| TMS | BEECH HALL CRESCENT, WALTHAMSTOW CSO | UBA8.SEW.S39109 | 08TW101050a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2026-03-18 01:55 | 2027-03-17 01:55 | 2027-07-03 03:20 | 2028-09-24 | 2029-03-31 |  | IM1 | 2024-08-28 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-09-30 |  |  | 0.11692 | 4.0426 |  |  |  |  | 0.092717 | 1.9365 | 3.0244 | 3.8313 | 3.8313 | 3.8313 | 0 | 0 | 0.11692 | 0.4182 | 0.88035 | 3.6042 | 4.1371 | 4.1596 | No | Other | AMP8
| TMS | SOUTH PARK, ILFORD CSO | UBA8.SEW.S39108 | 08TW101051a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 05:25 | 2028-09-14 05:25 | 2028-12-20 04:44 | 2030-01-27 | 2030-03-31 |  | IM1 | 2024-11-06 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2029-12-31 |  |  | 0.11692 | 4.0957 | [5 empty] | 0.066255 | 0.81627 | 2.7599 | 3.891 | 3.891 | 0 | 0 | 0.11692 | 0.4182 | 1.2582 | 3.6852 | 4.1671 | 4.2126 | No | Other | AMP8
| TMS | RAY LODGE ROAD (RAY PARK 1) CSO | UBA8.SEW.S39107 | 08TW101052a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 01:50 | 2028-09-14 01:50 | 2028-12-16 18:41 | 2030-01-10 | 2030-03-31 |  | IM1 | 2024-11-06 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2029-12-31 |  |  | 0.11692 | 3.915 | [5 empty] | 0.062866 | 0.77365 | 2.6378 | 3.692 | 3.692 | 0 | 0 | 0.11692 | 0.4182 | 1.2286 | 3.5314 | 3.9887 | 4.0319 | No | Other | AMP8
| TMS | Prospect road , woodford CSO (Monkhams Lane) | UBA8.SEW.S39106 | 08TW101053a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2027-03-31 01:27 | 2027-12-06 19:47 | 2028-01-31 19:47 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-11-20 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-06-30 |  |  | 0.11692 | 3.8148 |  |  |  |  | 0.086258 | 1.8509 | 3.0005 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.11692 | 0.4182 | 1.2122 | 3.4462 | 3.8898 | 3.9317 | No | Other | AMP8
| TMS | WORCESTER CRESCENT CSO | UBA8.SEW.S39105 | 08TW101054a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-04-01 | 2027-09-16 22:18 | 2028-09-14 22:18 | 2028-12-15 21:55 | 2030-01-02 | 2030-03-31 |  | IM1 | 2026-01-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2029-12-31 |  |  | 0.11692 | 3.7573 | [5 empty] | 0.060614 | 0.68831 | 2.5576 | 3.5985 | 3.5985 | 0 | 0 | 0.11692 | 0.4182 | 1.2147 | 3.4592 | 3.8742 | 3.8742 | No | Other | AMP8
| TMS | MULBERRY COURT, HALL ROAD CSO | UBA8.SEW.S39103 | 08TW101056a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 05:24 | 2027-12-06 21:21 | 2028-01-31 21:21 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-06-30 |  |  | 0.11692 | 4.0797 |  |  |  |  | 0.093244 | 2.0623 | 3.4252 | 3.8734 | 3.8734 | 3.8734 | 0 | 0 | 0.11692 | 0.4182 | 1.2556 | 3.6715 | 4.1513 | 4.1966 | No | Other | AMP8
| TMS | LONGBRIDGE ROAD CSO | UBA8.SEW.S39102 | 08TW101057a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-03-18 10:37 | 2027-03-17 10:37 | 2027-06-25 11:25 | 2028-08-14 | 2029-03-31 |  | IM1 | 2024-11-20 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-09-30 |  |  | 0.11692 | 3.8148 |  |  |  |  | 0.086482 | 1.8292 | 2.9369 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.11692 | 0.4182 | 1.2122 | 3.4462 | 3.8898 | 3.9317 | No | Other | AMP8
| TMS | HIGH ROAD, WOODFORD CSO | UBA8.SEW.S39101 | 08TW101058a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-05-20 16:38 | 2028-05-18 16:38 | 2028-08-27 06:15 | 2029-10-19 | 2030-03-31 |  | IM1 | 2024-10-23 | 2026-06-16 | 2027-02-22 | 2027-12-20 | 2029-01-18 | 2027-09-30 |  |  | 0.11692 | 4.0051 | [5 empty] | 0.076195 | 1.5268 | 2.8349 | 3.6323 | 3.6323 | 0 | 0 | 0.11692 | 0.44519 | 1.8571 | 4.0568 | 4.1151 | 4.122 | No | Other | AMP8
| TMS | AUCKLAND ROAD STORM TANKS SPS | UBA8.SEW.S39100 | 08TW101059a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2029-03-30 06:36 | 2029-12-05 21:50 | 2030-01-30 21:50 | 2030-07-17 | 2031-03-31 |  | IM1 | 2024-11-20 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2030-06-30 |  |  | 0.11692 | 3.6158 | [6 empty] | 0.080915 | 1.7319 | 2.8266 | 3.3625 | 0 | 0 | 0.11692 | 0.4182 | 1.1795 | 3.2769 | 3.6933 | 3.7327 | No | Other | AMP8
| TMS | BROOK WAY, CHIGWELL CSO | UBA8.SEW.S39099 | 08TW101060a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-05-20 18:38 | 2027-05-19 18:38 | 2027-08-18 19:40 | 2028-08-31 | 2029-03-31 |  | IM1 | 2024-11-20 | 2026-11-19 | 2027-08-17 | 2027-12-08 | 2029-01-08 | 2028-09-30 |  |  | 0.11692 | 3.8127 |  |  |  |  | 0.074995 | 1.5218 | 2.8607 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.11692 | 0.4182 | 1.7824 | 3.8666 | 3.925 | 3.9296 | No | Other | AMP8
| TMS | REDBRIDGE LANE WEST, WANSTEAD CSO | UBA8.SEW.S39098 | 08TW101061a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2026-05-20 13:51 | 2027-05-19 13:51 | 2027-09-01 05:48 | 2028-11-09 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-12-31 |  |  | 0.11692 | 3.7571 |  |  |  |  | 0.073855 | 1.4722 | 2.6663 | 3.5181 | 3.5181 | 3.5181 | 0 | 0 | 0.11692 | 0.4182 | 1.2027 | 3.3971 | 3.8328 | 3.874 | No | Other | AMP8
| TMS | ROAD A3, ROEHAMPTON VALE CSO | UBA8.SEW.S39096 | 08TW101063a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-03-31 18:20 | 2027-06-27 | 2027-08-22 | 2027-11-21 | 2028-03-31 |  | IM1 | 2024-11-06 | 2026-07-23 | 2027-03-23 | 2028-01-26 | 2029-02-16 | 2027-12-31 |  |  | 0.11692 | 4.0927 | [5 empty] | 0.097233 | 3.8893 | 3.8893 | 3.8893 | 3.8893 | 0 | 0 | 0.11692 | 0.42145 | 1.5607 | 4.1363 | 4.1958 | 4.2097 | No | Other | AMP8
| TMS | STREATHAM STORM RELIEF CSO B | UBA8.SEW.S38550 | 08TW101064a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-05-19 06:44 | 2029-05-18 06:44 | 2029-09-02 07:56 | 2030-11-21 | 2031-03-31 |  | IM1 | 2024-11-20 | 2027-02-18 | 2027-10-26 | 2028-08-30 | 2030-05-09 | 2030-12-31 |  |  | 0.11692 | 13.2832 | [6 empty] | 0.31674 | 3.9327 | 8.4706 | 13.9998 | 0 | 0 | 0.11692 | 0.4182 | 1.951 | 5.8302 | 13.0007 | 13.4001 | No | Other | AMP8
| TMS | STREATHAM VALE STORM RELIEF CSO | UBA8.SEW.S38373 | 08TW101065a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-05-20 04:13 | 2028-05-18 04:13 | 2028-10-30 06:16 | 2030-09-16 | 2031-03-31 |  | IM1 | 2024-11-06 | 2027-02-18 | 2027-10-26 | 2028-08-30 | 2029-09-21 | 2030-09-30 |  |  | 0.11692 | 3.7698 | [5 empty] | 0.077138 | 1.2447 | 2.3148 | 3.1005 | 3.5307 | 0 | 0 | 0.11692 | 0.4182 | 0.99987 | 2.7475 | 3.8356 | 3.8867 | No | Other | AMP8
| TMS | CROFTON ROAD, SUNNYDALE CSO | UBA8.SEW.S39093 | 08TW101066a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-02-18 00:53 | 2027-02-17 00:53 | 2027-06-24 02:52 | 2028-12-03 | 2029-03-31 |  | IM1 | 2024-11-20 | 2027-09-23 | 2028-06-21 | 2029-04-24 | 2030-05-17 | 2028-12-31 |  |  | 0.11692 | 3.8181 |  |  |  |  | 0.1112 | 0.86274 | 2.3139 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 1.2851 | 3.783 | 3.935 | No | Other | AMP8
| TMS | OUTSIDE 135 LEESIDE CRESCENT (FORMERLY BROOKSIDE ROAD, GOLDERS GREEN) | UBA8.SEW.S38357 | 08TW101068a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-02-18 01:10 | 2026-10-01 12:09 | 2026-11-26 20:54 | 2027-07-19 | 2028-03-31 |  | IM1 | 2024-11-20 | 2026-12-17 | 2027-09-17 | 2028-07-21 | 2029-08-14 | 2028-06-30 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 5.9183 |  |  |  |  | 0.19638 | 3.9956 | 5.897 | 5.897 | 5.897 | 5.897 | 0 | 0 | 0.11692 | 0.4182 | 1.4297 | 4.7725 | 5.9569 | 6.0352 | No | Other | AMP8
| TMS | HONEYPOT LANE (Winchester Avenue) CSO | UBA8.SEW.S39090 | 08TW101069a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-03-31 03:40 | 2026-05-29 | 2026-07-24 | 2026-10-23 | 2027-03-31 |  | IM1 | 2024-11-20 | 2026-12-17 | 2027-09-17 | 2028-07-21 | 2029-08-14 | 2030-03-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 3.9352 |  |  |  |  | 0.095472 | 3.7137 | 3.7137 | 3.7137 | 3.7137 | 3.7137 | 0 | 0 | 0.11692 | 0.4182 | 1.1518 | 3.2569 | 4.0028 | 4.0521 | No | Other | AMP8
| TMS | DAINTRY CLOSE CSO | UBA8.SEW.S39088 | 08TW101071a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2027-03-31 04:16 | 2027-09-16 06:31 | 2027-11-11 06:31 | 2028-03-03 | 2028-03-31 |  | IM1 | 2024-11-20 | 2027-02-18 | 2027-10-26 | 2028-08-30 | 2029-10-19 | 2028-12-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 3.8083 |  |  |  |  | 0.10941 | 2.3956 | 3.615 | 3.5729 | 3.5729 | 3.5729 | 0 | 0 | 0.11692 | 0.4182 | 1.0037 | 2.6251 | 3.8703 | 3.9252 | No | Other | AMP8
| TMS | ABBESS RODING STW | UBA8.SEW.S39087 | 08TW101072a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-02-18 20:30 | 2028-08-03 16:45 | 2028-11-22 22:15 | 2029-08-28 | 2030-03-31 |  | IM1 | 2024-10-02 | 2028-01-20 | 2028-11-22 | 2029-06-13 | 2030-06-28 | 2029-09-30 |  |  | 0.087687 | 2.9908 | [6 empty] | 0.11634 | 2.0501 | 2.8259 | 2.8259 | 0 | 0 | 0.087687 | 0.31365 | 0.50932 | 0.86618 | 2.7765 | 3.0785 | No | Other | AMP8
| TMS | ABBESS RODING STW | UBA8.SEW.S39087 | 08TW101072a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-02-18 20:30 | 2028-08-03 16:45 | 2028-11-22 22:15 | 2029-08-28 | 2030-03-31 |  | IM1 | 2024-10-02 | 2028-01-20 | 2028-11-22 | 2029-06-13 | 2030-06-28 | 2029-09-30 |  |  | 0.029229 | 2.7097 | [6 empty] | 0.11634 | 2.0501 | 2.8259 | 2.8259 | 0 | 0 | 0.029229 | 0.10455 | 0.16977 | 0.52663 | 2.437 | 2.7389 | No | Other | AMP8
| TMS | HOLYBOURNE SPS | UBA8.SEW.S39209 | 08TW101073a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-03-30 03:40 | 2028-06-17 | 2028-08-12 | 2028-11-11 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-06-01 | 2027-02-22 | 2027-12-20 | 2029-01-18 | 2026-12-31 |  |  | 0.11692 | 3.8022 | [6 empty] | 0.088604 | 3.5697 | 3.5697 | 3.5697 | 0 | 0 | 0.11692 | 0.43801 | 1.6568 | 3.8749 | 3.9144 | 3.9191 | No | Other | AMP8
| TMS | WARDINGTON SPS | UBA8.SEW.S39205 | 08TW101077a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-03-17 17:07 | 2029-02-04 19:58 | 2029-04-26 20:41 | 2030-01-23 | 2030-03-31 |  | IM1 | 2024-11-20 | 2027-04-22 | 2027-12-16 | 2028-10-20 | 2030-10-30 | 2029-12-31 |  |  | 0.11692 | 3.9413 | [6 empty] | 0.096152 | 1.3969 | 3.7172 | 3.7172 | 0 | 0 | 0.11692 | 0.4182 | 0.80919 | 1.5326 | 3.491 | 4.0582 | No | Other | AMP8
| TMS | Rusper Stw | UBA8.SEW.S39204 | 08TW101078a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-03-17 04:01 | 2029-03-16 04:01 | 2029-07-06 06:49 | 2030-10-15 | 2031-03-31 |  | IM1 | 2024-11-20 | 2027-02-18 | 2027-10-26 | 2028-08-30 | 2029-09-21 | 2030-09-30 |  |  | 0.11692 | 3.6812 | [6 empty] | 0.088315 | 1.3391 | 2.5131 | 3.4807 | 0 | 0 | 0.11692 | 0.4182 | 0.91977 | 2.6738 | 3.7981 | 3.7981 | No | Other | AMP8
| TMS | CROPREDY STW | UBA8.SEW.S39203 | 08TW101079a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2028-01-21 02:07 | 2028-10-02 08:41 | 2029-03-21 13:03 | 2030-05-21 | 2031-03-31 |  | IM1 | 2024-07-31 | 2027-01-21 | 2027-11-24 | 2028-06-14 | 2030-07-15 | 2030-06-30 |  |  | 0.11692 | 4.2144 | [6 empty] | 0.15256 | 1.3796 | 3.7636 | 4.0878 | 0 | 0 | 0.11692 | 0.4182 | 1.2237 | 2.375 | 4.202 | 4.3313 | No | Other | AMP8
| TMS | EAST GARSTON SPS | M547 | 08TW101081a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39201 | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2025-12-17 20:14 | 2026-10-30 17:04 | 2027-01-17 22:16 | 2027-10-10 | 2028-03-31 |  | IM1 | 2024-10-23 | 2026-05-27 | 2026-12-03 | 2027-10-08 | 2030-03-08 | 2027-09-30 |  |  | 0.11692 | 3.9414 |  |  |  |  | 0.31101 | 1.7435 | 3.7174 | 3.7174 | 3.7174 | 3.7174 | 0 | 0 | 0.11692 | 0.4182 | 1.9217 | 3.3242 | 4.0268 | 4.0583 | No | Other | AMP8
| TMS | COBHAM BRIDGE, ADJ COBHAM PS CSO | UBA8.SEW.S39200 | 08TW101082a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2026-09-17 01:10 | 2027-04-30 12:09 | 2027-06-25 20:54 | 2028-02-15 | 2028-03-31 |  | IM1 | 2024-10-23 | 2027-01-21 | 2027-09-17 | 2028-07-21 | 2029-09-12 | 2032-03-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 3.6106 |  |  |  |  | 0.06263 | 0.80033 | 3.4142 | 3.4142 | 3.4142 | 3.4142 | 0 | 0 | 0.11692 | 0.4182 | 1.1496 | 2.9105 | 3.7275 | 3.7275 | No | Other | AMP8
| TMS | HAMBLEDEN STW | UBA8.SEW.S39197 | 08TW101084a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-10-20 09:40 | 2029-03-20 04:22 | 2029-06-28 16:50 | 2030-03-07 | 2030-03-31 |  | IM1 | 2024-11-06 | 2026-10-30 | 2027-09-24 | 2028-04-10 | 2029-04-27 | 2026-09-30 |  |  | 0.11692 | 2.8665 | [6 empty] | 0.044646 | 0.66847 | 2.501 | 2.5378 | 0 | 0 | 0.11692 | 0.4182 | 1.0526 | 2.9237 | 2.9708 | 2.9834 | No | Other | AMP8
| TMS | NEWBURY STW | UBA8.SEW.S39196 | 08TW101085a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2027-12-18 | 2028-12-16 | 2029-09-08 | 2032-09-04 | 2033-03-31 |  | IM1 | 2024-07-10 | 2026-11-18 | 2027-09-24 | 2028-04-10 | 2030-05-15 | 2032-09-30 |  |  | 0.11692 | 34.032 | [6 empty] | 1.6279 | 5.9592 | 12.5245 | 36.8261 | 0 | 0 | 0.11692 | 0.4182 | 1.3718 | 15.9771 | 33.2394 | 34.1489 | No | Delivery Mechanism | AMP8
| TMS | WEALDBRIDGE, NORTH WEALD SPS | UBA8.SEW.S39195 | 08TW101086a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-02-18 13:47 | 2028-10-01 00:46 | 2028-11-26 09:30 | 2029-06-03 | 2030-03-31 |  | IM1 | 2024-11-06 | 2027-03-19 | 2027-11-17 | 2028-09-21 | 2029-10-15 | 2029-06-30 |  |  | 0.11692 | 3.5114 | [6 empty] | 0.17139 | 2.6258 | 3.3007 | 3.3007 | 0 | 0 | 0.11692 | 0.4182 | 0.91153 | 2.4212 | 3.6283 | 3.6283 | No | Other | AMP8
| TMS | CASSINGTON STW | UBA8.SEW.S39194 | 08TW101087a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-10-22 18:53 | 2028-10-20 18:53 | 2029-03-08 16:55 | 2030-02-19 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-02 | 2028-05-22 | 2030-01-18 | 2030-03-31 |  |  | 0.087687 | 11.1295 | [6 empty] | 0.72743 | 6.7895 | 11.7819 | 11.7819 | 0 | 0 | 0.087687 | 0.31365 | 0.56864 | 6.1902 | 11.0747 | 11.2172 | No | Other | AMP8
| TMS | CASSINGTON STW | UBA8.SEW.S39194 | 08TW101087a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-10-22 18:53 | 2028-10-20 18:53 | 2029-03-08 16:55 | 2030-02-19 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-02 | 2028-05-22 | 2030-01-18 | 2030-03-31 |  |  | 0.029229 | 14.9275 | [6 empty] | 1.0045 | 9.376 | 16.2702 | 16.2702 | 0 | 0 | 0.029229 | 0.10455 | 0.25168 | 8.0147 | 14.76 | 14.9568 | No | Other | AMP8
| TMS | Selborne STW | UBA8.SEW.S39192 | 08TW101089a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2026-06-24 02:51 | 2026-12-05 11:36 | 2027-03-25 01:26 | 2027-12-24 | 2028-03-31 |  | IM1 | 2024-06-19 | 2027-07-22 | 2028-06-28 | 2029-01-12 | 2030-05-02 | 2028-12-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 2.8039 |  |  |  |  | 0.049954 | 0.71292 | 2.4661 | 2.4661 | 2.4661 | 2.4661 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 1.1769 | 2.8643 | 2.9208 | No | Other | AMP8
| TMS | SEVENHAMPTON VILLAGE STW | M527 | 08TW101090a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S39191 | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2026-03-18 14:10 | 2026-11-25 13:01 | 2027-01-27 12:43 | 2027-07-04 | 2028-03-31 |  | IM1 | 2024-10-02 | 2027-07-15 | 2028-04-13 | 2028-10-24 | 2030-02-18 | 2032-06-30 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 3.9821 |  |  |  |  | 0.11367 | 2.562 | 3.55 | 3.55 | 3.55 | 3.55 | 0 | 0 | 0.11692 | 1.4499 | 1.9169 | 3.0997 | 4.0834 | 4.099 | No | Other | AMP8
| TMS | HADHAM MILL SPS | UBA8.SEW.S39190 | 08TW101091a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-05-20 | 2028-07-15 | 2028-09-09 | 2028-12-09 | 2029-03-31 |  | IM1 | 2024-11-06 | 2026-07-10 | 2027-03-23 | 2028-01-26 | 2029-02-16 | 2028-03-31 |  |  | 0.11692 | 3.5144 | [6 empty] | 0.075927 | 3.3072 | 3.3072 | 3.3072 | 0 | 0 | 0.11692 | 0.42108 | 1.4521 | 3.6313 | 3.6313 | 3.6313 | No | Other | AMP8
| TMS | WINTERBOURNE STW | UBA8.SEW.S39189 | 08TW101092a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-09-16 13:03 | 2027-06-26 10:53 | 2027-09-05 04:21 | 2028-02-29 | 2028-03-31 |  | IM1 | 2024-07-31 | 2026-05-01 | 2027-04-01 | 2027-10-12 | 2028-10-26 | 2028-03-31 |  |  | 0.11692 | 1.9139 |  |  |  |  | 0.026316 | 0.38243 | 1.5053 | 1.5053 | 1.5053 | 1.5053 | 0 | 0 | 0.11692 | 0.4182 | 1.3239 | 2.0308 | 2.0308 | 2.0308 | No | Other | AMP8
| TMS | STREATHAM STORM RELIEF CSO A | UBA8.SEW.S38550 | 08TW101096a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-05-19 06:44 | 2029-05-18 06:44 | 2029-09-02 07:56 | 2030-11-21 | 2031-03-31 |  | IM1 | 2024-11-20 | 2027-02-18 | 2027-10-26 | 2028-08-30 | 2030-05-09 | 2030-12-31 |  |  | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | STREATHAM STORM RELIEF CSO E | UBA8.SEW.S38372 | 08TW101097a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-05-20 10:57 | 2026-12-01 11:28 | 2027-01-26 11:28 | 2027-08-17 | 2028-03-31 |  | IM1 | 2024-11-20 | 2027-02-18 | 2027-10-26 | 2028-08-30 | 2030-05-09 | 2030-03-31 |  | Programme efficiency - this site moved back to accommodate complexity, but balanced out with other sites moved forward | 0.11692 | 4.5532 |  |  |  |  | 0.10147 | 2.6984 | 4.3922 | 4.3922 | 4.3922 | 4.3922 | 0 | 0 | 0.11692 | 0.4182 | 1.0781 | 2.2951 | 4.5448 | 4.6701 | No | Other | AMP8
| TMS | ALICIA AVENUE CSO | UBA8.SEW.S39182 | 08TW101099a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2029-03-29 04:16 | 2029-09-14 06:31 | 2029-11-09 06:31 | 2030-03-02 | 2030-03-31 |  | IM1 | 2024-10-02 | 2027-02-18 | 2027-10-26 | 2028-08-30 | 2029-09-21 | 2030-03-31 |  |  | 0.11692 | 3.7481 | [6 empty] | 0.081922 | 2.2197 | 3.5483 | 3.5069 | 0 | 0 | 0.11692 | 0.4182 | 1.0099 | 2.7537 | 3.8272 | 3.865 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101100a | UBA8.SEW.S39181 | 08TW101100a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:07 | 2027-12-06 21:39 | 2028-01-31 21:39 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-06-30 |  |  | 0.11692 | 3.8349 |  |  |  |  | 0.1583 | 1.9918 | 3.2285 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.11692 | 0.4182 | 1.2075 | 3.5229 | 3.9518 | 3.9518 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101101a | UBA8.SEW.S39180 | 08TW101101a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 04:11 | 2027-12-06 20:53 | 2028-01-31 20:53 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-06-30 |  |  | 0.11692 | 3.8349 |  |  |  |  | 0.15831 | 1.9909 | 3.2262 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.11692 | 0.4182 | 1.2075 | 3.5229 | 3.9518 | 3.9518 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101102a | UBA8.SEW.S39179 | 08TW101102a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:22 | 2027-12-06 21:45 | 2028-01-31 21:45 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-10-19 | 2027-07-20 | 2028-05-23 | 2029-06-15 | 2028-06-30 |  |  | 0.11692 | 3.8345 |  |  |  |  | 0.1583 | 1.9918 | 3.2285 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.11692 | 0.4182 | 1.2541 | 3.731 | 3.9514 | 3.9514 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101103a | UBA8.SEW.S39178 | 08TW101103a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 00:19 | 2027-12-06 19:20 | 2028-01-31 19:20 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2027-06-30 |  |  | 0.11692 | 3.8349 |  |  |  |  | 0.15851 | 1.9845 | 3.2102 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.11692 | 0.4182 | 1.2075 | 3.5229 | 3.9518 | 3.9518 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101104a | UBA8.SEW.S39176 | 08TW101104a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 00:19 | 2027-12-06 19:20 | 2028-01-31 19:20 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-10-19 | 2027-07-20 | 2028-05-23 | 2029-06-15 | 2028-06-30 |  |  | 0.11692 | 3.8345 |  |  |  |  | 0.15851 | 1.9845 | 3.2102 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.11692 | 0.4182 | 1.2541 | 3.731 | 3.9514 | 3.9514 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101105a | UBA8.SEW.S39175 | 08TW101105a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:27 | 2027-12-06 21:47 | 2028-01-31 21:47 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2027-06-30 |  |  | 0.11692 | 3.8349 |  |  |  |  | 0.1583 | 1.9917 | 3.2282 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.11692 | 0.4182 | 1.2075 | 3.5229 | 3.9518 | 3.9518 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101106a | UBA8.SEW.S39174 | 08TW101106a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 05:43 | 2027-12-06 21:29 | 2028-01-31 21:29 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-06-30 |  |  | 0.11692 | 3.8349 |  |  |  |  | 0.15833 | 1.9888 | 3.2214 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.11692 | 0.4182 | 1.2075 | 3.5229 | 3.9518 | 3.9518 | No | Other | AMP8
| TMS | CHIGWELL ROAD, WOODFORD GREEN 08TW101107a | UBA8.SEW.S39173 | 08TW101107a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:27 | 2027-12-06 21:47 | 2028-01-31 21:47 | 2028-07-17 | 2029-03-31 |  | IM1 | 2024-10-02 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2028-06-30 |  |  | 0.11692 | 3.719 |  |  |  |  | 0.15279 | 1.922 | 3.1151 | 3.5342 | 3.5342 | 3.5342 | 0 | 0 | 0.11692 | 0.4182 | 1.2187 | 3.4277 | 3.8359 | 3.8359 | No | Other | AMP8
| TMS | Burstow STW | UBA8.SEW.S38363 | 08TW101113a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  | IM1 | 2024-10-16 | 2027-07-23 | 2028-06-28 | 2029-01-12 | 2030-03-26 | 2032-12-31 |  |  | 0.058458 | 16.077 | [6 empty] | 0.56143 | 3.3005 | 7.8492 | 17.3764 | 0 | 0 | 0.058458 | 0.2091 | 0.33955 | 2.5477 | 15.9613 | 16.1355 | No | Delivery Mechanism | AMP8
| TMS | Burstow STW | UBA8.SEW.S38363 | 08TW101113a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  | IM1 | 2024-10-16 | 2027-07-23 | 2028-06-28 | 2029-01-12 | 2030-03-26 | 2032-12-31 |  |  | 0.058458 | 9.5581 | [6 empty] | 0.32973 | 1.9384 | 4.6099 | 10.2052 | 0 | 0 | 0.058458 | 0.2091 | 0.33955 | 1.6364 | 9.5143 | 9.6165 | No | Delivery Mechanism | AMP8
| TMS | Arborfield STW Cypermethrin - IMP & ND | UBA8.SEW.S40667 | 08TW101448a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2028-12-22 | 2030-02-14 | 2030-08-17 | 2032-11-15 | 2034-03-31 |  | IM1 | 2024-10-16 | 2027-04-23 | 2028-05-05 | 2029-04-06 | 2030-11-22 | 2034-03-31 |  |  | 0 | 17.6053 | [5 empty] | 0.029304 | 2.8237 | 4.9386 | 12.6782 | 18.3279 | 0 | 0 | 0 | 0 | 2.7096 | 4.7743 | 11.5404 | 17.6053 | No | Delivery Mechanism | AMP8
| TMS | Bracknell STW AMP8 Low P BOD and Chem | L842 | 08TW101449a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2033-03-31 | 2033-03-31 |  | IM2 | 2024-09-18 | 2025-06-19 | 2026-12-02 | 2027-04-22 | 2033-12-20 | 2033-03-31 |  |  | 4.8899 | 39.6973 |  |  |  |  | 1.3276 | 12.3272 | 20.9423 | 27.6926 | 32.279 | 46.2197 | 0 | 0 | 4.8899 | 8.1766 | 10.4891 | 20.6758 | 30.2285 | 44.5871 | Yes | Delivery Mechanism | AMP8
| TMS | Middleton Cheney STW WINEP8 Cypermethrin | M097 | 08TW101452a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained | UBA8.SEW.S40580 | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2025-12-07 | 2027-02-22 | 2027-08-12 | 2029-11-19 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-06-18 | 2027-04-30 | 2027-09-10 | 2030-06-19 | 2031-03-31 |  |  | 0.10936 | 10.1346 | [5 empty] | 0.58544 | 1.6509 | 3.0127 | 7.5539 | 10.2528 | 0 | 0 | 0.10936 | 1.2491 | 3.148 | 6.8535 | 9.7202 | 10.244 | No | Delivery Mechanism | AMP8
| TMS | Purton STW - 08TW101887a | M288 | 08TW101887a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38928 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-02-21 | 2027-02-03 | 2027-08-21 | 2028-12-08 | 2030-03-31 |  | IM1 | 2024-10-16 | 2027-03-18 | 2028-01-19 | 2028-07-14 | 2029-03-22 | 2030-03-31 |  |  | 0.1252 | 8.2258 | [5 empty] | 0.56977 | 1.9668 | 4.6599 | 8.1514 | 8.3111 | 0 | 0 | 0.1252 | 0.32785 | 1.1403 | 8.1864 | 8.351 | 8.351 | No | Other | AMP8
| TMS | Earlswood STW - 08TW101888a | M240 | 08TW101888a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39022 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2026-02-10 | 2026-08-21 | 2029-12-21 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-11-19 | 2027-10-27 | 2028-05-12 | 2029-08-31 | 2031-03-31 |  |  | 0 | 19.7454 | [5 empty] | 1.2237 | 3.2767 | 8.2045 | 19.5712 | 20.1284 | 0 | 0 | 0 | 0.97913 | 3.8421 | 16.0134 | 19.5577 | 19.7454 | No | Other | AMP8
| TMS | Thame STW - 08TW101889a | M247 | 08TW101889a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38933 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-01 | 2029-02-09 | 2029-08-22 | 2030-12-07 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-10-12 | 2028-04-26 | 2029-08-15 | 2032-03-31 |  |  | 0.12064 | 9.0676 | [6 empty] | 0.31412 | 1.1408 | 2.7305 | 7.585 | 0 | 0 | 0.12064 | 0.53747 | 2.4134 | 7.7792 | 9.0617 | 9.1882 | No | Delivery Mechanism | AMP8
| TMS | Bracknell STW - 09TW100015a, Bracknell STW - 08TW100878a | L842 | 09TW100015a/08TW100878a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  | IM2 | 2024-09-18 | 2025-06-19 | 2026-12-02 | 2027-04-22 | 2033-12-20 | 2033-03-31 |  |  | 2.8361 | 23.0244 |  |  |  |  | 0.77 | 7.1498 | 12.1465 | 16.0617 | 18.7218 | 26.8074 | 0 | 0 | 2.8361 | 4.7424 | 6.0837 | 11.992 | 17.5325 | 25.8605 | Yes | Delivery Mechanism | AMP8
| TMS | Basingstoke STW - 09TW100022a | M373 | 09TW100022a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38948 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-04-04 | 2030-02-22 | 2030-08-21 | 2032-11-24 | 2034-03-31 |  | IM1 | 2024-10-16 | 2026-07-16 | 2027-10-12 | 2028-05-11 | 2030-01-28 | 2034-03-31 |  |  | 0 | 23.5602 | [8 empty] | 0.9394 | 21.547 | 0 | 0 | 0 | 1.0717 | 6.2 | 15.5638 | 23.0927 | 23.5602 | No | Delivery Mechanism | AMP8
| TMS | Berkhamsted STW - 09TW100023a | M465 | 09TW100023a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38965 | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2029-08-29 | 2030-09-13 | 2031-03-15 | 2032-11-20 | 2034-03-31 |  | IM1 | 2024-11-20 | 2027-04-15 | 2028-01-26 | 2028-08-04 | 2030-03-22 | 2034-03-31 |  |  | 0 | 9.6185 | [8 empty] | 0.36165 | 8.794 | 0 | 0 | 0 | 0.12114 | 1.29 | 5.0054 | 9.4274 | 9.6185 | No | Delivery Mechanism | AMP8
| TMS | Broughton STW - 09TW100025a | M481 | 09TW100025a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39728 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-06 | 2026-06-19 | 2027-01-17 | 2028-11-17 | 2030-03-31 |  | IM1 | 2024-10-16 | 2027-05-20 | 2028-03-07 | 2028-09-15 | 2030-01-10 | 2030-03-31 |  |  | 0.039118 | 2.0674 | [5 empty] | 0.12486 | 0.39854 | 0.96866 | 2.0318 | 2.094 | 0 | 0 | 0.039118 | 0.098456 | 0.26478 | 1.0806 | 2.1065 | 2.1065 | No | Other | AMP8
| TMS | Chobham STW - 09TW100028a | L892 | 09TW100028a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-10-16 | 2027-07-13 | 2027-11-09 | 2028-01-03 | 2028-12-06 | 2030-03-31 |  | IM6 | 2024-10-16 | 2025-04-17 | 2025-08-14 | 2025-10-08 | 2026-09-11 | 2026-03-31 |  |  | 3.4806 | 5.6636 |  |  |  |  | 2.0993 | 3.8445 | 6.2809 | 8.199 | 8.6432 | 8.7181 | 0 | 0 | 3.4806 | 9.1442 | 9.1442 | 9.1442 | 9.1442 | 9.1442 | No | Other | AMP8
| TMS | Cropredy STW - 09TW100031a | M285 | 09TW100031a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39726 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-08-10 | 2028-02-22 | 2029-06-14 | 2030-03-31 |  |  | 0.083521 | 5.5667 |  |  |  |  | 0.34588 | 1.2303 | 2.8699 | 5.6097 | 5.7259 | 5.7683 | 0 | 0 | 0.083521 | 0.70477 | 1.5856 | 5.3032 | 5.5929 | 5.6502 | No | Other | AMP8
| TMS | Mill Green STW - 09TW100035a | M238 | 09TW100035a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39011 | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  | IM1 | 2024-11-20 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2032-03-31 |  |  | 0.13249 | 12.5712 | [6 empty] | 0.39749 | 1.3859 | 3.1759 | 9.6653 | 0 | 0 | 0.13249 | 0.72903 | 2.2263 | 8.8777 | 12.1471 | 12.7037 | No | Delivery Mechanism | AMP8
| TMS | Kings Sutton STW - 09TW100038a | M284 | 09TW100038a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38906 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-14 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2027-08-10 | 2028-02-22 | 2029-06-14 | 2032-03-31 |  |  | 0.066353 | 6.6041 | [6 empty] | 0.22333 | 0.85847 | 1.6109 | 6.441 | 0 | 0 | 0.066353 | 0.71116 | 1.8113 | 6.1674 | 6.5552 | 6.6704 | No | Delivery Mechanism | AMP8
| TMS | Little Marlow STW - 09TW100040a | M245 | 09TW100040a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39715 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-31 | 2028-02-07 | 2028-08-15 | 2029-12-10 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2031-03-31 |  |  | 0.11167 | 33.9817 | [5 empty] | 0.29237 | 4.6838 | 9.3578 | 24.9203 | 31.4694 | 0 | 0 | 0.11167 | 3.0043 | 8.0963 | 24.1444 | 33.7157 | 34.0933 | No | Other | AMP8
| TMS | High Wycombe STW - 08TW101485a | M245 | 08TW101485a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39715 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-31 | 2028-02-07 | 2028-08-15 | 2029-12-10 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-12-17 | 2027-11-29 | 2028-06-15 | 2029-10-03 | 2030-03-31 |  |  | 0 | 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | Rye Meads STW - 09TW100046a | M109 | 09TW100046a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39010 | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-02-19 | 2027-07-07 | 2028-12-18 | 2032-03-09 | 2033-03-31 |  | IM1 | 2024-11-20 | 2026-08-20 | 2028-01-19 | 2029-02-07 | 2032-09-21 | 2033-03-31 |  |  | 1.1745 | 174.4072 | [6 empty] | 6.1936 | 17.703 | 32.399 | 109.1367 | 0 | 0 | 1.1745 | 4.3813 | 8.5658 | 29.3488 | 39.6648 | 175.5817 | Yes | Enhanced engagement | AMP8
| TMS | Wantage STW - 09TW100048a | M182 | 09TW100048a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38997 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-08-29 | 2027-02-20 | 2027-08-14 | 2029-11-19 | 2031-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-05-09 | 2028-12-12 | 2031-03-26 | 2031-03-31 |  |  | 0.15802 | 12.2097 | [5 empty] | 0.44898 | 0.8626 | 2.3109 | 9.481 | 12.779 | 0 | 0 | 0.15802 | 0.40523 | 0.9435 | 3.5891 | 11.5758 | 12.3677 | No | Delivery Mechanism | AMP8
| TMS | Weybridge STW - 09TW100049a | M118 | 09TW100049a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38921 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-06 | 2026-05-22 | 2026-12-07 | 2028-11-17 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-10-22 | 2028-02-07 | 2028-08-16 | 2030-01-04 | 2030-03-31 |  |  | 0.12908 | 32.1901 |  |  |  |  | 0.62101 | 2.2089 | 5.1528 | 10.072 | 10.2805 | 10.3566 | 0 | 0 | 0.12908 | 0.9552 | 5.5386 | 18.6067 | 31.6878 | 32.3192 | No | Other | AMP8
| TMS | Horley (Oxon) STW - 09TW100052a | M295 | 09TW100052a | P-removal | PCDWW10 | Retained | UBA8.SEW.S39840 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-12-06 | 2028-06-28 | 2029-01-19 | 2030-12-11 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-04-15 | 2028-01-24 | 2028-07-19 | 2029-05-03 | 2032-03-31 |  |  | 0.046516 | 3.6781 | [6 empty] | 0.031427 | 0.52137 | 1.2291 | 3.3904 | 0 | 0 | 0.046516 | 0.20166 | 0.59005 | 3.6426 | 3.7246 | 3.7246 | No | Delivery Mechanism | AMP8
| TMS | SNAKES LANE CSO | UBA8.SEW.S41337 | 09TW100081a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 00:49 | 2028-09-14 00:49 | 2028-12-16 22:30 | 2030-01-11 | 2030-03-31 |  | IM1 | 2024-11-06 | 2027-08-19 | 2028-03-27 | 2029-01-30 | 2030-05-14 | 2029-12-31 |  |  | 0 | 0 | [5 empty] | 0.066186 | 0.81457 | 2.7758 | 3.887 | 3.887 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | No | Other | AMP8
| TMS | Stratfield Mortimer STW - 09TW100180a | M290 | 09TW100180a | P-removal | PCDWW10 | Retained | UBA8.SEW.S40733 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  | IM1 | 2024-10-16 | 2026-07-16 | 2027-01-28 | 2027-06-14 | 2028-09-08 | 2030-03-31 |  |  | 0.048833 | 6.7712 | [5 empty] | 0.58213 | 1.6645 | 4.0845 | 6.6593 | 6.75 | 0 | 0 | 0.048833 | 0.98127 | 5.3447 | 6.7263 | 6.8201 | 6.8201 | No | Other | AMP8
| TMS | HOLMWOOD STW | UBA8.SEW.S41562 | 10TW100024a | Storm overflows | PCDWW5 | Retained |  | 2028-03-31 | 2028-03-31 | 2024-06-19 | 2026-04-23 | 2027-04-22 | 2028-01-13 | 2031-01-09 | 2031-03-31 |  | IM1 | 2024-06-19 | 2027-01-21 | 2027-11-24 | 2028-06-14 | 2029-07-30 | 2030-12-31 |  |  | 0.093532 | 8.9527 |  |  |  |  | 0.3116 | 1.5004 | 3.1828 | 5.6947 | 8.2066 | 9.3582 | 0 | 0 | 0.093532 | 0.33456 | 0.58445 | 7.3644 | 8.9669 | 9.0463 | No | Other | AMP8
| TMS | HOLMWOOD STW | UBA8.SEW.S41562 | 10TW100024a | Flow to Full Treatment | PCDWW4 | Retained |  | 2028-03-31 | 2028-03-31 | 2024-06-19 | 2026-04-23 | 2027-04-22 | 2028-01-13 | 2031-01-09 | 2031-03-31 |  | IM1 | 2024-06-19 | 2027-01-21 | 2027-11-24 | 2028-06-14 | 2029-07-30 | 2030-12-31 |  |  | 0.023383 | 8.6154 |  |  |  |  | 0.3116 | 1.5004 | 3.1828 | 5.6947 | 8.2066 | 9.3582 | 0 | 0 | 0.023383 | 0.083641 | 0.17699 | 6.957 | 8.5595 | 8.6388 | No | Other | AMP8
| TMS | LEATHERHEAD STW | UBA8.SEW.S42167 | 10TW100025a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-12-17 22:39 | 2028-07-23 15:52 | 2028-12-16 11:20 | 2029-12-16 | 2030-03-31 |  | IM1 | 2024-06-26 | 2027-02-18 | 2027-12-23 | 2028-07-13 | 2030-04-10 | 2029-12-31 |  |  | 0.11692 | 12.1862 | [6 empty] | 1.3804 | 6.784 | 12.7891 | 12.7891 | 0 | 0 | 0.11692 | 0.4182 | 0.90234 | 5.2042 | 12.0768 | 12.3031 | No | Other | AMP8
| TMS | NORTH WEALD STW | UBA8.SEW.S40742 | 10TW100031a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-01-21 10:12 | 2027-01-20 10:12 | 2027-10-13 10:12 | 2030-02-01 | 2030-03-31 |  | IM1 | 2024-06-26 | 2026-12-17 | 2027-11-02 | 2028-05-22 | 2029-06-07 | 2030-03-31 |  |  | 0.11692 | 8.8083 |  |  |  |  | 0.33967 | 1.4904 | 3.0883 | 6.2681 | 9.0774 | 9.0774 | 0 | 0 | 0.11692 | 0.4182 | 0.94512 | 8.2494 | 8.8617 | 8.9252 | No | Other | AMP8
| TMS | Bampton STW | M581 | 11TW100004a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S40740 | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-11-20 | 2028-11-18 | 2029-08-11 | 2032-08-07 | 2033-03-31 |  | IM1 | 2024-06-19 | 2026-05-26 | 2026-12-03 | 2027-10-08 | 2030-07-18 | 2032-09-30 |  |  | 0.093532 | 9.5473 | [6 empty] | 0.32075 | 1.2773 | 2.3208 | 5.4409 | 0 | 0 | 0.093532 | 0.33456 | 5.1052 | 7.9415 | 9.5301 | 9.6408 | No | Delivery Mechanism | AMP8
| TMS | Bampton STW | M581 | 11TW100004a | Flow to Full Treatment | PCDWW4 | Retained | UBA8.SEW.S40740 | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-11-20 | 2028-11-18 | 2029-08-11 | 2032-08-07 | 2033-03-31 |  | IM1 | 2024-06-19 | 2026-05-26 | 2026-12-03 | 2027-10-08 | 2030-07-18 | 2032-09-30 |  |  | 0.023383 | 3.2588 | [6 empty] | 0.46157 | 1.8381 | 3.3397 | 7.8295 | 0 | 0 | 0.023383 | 0.083641 | 0.30957 | 0.97684 | 3.1229 | 3.2822 | No | Delivery Mechanism | AMP8
| TMS | Benson STW | M236 | 11TW100007a | Storm overflows | PCDWW5 | Retained | UBA8.SEW.S41609 | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2025-09-17 10:55 | 2026-09-16 10:55 | 2027-06-09 10:55 | 2030-05-21 | 2031-03-31 |  | IM1 | 2025-01-07 | 2026-07-16 | 2027-09-03 | 2027-09-17 | 2029-11-01 | 2030-06-30 |  |  | 0.56391 | 16.4111 |  |  |  |  | 1.1475 | 3.2708 | 7.9742 | 12.738 | 16.5939 | 17.2315 | 0 | 0 | 0.56391 | 1.0821 | 8.7213 | 16.8403 | 16.963 | 16.975 | No | Other | AMP8
| TMS | Benson STW | M236 | 11TW100007a | Flow to Full Treatment | PCDWW4 | Retained | UBA8.SEW.S41609 | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2025-09-17 10:55 | 2026-09-16 10:55 | 2027-06-09 10:55 | 2030-05-21 | 2031-03-31 |  | IM1 | 2025-01-07 | 2026-07-16 | 2027-09-03 | 2027-09-17 | 2029-11-01 | 2030-06-30 |  |  | 0.31168 | 9.8952 |  |  |  |  | 0.70329 | 2.0047 | 4.8874 | 7.8072 | 10.1705 | 10.5612 | 0 | 0 | 0.31168 | 0.5418 | 5.1481 | 10.1243 | 10.1995 | 10.2069 | No | Other | AMP8
| TMS | BARKWAY STW | UBA8.SEW.S39214 | 11TW100011a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-12-17 12:34 | 2028-06-03 13:36 | 2028-09-24 06:17 | 2029-07-03 | 2030-03-31 |  | IM1 | 2024-06-26 | 2027-09-23 | 2028-08-22 | 2029-03-08 | 2030-04-24 | 2029-06-30 |  |  | 0.11692 | 2.138 | [6 empty] | 0.10884 | 1.3675 | 1.7336 | 1.7336 | 0 | 0 | 0.11692 | 0.4182 | 0.6791 | 0.98346 | 2.2167 | 2.2549 | No | Other | AMP8
| TMS | FARNHAM STW | UBA8.SEW.S41575 | 11TW100035a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-06-24 | 2029-06-23 | 2030-03-16 | 2033-03-12 | 2033-03-31 |  | IM1 | 2024-10-16 | 2027-03-22 | 2027-10-27 | 2028-05-31 | 2030-04-03 | 2033-03-31 |  |  | 0.11692 | 3.9405 | [6 empty] | 0.079275 | 0.48271 | 1.0172 | 3.7181 | 0 | 0 | 0.11692 | 0.4182 | 1.0018 | 2.3095 | 4.0064 | 4.0574 | No | Other | AMP8
| TMS | Constable's Piece (Beckley) STW | UBA8.SEW.S41499 | 11TW100087a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-04-21 12:27 | 2028-11-09 06:19 | 2029-03-23 18:14 | 2030-02-23 | 2030-03-31 |  | IM1 | 2024-10-23 | 2026-12-15 | 2027-11-02 | 2028-05-22 | 2029-06-07 | 2027-09-30 |  |  | 0.11692 | 3.7124 | [6 empty] | 0.082488 | 0.90461 | 3.4692 | 3.4692 | 0 | 0 | 0.11692 | 0.4182 | 1.1998 | 3.6044 | 3.8052 | 3.8293 | No | Other | AMP8
| TMS | NEW STORM TANKS AT CASCADE ROAD | UBA8.SEW.S41156 | 11TW100190a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 17:45 | 2028-09-13 13:01 | 2028-12-13 05:50 | 2029-12-25 | 2030-03-31 |  | IM1 | 2024-11-06 | 2026-11-19 | 2027-08-17 | 2028-06-21 | 2029-07-13 | 2029-12-31 |  |  | 0.11692 | 4.6279 | [5 empty] | 0.07698 | 1.0127 | 3.247 | 4.4763 | 4.4763 | 0 | 0 | 0.11692 | 0.4182 | 1.1362 | 4.1309 | 4.7143 | 4.7448 | No | Other | AMP8
| TMS | LITTLE MILTON STW | UBA8.SEW.S41490 | 12TW100070a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2026-07-22 08:11 | 2027-02-14 20:08 | 2027-07-03 04:06 | 2028-06-13 | 2029-03-31 |  | IM1 | 2024-10-16 | 2026-10-30 | 2027-09-24 | 2028-04-10 | 2029-04-27 | 2028-06-30 |  |  | 0.11692 | 3.7809 |  |  |  |  | 0.071288 | 0.89696 | 3.215 | 3.5446 | 3.5446 | 3.5446 | 0 | 0 | 0.11692 | 0.4182 | 1.1257 | 3.8174 | 3.8818 | 3.8978 | No | Other | AMP8
| TMS | Tiddington STW - 08TW100940a | M305 | 08TW100940a | P-removal | PCDWW10 | Retained | UBA8.SEW.S38986 | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  | IM1 | 2024-10-16 | 2027-02-18 | 2028-01-05 | 2028-07-14 | 2029-11-01 | 2032-03-31 |  |  | 0.10708 | 3.8212 | [6 empty] | 0.15007 | 0.545 | 1.3045 | 3.6237 | 0 | 0 | 0.10708 | 0.43136 | 0.84478 | 2.6955 | 3.8788 | 3.9283 | No | Delivery Mechanism | AMP8

## DPWW5
DPWW5
Scheme-level data - Wastewater - Growth at Sewage Treatment Works Schemes (excluding any critical high-profile projects)
| Company | Scheme name | Scheme ID | EA ID | Type of scheme (retained/dropped/added) | Name of the substituted scheme | Original regulatory date | Current regulatory date | Interim milestone completion dates - Baseline | [6 empty] | Current interim milestone | Interim milestone completion dates - Forecast | [6 empty] | Primary reson for delay where IM date moves more than 90 days later than baseline | Spend to date (£m) - cumulative | Forecast expenditure to complete scheme (£m) - cumulative | Forecast outturn cost (£m) | % Spend to date | Baseline expenditure profile (£m) - cumulative | [7 empty] | Forecast expenditure profile (£m) - cumulative | [7 empty] | AMP
[29 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9
[9 empty] | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 |  | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 | [5 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!
[27 empty] | 0 | #DIV/0!

## DPW1
DPW1 | [43 empty] | Ofwat Bon Numbers
Enhancement - PCD Output - Water - Programme Level
Header | Company | PCD Model | PCD Ref | PCD Applicable? Y/N | Line Description | PCD Output Description | Units | DPs | PCD Output (Cumulative) - Target | [11 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD Output (Cumulative) - Outturn & Forecast | [11 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP Reference |  |  | PCD Output (Cumulative) - Target | [11 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | PCD Output (Cumulative) - Outturn & Forecast | [11 empty] | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Performance (Output)
[9 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  |  |  | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Outturn & Forecast by 2029-30 |  | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | PCD Output Outturn & Forecast by 2034-35
Start_Data | [8 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [8 empty] | Start_BON | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation hectares | Hectares of environmental improvement | ha | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.1 |  |  | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1_T | PCD_DPW1_BIOCON1_T | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_OT | PCD_DPW1_BIOCON1_OT | PCD_DPW1_BIOCON1_P | PCD_DPW1_BIOCON1_P
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation kilometres | Kilometres of environmental improvement | km | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.2 |  |  | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2_T | PCD_DPW1_BIOCON2_T | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_OT | PCD_DPW1_BIOCON2_OT | PCD_DPW1_BIOCON2_P | PCD_DPW1_BIOCON2_P
| TMS | PR24CA106 Water WINEP | PCDW4 | 0 | Drinking Water Protected Areas | No Deterioration and Implementation actions | Nr | 0 | [12 empty] | 0 | 0 | [18 empty] | DPW1.3 |  |  | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA_T | PCD_DPW1_DWPA_T | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_OT | PCD_DPW1_DWPA_OT | PCD_DPW1_DWPA_P | PCD_DPW1_DWPA_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive interconnector | Length of WFD interconnector | km | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | [6 empty] | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 100% | 100% | Amber | Amber | DPW1.4 |  |  | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI_T | PCD_DPW1_WFDI_T | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_OT | PCD_DPW1_WFDI_OT | PCD_DPW1_WFDI_P | PCD_DPW1_WFDI_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive actions | Other WFD actions | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | [6 empty] | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 100% | 100% | Green | Green | DPW1.5 |  |  | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA_T | PCD_DPW1_WFDA_T | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_OT | PCD_DPW1_WFDA_OT | PCD_DPW1_WFDA_P | PCD_DPW1_WFDA_P
| TMS | PR24CA106 Water WINEP | PCDW8 | Y | Water WINEP/NEP Investigations | Water WINEP/NEP Investigations | Nr | 0 |  |  | 0 | 0 | 37 | 37 | 37 | [5 empty] | 37 | 0 |  |  |  | 22 | 35 | 35 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 100% |  | Amber | Amber | DPW1.6 |  |  | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG_T | PCD_DPW1_WIVG_T | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_OT | PCD_DPW1_WIVG_OT | PCD_DPW1_WIVG_P | PCD_DPW1_WIVG_P
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 | Y | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | Nr | 0 | [8 empty] | 5 | 5 | 5 | 6 | 0 | 6 | [12 empty] | 0 | 0 |  | 0% |  |  | DPW1.7 |  |  | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD_T | PCD_DPW1_RWD_T | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_OT | PCD_DPW1_RWD_OT | PCD_DPW1_RWD_P | PCD_DPW1_RWD_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead communication pipes replaced/relined | Nr | 0 | 0 | 0 | 8000 | 19500 | 31000 | 42500 | 54000 | [5 empty] | 54000 | 0 |  |  | 6222 | 18375 | 30250 | 42125 | 54000 | [5 empty] | 54000 |  | 100% |  | Green | Green | DPW1.8 |  |  | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1_T | PCD_DPW1_LEAD1_T | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_OT | PCD_DPW1_LEAD1_OT | PCD_DPW1_LEAD1_P | PCD_DPW1_LEAD1_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Non-schools | Nr | 0 | [12 empty] | 0 | 0 | [18 empty] | DPW1.9 |  |  | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2_T | PCD_DPW1_LEAD2_T | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_OT | PCD_DPW1_LEAD2_OT | PCD_DPW1_LEAD2_P | PCD_DPW1_LEAD2_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Schools | Nr | 0 | [12 empty] | 0 | 0 | [18 empty] | DPW1.10 |  |  | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3_T | PCD_DPW1_LEAD3_T | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_OT | PCD_DPW1_LEAD3_OT | PCD_DPW1_LEAD3_P | PCD_DPW1_LEAD3_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Non-schools | Nr | 0 | [12 empty] | 0 | 0 | [18 empty] | DPW1.11 |  |  | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4_T | PCD_DPW1_LEAD4_T | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_OT | PCD_DPW1_LEAD4_OT | PCD_DPW1_LEAD4_P | PCD_DPW1_LEAD4_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Schools | Nr | 0 | [12 empty] | 0 | 0 | [18 empty] | DPW1.12 |  |  | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5_T | PCD_DPW1_LEAD5_T | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_OT | PCD_DPW1_LEAD5_OT | PCD_DPW1_LEAD5_P | PCD_DPW1_LEAD5_P
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 | Y | W Resilience CC Uplift | Spend on scheme as a % of allowance | % | 0 | [6 empty] | 100 | [5 empty] | 100 | 0 | 0 | 0 | 3.1888 | 13.219 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.67% |  | Red | Red | DPW1.13 |  |  | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP_T | PCD_DPW1_WRESUP_T | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_OT | PCD_DPW1_WRESUP_OT | PCD_DPW1_WRESUP_P | PCD_DPW1_WRESUP_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | New installations | Nr | 0 | 0 | 0 | 69816 | 139633 | 209449 | 279266 | 349082 | [5 empty] | 349082 | 0 |  |  | 99861 | 181638 | 245466 | 296811 | 349081 | 349081 | 349081 | 349081 | 349081 | 349081 | 349081 | 349081 | 100% |  | Green | Green | DPW1.14 |  |  | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1_T | PCD_DPW1_MTR1_T | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_OT | PCD_DPW1_MTR1_OT | PCD_DPW1_MTR1_P | PCD_DPW1_MTR1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Household meter upgrades | Nr | 0 | 0 | 0 | 129098 | 258196 | 387294 | 516392 | 645490 | [5 empty] | 645490 | 0 |  |  | 145741 | 314801 | 466801 | 585998 | 694491 | 694491 | 694491 | 694491 | 694491 | 694491 | 694491 | 694491 | 107.6% |  | Green | Green | DPW1.15 |  |  | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2_T | PCD_DPW1_MTR2_T | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_OT | PCD_DPW1_MTR2_OT | PCD_DPW1_MTR2_P | PCD_DPW1_MTR2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Non household meter upgrades | Nr | 0 | 0 | 0 | 22657 | 45315 | 67971 | 90629 | 113286 | [5 empty] | 113286 | 0 |  |  | 24418 | 51185 | 79685 | 107685 | 128286 | 128286 | 128286 | 128286 | 128286 | 128286 | 128286 | 128286 | 113.2% |  | Green | Green | DPW1.16 |  |  | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3_T | PCD_DPW1_MTR3_T | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_OT | PCD_DPW1_MTR3_OT | PCD_DPW1_MTR3_P | PCD_DPW1_MTR3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Large bulk meters | Nr | 0 | 0 | 0 | 875 | 1750 | 2625 | 3500 | 4375 | [5 empty] | 4375 | 0 |  |  | 905 | 3050 | 5260 | 6818 | 9175 | 9175 | 9175 | 9175 | 9175 | 9175 | 9175 | 9175 | 209.7% |  | Green | Green | DPW1.17 |  |  | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4_T | PCD_DPW1_MTR4_T | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_OT | PCD_DPW1_MTR4_OT | PCD_DPW1_MTR4_P | PCD_DPW1_MTR4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Small bulk meters | Nr | 0 | 0 | 0 | 10184 | 20368 | 30552 | 40736 | 50920 | [5 empty] | 50920 | 0 |  |  | 5626 | 17012 | 30782 | 42552 | 50920 | 50920 | 50920 | 50920 | 50920 | 50920 | 50920 | 50920 | 100% |  | Green | Green | DPW1.18 |  |  | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5_T | PCD_DPW1_MTR5_T | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_OT | PCD_DPW1_MTR5_OT | PCD_DPW1_MTR5_P | PCD_DPW1_MTR5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Meter Replacements | Nr | 0 | 0 | 0 | 151755 | 303511 | 455266 | 607021 | 758776 | [5 empty] | 758776 | 0 |  |  | 170421 | 368421.0338 | 548921.0338 | 696118.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 108.8% |  | Green | Green | DPW1.19 |  |  | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6_T | PCD_DPW1_MTR6_T | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_OT | PCD_DPW1_MTR6_OT | PCD_DPW1_MTR6_P | PCD_DPW1_MTR6_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Connected meters | Nr | 0 | 0 | 0 | 0 | 116315 | 279157 | 488525 | 744419 | [5 empty] | 744419 | 0 |  |  | 0 | 138275.5 | 340611.6 | 579595.8 | 831891.2 | 831891.2 | 831891.2 | 831891.2 | 831891.2 | 831891.2 | 831891.2 | 831891.2 | 111.8% |  | Green | Green | DPW1.20 |  |  | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7_T | PCD_DPW1_MTR7_T | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_OT | PCD_DPW1_MTR7_OT | PCD_DPW1_MTR7_P | PCD_DPW1_MTR7_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Base Overlap Schemes] | Ml/d | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [18 empty] | DPW1.21 |  |  | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1_T | PCD_DPW1_SPL1_T | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_OT | PCD_DPW1_SPL1_OT | PCD_DPW1_SPL1_P | PCD_DPW1_SPL1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Medium] | Ml/d | 3 | 0 | 0 | 0 | 0 | 2.7 | 2.7 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | [6 empty] | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 100% | 100% | Green | Green | DPW1.22 |  |  | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2_T | PCD_DPW1_SPL2_T | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_OT | PCD_DPW1_SPL2_OT | PCD_DPW1_SPL2_P | PCD_DPW1_SPL2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Low] | Ml/d | 3 | 0 | 0 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 0 | 0 | 0 | 0 | 0 | 22.6 | 0 |  |  | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 100% |  | Green | Green | DPW1.23 |  |  | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3_T | PCD_DPW1_SPL3_T | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_OT | PCD_DPW1_SPL3_OT | PCD_DPW1_SPL3_P | PCD_DPW1_SPL3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Very Low] | Ml/d | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | DPW1.24 |  |  | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4_T | PCD_DPW1_SPL4_T | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_OT | PCD_DPW1_SPL4_OT | PCD_DPW1_SPL4_P | PCD_DPW1_SPL4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Total] | Ml/d | 3 | 0 | 0 | 22.6 | 22.6 | 25.3 | 25.3 | 43.36 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 43.36 | 20.76 | 0 | 0 | 22.6 | 22.6 | 22.6 | 22.6 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 100% | 208.9% | Green | Green | DPW1.25 |  |  | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5_T | PCD_DPW1_SPL5_T | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_OT | PCD_DPW1_SPL5_OT | PCD_DPW1_SPL5_P | PCD_DPW1_SPL5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | WAFU Benefit | Ml/d | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.26 |  |  | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1_T | PCD_DPW1_SPLIN1_T | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_OT | PCD_DPW1_SPLIN1_OT | PCD_DPW1_SPLIN1_P | PCD_DPW1_SPLIN1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | Pipeline length | Km | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.27 |  |  | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2_T | PCD_DPW1_SPLIN2_T | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_OT | PCD_DPW1_SPLIN2_OT | PCD_DPW1_SPLIN2_P | PCD_DPW1_SPLIN2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW9 | 0 | Efficiency | Water demand savings (benefit) | Ml/d | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.28 |  |  | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY_T | PCD_DPW1_EFCY_T | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_OT | PCD_DPW1_EFCY_OT | PCD_DPW1_EFCY_P | PCD_DPW1_EFCY_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Length of resilience interconnector | km | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.29 |  |  | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1_T | PCD_DPW1_RESIN1_T | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_OT | PCD_DPW1_RESIN1_OT | PCD_DPW1_RESIN1_P | PCD_DPW1_RESIN1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Crossing connections improvement | Nr | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.30 |  |  | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2_T | PCD_DPW1_RESIN2_T | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_OT | PCD_DPW1_RESIN2_OT | PCD_DPW1_RESIN2_P | PCD_DPW1_RESIN2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Additional storage at reservoirs | Ml | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.31 |  |  | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3_T | PCD_DPW1_RESIN3_T | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_OT | PCD_DPW1_RESIN3_OT | PCD_DPW1_RESIN3_P | PCD_DPW1_RESIN3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Reservoir bypass | Nr | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.32 |  |  | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4_T | PCD_DPW1_RESIN4_T | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_OT | PCD_DPW1_RESIN4_OT | PCD_DPW1_RESIN4_P | PCD_DPW1_RESIN4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Number of water treatment works with new equipment | Nr | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.33 |  |  | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1_T | PCD_DPW1_RES1_T | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_OT | PCD_DPW1_RES1_OT | PCD_DPW1_RES1_P | PCD_DPW1_RES1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Upgrade works at water treatment works | % | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.34 |  |  | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2_T | PCD_DPW1_RES2_T | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_OT | PCD_DPW1_RES2_OT | PCD_DPW1_RES2_P | PCD_DPW1_RES2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Service reservoirs with new enhanced bypass provision | Nr | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.35 |  |  | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3_T | PCD_DPW1_RES3_T | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_OT | PCD_DPW1_RES3_OT | PCD_DPW1_RES3_P | PCD_DPW1_RES3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Installation of new equipment | Nr | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.36 |  |  | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4_T | PCD_DPW1_RES4_T | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_OT | PCD_DPW1_RES4_OT | PCD_DPW1_RES4_P | PCD_DPW1_RES4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml of additional service reservoir storage at service reservoirs | Ml | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.37 |  |  | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5_T | PCD_DPW1_RES5_T | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_OT | PCD_DPW1_RES5_OT | PCD_DPW1_RES5_P | PCD_DPW1_RES5_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml/d of peak week production capacity of additional process stream | Ml/d | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.38 |  |  | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6_T | PCD_DPW1_RES6_T | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_OT | PCD_DPW1_RES6_OT | PCD_DPW1_RES6_P | PCD_DPW1_RES6_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16c | Y | Resilience | Number of raw water reservoirs with the delivery of specified safety improvements | Nr | 0 | [12 empty] | 0 | 0 | [18 empty] | DPW1.39 |  |  | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7_T | PCD_DPW1_RES7_T | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_OT | PCD_DPW1_RES7_OT | PCD_DPW1_RES7_P | PCD_DPW1_RES7_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17b | Y | Cyber | Legal instruments | Nr | 0 | [8 empty] | 1 | 1 | 1 | 1 | 0 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 100% | Green | Green | DPW1.40 |  |  | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR_T | PCD_DPW1_CYBR_T | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_OT | PCD_DPW1_CYBR_OT | PCD_DPW1_CYBR_P | PCD_DPW1_CYBR_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17a | Y | SEMD | Legal instruments | Nr | 0 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 |  | 1 |  | 100% | Green | Green | DPW1.41 |  |  | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD_T | PCD_DPW1_SEMD_T | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_OT | PCD_DPW1_SEMD_OT | PCD_DPW1_SEMD_P | PCD_DPW1_SEMD_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | tCO2e | tonnes | 3 | [12 empty] | 0 | 0 | [18 empty] | DPW1.42 |  |  | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1_T | PCD_DPW1_GGR1_T | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_OT | PCD_DPW1_GGR1_OT | PCD_DPW1_GGR1_P | PCD_DPW1_GGR1_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of hectares | Nr | 0 | [12 empty] | 0 | 0 | [18 empty] | DPW1.43 |  |  | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR_T | PCD_DPW1_GGR_T | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_OT | PCD_DPW1_GGR_OT | PCD_DPW1_GGR_P | PCD_DPW1_GGR_P
[42 empty] | End_Data | [31 empty] | End_BON

## DPW2
DPW2 | [42 empty] | Ofwat Bon Numbers
Enhancement PCD Expenditure - Water - Progamme Level
[43 empty] | _NP | [12 empty] | _T | _T | [12 empty] | _OT | _OT | _P | _P
Header | Company | PCD Model | PCD Ref | PCD applicable to company | Line Description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [11 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [11 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [11 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [11 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance (Expenditure)
[10 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%)
Start_Data | [9 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [6 empty] | Start_BON | 2025-30 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation hectares | Hectares of environmental improvement | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.1 |  |  | PCD_DPW2_BIOCON1_NP | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1_T | PCD_DPW2_BIOCON1_T | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_OT | PCD_DPW2_BIOCON1_OT | PCD_DPW2_BIOCON1_P | PCD_DPW2_BIOCON1_P
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation kilometres | Kilometres of environmental improvement | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.2 |  |  | PCD_DPW2_BIOCON2_NP | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2_T | PCD_DPW2_BIOCON2_T | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_OT | PCD_DPW2_BIOCON2_OT | PCD_DPW2_BIOCON2_P | PCD_DPW2_BIOCON2_P
| TMS | PR24CA106 Water WINEP | PCDW4 | 0 | Drinking Water Protected Areas | No Deterioration and Implementation actions | £m | 0 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.3 |  |  | PCD_DPW2_DWPA_NP | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA_T | PCD_DPW2_DWPA_T | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_OT | PCD_DPW2_DWPA_OT | PCD_DPW2_DWPA_P | PCD_DPW2_DWPA_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive interconnector | Length of WFD interconnector | £m | 3 | 2.8971 |  |  | 0.64263 | 2.1634 | 5.1229 | 10.3129 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 0 | 0 | 0.085785 | 0.15477 | 0.7828 | 1.3994 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 7.281% | 7.281% | DPW2.4 |  |  | PCD_DPW2_WFDI_NP | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI_T | PCD_DPW2_WFDI_T | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_OT | PCD_DPW2_WFDI_OT | PCD_DPW2_WFDI_P | PCD_DPW2_WFDI_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive actions | Other WFD actions | £m | 0 | 1.0004 |  |  | 0.44384 | 1.4942 | 3.5382 | 7.1227 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 0 | 0.055 | 0.42319 | 2.6442 | 7.4164 | 19.2107 | 23.5481 | 23.6262 | 23.629 | 23.629 | 23.629 | 23.629 | 23.5481 | 23.629 | 123.9% | 124.3% | DPW2.5 |  |  | PCD_DPW2_WFDA_NP | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA_T | PCD_DPW2_WFDA_T | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_OT | PCD_DPW2_WFDA_OT | PCD_DPW2_WFDA_P | PCD_DPW2_WFDA_P
| TMS | PR24CA106 Water WINEP | PCDW8 | Y | Water WINEP/NEP Investigations | Water WINEP/NEP Investigations | £m | 3 | 0.471 | 0 | 0 | 5.5903 | 11.601 | 13.5926 | 15.5641 | 17.427 | [5 empty] | 17.427 | 0 | 0 | 0 | 1.6196 | 7.1759 | 12.6193 | 21.2562 | 31.8677 | 31.9892 | 31.9892 | 31.9892 | 31.9892 | 31.9892 | 31.8677 | 31.9892 | 182.9% |  | DPW2.6 |  |  | PCD_DPW2_WIVG_NP | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG_T | PCD_DPW2_WIVG_T | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_OT | PCD_DPW2_WIVG_OT | PCD_DPW2_WIVG_P | PCD_DPW2_WIVG_P
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 | Y | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.7 |  |  | PCD_DPW2_RWD_NP | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD_T | PCD_DPW2_RWD_T | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_OT | PCD_DPW2_RWD_OT | PCD_DPW2_RWD_P | PCD_DPW2_RWD_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead communication pipes replaced/relined | £m | 3 | 0.0015441 |  |  | 11.3753 | 29.1756 | 48.392 | 67.462 | 83.384 | [5 empty] | 83.384 | 0 | 0 | 0 | 7.7785 | 24.472 | 40.2264 | 56.1587 | 72.2989 | 72.2989 | 72.2989 | 72.2989 | 72.2989 | 72.2989 | 72.2989 | 72.2989 | 86.71% |  | DPW2.8 |  |  | PCD_DPW2_LEAD1_NP | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1_T | PCD_DPW2_LEAD1_T | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_OT | PCD_DPW2_LEAD1_OT | PCD_DPW2_LEAD1_P | PCD_DPW2_LEAD1_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Non-schools | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.9 |  |  | PCD_DPW2_LEAD2_NP | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2_T | PCD_DPW2_LEAD2_T | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_OT | PCD_DPW2_LEAD2_OT | PCD_DPW2_LEAD2_P | PCD_DPW2_LEAD2_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Schools | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.10 |  |  | PCD_DPW2_LEAD3_NP | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3_T | PCD_DPW2_LEAD3_T | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_OT | PCD_DPW2_LEAD3_OT | PCD_DPW2_LEAD3_P | PCD_DPW2_LEAD3_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Non-schools | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.11 |  |  | PCD_DPW2_LEAD4_NP | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4_T | PCD_DPW2_LEAD4_T | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_OT | PCD_DPW2_LEAD4_OT | PCD_DPW2_LEAD4_P | PCD_DPW2_LEAD4_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Schools | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.12 |  |  | PCD_DPW2_LEAD5_NP | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5_T | PCD_DPW2_LEAD5_T | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_OT | PCD_DPW2_LEAD5_OT | PCD_DPW2_LEAD5_P | PCD_DPW2_LEAD5_P
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 | Y | W Resilience CC Uplift | Spend on scheme as a % of allowance | £m | 3 | 0.3291 |  | 0 | 4.0293 | 11.3859 | 18.6016 | 26.0632 | 32.9099 | [5 empty] | 32.9099 | 0 | 0 | 0 | 1.0494 | 4.3504 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 15.67% |  | DPW2.13 |  |  | PCD_DPW2_WRESUP_NP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP_T | PCD_DPW2_WRESUP_T | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_OT | PCD_DPW2_WRESUP_OT | PCD_DPW2_WRESUP_P | PCD_DPW2_WRESUP_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | New installations | £m | 3 | 0.00041923 |  | 0 | 29.269 | 58.5384 | 87.8074 | 117.0768 | 146.3458 | [5 empty] | 146.3458 | 0 | 0 | 0 | 52.0547 | 89.3931 | 119.8258 | 147.1651 | 176.3068 | 176.3068 | 176.3068 | 176.3068 | 176.3068 | 176.3068 | 176.3068 | 176.3068 | 120.5% |  | DPW2.14 |  |  | PCD_DPW2_MTR1_NP | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1_T | PCD_DPW2_MTR1_T | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_OT | PCD_DPW2_MTR1_OT | PCD_DPW2_MTR1_P | PCD_DPW2_MTR1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Household meter upgrades | £m | 3 | 3.2257e-05 |  | 0 | 4.1643 | 8.3286 | 12.4929 | 16.6572 | 20.8214 | [5 empty] | 20.8214 | 0 | 0 | 0 | 8.0067 | 17.433 | 25.9817 | 32.7611 | 38.9923 | 38.9923 | 38.9923 | 38.9923 | 38.9923 | 38.9923 | 38.9923 | 38.9923 | 187.3% |  | DPW2.15 |  |  | PCD_DPW2_MTR2_NP | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2_T | PCD_DPW2_MTR2_T | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_OT | PCD_DPW2_MTR2_OT | PCD_DPW2_MTR2_P | PCD_DPW2_MTR2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Non household meter upgrades | £m | 3 | 3.2257e-05 |  | 0 | 0.73084 | 1.4617 | 2.1925 | 2.9234 | 3.6542 | [5 empty] | 3.6542 | 0 | 0 | 0 | 1.3225 | 2.7939 | 4.3741 | 5.9441 | 7.1106 | 7.1106 | 7.1106 | 7.1106 | 7.1106 | 7.1106 | 7.1106 | 7.1106 | 194.6% |  | DPW2.16 |  |  | PCD_DPW2_MTR3_NP | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3_T | PCD_DPW2_MTR3_T | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_OT | PCD_DPW2_MTR3_OT | PCD_DPW2_MTR3_P | PCD_DPW2_MTR3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Large bulk meters | £m | 3 | 0.0035777 |  | 0 | 3.1305 | 6.261 | 9.3915 | 12.522 | 15.6525 | [5 empty] | 15.6525 | 0 | 0 | 0 | 5.1906 | 16.9522 | 28.4961 | 37.3949 | 49.1827 | 49.1827 | 49.1827 | 49.1827 | 49.1827 | 49.1827 | 49.1827 | 49.1827 | 314.2% |  | DPW2.17 |  |  | PCD_DPW2_MTR4_NP | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4_T | PCD_DPW2_MTR4_T | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_OT | PCD_DPW2_MTR4_OT | PCD_DPW2_MTR4_P | PCD_DPW2_MTR4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Small bulk meters | £m | 3 | 0.0005835 |  | 0 | 5.9423 | 11.8847 | 17.827 | 23.7693 | 29.7117 | [5 empty] | 29.7117 | 0 | 0 | 0 | 3.0632 | 9.1954 | 15.8885 | 21.649 | 25.8727 | 25.8727 | 25.8727 | 25.8727 | 25.8727 | 25.8727 | 25.8727 | 25.8727 | 87.08% |  | DPW2.18 |  |  | PCD_DPW2_MTR5_NP | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5_T | PCD_DPW2_MTR5_T | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_OT | PCD_DPW2_MTR5_OT | PCD_DPW2_MTR5_P | PCD_DPW2_MTR5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Meter Replacements | £m | 3 | 0.00012131 |  | 0 | 18.4094 | 36.8189 | 55.2283 | 73.6377 | 92.0471 | [5 empty] | 92.0471 | 0 | 0 | 0 | 20.634 | 51.3401 | 81.6051 | 106.4687 | 129.633 | 129.633 | 129.633 | 129.633 | 129.633 | 129.633 | 129.633 | 129.633 | 140.8% |  | DPW2.19 |  |  | PCD_DPW2_MTR6_NP | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6_T | PCD_DPW2_MTR6_T | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_OT | PCD_DPW2_MTR6_OT | PCD_DPW2_MTR6_P | PCD_DPW2_MTR6_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Connected meters | £m | 3 | 4.9836e-05 | 0 | 0 | 11.5934 | 23.1869 | 34.7803 | 46.3738 | 57.9672 | [5 empty] | 57.9672 | 0 | 0 | 0 | 7.041 | 14.0284 | 21.148 | 28.4423 | 35.8935 | 35.8935 | 35.8935 | 35.8935 | 35.8935 | 35.8935 | 35.8935 | 35.8935 | 61.92% |  | DPW2.20 |  |  | PCD_DPW2_MTR7_NP | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7_T | PCD_DPW2_MTR7_T | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_OT | PCD_DPW2_MTR7_OT | PCD_DPW2_MTR7_P | PCD_DPW2_MTR7_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Base Overlap Schemes] | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.21 |  |  | PCD_DPW2_SPL1_NP | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1_T | PCD_DPW2_SPL1_T | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_OT | PCD_DPW2_SPL1_OT | PCD_DPW2_SPL1_P | PCD_DPW2_SPL1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Medium] | £m | 3 |  |  |  | 6.9099 | 18.3405 | 40.1917 | 61.3835 | 80.1504 | [5 empty] | 80.1504 | 0 | 0 | 0 | 1.136 | 5.8859 | 20.617 | 38.7641 | 48.8532 | 49.0116 | 49.0879 | 49.0879 | 49.0879 | 49.0879 | 48.8532 | 49.0879 | 60.95% |  | DPW2.22 |  |  | PCD_DPW2_SPL2_NP | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2_T | PCD_DPW2_SPL2_T | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_OT | PCD_DPW2_SPL2_OT | PCD_DPW2_SPL2_P | PCD_DPW2_SPL2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Low] | £m | 3 |  |  |  | 3.0306 | 6.105 | 9.2251 | 12.3899 | 15.6013 | [5 empty] | 15.6013 | 0 | 2.2322 | 4.4185 | 7.0806 | 9.863 | 12.6349 | 15.4058 | 18.1751 | 18.1751 | 18.1751 | 18.1751 | 18.1751 | 18.1751 | 18.1751 | 18.1751 | 116.5% |  | DPW2.23 |  |  | PCD_DPW2_SPL3_NP | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3_T | PCD_DPW2_SPL3_T | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_OT | PCD_DPW2_SPL3_OT | PCD_DPW2_SPL3_P | PCD_DPW2_SPL3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Very Low] | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.24 |  |  | PCD_DPW2_SPL4_NP | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4_T | PCD_DPW2_SPL4_T | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_OT | PCD_DPW2_SPL4_OT | PCD_DPW2_SPL4_P | PCD_DPW2_SPL4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Total] | £m | 3 |  |  |  | 9.9405 | 24.4456 | 49.4168 | 73.7734 | 95.7517 | [5 empty] | 95.7517 | 0 | 2.2322 | 4.4185 | 8.2166 | 15.749 | 33.2519 | 54.1699 | 67.0283 | 67.1866 | 67.2629 | 67.2629 | 67.2629 | 67.2629 | 67.0283 | 67.2629 | 70% |  | DPW2.25 |  |  | PCD_DPW2_SPL5_NP | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5_T | PCD_DPW2_SPL5_T | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_OT | PCD_DPW2_SPL5_OT | PCD_DPW2_SPL5_P | PCD_DPW2_SPL5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | WAFU Benefit | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.26 |  |  | PCD_DPW2_SPLIN1_NP | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1_T | PCD_DPW2_SPLIN1_T | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_OT | PCD_DPW2_SPLIN1_OT | PCD_DPW2_SPLIN1_P | PCD_DPW2_SPLIN1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | Pipeline length | Km | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.27 |  |  | PCD_DPW2_SPLIN2_NP | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2_T | PCD_DPW2_SPLIN2_T | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_OT | PCD_DPW2_SPLIN2_OT | PCD_DPW2_SPLIN2_P | PCD_DPW2_SPLIN2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW9 | 0 | Efficiency | Water demand savings (benefit) | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.28 |  |  | PCD_DPW2_EFCY_NP | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY_T | PCD_DPW2_EFCY_T | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_OT | PCD_DPW2_EFCY_OT | PCD_DPW2_EFCY_P | PCD_DPW2_EFCY_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Length of resilience interconnector | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.29 |  |  | PCD_DPW2_RESIN1_NP | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1_T | PCD_DPW2_RESIN1_T | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_OT | PCD_DPW2_RESIN1_OT | PCD_DPW2_RESIN1_P | PCD_DPW2_RESIN1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Crossing connections improvement | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.30 |  |  | PCD_DPW2_RESIN2_NP | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2_T | PCD_DPW2_RESIN2_T | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_OT | PCD_DPW2_RESIN2_OT | PCD_DPW2_RESIN2_P | PCD_DPW2_RESIN2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Additional storage at reservoirs | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.31 |  |  | PCD_DPW2_RESIN3_NP | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3_T | PCD_DPW2_RESIN3_T | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_OT | PCD_DPW2_RESIN3_OT | PCD_DPW2_RESIN3_P | PCD_DPW2_RESIN3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Reservoir bypass | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.32 |  |  | PCD_DPW2_RESIN4_NP | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4_T | PCD_DPW2_RESIN4_T | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_OT | PCD_DPW2_RESIN4_OT | PCD_DPW2_RESIN4_P | PCD_DPW2_RESIN4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Number of water treatment works with new equipment | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.33 |  |  | PCD_DPW2_RES1_NP | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1_T | PCD_DPW2_RES1_T | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_OT | PCD_DPW2_RES1_OT | PCD_DPW2_RES1_P | PCD_DPW2_RES1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Upgrade works at water treatment works | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.34 |  |  | PCD_DPW2_RES2_NP | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2_T | PCD_DPW2_RES2_T | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_OT | PCD_DPW2_RES2_OT | PCD_DPW2_RES2_P | PCD_DPW2_RES2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Service reservoirs with new enhanced bypass provision | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.35 |  |  | PCD_DPW2_RES3_NP | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3_T | PCD_DPW2_RES3_T | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_OT | PCD_DPW2_RES3_OT | PCD_DPW2_RES3_P | PCD_DPW2_RES3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Installation of new equipment | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.36 |  |  | PCD_DPW2_RES4_NP | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4_T | PCD_DPW2_RES4_T | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_OT | PCD_DPW2_RES4_OT | PCD_DPW2_RES4_P | PCD_DPW2_RES4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml of additional service reservoir storage at service reservoirs | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.37 |  |  | PCD_DPW2_RES5_NP | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5_T | PCD_DPW2_RES5_T | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_OT | PCD_DPW2_RES5_OT | PCD_DPW2_RES5_P | PCD_DPW2_RES5_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml/d of peak week production capacity of additional process stream | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.38 |  |  | PCD_DPW2_RES6_NP | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6_T | PCD_DPW2_RES6_T | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_OT | PCD_DPW2_RES6_OT | PCD_DPW2_RES6_P | PCD_DPW2_RES6_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16c | 0 | Resilience | Number of raw water reservoirs with the delivery of specified safety improvements | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.39 |  |  | PCD_DPW2_RES7_NP | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7_T | PCD_DPW2_RES7_T | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_OT | PCD_DPW2_RES7_OT | PCD_DPW2_RES7_P | PCD_DPW2_RES6_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16c | 0 | Resilience | Reservoirs - spend on MITIOS (Measures in the Interest of Safety) | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.40 |  |  | PCD_DPW2_RES8_NP | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8_T | PCD_DPW2_RES8_T | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_OT | PCD_DPW2_RES8_OT | PCD_DPW2_RES8_P | PCD_DPW2_RES8_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17b | Y | Cyber | Legal instruments | £m | 3 | 112.0115 |  |  | 25.9834 | 47.7608 | 68.3195 | 90.9236 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 0 | 0 | 9.6532 | 23.4709 | 47.8109 | 77.4377 | 103.5306 | 104.8426 | 104.8426 | 104.8426 | 104.8426 | 104.8426 | 103.5306 | 104.8426 | 92.43% | 93.6% | DPW2.41 |  |  | PCD_DPW2_CYBR_NP | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR_T | PCD_DPW2_CYBR_T | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_OT | PCD_DPW2_CYBR_OT | PCD_DPW2_CYBR_P | PCD_DPW2_CYBR_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17a | Y | SEMD | Legal instruments | £m | 3 | 28.088 |  |  | 2.2744 | 5.5131 | 9.9145 | 17.8311 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 0 | 0 | 1.81 | 6.261 | 12.1236 | 21.6335 | 29.8096 | 29.8096 | 29.8096 | 29.8096 | 29.8096 | 29.8096 | 29.8096 | 29.8096 | 106.1% | 106.1% | DPW2.42 |  |  | PCD_DPW2_SEMD_NP | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD_T | PCD_DPW2_SEMD_T | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_OT | PCD_DPW2_SEMD_OT | PCD_DPW2_SEMD_P | PCD_DPW2_SEMD_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of hectares | £m | 3 | [13 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  | DPW2.43 |  |  | PCD_DPW2_GGR_NP | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR_T | PCD_DPW2_GGR_T | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_OT | PCD_DPW2_GGR_OT | PCD_DPW2_GGR_P | PCD_DPW2_GGR_P
NONPCD1 | TMS |  |  |  | Total other non - PCD enhancement water expenditure, totex | Total other non - PCD enhancement water expenditure, totex | £m | 3 | [13 empty] | 0 | 0 | 85.087 | 206.401 | 520.4182 | 991.1657 | 1696.2395 | 2489.0562 | 3272.127 | 3639.5756 | 3961.559 | 4240.5066 | 4396.6537 | 4364.9218 | 3272.127 | 4364.9218 |  |  | DPW2.44 |  |  | PCD_DPW2_NONPCD1_NP | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1_T | PCD_DPW2_NONPCD1_T | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_OT | PCD_DPW2_NONPCD1_OT | PCD_DPW2_NONPCD1_P | PCD_DPW2_NONPCD1_P
NONPCD2 | TMS |  |  |  | Total PCD and non - PCD enhancement expenditure; water totex | Total PCD and non - PCD enhancement expenditure; water totex | £m | 3 |  | 0 | 0 | 133.5195 | 280.0197 | 436.618 | 602.0132 | 782.3029 | 186.6302 | 186.6302 | 186.6302 | 186.6302 | 186.6302 | 782.3029 | 186.6302 | 87.3192 | 210.8745 | 648.3671 | 1276.5797 | 2152.9455 | 3125.3031 | 4070.3612 | 4439.4798 | 4761.5422 | 5040.4898 | 5196.6369 | 5164.905 | 4070.3612 | 5164.905 | 520.3% | 2767% | DPW2.45 |  |  | PCD_DPW2_NONPCD2_NP | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2_T | PCD_DPW2_NONPCD2_T | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_OT | PCD_DPW2_NONPCD2_OT | PCD_DPW2_NONPCD2_P | PCD_DPW2_NONPCD2_P
[41 empty] | End_Data | [32 empty] | End_BON

## DPW3
DPW3
[109 empty] | _DLY | _IR | _SCR | _CS | _SCS | _PP | _TPI | _CI | _SI | _ER | _RS | _PLE
Interim Milestones - Water - Programme Level
| Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | Total Number of Schemes with IMs (Nr) | [41 empty] | Total number of schemes with a 90+ day delay by IM (No.) | Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category | [10 empty] | DP Reference |  | Number of Schemes with IMs (Nr) |  | Number of schemes at Stage 0: IM1 has yet to be achieved | [41 empty] | _DLY: Total number of schemes with a 90+ day delay for any given IM; _IR: Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category
[10 empty] | Pre - AMP8 | AMP8 | [19 empty] | AMP9 | [20 empty] | Lack of internal resourcing | Lack of supply chain resourcing | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency |  |  |  |  | Pre - AMP8 | AMP8 | [19 empty] | AMP9 | [21 empty] | Lack of resources - internal | Lack of resources - external | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency
Start_Dta | [6 empty] | Nr | 0 | 0 | Pre 2025-26 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | 2030-31 Q1 | 2030-31 Q2 | 2030-31 Q3 | 2030-31 Q4 | 2031-32 Q1 | 2031-32 Q2 | 2031-32 Q3 | 2031-32 Q4 | 2032-33 Q1 | 2032-33 Q2 | 2032-33 Q3 | 2032-33 Q4 | 2033-34 Q1 | 2033-34 Q2 | 2033-34 Q3 | 2033-34 Q4 | 2034-35 Q1 | 2034-35 Q2 | 2034-35 Q3 | 2034-35 Q4 | [13 empty] | Start_BON | Constant |  | 2024-25 Q4 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | 2030-31 Q1 | 2030-31 Q2 | 2030-31 Q3 | 2030-31 Q4 | 2031-32 Q1 | 2031-32 Q2 | 2031-32 Q3 | 2031-32 Q4 | 2032-33 Q1 | 2032-33 Q2 | 2032-33 Q3 | 2032-33 Q4 | 2033-34 Q1 | 2033-34 Q2 | 2033-34 Q3 | 2033-34 Q4 | 2034-35 Q1 | 2034-35 Q2 | 2034-35 Q3 | 2034-35 Q4 |  | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 0 | Nr | 0 | 7 | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  | PCD_DPW3_WFDI1_NR | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 |  | PCD_DPW3_WFDI1_DLY | PCD_DPW3_WFDI1_DIR | PCD_DPW3_WFDI1_DSCR | PCD_DPW3_WFDI1_DCS | PCD_DPW3_WFDI1_DSPC | PCD_DPW3_WFDI1_DPP | PCD_DPW3_WFDI1_DTPI | PCD_DPW3_WFDI1_DCI | PCD_DPW3_WFDI1_DSI | PCD_DPW3_WFDI1_DER | PCD_DPW3_WFDI1_RS | PCD_DPW3_WFDI1_DPLE
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 3 | 4 | 5 | 5 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | _S1 | PCD_DPW3_WFDI1_DLY_S1 | PCD_DPW3_WFDI1_DIR_S1 | PCD_DPW3_WFDI1_DSCR_S1 | PCD_DPW3_WFDI1_DCS_S1 | PCD_DPW3_WFDI1_DSPC_S1 | PCD_DPW3_WFDI1_DPP_S1 | PCD_DPW3_WFDI1_DTPI_S1 | PCD_DPW3_WFDI1_DCI_S1 | PCD_DPW3_WFDI1_DSI_S1 | PCD_DPW3_WFDI1_DER_S1 | PCD_DPW3_WFDI1_RS_S1 | PCD_DPW3_WFDI1_DPLE_S1
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 2 | Nr | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | _S2 | PCD_DPW3_WFDI1_DLY_S2 | PCD_DPW3_WFDI1_DIR_S2 | PCD_DPW3_WFDI1_DSCR_S2 | PCD_DPW3_WFDI1_DCS_S2 | PCD_DPW3_WFDI1_DSPC_S2 | PCD_DPW3_WFDI1_DPP_S2 | PCD_DPW3_WFDI1_DTPI_S2 | PCD_DPW3_WFDI1_DCI_S2 | PCD_DPW3_WFDI1_DSI_S2 | PCD_DPW3_WFDI1_DER_S2 | PCD_DPW3_WFDI1_RS_S2 | PCD_DPW3_WFDI1_DPLE_S2
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | _S3 | PCD_DPW3_WFDI1_DLY_S3 | PCD_DPW3_WFDI1_DIR_S3 | PCD_DPW3_WFDI1_DSCR_S3 | PCD_DPW3_WFDI1_DCS_S3 | PCD_DPW3_WFDI1_DSPC_S3 | PCD_DPW3_WFDI1_DPP_S3 | PCD_DPW3_WFDI1_DTPI_S3 | PCD_DPW3_WFDI1_DCI_S3 | PCD_DPW3_WFDI1_DSI_S3 | PCD_DPW3_WFDI1_DER_S3 | PCD_DPW3_WFDI1_RS_S3 | PCD_DPW3_WFDI1_DPLE_S3
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | _S4 | PCD_DPW3_WFDI1_DLY_S4 | PCD_DPW3_WFDI1_DIR_S4 | PCD_DPW3_WFDI1_DSCR_S4 | PCD_DPW3_WFDI1_DCS_S4 | PCD_DPW3_WFDI1_DSPC_S4 | PCD_DPW3_WFDI1_DPP_S4 | PCD_DPW3_WFDI1_DTPI_S4 | PCD_DPW3_WFDI1_DCI_S4 | PCD_DPW3_WFDI1_DSI_S4 | PCD_DPW3_WFDI1_DER_S4 | PCD_DPW3_WFDI1_RS_S4 | PCD_DPW3_WFDI1_DPLE_S4
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 5 | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | _S5 | PCD_DPW3_WFDI1_DLY_S5 | PCD_DPW3_WFDI1_DIR_S5 | PCD_DPW3_WFDI1_DSCR_S5 | PCD_DPW3_WFDI1_DCS_S5 | PCD_DPW3_WFDI1_DSPC_S5 | PCD_DPW3_WFDI1_DPP_S5 | PCD_DPW3_WFDI1_DTPI_S5 | PCD_DPW3_WFDI1_DCI_S5 | PCD_DPW3_WFDI1_DSI_S5 | PCD_DPW3_WFDI1_DER_S5 | PCD_DPW3_WFDI1_RS_S5 | PCD_DPW3_WFDI1_DPLE_S5
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | [11 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | _S6 | PCD_DPW3_WFDI1_DLY_S6 | PCD_DPW3_WFDI1_DIR_S6 | PCD_DPW3_WFDI1_DSCR_S6 | PCD_DPW3_WFDI1_DCS_S6 | PCD_DPW3_WFDI1_DSPC_S6 | PCD_DPW3_WFDI1_DPP_S6 | PCD_DPW3_WFDI1_DTPI_S6 | PCD_DPW3_WFDI1_DCI_S6 | PCD_DPW3_WFDI1_DSI_S6 | PCD_DPW3_WFDI1_DER_S6 | PCD_DPW3_WFDI1_RS_S6 | PCD_DPW3_WFDI1_DPLE_S6
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | _S7 | PCD_DPW3_WFDI1_DLY_S7 | PCD_DPW3_WFDI1_DIR_S7 | PCD_DPW3_WFDI1_DSCR_S7 | PCD_DPW3_WFDI1_DCS_S7 | PCD_DPW3_WFDI1_DSPC_S7 | PCD_DPW3_WFDI1_DPP_S7 | PCD_DPW3_WFDI1_DTPI_S7 | PCD_DPW3_WFDI1_DCI_S7 | PCD_DPW3_WFDI1_DSI_S7 | PCD_DPW3_WFDI1_DER_S7 | PCD_DPW3_WFDI1_RS_S7 | PCD_DPW3_WFDI1_DPLE_S7
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | _ST | PCD_DPW3_WFDI1_DLY_ST | PCD_DPW3_WFDI1_DIR_ST | PCD_DPW3_WFDI1_DSCR_ST | PCD_DPW3_WFDI1_DCS_ST | PCD_DPW3_WFDI1_DSPC_ST | PCD_DPW3_WFDI1_DPP_ST | PCD_DPW3_WFDI1_DTPI_ST | PCD_DPW3_WFDI1_DCI_ST | PCD_DPW3_WFDI1_DSI_ST | PCD_DPW3_WFDI1_DER_ST | PCD_DPW3_WFDI1_RS_ST | PCD_DPW3_WFDI1_DPLE_ST
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  | PCD_DPW3_RWD_NR | PCD_DPW3_RWD | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 |  | PCD_DPW3_RWD_DLY | PCD_DPW3_RWD_DIR | PCD_DPW3_RWD_DSCR | PCD_DPW3_RWD_DCS | PCD_DPW3_RWD_DSPC | PCD_DPW3_RWD_DPP | PCD_DPW3_RWD_DTPI | PCD_DPW3_RWD_DCI | PCD_DPW3_RWD_DSI | PCD_DPW3_RWD_DER | PCD_DPW3_RWD_RS | PCD_DPW3_RWD_DPLE
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 |  | PCD_DPW3_RWD_DLY_S1 | PCD_DPW3_RWD_DIR_S1 | PCD_DPW3_RWD_DSCR_S1 | PCD_DPW3_RWD_DCS_S1 | PCD_DPW3_RWD_DSPC_S1 | PCD_DPW3_RWD_DPP_S1 | PCD_DPW3_RWD_DTPI_S1 | PCD_DPW3_RWD_DCI_S1 | PCD_DPW3_RWD_DSI_S1 | PCD_DPW3_RWD_DER_S1 | PCD_DPW3_RWD_RS_S1 | PCD_DPW3_RWD_DPLE_S1
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 |  | PCD_DPW3_RWD_DLY_S2 | PCD_DPW3_RWD_DIR_S2 | PCD_DPW3_RWD_DSCR_S2 | PCD_DPW3_RWD_DCS_S2 | PCD_DPW3_RWD_DSPC_S2 | PCD_DPW3_RWD_DPP_S2 | PCD_DPW3_RWD_DTPI_S2 | PCD_DPW3_RWD_DCI_S2 | PCD_DPW3_RWD_DSI_S2 | PCD_DPW3_RWD_DER_S2 | PCD_DPW3_RWD_RS_S2 | PCD_DPW3_RWD_DPLE_S2
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 |  | PCD_DPW3_RWD_DLY_S3 | PCD_DPW3_RWD_DIR_S3 | PCD_DPW3_RWD_DSCR_S3 | PCD_DPW3_RWD_DCS_S3 | PCD_DPW3_RWD_DSPC_S3 | PCD_DPW3_RWD_DPP_S3 | PCD_DPW3_RWD_DTPI_S3 | PCD_DPW3_RWD_DCI_S3 | PCD_DPW3_RWD_DSI_S3 | PCD_DPW3_RWD_DER_S3 | PCD_DPW3_RWD_RS_S3 | PCD_DPW3_RWD_DPLE_S3
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 |  | PCD_DPW3_RWD_DLY_S4 | PCD_DPW3_RWD_DIR_S4 | PCD_DPW3_RWD_DSCR_S4 | PCD_DPW3_RWD_DCS_S4 | PCD_DPW3_RWD_DSPC_S4 | PCD_DPW3_RWD_DPP_S4 | PCD_DPW3_RWD_DTPI_S4 | PCD_DPW3_RWD_DCI_S4 | PCD_DPW3_RWD_DSI_S4 | PCD_DPW3_RWD_DER_S4 | PCD_DPW3_RWD_RS_S4 | PCD_DPW3_RWD_DPLE_S4
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 |  | PCD_DPW3_RWD_DLY_S5 | PCD_DPW3_RWD_DIR_S5 | PCD_DPW3_RWD_DSCR_S5 | PCD_DPW3_RWD_DCS_S5 | PCD_DPW3_RWD_DSPC_S5 | PCD_DPW3_RWD_DPP_S5 | PCD_DPW3_RWD_DTPI_S5 | PCD_DPW3_RWD_DCI_S5 | PCD_DPW3_RWD_DSI_S5 | PCD_DPW3_RWD_DER_S5 | PCD_DPW3_RWD_RS_S5 | PCD_DPW3_RWD_DPLE_S5
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 |  | PCD_DPW3_RWD_DLY_S6 | PCD_DPW3_RWD_DIR_S6 | PCD_DPW3_RWD_DSCR_S6 | PCD_DPW3_RWD_DCS_S6 | PCD_DPW3_RWD_DSPC_S6 | PCD_DPW3_RWD_DPP_S6 | PCD_DPW3_RWD_DTPI_S6 | PCD_DPW3_RWD_DCI_S6 | PCD_DPW3_RWD_DSI_S6 | PCD_DPW3_RWD_DER_S6 | PCD_DPW3_RWD_RS_S6 | PCD_DPW3_RWD_DPLE_S6
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 |  | PCD_DPW3_RWD_DLY_S7 | PCD_DPW3_RWD_DIR_S7 | PCD_DPW3_RWD_DSCR_S7 | PCD_DPW3_RWD_DCS_S7 | PCD_DPW3_RWD_DSPC_S7 | PCD_DPW3_RWD_DPP_S7 | PCD_DPW3_RWD_DTPI_S7 | PCD_DPW3_RWD_DCI_S7 | PCD_DPW3_RWD_DSI_S7 | PCD_DPW3_RWD_DER_S7 | PCD_DPW3_RWD_RS_S7 | PCD_DPW3_RWD_DPLE_S7
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST |  | PCD_DPW3_RWD_DLY_ST | PCD_DPW3_RWD_DIR_ST | PCD_DPW3_RWD_DSCR_ST | PCD_DPW3_RWD_DCS_ST | PCD_DPW3_RWD_DSPC_ST | PCD_DPW3_RWD_DPP_ST | PCD_DPW3_RWD_DTPI_ST | PCD_DPW3_RWD_DCI_ST | PCD_DPW3_RWD_DSI_ST | PCD_DPW3_RWD_DER_ST | PCD_DPW3_RWD_RS_ST | PCD_DPW3_RWD_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 0 | Nr | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  | PCD_DPW3_WRESUP_NR | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 |  | PCD_DPW3_WRESUP_DLY | PCD_DPW3_WRESUP_DIR | PCD_DPW3_WRESUP_DSCR | PCD_DPW3_WRESUP_DCS | PCD_DPW3_WRESUP_DSPC | PCD_DPW3_WRESUP_DPP | PCD_DPW3_WRESUP_DTPI | PCD_DPW3_WRESUP_DCI | PCD_DPW3_WRESUP_DSI | PCD_DPW3_WRESUP_DER | PCD_DPW3_WRESUP_RS | PCD_DPW3_WRESUP_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 |  | PCD_DPW3_WRESUP_DLY_S1 | PCD_DPW3_WRESUP_DIR_S1 | PCD_DPW3_WRESUP_DSCR_S1 | PCD_DPW3_WRESUP_DCS_S1 | PCD_DPW3_WRESUP_DSPC_S1 | PCD_DPW3_WRESUP_DPP_S1 | PCD_DPW3_WRESUP_DTPI_S1 | PCD_DPW3_WRESUP_DCI_S1 | PCD_DPW3_WRESUP_DSI_S1 | PCD_DPW3_WRESUP_DER_S1 | PCD_DPW3_WRESUP_RS_S1 | PCD_DPW3_WRESUP_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 |  | PCD_DPW3_WRESUP_DLY_S2 | PCD_DPW3_WRESUP_DIR_S2 | PCD_DPW3_WRESUP_DSCR_S2 | PCD_DPW3_WRESUP_DCS_S2 | PCD_DPW3_WRESUP_DSPC_S2 | PCD_DPW3_WRESUP_DPP_S2 | PCD_DPW3_WRESUP_DTPI_S2 | PCD_DPW3_WRESUP_DCI_S2 | PCD_DPW3_WRESUP_DSI_S2 | PCD_DPW3_WRESUP_DER_S2 | PCD_DPW3_WRESUP_RS_S2 | PCD_DPW3_WRESUP_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 |  | PCD_DPW3_WRESUP_DLY_S3 | PCD_DPW3_WRESUP_DIR_S3 | PCD_DPW3_WRESUP_DSCR_S3 | PCD_DPW3_WRESUP_DCS_S3 | PCD_DPW3_WRESUP_DSPC_S3 | PCD_DPW3_WRESUP_DPP_S3 | PCD_DPW3_WRESUP_DTPI_S3 | PCD_DPW3_WRESUP_DCI_S3 | PCD_DPW3_WRESUP_DSI_S3 | PCD_DPW3_WRESUP_DER_S3 | PCD_DPW3_WRESUP_RS_S3 | PCD_DPW3_WRESUP_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 |  | PCD_DPW3_WRESUP_DLY_S4 | PCD_DPW3_WRESUP_DIR_S4 | PCD_DPW3_WRESUP_DSCR_S4 | PCD_DPW3_WRESUP_DCS_S4 | PCD_DPW3_WRESUP_DSPC_S4 | PCD_DPW3_WRESUP_DPP_S4 | PCD_DPW3_WRESUP_DTPI_S4 | PCD_DPW3_WRESUP_DCI_S4 | PCD_DPW3_WRESUP_DSI_S4 | PCD_DPW3_WRESUP_DER_S4 | PCD_DPW3_WRESUP_RS_S4 | PCD_DPW3_WRESUP_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 |  | PCD_DPW3_WRESUP_DLY_S5 | PCD_DPW3_WRESUP_DIR_S5 | PCD_DPW3_WRESUP_DSCR_S5 | PCD_DPW3_WRESUP_DCS_S5 | PCD_DPW3_WRESUP_DSPC_S5 | PCD_DPW3_WRESUP_DPP_S5 | PCD_DPW3_WRESUP_DTPI_S5 | PCD_DPW3_WRESUP_DCI_S5 | PCD_DPW3_WRESUP_DSI_S5 | PCD_DPW3_WRESUP_DER_S5 | PCD_DPW3_WRESUP_RS_S5 | PCD_DPW3_WRESUP_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 |  | PCD_DPW3_WRESUP_DLY_S6 | PCD_DPW3_WRESUP_DIR_S6 | PCD_DPW3_WRESUP_DSCR_S6 | PCD_DPW3_WRESUP_DCS_S6 | PCD_DPW3_WRESUP_DSPC_S6 | PCD_DPW3_WRESUP_DPP_S6 | PCD_DPW3_WRESUP_DTPI_S6 | PCD_DPW3_WRESUP_DCI_S6 | PCD_DPW3_WRESUP_DSI_S6 | PCD_DPW3_WRESUP_DER_S6 | PCD_DPW3_WRESUP_RS_S6 | PCD_DPW3_WRESUP_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 |  | PCD_DPW3_WRESUP_DLY_S7 | PCD_DPW3_WRESUP_DIR_S7 | PCD_DPW3_WRESUP_DSCR_S7 | PCD_DPW3_WRESUP_DCS_S7 | PCD_DPW3_WRESUP_DSPC_S7 | PCD_DPW3_WRESUP_DPP_S7 | PCD_DPW3_WRESUP_DTPI_S7 | PCD_DPW3_WRESUP_DCI_S7 | PCD_DPW3_WRESUP_DSI_S7 | PCD_DPW3_WRESUP_DER_S7 | PCD_DPW3_WRESUP_RS_S7 | PCD_DPW3_WRESUP_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST |  | PCD_DPW3_WRESUP_DLY_ST | PCD_DPW3_WRESUP_DIR_ST | PCD_DPW3_WRESUP_DSCR_ST | PCD_DPW3_WRESUP_DCS_ST | PCD_DPW3_WRESUP_DSPC_ST | PCD_DPW3_WRESUP_DPP_ST | PCD_DPW3_WRESUP_DTPI_ST | PCD_DPW3_WRESUP_DCI_ST | PCD_DPW3_WRESUP_DSI_ST | PCD_DPW3_WRESUP_DER_ST | PCD_DPW3_WRESUP_RS_ST | PCD_DPW3_WRESUP_DPLE_ST
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 0 | Nr | 0 | 3 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  | PCD_DPW3_SPL5_NR | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 |  | PCD_DPW3_SPL5_DLY | PCD_DPW3_SPL5_DIR | PCD_DPW3_SPL5_DSCR | PCD_DPW3_SPL5_DCS | PCD_DPW3_SPL5_DSPC | PCD_DPW3_SPL5_DPP | PCD_DPW3_SPL5_DTPI | PCD_DPW3_SPL5_DCI | PCD_DPW3_SPL5_DSI | PCD_DPW3_SPL5_DER | PCD_DPW3_SPL5_RS | PCD_DPW3_SPL5_DPLE
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 |  | PCD_DPW3_SPL5_DLY_S1 | PCD_DPW3_SPL5_DIR_S1 | PCD_DPW3_SPL5_DSCR_S1 | PCD_DPW3_SPL5_DCS_S1 | PCD_DPW3_SPL5_DSPC_S1 | PCD_DPW3_SPL5_DPP_S1 | PCD_DPW3_SPL5_DTPI_S1 | PCD_DPW3_SPL5_DCI_S1 | PCD_DPW3_SPL5_DSI_S1 | PCD_DPW3_SPL5_DER_S1 | PCD_DPW3_SPL5_RS_S1 | PCD_DPW3_SPL5_DPLE_S1
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 |  | PCD_DPW3_SPL5_DLY_S2 | PCD_DPW3_SPL5_DIR_S2 | PCD_DPW3_SPL5_DSCR_S2 | PCD_DPW3_SPL5_DCS_S2 | PCD_DPW3_SPL5_DSPC_S2 | PCD_DPW3_SPL5_DPP_S2 | PCD_DPW3_SPL5_DTPI_S2 | PCD_DPW3_SPL5_DCI_S2 | PCD_DPW3_SPL5_DSI_S2 | PCD_DPW3_SPL5_DER_S2 | PCD_DPW3_SPL5_RS_S2 | PCD_DPW3_SPL5_DPLE_S2
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 |  | PCD_DPW3_SPL5_DLY_S3 | PCD_DPW3_SPL5_DIR_S3 | PCD_DPW3_SPL5_DSCR_S3 | PCD_DPW3_SPL5_DCS_S3 | PCD_DPW3_SPL5_DSPC_S3 | PCD_DPW3_SPL5_DPP_S3 | PCD_DPW3_SPL5_DTPI_S3 | PCD_DPW3_SPL5_DCI_S3 | PCD_DPW3_SPL5_DSI_S3 | PCD_DPW3_SPL5_DER_S3 | PCD_DPW3_SPL5_RS_S3 | PCD_DPW3_SPL5_DPLE_S3
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 |  | PCD_DPW3_SPL5_DLY_S4 | PCD_DPW3_SPL5_DIR_S4 | PCD_DPW3_SPL5_DSCR_S4 | PCD_DPW3_SPL5_DCS_S4 | PCD_DPW3_SPL5_DSPC_S4 | PCD_DPW3_SPL5_DPP_S4 | PCD_DPW3_SPL5_DTPI_S4 | PCD_DPW3_SPL5_DCI_S4 | PCD_DPW3_SPL5_DSI_S4 | PCD_DPW3_SPL5_DER_S4 | PCD_DPW3_SPL5_RS_S4 | PCD_DPW3_SPL5_DPLE_S4
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 |  | PCD_DPW3_SPL5_DLY_S5 | PCD_DPW3_SPL5_DIR_S5 | PCD_DPW3_SPL5_DSCR_S5 | PCD_DPW3_SPL5_DCS_S5 | PCD_DPW3_SPL5_DSPC_S5 | PCD_DPW3_SPL5_DPP_S5 | PCD_DPW3_SPL5_DTPI_S5 | PCD_DPW3_SPL5_DCI_S5 | PCD_DPW3_SPL5_DSI_S5 | PCD_DPW3_SPL5_DER_S5 | PCD_DPW3_SPL5_RS_S5 | PCD_DPW3_SPL5_DPLE_S5
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 |  | PCD_DPW3_SPL5_DLY_S6 | PCD_DPW3_SPL5_DIR_S6 | PCD_DPW3_SPL5_DSCR_S6 | PCD_DPW3_SPL5_DCS_S6 | PCD_DPW3_SPL5_DSPC_S6 | PCD_DPW3_SPL5_DPP_S6 | PCD_DPW3_SPL5_DTPI_S6 | PCD_DPW3_SPL5_DCI_S6 | PCD_DPW3_SPL5_DSI_S6 | PCD_DPW3_SPL5_DER_S6 | PCD_DPW3_SPL5_RS_S6 | PCD_DPW3_SPL5_DPLE_S6
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 |  | PCD_DPW3_SPL5_DLY_S7 | PCD_DPW3_SPL5_DIR_S7 | PCD_DPW3_SPL5_DSCR_S7 | PCD_DPW3_SPL5_DCS_S7 | PCD_DPW3_SPL5_DSPC_S7 | PCD_DPW3_SPL5_DPP_S7 | PCD_DPW3_SPL5_DTPI_S7 | PCD_DPW3_SPL5_DCI_S7 | PCD_DPW3_SPL5_DSI_S7 | PCD_DPW3_SPL5_DER_S7 | PCD_DPW3_SPL5_RS_S7 | PCD_DPW3_SPL5_DPLE_S7
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST |  | PCD_DPW3_SPL5_DLY_ST | PCD_DPW3_SPL5_DIR_ST | PCD_DPW3_SPL5_DSCR_ST | PCD_DPW3_SPL5_DCS_ST | PCD_DPW3_SPL5_DSPC_ST | PCD_DPW3_SPL5_DPP_ST | PCD_DPW3_SPL5_DTPI_ST | PCD_DPW3_SPL5_DCI_ST | PCD_DPW3_SPL5_DSI_ST | PCD_DPW3_SPL5_DER_ST | PCD_DPW3_SPL5_RS_ST | PCD_DPW3_SPL5_DPLE_ST
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  | PCD_DPW3_SPLIN1_NR | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 |  | PCD_DPW3_SPLIN1_DLY | PCD_DPW3_SPLIN1_DIR | PCD_DPW3_SPLIN1_DSCR | PCD_DPW3_SPLIN1_DCS | PCD_DPW3_SPLIN1_DSPC | PCD_DPW3_SPLIN1_DPP | PCD_DPW3_SPLIN1_DTPI | PCD_DPW3_SPLIN1_DCI | PCD_DPW3_SPLIN1_DSI | PCD_DPW3_SPLIN1_DER | PCD_DPW3_SPLIN1_RS | PCD_DPW3_SPLIN1_DPLE
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 |  | PCD_DPW3_SPLIN1_DLY_S1 | PCD_DPW3_SPLIN1_DIR_S1 | PCD_DPW3_SPLIN1_DSCR_S1 | PCD_DPW3_SPLIN1_DCS_S1 | PCD_DPW3_SPLIN1_DSPC_S1 | PCD_DPW3_SPLIN1_DPP_S1 | PCD_DPW3_SPLIN1_DTPI_S1 | PCD_DPW3_SPLIN1_DCI_S1 | PCD_DPW3_SPLIN1_DSI_S1 | PCD_DPW3_SPLIN1_DER_S1 | PCD_DPW3_SPLIN1_RS_S1 | PCD_DPW3_SPLIN1_DPLE_S1
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 |  | PCD_DPW3_SPLIN1_DLY_S2 | PCD_DPW3_SPLIN1_DIR_S2 | PCD_DPW3_SPLIN1_DSCR_S2 | PCD_DPW3_SPLIN1_DCS_S2 | PCD_DPW3_SPLIN1_DSPC_S2 | PCD_DPW3_SPLIN1_DPP_S2 | PCD_DPW3_SPLIN1_DTPI_S2 | PCD_DPW3_SPLIN1_DCI_S2 | PCD_DPW3_SPLIN1_DSI_S2 | PCD_DPW3_SPLIN1_DER_S2 | PCD_DPW3_SPLIN1_RS_S2 | PCD_DPW3_SPLIN1_DPLE_S2
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 |  | PCD_DPW3_SPLIN1_DLY_S3 | PCD_DPW3_SPLIN1_DIR_S3 | PCD_DPW3_SPLIN1_DSCR_S3 | PCD_DPW3_SPLIN1_DCS_S3 | PCD_DPW3_SPLIN1_DSPC_S3 | PCD_DPW3_SPLIN1_DPP_S3 | PCD_DPW3_SPLIN1_DTPI_S3 | PCD_DPW3_SPLIN1_DCI_S3 | PCD_DPW3_SPLIN1_DSI_S3 | PCD_DPW3_SPLIN1_DER_S3 | PCD_DPW3_SPLIN1_RS_S3 | PCD_DPW3_SPLIN1_DPLE_S3
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 |  | PCD_DPW3_SPLIN1_DLY_S4 | PCD_DPW3_SPLIN1_DIR_S4 | PCD_DPW3_SPLIN1_DSCR_S4 | PCD_DPW3_SPLIN1_DCS_S4 | PCD_DPW3_SPLIN1_DSPC_S4 | PCD_DPW3_SPLIN1_DPP_S4 | PCD_DPW3_SPLIN1_DTPI_S4 | PCD_DPW3_SPLIN1_DCI_S4 | PCD_DPW3_SPLIN1_DSI_S4 | PCD_DPW3_SPLIN1_DER_S4 | PCD_DPW3_SPLIN1_RS_S4 | PCD_DPW3_SPLIN1_DPLE_S4
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 |  | PCD_DPW3_SPLIN1_DLY_S5 | PCD_DPW3_SPLIN1_DIR_S5 | PCD_DPW3_SPLIN1_DSCR_S5 | PCD_DPW3_SPLIN1_DCS_S5 | PCD_DPW3_SPLIN1_DSPC_S5 | PCD_DPW3_SPLIN1_DPP_S5 | PCD_DPW3_SPLIN1_DTPI_S5 | PCD_DPW3_SPLIN1_DCI_S5 | PCD_DPW3_SPLIN1_DSI_S5 | PCD_DPW3_SPLIN1_DER_S5 | PCD_DPW3_SPLIN1_RS_S5 | PCD_DPW3_SPLIN1_DPLE_S5
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 |  | PCD_DPW3_SPLIN1_DLY_S6 | PCD_DPW3_SPLIN1_DIR_S6 | PCD_DPW3_SPLIN1_DSCR_S6 | PCD_DPW3_SPLIN1_DCS_S6 | PCD_DPW3_SPLIN1_DSPC_S6 | PCD_DPW3_SPLIN1_DPP_S6 | PCD_DPW3_SPLIN1_DTPI_S6 | PCD_DPW3_SPLIN1_DCI_S6 | PCD_DPW3_SPLIN1_DSI_S6 | PCD_DPW3_SPLIN1_DER_S6 | PCD_DPW3_SPLIN1_RS_S6 | PCD_DPW3_SPLIN1_DPLE_S6
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 |  | PCD_DPW3_SPLIN1_DLY_S7 | PCD_DPW3_SPLIN1_DIR_S7 | PCD_DPW3_SPLIN1_DSCR_S7 | PCD_DPW3_SPLIN1_DCS_S7 | PCD_DPW3_SPLIN1_DSPC_S7 | PCD_DPW3_SPLIN1_DPP_S7 | PCD_DPW3_SPLIN1_DTPI_S7 | PCD_DPW3_SPLIN1_DCI_S7 | PCD_DPW3_SPLIN1_DSI_S7 | PCD_DPW3_SPLIN1_DER_S7 | PCD_DPW3_SPLIN1_RS_S7 | PCD_DPW3_SPLIN1_DPLE_S7
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST |  | PCD_DPW3_SPLIN1_DLY_ST | PCD_DPW3_SPLIN1_DIR_ST | PCD_DPW3_SPLIN1_DSCR_ST | PCD_DPW3_SPLIN1_DCS_ST | PCD_DPW3_SPLIN1_DSPC_ST | PCD_DPW3_SPLIN1_DPP_ST | PCD_DPW3_SPLIN1_DTPI_ST | PCD_DPW3_SPLIN1_DCI_ST | PCD_DPW3_SPLIN1_DSI_ST | PCD_DPW3_SPLIN1_DER_ST | PCD_DPW3_SPLIN1_RS_ST | PCD_DPW3_SPLIN1_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  | PCD_DPW3_RESIN1_NR | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 |  | PCD_DPW3_RESIN1_DLY | PCD_DPW3_RESIN1_DIR | PCD_DPW3_RESIN1_DSCR | PCD_DPW3_RESIN1_DCS | PCD_DPW3_RESIN1_DSPC | PCD_DPW3_RESIN1_DPP | PCD_DPW3_RESIN1_DTPI | PCD_DPW3_RESIN1_DCI | PCD_DPW3_RESIN1_DSI | PCD_DPW3_RESIN1_DER | PCD_DPW3_RESIN1_RS | PCD_DPW3_RESIN1_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 |  | PCD_DPW3_RESIN1_DLY_S1 | PCD_DPW3_RESIN1_DIR_S1 | PCD_DPW3_RESIN1_DSCR_S1 | PCD_DPW3_RESIN1_DCS_S1 | PCD_DPW3_RESIN1_DSPC_S1 | PCD_DPW3_RESIN1_DPP_S1 | PCD_DPW3_RESIN1_DTPI_S1 | PCD_DPW3_RESIN1_DCI_S1 | PCD_DPW3_RESIN1_DSI_S1 | PCD_DPW3_RESIN1_DER_S1 | PCD_DPW3_RESIN1_RS_S1 | PCD_DPW3_RESIN1_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 |  | PCD_DPW3_RESIN1_DLY_S2 | PCD_DPW3_RESIN1_DIR_S2 | PCD_DPW3_RESIN1_DSCR_S2 | PCD_DPW3_RESIN1_DCS_S2 | PCD_DPW3_RESIN1_DSPC_S2 | PCD_DPW3_RESIN1_DPP_S2 | PCD_DPW3_RESIN1_DTPI_S2 | PCD_DPW3_RESIN1_DCI_S2 | PCD_DPW3_RESIN1_DSI_S2 | PCD_DPW3_RESIN1_DER_S2 | PCD_DPW3_RESIN1_RS_S2 | PCD_DPW3_RESIN1_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 |  | PCD_DPW3_RESIN1_DLY_S3 | PCD_DPW3_RESIN1_DIR_S3 | PCD_DPW3_RESIN1_DSCR_S3 | PCD_DPW3_RESIN1_DCS_S3 | PCD_DPW3_RESIN1_DSPC_S3 | PCD_DPW3_RESIN1_DPP_S3 | PCD_DPW3_RESIN1_DTPI_S3 | PCD_DPW3_RESIN1_DCI_S3 | PCD_DPW3_RESIN1_DSI_S3 | PCD_DPW3_RESIN1_DER_S3 | PCD_DPW3_RESIN1_RS_S3 | PCD_DPW3_RESIN1_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 |  | PCD_DPW3_RESIN1_DLY_S4 | PCD_DPW3_RESIN1_DIR_S4 | PCD_DPW3_RESIN1_DSCR_S4 | PCD_DPW3_RESIN1_DCS_S4 | PCD_DPW3_RESIN1_DSPC_S4 | PCD_DPW3_RESIN1_DPP_S4 | PCD_DPW3_RESIN1_DTPI_S4 | PCD_DPW3_RESIN1_DCI_S4 | PCD_DPW3_RESIN1_DSI_S4 | PCD_DPW3_RESIN1_DER_S4 | PCD_DPW3_RESIN1_RS_S4 | PCD_DPW3_RESIN1_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 |  | PCD_DPW3_RESIN1_DLY_S5 | PCD_DPW3_RESIN1_DIR_S5 | PCD_DPW3_RESIN1_DSCR_S5 | PCD_DPW3_RESIN1_DCS_S5 | PCD_DPW3_RESIN1_DSPC_S5 | PCD_DPW3_RESIN1_DPP_S5 | PCD_DPW3_RESIN1_DTPI_S5 | PCD_DPW3_RESIN1_DCI_S5 | PCD_DPW3_RESIN1_DSI_S5 | PCD_DPW3_RESIN1_DER_S5 | PCD_DPW3_RESIN1_RS_S5 | PCD_DPW3_RESIN1_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 |  | PCD_DPW3_RESIN1_DLY_S6 | PCD_DPW3_RESIN1_DIR_S6 | PCD_DPW3_RESIN1_DSCR_S6 | PCD_DPW3_RESIN1_DCS_S6 | PCD_DPW3_RESIN1_DSPC_S6 | PCD_DPW3_RESIN1_DPP_S6 | PCD_DPW3_RESIN1_DTPI_S6 | PCD_DPW3_RESIN1_DCI_S6 | PCD_DPW3_RESIN1_DSI_S6 | PCD_DPW3_RESIN1_DER_S6 | PCD_DPW3_RESIN1_RS_S6 | PCD_DPW3_RESIN1_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 |  | PCD_DPW3_RESIN1_DLY_S7 | PCD_DPW3_RESIN1_DIR_S7 | PCD_DPW3_RESIN1_DSCR_S7 | PCD_DPW3_RESIN1_DCS_S7 | PCD_DPW3_RESIN1_DSPC_S7 | PCD_DPW3_RESIN1_DPP_S7 | PCD_DPW3_RESIN1_DTPI_S7 | PCD_DPW3_RESIN1_DCI_S7 | PCD_DPW3_RESIN1_DSI_S7 | PCD_DPW3_RESIN1_DER_S7 | PCD_DPW3_RESIN1_RS_S7 | PCD_DPW3_RESIN1_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST |  | PCD_DPW3_RESIN1_DLY_ST | PCD_DPW3_RESIN1_DIR_ST | PCD_DPW3_RESIN1_DSCR_ST | PCD_DPW3_RESIN1_DCS_ST | PCD_DPW3_RESIN1_DSPC_ST | PCD_DPW3_RESIN1_DPP_ST | PCD_DPW3_RESIN1_DTPI_ST | PCD_DPW3_RESIN1_DCI_ST | PCD_DPW3_RESIN1_DSI_ST | PCD_DPW3_RESIN1_DER_ST | PCD_DPW3_RESIN1_RS_ST | PCD_DPW3_RESIN1_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  | PCD_DPW3_RES1_NR | PCD_DPW3_RES1 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 |  | PCD_DPW3_RES1_DLY | PCD_DPW3_RES1_DIR | PCD_DPW3_RES1_DSCR | PCD_DPW3_RES1_DCS | PCD_DPW3_RES1_DSPC | PCD_DPW3_RES1_DPP | PCD_DPW3_RES1_DTPI | PCD_DPW3_RES1_DCI | PCD_DPW3_RES1_DSI | PCD_DPW3_RES1_DER | PCD_DPW3_RES1_RS | PCD_DPW3_RES1_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 |  | PCD_DPW3_RES1_DLY_S1 | PCD_DPW3_RES1_DIR_S1 | PCD_DPW3_RES1_DSCR_S1 | PCD_DPW3_RES1_DCS_S1 | PCD_DPW3_RES1_DSPC_S1 | PCD_DPW3_RES1_DPP_S1 | PCD_DPW3_RES1_DTPI_S1 | PCD_DPW3_RES1_DCI_S1 | PCD_DPW3_RES1_DSI_S1 | PCD_DPW3_RES1_DER_S1 | PCD_DPW3_RES1_RS_S1 | PCD_DPW3_RES1_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 |  | PCD_DPW3_RES1_DLY_S2 | PCD_DPW3_RES1_DIR_S2 | PCD_DPW3_RES1_DSCR_S2 | PCD_DPW3_RES1_DCS_S2 | PCD_DPW3_RES1_DSPC_S2 | PCD_DPW3_RES1_DPP_S2 | PCD_DPW3_RES1_DTPI_S2 | PCD_DPW3_RES1_DCI_S2 | PCD_DPW3_RES1_DSI_S2 | PCD_DPW3_RES1_DER_S2 | PCD_DPW3_RES1_RS_S2 | PCD_DPW3_RES1_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 |  | PCD_DPW3_RES1_DLY_S3 | PCD_DPW3_RES1_DIR_S3 | PCD_DPW3_RES1_DSCR_S3 | PCD_DPW3_RES1_DCS_S3 | PCD_DPW3_RES1_DSPC_S3 | PCD_DPW3_RES1_DPP_S3 | PCD_DPW3_RES1_DTPI_S3 | PCD_DPW3_RES1_DCI_S3 | PCD_DPW3_RES1_DSI_S3 | PCD_DPW3_RES1_DER_S3 | PCD_DPW3_RES1_RS_S3 | PCD_DPW3_RES1_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 |  | PCD_DPW3_RES1_DLY_S4 | PCD_DPW3_RES1_DIR_S4 | PCD_DPW3_RES1_DSCR_S4 | PCD_DPW3_RES1_DCS_S4 | PCD_DPW3_RES1_DSPC_S4 | PCD_DPW3_RES1_DPP_S4 | PCD_DPW3_RES1_DTPI_S4 | PCD_DPW3_RES1_DCI_S4 | PCD_DPW3_RES1_DSI_S4 | PCD_DPW3_RES1_DER_S4 | PCD_DPW3_RES1_RS_S4 | PCD_DPW3_RES1_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 |  | PCD_DPW3_RES1_DLY_S5 | PCD_DPW3_RES1_DIR_S5 | PCD_DPW3_RES1_DSCR_S5 | PCD_DPW3_RES1_DCS_S5 | PCD_DPW3_RES1_DSPC_S5 | PCD_DPW3_RES1_DPP_S5 | PCD_DPW3_RES1_DTPI_S5 | PCD_DPW3_RES1_DCI_S5 | PCD_DPW3_RES1_DSI_S5 | PCD_DPW3_RES1_DER_S5 | PCD_DPW3_RES1_RS_S5 | PCD_DPW3_RES1_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 |  | PCD_DPW3_RES1_DLY_S6 | PCD_DPW3_RES1_DIR_S6 | PCD_DPW3_RES1_DSCR_S6 | PCD_DPW3_RES1_DCS_S6 | PCD_DPW3_RES1_DSPC_S6 | PCD_DPW3_RES1_DPP_S6 | PCD_DPW3_RES1_DTPI_S6 | PCD_DPW3_RES1_DCI_S6 | PCD_DPW3_RES1_DSI_S6 | PCD_DPW3_RES1_DER_S6 | PCD_DPW3_RES1_RS_S6 | PCD_DPW3_RES1_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 |  | PCD_DPW3_RES1_DLY_S7 | PCD_DPW3_RES1_DIR_S7 | PCD_DPW3_RES1_DSCR_S7 | PCD_DPW3_RES1_DCS_S7 | PCD_DPW3_RES1_DSPC_S7 | PCD_DPW3_RES1_DPP_S7 | PCD_DPW3_RES1_DTPI_S7 | PCD_DPW3_RES1_DCI_S7 | PCD_DPW3_RES1_DSI_S7 | PCD_DPW3_RES1_DER_S7 | PCD_DPW3_RES1_RS_S7 | PCD_DPW3_RES1_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST |  | PCD_DPW3_RES1_DLY_ST | PCD_DPW3_RES1_DIR_ST | PCD_DPW3_RES1_DSCR_ST | PCD_DPW3_RES1_DCS_ST | PCD_DPW3_RES1_DSPC_ST | PCD_DPW3_RES1_DPP_ST | PCD_DPW3_RES1_DTPI_ST | PCD_DPW3_RES1_DCI_ST | PCD_DPW3_RES1_DSI_ST | PCD_DPW3_RES1_DER_ST | PCD_DPW3_RES1_RS_ST | PCD_DPW3_RES1_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  | PCD_DPW3_RES2_NR | PCD_DPW3_RES2 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 |  | PCD_DPW3_RES2_DLY | PCD_DPW3_RES2_DIR | PCD_DPW3_RES2_DSCR | PCD_DPW3_RES2_DCS | PCD_DPW3_RES2_DSPC | PCD_DPW3_RES2_DPP | PCD_DPW3_RES2_DTPI | PCD_DPW3_RES2_DCI | PCD_DPW3_RES2_DSI | PCD_DPW3_RES2_DER | PCD_DPW3_RES2_RS | PCD_DPW3_RES2_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 |  | PCD_DPW3_RES2_DLY_S1 | PCD_DPW3_RES2_DIR_S1 | PCD_DPW3_RES2_DSCR_S1 | PCD_DPW3_RES2_DCS_S1 | PCD_DPW3_RES2_DSPC_S1 | PCD_DPW3_RES2_DPP_S1 | PCD_DPW3_RES2_DTPI_S1 | PCD_DPW3_RES2_DCI_S1 | PCD_DPW3_RES2_DSI_S1 | PCD_DPW3_RES2_DER_S1 | PCD_DPW3_RES2_RS_S1 | PCD_DPW3_RES2_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 |  | PCD_DPW3_RES2_DLY_S2 | PCD_DPW3_RES2_DIR_S2 | PCD_DPW3_RES2_DSCR_S2 | PCD_DPW3_RES2_DCS_S2 | PCD_DPW3_RES2_DSPC_S2 | PCD_DPW3_RES2_DPP_S2 | PCD_DPW3_RES2_DTPI_S2 | PCD_DPW3_RES2_DCI_S2 | PCD_DPW3_RES2_DSI_S2 | PCD_DPW3_RES2_DER_S2 | PCD_DPW3_RES2_RS_S2 | PCD_DPW3_RES2_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 |  | PCD_DPW3_RES2_DLY_S3 | PCD_DPW3_RES2_DIR_S3 | PCD_DPW3_RES2_DSCR_S3 | PCD_DPW3_RES2_DCS_S3 | PCD_DPW3_RES2_DSPC_S3 | PCD_DPW3_RES2_DPP_S3 | PCD_DPW3_RES2_DTPI_S3 | PCD_DPW3_RES2_DCI_S3 | PCD_DPW3_RES2_DSI_S3 | PCD_DPW3_RES2_DER_S3 | PCD_DPW3_RES2_RS_S3 | PCD_DPW3_RES2_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 |  | PCD_DPW3_RES2_DLY_S4 | PCD_DPW3_RES2_DIR_S4 | PCD_DPW3_RES2_DSCR_S4 | PCD_DPW3_RES2_DCS_S4 | PCD_DPW3_RES2_DSPC_S4 | PCD_DPW3_RES2_DPP_S4 | PCD_DPW3_RES2_DTPI_S4 | PCD_DPW3_RES2_DCI_S4 | PCD_DPW3_RES2_DSI_S4 | PCD_DPW3_RES2_DER_S4 | PCD_DPW3_RES2_RS_S4 | PCD_DPW3_RES2_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 |  | PCD_DPW3_RES2_DLY_S5 | PCD_DPW3_RES2_DIR_S5 | PCD_DPW3_RES2_DSCR_S5 | PCD_DPW3_RES2_DCS_S5 | PCD_DPW3_RES2_DSPC_S5 | PCD_DPW3_RES2_DPP_S5 | PCD_DPW3_RES2_DTPI_S5 | PCD_DPW3_RES2_DCI_S5 | PCD_DPW3_RES2_DSI_S5 | PCD_DPW3_RES2_DER_S5 | PCD_DPW3_RES2_RS_S5 | PCD_DPW3_RES2_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 |  | PCD_DPW3_RES2_DLY_S6 | PCD_DPW3_RES2_DIR_S6 | PCD_DPW3_RES2_DSCR_S6 | PCD_DPW3_RES2_DCS_S6 | PCD_DPW3_RES2_DSPC_S6 | PCD_DPW3_RES2_DPP_S6 | PCD_DPW3_RES2_DTPI_S6 | PCD_DPW3_RES2_DCI_S6 | PCD_DPW3_RES2_DSI_S6 | PCD_DPW3_RES2_DER_S6 | PCD_DPW3_RES2_RS_S6 | PCD_DPW3_RES2_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 |  | PCD_DPW3_RES2_DLY_S7 | PCD_DPW3_RES2_DIR_S7 | PCD_DPW3_RES2_DSCR_S7 | PCD_DPW3_RES2_DCS_S7 | PCD_DPW3_RES2_DSPC_S7 | PCD_DPW3_RES2_DPP_S7 | PCD_DPW3_RES2_DTPI_S7 | PCD_DPW3_RES2_DCI_S7 | PCD_DPW3_RES2_DSI_S7 | PCD_DPW3_RES2_DER_S7 | PCD_DPW3_RES2_RS_S7 | PCD_DPW3_RES2_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST |  | PCD_DPW3_RES2_DLY_ST | PCD_DPW3_RES2_DIR_ST | PCD_DPW3_RES2_DSCR_ST | PCD_DPW3_RES2_DCS_ST | PCD_DPW3_RES2_DSPC_ST | PCD_DPW3_RES2_DPP_ST | PCD_DPW3_RES2_DTPI_ST | PCD_DPW3_RES2_DCI_ST | PCD_DPW3_RES2_DSI_ST | PCD_DPW3_RES2_DER_ST | PCD_DPW3_RES2_RS_ST | PCD_DPW3_RES2_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  | PCD_DPW3_RES3_NR | PCD_DPW3_RES3 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 |  | PCD_DPW3_RES3_DLY | PCD_DPW3_RES3_DIR | PCD_DPW3_RES3_DSCR | PCD_DPW3_RES3_DCS | PCD_DPW3_RES3_DSPC | PCD_DPW3_RES3_DPP | PCD_DPW3_RES3_DTPI | PCD_DPW3_RES3_DCI | PCD_DPW3_RES3_DSI | PCD_DPW3_RES3_DER | PCD_DPW3_RES3_RS | PCD_DPW3_RES3_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 |  | PCD_DPW3_RES3_DLY_S1 | PCD_DPW3_RES3_DIR_S1 | PCD_DPW3_RES3_DSCR_S1 | PCD_DPW3_RES3_DCS_S1 | PCD_DPW3_RES3_DSPC_S1 | PCD_DPW3_RES3_DPP_S1 | PCD_DPW3_RES3_DTPI_S1 | PCD_DPW3_RES3_DCI_S1 | PCD_DPW3_RES3_DSI_S1 | PCD_DPW3_RES3_DER_S1 | PCD_DPW3_RES3_RS_S1 | PCD_DPW3_RES3_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 |  | PCD_DPW3_RES3_DLY_S2 | PCD_DPW3_RES3_DIR_S2 | PCD_DPW3_RES3_DSCR_S2 | PCD_DPW3_RES3_DCS_S2 | PCD_DPW3_RES3_DSPC_S2 | PCD_DPW3_RES3_DPP_S2 | PCD_DPW3_RES3_DTPI_S2 | PCD_DPW3_RES3_DCI_S2 | PCD_DPW3_RES3_DSI_S2 | PCD_DPW3_RES3_DER_S2 | PCD_DPW3_RES3_RS_S2 | PCD_DPW3_RES3_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 |  | PCD_DPW3_RES3_DLY_S3 | PCD_DPW3_RES3_DIR_S3 | PCD_DPW3_RES3_DSCR_S3 | PCD_DPW3_RES3_DCS_S3 | PCD_DPW3_RES3_DSPC_S3 | PCD_DPW3_RES3_DPP_S3 | PCD_DPW3_RES3_DTPI_S3 | PCD_DPW3_RES3_DCI_S3 | PCD_DPW3_RES3_DSI_S3 | PCD_DPW3_RES3_DER_S3 | PCD_DPW3_RES3_RS_S3 | PCD_DPW3_RES3_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 |  | PCD_DPW3_RES3_DLY_S4 | PCD_DPW3_RES3_DIR_S4 | PCD_DPW3_RES3_DSCR_S4 | PCD_DPW3_RES3_DCS_S4 | PCD_DPW3_RES3_DSPC_S4 | PCD_DPW3_RES3_DPP_S4 | PCD_DPW3_RES3_DTPI_S4 | PCD_DPW3_RES3_DCI_S4 | PCD_DPW3_RES3_DSI_S4 | PCD_DPW3_RES3_DER_S4 | PCD_DPW3_RES3_RS_S4 | PCD_DPW3_RES3_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 |  | PCD_DPW3_RES3_DLY_S5 | PCD_DPW3_RES3_DIR_S5 | PCD_DPW3_RES3_DSCR_S5 | PCD_DPW3_RES3_DCS_S5 | PCD_DPW3_RES3_DSPC_S5 | PCD_DPW3_RES3_DPP_S5 | PCD_DPW3_RES3_DTPI_S5 | PCD_DPW3_RES3_DCI_S5 | PCD_DPW3_RES3_DSI_S5 | PCD_DPW3_RES3_DER_S5 | PCD_DPW3_RES3_RS_S5 | PCD_DPW3_RES3_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 |  | PCD_DPW3_RES3_DLY_S6 | PCD_DPW3_RES3_DIR_S6 | PCD_DPW3_RES3_DSCR_S6 | PCD_DPW3_RES3_DCS_S6 | PCD_DPW3_RES3_DSPC_S6 | PCD_DPW3_RES3_DPP_S6 | PCD_DPW3_RES3_DTPI_S6 | PCD_DPW3_RES3_DCI_S6 | PCD_DPW3_RES3_DSI_S6 | PCD_DPW3_RES3_DER_S6 | PCD_DPW3_RES3_RS_S6 | PCD_DPW3_RES3_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 |  | PCD_DPW3_RES3_DLY_S7 | PCD_DPW3_RES3_DIR_S7 | PCD_DPW3_RES3_DSCR_S7 | PCD_DPW3_RES3_DCS_S7 | PCD_DPW3_RES3_DSPC_S7 | PCD_DPW3_RES3_DPP_S7 | PCD_DPW3_RES3_DTPI_S7 | PCD_DPW3_RES3_DCI_S7 | PCD_DPW3_RES3_DSI_S7 | PCD_DPW3_RES3_DER_S7 | PCD_DPW3_RES3_RS_S7 | PCD_DPW3_RES3_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST |  | PCD_DPW3_RES3_DLY_ST | PCD_DPW3_RES3_DIR_ST | PCD_DPW3_RES3_DSCR_ST | PCD_DPW3_RES3_DCS_ST | PCD_DPW3_RES3_DSPC_ST | PCD_DPW3_RES3_DPP_ST | PCD_DPW3_RES3_DTPI_ST | PCD_DPW3_RES3_DCI_ST | PCD_DPW3_RES3_DSI_ST | PCD_DPW3_RES3_DER_ST | PCD_DPW3_RES3_RS_ST | PCD_DPW3_RES3_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  | PCD_DPW3_RES4_NR | PCD_DPW3_RES4 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 |  | PCD_DPW3_RES4_DLY | PCD_DPW3_RES4_DIR | PCD_DPW3_RES4_DSCR | PCD_DPW3_RES4_DCS | PCD_DPW3_RES4_DSPC | PCD_DPW3_RES4_DPP | PCD_DPW3_RES4_DTPI | PCD_DPW3_RES4_DCI | PCD_DPW3_RES4_DSI | PCD_DPW3_RES4_DER | PCD_DPW3_RES4_RS | PCD_DPW3_RES4_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 |  | PCD_DPW3_RES4_DLY_S1 | PCD_DPW3_RES4_DIR_S1 | PCD_DPW3_RES4_DSCR_S1 | PCD_DPW3_RES4_DCS_S1 | PCD_DPW3_RES4_DSPC_S1 | PCD_DPW3_RES4_DPP_S1 | PCD_DPW3_RES4_DTPI_S1 | PCD_DPW3_RES4_DCI_S1 | PCD_DPW3_RES4_DSI_S1 | PCD_DPW3_RES4_DER_S1 | PCD_DPW3_RES4_RS_S1 | PCD_DPW3_RES4_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 |  | PCD_DPW3_RES4_DLY_S2 | PCD_DPW3_RES4_DIR_S2 | PCD_DPW3_RES4_DSCR_S2 | PCD_DPW3_RES4_DCS_S2 | PCD_DPW3_RES4_DSPC_S2 | PCD_DPW3_RES4_DPP_S2 | PCD_DPW3_RES4_DTPI_S2 | PCD_DPW3_RES4_DCI_S2 | PCD_DPW3_RES4_DSI_S2 | PCD_DPW3_RES4_DER_S2 | PCD_DPW3_RES4_RS_S2 | PCD_DPW3_RES4_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 |  | PCD_DPW3_RES4_DLY_S3 | PCD_DPW3_RES4_DIR_S3 | PCD_DPW3_RES4_DSCR_S3 | PCD_DPW3_RES4_DCS_S3 | PCD_DPW3_RES4_DSPC_S3 | PCD_DPW3_RES4_DPP_S3 | PCD_DPW3_RES4_DTPI_S3 | PCD_DPW3_RES4_DCI_S3 | PCD_DPW3_RES4_DSI_S3 | PCD_DPW3_RES4_DER_S3 | PCD_DPW3_RES4_RS_S3 | PCD_DPW3_RES4_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 |  | PCD_DPW3_RES4_DLY_S4 | PCD_DPW3_RES4_DIR_S4 | PCD_DPW3_RES4_DSCR_S4 | PCD_DPW3_RES4_DCS_S4 | PCD_DPW3_RES4_DSPC_S4 | PCD_DPW3_RES4_DPP_S4 | PCD_DPW3_RES4_DTPI_S4 | PCD_DPW3_RES4_DCI_S4 | PCD_DPW3_RES4_DSI_S4 | PCD_DPW3_RES4_DER_S4 | PCD_DPW3_RES4_RS_S4 | PCD_DPW3_RES4_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 |  | PCD_DPW3_RES4_DLY_S5 | PCD_DPW3_RES4_DIR_S5 | PCD_DPW3_RES4_DSCR_S5 | PCD_DPW3_RES4_DCS_S5 | PCD_DPW3_RES4_DSPC_S5 | PCD_DPW3_RES4_DPP_S5 | PCD_DPW3_RES4_DTPI_S5 | PCD_DPW3_RES4_DCI_S5 | PCD_DPW3_RES4_DSI_S5 | PCD_DPW3_RES4_DER_S5 | PCD_DPW3_RES4_RS_S5 | PCD_DPW3_RES4_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 |  | PCD_DPW3_RES4_DLY_S6 | PCD_DPW3_RES4_DIR_S6 | PCD_DPW3_RES4_DSCR_S6 | PCD_DPW3_RES4_DCS_S6 | PCD_DPW3_RES4_DSPC_S6 | PCD_DPW3_RES4_DPP_S6 | PCD_DPW3_RES4_DTPI_S6 | PCD_DPW3_RES4_DCI_S6 | PCD_DPW3_RES4_DSI_S6 | PCD_DPW3_RES4_DER_S6 | PCD_DPW3_RES4_RS_S6 | PCD_DPW3_RES4_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 |  | PCD_DPW3_RES4_DLY_S7 | PCD_DPW3_RES4_DIR_S7 | PCD_DPW3_RES4_DSCR_S7 | PCD_DPW3_RES4_DCS_S7 | PCD_DPW3_RES4_DSPC_S7 | PCD_DPW3_RES4_DPP_S7 | PCD_DPW3_RES4_DTPI_S7 | PCD_DPW3_RES4_DCI_S7 | PCD_DPW3_RES4_DSI_S7 | PCD_DPW3_RES4_DER_S7 | PCD_DPW3_RES4_RS_S7 | PCD_DPW3_RES4_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST |  | PCD_DPW3_RES4_DLY_ST | PCD_DPW3_RES4_DIR_ST | PCD_DPW3_RES4_DSCR_ST | PCD_DPW3_RES4_DCS_ST | PCD_DPW3_RES4_DSPC_ST | PCD_DPW3_RES4_DPP_ST | PCD_DPW3_RES4_DTPI_ST | PCD_DPW3_RES4_DCI_ST | PCD_DPW3_RES4_DSI_ST | PCD_DPW3_RES4_DER_ST | PCD_DPW3_RES4_RS_ST | PCD_DPW3_RES4_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  | PCD_DPW3_RES5_NR | PCD_DPW3_RES5 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 |  | PCD_DPW3_RES5_DLY | PCD_DPW3_RES5_DIR | PCD_DPW3_RES5_DSCR | PCD_DPW3_RES5_DCS | PCD_DPW3_RES5_DSPC | PCD_DPW3_RES5_DPP | PCD_DPW3_RES5_DTPI | PCD_DPW3_RES5_DCI | PCD_DPW3_RES5_DSI | PCD_DPW3_RES5_DER | PCD_DPW3_RES5_RS | PCD_DPW3_RES5_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 |  | PCD_DPW3_RES5_DLY_S1 | PCD_DPW3_RES5_DIR_S1 | PCD_DPW3_RES5_DSCR_S1 | PCD_DPW3_RES5_DCS_S1 | PCD_DPW3_RES5_DSPC_S1 | PCD_DPW3_RES5_DPP_S1 | PCD_DPW3_RES5_DTPI_S1 | PCD_DPW3_RES5_DCI_S1 | PCD_DPW3_RES5_DSI_S1 | PCD_DPW3_RES5_DER_S1 | PCD_DPW3_RES5_RS_S1 | PCD_DPW3_RES5_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 |  | PCD_DPW3_RES5_DLY_S2 | PCD_DPW3_RES5_DIR_S2 | PCD_DPW3_RES5_DSCR_S2 | PCD_DPW3_RES5_DCS_S2 | PCD_DPW3_RES5_DSPC_S2 | PCD_DPW3_RES5_DPP_S2 | PCD_DPW3_RES5_DTPI_S2 | PCD_DPW3_RES5_DCI_S2 | PCD_DPW3_RES5_DSI_S2 | PCD_DPW3_RES5_DER_S2 | PCD_DPW3_RES5_RS_S2 | PCD_DPW3_RES5_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 |  | PCD_DPW3_RES5_DLY_S3 | PCD_DPW3_RES5_DIR_S3 | PCD_DPW3_RES5_DSCR_S3 | PCD_DPW3_RES5_DCS_S3 | PCD_DPW3_RES5_DSPC_S3 | PCD_DPW3_RES5_DPP_S3 | PCD_DPW3_RES5_DTPI_S3 | PCD_DPW3_RES5_DCI_S3 | PCD_DPW3_RES5_DSI_S3 | PCD_DPW3_RES5_DER_S3 | PCD_DPW3_RES5_RS_S3 | PCD_DPW3_RES5_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 |  | PCD_DPW3_RES5_DLY_S4 | PCD_DPW3_RES5_DIR_S4 | PCD_DPW3_RES5_DSCR_S4 | PCD_DPW3_RES5_DCS_S4 | PCD_DPW3_RES5_DSPC_S4 | PCD_DPW3_RES5_DPP_S4 | PCD_DPW3_RES5_DTPI_S4 | PCD_DPW3_RES5_DCI_S4 | PCD_DPW3_RES5_DSI_S4 | PCD_DPW3_RES5_DER_S4 | PCD_DPW3_RES5_RS_S4 | PCD_DPW3_RES5_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 |  | PCD_DPW3_RES5_DLY_S5 | PCD_DPW3_RES5_DIR_S5 | PCD_DPW3_RES5_DSCR_S5 | PCD_DPW3_RES5_DCS_S5 | PCD_DPW3_RES5_DSPC_S5 | PCD_DPW3_RES5_DPP_S5 | PCD_DPW3_RES5_DTPI_S5 | PCD_DPW3_RES5_DCI_S5 | PCD_DPW3_RES5_DSI_S5 | PCD_DPW3_RES5_DER_S5 | PCD_DPW3_RES5_RS_S5 | PCD_DPW3_RES5_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 |  | PCD_DPW3_RES5_DLY_S6 | PCD_DPW3_RES5_DIR_S6 | PCD_DPW3_RES5_DSCR_S6 | PCD_DPW3_RES5_DCS_S6 | PCD_DPW3_RES5_DSPC_S6 | PCD_DPW3_RES5_DPP_S6 | PCD_DPW3_RES5_DTPI_S6 | PCD_DPW3_RES5_DCI_S6 | PCD_DPW3_RES5_DSI_S6 | PCD_DPW3_RES5_DER_S6 | PCD_DPW3_RES5_RS_S6 | PCD_DPW3_RES5_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 |  | PCD_DPW3_RES5_DLY_S7 | PCD_DPW3_RES5_DIR_S7 | PCD_DPW3_RES5_DSCR_S7 | PCD_DPW3_RES5_DCS_S7 | PCD_DPW3_RES5_DSPC_S7 | PCD_DPW3_RES5_DPP_S7 | PCD_DPW3_RES5_DTPI_S7 | PCD_DPW3_RES5_DCI_S7 | PCD_DPW3_RES5_DSI_S7 | PCD_DPW3_RES5_DER_S7 | PCD_DPW3_RES5_RS_S7 | PCD_DPW3_RES5_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST |  | PCD_DPW3_RES5_DLY_ST | PCD_DPW3_RES5_DIR_ST | PCD_DPW3_RES5_DSCR_ST | PCD_DPW3_RES5_DCS_ST | PCD_DPW3_RES5_DSPC_ST | PCD_DPW3_RES5_DPP_ST | PCD_DPW3_RES5_DTPI_ST | PCD_DPW3_RES5_DCI_ST | PCD_DPW3_RES5_DSI_ST | PCD_DPW3_RES5_DER_ST | PCD_DPW3_RES5_RS_ST | PCD_DPW3_RES5_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  | PCD_DPW3_RES6_NR | PCD_DPW3_RES6 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 |  | PCD_DPW3_RES6_DLY | PCD_DPW3_RES6_DIR | PCD_DPW3_RES6_DSCR | PCD_DPW3_RES6_DCS | PCD_DPW3_RES6_DSPC | PCD_DPW3_RES6_DPP | PCD_DPW3_RES6_DTPI | PCD_DPW3_RES6_DCI | PCD_DPW3_RES6_DSI | PCD_DPW3_RES6_DER | PCD_DPW3_RES6_RS | PCD_DPW3_RES6_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 |  | PCD_DPW3_RES6_DLY_S1 | PCD_DPW3_RES6_DIR_S1 | PCD_DPW3_RES6_DSCR_S1 | PCD_DPW3_RES6_DCS_S1 | PCD_DPW3_RES6_DSPC_S1 | PCD_DPW3_RES6_DPP_S1 | PCD_DPW3_RES6_DTPI_S1 | PCD_DPW3_RES6_DCI_S1 | PCD_DPW3_RES6_DSI_S1 | PCD_DPW3_RES6_DER_S1 | PCD_DPW3_RES6_RS_S1 | PCD_DPW3_RES6_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 |  | PCD_DPW3_RES6_DLY_S2 | PCD_DPW3_RES6_DIR_S2 | PCD_DPW3_RES6_DSCR_S2 | PCD_DPW3_RES6_DCS_S2 | PCD_DPW3_RES6_DSPC_S2 | PCD_DPW3_RES6_DPP_S2 | PCD_DPW3_RES6_DTPI_S2 | PCD_DPW3_RES6_DCI_S2 | PCD_DPW3_RES6_DSI_S2 | PCD_DPW3_RES6_DER_S2 | PCD_DPW3_RES6_RS_S2 | PCD_DPW3_RES6_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 |  | PCD_DPW3_RES6_DLY_S3 | PCD_DPW3_RES6_DIR_S3 | PCD_DPW3_RES6_DSCR_S3 | PCD_DPW3_RES6_DCS_S3 | PCD_DPW3_RES6_DSPC_S3 | PCD_DPW3_RES6_DPP_S3 | PCD_DPW3_RES6_DTPI_S3 | PCD_DPW3_RES6_DCI_S3 | PCD_DPW3_RES6_DSI_S3 | PCD_DPW3_RES6_DER_S3 | PCD_DPW3_RES6_RS_S3 | PCD_DPW3_RES6_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 |  | PCD_DPW3_RES6_DLY_S4 | PCD_DPW3_RES6_DIR_S4 | PCD_DPW3_RES6_DSCR_S4 | PCD_DPW3_RES6_DCS_S4 | PCD_DPW3_RES6_DSPC_S4 | PCD_DPW3_RES6_DPP_S4 | PCD_DPW3_RES6_DTPI_S4 | PCD_DPW3_RES6_DCI_S4 | PCD_DPW3_RES6_DSI_S4 | PCD_DPW3_RES6_DER_S4 | PCD_DPW3_RES6_RS_S4 | PCD_DPW3_RES6_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 |  | PCD_DPW3_RES6_DLY_S5 | PCD_DPW3_RES6_DIR_S5 | PCD_DPW3_RES6_DSCR_S5 | PCD_DPW3_RES6_DCS_S5 | PCD_DPW3_RES6_DSPC_S5 | PCD_DPW3_RES6_DPP_S5 | PCD_DPW3_RES6_DTPI_S5 | PCD_DPW3_RES6_DCI_S5 | PCD_DPW3_RES6_DSI_S5 | PCD_DPW3_RES6_DER_S5 | PCD_DPW3_RES6_RS_S5 | PCD_DPW3_RES6_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 |  | PCD_DPW3_RES6_DLY_S6 | PCD_DPW3_RES6_DIR_S6 | PCD_DPW3_RES6_DSCR_S6 | PCD_DPW3_RES6_DCS_S6 | PCD_DPW3_RES6_DSPC_S6 | PCD_DPW3_RES6_DPP_S6 | PCD_DPW3_RES6_DTPI_S6 | PCD_DPW3_RES6_DCI_S6 | PCD_DPW3_RES6_DSI_S6 | PCD_DPW3_RES6_DER_S6 | PCD_DPW3_RES6_RS_S6 | PCD_DPW3_RES6_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 |  | PCD_DPW3_RES6_DLY_S7 | PCD_DPW3_RES6_DIR_S7 | PCD_DPW3_RES6_DSCR_S7 | PCD_DPW3_RES6_DCS_S7 | PCD_DPW3_RES6_DSPC_S7 | PCD_DPW3_RES6_DPP_S7 | PCD_DPW3_RES6_DTPI_S7 | PCD_DPW3_RES6_DCI_S7 | PCD_DPW3_RES6_DSI_S7 | PCD_DPW3_RES6_DER_S7 | PCD_DPW3_RES6_RS_S7 | PCD_DPW3_RES6_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST |  | PCD_DPW3_RES6_DLY_ST | PCD_DPW3_RES6_DIR_ST | PCD_DPW3_RES6_DSCR_ST | PCD_DPW3_RES6_DCS_ST | PCD_DPW3_RES6_DSPC_ST | PCD_DPW3_RES6_DPP_ST | PCD_DPW3_RES6_DTPI_ST | PCD_DPW3_RES6_DCI_ST | PCD_DPW3_RES6_DSI_ST | PCD_DPW3_RES6_DER_ST | PCD_DPW3_RES6_RS_ST | PCD_DPW3_RES6_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  | PCD_DPW3_RES7_NR | PCD_DPW3_RES7 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 |  | PCD_DPW3_RES7_DLY | PCD_DPW3_RES7_DIR | PCD_DPW3_RES7_DSCR | PCD_DPW3_RES7_DCS | PCD_DPW3_RES7_DSPC | PCD_DPW3_RES7_DPP | PCD_DPW3_RES7_DTPI | PCD_DPW3_RES7_DCI | PCD_DPW3_RES7_DSI | PCD_DPW3_RES7_DER | PCD_DPW3_RES7_RS | PCD_DPW3_RES7_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 |  | PCD_DPW3_RES7_DLY_S1 | PCD_DPW3_RES7_DIR_S1 | PCD_DPW3_RES7_DSCR_S1 | PCD_DPW3_RES7_DCS_S1 | PCD_DPW3_RES7_DSPC_S1 | PCD_DPW3_RES7_DPP_S1 | PCD_DPW3_RES7_DTPI_S1 | PCD_DPW3_RES7_DCI_S1 | PCD_DPW3_RES7_DSI_S1 | PCD_DPW3_RES7_DER_S1 | PCD_DPW3_RES7_RS_S1 | PCD_DPW3_RES7_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 |  | PCD_DPW3_RES7_DLY_S2 | PCD_DPW3_RES7_DIR_S2 | PCD_DPW3_RES7_DSCR_S2 | PCD_DPW3_RES7_DCS_S2 | PCD_DPW3_RES7_DSPC_S2 | PCD_DPW3_RES7_DPP_S2 | PCD_DPW3_RES7_DTPI_S2 | PCD_DPW3_RES7_DCI_S2 | PCD_DPW3_RES7_DSI_S2 | PCD_DPW3_RES7_DER_S2 | PCD_DPW3_RES7_RS_S2 | PCD_DPW3_RES7_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 |  | PCD_DPW3_RES7_DLY_S3 | PCD_DPW3_RES7_DIR_S3 | PCD_DPW3_RES7_DSCR_S3 | PCD_DPW3_RES7_DCS_S3 | PCD_DPW3_RES7_DSPC_S3 | PCD_DPW3_RES7_DPP_S3 | PCD_DPW3_RES7_DTPI_S3 | PCD_DPW3_RES7_DCI_S3 | PCD_DPW3_RES7_DSI_S3 | PCD_DPW3_RES7_DER_S3 | PCD_DPW3_RES7_RS_S3 | PCD_DPW3_RES7_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 |  | PCD_DPW3_RES7_DLY_S4 | PCD_DPW3_RES7_DIR_S4 | PCD_DPW3_RES7_DSCR_S4 | PCD_DPW3_RES7_DCS_S4 | PCD_DPW3_RES7_DSPC_S4 | PCD_DPW3_RES7_DPP_S4 | PCD_DPW3_RES7_DTPI_S4 | PCD_DPW3_RES7_DCI_S4 | PCD_DPW3_RES7_DSI_S4 | PCD_DPW3_RES7_DER_S4 | PCD_DPW3_RES7_RS_S4 | PCD_DPW3_RES7_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 |  | PCD_DPW3_RES7_DLY_S5 | PCD_DPW3_RES7_DIR_S5 | PCD_DPW3_RES7_DSCR_S5 | PCD_DPW3_RES7_DCS_S5 | PCD_DPW3_RES7_DSPC_S5 | PCD_DPW3_RES7_DPP_S5 | PCD_DPW3_RES7_DTPI_S5 | PCD_DPW3_RES7_DCI_S5 | PCD_DPW3_RES7_DSI_S5 | PCD_DPW3_RES7_DER_S5 | PCD_DPW3_RES7_RS_S5 | PCD_DPW3_RES7_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 |  | PCD_DPW3_RES7_DLY_S6 | PCD_DPW3_RES7_DIR_S6 | PCD_DPW3_RES7_DSCR_S6 | PCD_DPW3_RES7_DCS_S6 | PCD_DPW3_RES7_DSPC_S6 | PCD_DPW3_RES7_DPP_S6 | PCD_DPW3_RES7_DTPI_S6 | PCD_DPW3_RES7_DCI_S6 | PCD_DPW3_RES7_DSI_S6 | PCD_DPW3_RES7_DER_S6 | PCD_DPW3_RES7_RS_S6 | PCD_DPW3_RES7_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 |  | PCD_DPW3_RES7_DLY_S7 | PCD_DPW3_RES7_DIR_S7 | PCD_DPW3_RES7_DSCR_S7 | PCD_DPW3_RES7_DCS_S7 | PCD_DPW3_RES7_DSPC_S7 | PCD_DPW3_RES7_DPP_S7 | PCD_DPW3_RES7_DTPI_S7 | PCD_DPW3_RES7_DCI_S7 | PCD_DPW3_RES7_DSI_S7 | PCD_DPW3_RES7_DER_S7 | PCD_DPW3_RES7_RS_S7 | PCD_DPW3_RES7_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST |  | PCD_DPW3_RES7_DLY_ST | PCD_DPW3_RES7_DIR_ST | PCD_DPW3_RES7_DSCR_ST | PCD_DPW3_RES7_DCS_ST | PCD_DPW3_RES7_DSPC_ST | PCD_DPW3_RES7_DPP_ST | PCD_DPW3_RES7_DTPI_ST | PCD_DPW3_RES7_DCI_ST | PCD_DPW3_RES7_DSI_ST | PCD_DPW3_RES7_DER_ST | PCD_DPW3_RES7_RS_ST | PCD_DPW3_RES7_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 0 | Nr | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  | PCD_DPW3_CYBR_NR | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 |  | PCD_DPW3_CYBR_DLY | PCD_DPW3_CYBR_DIR | PCD_DPW3_CYBR_DSCR | PCD_DPW3_CYBR_DCS | PCD_DPW3_CYBR_DSPC | PCD_DPW3_CYBR_DPP | PCD_DPW3_CYBR_DTPI | PCD_DPW3_CYBR_DCI | PCD_DPW3_CYBR_DSI | PCD_DPW3_CYBR_DER | PCD_DPW3_CYBR_RS | PCD_DPW3_CYBR_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 |  | PCD_DPW3_CYBR_DLY_S1 | PCD_DPW3_CYBR_DIR_S1 | PCD_DPW3_CYBR_DSCR_S1 | PCD_DPW3_CYBR_DCS_S1 | PCD_DPW3_CYBR_DSPC_S1 | PCD_DPW3_CYBR_DPP_S1 | PCD_DPW3_CYBR_DTPI_S1 | PCD_DPW3_CYBR_DCI_S1 | PCD_DPW3_CYBR_DSI_S1 | PCD_DPW3_CYBR_DER_S1 | PCD_DPW3_CYBR_RS_S1 | PCD_DPW3_CYBR_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 |  | PCD_DPW3_CYBR_DLY_S2 | PCD_DPW3_CYBR_DIR_S2 | PCD_DPW3_CYBR_DSCR_S2 | PCD_DPW3_CYBR_DCS_S2 | PCD_DPW3_CYBR_DSPC_S2 | PCD_DPW3_CYBR_DPP_S2 | PCD_DPW3_CYBR_DTPI_S2 | PCD_DPW3_CYBR_DCI_S2 | PCD_DPW3_CYBR_DSI_S2 | PCD_DPW3_CYBR_DER_S2 | PCD_DPW3_CYBR_RS_S2 | PCD_DPW3_CYBR_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 |  | PCD_DPW3_CYBR_DLY_S3 | PCD_DPW3_CYBR_DIR_S3 | PCD_DPW3_CYBR_DSCR_S3 | PCD_DPW3_CYBR_DCS_S3 | PCD_DPW3_CYBR_DSPC_S3 | PCD_DPW3_CYBR_DPP_S3 | PCD_DPW3_CYBR_DTPI_S3 | PCD_DPW3_CYBR_DCI_S3 | PCD_DPW3_CYBR_DSI_S3 | PCD_DPW3_CYBR_DER_S3 | PCD_DPW3_CYBR_RS_S3 | PCD_DPW3_CYBR_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 |  | PCD_DPW3_CYBR_DLY_S4 | PCD_DPW3_CYBR_DIR_S4 | PCD_DPW3_CYBR_DSCR_S4 | PCD_DPW3_CYBR_DCS_S4 | PCD_DPW3_CYBR_DSPC_S4 | PCD_DPW3_CYBR_DPP_S4 | PCD_DPW3_CYBR_DTPI_S4 | PCD_DPW3_CYBR_DCI_S4 | PCD_DPW3_CYBR_DSI_S4 | PCD_DPW3_CYBR_DER_S4 | PCD_DPW3_CYBR_RS_S4 | PCD_DPW3_CYBR_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 |  | PCD_DPW3_CYBR_DLY_S5 | PCD_DPW3_CYBR_DIR_S5 | PCD_DPW3_CYBR_DSCR_S5 | PCD_DPW3_CYBR_DCS_S5 | PCD_DPW3_CYBR_DSPC_S5 | PCD_DPW3_CYBR_DPP_S5 | PCD_DPW3_CYBR_DTPI_S5 | PCD_DPW3_CYBR_DCI_S5 | PCD_DPW3_CYBR_DSI_S5 | PCD_DPW3_CYBR_DER_S5 | PCD_DPW3_CYBR_RS_S5 | PCD_DPW3_CYBR_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 |  | PCD_DPW3_CYBR_DLY_S6 | PCD_DPW3_CYBR_DIR_S6 | PCD_DPW3_CYBR_DSCR_S6 | PCD_DPW3_CYBR_DCS_S6 | PCD_DPW3_CYBR_DSPC_S6 | PCD_DPW3_CYBR_DPP_S6 | PCD_DPW3_CYBR_DTPI_S6 | PCD_DPW3_CYBR_DCI_S6 | PCD_DPW3_CYBR_DSI_S6 | PCD_DPW3_CYBR_DER_S6 | PCD_DPW3_CYBR_RS_S6 | PCD_DPW3_CYBR_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 |  | PCD_DPW3_CYBR_DLY_S7 | PCD_DPW3_CYBR_DIR_S7 | PCD_DPW3_CYBR_DSCR_S7 | PCD_DPW3_CYBR_DCS_S7 | PCD_DPW3_CYBR_DSPC_S7 | PCD_DPW3_CYBR_DPP_S7 | PCD_DPW3_CYBR_DTPI_S7 | PCD_DPW3_CYBR_DCI_S7 | PCD_DPW3_CYBR_DSI_S7 | PCD_DPW3_CYBR_DER_S7 | PCD_DPW3_CYBR_RS_S7 | PCD_DPW3_CYBR_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST |  | PCD_DPW3_CYBR_DLY_ST | PCD_DPW3_CYBR_DIR_ST | PCD_DPW3_CYBR_DSCR_ST | PCD_DPW3_CYBR_DCS_ST | PCD_DPW3_CYBR_DSPC_ST | PCD_DPW3_CYBR_DPP_ST | PCD_DPW3_CYBR_DTPI_ST | PCD_DPW3_CYBR_DCI_ST | PCD_DPW3_CYBR_DSI_ST | PCD_DPW3_CYBR_DER_ST | PCD_DPW3_CYBR_RS_ST | PCD_DPW3_CYBR_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 0 | Nr | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.15 |  | PCD_DPW3_SEMD_NR | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 |  | PCD_DPW3_SEMD_DLY | PCD_DPW3_SEMD_DIR | PCD_DPW3_SEMD_DSCR | PCD_DPW3_SEMD_DCS | PCD_DPW3_SEMD_DSPC | PCD_DPW3_SEMD_DPP | PCD_DPW3_SEMD_DTPI | PCD_DPW3_SEMD_DCI | PCD_DPW3_SEMD_DSI | PCD_DPW3_SEMD_DER | PCD_DPW3_SEMD_RS | PCD_DPW3_SEMD_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 |  | PCD_DPW3_SEMD_DLY_S1 | PCD_DPW3_SEMD_DIR_S1 | PCD_DPW3_SEMD_DSCR_S1 | PCD_DPW3_SEMD_DCS_S1 | PCD_DPW3_SEMD_DSPC_S1 | PCD_DPW3_SEMD_DPP_S1 | PCD_DPW3_SEMD_DTPI_S1 | PCD_DPW3_SEMD_DCI_S1 | PCD_DPW3_SEMD_DSI_S1 | PCD_DPW3_SEMD_DER_S1 | PCD_DPW3_SEMD_RS_S1 | PCD_DPW3_SEMD_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 |  | PCD_DPW3_SEMD_DLY_S2 | PCD_DPW3_SEMD_DIR_S2 | PCD_DPW3_SEMD_DSCR_S2 | PCD_DPW3_SEMD_DCS_S2 | PCD_DPW3_SEMD_DSPC_S2 | PCD_DPW3_SEMD_DPP_S2 | PCD_DPW3_SEMD_DTPI_S2 | PCD_DPW3_SEMD_DCI_S2 | PCD_DPW3_SEMD_DSI_S2 | PCD_DPW3_SEMD_DER_S2 | PCD_DPW3_SEMD_RS_S2 | PCD_DPW3_SEMD_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 |  | PCD_DPW3_SEMD_DLY_S3 | PCD_DPW3_SEMD_DIR_S3 | PCD_DPW3_SEMD_DSCR_S3 | PCD_DPW3_SEMD_DCS_S3 | PCD_DPW3_SEMD_DSPC_S3 | PCD_DPW3_SEMD_DPP_S3 | PCD_DPW3_SEMD_DTPI_S3 | PCD_DPW3_SEMD_DCI_S3 | PCD_DPW3_SEMD_DSI_S3 | PCD_DPW3_SEMD_DER_S3 | PCD_DPW3_SEMD_RS_S3 | PCD_DPW3_SEMD_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 |  | PCD_DPW3_SEMD_DLY_S4 | PCD_DPW3_SEMD_DIR_S4 | PCD_DPW3_SEMD_DSCR_S4 | PCD_DPW3_SEMD_DCS_S4 | PCD_DPW3_SEMD_DSPC_S4 | PCD_DPW3_SEMD_DPP_S4 | PCD_DPW3_SEMD_DTPI_S4 | PCD_DPW3_SEMD_DCI_S4 | PCD_DPW3_SEMD_DSI_S4 | PCD_DPW3_SEMD_DER_S4 | PCD_DPW3_SEMD_RS_S4 | PCD_DPW3_SEMD_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 |  | PCD_DPW3_SEMD_DLY_S5 | PCD_DPW3_SEMD_DIR_S5 | PCD_DPW3_SEMD_DSCR_S5 | PCD_DPW3_SEMD_DCS_S5 | PCD_DPW3_SEMD_DSPC_S5 | PCD_DPW3_SEMD_DPP_S5 | PCD_DPW3_SEMD_DTPI_S5 | PCD_DPW3_SEMD_DCI_S5 | PCD_DPW3_SEMD_DSI_S5 | PCD_DPW3_SEMD_DER_S5 | PCD_DPW3_SEMD_RS_S5 | PCD_DPW3_SEMD_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 |  | PCD_DPW3_SEMD_DLY_S6 | PCD_DPW3_SEMD_DIR_S6 | PCD_DPW3_SEMD_DSCR_S6 | PCD_DPW3_SEMD_DCS_S6 | PCD_DPW3_SEMD_DSPC_S6 | PCD_DPW3_SEMD_DPP_S6 | PCD_DPW3_SEMD_DTPI_S6 | PCD_DPW3_SEMD_DCI_S6 | PCD_DPW3_SEMD_DSI_S6 | PCD_DPW3_SEMD_DER_S6 | PCD_DPW3_SEMD_RS_S6 | PCD_DPW3_SEMD_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 |  | PCD_DPW3_SEMD_DLY_S7 | PCD_DPW3_SEMD_DIR_S7 | PCD_DPW3_SEMD_DSCR_S7 | PCD_DPW3_SEMD_DCS_S7 | PCD_DPW3_SEMD_DSPC_S7 | PCD_DPW3_SEMD_DPP_S7 | PCD_DPW3_SEMD_DTPI_S7 | PCD_DPW3_SEMD_DCI_S7 | PCD_DPW3_SEMD_DSI_S7 | PCD_DPW3_SEMD_DER_S7 | PCD_DPW3_SEMD_RS_S7 | PCD_DPW3_SEMD_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST |  | PCD_DPW3_SEMD_DLY_ST | PCD_DPW3_SEMD_DIR_ST | PCD_DPW3_SEMD_DSCR_ST | PCD_DPW3_SEMD_DCS_ST | PCD_DPW3_SEMD_DSPC_ST | PCD_DPW3_SEMD_DPP_ST | PCD_DPW3_SEMD_DTPI_ST | PCD_DPW3_SEMD_DCI_ST | PCD_DPW3_SEMD_DSI_ST | PCD_DPW3_SEMD_DER_ST | PCD_DPW3_SEMD_RS_ST | PCD_DPW3_SEMD_DPLE_ST
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  | PCD_DPW3_GGR_NR | PCD_DPW3_GGR | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 |  | PCD_DPW3_GGR_DLY | PCD_DPW3_GGR_DIR | PCD_DPW3_GGR_DSCR | PCD_DPW3_GGR_DCS | PCD_DPW3_GGR_DSPC | PCD_DPW3_GGR_DPP | PCD_DPW3_GGR_DTPI | PCD_DPW3_GGR_DCI | PCD_DPW3_GGR_DSI | PCD_DPW3_GGR_DER | PCD_DPW3_GGR_RS | PCD_DPW3_GGR_DPLE
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 |  | PCD_DPW3_GGR_DLY_S1 | PCD_DPW3_GGR_DIR_S1 | PCD_DPW3_GGR_DSCR_S1 | PCD_DPW3_GGR_DCS_S1 | PCD_DPW3_GGR_DSPC_S1 | PCD_DPW3_GGR_DPP_S1 | PCD_DPW3_GGR_DTPI_S1 | PCD_DPW3_GGR_DCI_S1 | PCD_DPW3_GGR_DSI_S1 | PCD_DPW3_GGR_DER_S1 | PCD_DPW3_GGR_RS_S1 | PCD_DPW3_GGR_DPLE_S1
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 |  | PCD_DPW3_GGR_DLY_S2 | PCD_DPW3_GGR_DIR_S2 | PCD_DPW3_GGR_DSCR_S2 | PCD_DPW3_GGR_DCS_S2 | PCD_DPW3_GGR_DSPC_S2 | PCD_DPW3_GGR_DPP_S2 | PCD_DPW3_GGR_DTPI_S2 | PCD_DPW3_GGR_DCI_S2 | PCD_DPW3_GGR_DSI_S2 | PCD_DPW3_GGR_DER_S2 | PCD_DPW3_GGR_RS_S2 | PCD_DPW3_GGR_DPLE_S2
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 |  | PCD_DPW3_GGR_DLY_S3 | PCD_DPW3_GGR_DIR_S3 | PCD_DPW3_GGR_DSCR_S3 | PCD_DPW3_GGR_DCS_S3 | PCD_DPW3_GGR_DSPC_S3 | PCD_DPW3_GGR_DPP_S3 | PCD_DPW3_GGR_DTPI_S3 | PCD_DPW3_GGR_DCI_S3 | PCD_DPW3_GGR_DSI_S3 | PCD_DPW3_GGR_DER_S3 | PCD_DPW3_GGR_RS_S3 | PCD_DPW3_GGR_DPLE_S3
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 |  | PCD_DPW3_GGR_DLY_S4 | PCD_DPW3_GGR_DIR_S4 | PCD_DPW3_GGR_DSCR_S4 | PCD_DPW3_GGR_DCS_S4 | PCD_DPW3_GGR_DSPC_S4 | PCD_DPW3_GGR_DPP_S4 | PCD_DPW3_GGR_DTPI_S4 | PCD_DPW3_GGR_DCI_S4 | PCD_DPW3_GGR_DSI_S4 | PCD_DPW3_GGR_DER_S4 | PCD_DPW3_GGR_RS_S4 | PCD_DPW3_GGR_DPLE_S4
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 |  | PCD_DPW3_GGR_DLY_S5 | PCD_DPW3_GGR_DIR_S5 | PCD_DPW3_GGR_DSCR_S5 | PCD_DPW3_GGR_DCS_S5 | PCD_DPW3_GGR_DSPC_S5 | PCD_DPW3_GGR_DPP_S5 | PCD_DPW3_GGR_DTPI_S5 | PCD_DPW3_GGR_DCI_S5 | PCD_DPW3_GGR_DSI_S5 | PCD_DPW3_GGR_DER_S5 | PCD_DPW3_GGR_RS_S5 | PCD_DPW3_GGR_DPLE_S5
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 |  | PCD_DPW3_GGR_DLY_S6 | PCD_DPW3_GGR_DIR_S6 | PCD_DPW3_GGR_DSCR_S6 | PCD_DPW3_GGR_DCS_S6 | PCD_DPW3_GGR_DSPC_S6 | PCD_DPW3_GGR_DPP_S6 | PCD_DPW3_GGR_DTPI_S6 | PCD_DPW3_GGR_DCI_S6 | PCD_DPW3_GGR_DSI_S6 | PCD_DPW3_GGR_DER_S6 | PCD_DPW3_GGR_RS_S6 | PCD_DPW3_GGR_DPLE_S6
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 7 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 |  | PCD_DPW3_GGR_DLY_S7 | PCD_DPW3_GGR_DIR_S7 | PCD_DPW3_GGR_DSCR_S7 | PCD_DPW3_GGR_DCS_S7 | PCD_DPW3_GGR_DSPC_S7 | PCD_DPW3_GGR_DPP_S7 | PCD_DPW3_GGR_DTPI_S7 | PCD_DPW3_GGR_DCI_S7 | PCD_DPW3_GGR_DSI_S7 | PCD_DPW3_GGR_DER_S7 | PCD_DPW3_GGR_RS_S7 | PCD_DPW3_GGR_DPLE_S7
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST |  | PCD_DPW3_GGR_DLY_ST | PCD_DPW3_GGR_DIR_ST | PCD_DPW3_GGR_DSCR_ST | PCD_DPW3_GGR_DCS_ST | PCD_DPW3_GGR_DSPC_ST | PCD_DPW3_GGR_DPP_ST | PCD_DPW3_GGR_DTPI_ST | PCD_DPW3_GGR_DCI_ST | PCD_DPW3_GGR_DSI_ST | PCD_DPW3_GGR_DER_ST | PCD_DPW3_GGR_RS_ST | PCD_DPW3_GGR_DPLE_ST

## DPW4
DPW4
Scheme-level data - Water - Enhanced engagement, Large gated, Critical High-profile schemes
| Company | Scheme name | Scheme ID | WINEP/NEP ID | Enhancement line description | PCD reference | Type of scheme (retained/dropped/added) | Name of the substituted scheme | Original regulatory date [if relevant] | Current regulatory date [if relevant] | Interim milestone completion dates - Baseline | [6 empty] | Current interim milestone | Interim milestone completion dates - Forecast | [6 empty] | Primary reson for delay where IM date moves more than 90 days later than baseline | Spend to date (£m) - cumulative | Forecast expenditure to complete scheme (£m) - cumulative | Forecast outturn cost (£m) | % Spend to date | Baseline expenditure profile (£m) - cumulative | [7 empty] | Forecast expenditure profile (£m) - cumulative | [7 empty] | Critical high profile (Yes/No) | Type of scheme (enhanced engagement, large gated, other) | AMP
[31 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9
[11 empty] | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 |  | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 | [5 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total
| TMS | PR24 SEMD - ESS/OT | UBA8.WAT.S41877 |  | SEMD | Gated scheme - NO PCD | Retained |  | 2035-03-31 | 2035-03-31 | 2025-04-02 | 2026-06-17 | 2027-05-27 | 2027-12-20 | 2031-12-19 | 2031-12-19 |  | IM2 | 2025-04-02 | 2026-06-17 | 2027-05-27 | 2027-12-20 | 2031-12-19 | 2031-12-19 |  |  | 0 | 14.6534 | 14.6534 | 0% |  |  | 1.3555 | 4.1129 | 7.5336 | 11.1688 | 15.3341 | 27.9708 | 0 | 0 | 0 | 3.2041 | 6.5242 | 10.0516 | 14.0899 | 14.6534 | No | Large Gated | AMP8
| TMS | PR24 SEMD - Patrol and Response | UBA8.WAT.S41876 |  | SEMD | Gated scheme - NO PCD | Retained |  |  |  | 2025-04-01 | 2027-01-19 | 2027-11-08 | 2028-07-27 | 2029-04-16 | 2029-04-16 |  | IM1 | 2025-04-01 | 2027-01-19 | 2027-11-08 | 2028-07-27 | 2029-04-16 | 2029-04-16 |  |  | 0 | 40.3459 | 40.3459 | 0% |  |  | 0.68053 | 1.361 | 2.0416 | 2.7221 | 3.4018 | 3.4018 | 0 | 0 | 0 | 9.794 | 19.3853 | 28.7885 | 38.0073 | 40.3459 | No | Large Gated | AMP8
| TMS | SEMD - CAT 3-5 | L827 |  | SEMD | Gated scheme - NO PCD | Retained |  | 2035-03-31 | 2035-03-31 | 2024-05-21 | 2026-08-19 | 2027-07-06 | 2028-02-10 | 2033-01-21 | 2033-01-21 |  | IM1 | 2024-05-21 | 2026-08-19 | 2027-07-06 | 2028-02-10 | 2033-01-21 | 2033-01-21 |  |  | 0.64952 | 81.7975 | 82.447 | 0.7878% | 0 | 0.217 | 4.1 | 15.066 | 81.109 | 124.168 | 190.294 | 400.561 | 0 | 0.217 | 0.64952 | 0.86626 | 1.8843 | 12.4636 | 31.6063 | 82.447 | No | Large Gated | AMP8
| TMS | 3155, 3156, 3157, 3158 | L744 |  | SEMD | Gated scheme - NO PCD | Retained |  | 2028-01-06 | 2028-01-06 | 2024-05-22 | 2025-01-23 | 2025-11-19 | 2027-08-31 | 2028-10-28 | 2028-10-10 |  | IM3 | 2024-05-22 | 2025-01-23 | 2025-11-19 | 2027-08-31 | 2028-10-10 | 2028-10-10 |  |  | 5.2874 | 82.462 | 87.7494 | 6.026% |  | 0.22511 | 1.2927 | 11.6689 | 31.1833 | 37.5756 | 37.9157 | 37.956 | 0 | 0.225 | 5.2874 | 42.331 | 75.7622 | 80.1821 | 87.2772 | 87.7494 | No | Large Gated | AMP8
| TMS | 3185, 3186, 3187 | M321 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM3 | 2024-05-22 | 2025-07-17 | 2026-02-12 | 2027-11-22 | 2029-01-08 | 2028-09-29 |  |  | 0.35418 | 25.122 | 25.4762 | 1.39% | [8 empty] | 0 | 0 | 0.35418 | 7.2218 | 24.7762 | 25.3087 | 25.4147 | 25.4762 | No | Large Gated | AMP8
| TMS | 3160, 3161, 3162, 3163 | M322 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2025-05-22 | 2025-06-19 | 2027-01-25 | 2030-03-05 | 2032-06-24 | 2032-03-31 |  |  | 0.67006 | 41.1799 | 41.85 | 1.601% | [8 empty] | 0 | 0 | 0.67006 | 1.248 | 3.815 | 12.9521 | 24.6593 | 41.85 | No | Large Gated | AMP8
| TMS | 3179 | M323 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-06-19 | 2027-05-28 | 2030-07-25 | 2032-07-02 | 2032-03-31 |  |  | 0.48497 | 10.755 | 11.24 | 4.315% | [8 empty] | 0 | 0 | 0.48497 | 1.0629 | 1.6233 | 2.2585 | 2.2053 | 11.24 | No | Large Gated | AMP8
| TMS | 3210, 3211 | M325 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-07-17 | 2026-10-27 | 2028-10-30 | 2031-11-28 | 2031-08-29 |  |  | 0.065921 | 16.9641 | 17.03 | 0.3871% | [8 empty] | 0 | 0 | 0.065921 | 0.24258 | 0.97038 | 1.6853 | 4.4938 | 17.03 | No | Large Gated | AMP8
| TMS | 3195, 3196, 3197, 3198 | M326 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM3 | 2024-05-22 | 2025-06-19 | 2026-05-29 | 2028-05-23 | 2029-12-20 | 2029-09-28 |  |  | 1.1023 | 35.9815 | 37.0838 | 2.972% | [8 empty] | 0 | 0 | 1.1023 | 7.3472 | 25.5705 | 36.6594 | 36.7826 | 37.0838 | No | Large Gated | AMP8
| TMS | 3215, 3216, 3217 | M327 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM3 | 2024-05-22 | 2025-07-17 | 2026-02-12 | 2028-08-17 | 2030-07-04 | 2030-03-29 |  |  | 0.54601 | 27.4029 | 27.949 | 1.954% | [8 empty] | 0 | 0 | 0.54601 | 2.3974 | 4.1276 | 16.0644 | 26.8307 | 27.949 | No | Large Gated | AMP8
| TMS | 3170 | M328 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM3 | 2024-05-22 | 2025-06-19 | 2026-01-29 | 2028-03-10 | 2029-06-26 | 2029-03-29 |  |  | 0.57162 | 30.3374 | 30.909 | 1.849% | [8 empty] | 0 | 0 | 0.57162 | 4.2574 | 27.7894 | 30.3554 | 29.5423 | 30.909 | No | Large Gated | AMP8
| TMS | 3175, 3176, 3177, 3178 | M329 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-06-19 | 2027-03-30 | 2029-10-25 | 2031-12-22 | 2031-09-30 |  |  | 0.46049 | 42.8895 | 43.35 | 1.062% | [8 empty] | 0 | 0 | 0.46049 | 1.0384 | 1.5988 | 13.0241 | 27.1084 | 43.35 | No | Large Gated | AMP8
| TMS | 3205, 3206, 3207 | M331 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM3 | 2024-05-22 | 2025-06-17 | 2026-05-29 | 2028-07-18 | 2030-06-26 | 2030-03-29 |  |  | 0.86673 | 31.0667 | 31.9334 | 2.714% | [8 empty] | 0 | 0 | 0.86673 | 6.8213 | 12.7484 | 26.3962 | 30.777 | 31.9334 | No | Large Gated | AMP8
| TMS | 3190, 3191, 3192 | M332 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-08-21 | 2030-11-22 | 2032-04-20 | 2033-07-06 | 2033-03-31 |  |  | 0.21267 | 29.0773 | 29.29 | 0.7261% | [8 empty] | 0 | 0 | 0.21267 | 0.79063 | 1.351 | 1.9066 | 2.4621 | 29.29 | No | Large Gated | AMP8
| TMS | 3072 | M333 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-06-19 | 2026-10-27 | 2028-06-21 | 2030-06-26 | 2030-03-29 |  |  | 0.27567 | 10.4043 | 10.68 | 2.581% | [8 empty] | 0 | 0 | 0.27567 | 0.85362 | 1.414 | 4.0736 | 9.2987 | 10.68 | No | Large Gated | AMP8
| TMS | 3180, 3181, 3182 | M334 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-06-19 | 2027-01-05 | 2028-11-29 | 2030-06-26 | 2030-03-29 |  |  | 0.25924 | 41.3882 | 41.6474 | 0.6225% | [8 empty] | 0 | 0 | 0.25924 | 1.2485 | 17.13 | 39.2909 | 40.2852 | 41.6474 | No | Large Gated | AMP8
| TMS | 3164 | M364 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-07-17 | 2030-10-29 | 2032-08-20 | 2034-06-28 | 2034-03-31 |  |  | 0.068723 | 52.3913 | 52.46 | 0.131% | [8 empty] | 0 | 0 | 0.068723 | 0.11988 | 0.40762 | 0.40762 | 0.40762 | 52.46 | No | Large Gated | AMP8
| TMS | 3200 | M365 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-06-19 | 2030-10-29 | 2032-05-20 | 2034-01-09 | 2033-09-30 |  |  | 0.068995 | 41.671 | 41.74 | 0.1653% | [8 empty] | 0 | 0 | 0.068995 | 0.13499 | 0.42272 | 0.42272 | 0.42272 | 41.74 | No | Large Gated | AMP8
| TMS | 3300 | M370 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-08-21 | 2030-10-29 | 2032-08-24 | 2034-07-06 | 2034-03-31 |  |  | 0.069 | 57.011 | 57.08 | 0.1209% | [8 empty] | 0 | 0 | 0.069 | 0.13394 | 0.42168 | 0.42168 | 0.42168 | 57.08 | No | Large Gated | AMP8
| TMS | 3165 | M371 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-07-17 | 2026-11-23 | 2028-02-17 | 2029-06-26 | 2029-03-29 |  |  | 0.46525 | 34.9847 | 35.45 | 1.312% | [8 empty] | 0 | 0 | 0.46525 | 1.0432 | 15.6581 | 22.4531 | 23.2943 | 35.45 | No | Large Gated | AMP8
| TMS | 3166 | M372 |  | SEMD | Gated scheme - NO PCD | Retained | [10 empty] | IM2 | 2024-05-22 | 2025-08-21 | 2026-11-23 | 2028-11-23 | 2031-03-25 | 2030-12-24 |  |  | 0.50877 | 41.4012 | 41.91 | 1.214% | [8 empty] | 0 | 0 | 0.50877 | 1.0867 | 1.2808 | 7.5916 | 27.072 | 41.91 | No | Large Gated | AMP8
| TMS | SEMD AMC – System and Sites CNI Pack 11 | M586 |  | SEMD | Gated scheme - NO PCD | Retained |  | 2035-03-31 | 2035-03-31 | 2025-04-23 | 2026-06-15 | 2027-05-27 | 2028-01-04 | 2032-12-22 | 2032-12-22 |  | IM2 | 2025-04-23 | 2026-06-15 | 2027-05-27 | 2028-01-04 | 2032-12-22 | 2032-12-22 |  |  | 0.16494 | 11.6851 | 11.85 | 1.392% |  |  | 0.067856 | 0.20606 | 0.36475 | 0.51332 | 0.66015 | 1.4012 | 0 | 0 | 0.16494 | 2.9555 | 3.4575 | 6.2784 | 9.0441 | 11.85 | No | Large Gated | AMP8
| TMS | Hampton UV Treatment | L479 |  | Raw Water Deterioration and Taste, Odour and Colour | Gated scheme - NO PCD | Retained |  | 2031-04-30 | 2031-04-30 | 2023-09-20 | 2026-07-31 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  | IM2 | 2023-09-20 | 2025-10-31 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  |  | 2.6133 | 122.5647 | 125.178 | 2.088% | 0.12742 | 0.64744 | 2.0459 | 3.5248 | 20.2874 | 40.7314 | 60.7746 | 61.0862 | 0.128 | 0.732 | 2.6133 | 6.0198 | 16.4824 | 71.1619 | 125.0545 | 125.178 | Yes | Large Gated | AMP8
| TMS | Ashford UV Treatment | L844 |  | Raw Water Deterioration and Taste, Odour and Colour | Gated scheme - NO PCD | Retained |  | 2031-04-30 | 2031-04-30 | 2024-03-22 | 2026-09-30 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  | IM2 | 2024-03-22 | 2025-10-31 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  |  | 3.8249 | 119.8701 | 123.695 | 3.092% |  | 0.29199 | 2.6977 | 5.2207 | 31.7818 | 64.1886 | 95.9599 | 96.453 | 0 | 0.376 | 3.8249 | 7.2215 | 17.7421 | 71.0728 | 123.6144 | 123.695 | Yes | Large Gated | AMP8
| TMS | Coppermills UV Treatment Design Work | UBA8.WAT.S40977 |  | Raw Water Deterioration and Taste, Odour and Colour | Gated scheme - NO PCD | Retained |  | 2030-03-31 | 2030-03-31 | 2025-12-16 | 2026-10-15 | 2026-10-15 | 2027-03-01 | 2027-08-16 | 2027-08-16 |  | IM6 | 2025-12-16 | 2028-09-30 | [6 empty] | 0.016739 | 4.8942 | 4.9109 | 0.3409% |  |  | 0.81153 | 4.7088 | 4.9109 | 4.9109 | 4.9109 | 4.9109 | 0 | 0 | 0.016739 | 4.1127 | 4.5136 | 4.7122 | 4.9109 | 4.9109 | No | Large Gated | AMP8
| TMS | Kempton UV Treatment Design Work | UBA8.WAT.S40978 |  | Raw Water Deterioration and Taste, Odour and Colour | Gated scheme - NO PCD | Retained |  | 2030-03-31 | 2030-03-31 | 2025-12-16 | 2026-10-15 | 2026-10-15 | 2027-03-01 | 2027-08-16 | 2027-08-16 |  | IM6 | 2025-12-16 | 2027-09-30 | [6 empty] | 0.0014324 | 2.182 | 2.1834 | 0.0656% |  |  | 0.37928 | 2.0945 | 2.1834 | 2.1834 | 2.1834 | 2.1834 | 0 | 0 | 0.0014324 | 1.9055 | 2.1834 | 2.1834 | 2.1834 | 2.1834 | No | Large Gated | AMP8
| TMS | Metering Programme | UBA8.WAT.S39396, UBA8.WAT.S39404, UBA8.WAT.S39405, UBA8.WAT.S39406, UBA8.WAT.S39407, UBA8.WAT.S39408, UBA8.WAT.S39409, UBA8.WAT.S40145, UBA8.WAT.S40147, UBA8.WAT.S40148, UBA8.WAT.S40149, UBA8.WAT.S40151, UBA8.WAT.S40152, UBA8.WAT.S42275, UBA8.WAT.S39412, UBA8.WAT.S39413, UBA8.WAT.S39419, UBA8.WAT.S39428, UBA8.WAT.S39429 |  | Metering | PCDW12 | Retained | [11 empty] | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 97.3126 | 365.679 | 462.9915 | 21.02% |  |  | 80.6257 | 156.7914 | 232.7466 | 309.0679 | 385.775 | 385.775 | 0 | 0 | 97.3126 | 201.136 | 297.3192 | 379.8252 | 462.9915 | 462.9915 | No | Other | AMP8
| TMS | Lead Strategy | Lead Strategy |  | Raw Water Deterioration and Taste, Odour and Colour | Gated scheme - NO PCD | Retained |  | 2031-04-30 | 2031-04-30 | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  | IM6 | [8 empty] | 0 | 0.2 | 0.2 | 0% | [16 empty] | No | Large Gated | AMP8
| TMS | PFAS Strategy | PFAS Strategy |  | Raw Water Deterioration and Taste, Odour and Colour | Gated scheme - NO PCD | Retained |  | 2031-04-30 | 2031-04-30 | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  | IM6 | [8 empty] | 0 | 0.2 | 0.2 | 0% | [16 empty] | No | Large Gated | AMP8
| TMS | WRMP19_ML_ Didcot Raw Water Purchase | UBA8.WAT.S36984 |  | Supply | PCDW11a | Retained |  |  |  |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  | IM6 |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 7.0806 | 11.0944 | 18.1751 | 38.96% | 2.2322 | 4.4185 | 7.2606 | 10.0991 | 12.9321 | 15.7609 | 18.5898 | 18.5898 | 2.2322 | 4.4185 | 7.0806 | 9.863 | 12.6349 | 15.4058 | 18.1751 | 18.1751 | No | Other | AMP8
| TMS | SEMD Alternative water supply | UBA8.WAT.S41951 |  | SEMD | PCDW17a | Retained |  | 2030-09-30 | 2030-09-30 | [16 empty] | 1.81 | 27.9996 | 29.8096 | 6.072% |  |  | 7.3726 | 12.6009 | 17.8194 | 23.0252 | 28.226 | 28.226 | 0 | 0 | 1.81 | 6.261 | 12.1236 | 21.6335 | 29.8096 | 29.8096 | No | Other | AMP8
| TMS | Coppermills System Resilience | K665.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2031-01-31 | 2023-01-31 | 2023-07-18 | 2025-03-31 | 2026-09-23 | 2032-04-06 | 2031-03-31 |  | IM3 | 2023-01-31 | 2023-07-18 | 2025-03-31 | 2026-12-21 | 2032-05-13 | 2031-01-31 |  |  | 36.875 | 399.3532 | 436.2282 | 8.453% | 7.8229 | 16.178 | 42.3529 | 134.2411 | 231.8907 | 330.7646 | 415.1053 | 466.2205 | 7.8161 | 16.1712 | 36.875 | 68.9175 | 184.538 | 297.3598 | 403.0686 | 436.2282 | No | Other | AMP7
| TMS | Hampton WTW TWRM Structural Fault WSSRP | L169.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2030-03-31 | 2021-10-26 | 2023-03-22 | 2029-06-01 | 2029-07-31 | 2030-03-29 | 2030-01-05 |  | IM2 | 2021-10-26 | 2023-03-22 | 2027-06-14 | 2027-08-11 | 2028-03-16 | 2027-10-26 |  |  | 0.25879 | 1.0289 | 1.2877 | 20.1% | 0.25714 | 0.25821 | 0.26034 | 0.38034 | 0.38238 | 0.38437 | 1.2555 | 1.2555 | 0.25714 | 0.25821 | 0.25879 | 0.26084 | 1.1723 | 1.2877 | 1.2877 | 1.2877 | No | Other | AMP7
| TMS | Hampton WTW GJ Vehicle Barrier (WSSRP) | L191.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2026-03-31 | 2021-10-26 | 2023-03-23 | 2023-09-22 | 2024-06-26 | 2026-02-16 | 2026-02-01 |  | IM6 | 2021-10-26 | 2023-03-23 | 2023-09-22 | 2024-06-26 | 2026-02-16 | 2025-11-20 |  |  | 3.1915 | 0.014797 | 3.2063 | 99.54% | 0.45672 | 1.2209 | 3.3138 | 3.3138 | 3.3138 | 3.3138 | 3.3138 | 3.3138 | 0.45671 | 1.2209 | 3.1915 | 3.2063 | 3.2063 | 3.2063 | 3.2063 | 3.2063 | No | Other | AMP7
| TMS | Hampton WTW Bulk Recycling (WSSRP) | L193.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2027-03-31 | 2021-10-26 | 2023-05-23 | 2026-07-06 | 2027-05-24 | 2028-12-01 | 2029-01-13 |  | IM2 | 2021-10-26 | 2023-05-23 | 2026-07-06 | 2027-05-24 | 2028-12-01 | 2028-11-13 |  |  | 2.4607 | 15.6722 | 18.1329 | 13.57% | 0.4173 | 1.0089 | 1.5775 | 2.5321 | 12.4296 | 17.713 | 17.8824 | 17.8824 | 0.4173 | 1.0089 | 2.4607 | 7.1388 | 14.7701 | 18.003 | 18.1329 | 18.1329 | No | Other | AMP7
| TMS | Mogden TWRM Shaft Pump Out (WSSRP) | L204.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2028-03-31 | 2021-10-26 | 2023-05-23 | 2024-04-15 | 2025-09-17 | 2028-04-26 | 2028-04-28 |  | IM4 | 2021-10-26 | 2023-05-23 | 2024-04-15 | 2026-05-29 | 2028-08-08 | 2028-06-13 |  |  | 13.8183 | 12.1362 | 25.9545 | 53.24% | 1.0376 | 4.4757 | 14.8181 | 24.3808 | 27.1529 | 27.1529 | 27.1529 | 27.1529 | 1.0376 | 4.4757 | 13.8183 | 19.6338 | 25.9545 | 25.9545 | 25.9545 | 25.9545 | No | Other | AMP7
| TMS | Pentonville Road? Trunk Main Replacement | K371.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-05-26 | 2021-11-24 | 2023-09-29 | 2024-07-23 | 2027-12-03 | 2027-12-02 |  | IM4 | 2021-05-26 | 2021-11-24 | 2023-09-29 | 2024-07-23 | 2028-03-14 | 2028-03-02 |  |  | 19.0499 | 24.5982 | 43.6481 | 43.64% | 3.5467 | 10.3892 | 24.8457 | 34.8121 | 38.4629 | 38.4629 | 38.4629 | 38.4629 | 3.5467 | 10.3894 | 19.0499 | 26.7055 | 38.6524 | 43.6481 | 43.6481 | 43.6481 | No | Other | AMP7
| TMS | K372 Fortis Green to Cockfosters Trunk M | K372.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2020-09-07 | 2021-11-11 | 2023-02-10 | 2023-06-26 | 2025-09-22 | 2025-04-17 |  | IM5 | 2020-09-07 | 2021-11-11 | 2023-02-10 | 2023-06-26 | 2026-05-12 | 2025-06-04 |  |  | 24.6533 | 0.47853 | 25.1318 | 98.1% | 8.9371 | 21.848 | 23.9608 | 23.9608 | 23.9608 | 23.9608 | 23.9608 | 23.9608 | 8.9371 | 21.848 | 24.6533 | 25.1318 | 25.1318 | 25.1318 | 25.1318 | 25.1318 | No | Other | AMP7
| TMS | Victoria Station 30in? Trunk Main | K374.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-05-26 | 2021-11-24 | 2023-08-30 | 2023-08-31 | 2025-04-10 | 2025-06-30 |  | IM6 | 2021-05-26 | 2021-11-24 | 2023-08-30 | 2023-08-31 | 2025-07-24 | 2025-06-30 |  |  | 9.4582 | 0.0027032 | 9.4609 | 99.97% | 3.751 | 8.9123 | 9.232 | 9.232 | 9.232 | 9.232 | 9.232 | 9.232 | 3.751 | 8.9123 | 9.4582 | 9.4609 | 9.4609 | 9.4609 | 9.4609 | 9.4609 | No | Other | AMP7
| TMS | Surbiton 30in no 1 & 3? Trunk Mains | K375.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-05-26 | 2021-10-26 | 2024-01-10 | 2024-03-28 | 2025-10-16 | 2025-07-30 |  | IM4 | 2021-05-26 | 2021-10-26 | 2024-01-10 | 2024-03-28 | 2026-12-16 | 2026-09-30 |  | Site issues | 14.6053 | 3.7526 | 18.3578 | 79.56% | 2.7266 | 9.9837 | 15.291 | 15.291 | 15.291 | 15.291 | 15.291 | 15.291 | 2.7266 | 9.9868 | 14.6053 | 18.3578 | 18.3578 | 18.3578 | 18.3578 | 18.3578 | No | Other | AMP7
| TMS | Mile End Park & Station | K493.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-08-25 | 2021-12-20 | 2023-09-25 | 2024-07-19 | 2027-04-26 | 2027-04-01 |  | IM4 | 2021-08-25 | 2021-12-20 | 2023-09-25 | 2024-07-19 | 2028-01-25 | 2027-12-15 |  |  | 16.8995 | 15.3864 | 32.2859 | 52.34% | 3.6524 | 9.8703 | 20.0087 | 27.382 | 28.9976 | 28.9976 | 28.9976 | 28.9976 | 3.6524 | 9.8703 | 16.8995 | 22.6042 | 29.3436 | 32.2859 | 32.2859 | 32.2859 | No | Other | AMP7
| TMS | Guildford Power Resilience | M252 |  | Climate change uplift | PCDWW32 | Retained | UBA8.WAT.S30939 |  |  | 2025-09-01 | 2025-10-01 | 2026-01-01 | 2026-03-01 | 2030-02-28 | 2030-02-28 |  | IM4 | 2025-09-01 | 2025-10-01 | 2026-01-01 | 2026-03-01 | 2030-02-28 | 2030-02-28 |  |  | 1.0494 | 4.106 | 5.1555 | 20.36% |  |  | 0.51118 | 1.1774 | 1.8437 | 2.5099 | 3.1762 | 3.1762 | 0 | 0 | 1.0494 | 4.3504 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | No | Other | AMP8
| TMS | Fish Passages (FP) TV | M203 | 08TW100205a, 08TW100206a, 08TW100212a, 08TW100214a | Water WINEP/NEP Investigations | PCDW8 | Retained | UBA8.WAT.S40860, UBA8.WAT.S40861, UBA8.WAT.S41653, UBA8.WAT.S41654 | 2027-04-30 | 2027-04-30 | 2025-04-01 | 2026-12-21 | 2027-05-27 | 2027-10-25 | 2030-03-21 | 2030-03-21 |  | IM1 | 2024-04-23 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 0.10807 | 11.2669 | 11.375 | 0.95% |  | 0.0081028 | 0.14127 | 0.32054 | 0.53875 | 0.86685 | 1.0806 | 1.0888 | 0 | 0 | 0.10807 | 0.92817 | 2.599 | 7.4738 | 11.375 | 11.375 | No | Other | AMP8
| TMS | PR24 WINEP ED Bradfield | L875 | 08TW100003a | Water Framework Directive actions | PCDW5 | Retained | UBA8.WAT.S38441 | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2025-07-10 | 2026-07-28 | 2026-12-18 | 2028-09-12 | 2028-09-12 |  | IM1 | 2025-07-17 | 2027-02-26 | 2027-09-01 | 2028-04-01 | 2030-03-31 | 2030-03-31 |  |  | 0.097622 | 1.8566 | 1.9542 | 4.995% |  | 0.00023902 | 0.30938 | 0.60649 | 1.8282 | 2.2239 | 2.2463 | 2.2463 | 0 | 0 | 0.097622 | 0.46817 | 1.4644 | 1.9389 | 1.9528 | 1.9542 | No | Other | AMP8
| TMS | WINEP AMP8 Catchment Management Schemes – Drinking Water Protected Areas (DrWPA) | M221 | 08TW100047a | Water WINEP/NEP Investigations | PCDW8 | Retained | UBA8.WAT.S38741 | 2027-04-30 | 2027-04-30 | 2025-04-01 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  | IM1 | 2025-04-01 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 0.021697 | 0.54653 | 0.56822 | 3.818% |  |  | 0.22021 | 0.44041 | 0.49546 | 0.52299 | 0.55051 | 0.55051 | 0 | 0 | 0.021697 | 0.089929 | 0.2714 | 0.4098 | 0.56822 | 0.56822 | No | Other | AMP8
| TMS | Hornsey Bromate Removal (New Gauge Abs) | L784 | 08TW100032a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-14 | 2025-07-16 | 2026-07-23 | 2027-01-18 | 2029-02-05 | 2029-02-05 |  | IM1 | 2024-06-14 | 2026-07-16 | 2027-04-23 | 2027-10-13 | 2030-01-23 | 2030-03-31 |  | Water WINEP - All dates realigned to Reg date to reflect corporate forecast date | 0.081211 | 8.1688 | 8.25 | 0.9844% |  | 0.054924 | 0.41272 | 0.95297 | 4.7677 | 7.8506 | 7.918 | 7.9317 | 0 | 0.055 | 0.081211 | 0.49257 | 1.2051 | 6.7185 | 8.2103 | 8.25 | No | Other | AMP8
| TMS | Implemetning company - wide INNS plan | M171 | 08TW100041a | Water WINEP/NEP Investigations | PCDW8 | Retained | UBA8.WAT.S38605 | 2027-04-30 | 2030-03-31 | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  | IM1 | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 0.019637 | 0.31446 | 0.33409 | 5.878% |  |  | 0.08 | 0.16 | 0.24 | 0.32 | 0.4 | 0.4 | 0 | 0 | 0.019637 | 0.055628 | 0.15731 | 0.2434 | 0.33409 | 0.33409 | No | Other | AMP8
| TMS | Low Flow & Env Destination Inv & Eels | M046 | 08TW100040a, 08TW100039a, 08TW100038a, 08TW100037a, 08TW100036a, 08TW100035a, 08TW100034a, 08TW100031a, 08TW100030a, 08TW100029a, 08TW100029b, 08TW100029c, 08TW100030b, 08TW100030d, 08TW100030c, 08TW100030e, 08TW100030f, 08TW101379a, 08TW101405b, 08TW101405c, 08TW101405d, 08TW101405e, 08TW101405f, 08TW101405g, 08TW101405h, 08TW101405i, 08TW101405j, 08TW101405k, 08TW101405l, 08TW101405m, 08TW101405a, 08TW101460a, 08TW101467a, 08TW104005a, 08TW101462a, 08TW101373a, 08TW101376a, 08TW101377a, 08TW101378a, 08TW104009a, 08TW104004a | Water WINEP/NEP Investigations | PCDW8 | Retained | UBA8.WAT.S38636, UBA8.WAT.S39358, UBA8.WAT.S40117, UBA8.WAT.S40120, UBA8.WAT.S40121, UBA8.WAT.S40122, UBA8.WAT.S40123, UBA8.WAT.S40767, UBA8.WAT.S40770, UBA8.SEW.S40771, UBA8.WAT.S40781, UBA8.WAT.S40786, UBA8.WAT.S40788 | 2026-12-31 | 2026-12-31 | 2025-01-04 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 | 2027-04-01 |  | IM1 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 1.2152 | 7.6668 | 8.882 | 13.68% |  |  | 4.2877 | 8.9468 | 10.0904 | 11.2341 | 12.3777 | 12.3777 | 0 | 0 | 1.2152 | 4.5688 | 6.8335 | 7.9853 | 8.882 | 8.882 | No | Other | AMP8
| TMS | PR24 WINEP ED Netley Mill Sustainability | L874 | 08TW100002a | Water Framework Directive interconnector | PCDW5 | Retained | UBA8.WAT.S38445 | 2030-03-31 | 2030-03-31 | 2020-05-29 | 2021-03-24 | 2023-09-28 | 2024-03-18 | 2026-12-17 | 2026-12-17 |  | IM4 | 2020-05-29 | 2021-03-24 | 2023-09-28 | 2024-03-18 | 2026-12-17 | 2030-03-31 |  | Water WINEP - All dates realigned to Reg date to reflect corporate forecast date | 0.085785 | 1.9182 | 2.004 | 4.281% |  |  |  | 0.17749 | 3.554 | 8.6188 | 15.319 | 15.4878 | 0 | 0 | 0.085785 | 0.15477 | 0.7828 | 1.3994 | 2.004 | 2.004 | No | Other | AMP8
| TMS | WRMP'24 Ml/d | M213, M470, M469, M468 |  | Supply | PCDW11a | Retained | UBA8.WAT.S42273 |  |  |  | 2030-01-08 | 2030-01-08 | 2030-01-08 | 2030-01-08 | 2030-01-08 |  | IM1 | 2025-02-20 | 2026-11-19 | 2027-09-15 | 2027-08-18 | 2030-07-24 | 2030-01-08 |  |  | 0.60162 | 43.2625 | 43.8641 | 1.372% |  |  | 0.66234 | 7.6636 | 23.2323 | 40.944 | 51.5769 | 51.5769 | 0 | 0 | 0.60162 | 4.4441 | 15.5841 | 33.5588 | 43.6295 | 43.8641 | No | Other | AMP8
| TMS | PR24 Digital Cyber Enhancement Case | M402, M403, UBA8.WAT.S41624.OX |  | Cyber | PCDW17b | Retained | UBA8.WAT.S41624 | 2030-04-30 | 2030-04-30 | [7 empty] | IM2 | [5 empty] | 2030-04-30 |  |  | 9.6532 | 95.1894 | 104.8426 | 9.207% |  |  | 19.0705 | 48.0883 | 72.8448 | 86.6581 | 102.1947 | 102.1947 | 0 | 0 | 9.6532 | 23.4709 | 47.8109 | 77.4377 | 103.5306 | 104.8426 | No | Other | AMP8
| TMS | PR24 WINEP New gauge investigation | UBA8.WAT.S40116 | 08TW100032a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-09-01 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 |  | IM1 | 2025-09-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  | Water WINEP - All dates realigned to Reg date to reflect corporate forecast date | 0 | 0.93029 | 0.93029 | 0% |  |  | 0.50304 | 1.0061 | 1.0061 | 1.0061 | 1.0061 | 1.0061 | 0 | 0 | 0 | 0.41471 | 0.71816 | 0.91426 | 0.93029 | 0.93029 | No | Other | AMP8
| TMS | Fish Passages (FP) LDN | M209 | 08TW101456a, 08TW101458a, 08TW101455a, 08TW101457a | Water WINEP/NEP Investigations | PCDW8 | Retained | UBA8.WAT.S40790, UBA8.WAT.S40791, UBA8.WAT.S40792, UBA8.WAT.S40793 | 2027-04-30 | 2027-04-30 | 2025-01-04 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  | IM1 | 2024-04-23 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 0.23924 | 8.4502 | 8.6895 | 2.753% |  |  | 0.21592 | 0.43185 | 0.53927 | 0.64669 | 0.75953 | 0.75953 | 0 | 0 | 0.23924 | 0.88834 | 1.5567 | 3.33 | 8.568 | 8.6895 | No | Other | AMP8
| TMS | Lead Pipe Replacement | M039 |  | Lead | PCDW15 | Retained | UBA8.WAT.S39253 | 2030-03-31 | 2030-03-31 | [16 empty] | 7.7785 | 64.5205 | 72.2989 | 10.76% |  |  | 10.5781 | 25.7394 | 40.7947 | 55.8583 | 70.9011 | 70.9011 | 0 | 0 | 7.7785 | 24.472 | 40.2264 | 56.1587 | 72.2989 | 72.2989 | No | Other | AMP8
| TMS | River Restoration (RR) LND | L898 | 08TW100028a, 08TW100027a, 09TW100013a, 09TW100014a, 08TW100020a, 08TW100025a, 08TW100026a, 08TW100033a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2025-10-15 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  | IM1 | 2024-09-18 | 2026-07-16 | 2027-06-10 | 2027-10-06 | 2029-09-04 | 2030-03-31 |  | Water WINEP - All dates realigned to Reg date to reflect corporate forecast date | 0.19637 | 7.4014 | 7.5978 | 2.585% |  |  | 0.35944 | 0.83964 | 3.7092 | 6.4504 | 6.5075 | 6.5119 | 0 | 0 | 0.19637 | 0.73465 | 2.7157 | 6.1016 | 7.5738 | 7.5978 | No | Other | AMP8
| TMS | River Restoration (RR) TV | L896 | 08TW100023a, 08TW100022a, 08TW104006a, 08TW104007a, 08TW100024a, 08TW100021a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2026-08-28 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  | IM1 | 2024-09-18 | 2027-04-30 | 2027-11-08 | 2028-03-10 | 2030-01-09 | 2030-03-31 |  | Water WINEP - All dates realigned to Reg date to reflect corporate forecast date | 0.047984 | 3.6485 | 3.6965 | 1.298% |  |  | 0.47668 | 0.8106 | 2.011 | 3.147 | 3.1709 | 3.1726 | 0 | 0 | 0.047984 | 0.70349 | 1.4759 | 2.7479 | 3.6965 | 3.6965 | No | Other | AMP8
| TMS | River Restoration (RR) TV | L896 | 08TW100207a, 08TW100208a, 08TW100209a, 08TW100210a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-09-18 | 2026-08-28 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  | IM1 | 2024-09-18 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 0.015708 | 1.1944 | 1.2101 | 1.298% |  |  | 0.14964 | 0.99515 | 1.0384 | 1.0384 | 1.0384 | 1.0384 | 0 | 0 | 0.015708 | 0.2303 | 0.48317 | 0.89959 | 1.2101 | 1.2101 | No | Other | AMP8
| TMS | PR24 WINEP SWELLS | UBA8.WAT.S37803 | 08TW100046a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2026-04-15 | 2027-05-27 | 2027-10-20 | 2029-07-12 | 2029-07-12 |  | IM1 | 2025-12-18 | 2026-12-17 | 2027-05-28 | 2027-12-14 | 2029-12-24 | 2030-03-31 |  | Water WINEP - All dates realigned to Reg date to reflect corporate forecast date | 0 | 2.0279 | 2.0279 | 0% |  |  | 0.12462 | 0.36962 | 0.83486 | 2.2298 | 2.478 | 2.5001 | 0 | 0 | 0 | 0.14283 | 0.45274 | 1.6012 | 2.0121 | 2.0279 | No | Other | AMP8
| TMS | WINEP Nrt New River Wells Chinnor licenc | M592 | 08TW100045a, 08TW100044a | Water Framework Directive actions | PCDW5 | Retained | UBA8.WAT.S38732 | 2030-03-31 | 2030-03-31 | 2025-04-01 | 2025-06-13 | 2025-08-25 | 2025-11-06 | 2026-01-19 | 2026-01-19 |  | IM5 | [5 empty] | 2030-03-31 |  |  | 0 | 0.10249 | 0.10249 | 0% |  |  | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0 | 0 | 0 | 0.10249 | 0.10249 | 0.10249 | 0.10249 | 0.10249 | No | Other | AMP8
| TMS | Addington Groundwater (WRMP) | M392 |  | Supply | PCDW11a | Retained | UBA8.WAT.S24423 |  |  | 2024-04-18 | 2026-01-09 | 2027-07-14 | 2028-07-13 | 2030-02-06 | 2030-02-06 |  | IM1 | 2024-04-18 | 2026-05-21 | 2027-01-13 | 2027-06-18 | 2028-05-17 | 2030-02-06 |  |  | 0.53434 | 4.6894 | 5.2237 | 10.23% |  |  | 0.64627 | 1.3427 | 3.4625 | 5.0262 | 5.0688 | 5.0688 | 0 | 0 | 0.53434 | 1.4418 | 5.033 | 5.2054 | 5.2237 | 5.2237 | No | Other | AMP8
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!

## DPW5
DPW5
Scheme-level data - Water Resilience schemes (excluding any critical high-profile projects)
| Company | Scheme name | Scheme ID | WINEP/NEP ID | Line description | PCD reference | Type of scheme (retained/dropped/added) | Name of the substituted scheme | Statutory scheme reference | Original regulatory date [if relevant] | Current regulatory date [if relevant] | Interim milestone completion dates - Baseline | [6 empty] | Current interim milestone | Interim milestone completion dates - Forecast | [6 empty] | Primary reson for delay where IM date moves more than 90 days later than baseline | Spend to date (£m) - cumulative | Forecast expenditure to complete scheme (£m) - cumulative | Forecast outturn cost (£m) | % Spend to date | Baseline expenditure profile (£m) - cumulative | [7 empty] | Forecast expenditure profile (£m) - cumulative | [7 empty] | AMP
[32 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9
[12 empty] | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 |  | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 | [5 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total
[5 empty] | Resilience | PCDW16a | Retained | [22 empty] | 0 | #DIV/0!
[5 empty] | Resilience Interconnector | PCDW16b | Dropped | [22 empty] | 0 | #DIV/0!
[5 empty] | Reservoir Safety | PCDW16c | Added | [22 empty] | 0 | #DIV/0!
[5 empty] | Resilience climate change uplift | PCDWW32 | [23 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!
[30 empty] | 0 | #DIV/0!

## Dictionary (hidden)
BonCode | BonCode Duplicate helper | Version | Description | Unit | Group | DPs | Price Base | Index | List | TotalEquation | Purpose | MergingPrinciple | Owner | Defintion | Equation
¬¬IF(ISBLANK('DPB1'!AT8),"",'DPB1'!AT8) | PCD_DPB1_MRBASE |  | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!AP5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) |  | ¬¬IF(ISBLANK('DPB1'!H8),"",'DPB1'!H8) | [7 empty] | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!AP5
¬¬IF(ISBLANK('DPB1'!BD8),"",'DPB1'!BD8) | PCD_DPB1_MRBASE_T |  | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BD5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) |  | ¬¬IF(ISBLANK('DPB1'!H8),"",'DPB1'!H8) | [7 empty] | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BD5
¬¬IF(ISBLANK('DPB1'!BH8),"",'DPB1'!BH8) | PCD_DPB1_MRBASE_O |  | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BE5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) |  | ¬¬IF(ISBLANK('DPB1'!H8),"",'DPB1'!H8) | [7 empty] | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BE5
¬¬IF(ISBLANK('DPB1'!BR8),"",'DPB1'!BR8) | PCD_DPB1_MRBASE_OT |  | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BR5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) |  | ¬¬IF(ISBLANK('DPB1'!H8),"",'DPB1'!H8) | [7 empty] | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BR5
¬¬IF(ISBLANK('DPB1'!BU8),"",'DPB1'!BU8) | PCD_DPB1_MRBASE_P |  | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BU5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) |  | ¬¬IF(ISBLANK('DPB1'!H8),"",'DPB1'!H8) | [7 empty] | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BU5
¬¬IF(ISBLANK('DPB1'!AT9),"",'DPB1'!AT9) | PCD_DPB1_MRAH |  | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!AP5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) |  | ¬¬IF(ISBLANK('DPB1'!H9),"",'DPB1'!H9) | [7 empty] | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!AP5
¬¬IF(ISBLANK('DPB1'!BD9),"",'DPB1'!BD9) | PCD_DPB1_MRAH_T |  | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BD5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) |  | ¬¬IF(ISBLANK('DPB1'!H9),"",'DPB1'!H9) | [7 empty] | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BD5
¬¬IF(ISBLANK('DPB1'!BH9),"",'DPB1'!BH9) | PCD_DPB1_MRAH_O |  | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BE5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) |  | ¬¬IF(ISBLANK('DPB1'!H9),"",'DPB1'!H9) | [7 empty] | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BE5
¬¬IF(ISBLANK('DPB1'!BR9),"",'DPB1'!BR9) | PCD_DPB1_MRAH_OT |  | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BR5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) |  | ¬¬IF(ISBLANK('DPB1'!H9),"",'DPB1'!H9) | [7 empty] | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BR5
¬¬IF(ISBLANK('DPB1'!BU9),"",'DPB1'!BU9) | PCD_DPB1_MRAH_P |  | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BU5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) |  | ¬¬IF(ISBLANK('DPB1'!H9),"",'DPB1'!H9) | [7 empty] | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BU5
¬¬IF(ISBLANK('DPB1'!AT10),"",'DPB1'!AT10) | PCD_DPB1_MRENHLEA |  | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!AP5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) |  | ¬¬IF(ISBLANK('DPB1'!H10),"",'DPB1'!H10) | [7 empty] | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!AP5
¬¬IF(ISBLANK('DPB1'!BD10),"",'DPB1'!BD10) | PCD_DPB1_MRENHLEA_T |  | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BD5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) |  | ¬¬IF(ISBLANK('DPB1'!H10),"",'DPB1'!H10) | [7 empty] | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BD5
¬¬IF(ISBLANK('DPB1'!BH10),"",'DPB1'!BH10) | PCD_DPB1_MRENHLEA_O |  | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BE5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) |  | ¬¬IF(ISBLANK('DPB1'!H10),"",'DPB1'!H10) | [7 empty] | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BE5
¬¬IF(ISBLANK('DPB1'!BR10),"",'DPB1'!BR10) | PCD_DPB1_MRENHLEA_OT |  | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BR5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) |  | ¬¬IF(ISBLANK('DPB1'!H10),"",'DPB1'!H10) | [7 empty] | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BR5
¬¬IF(ISBLANK('DPB1'!BU10),"",'DPB1'!BU10) | PCD_DPB1_MRENHLEA_P |  | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BU5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) |  | ¬¬IF(ISBLANK('DPB1'!H10),"",'DPB1'!H10) | [7 empty] | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BU5
¬¬IF(ISBLANK('DPB2'!AV8),"",'DPB2'!AV8) | PCD_DPB2_MR_BASE |  | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) |  | ¬¬IF(ISBLANK('DPB2'!H8),"",'DPB2'!H8) | [7 empty] | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!AS5
¬¬IF(ISBLANK('DPB2'!BF8),"",'DPB2'!BF8) | PCD_DPB2_MR_BASE_T |  | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) |  | ¬¬IF(ISBLANK('DPB2'!H8),"",'DPB2'!H8) | [7 empty] | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BF5
¬¬IF(ISBLANK('DPB2'!BJ8),"",'DPB2'!BJ8) | PCD_DPB2_MR_BASE_O |  | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) |  | ¬¬IF(ISBLANK('DPB2'!H8),"",'DPB2'!H8) | [7 empty] | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BG5
¬¬IF(ISBLANK('DPB2'!BT8),"",'DPB2'!BT8) | PCD_DPB2_MR_BASE_OT |  | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) |  | ¬¬IF(ISBLANK('DPB2'!H8),"",'DPB2'!H8) | [7 empty] | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BT5
¬¬IF(ISBLANK('DPB2'!BW8),"",'DPB2'!BW8) | PCD_DPB2_MR_BASE_P |  | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) |  | ¬¬IF(ISBLANK('DPB2'!H8),"",'DPB2'!H8) | [7 empty] | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BW5
¬¬IF(ISBLANK('DPB2'!AV9),"",'DPB2'!AV9) | PCD_DPB2_MR_AH |  | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) |  | ¬¬IF(ISBLANK('DPB2'!H9),"",'DPB2'!H9) | [7 empty] | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!AS5
¬¬IF(ISBLANK('DPB2'!BF9),"",'DPB2'!BF9) | PCD_DPB2_MR_AH_T |  | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) |  | ¬¬IF(ISBLANK('DPB2'!H9),"",'DPB2'!H9) | [7 empty] | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BF5
¬¬IF(ISBLANK('DPB2'!BJ9),"",'DPB2'!BJ9) | PCD_DPB2_MR_AH_O |  | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) |  | ¬¬IF(ISBLANK('DPB2'!H9),"",'DPB2'!H9) | [7 empty] | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BG5
¬¬IF(ISBLANK('DPB2'!BT9),"",'DPB2'!BT9) | PCD_DPB2_MR_AH_OT |  | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) |  | ¬¬IF(ISBLANK('DPB2'!H9),"",'DPB2'!H9) | [7 empty] | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BT5
¬¬IF(ISBLANK('DPB2'!BW9),"",'DPB2'!BW9) | PCD_DPB2_MR_AH_P |  | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) |  | ¬¬IF(ISBLANK('DPB2'!H9),"",'DPB2'!H9) | [7 empty] | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BW5
¬¬IF(ISBLANK('DPB2'!AV10),"",'DPB2'!AV10) | PCD_DPB2_MR_ENHLEA |  | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) |  | ¬¬IF(ISBLANK('DPB2'!H10),"",'DPB2'!H10) | [7 empty] | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!AS5
¬¬IF(ISBLANK('DPB2'!BF10),"",'DPB2'!BF10) | PCD_DPB2_MR_ENHLEA_T |  | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) |  | ¬¬IF(ISBLANK('DPB2'!H10),"",'DPB2'!H10) | [7 empty] | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BF5
¬¬IF(ISBLANK('DPB2'!BJ10),"",'DPB2'!BJ10) | PCD_DPB2_MR_ENHLEA_O |  | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) |  | ¬¬IF(ISBLANK('DPB2'!H10),"",'DPB2'!H10) | [7 empty] | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BG5
¬¬IF(ISBLANK('DPB2'!BT10),"",'DPB2'!BT10) | PCD_DPB2_MR_ENHLEA_OT |  | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) |  | ¬¬IF(ISBLANK('DPB2'!H10),"",'DPB2'!H10) | [7 empty] | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BT5
¬¬IF(ISBLANK('DPB2'!BW10),"",'DPB2'!BW10) | PCD_DPB2_MR_ENHLEA_P |  | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) |  | ¬¬IF(ISBLANK('DPB2'!H10),"",'DPB2'!H10) | [7 empty] | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BW5
¬¬IF(ISBLANK('DPB2'!AV11),"",'DPB2'!AV11) | PCD_DPB2_WN_RFT |  | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) |  | ¬¬IF(ISBLANK('DPB2'!H11),"",'DPB2'!H11) | [7 empty] | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!AS5
¬¬IF(ISBLANK('DPB2'!BF11),"",'DPB2'!BF11) | PCD_DPB2_WN_RFT_T |  | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) |  | ¬¬IF(ISBLANK('DPB2'!H11),"",'DPB2'!H11) | [7 empty] | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BF5
¬¬IF(ISBLANK('DPB2'!BJ11),"",'DPB2'!BJ11) | PCD_DPB2_WN_RFT_O |  | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) |  | ¬¬IF(ISBLANK('DPB2'!H11),"",'DPB2'!H11) | [7 empty] | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BG5
¬¬IF(ISBLANK('DPB2'!BT11),"",'DPB2'!BT11) | PCD_DPB2_WN_RFT_OT |  | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) |  | ¬¬IF(ISBLANK('DPB2'!H11),"",'DPB2'!H11) | [7 empty] | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BT5
¬¬IF(ISBLANK('DPB2'!BW11),"",'DPB2'!BW11) | PCD_DPB2_WN_RFT_P |  | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) |  | ¬¬IF(ISBLANK('DPB2'!H11),"",'DPB2'!H11) | [7 empty] | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BW5
¬¬IF(ISBLANK('DPB2'!AV12),"",'DPB2'!AV12) | PCD_DPB2_WWN_RFT |  | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) |  | ¬¬IF(ISBLANK('DPB2'!H12),"",'DPB2'!H12) | [7 empty] | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!AS5
¬¬IF(ISBLANK('DPB2'!BF12),"",'DPB2'!BF12) | PCD_DPB2_WWN_RFT_T |  | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) |  | ¬¬IF(ISBLANK('DPB2'!H12),"",'DPB2'!H12) | [7 empty] | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BF5
¬¬IF(ISBLANK('DPB2'!BJ12),"",'DPB2'!BJ12) | PCD_DPB2_WWN_RFT_O |  | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) |  | ¬¬IF(ISBLANK('DPB2'!H12),"",'DPB2'!H12) | [7 empty] | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BG5
¬¬IF(ISBLANK('DPB2'!BT12),"",'DPB2'!BT12) | PCD_DPB2_WWN_RFT_OT |  | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) |  | ¬¬IF(ISBLANK('DPB2'!H12),"",'DPB2'!H12) | [7 empty] | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BT5
¬¬IF(ISBLANK('DPB2'!BW12),"",'DPB2'!BW12) | PCD_DPB2_WWN_RFT_P |  | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) |  | ¬¬IF(ISBLANK('DPB2'!H12),"",'DPB2'!H12) | [7 empty] | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BW5
¬¬IF(ISBLANK(DPWW1!AT8),"",DPWW1!AT8) | PCD_DPWW1_FMS |  | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) |  | ¬¬IF(ISBLANK(DPWW1!I8),"",DPWW1!I8) | [7 empty] | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE8),"",DPWW1!BE8) | PCD_DPWW1_FMS_T |  | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) |  | ¬¬IF(ISBLANK(DPWW1!I8),"",DPWW1!I8) | [7 empty] | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH8),"",DPWW1!BH8) | PCD_DPWW1_FMS_O |  | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) |  | ¬¬IF(ISBLANK(DPWW1!I8),"",DPWW1!I8) | [7 empty] | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS8),"",DPWW1!BS8) | PCD_DPWW1_FMS_OT |  | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) |  | ¬¬IF(ISBLANK(DPWW1!I8),"",DPWW1!I8) | [7 empty] | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV8),"",DPWW1!BV8) | PCD_DPWW1_FMS_P |  | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) |  | ¬¬IF(ISBLANK(DPWW1!I8),"",DPWW1!I8) | [7 empty] | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT9),"",DPWW1!AT9) | PCD_DPWW1_FMC |  | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) |  | ¬¬IF(ISBLANK(DPWW1!I9),"",DPWW1!I9) | [7 empty] | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE9),"",DPWW1!BE9) | PCD_DPWW1_FMC_T |  | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) |  | ¬¬IF(ISBLANK(DPWW1!I9),"",DPWW1!I9) | [7 empty] | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH9),"",DPWW1!BH9) | PCD_DPWW1_FMC_O |  | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) |  | ¬¬IF(ISBLANK(DPWW1!I9),"",DPWW1!I9) | [7 empty] | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS9),"",DPWW1!BS9) | PCD_DPWW1_FMC_OT |  | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) |  | ¬¬IF(ISBLANK(DPWW1!I9),"",DPWW1!I9) | [7 empty] | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV9),"",DPWW1!BV9) | PCD_DPWW1_FMC_P |  | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) |  | ¬¬IF(ISBLANK(DPWW1!I9),"",DPWW1!I9) | [7 empty] | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT10),"",DPWW1!AT10) | PCD_DPWW1_CWQM |  | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) |  | ¬¬IF(ISBLANK(DPWW1!I10),"",DPWW1!I10) | [7 empty] | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE10),"",DPWW1!BE10) | PCD_DPWW1_CWQM_T |  | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) |  | ¬¬IF(ISBLANK(DPWW1!I10),"",DPWW1!I10) | [7 empty] | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH10),"",DPWW1!BH10) | PCD_DPWW1_CWQM_O |  | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) |  | ¬¬IF(ISBLANK(DPWW1!I10),"",DPWW1!I10) | [7 empty] | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS10),"",DPWW1!BS10) | PCD_DPWW1_CWQM_OT |  | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) |  | ¬¬IF(ISBLANK(DPWW1!I10),"",DPWW1!I10) | [7 empty] | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV10),"",DPWW1!BV10) | PCD_DPWW1_CWQM_P |  | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) |  | ¬¬IF(ISBLANK(DPWW1!I10),"",DPWW1!I10) | [7 empty] | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT11),"",DPWW1!AT11) | PCD_DPWW1_SPSO1 |  | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) |  | ¬¬IF(ISBLANK(DPWW1!I11),"",DPWW1!I11) | [7 empty] | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE11),"",DPWW1!BE11) | PCD_DPWW1_SPSO1_T |  | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) |  | ¬¬IF(ISBLANK(DPWW1!I11),"",DPWW1!I11) | [7 empty] | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH11),"",DPWW1!BH11) | PCD_DPWW1_SPSO1_O |  | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) |  | ¬¬IF(ISBLANK(DPWW1!I11),"",DPWW1!I11) | [7 empty] | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS11),"",DPWW1!BS11) | PCD_DPWW1_SPSO1_OT |  | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) |  | ¬¬IF(ISBLANK(DPWW1!I11),"",DPWW1!I11) | [7 empty] | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV11),"",DPWW1!BV11) | PCD_DPWW1_SPSO1_P |  | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) |  | ¬¬IF(ISBLANK(DPWW1!I11),"",DPWW1!I11) | [7 empty] | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT12),"",DPWW1!AT12) | PCD_DPWW1_SPSO2 |  | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) |  | ¬¬IF(ISBLANK(DPWW1!I12),"",DPWW1!I12) | [7 empty] | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE12),"",DPWW1!BE12) | PCD_DPWW1_SPSO2_T |  | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) |  | ¬¬IF(ISBLANK(DPWW1!I12),"",DPWW1!I12) | [7 empty] | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH12),"",DPWW1!BH12) | PCD_DPWW1_SPSO2_O |  | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) |  | ¬¬IF(ISBLANK(DPWW1!I12),"",DPWW1!I12) | [7 empty] | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS12),"",DPWW1!BS12) | PCD_DPWW1_SPSO2_OT |  | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) |  | ¬¬IF(ISBLANK(DPWW1!I12),"",DPWW1!I12) | [7 empty] | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV12),"",DPWW1!BV12) | PCD_DPWW1_SPSO2_P |  | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) |  | ¬¬IF(ISBLANK(DPWW1!I12),"",DPWW1!I12) | [7 empty] | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT13),"",DPWW1!AT13) | PCD_DPWW1_SPSO3 |  | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) |  | ¬¬IF(ISBLANK(DPWW1!I13),"",DPWW1!I13) | [7 empty] | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE13),"",DPWW1!BE13) | PCD_DPWW1_SPSO3_T |  | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) |  | ¬¬IF(ISBLANK(DPWW1!I13),"",DPWW1!I13) | [7 empty] | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH13),"",DPWW1!BH13) | PCD_DPWW1_SPSO3_O |  | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) |  | ¬¬IF(ISBLANK(DPWW1!I13),"",DPWW1!I13) | [7 empty] | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS13),"",DPWW1!BS13) | PCD_DPWW1_SPSO3_OT |  | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) |  | ¬¬IF(ISBLANK(DPWW1!I13),"",DPWW1!I13) | [7 empty] | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV13),"",DPWW1!BV13) | PCD_DPWW1_SPSO3_P |  | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) |  | ¬¬IF(ISBLANK(DPWW1!I13),"",DPWW1!I13) | [7 empty] | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT14),"",DPWW1!AT14) | PCD_DPWW1_SPSO4 |  | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) |  | ¬¬IF(ISBLANK(DPWW1!I14),"",DPWW1!I14) | [7 empty] | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE14),"",DPWW1!BE14) | PCD_DPWW1_SPSO4_T |  | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) |  | ¬¬IF(ISBLANK(DPWW1!I14),"",DPWW1!I14) | [7 empty] | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH14),"",DPWW1!BH14) | PCD_DPWW1_SPSO4_O |  | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) |  | ¬¬IF(ISBLANK(DPWW1!I14),"",DPWW1!I14) | [7 empty] | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS14),"",DPWW1!BS14) | PCD_DPWW1_SPSO4_OT |  | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) |  | ¬¬IF(ISBLANK(DPWW1!I14),"",DPWW1!I14) | [7 empty] | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV14),"",DPWW1!BV14) | PCD_DPWW1_SPSO4_P |  | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) |  | ¬¬IF(ISBLANK(DPWW1!I14),"",DPWW1!I14) | [7 empty] | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT15),"",DPWW1!AT15) | PCD_DPWW1_SPSO5 |  | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) |  | ¬¬IF(ISBLANK(DPWW1!I15),"",DPWW1!I15) | [7 empty] | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE15),"",DPWW1!BE15) | PCD_DPWW1_SPSO5_T |  | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) |  | ¬¬IF(ISBLANK(DPWW1!I15),"",DPWW1!I15) | [7 empty] | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH15),"",DPWW1!BH15) | PCD_DPWW1_SPSO5_O |  | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) |  | ¬¬IF(ISBLANK(DPWW1!I15),"",DPWW1!I15) | [7 empty] | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS15),"",DPWW1!BS15) | PCD_DPWW1_SPSO5_OT |  | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) |  | ¬¬IF(ISBLANK(DPWW1!I15),"",DPWW1!I15) | [7 empty] | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV15),"",DPWW1!BV15) | PCD_DPWW1_SPSO5_P |  | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) |  | ¬¬IF(ISBLANK(DPWW1!I15),"",DPWW1!I15) | [7 empty] | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT16),"",DPWW1!AT16) | PCD_DPWW1_SOFW1 |  | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) |  | ¬¬IF(ISBLANK(DPWW1!I16),"",DPWW1!I16) | [7 empty] | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE16),"",DPWW1!BE16) | PCD_DPWW1_SOFW1_T |  | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) |  | ¬¬IF(ISBLANK(DPWW1!I16),"",DPWW1!I16) | [7 empty] | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH16),"",DPWW1!BH16) | PCD_DPWW1_SOFW1_O |  | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) |  | ¬¬IF(ISBLANK(DPWW1!I16),"",DPWW1!I16) | [7 empty] | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS16),"",DPWW1!BS16) | PCD_DPWW1_SOFW1_OT |  | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) |  | ¬¬IF(ISBLANK(DPWW1!I16),"",DPWW1!I16) | [7 empty] | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV16),"",DPWW1!BV16) | PCD_DPWW1_SOFW1_P |  | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) |  | ¬¬IF(ISBLANK(DPWW1!I16),"",DPWW1!I16) | [7 empty] | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT17),"",DPWW1!AT17) | PCD_DPWW1_SOFW2 |  | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) |  | ¬¬IF(ISBLANK(DPWW1!I17),"",DPWW1!I17) | [7 empty] | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE17),"",DPWW1!BE17) | PCD_DPWW1_SOFW2_T |  | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) |  | ¬¬IF(ISBLANK(DPWW1!I17),"",DPWW1!I17) | [7 empty] | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH17),"",DPWW1!BH17) | PCD_DPWW1_SOFW2_O |  | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) |  | ¬¬IF(ISBLANK(DPWW1!I17),"",DPWW1!I17) | [7 empty] | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS17),"",DPWW1!BS17) | PCD_DPWW1_SOFW2_OT |  | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) |  | ¬¬IF(ISBLANK(DPWW1!I17),"",DPWW1!I17) | [7 empty] | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV17),"",DPWW1!BV17) | PCD_DPWW1_SOFW2_P |  | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) |  | ¬¬IF(ISBLANK(DPWW1!I17),"",DPWW1!I17) | [7 empty] | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT18),"",DPWW1!AT18) | PCD_DPWW1_SOFS |  | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) |  | ¬¬IF(ISBLANK(DPWW1!I18),"",DPWW1!I18) | [7 empty] | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE18),"",DPWW1!BE18) | PCD_DPWW1_SOFS_T |  | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) |  | ¬¬IF(ISBLANK(DPWW1!I18),"",DPWW1!I18) | [7 empty] | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH18),"",DPWW1!BH18) | PCD_DPWW1_SOFS_O |  | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) |  | ¬¬IF(ISBLANK(DPWW1!I18),"",DPWW1!I18) | [7 empty] | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS18),"",DPWW1!BS18) | PCD_DPWW1_SOFS_OT |  | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) |  | ¬¬IF(ISBLANK(DPWW1!I18),"",DPWW1!I18) | [7 empty] | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV18),"",DPWW1!BV18) | PCD_DPWW1_SOFS_P |  | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) |  | ¬¬IF(ISBLANK(DPWW1!I18),"",DPWW1!I18) | [7 empty] | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT19),"",DPWW1!AT19) | PCD_DPWW1_TCR1 |  | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) |  | ¬¬IF(ISBLANK(DPWW1!I19),"",DPWW1!I19) | [7 empty] | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE19),"",DPWW1!BE19) | PCD_DPWW1_TCR1_T |  | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) |  | ¬¬IF(ISBLANK(DPWW1!I19),"",DPWW1!I19) | [7 empty] | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH19),"",DPWW1!BH19) | PCD_DPWW1_TCR1_O |  | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) |  | ¬¬IF(ISBLANK(DPWW1!I19),"",DPWW1!I19) | [7 empty] | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS19),"",DPWW1!BS19) | PCD_DPWW1_TCR1_OT |  | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) |  | ¬¬IF(ISBLANK(DPWW1!I19),"",DPWW1!I19) | [7 empty] | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV19),"",DPWW1!BV19) | PCD_DPWW1_TCR1_P |  | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) |  | ¬¬IF(ISBLANK(DPWW1!I19),"",DPWW1!I19) | [7 empty] | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT20),"",DPWW1!AT20) | PCD_DPWW1_TCR2 |  | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) |  | ¬¬IF(ISBLANK(DPWW1!I20),"",DPWW1!I20) | [7 empty] | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE20),"",DPWW1!BE20) | PCD_DPWW1_TCR2_T |  | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) |  | ¬¬IF(ISBLANK(DPWW1!I20),"",DPWW1!I20) | [7 empty] | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH20),"",DPWW1!BH20) | PCD_DPWW1_TCR2_O |  | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) |  | ¬¬IF(ISBLANK(DPWW1!I20),"",DPWW1!I20) | [7 empty] | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS20),"",DPWW1!BS20) | PCD_DPWW1_TCR2_OT |  | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) |  | ¬¬IF(ISBLANK(DPWW1!I20),"",DPWW1!I20) | [7 empty] | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV20),"",DPWW1!BV20) | PCD_DPWW1_TCR2_P |  | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) |  | ¬¬IF(ISBLANK(DPWW1!I20),"",DPWW1!I20) | [7 empty] | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT21),"",DPWW1!AT21) | PCD_DPWW1_TNR1 |  | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) |  | ¬¬IF(ISBLANK(DPWW1!I21),"",DPWW1!I21) | [7 empty] | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE21),"",DPWW1!BE21) | PCD_DPWW1_TNR1_T |  | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) |  | ¬¬IF(ISBLANK(DPWW1!I21),"",DPWW1!I21) | [7 empty] | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH21),"",DPWW1!BH21) | PCD_DPWW1_TNR1_O |  | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) |  | ¬¬IF(ISBLANK(DPWW1!I21),"",DPWW1!I21) | [7 empty] | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS21),"",DPWW1!BS21) | PCD_DPWW1_TNR1_OT |  | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) |  | ¬¬IF(ISBLANK(DPWW1!I21),"",DPWW1!I21) | [7 empty] | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV21),"",DPWW1!BV21) | PCD_DPWW1_TNR1_P |  | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) |  | ¬¬IF(ISBLANK(DPWW1!I21),"",DPWW1!I21) | [7 empty] | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT22),"",DPWW1!AT22) | PCD_DPWW1_TNR2 |  | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) |  | ¬¬IF(ISBLANK(DPWW1!I22),"",DPWW1!I22) | [7 empty] | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE22),"",DPWW1!BE22) | PCD_DPWW1_TNR2_T |  | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) |  | ¬¬IF(ISBLANK(DPWW1!I22),"",DPWW1!I22) | [7 empty] | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH22),"",DPWW1!BH22) | PCD_DPWW1_TNR2_O |  | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) |  | ¬¬IF(ISBLANK(DPWW1!I22),"",DPWW1!I22) | [7 empty] | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS22),"",DPWW1!BS22) | PCD_DPWW1_TNR2_OT |  | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) |  | ¬¬IF(ISBLANK(DPWW1!I22),"",DPWW1!I22) | [7 empty] | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV22),"",DPWW1!BV22) | PCD_DPWW1_TNR2_P |  | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) |  | ¬¬IF(ISBLANK(DPWW1!I22),"",DPWW1!I22) | [7 empty] | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT23),"",DPWW1!AT23) | PCD_DPWW1_NBS_SOL |  | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) |  | ¬¬IF(ISBLANK(DPWW1!I23),"",DPWW1!I23) | [7 empty] | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE23),"",DPWW1!BE23) | PCD_DPWW1_NBS_SOL_T |  | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) |  | ¬¬IF(ISBLANK(DPWW1!I23),"",DPWW1!I23) | [7 empty] | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH23),"",DPWW1!BH23) | PCD_DPWW1_NBS_SOL_O |  | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) |  | ¬¬IF(ISBLANK(DPWW1!I23),"",DPWW1!I23) | [7 empty] | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS23),"",DPWW1!BS23) | PCD_DPWW1_NBS_SOL_OT |  | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) |  | ¬¬IF(ISBLANK(DPWW1!I23),"",DPWW1!I23) | [7 empty] | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV23),"",DPWW1!BV23) | PCD_DPWW1_NBS_SOL_P |  | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) |  | ¬¬IF(ISBLANK(DPWW1!I23),"",DPWW1!I23) | [7 empty] | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT24),"",DPWW1!AT24) | PCD_DPWW1_CS1 |  | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) |  | ¬¬IF(ISBLANK(DPWW1!I24),"",DPWW1!I24) | [7 empty] | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE24),"",DPWW1!BE24) | PCD_DPWW1_CS1_T |  | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) |  | ¬¬IF(ISBLANK(DPWW1!I24),"",DPWW1!I24) | [7 empty] | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH24),"",DPWW1!BH24) | PCD_DPWW1_CS1_O |  | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) |  | ¬¬IF(ISBLANK(DPWW1!I24),"",DPWW1!I24) | [7 empty] | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS24),"",DPWW1!BS24) | PCD_DPWW1_CS1_OT |  | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) |  | ¬¬IF(ISBLANK(DPWW1!I24),"",DPWW1!I24) | [7 empty] | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV24),"",DPWW1!BV24) | PCD_DPWW1_CS1_P |  | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) |  | ¬¬IF(ISBLANK(DPWW1!I24),"",DPWW1!I24) | [7 empty] | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT25),"",DPWW1!AT25) | PCD_DPWW1_CS2 |  | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) |  | ¬¬IF(ISBLANK(DPWW1!I25),"",DPWW1!I25) | [7 empty] | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE25),"",DPWW1!BE25) | PCD_DPWW1_CS2_T |  | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) |  | ¬¬IF(ISBLANK(DPWW1!I25),"",DPWW1!I25) | [7 empty] | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH25),"",DPWW1!BH25) | PCD_DPWW1_CS2_O |  | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) |  | ¬¬IF(ISBLANK(DPWW1!I25),"",DPWW1!I25) | [7 empty] | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS25),"",DPWW1!BS25) | PCD_DPWW1_CS2_OT |  | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) |  | ¬¬IF(ISBLANK(DPWW1!I25),"",DPWW1!I25) | [7 empty] | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV25),"",DPWW1!BV25) | PCD_DPWW1_CS2_P |  | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) |  | ¬¬IF(ISBLANK(DPWW1!I25),"",DPWW1!I25) | [7 empty] | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT26),"",DPWW1!AT26) | PCD_DPWW1_MBT1 |  | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) |  | ¬¬IF(ISBLANK(DPWW1!I26),"",DPWW1!I26) | [7 empty] | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE26),"",DPWW1!BE26) | PCD_DPWW1_MBT1_T |  | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) |  | ¬¬IF(ISBLANK(DPWW1!I26),"",DPWW1!I26) | [7 empty] | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH26),"",DPWW1!BH26) | PCD_DPWW1_MBT1_O |  | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) |  | ¬¬IF(ISBLANK(DPWW1!I26),"",DPWW1!I26) | [7 empty] | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS26),"",DPWW1!BS26) | PCD_DPWW1_MBT1_OT |  | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) |  | ¬¬IF(ISBLANK(DPWW1!I26),"",DPWW1!I26) | [7 empty] | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV26),"",DPWW1!BV26) | PCD_DPWW1_MBT1_P |  | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) |  | ¬¬IF(ISBLANK(DPWW1!I26),"",DPWW1!I26) | [7 empty] | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT27),"",DPWW1!AT27) | PCD_DPWW1_MBT2 |  | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) |  | ¬¬IF(ISBLANK(DPWW1!I27),"",DPWW1!I27) | [7 empty] | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE27),"",DPWW1!BE27) | PCD_DPWW1_MBT2_T |  | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) |  | ¬¬IF(ISBLANK(DPWW1!I27),"",DPWW1!I27) | [7 empty] | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH27),"",DPWW1!BH27) | PCD_DPWW1_MBT2_O |  | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) |  | ¬¬IF(ISBLANK(DPWW1!I27),"",DPWW1!I27) | [7 empty] | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS27),"",DPWW1!BS27) | PCD_DPWW1_MBT2_OT |  | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) |  | ¬¬IF(ISBLANK(DPWW1!I27),"",DPWW1!I27) | [7 empty] | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV27),"",DPWW1!BV27) | PCD_DPWW1_MBT2_P |  | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) |  | ¬¬IF(ISBLANK(DPWW1!I27),"",DPWW1!I27) | [7 empty] | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT28),"",DPWW1!AT28) | PCD_DPWW1_STR |  | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) |  | ¬¬IF(ISBLANK(DPWW1!I28),"",DPWW1!I28) | [7 empty] | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE28),"",DPWW1!BE28) | PCD_DPWW1_STR_T |  | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) |  | ¬¬IF(ISBLANK(DPWW1!I28),"",DPWW1!I28) | [7 empty] | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH28),"",DPWW1!BH28) | PCD_DPWW1_STR_O |  | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) |  | ¬¬IF(ISBLANK(DPWW1!I28),"",DPWW1!I28) | [7 empty] | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS28),"",DPWW1!BS28) | PCD_DPWW1_STR_OT |  | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) |  | ¬¬IF(ISBLANK(DPWW1!I28),"",DPWW1!I28) | [7 empty] | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV28),"",DPWW1!BV28) | PCD_DPWW1_STR_P |  | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) |  | ¬¬IF(ISBLANK(DPWW1!I28),"",DPWW1!I28) | [7 empty] | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT29),"",DPWW1!AT29) | PCD_DPWW1_25EP |  | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) |  | ¬¬IF(ISBLANK(DPWW1!I29),"",DPWW1!I29) | [7 empty] | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE29),"",DPWW1!BE29) | PCD_DPWW1_25EP_T |  | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) |  | ¬¬IF(ISBLANK(DPWW1!I29),"",DPWW1!I29) | [7 empty] | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH29),"",DPWW1!BH29) | PCD_DPWW1_25EP_O |  | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) |  | ¬¬IF(ISBLANK(DPWW1!I29),"",DPWW1!I29) | [7 empty] | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS29),"",DPWW1!BS29) | PCD_DPWW1_25EP_OT |  | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) |  | ¬¬IF(ISBLANK(DPWW1!I29),"",DPWW1!I29) | [7 empty] | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV29),"",DPWW1!BV29) | PCD_DPWW1_25EP_P |  | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) |  | ¬¬IF(ISBLANK(DPWW1!I29),"",DPWW1!I29) | [7 empty] | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT30),"",DPWW1!AT30) | PCD_DPWW1_WINIVG |  | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) |  | ¬¬IF(ISBLANK(DPWW1!I30),"",DPWW1!I30) | [7 empty] | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE30),"",DPWW1!BE30) | PCD_DPWW1_WINIVG_T |  | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) |  | ¬¬IF(ISBLANK(DPWW1!I30),"",DPWW1!I30) | [7 empty] | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH30),"",DPWW1!BH30) | PCD_DPWW1_WINIVG_O |  | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) |  | ¬¬IF(ISBLANK(DPWW1!I30),"",DPWW1!I30) | [7 empty] | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS30),"",DPWW1!BS30) | PCD_DPWW1_WINIVG_OT |  | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) |  | ¬¬IF(ISBLANK(DPWW1!I30),"",DPWW1!I30) | [7 empty] | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV30),"",DPWW1!BV30) | PCD_DPWW1_WINIVG_P |  | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) |  | ¬¬IF(ISBLANK(DPWW1!I30),"",DPWW1!I30) | [7 empty] | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT31),"",DPWW1!AT31) | PCD_DPWW1_ADWIN1 |  | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) |  | ¬¬IF(ISBLANK(DPWW1!I31),"",DPWW1!I31) | [7 empty] | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE31),"",DPWW1!BE31) | PCD_DPWW1_ADWIN1_T |  | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) |  | ¬¬IF(ISBLANK(DPWW1!I31),"",DPWW1!I31) | [7 empty] | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH31),"",DPWW1!BH31) | PCD_DPWW1_ADWIN1_O |  | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) |  | ¬¬IF(ISBLANK(DPWW1!I31),"",DPWW1!I31) | [7 empty] | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS31),"",DPWW1!BS31) | PCD_DPWW1_ADWIN1_OT |  | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) |  | ¬¬IF(ISBLANK(DPWW1!I31),"",DPWW1!I31) | [7 empty] | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV31),"",DPWW1!BV31) | PCD_DPWW1_ADWIN1_P |  | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) |  | ¬¬IF(ISBLANK(DPWW1!I31),"",DPWW1!I31) | [7 empty] | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT32),"",DPWW1!AT32) | PCD_DPWW1_ADWIN2 |  | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) |  | ¬¬IF(ISBLANK(DPWW1!I32),"",DPWW1!I32) | [7 empty] | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE32),"",DPWW1!BE32) | PCD_DPWW1_ADWIN2_T |  | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) |  | ¬¬IF(ISBLANK(DPWW1!I32),"",DPWW1!I32) | [7 empty] | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH32),"",DPWW1!BH32) | PCD_DPWW1_ADWIN2_O |  | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) |  | ¬¬IF(ISBLANK(DPWW1!I32),"",DPWW1!I32) | [7 empty] | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS32),"",DPWW1!BS32) | PCD_DPWW1_ADWIN2_OT |  | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) |  | ¬¬IF(ISBLANK(DPWW1!I32),"",DPWW1!I32) | [7 empty] | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV32),"",DPWW1!BV32) | PCD_DPWW1_ADWIN2_P |  | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) |  | ¬¬IF(ISBLANK(DPWW1!I32),"",DPWW1!I32) | [7 empty] | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT33),"",DPWW1!AT33) | PCD_DPWW1_ADWIN3 |  | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) |  | ¬¬IF(ISBLANK(DPWW1!I33),"",DPWW1!I33) | [7 empty] | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE33),"",DPWW1!BE33) | PCD_DPWW1_ADWIN3_T |  | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) |  | ¬¬IF(ISBLANK(DPWW1!I33),"",DPWW1!I33) | [7 empty] | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH33),"",DPWW1!BH33) | PCD_DPWW1_ADWIN3_O |  | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) |  | ¬¬IF(ISBLANK(DPWW1!I33),"",DPWW1!I33) | [7 empty] | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS33),"",DPWW1!BS33) | PCD_DPWW1_ADWIN3_OT |  | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) |  | ¬¬IF(ISBLANK(DPWW1!I33),"",DPWW1!I33) | [7 empty] | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV33),"",DPWW1!BV33) | PCD_DPWW1_ADWIN3_P |  | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) |  | ¬¬IF(ISBLANK(DPWW1!I33),"",DPWW1!I33) | [7 empty] | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT34),"",DPWW1!AT34) | PCD_DPWW1_SSTT |  | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) |  | ¬¬IF(ISBLANK(DPWW1!I34),"",DPWW1!I34) | [7 empty] | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE34),"",DPWW1!BE34) | PCD_DPWW1_SSTT_T |  | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) |  | ¬¬IF(ISBLANK(DPWW1!I34),"",DPWW1!I34) | [7 empty] | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH34),"",DPWW1!BH34) | PCD_DPWW1_SSTT_O |  | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) |  | ¬¬IF(ISBLANK(DPWW1!I34),"",DPWW1!I34) | [7 empty] | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS34),"",DPWW1!BS34) | PCD_DPWW1_SSTT_OT |  | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) |  | ¬¬IF(ISBLANK(DPWW1!I34),"",DPWW1!I34) | [7 empty] | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV34),"",DPWW1!BV34) | PCD_DPWW1_SSTT_P |  | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) |  | ¬¬IF(ISBLANK(DPWW1!I34),"",DPWW1!I34) | [7 empty] | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT35),"",DPWW1!AT35) | PCD_DPWW1_SSCP |  | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) |  | ¬¬IF(ISBLANK(DPWW1!I35),"",DPWW1!I35) | [7 empty] | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE35),"",DPWW1!BE35) | PCD_DPWW1_SSCP_T |  | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) |  | ¬¬IF(ISBLANK(DPWW1!I35),"",DPWW1!I35) | [7 empty] | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH35),"",DPWW1!BH35) | PCD_DPWW1_SSCP_O |  | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) |  | ¬¬IF(ISBLANK(DPWW1!I35),"",DPWW1!I35) | [7 empty] | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS35),"",DPWW1!BS35) | PCD_DPWW1_SSCP_OT |  | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) |  | ¬¬IF(ISBLANK(DPWW1!I35),"",DPWW1!I35) | [7 empty] | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV35),"",DPWW1!BV35) | PCD_DPWW1_SSCP_P |  | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) |  | ¬¬IF(ISBLANK(DPWW1!I35),"",DPWW1!I35) | [7 empty] | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT36),"",DPWW1!AT36) | PCD_DPWW1_STDW |  | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) |  | ¬¬IF(ISBLANK(DPWW1!I36),"",DPWW1!I36) | [7 empty] | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE36),"",DPWW1!BE36) | PCD_DPWW1_STDW_T |  | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) |  | ¬¬IF(ISBLANK(DPWW1!I36),"",DPWW1!I36) | [7 empty] | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH36),"",DPWW1!BH36) | PCD_DPWW1_STDW_O |  | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) |  | ¬¬IF(ISBLANK(DPWW1!I36),"",DPWW1!I36) | [7 empty] | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS36),"",DPWW1!BS36) | PCD_DPWW1_STDW_OT |  | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) |  | ¬¬IF(ISBLANK(DPWW1!I36),"",DPWW1!I36) | [7 empty] | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV36),"",DPWW1!BV36) | PCD_DPWW1_STDW_P |  | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) |  | ¬¬IF(ISBLANK(DPWW1!I36),"",DPWW1!I36) | [7 empty] | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT37),"",DPWW1!AT37) | PCD_DPWW1_STOTH1 |  | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) |  | ¬¬IF(ISBLANK(DPWW1!I37),"",DPWW1!I37) | [7 empty] | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE37),"",DPWW1!BE37) | PCD_DPWW1_STOTH1_T |  | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) |  | ¬¬IF(ISBLANK(DPWW1!I37),"",DPWW1!I37) | [7 empty] | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH37),"",DPWW1!BH37) | PCD_DPWW1_STOTH1_O |  | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) |  | ¬¬IF(ISBLANK(DPWW1!I37),"",DPWW1!I37) | [7 empty] | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS37),"",DPWW1!BS37) | PCD_DPWW1_STOTH1_OT |  | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) |  | ¬¬IF(ISBLANK(DPWW1!I37),"",DPWW1!I37) | [7 empty] | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV37),"",DPWW1!BV37) | PCD_DPWW1_STOTH1_P |  | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) |  | ¬¬IF(ISBLANK(DPWW1!I37),"",DPWW1!I37) | [7 empty] | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT38),"",DPWW1!AT38) | PCD_DPWW1_STOTH2 |  | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) |  | ¬¬IF(ISBLANK(DPWW1!I38),"",DPWW1!I38) | [7 empty] | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE38),"",DPWW1!BE38) | PCD_DPWW1_STOTH2_T |  | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) |  | ¬¬IF(ISBLANK(DPWW1!I38),"",DPWW1!I38) | [7 empty] | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH38),"",DPWW1!BH38) | PCD_DPWW1_STOTH2_O |  | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) |  | ¬¬IF(ISBLANK(DPWW1!I38),"",DPWW1!I38) | [7 empty] | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS38),"",DPWW1!BS38) | PCD_DPWW1_STOTH2_OT |  | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) |  | ¬¬IF(ISBLANK(DPWW1!I38),"",DPWW1!I38) | [7 empty] | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV38),"",DPWW1!BV38) | PCD_DPWW1_STOTH2_P |  | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) |  | ¬¬IF(ISBLANK(DPWW1!I38),"",DPWW1!I38) | [7 empty] | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT39),"",DPWW1!AT39) | PCD_DPWW1_BIO_IED |  | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) |  | ¬¬IF(ISBLANK(DPWW1!I39),"",DPWW1!I39) | [7 empty] | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE39),"",DPWW1!BE39) | PCD_DPWW1_BIO_IED_T |  | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) |  | ¬¬IF(ISBLANK(DPWW1!I39),"",DPWW1!I39) | [7 empty] | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH39),"",DPWW1!BH39) | PCD_DPWW1_BIO_IED_O |  | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) |  | ¬¬IF(ISBLANK(DPWW1!I39),"",DPWW1!I39) | [7 empty] | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS39),"",DPWW1!BS39) | PCD_DPWW1_BIO_IED_OT |  | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) |  | ¬¬IF(ISBLANK(DPWW1!I39),"",DPWW1!I39) | [7 empty] | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV39),"",DPWW1!BV39) | PCD_DPWW1_BIO_IED_P |  | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) |  | ¬¬IF(ISBLANK(DPWW1!I39),"",DPWW1!I39) | [7 empty] | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT40),"",DPWW1!AT40) | PCD_DPWW1_CCUP |  | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) |  | ¬¬IF(ISBLANK(DPWW1!I40),"",DPWW1!I40) | [7 empty] | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE40),"",DPWW1!BE40) | PCD_DPWW1_CCUP_T |  | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) |  | ¬¬IF(ISBLANK(DPWW1!I40),"",DPWW1!I40) | [7 empty] | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH40),"",DPWW1!BH40) | PCD_DPWW1_CCUP_O |  | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) |  | ¬¬IF(ISBLANK(DPWW1!I40),"",DPWW1!I40) | [7 empty] | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS40),"",DPWW1!BS40) | PCD_DPWW1_CCUP_OT |  | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) |  | ¬¬IF(ISBLANK(DPWW1!I40),"",DPWW1!I40) | [7 empty] | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV40),"",DPWW1!BV40) | PCD_DPWW1_CCUP_P |  | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) |  | ¬¬IF(ISBLANK(DPWW1!I40),"",DPWW1!I40) | [7 empty] | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT41),"",DPWW1!AT41) | PCD_DPWW1_CER1 |  | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) |  | ¬¬IF(ISBLANK(DPWW1!I41),"",DPWW1!I41) | [7 empty] | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE41),"",DPWW1!BE41) | PCD_DPWW1_CER1_T |  | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) |  | ¬¬IF(ISBLANK(DPWW1!I41),"",DPWW1!I41) | [7 empty] | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH41),"",DPWW1!BH41) | PCD_DPWW1_CER1_O |  | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) |  | ¬¬IF(ISBLANK(DPWW1!I41),"",DPWW1!I41) | [7 empty] | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS41),"",DPWW1!BS41) | PCD_DPWW1_CER1_OT |  | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) |  | ¬¬IF(ISBLANK(DPWW1!I41),"",DPWW1!I41) | [7 empty] | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV41),"",DPWW1!BV41) | PCD_DPWW1_CER1_P |  | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) |  | ¬¬IF(ISBLANK(DPWW1!I41),"",DPWW1!I41) | [7 empty] | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT42),"",DPWW1!AT42) | PCD_DPWW1_CER2 |  | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) |  | ¬¬IF(ISBLANK(DPWW1!I42),"",DPWW1!I42) | [7 empty] | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE42),"",DPWW1!BE42) | PCD_DPWW1_CER2_T |  | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) |  | ¬¬IF(ISBLANK(DPWW1!I42),"",DPWW1!I42) | [7 empty] | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH42),"",DPWW1!BH42) | PCD_DPWW1_CER2_O |  | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) |  | ¬¬IF(ISBLANK(DPWW1!I42),"",DPWW1!I42) | [7 empty] | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS42),"",DPWW1!BS42) | PCD_DPWW1_CER2_OT |  | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) |  | ¬¬IF(ISBLANK(DPWW1!I42),"",DPWW1!I42) | [7 empty] | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV42),"",DPWW1!BV42) | PCD_DPWW1_CER2_P |  | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) |  | ¬¬IF(ISBLANK(DPWW1!I42),"",DPWW1!I42) | [7 empty] | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT43),"",DPWW1!AT43) | PCD_DPWW1_CER3 |  | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) |  | ¬¬IF(ISBLANK(DPWW1!I43),"",DPWW1!I43) | [7 empty] | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE43),"",DPWW1!BE43) | PCD_DPWW1_CER3_T |  | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) |  | ¬¬IF(ISBLANK(DPWW1!I43),"",DPWW1!I43) | [7 empty] | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH43),"",DPWW1!BH43) | PCD_DPWW1_CER3_O |  | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) |  | ¬¬IF(ISBLANK(DPWW1!I43),"",DPWW1!I43) | [7 empty] | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS43),"",DPWW1!BS43) | PCD_DPWW1_CER3_OT |  | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) |  | ¬¬IF(ISBLANK(DPWW1!I43),"",DPWW1!I43) | [7 empty] | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV43),"",DPWW1!BV43) | PCD_DPWW1_CER3_P |  | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) |  | ¬¬IF(ISBLANK(DPWW1!I43),"",DPWW1!I43) | [7 empty] | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT44),"",DPWW1!AT44) | PCD_DPWW1_CER4 |  | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) |  | ¬¬IF(ISBLANK(DPWW1!I44),"",DPWW1!I44) | [7 empty] | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE44),"",DPWW1!BE44) | PCD_DPWW1_CER4_T |  | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) |  | ¬¬IF(ISBLANK(DPWW1!I44),"",DPWW1!I44) | [7 empty] | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH44),"",DPWW1!BH44) | PCD_DPWW1_CER4_O |  | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) |  | ¬¬IF(ISBLANK(DPWW1!I44),"",DPWW1!I44) | [7 empty] | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS44),"",DPWW1!BS44) | PCD_DPWW1_CER4_OT |  | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) |  | ¬¬IF(ISBLANK(DPWW1!I44),"",DPWW1!I44) | [7 empty] | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV44),"",DPWW1!BV44) | PCD_DPWW1_CER4_P |  | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) |  | ¬¬IF(ISBLANK(DPWW1!I44),"",DPWW1!I44) | [7 empty] | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT45),"",DPWW1!AT45) | PCD_DPWW1_CER5 |  | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) |  | ¬¬IF(ISBLANK(DPWW1!I45),"",DPWW1!I45) | [7 empty] | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE45),"",DPWW1!BE45) | PCD_DPWW1_CER5_T |  | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) |  | ¬¬IF(ISBLANK(DPWW1!I45),"",DPWW1!I45) | [7 empty] | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH45),"",DPWW1!BH45) | PCD_DPWW1_CER5_O |  | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) |  | ¬¬IF(ISBLANK(DPWW1!I45),"",DPWW1!I45) | [7 empty] | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS45),"",DPWW1!BS45) | PCD_DPWW1_CER5_OT |  | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) |  | ¬¬IF(ISBLANK(DPWW1!I45),"",DPWW1!I45) | [7 empty] | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV45),"",DPWW1!BV45) | PCD_DPWW1_CER5_P |  | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) |  | ¬¬IF(ISBLANK(DPWW1!I45),"",DPWW1!I45) | [7 empty] | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT46),"",DPWW1!AT46) | PCD_DPWW1_CER6 |  | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) |  | ¬¬IF(ISBLANK(DPWW1!I46),"",DPWW1!I46) | [7 empty] | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE46),"",DPWW1!BE46) | PCD_DPWW1_CER6_T |  | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) |  | ¬¬IF(ISBLANK(DPWW1!I46),"",DPWW1!I46) | [7 empty] | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH46),"",DPWW1!BH46) | PCD_DPWW1_CER6_O |  | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) |  | ¬¬IF(ISBLANK(DPWW1!I46),"",DPWW1!I46) | [7 empty] | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS46),"",DPWW1!BS46) | PCD_DPWW1_CER6_OT |  | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) |  | ¬¬IF(ISBLANK(DPWW1!I46),"",DPWW1!I46) | [7 empty] | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV46),"",DPWW1!BV46) | PCD_DPWW1_CER6_P |  | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) |  | ¬¬IF(ISBLANK(DPWW1!I46),"",DPWW1!I46) | [7 empty] | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT47),"",DPWW1!AT47) | PCD_DPWW1_INF |  | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) |  | ¬¬IF(ISBLANK(DPWW1!I47),"",DPWW1!I47) | [7 empty] | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE47),"",DPWW1!BE47) | PCD_DPWW1_INF_T |  | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) |  | ¬¬IF(ISBLANK(DPWW1!I47),"",DPWW1!I47) | [7 empty] | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH47),"",DPWW1!BH47) | PCD_DPWW1_INF_O |  | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) |  | ¬¬IF(ISBLANK(DPWW1!I47),"",DPWW1!I47) | [7 empty] | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS47),"",DPWW1!BS47) | PCD_DPWW1_INF_OT |  | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) |  | ¬¬IF(ISBLANK(DPWW1!I47),"",DPWW1!I47) | [7 empty] | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV47),"",DPWW1!BV47) | PCD_DPWW1_INF_P |  | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) |  | ¬¬IF(ISBLANK(DPWW1!I47),"",DPWW1!I47) | [7 empty] | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT48),"",DPWW1!AT48) | PCD_DPWW1_WWPF1 |  | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) |  | ¬¬IF(ISBLANK(DPWW1!I48),"",DPWW1!I48) | [7 empty] | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE48),"",DPWW1!BE48) | PCD_DPWW1_WWPF1_T |  | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) |  | ¬¬IF(ISBLANK(DPWW1!I48),"",DPWW1!I48) | [7 empty] | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH48),"",DPWW1!BH48) | PCD_DPWW1_WWPF1_O |  | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) |  | ¬¬IF(ISBLANK(DPWW1!I48),"",DPWW1!I48) | [7 empty] | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS48),"",DPWW1!BS48) | PCD_DPWW1_WWPF1_OT |  | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) |  | ¬¬IF(ISBLANK(DPWW1!I48),"",DPWW1!I48) | [7 empty] | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV48),"",DPWW1!BV48) | PCD_DPWW1_WWPF1_P |  | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) |  | ¬¬IF(ISBLANK(DPWW1!I48),"",DPWW1!I48) | [7 empty] | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT49),"",DPWW1!AT49) | PCD_DPWW1_WWPF2 |  | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) |  | ¬¬IF(ISBLANK(DPWW1!I49),"",DPWW1!I49) | [7 empty] | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE49),"",DPWW1!BE49) | PCD_DPWW1_WWPF2_T |  | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) |  | ¬¬IF(ISBLANK(DPWW1!I49),"",DPWW1!I49) | [7 empty] | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH49),"",DPWW1!BH49) | PCD_DPWW1_WWPF2_O |  | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) |  | ¬¬IF(ISBLANK(DPWW1!I49),"",DPWW1!I49) | [7 empty] | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS49),"",DPWW1!BS49) | PCD_DPWW1_WWPF2_OT |  | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) |  | ¬¬IF(ISBLANK(DPWW1!I49),"",DPWW1!I49) | [7 empty] | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV49),"",DPWW1!BV49) | PCD_DPWW1_WWPF2_P |  | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) |  | ¬¬IF(ISBLANK(DPWW1!I49),"",DPWW1!I49) | [7 empty] | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT50),"",DPWW1!AT50) | PCD_DPWW1_RRM1 |  | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) |  | ¬¬IF(ISBLANK(DPWW1!I50),"",DPWW1!I50) | [7 empty] | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE50),"",DPWW1!BE50) | PCD_DPWW1_RRM1_T |  | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) |  | ¬¬IF(ISBLANK(DPWW1!I50),"",DPWW1!I50) | [7 empty] | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH50),"",DPWW1!BH50) | PCD_DPWW1_RRM1_O |  | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) |  | ¬¬IF(ISBLANK(DPWW1!I50),"",DPWW1!I50) | [7 empty] | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS50),"",DPWW1!BS50) | PCD_DPWW1_RRM1_OT |  | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) |  | ¬¬IF(ISBLANK(DPWW1!I50),"",DPWW1!I50) | [7 empty] | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV50),"",DPWW1!BV50) | PCD_DPWW1_RRM1_P |  | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) |  | ¬¬IF(ISBLANK(DPWW1!I50),"",DPWW1!I50) | [7 empty] | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT51),"",DPWW1!AT51) | PCD_DPWW1_RRM2 |  | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) |  | ¬¬IF(ISBLANK(DPWW1!I51),"",DPWW1!I51) | [7 empty] | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE51),"",DPWW1!BE51) | PCD_DPWW1_RRM2_T |  | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) |  | ¬¬IF(ISBLANK(DPWW1!I51),"",DPWW1!I51) | [7 empty] | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH51),"",DPWW1!BH51) | PCD_DPWW1_RRM2_O |  | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) |  | ¬¬IF(ISBLANK(DPWW1!I51),"",DPWW1!I51) | [7 empty] | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS51),"",DPWW1!BS51) | PCD_DPWW1_RRM2_OT |  | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) |  | ¬¬IF(ISBLANK(DPWW1!I51),"",DPWW1!I51) | [7 empty] | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV51),"",DPWW1!BV51) | PCD_DPWW1_RRM2_P |  | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) |  | ¬¬IF(ISBLANK(DPWW1!I51),"",DPWW1!I51) | [7 empty] | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT52),"",DPWW1!AT52) | PCD_DPWW1_FP2 |  | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) |  | ¬¬IF(ISBLANK(DPWW1!I52),"",DPWW1!I52) | [7 empty] | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE52),"",DPWW1!BE52) | PCD_DPWW1_FP2_T |  | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) |  | ¬¬IF(ISBLANK(DPWW1!I52),"",DPWW1!I52) | [7 empty] | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH52),"",DPWW1!BH52) | PCD_DPWW1_FP2_O |  | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) |  | ¬¬IF(ISBLANK(DPWW1!I52),"",DPWW1!I52) | [7 empty] | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS52),"",DPWW1!BS52) | PCD_DPWW1_FP2_OT |  | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) |  | ¬¬IF(ISBLANK(DPWW1!I52),"",DPWW1!I52) | [7 empty] | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV52),"",DPWW1!BV52) | PCD_DPWW1_FP2_P |  | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) |  | ¬¬IF(ISBLANK(DPWW1!I52),"",DPWW1!I52) | [7 empty] | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT53),"",DPWW1!AT53) | PCD_DPWW1_FP2 |  | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H53),"",DPWW1!H53) |  | ¬¬IF(ISBLANK(DPWW1!I53),"",DPWW1!I53) | [7 empty] | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE53),"",DPWW1!BE53) | PCD_DPWW1_FP2_T |  | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H53),"",DPWW1!H53) |  | ¬¬IF(ISBLANK(DPWW1!I53),"",DPWW1!I53) | [7 empty] | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH53),"",DPWW1!BH53) | PCD_DPWW1_FP2_O |  | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H53),"",DPWW1!H53) |  | ¬¬IF(ISBLANK(DPWW1!I53),"",DPWW1!I53) | [7 empty] | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS53),"",DPWW1!BS53) | PCD_DPWW1_FP2_OT |  | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H53),"",DPWW1!H53) |  | ¬¬IF(ISBLANK(DPWW1!I53),"",DPWW1!I53) | [7 empty] | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV53),"",DPWW1!BV53) | PCD_DPWW1_FP2_P |  | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H53),"",DPWW1!H53) |  | ¬¬IF(ISBLANK(DPWW1!I53),"",DPWW1!I53) | [7 empty] | ¬¬DPWW1!F53 & "," & DPWW1!G53 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT54),"",DPWW1!AT54) | PCD_DPWW1_FTS |  | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) |  | ¬¬IF(ISBLANK(DPWW1!I54),"",DPWW1!I54) | [7 empty] | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE54),"",DPWW1!BE54) | PCD_DPWW1_FTS_T |  | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) |  | ¬¬IF(ISBLANK(DPWW1!I54),"",DPWW1!I54) | [7 empty] | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH54),"",DPWW1!BH54) | PCD_DPWW1_FTS_O |  | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) |  | ¬¬IF(ISBLANK(DPWW1!I54),"",DPWW1!I54) | [7 empty] | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS54),"",DPWW1!BS54) | PCD_DPWW1_FTS_OT |  | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) |  | ¬¬IF(ISBLANK(DPWW1!I54),"",DPWW1!I54) | [7 empty] | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV54),"",DPWW1!BV54) | PCD_DPWW1_FTS_P |  | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) |  | ¬¬IF(ISBLANK(DPWW1!I54),"",DPWW1!I54) | [7 empty] | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT55),"",DPWW1!AT55) | PCD_DPWW1_GRC1 |  | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) |  | ¬¬IF(ISBLANK(DPWW1!I55),"",DPWW1!I55) | [7 empty] | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE55),"",DPWW1!BE55) | PCD_DPWW1_GRC1_T |  | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) |  | ¬¬IF(ISBLANK(DPWW1!I55),"",DPWW1!I55) | [7 empty] | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH55),"",DPWW1!BH55) | PCD_DPWW1_GRC1_O |  | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) |  | ¬¬IF(ISBLANK(DPWW1!I55),"",DPWW1!I55) | [7 empty] | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS55),"",DPWW1!BS55) | PCD_DPWW1_GRC1_OT |  | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) |  | ¬¬IF(ISBLANK(DPWW1!I55),"",DPWW1!I55) | [7 empty] | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV55),"",DPWW1!BV55) | PCD_DPWW1_GRC1_P |  | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) |  | ¬¬IF(ISBLANK(DPWW1!I55),"",DPWW1!I55) | [7 empty] | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT56),"",DPWW1!AT56) | PCD_DPWW1_GRC2 |  | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) |  | ¬¬IF(ISBLANK(DPWW1!I56),"",DPWW1!I56) | [7 empty] | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE56),"",DPWW1!BE56) | PCD_DPWW1_GRC2_T |  | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) |  | ¬¬IF(ISBLANK(DPWW1!I56),"",DPWW1!I56) | [7 empty] | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH56),"",DPWW1!BH56) | PCD_DPWW1_GRC2_O |  | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) |  | ¬¬IF(ISBLANK(DPWW1!I56),"",DPWW1!I56) | [7 empty] | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS56),"",DPWW1!BS56) | PCD_DPWW1_GRC2_OT |  | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) |  | ¬¬IF(ISBLANK(DPWW1!I56),"",DPWW1!I56) | [7 empty] | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV56),"",DPWW1!BV56) | PCD_DPWW1_GRC2_P |  | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) |  | ¬¬IF(ISBLANK(DPWW1!I56),"",DPWW1!I56) | [7 empty] | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT57),"",DPWW1!AT57) | PCD_DPWW1_SOFES |  | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) |  | ¬¬IF(ISBLANK(DPWW1!I57),"",DPWW1!I57) | [7 empty] | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE57),"",DPWW1!BE57) | PCD_DPWW1_SOFES_T |  | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) |  | ¬¬IF(ISBLANK(DPWW1!I57),"",DPWW1!I57) | [7 empty] | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH57),"",DPWW1!BH57) | PCD_DPWW1_SOFES_O |  | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) |  | ¬¬IF(ISBLANK(DPWW1!I57),"",DPWW1!I57) | [7 empty] | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS57),"",DPWW1!BS57) | PCD_DPWW1_SOFES_OT |  | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) |  | ¬¬IF(ISBLANK(DPWW1!I57),"",DPWW1!I57) | [7 empty] | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV57),"",DPWW1!BV57) | PCD_DPWW1_SOFES_P |  | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) |  | ¬¬IF(ISBLANK(DPWW1!I57),"",DPWW1!I57) | [7 empty] | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT58),"",DPWW1!AT58) | PCD_DPWW1_FTFT |  | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) |  | ¬¬IF(ISBLANK(DPWW1!I58),"",DPWW1!I58) | [7 empty] | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE58),"",DPWW1!BE58) | PCD_DPWW1_FTFT_T |  | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) |  | ¬¬IF(ISBLANK(DPWW1!I58),"",DPWW1!I58) | [7 empty] | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH58),"",DPWW1!BH58) | PCD_DPWW1_FTFT_O |  | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) |  | ¬¬IF(ISBLANK(DPWW1!I58),"",DPWW1!I58) | [7 empty] | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS58),"",DPWW1!BS58) | PCD_DPWW1_FTFT_OT |  | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) |  | ¬¬IF(ISBLANK(DPWW1!I58),"",DPWW1!I58) | [7 empty] | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV58),"",DPWW1!BV58) | PCD_DPWW1_FTFT_P |  | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) |  | ¬¬IF(ISBLANK(DPWW1!I58),"",DPWW1!I58) | [7 empty] | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT59),"",DPWW1!AT59) | PCD_DPWW1_PRMVL |  | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) |  | ¬¬IF(ISBLANK(DPWW1!I59),"",DPWW1!I59) | [7 empty] | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE59),"",DPWW1!BE59) | PCD_DPWW1_PRMVL_T |  | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) |  | ¬¬IF(ISBLANK(DPWW1!I59),"",DPWW1!I59) | [7 empty] | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH59),"",DPWW1!BH59) | PCD_DPWW1_PRMVL_O |  | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) |  | ¬¬IF(ISBLANK(DPWW1!I59),"",DPWW1!I59) | [7 empty] | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS59),"",DPWW1!BS59) | PCD_DPWW1_PRMVL_OT |  | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) |  | ¬¬IF(ISBLANK(DPWW1!I59),"",DPWW1!I59) | [7 empty] | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV59),"",DPWW1!BV59) | PCD_DPWW1_PRMVL_P |  | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) |  | ¬¬IF(ISBLANK(DPWW1!I59),"",DPWW1!I59) | [7 empty] | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT60),"",DPWW1!AT60) | PCD_DPWW1_GSTW |  | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) |  | ¬¬IF(ISBLANK(DPWW1!I60),"",DPWW1!I60) | [7 empty] | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE60),"",DPWW1!BE60) | PCD_DPWW1_GSTW_T |  | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) |  | ¬¬IF(ISBLANK(DPWW1!I60),"",DPWW1!I60) | [7 empty] | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH60),"",DPWW1!BH60) | PCD_DPWW1_GSTW_O |  | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) |  | ¬¬IF(ISBLANK(DPWW1!I60),"",DPWW1!I60) | [7 empty] | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS60),"",DPWW1!BS60) | PCD_DPWW1_GSTW_OT |  | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) |  | ¬¬IF(ISBLANK(DPWW1!I60),"",DPWW1!I60) | [7 empty] | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV60),"",DPWW1!BV60) | PCD_DPWW1_GSTW_P |  | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) |  | ¬¬IF(ISBLANK(DPWW1!I60),"",DPWW1!I60) | [7 empty] | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT61),"",DPWW1!AT61) | PCD_DPWW1_TTSP |  | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) |  | ¬¬IF(ISBLANK(DPWW1!I61),"",DPWW1!I61) | [7 empty] | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE61),"",DPWW1!BE61) | PCD_DPWW1_TTSP_T |  | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) |  | ¬¬IF(ISBLANK(DPWW1!I61),"",DPWW1!I61) | [7 empty] | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH61),"",DPWW1!BH61) | PCD_DPWW1_TTSP_O |  | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) |  | ¬¬IF(ISBLANK(DPWW1!I61),"",DPWW1!I61) | [7 empty] | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS61),"",DPWW1!BS61) | PCD_DPWW1_TTSP_OT |  | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) |  | ¬¬IF(ISBLANK(DPWW1!I61),"",DPWW1!I61) | [7 empty] | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV61),"",DPWW1!BV61) | PCD_DPWW1_TTSP_P |  | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) |  | ¬¬IF(ISBLANK(DPWW1!I61),"",DPWW1!I61) | [7 empty] | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT62),"",DPWW1!AT62) | PCD_DPWW1_PR19WINCA |  | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) |  | ¬¬IF(ISBLANK(DPWW1!I62),"",DPWW1!I62) | [7 empty] | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE62),"",DPWW1!BE62) | PCD_DPWW1_PR19WINCA_T |  | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) |  | ¬¬IF(ISBLANK(DPWW1!I62),"",DPWW1!I62) | [7 empty] | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH62),"",DPWW1!BH62) | PCD_DPWW1_PR19WINCA_O |  | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) |  | ¬¬IF(ISBLANK(DPWW1!I62),"",DPWW1!I62) | [7 empty] | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS62),"",DPWW1!BS62) | PCD_DPWW1_PR19WINCA_OT |  | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) |  | ¬¬IF(ISBLANK(DPWW1!I62),"",DPWW1!I62) | [7 empty] | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV62),"",DPWW1!BV62) | PCD_DPWW1_PR19WINCA_P |  | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) |  | ¬¬IF(ISBLANK(DPWW1!I62),"",DPWW1!I62) | [7 empty] | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT63),"",DPWW1!AT63) | PCD_DPWW1_GGR1 |  | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) |  | ¬¬IF(ISBLANK(DPWW1!I63),"",DPWW1!I63) | [7 empty] | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE63),"",DPWW1!BE63) | PCD_DPWW1_GGR1_T |  | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) |  | ¬¬IF(ISBLANK(DPWW1!I63),"",DPWW1!I63) | [7 empty] | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH63),"",DPWW1!BH63) | PCD_DPWW1_GGR1_O |  | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) |  | ¬¬IF(ISBLANK(DPWW1!I63),"",DPWW1!I63) | [7 empty] | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS63),"",DPWW1!BS63) | PCD_DPWW1_GGR1_OT |  | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) |  | ¬¬IF(ISBLANK(DPWW1!I63),"",DPWW1!I63) | [7 empty] | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV63),"",DPWW1!BV63) | PCD_DPWW1_GGR1_P |  | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) |  | ¬¬IF(ISBLANK(DPWW1!I63),"",DPWW1!I63) | [7 empty] | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW1!AT64),"",DPWW1!AT64) | PCD_DPWW1_GGR2 |  | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) |  | ¬¬IF(ISBLANK(DPWW1!I64),"",DPWW1!I64) | [7 empty] | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!AQ5
¬¬IF(ISBLANK(DPWW1!BE64),"",DPWW1!BE64) | PCD_DPWW1_GGR2_T |  | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) |  | ¬¬IF(ISBLANK(DPWW1!I64),"",DPWW1!I64) | [7 empty] | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BE5
¬¬IF(ISBLANK(DPWW1!BH64),"",DPWW1!BH64) | PCD_DPWW1_GGR2_O |  | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) |  | ¬¬IF(ISBLANK(DPWW1!I64),"",DPWW1!I64) | [7 empty] | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BF5
¬¬IF(ISBLANK(DPWW1!BS64),"",DPWW1!BS64) | PCD_DPWW1_GGR2_OT |  | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) |  | ¬¬IF(ISBLANK(DPWW1!I64),"",DPWW1!I64) | [7 empty] | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BS5
¬¬IF(ISBLANK(DPWW1!BV64),"",DPWW1!BV64) | PCD_DPWW1_GGR2_P |  | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) |  | ¬¬IF(ISBLANK(DPWW1!I64),"",DPWW1!I64) | [7 empty] | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BV5
¬¬IF(ISBLANK(DPWW2!AT8),"",DPWW2!AT8) | PCD_DPWW2_FMS_NP |  | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) |  | ¬¬IF(ISBLANK(DPWW2!I8),"",DPWW2!I8) | [7 empty] | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV8),"",DPWW2!AV8) | PCD_DPWW2_FMS |  | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) |  | ¬¬IF(ISBLANK(DPWW2!I8),"",DPWW2!I8) | [7 empty] | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG8),"",DPWW2!BG8) | PCD_DPWW2_FMS_T |  | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) |  | ¬¬IF(ISBLANK(DPWW2!I8),"",DPWW2!I8) | [7 empty] | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ8),"",DPWW2!BJ8) | PCD_DPWW2_FMS_O |  | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) |  | ¬¬IF(ISBLANK(DPWW2!I8),"",DPWW2!I8) | [7 empty] | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU8),"",DPWW2!BU8) | PCD_DPWW2_FMS_OT |  | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) |  | ¬¬IF(ISBLANK(DPWW2!I8),"",DPWW2!I8) | [7 empty] | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX8),"",DPWW2!BX8) | PCD_DPWW2_FMS_P |  | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) |  | ¬¬IF(ISBLANK(DPWW2!I8),"",DPWW2!I8) | [7 empty] | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT9),"",DPWW2!AT9) | PCD_DPWW2_FMC_NP |  | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) |  | ¬¬IF(ISBLANK(DPWW2!I9),"",DPWW2!I9) | [7 empty] | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV9),"",DPWW2!AV9) | PCD_DPWW2_FMC |  | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) |  | ¬¬IF(ISBLANK(DPWW2!I9),"",DPWW2!I9) | [7 empty] | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG9),"",DPWW2!BG9) | PCD_DPWW2_FMC_T |  | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) |  | ¬¬IF(ISBLANK(DPWW2!I9),"",DPWW2!I9) | [7 empty] | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ9),"",DPWW2!BJ9) | PCD_DPWW2_FMC_O |  | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) |  | ¬¬IF(ISBLANK(DPWW2!I9),"",DPWW2!I9) | [7 empty] | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU9),"",DPWW2!BU9) | PCD_DPWW2_FMC_OT |  | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) |  | ¬¬IF(ISBLANK(DPWW2!I9),"",DPWW2!I9) | [7 empty] | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX9),"",DPWW2!BX9) | PCD_DPWW2_FMC_P |  | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) |  | ¬¬IF(ISBLANK(DPWW2!I9),"",DPWW2!I9) | [7 empty] | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT10),"",DPWW2!AT10) | PCD_DPWW2_CWQM_NP |  | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) |  | ¬¬IF(ISBLANK(DPWW2!I10),"",DPWW2!I10) | [7 empty] | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV10),"",DPWW2!AV10) | PCD_DPWW2_CWQM |  | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) |  | ¬¬IF(ISBLANK(DPWW2!I10),"",DPWW2!I10) | [7 empty] | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG10),"",DPWW2!BG10) | PCD_DPWW2_CWQM_T |  | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) |  | ¬¬IF(ISBLANK(DPWW2!I10),"",DPWW2!I10) | [7 empty] | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ10),"",DPWW2!BJ10) | PCD_DPWW2_CWQM_O |  | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) |  | ¬¬IF(ISBLANK(DPWW2!I10),"",DPWW2!I10) | [7 empty] | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU10),"",DPWW2!BU10) | PCD_DPWW2_CWQM_OT |  | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) |  | ¬¬IF(ISBLANK(DPWW2!I10),"",DPWW2!I10) | [7 empty] | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX10),"",DPWW2!BX10) | PCD_DPWW2_CWQM_P |  | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) |  | ¬¬IF(ISBLANK(DPWW2!I10),"",DPWW2!I10) | [7 empty] | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT11),"",DPWW2!AT11) | PCD_DPWW2_SPSO1_NP |  | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) |  | ¬¬IF(ISBLANK(DPWW2!I11),"",DPWW2!I11) | [7 empty] | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV11),"",DPWW2!AV11) | PCD_DPWW2_SPSO1 |  | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) |  | ¬¬IF(ISBLANK(DPWW2!I11),"",DPWW2!I11) | [7 empty] | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG11),"",DPWW2!BG11) | PCD_DPWW2_SPSO1_T |  | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) |  | ¬¬IF(ISBLANK(DPWW2!I11),"",DPWW2!I11) | [7 empty] | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ11),"",DPWW2!BJ11) | PCD_DPWW2_SPSO1_O |  | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) |  | ¬¬IF(ISBLANK(DPWW2!I11),"",DPWW2!I11) | [7 empty] | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU11),"",DPWW2!BU11) | PCD_DPWW2_SPSO1_OT |  | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) |  | ¬¬IF(ISBLANK(DPWW2!I11),"",DPWW2!I11) | [7 empty] | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX11),"",DPWW2!BX11) | PCD_DPWW2_SPSO1_P |  | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) |  | ¬¬IF(ISBLANK(DPWW2!I11),"",DPWW2!I11) | [7 empty] | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT12),"",DPWW2!AT12) | PCD_DPWW2_SPSO2_NP |  | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) |  | ¬¬IF(ISBLANK(DPWW2!I12),"",DPWW2!I12) | [7 empty] | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV12),"",DPWW2!AV12) | PCD_DPWW2_SPSO2 |  | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) |  | ¬¬IF(ISBLANK(DPWW2!I12),"",DPWW2!I12) | [7 empty] | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG12),"",DPWW2!BG12) | PCD_DPWW2_SPSO2_T |  | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) |  | ¬¬IF(ISBLANK(DPWW2!I12),"",DPWW2!I12) | [7 empty] | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ12),"",DPWW2!BJ12) | PCD_DPWW2_SPSO2_O |  | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) |  | ¬¬IF(ISBLANK(DPWW2!I12),"",DPWW2!I12) | [7 empty] | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU12),"",DPWW2!BU12) | PCD_DPWW2_SPSO2_OT |  | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) |  | ¬¬IF(ISBLANK(DPWW2!I12),"",DPWW2!I12) | [7 empty] | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX12),"",DPWW2!BX12) | PCD_DPWW2_SPSO2_P |  | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) |  | ¬¬IF(ISBLANK(DPWW2!I12),"",DPWW2!I12) | [7 empty] | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT13),"",DPWW2!AT13) | PCD_DPWW2_SPSO3_NP |  | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) |  | ¬¬IF(ISBLANK(DPWW2!I13),"",DPWW2!I13) | [7 empty] | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV13),"",DPWW2!AV13) | PCD_DPWW2_SPSO3 |  | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) |  | ¬¬IF(ISBLANK(DPWW2!I13),"",DPWW2!I13) | [7 empty] | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG13),"",DPWW2!BG13) | PCD_DPWW2_SPSO3_T |  | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) |  | ¬¬IF(ISBLANK(DPWW2!I13),"",DPWW2!I13) | [7 empty] | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ13),"",DPWW2!BJ13) | PCD_DPWW2_SPSO3_O |  | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) |  | ¬¬IF(ISBLANK(DPWW2!I13),"",DPWW2!I13) | [7 empty] | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU13),"",DPWW2!BU13) | PCD_DPWW2_SPSO3_OT |  | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) |  | ¬¬IF(ISBLANK(DPWW2!I13),"",DPWW2!I13) | [7 empty] | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX13),"",DPWW2!BX13) | PCD_DPWW2_SPSO3_P |  | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) |  | ¬¬IF(ISBLANK(DPWW2!I13),"",DPWW2!I13) | [7 empty] | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT14),"",DPWW2!AT14) | PCD_DPWW2_SPSO4_NP |  | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) |  | ¬¬IF(ISBLANK(DPWW2!I14),"",DPWW2!I14) | [7 empty] | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV14),"",DPWW2!AV14) | PCD_DPWW2_SPSO4 |  | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) |  | ¬¬IF(ISBLANK(DPWW2!I14),"",DPWW2!I14) | [7 empty] | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG14),"",DPWW2!BG14) | PCD_DPWW2_SPSO4_T |  | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) |  | ¬¬IF(ISBLANK(DPWW2!I14),"",DPWW2!I14) | [7 empty] | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ14),"",DPWW2!BJ14) | PCD_DPWW2_SPSO4_O |  | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) |  | ¬¬IF(ISBLANK(DPWW2!I14),"",DPWW2!I14) | [7 empty] | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU14),"",DPWW2!BU14) | PCD_DPWW2_SPSO4_OT |  | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) |  | ¬¬IF(ISBLANK(DPWW2!I14),"",DPWW2!I14) | [7 empty] | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX14),"",DPWW2!BX14) | PCD_DPWW2_SPSO4_P |  | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) |  | ¬¬IF(ISBLANK(DPWW2!I14),"",DPWW2!I14) | [7 empty] | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT15),"",DPWW2!AT15) | PCD_DPWW2_SPSO5_NP |  | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) |  | ¬¬IF(ISBLANK(DPWW2!I15),"",DPWW2!I15) | [7 empty] | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV15),"",DPWW2!AV15) | PCD_DPWW2_SPSO5 |  | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) |  | ¬¬IF(ISBLANK(DPWW2!I15),"",DPWW2!I15) | [7 empty] | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG15),"",DPWW2!BG15) | PCD_DPWW2_SPSO5_T |  | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) |  | ¬¬IF(ISBLANK(DPWW2!I15),"",DPWW2!I15) | [7 empty] | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ15),"",DPWW2!BJ15) | PCD_DPWW2_SPSO5_O |  | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) |  | ¬¬IF(ISBLANK(DPWW2!I15),"",DPWW2!I15) | [7 empty] | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU15),"",DPWW2!BU15) | PCD_DPWW2_SPSO5_OT |  | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) |  | ¬¬IF(ISBLANK(DPWW2!I15),"",DPWW2!I15) | [7 empty] | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX15),"",DPWW2!BX15) | PCD_DPWW2_SPSO5_P |  | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) |  | ¬¬IF(ISBLANK(DPWW2!I15),"",DPWW2!I15) | [7 empty] | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT16),"",DPWW2!AT16) | PCD_DPWW2_SOFW1_NP |  | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) |  | ¬¬IF(ISBLANK(DPWW2!I16),"",DPWW2!I16) | [7 empty] | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV16),"",DPWW2!AV16) | PCD_DPWW2_SOFW1 |  | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) |  | ¬¬IF(ISBLANK(DPWW2!I16),"",DPWW2!I16) | [7 empty] | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG16),"",DPWW2!BG16) | PCD_DPWW2_SOFW1_T |  | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) |  | ¬¬IF(ISBLANK(DPWW2!I16),"",DPWW2!I16) | [7 empty] | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ16),"",DPWW2!BJ16) | PCD_DPWW2_SOFW1_O |  | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) |  | ¬¬IF(ISBLANK(DPWW2!I16),"",DPWW2!I16) | [7 empty] | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU16),"",DPWW2!BU16) | PCD_DPWW2_SOFW1_OT |  | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) |  | ¬¬IF(ISBLANK(DPWW2!I16),"",DPWW2!I16) | [7 empty] | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX16),"",DPWW2!BX16) | PCD_DPWW2_SOFW1_P |  | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) |  | ¬¬IF(ISBLANK(DPWW2!I16),"",DPWW2!I16) | [7 empty] | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT17),"",DPWW2!AT17) | PCD_DPWW2_SOFW2_NP |  | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) |  | ¬¬IF(ISBLANK(DPWW2!I17),"",DPWW2!I17) | [7 empty] | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV17),"",DPWW2!AV17) | PCD_DPWW2_SOFW2 |  | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) |  | ¬¬IF(ISBLANK(DPWW2!I17),"",DPWW2!I17) | [7 empty] | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG17),"",DPWW2!BG17) | PCD_DPWW2_SOFW2_T |  | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) |  | ¬¬IF(ISBLANK(DPWW2!I17),"",DPWW2!I17) | [7 empty] | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ17),"",DPWW2!BJ17) | PCD_DPWW2_SOFW2_O |  | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) |  | ¬¬IF(ISBLANK(DPWW2!I17),"",DPWW2!I17) | [7 empty] | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU17),"",DPWW2!BU17) | PCD_DPWW2_SOFW2_OT |  | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) |  | ¬¬IF(ISBLANK(DPWW2!I17),"",DPWW2!I17) | [7 empty] | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX17),"",DPWW2!BX17) | PCD_DPWW2_SOFW2_P |  | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) |  | ¬¬IF(ISBLANK(DPWW2!I17),"",DPWW2!I17) | [7 empty] | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT18),"",DPWW2!AT18) | PCD_DPWW2_TCR1_NP |  | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) |  | ¬¬IF(ISBLANK(DPWW2!I18),"",DPWW2!I18) | [7 empty] | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV18),"",DPWW2!AV18) | PCD_DPWW2_TCR1 |  | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) |  | ¬¬IF(ISBLANK(DPWW2!I18),"",DPWW2!I18) | [7 empty] | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG18),"",DPWW2!BG18) | PCD_DPWW2_TCR1_T |  | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) |  | ¬¬IF(ISBLANK(DPWW2!I18),"",DPWW2!I18) | [7 empty] | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ18),"",DPWW2!BJ18) | PCD_DPWW2_TCR1_O |  | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) |  | ¬¬IF(ISBLANK(DPWW2!I18),"",DPWW2!I18) | [7 empty] | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU18),"",DPWW2!BU18) | PCD_DPWW2_TCR1_OT |  | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) |  | ¬¬IF(ISBLANK(DPWW2!I18),"",DPWW2!I18) | [7 empty] | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX18),"",DPWW2!BX18) | PCD_DPWW2_TCR1_P |  | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) |  | ¬¬IF(ISBLANK(DPWW2!I18),"",DPWW2!I18) | [7 empty] | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT19),"",DPWW2!AT19) | PCD_DPWW2_TNR1_NP |  | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) |  | ¬¬IF(ISBLANK(DPWW2!I19),"",DPWW2!I19) | [7 empty] | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV19),"",DPWW2!AV19) | PCD_DPWW2_TNR1 |  | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) |  | ¬¬IF(ISBLANK(DPWW2!I19),"",DPWW2!I19) | [7 empty] | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG19),"",DPWW2!BG19) | PCD_DPWW2_TNR1_T |  | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) |  | ¬¬IF(ISBLANK(DPWW2!I19),"",DPWW2!I19) | [7 empty] | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ19),"",DPWW2!BJ19) | PCD_DPWW2_TNR1_O |  | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) |  | ¬¬IF(ISBLANK(DPWW2!I19),"",DPWW2!I19) | [7 empty] | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU19),"",DPWW2!BU19) | PCD_DPWW2_TNR1_OT |  | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) |  | ¬¬IF(ISBLANK(DPWW2!I19),"",DPWW2!I19) | [7 empty] | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX19),"",DPWW2!BX19) | PCD_DPWW2_TNR1_P |  | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) |  | ¬¬IF(ISBLANK(DPWW2!I19),"",DPWW2!I19) | [7 empty] | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT20),"",DPWW2!AT20) | PCD_DPWW2_NBS_SOL_NP |  | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) |  | ¬¬IF(ISBLANK(DPWW2!I20),"",DPWW2!I20) | [7 empty] | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV20),"",DPWW2!AV20) | PCD_DPWW2_NBS_SOL |  | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) |  | ¬¬IF(ISBLANK(DPWW2!I20),"",DPWW2!I20) | [7 empty] | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG20),"",DPWW2!BG20) | PCD_DPWW2_NBS_SOL_T |  | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) |  | ¬¬IF(ISBLANK(DPWW2!I20),"",DPWW2!I20) | [7 empty] | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ20),"",DPWW2!BJ20) | PCD_DPWW2_NBS_SOL_O |  | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) |  | ¬¬IF(ISBLANK(DPWW2!I20),"",DPWW2!I20) | [7 empty] | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU20),"",DPWW2!BU20) | PCD_DPWW2_NBS_SOL_OT |  | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) |  | ¬¬IF(ISBLANK(DPWW2!I20),"",DPWW2!I20) | [7 empty] | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX20),"",DPWW2!BX20) | PCD_DPWW2_NBS_SOL_P |  | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) |  | ¬¬IF(ISBLANK(DPWW2!I20),"",DPWW2!I20) | [7 empty] | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT21),"",DPWW2!AT21) | PCD_DPWW2_CS1_NP |  | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) |  | ¬¬IF(ISBLANK(DPWW2!I21),"",DPWW2!I21) | [7 empty] | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV21),"",DPWW2!AV21) | PCD_DPWW2_CS1 |  | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) |  | ¬¬IF(ISBLANK(DPWW2!I21),"",DPWW2!I21) | [7 empty] | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG21),"",DPWW2!BG21) | PCD_DPWW2_CS1_T |  | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) |  | ¬¬IF(ISBLANK(DPWW2!I21),"",DPWW2!I21) | [7 empty] | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ21),"",DPWW2!BJ21) | PCD_DPWW2_CS1_O |  | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) |  | ¬¬IF(ISBLANK(DPWW2!I21),"",DPWW2!I21) | [7 empty] | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU21),"",DPWW2!BU21) | PCD_DPWW2_CS1_OT |  | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) |  | ¬¬IF(ISBLANK(DPWW2!I21),"",DPWW2!I21) | [7 empty] | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX21),"",DPWW2!BX21) | PCD_DPWW2_CS1_P |  | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) |  | ¬¬IF(ISBLANK(DPWW2!I21),"",DPWW2!I21) | [7 empty] | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT22),"",DPWW2!AT22) | PCD_DPWW2_CS2_NP |  | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) |  | ¬¬IF(ISBLANK(DPWW2!I22),"",DPWW2!I22) | [7 empty] | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV22),"",DPWW2!AV22) | PCD_DPWW2_CS2 |  | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) |  | ¬¬IF(ISBLANK(DPWW2!I22),"",DPWW2!I22) | [7 empty] | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG22),"",DPWW2!BG22) | PCD_DPWW2_CS2_T |  | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) |  | ¬¬IF(ISBLANK(DPWW2!I22),"",DPWW2!I22) | [7 empty] | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ22),"",DPWW2!BJ22) | PCD_DPWW2_CS2_O |  | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) |  | ¬¬IF(ISBLANK(DPWW2!I22),"",DPWW2!I22) | [7 empty] | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU22),"",DPWW2!BU22) | PCD_DPWW2_CS2_OT |  | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) |  | ¬¬IF(ISBLANK(DPWW2!I22),"",DPWW2!I22) | [7 empty] | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX22),"",DPWW2!BX22) | PCD_DPWW2_CS2_P |  | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) |  | ¬¬IF(ISBLANK(DPWW2!I22),"",DPWW2!I22) | [7 empty] | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT23),"",DPWW2!AT23) | PCD_DPWW2_MBT1_NP |  | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) |  | ¬¬IF(ISBLANK(DPWW2!I23),"",DPWW2!I23) | [7 empty] | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV23),"",DPWW2!AV23) | PCD_DPWW2_MBT1 |  | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) |  | ¬¬IF(ISBLANK(DPWW2!I23),"",DPWW2!I23) | [7 empty] | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG23),"",DPWW2!BG23) | PCD_DPWW2_MBT1_T |  | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) |  | ¬¬IF(ISBLANK(DPWW2!I23),"",DPWW2!I23) | [7 empty] | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ23),"",DPWW2!BJ23) | PCD_DPWW2_MBT1_O |  | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) |  | ¬¬IF(ISBLANK(DPWW2!I23),"",DPWW2!I23) | [7 empty] | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU23),"",DPWW2!BU23) | PCD_DPWW2_MBT1_OT |  | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) |  | ¬¬IF(ISBLANK(DPWW2!I23),"",DPWW2!I23) | [7 empty] | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX23),"",DPWW2!BX23) | PCD_DPWW2_MBT1_P |  | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) |  | ¬¬IF(ISBLANK(DPWW2!I23),"",DPWW2!I23) | [7 empty] | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT24),"",DPWW2!AT24) | PCD_DPWW2_STR_NP |  | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) |  | ¬¬IF(ISBLANK(DPWW2!I24),"",DPWW2!I24) | [7 empty] | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV24),"",DPWW2!AV24) | PCD_DPWW2_STR |  | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) |  | ¬¬IF(ISBLANK(DPWW2!I24),"",DPWW2!I24) | [7 empty] | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG24),"",DPWW2!BG24) | PCD_DPWW2_STR_T |  | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) |  | ¬¬IF(ISBLANK(DPWW2!I24),"",DPWW2!I24) | [7 empty] | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ24),"",DPWW2!BJ24) | PCD_DPWW2_STR_O |  | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) |  | ¬¬IF(ISBLANK(DPWW2!I24),"",DPWW2!I24) | [7 empty] | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU24),"",DPWW2!BU24) | PCD_DPWW2_STR_OT |  | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) |  | ¬¬IF(ISBLANK(DPWW2!I24),"",DPWW2!I24) | [7 empty] | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX24),"",DPWW2!BX24) | PCD_DPWW2_STR_P |  | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) |  | ¬¬IF(ISBLANK(DPWW2!I24),"",DPWW2!I24) | [7 empty] | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT25),"",DPWW2!AT25) | PCD_DPWW2_25EP_NP |  | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) |  | ¬¬IF(ISBLANK(DPWW2!I25),"",DPWW2!I25) | [7 empty] | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV25),"",DPWW2!AV25) | PCD_DPWW2_25EP |  | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) |  | ¬¬IF(ISBLANK(DPWW2!I25),"",DPWW2!I25) | [7 empty] | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG25),"",DPWW2!BG25) | PCD_DPWW2_25EP_T |  | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) |  | ¬¬IF(ISBLANK(DPWW2!I25),"",DPWW2!I25) | [7 empty] | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ25),"",DPWW2!BJ25) | PCD_DPWW2_25EP_O |  | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) |  | ¬¬IF(ISBLANK(DPWW2!I25),"",DPWW2!I25) | [7 empty] | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU25),"",DPWW2!BU25) | PCD_DPWW2_25EP_OT |  | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) |  | ¬¬IF(ISBLANK(DPWW2!I25),"",DPWW2!I25) | [7 empty] | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX25),"",DPWW2!BX25) | PCD_DPWW2_25EP_P |  | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) |  | ¬¬IF(ISBLANK(DPWW2!I25),"",DPWW2!I25) | [7 empty] | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT26),"",DPWW2!AT26) | PCD_DPWW2_WINIVG_NP |  | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) |  | ¬¬IF(ISBLANK(DPWW2!I26),"",DPWW2!I26) | [7 empty] | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV26),"",DPWW2!AV26) | PCD_DPWW2_WINIVG |  | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) |  | ¬¬IF(ISBLANK(DPWW2!I26),"",DPWW2!I26) | [7 empty] | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG26),"",DPWW2!BG26) | PCD_DPWW2_WINIVG_T |  | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) |  | ¬¬IF(ISBLANK(DPWW2!I26),"",DPWW2!I26) | [7 empty] | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ26),"",DPWW2!BJ26) | PCD_DPWW2_WINIVG_O |  | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) |  | ¬¬IF(ISBLANK(DPWW2!I26),"",DPWW2!I26) | [7 empty] | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU26),"",DPWW2!BU26) | PCD_DPWW2_WINIVG_OT |  | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) |  | ¬¬IF(ISBLANK(DPWW2!I26),"",DPWW2!I26) | [7 empty] | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX26),"",DPWW2!BX26) | PCD_DPWW2_WINIVG_P |  | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) |  | ¬¬IF(ISBLANK(DPWW2!I26),"",DPWW2!I26) | [7 empty] | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT27),"",DPWW2!AT27) | PCD_DPWW2_ADWIN1_NP |  | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) |  | ¬¬IF(ISBLANK(DPWW2!I27),"",DPWW2!I27) | [7 empty] | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV27),"",DPWW2!AV27) | PCD_DPWW2_ADWIN1 |  | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) |  | ¬¬IF(ISBLANK(DPWW2!I27),"",DPWW2!I27) | [7 empty] | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG27),"",DPWW2!BG27) | PCD_DPWW2_ADWIN1_T |  | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) |  | ¬¬IF(ISBLANK(DPWW2!I27),"",DPWW2!I27) | [7 empty] | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ27),"",DPWW2!BJ27) | PCD_DPWW2_ADWIN1_O |  | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) |  | ¬¬IF(ISBLANK(DPWW2!I27),"",DPWW2!I27) | [7 empty] | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU27),"",DPWW2!BU27) | PCD_DPWW2_ADWIN1_OT |  | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) |  | ¬¬IF(ISBLANK(DPWW2!I27),"",DPWW2!I27) | [7 empty] | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX27),"",DPWW2!BX27) | PCD_DPWW2_ADWIN1_P |  | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) |  | ¬¬IF(ISBLANK(DPWW2!I27),"",DPWW2!I27) | [7 empty] | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT28),"",DPWW2!AT28) | PCD_DPWW2_ADWIN2_NP |  | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) |  | ¬¬IF(ISBLANK(DPWW2!I28),"",DPWW2!I28) | [7 empty] | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV28),"",DPWW2!AV28) | PCD_DPWW2_ADWIN2 |  | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) |  | ¬¬IF(ISBLANK(DPWW2!I28),"",DPWW2!I28) | [7 empty] | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG28),"",DPWW2!BG28) | PCD_DPWW2_ADWIN2_T |  | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) |  | ¬¬IF(ISBLANK(DPWW2!I28),"",DPWW2!I28) | [7 empty] | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ28),"",DPWW2!BJ28) | PCD_DPWW2_ADWIN2_O |  | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) |  | ¬¬IF(ISBLANK(DPWW2!I28),"",DPWW2!I28) | [7 empty] | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU28),"",DPWW2!BU28) | PCD_DPWW2_ADWIN2_OT |  | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) |  | ¬¬IF(ISBLANK(DPWW2!I28),"",DPWW2!I28) | [7 empty] | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX28),"",DPWW2!BX28) | PCD_DPWW2_ADWIN2_P |  | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) |  | ¬¬IF(ISBLANK(DPWW2!I28),"",DPWW2!I28) | [7 empty] | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT29),"",DPWW2!AT29) | PCD_DPWW2_SSTT_NP |  | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) |  | ¬¬IF(ISBLANK(DPWW2!I29),"",DPWW2!I29) | [7 empty] | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV29),"",DPWW2!AV29) | PCD_DPWW2_SSTT |  | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) |  | ¬¬IF(ISBLANK(DPWW2!I29),"",DPWW2!I29) | [7 empty] | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG29),"",DPWW2!BG29) | PCD_DPWW2_SSTT_T |  | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) |  | ¬¬IF(ISBLANK(DPWW2!I29),"",DPWW2!I29) | [7 empty] | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ29),"",DPWW2!BJ29) | PCD_DPWW2_SSTT_O |  | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) |  | ¬¬IF(ISBLANK(DPWW2!I29),"",DPWW2!I29) | [7 empty] | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU29),"",DPWW2!BU29) | PCD_DPWW2_SSTT_OT |  | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) |  | ¬¬IF(ISBLANK(DPWW2!I29),"",DPWW2!I29) | [7 empty] | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX29),"",DPWW2!BX29) | PCD_DPWW2_SSTT_P |  | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) |  | ¬¬IF(ISBLANK(DPWW2!I29),"",DPWW2!I29) | [7 empty] | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT30),"",DPWW2!AT30) | PCD_DPWW2_SSCP_NP |  | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) |  | ¬¬IF(ISBLANK(DPWW2!I30),"",DPWW2!I30) | [7 empty] | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV30),"",DPWW2!AV30) | PCD_DPWW2_SSCP |  | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) |  | ¬¬IF(ISBLANK(DPWW2!I30),"",DPWW2!I30) | [7 empty] | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG30),"",DPWW2!BG30) | PCD_DPWW2_SSCP_T |  | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) |  | ¬¬IF(ISBLANK(DPWW2!I30),"",DPWW2!I30) | [7 empty] | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ30),"",DPWW2!BJ30) | PCD_DPWW2_SSCP_O |  | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) |  | ¬¬IF(ISBLANK(DPWW2!I30),"",DPWW2!I30) | [7 empty] | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU30),"",DPWW2!BU30) | PCD_DPWW2_SSCP_OT |  | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) |  | ¬¬IF(ISBLANK(DPWW2!I30),"",DPWW2!I30) | [7 empty] | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX30),"",DPWW2!BX30) | PCD_DPWW2_SSCP_P |  | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) |  | ¬¬IF(ISBLANK(DPWW2!I30),"",DPWW2!I30) | [7 empty] | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT31),"",DPWW2!AT31) | PCD_DPWW2_STDW_NP |  | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) |  | ¬¬IF(ISBLANK(DPWW2!I31),"",DPWW2!I31) | [7 empty] | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV31),"",DPWW2!AV31) | PCD_DPWW2_STDW |  | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) |  | ¬¬IF(ISBLANK(DPWW2!I31),"",DPWW2!I31) | [7 empty] | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG31),"",DPWW2!BG31) | PCD_DPWW2_STDW_T |  | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) |  | ¬¬IF(ISBLANK(DPWW2!I31),"",DPWW2!I31) | [7 empty] | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ31),"",DPWW2!BJ31) | PCD_DPWW2_STDW_O |  | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) |  | ¬¬IF(ISBLANK(DPWW2!I31),"",DPWW2!I31) | [7 empty] | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU31),"",DPWW2!BU31) | PCD_DPWW2_STDW_OT |  | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) |  | ¬¬IF(ISBLANK(DPWW2!I31),"",DPWW2!I31) | [7 empty] | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX31),"",DPWW2!BX31) | PCD_DPWW2_STDW_P |  | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) |  | ¬¬IF(ISBLANK(DPWW2!I31),"",DPWW2!I31) | [7 empty] | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT32),"",DPWW2!AT32) | PCD_DPWW2_STOTH1_NP |  | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) |  | ¬¬IF(ISBLANK(DPWW2!I32),"",DPWW2!I32) | [7 empty] | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV32),"",DPWW2!AV32) | PCD_DPWW2_STOTH1 |  | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) |  | ¬¬IF(ISBLANK(DPWW2!I32),"",DPWW2!I32) | [7 empty] | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG32),"",DPWW2!BG32) | PCD_DPWW2_STOTH1_T |  | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) |  | ¬¬IF(ISBLANK(DPWW2!I32),"",DPWW2!I32) | [7 empty] | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ32),"",DPWW2!BJ32) | PCD_DPWW2_STOTH1_O |  | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) |  | ¬¬IF(ISBLANK(DPWW2!I32),"",DPWW2!I32) | [7 empty] | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU32),"",DPWW2!BU32) | PCD_DPWW2_STOTH1_OT |  | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) |  | ¬¬IF(ISBLANK(DPWW2!I32),"",DPWW2!I32) | [7 empty] | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX32),"",DPWW2!BX32) | PCD_DPWW2_STOTH1_P |  | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) |  | ¬¬IF(ISBLANK(DPWW2!I32),"",DPWW2!I32) | [7 empty] | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT33),"",DPWW2!AT33) | PCD_DPWW2_STOTH2_NP |  | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) |  | ¬¬IF(ISBLANK(DPWW2!I33),"",DPWW2!I33) | [7 empty] | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV33),"",DPWW2!AV33) | PCD_DPWW2_STOTH2 |  | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) |  | ¬¬IF(ISBLANK(DPWW2!I33),"",DPWW2!I33) | [7 empty] | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG33),"",DPWW2!BG33) | PCD_DPWW2_STOTH2_T |  | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) |  | ¬¬IF(ISBLANK(DPWW2!I33),"",DPWW2!I33) | [7 empty] | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ33),"",DPWW2!BJ33) | PCD_DPWW2_STOTH2_O |  | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) |  | ¬¬IF(ISBLANK(DPWW2!I33),"",DPWW2!I33) | [7 empty] | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU33),"",DPWW2!BU33) | PCD_DPWW2_STOTH2_OT |  | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) |  | ¬¬IF(ISBLANK(DPWW2!I33),"",DPWW2!I33) | [7 empty] | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX33),"",DPWW2!BX33) | PCD_DPWW2_STOTH2_P |  | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) |  | ¬¬IF(ISBLANK(DPWW2!I33),"",DPWW2!I33) | [7 empty] | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT34),"",DPWW2!AT34) | PCD_DPWW2_BIO_IED_NP |  | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) |  | ¬¬IF(ISBLANK(DPWW2!I34),"",DPWW2!I34) | [7 empty] | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV34),"",DPWW2!AV34) | PCD_DPWW2_BIO_IED |  | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) |  | ¬¬IF(ISBLANK(DPWW2!I34),"",DPWW2!I34) | [7 empty] | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG34),"",DPWW2!BG34) | PCD_DPWW2_BIO_IED_T |  | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) |  | ¬¬IF(ISBLANK(DPWW2!I34),"",DPWW2!I34) | [7 empty] | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ34),"",DPWW2!BJ34) | PCD_DPWW2_BIO_IED_O |  | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) |  | ¬¬IF(ISBLANK(DPWW2!I34),"",DPWW2!I34) | [7 empty] | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU34),"",DPWW2!BU34) | PCD_DPWW2_BIO_IED_OT |  | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) |  | ¬¬IF(ISBLANK(DPWW2!I34),"",DPWW2!I34) | [7 empty] | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX34),"",DPWW2!BX34) | PCD_DPWW2_BIO_IED_P |  | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) |  | ¬¬IF(ISBLANK(DPWW2!I34),"",DPWW2!I34) | [7 empty] | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT35),"",DPWW2!AT35) | PCD_DPWW2_CCUP_NP |  | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) |  | ¬¬IF(ISBLANK(DPWW2!I35),"",DPWW2!I35) | [7 empty] | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV35),"",DPWW2!AV35) | PCD_DPWW2_CCUP |  | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) |  | ¬¬IF(ISBLANK(DPWW2!I35),"",DPWW2!I35) | [7 empty] | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG35),"",DPWW2!BG35) | PCD_DPWW2_CCUP_T |  | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) |  | ¬¬IF(ISBLANK(DPWW2!I35),"",DPWW2!I35) | [7 empty] | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ35),"",DPWW2!BJ35) | PCD_DPWW2_CCUP_O |  | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) |  | ¬¬IF(ISBLANK(DPWW2!I35),"",DPWW2!I35) | [7 empty] | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU35),"",DPWW2!BU35) | PCD_DPWW2_CCUP_OT |  | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) |  | ¬¬IF(ISBLANK(DPWW2!I35),"",DPWW2!I35) | [7 empty] | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX35),"",DPWW2!BX35) | PCD_DPWW2_CCUP_P |  | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) |  | ¬¬IF(ISBLANK(DPWW2!I35),"",DPWW2!I35) | [7 empty] | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT36),"",DPWW2!AT36) | PCD_DPWW2_CER1_NP |  | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) |  | ¬¬IF(ISBLANK(DPWW2!I36),"",DPWW2!I36) | [7 empty] | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV36),"",DPWW2!AV36) | PCD_DPWW2_CER1 |  | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) |  | ¬¬IF(ISBLANK(DPWW2!I36),"",DPWW2!I36) | [7 empty] | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG36),"",DPWW2!BG36) | PCD_DPWW2_CER1_T |  | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) |  | ¬¬IF(ISBLANK(DPWW2!I36),"",DPWW2!I36) | [7 empty] | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ36),"",DPWW2!BJ36) | PCD_DPWW2_CER1_O |  | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) |  | ¬¬IF(ISBLANK(DPWW2!I36),"",DPWW2!I36) | [7 empty] | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU36),"",DPWW2!BU36) | PCD_DPWW2_CER1_OT |  | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) |  | ¬¬IF(ISBLANK(DPWW2!I36),"",DPWW2!I36) | [7 empty] | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX36),"",DPWW2!BX36) | PCD_DPWW2_CER1_P |  | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) |  | ¬¬IF(ISBLANK(DPWW2!I36),"",DPWW2!I36) | [7 empty] | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT37),"",DPWW2!AT37) | PCD_DPWW2_INF_NP |  | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) |  | ¬¬IF(ISBLANK(DPWW2!I37),"",DPWW2!I37) | [7 empty] | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV37),"",DPWW2!AV37) | PCD_DPWW2_INF |  | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) |  | ¬¬IF(ISBLANK(DPWW2!I37),"",DPWW2!I37) | [7 empty] | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG37),"",DPWW2!BG37) | PCD_DPWW2_INF_T |  | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) |  | ¬¬IF(ISBLANK(DPWW2!I37),"",DPWW2!I37) | [7 empty] | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ37),"",DPWW2!BJ37) | PCD_DPWW2_INF_O |  | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) |  | ¬¬IF(ISBLANK(DPWW2!I37),"",DPWW2!I37) | [7 empty] | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU37),"",DPWW2!BU37) | PCD_DPWW2_INF_OT |  | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) |  | ¬¬IF(ISBLANK(DPWW2!I37),"",DPWW2!I37) | [7 empty] | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX37),"",DPWW2!BX37) | PCD_DPWW2_INF_P |  | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) |  | ¬¬IF(ISBLANK(DPWW2!I37),"",DPWW2!I37) | [7 empty] | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT38),"",DPWW2!AT38) | PCD_DPWW2_WWPF1_NP |  | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) |  | ¬¬IF(ISBLANK(DPWW2!I38),"",DPWW2!I38) | [7 empty] | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV38),"",DPWW2!AV38) | PCD_DPWW2_WWPF1 |  | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) |  | ¬¬IF(ISBLANK(DPWW2!I38),"",DPWW2!I38) | [7 empty] | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG38),"",DPWW2!BG38) | PCD_DPWW2_WWPF1_T |  | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) |  | ¬¬IF(ISBLANK(DPWW2!I38),"",DPWW2!I38) | [7 empty] | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ38),"",DPWW2!BJ38) | PCD_DPWW2_WWPF1_O |  | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) |  | ¬¬IF(ISBLANK(DPWW2!I38),"",DPWW2!I38) | [7 empty] | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU38),"",DPWW2!BU38) | PCD_DPWW2_WWPF1_OT |  | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) |  | ¬¬IF(ISBLANK(DPWW2!I38),"",DPWW2!I38) | [7 empty] | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX38),"",DPWW2!BX38) | PCD_DPWW2_WWPF1_P |  | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) |  | ¬¬IF(ISBLANK(DPWW2!I38),"",DPWW2!I38) | [7 empty] | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT39),"",DPWW2!AT39) | PCD_DPWW2_RRM_NP |  | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) |  | ¬¬IF(ISBLANK(DPWW2!I39),"",DPWW2!I39) | [7 empty] | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV39),"",DPWW2!AV39) | PCD_DPWW2_RRM |  | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) |  | ¬¬IF(ISBLANK(DPWW2!I39),"",DPWW2!I39) | [7 empty] | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG39),"",DPWW2!BG39) | PCD_DPWW2_RRM_T |  | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) |  | ¬¬IF(ISBLANK(DPWW2!I39),"",DPWW2!I39) | [7 empty] | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ39),"",DPWW2!BJ39) | PCD_DPWW2_RRM_O |  | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) |  | ¬¬IF(ISBLANK(DPWW2!I39),"",DPWW2!I39) | [7 empty] | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU39),"",DPWW2!BU39) | PCD_DPWW2_RRM_OT |  | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) |  | ¬¬IF(ISBLANK(DPWW2!I39),"",DPWW2!I39) | [7 empty] | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX39),"",DPWW2!BX39) | PCD_DPWW2_RRM_P |  | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) |  | ¬¬IF(ISBLANK(DPWW2!I39),"",DPWW2!I39) | [7 empty] | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT40),"",DPWW2!AT40) | PCD_DPWW2_FP_NP |  | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) |  | ¬¬IF(ISBLANK(DPWW2!I40),"",DPWW2!I40) | [7 empty] | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV40),"",DPWW2!AV40) | PCD_DPWW2_FP |  | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) |  | ¬¬IF(ISBLANK(DPWW2!I40),"",DPWW2!I40) | [7 empty] | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG40),"",DPWW2!BG40) | PCD_DPWW2_FP_T |  | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) |  | ¬¬IF(ISBLANK(DPWW2!I40),"",DPWW2!I40) | [7 empty] | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ40),"",DPWW2!BJ40) | PCD_DPWW2_FP_O |  | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) |  | ¬¬IF(ISBLANK(DPWW2!I40),"",DPWW2!I40) | [7 empty] | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU40),"",DPWW2!BU40) | PCD_DPWW2_FP_OT |  | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) |  | ¬¬IF(ISBLANK(DPWW2!I40),"",DPWW2!I40) | [7 empty] | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX40),"",DPWW2!BX40) | PCD_DPWW2_FP_P |  | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) |  | ¬¬IF(ISBLANK(DPWW2!I40),"",DPWW2!I40) | [7 empty] | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT41),"",DPWW2!AT41) | PCD_DPWW2_FP_NP |  | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H41),"",DPWW2!H41) |  | ¬¬IF(ISBLANK(DPWW2!I41),"",DPWW2!I41) | [7 empty] | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV41),"",DPWW2!AV41) | PCD_DPWW2_FP |  | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H41),"",DPWW2!H41) |  | ¬¬IF(ISBLANK(DPWW2!I41),"",DPWW2!I41) | [7 empty] | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG41),"",DPWW2!BG41) | PCD_DPWW2_FP_T |  | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H41),"",DPWW2!H41) |  | ¬¬IF(ISBLANK(DPWW2!I41),"",DPWW2!I41) | [7 empty] | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ41),"",DPWW2!BJ41) | PCD_DPWW2_FP_O |  | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H41),"",DPWW2!H41) |  | ¬¬IF(ISBLANK(DPWW2!I41),"",DPWW2!I41) | [7 empty] | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU41),"",DPWW2!BU41) | PCD_DPWW2_FP_OT |  | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H41),"",DPWW2!H41) |  | ¬¬IF(ISBLANK(DPWW2!I41),"",DPWW2!I41) | [7 empty] | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX41),"",DPWW2!BX41) | PCD_DPWW2_FP_P |  | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H41),"",DPWW2!H41) |  | ¬¬IF(ISBLANK(DPWW2!I41),"",DPWW2!I41) | [7 empty] | ¬¬DPWW2!F41 & "," & DPWW2!G41 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT42),"",DPWW2!AT42) | PCD_DPWW2_FTS_NP |  | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) |  | ¬¬IF(ISBLANK(DPWW2!I42),"",DPWW2!I42) | [7 empty] | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV42),"",DPWW2!AV42) | PCD_DPWW2_FTS |  | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) |  | ¬¬IF(ISBLANK(DPWW2!I42),"",DPWW2!I42) | [7 empty] | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG42),"",DPWW2!BG42) | PCD_DPWW2_FTS_T |  | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) |  | ¬¬IF(ISBLANK(DPWW2!I42),"",DPWW2!I42) | [7 empty] | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ42),"",DPWW2!BJ42) | PCD_DPWW2_FTS_O |  | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) |  | ¬¬IF(ISBLANK(DPWW2!I42),"",DPWW2!I42) | [7 empty] | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU42),"",DPWW2!BU42) | PCD_DPWW2_FTS_OT |  | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) |  | ¬¬IF(ISBLANK(DPWW2!I42),"",DPWW2!I42) | [7 empty] | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX42),"",DPWW2!BX42) | PCD_DPWW2_FTS_P |  | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) |  | ¬¬IF(ISBLANK(DPWW2!I42),"",DPWW2!I42) | [7 empty] | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT43),"",DPWW2!AT43) | PCD_DPWW2_PR19GRC_NP |  | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) |  | ¬¬IF(ISBLANK(DPWW2!I43),"",DPWW2!I43) | [7 empty] | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV43),"",DPWW2!AV43) | PCD_DPWW2_PR19GRC |  | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) |  | ¬¬IF(ISBLANK(DPWW2!I43),"",DPWW2!I43) | [7 empty] | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG43),"",DPWW2!BG43) | PCD_DPWW2_PR19GRC_T |  | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) |  | ¬¬IF(ISBLANK(DPWW2!I43),"",DPWW2!I43) | [7 empty] | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ43),"",DPWW2!BJ43) | PCD_DPWW2_PR19GRC_O |  | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) |  | ¬¬IF(ISBLANK(DPWW2!I43),"",DPWW2!I43) | [7 empty] | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU43),"",DPWW2!BU43) | PCD_DPWW2_PR19GRC_OT |  | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) |  | ¬¬IF(ISBLANK(DPWW2!I43),"",DPWW2!I43) | [7 empty] | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX43),"",DPWW2!BX43) | PCD_DPWW2_PR19GRC_P |  | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) |  | ¬¬IF(ISBLANK(DPWW2!I43),"",DPWW2!I43) | [7 empty] | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT44),"",DPWW2!AT44) | PCD_DPWW2_SOFES_NP |  | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) |  | ¬¬IF(ISBLANK(DPWW2!I44),"",DPWW2!I44) | [7 empty] | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV44),"",DPWW2!AV44) | PCD_DPWW2_SOFES |  | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) |  | ¬¬IF(ISBLANK(DPWW2!I44),"",DPWW2!I44) | [7 empty] | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG44),"",DPWW2!BG44) | PCD_DPWW2_SOFES_T |  | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) |  | ¬¬IF(ISBLANK(DPWW2!I44),"",DPWW2!I44) | [7 empty] | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ44),"",DPWW2!BJ44) | PCD_DPWW2_SOFES_O |  | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) |  | ¬¬IF(ISBLANK(DPWW2!I44),"",DPWW2!I44) | [7 empty] | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU44),"",DPWW2!BU44) | PCD_DPWW2_SOFES_OT |  | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) |  | ¬¬IF(ISBLANK(DPWW2!I44),"",DPWW2!I44) | [7 empty] | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX44),"",DPWW2!BX44) | PCD_DPWW2_SOFES_P |  | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) |  | ¬¬IF(ISBLANK(DPWW2!I44),"",DPWW2!I44) | [7 empty] | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT45),"",DPWW2!AT45) | PCD_DPWW2_FTFT_NP |  | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) |  | ¬¬IF(ISBLANK(DPWW2!I45),"",DPWW2!I45) | [7 empty] | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV45),"",DPWW2!AV45) | PCD_DPWW2_FTFT |  | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) |  | ¬¬IF(ISBLANK(DPWW2!I45),"",DPWW2!I45) | [7 empty] | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG45),"",DPWW2!BG45) | PCD_DPWW2_FTFT_T |  | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) |  | ¬¬IF(ISBLANK(DPWW2!I45),"",DPWW2!I45) | [7 empty] | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ45),"",DPWW2!BJ45) | PCD_DPWW2_FTFT_O |  | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) |  | ¬¬IF(ISBLANK(DPWW2!I45),"",DPWW2!I45) | [7 empty] | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU45),"",DPWW2!BU45) | PCD_DPWW2_FTFT_OT |  | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) |  | ¬¬IF(ISBLANK(DPWW2!I45),"",DPWW2!I45) | [7 empty] | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX45),"",DPWW2!BX45) | PCD_DPWW2_FTFT_P |  | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) |  | ¬¬IF(ISBLANK(DPWW2!I45),"",DPWW2!I45) | [7 empty] | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT46),"",DPWW2!AT46) | PCD_DPWW2_PRMVL_NP |  | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) |  | ¬¬IF(ISBLANK(DPWW2!I46),"",DPWW2!I46) | [7 empty] | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV46),"",DPWW2!AV46) | PCD_DPWW2_PRMVL |  | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) |  | ¬¬IF(ISBLANK(DPWW2!I46),"",DPWW2!I46) | [7 empty] | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG46),"",DPWW2!BG46) | PCD_DPWW2_PRMVL_T |  | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) |  | ¬¬IF(ISBLANK(DPWW2!I46),"",DPWW2!I46) | [7 empty] | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ46),"",DPWW2!BJ46) | PCD_DPWW2_PRMVL_O |  | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) |  | ¬¬IF(ISBLANK(DPWW2!I46),"",DPWW2!I46) | [7 empty] | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU46),"",DPWW2!BU46) | PCD_DPWW2_PRMVL_OT |  | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) |  | ¬¬IF(ISBLANK(DPWW2!I46),"",DPWW2!I46) | [7 empty] | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX46),"",DPWW2!BX46) | PCD_DPWW2_PRMVL_P |  | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) |  | ¬¬IF(ISBLANK(DPWW2!I46),"",DPWW2!I46) | [7 empty] | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT47),"",DPWW2!AT47) | PCD_DPWW2_GSTW_NP |  | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) |  | ¬¬IF(ISBLANK(DPWW2!I47),"",DPWW2!I47) | [7 empty] | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV47),"",DPWW2!AV47) | PCD_DPWW2_GSTW |  | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) |  | ¬¬IF(ISBLANK(DPWW2!I47),"",DPWW2!I47) | [7 empty] | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG47),"",DPWW2!BG47) | PCD_DPWW2_GSTW_T |  | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) |  | ¬¬IF(ISBLANK(DPWW2!I47),"",DPWW2!I47) | [7 empty] | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ47),"",DPWW2!BJ47) | PCD_DPWW2_GSTW_O |  | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) |  | ¬¬IF(ISBLANK(DPWW2!I47),"",DPWW2!I47) | [7 empty] | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU47),"",DPWW2!BU47) | PCD_DPWW2_GSTW_OT |  | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) |  | ¬¬IF(ISBLANK(DPWW2!I47),"",DPWW2!I47) | [7 empty] | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX47),"",DPWW2!BX47) | PCD_DPWW2_GSTW_P |  | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) |  | ¬¬IF(ISBLANK(DPWW2!I47),"",DPWW2!I47) | [7 empty] | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT48),"",DPWW2!AT48) | PCD_DPWW2_TTSP_NP |  | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) |  | ¬¬IF(ISBLANK(DPWW2!I48),"",DPWW2!I48) | [7 empty] | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV48),"",DPWW2!AV48) | PCD_DPWW2_TTSP |  | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) |  | ¬¬IF(ISBLANK(DPWW2!I48),"",DPWW2!I48) | [7 empty] | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG48),"",DPWW2!BG48) | PCD_DPWW2_TTSP_T |  | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) |  | ¬¬IF(ISBLANK(DPWW2!I48),"",DPWW2!I48) | [7 empty] | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ48),"",DPWW2!BJ48) | PCD_DPWW2_TTSP_O |  | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) |  | ¬¬IF(ISBLANK(DPWW2!I48),"",DPWW2!I48) | [7 empty] | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU48),"",DPWW2!BU48) | PCD_DPWW2_TTSP_OT |  | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) |  | ¬¬IF(ISBLANK(DPWW2!I48),"",DPWW2!I48) | [7 empty] | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX48),"",DPWW2!BX48) | PCD_DPWW2_TTSP_P |  | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) |  | ¬¬IF(ISBLANK(DPWW2!I48),"",DPWW2!I48) | [7 empty] | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT49),"",DPWW2!AT49) | PCD_DPWW2_PR19WINCA_NP |  | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) |  | ¬¬IF(ISBLANK(DPWW2!I49),"",DPWW2!I49) | [7 empty] | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV49),"",DPWW2!AV49) | PCD_DPWW2_PR19WINCA |  | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) |  | ¬¬IF(ISBLANK(DPWW2!I49),"",DPWW2!I49) | [7 empty] | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG49),"",DPWW2!BG49) | PCD_DPWW2_PR19WINCA_T |  | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) |  | ¬¬IF(ISBLANK(DPWW2!I49),"",DPWW2!I49) | [7 empty] | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ49),"",DPWW2!BJ49) | PCD_DPWW2_PR19WINCA_O |  | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) |  | ¬¬IF(ISBLANK(DPWW2!I49),"",DPWW2!I49) | [7 empty] | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU49),"",DPWW2!BU49) | PCD_DPWW2_PR19WINCA_OT |  | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) |  | ¬¬IF(ISBLANK(DPWW2!I49),"",DPWW2!I49) | [7 empty] | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX49),"",DPWW2!BX49) | PCD_DPWW2_PR19WINCA_P |  | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) |  | ¬¬IF(ISBLANK(DPWW2!I49),"",DPWW2!I49) | [7 empty] | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT50),"",DPWW2!AT50) | PCD_DPWW2_GGR1_NP |  | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) |  | ¬¬IF(ISBLANK(DPWW2!I50),"",DPWW2!I50) | [7 empty] | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV50),"",DPWW2!AV50) | PCD_DPWW2_GGR1 |  | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) |  | ¬¬IF(ISBLANK(DPWW2!I50),"",DPWW2!I50) | [7 empty] | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG50),"",DPWW2!BG50) | PCD_DPWW2_GGR1_T |  | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) |  | ¬¬IF(ISBLANK(DPWW2!I50),"",DPWW2!I50) | [7 empty] | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ50),"",DPWW2!BJ50) | PCD_DPWW2_GGR1_O |  | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) |  | ¬¬IF(ISBLANK(DPWW2!I50),"",DPWW2!I50) | [7 empty] | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU50),"",DPWW2!BU50) | PCD_DPWW2_GGR1_OT |  | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) |  | ¬¬IF(ISBLANK(DPWW2!I50),"",DPWW2!I50) | [7 empty] | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX50),"",DPWW2!BX50) | PCD_DPWW2_GGR1_P |  | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) |  | ¬¬IF(ISBLANK(DPWW2!I50),"",DPWW2!I50) | [7 empty] | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT51),"",DPWW2!AT51) | PCD_DPWW2_GGR2_NP |  | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H51),"",DPWW2!H51) |  | ¬¬IF(ISBLANK(DPWW2!I51),"",DPWW2!I51) | [7 empty] | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV51),"",DPWW2!AV51) | PCD_DPWW2_GGR2 |  | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H51),"",DPWW2!H51) |  | ¬¬IF(ISBLANK(DPWW2!I51),"",DPWW2!I51) | [7 empty] | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG51),"",DPWW2!BG51) | PCD_DPWW2_GGR2_T |  | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H51),"",DPWW2!H51) |  | ¬¬IF(ISBLANK(DPWW2!I51),"",DPWW2!I51) | [7 empty] | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ51),"",DPWW2!BJ51) | PCD_DPWW2_GGR2_O |  | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H51),"",DPWW2!H51) |  | ¬¬IF(ISBLANK(DPWW2!I51),"",DPWW2!I51) | [7 empty] | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU51),"",DPWW2!BU51) | PCD_DPWW2_GGR2_OT |  | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H51),"",DPWW2!H51) |  | ¬¬IF(ISBLANK(DPWW2!I51),"",DPWW2!I51) | [7 empty] | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX51),"",DPWW2!BX51) | PCD_DPWW2_GGR2_P |  | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H51),"",DPWW2!H51) |  | ¬¬IF(ISBLANK(DPWW2!I51),"",DPWW2!I51) | [7 empty] | ¬¬DPWW2!F51 & "," & DPWW2!G51 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT52),"",DPWW2!AT52) | PCD_DPWW2_GGR3_NP |  | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) |  | ¬¬IF(ISBLANK(DPWW2!I52),"",DPWW2!I52) | [7 empty] | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV52),"",DPWW2!AV52) | PCD_DPWW2_GGR3 |  | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) |  | ¬¬IF(ISBLANK(DPWW2!I52),"",DPWW2!I52) | [7 empty] | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG52),"",DPWW2!BG52) | PCD_DPWW2_GGR3_T |  | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) |  | ¬¬IF(ISBLANK(DPWW2!I52),"",DPWW2!I52) | [7 empty] | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ52),"",DPWW2!BJ52) | PCD_DPWW2_GGR3_O |  | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) |  | ¬¬IF(ISBLANK(DPWW2!I52),"",DPWW2!I52) | [7 empty] | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU52),"",DPWW2!BU52) | PCD_DPWW2_GGR3_OT |  | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) |  | ¬¬IF(ISBLANK(DPWW2!I52),"",DPWW2!I52) | [7 empty] | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX52),"",DPWW2!BX52) | PCD_DPWW2_GGR3_P |  | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) |  | ¬¬IF(ISBLANK(DPWW2!I52),"",DPWW2!I52) | [7 empty] | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW2!AT53),"",DPWW2!AT53) | PCD_DPWW2_OTH1_NP |  | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) |  | ¬¬IF(ISBLANK(DPWW2!I53),"",DPWW2!I53) | [7 empty] | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!AV53),"",DPWW2!AV53) | PCD_DPWW2_OTH1 |  | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) |  | ¬¬IF(ISBLANK(DPWW2!I53),"",DPWW2!I53) | [7 empty] | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!AT5
¬¬IF(ISBLANK(DPWW2!BG53),"",DPWW2!BG53) | PCD_DPWW2_OTH1_T |  | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) |  | ¬¬IF(ISBLANK(DPWW2!I53),"",DPWW2!I53) | [7 empty] | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BG5
¬¬IF(ISBLANK(DPWW2!BJ53),"",DPWW2!BJ53) | PCD_DPWW2_OTH1_O |  | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) |  | ¬¬IF(ISBLANK(DPWW2!I53),"",DPWW2!I53) | [7 empty] | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BH5
¬¬IF(ISBLANK(DPWW2!BU53),"",DPWW2!BU53) | PCD_DPWW2_OTH1_OT |  | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) |  | ¬¬IF(ISBLANK(DPWW2!I53),"",DPWW2!I53) | [7 empty] | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BU5
¬¬IF(ISBLANK(DPWW2!BX53),"",DPWW2!BX53) | PCD_DPWW2_OTH1_P |  | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) |  | ¬¬IF(ISBLANK(DPWW2!I53),"",DPWW2!I53) | [7 empty] | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BX5
¬¬IF(ISBLANK(DPWW3!GW7),"",DPWW3!GW7) | PCD_DPWW3_SOW1_NR |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY7),"",DPWW3!GY7) | PCD_DPWW3_SOW1_S0 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU7),"",DPWW3!HU7) | PCD_DPWW3_SOW1_S1 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ7),"",DPWW3!IQ7) | PCD_DPWW3_SOW1_S2 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM7),"",DPWW3!JM7) | PCD_DPWW3_SOW1_S3 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI7),"",DPWW3!KI7) | PCD_DPWW3_SOW1_S4 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE7),"",DPWW3!LE7) | PCD_DPWW3_SOW1_S5 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA7),"",DPWW3!MA7) | PCD_DPWW3_SOW1_S6 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW7),"",DPWW3!MW7) | PCD_DPWW3_SOW1_S7 |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS7),"",DPWW3!NS7) | PCD_DPWW3_SOW1_DLY |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT7),"",DPWW3!NT7) | PCD_DPWW3_SOW1_DIR |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU7),"",DPWW3!NU7) | PCD_DPWW3_SOW1_DSCR |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV7),"",DPWW3!NV7) | PCD_DPWW3_SOW1_DCS |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW7),"",DPWW3!NW7) | PCD_DPWW3_SOW1_DSCS |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX7),"",DPWW3!NX7) | PCD_DPWW3_SOW1_DPP |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY7),"",DPWW3!NY7) | PCD_DPWW3_SOW1_DTPI |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ7),"",DPWW3!NZ7) | PCD_DPWW3_SOW1_DCI |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA7),"",DPWW3!OA7) | PCD_DPWW3_SOW1_DSI |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB7),"",DPWW3!OB7) | PCD_DPWW3_SOW1_DER |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC7),"",DPWW3!OC7) | PCD_DPWW3_SOW1_DPLE |  | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) |  | ¬¬IF(ISBLANK(DPWW3!I7),"",DPWW3!I7) | [7 empty] | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW8),"",DPWW3!GW8) | PCD_DPWW3_TCR1_NR |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY8),"",DPWW3!GY8) | PCD_DPWW3_TCR1_S0 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU8),"",DPWW3!HU8) | PCD_DPWW3_TCR1_S1 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ8),"",DPWW3!IQ8) | PCD_DPWW3_TCR1_S2 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM8),"",DPWW3!JM8) | PCD_DPWW3_TCR1_S3 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI8),"",DPWW3!KI8) | PCD_DPWW3_TCR1_S4 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE8),"",DPWW3!LE8) | PCD_DPWW3_TCR1_S5 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA8),"",DPWW3!MA8) | PCD_DPWW3_TCR1_S6 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW8),"",DPWW3!MW8) | PCD_DPWW3_TCR1_S7 |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS8),"",DPWW3!NS8) | PCD_DPWW3_TCR1_DLY |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT8),"",DPWW3!NT8) | PCD_DPWW3_TCR1_DIR |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU8),"",DPWW3!NU8) | PCD_DPWW3_TCR1_DSCR |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV8),"",DPWW3!NV8) | PCD_DPWW3_TCR1_DCS |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW8),"",DPWW3!NW8) | PCD_DPWW3_TCR1_DSCS |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX8),"",DPWW3!NX8) | PCD_DPWW3_TCR1_DPP |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY8),"",DPWW3!NY8) | PCD_DPWW3_TCR1_DTPI |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ8),"",DPWW3!NZ8) | PCD_DPWW3_TCR1_DCI |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA8),"",DPWW3!OA8) | PCD_DPWW3_TCR1_DSI |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB8),"",DPWW3!OB8) | PCD_DPWW3_TCR1_DER |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC8),"",DPWW3!OC8) | PCD_DPWW3_TCR1_DPLE |  | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) |  | ¬¬IF(ISBLANK(DPWW3!I8),"",DPWW3!I8) | [7 empty] | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW9),"",DPWW3!GW9) | PCD_DPWW3_TNR1_NR |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY9),"",DPWW3!GY9) | PCD_DPWW3_TNR1_S0 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU9),"",DPWW3!HU9) | PCD_DPWW3_TNR1_S1 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ9),"",DPWW3!IQ9) | PCD_DPWW3_TNR1_S2 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM9),"",DPWW3!JM9) | PCD_DPWW3_TNR1_S3 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI9),"",DPWW3!KI9) | PCD_DPWW3_TNR1_S4 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE9),"",DPWW3!LE9) | PCD_DPWW3_TNR1_S5 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA9),"",DPWW3!MA9) | PCD_DPWW3_TNR1_S6 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW9),"",DPWW3!MW9) | PCD_DPWW3_TNR1_S7 |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS9),"",DPWW3!NS9) | PCD_DPWW3_TNR1_DLY |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT9),"",DPWW3!NT9) | PCD_DPWW3_TNR1_DIR |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU9),"",DPWW3!NU9) | PCD_DPWW3_TNR1_DSCR |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV9),"",DPWW3!NV9) | PCD_DPWW3_TNR1_DCS |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW9),"",DPWW3!NW9) | PCD_DPWW3_TNR1_DSCS |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX9),"",DPWW3!NX9) | PCD_DPWW3_TNR1_DPP |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY9),"",DPWW3!NY9) | PCD_DPWW3_TNR1_DTPI |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ9),"",DPWW3!NZ9) | PCD_DPWW3_TNR1_DCI |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA9),"",DPWW3!OA9) | PCD_DPWW3_TNR1_DSI |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB9),"",DPWW3!OB9) | PCD_DPWW3_TNR1_DER |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC9),"",DPWW3!OC9) | PCD_DPWW3_TNR1_DPLE |  | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) |  | ¬¬IF(ISBLANK(DPWW3!I9),"",DPWW3!I9) | [7 empty] | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW10),"",DPWW3!GW10) | PCD_DPWW3_NBS_SOL_NR |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY10),"",DPWW3!GY10) | PCD_DPWW3_NBS_SOL_S0 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU10),"",DPWW3!HU10) | PCD_DPWW3_NBS_SOL_S1 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ10),"",DPWW3!IQ10) | PCD_DPWW3_NBS_SOL_S2 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM10),"",DPWW3!JM10) | PCD_DPWW3_NBS_SOL_S3 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI10),"",DPWW3!KI10) | PCD_DPWW3_NBS_SOL_S4 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE10),"",DPWW3!LE10) | PCD_DPWW3_NBS_SOL_S5 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA10),"",DPWW3!MA10) | PCD_DPWW3_NBS_SOL_S6 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW10),"",DPWW3!MW10) | PCD_DPWW3_NBS_SOL_S7 |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS10),"",DPWW3!NS10) | PCD_DPWW3_NBS_SOL_DLY |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT10),"",DPWW3!NT10) | PCD_DPWW3_NBS_SOL_DIR |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU10),"",DPWW3!NU10) | PCD_DPWW3_NBS_SOL_DSCR |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV10),"",DPWW3!NV10) | PCD_DPWW3_NBS_SOL_DCS |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW10),"",DPWW3!NW10) | PCD_DPWW3_NBS_SOL_DSCS |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX10),"",DPWW3!NX10) | PCD_DPWW3_NBS_SOL_DPP |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY10),"",DPWW3!NY10) | PCD_DPWW3_NBS_SOL_DTPI |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ10),"",DPWW3!NZ10) | PCD_DPWW3_NBS_SOL_DCI |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA10),"",DPWW3!OA10) | PCD_DPWW3_NBS_SOL_DSI |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB10),"",DPWW3!OB10) | PCD_DPWW3_NBS_SOL_DER |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC10),"",DPWW3!OC10) | PCD_DPWW3_NBS_SOL_DPLE |  | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) |  | ¬¬IF(ISBLANK(DPWW3!I10),"",DPWW3!I10) | [7 empty] | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW11),"",DPWW3!GW11) | PCD_DPWW3_MBT1_NR |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY11),"",DPWW3!GY11) | PCD_DPWW3_MBT1_S0 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU11),"",DPWW3!HU11) | PCD_DPWW3_MBT1_S1 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ11),"",DPWW3!IQ11) | PCD_DPWW3_MBT1_S2 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM11),"",DPWW3!JM11) | PCD_DPWW3_MBT1_S3 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI11),"",DPWW3!KI11) | PCD_DPWW3_MBT1_S4 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE11),"",DPWW3!LE11) | PCD_DPWW3_MBT1_S5 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA11),"",DPWW3!MA11) | PCD_DPWW3_MBT1_S6 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW11),"",DPWW3!MW11) | PCD_DPWW3_MBT1_S7 |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS11),"",DPWW3!NS11) | PCD_DPWW3_MBT1_DLY |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT11),"",DPWW3!NT11) | PCD_DPWW3_MBT1_DIR |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU11),"",DPWW3!NU11) | PCD_DPWW3_MBT1_DSCR |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV11),"",DPWW3!NV11) | PCD_DPWW3_MBT1_DCS |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW11),"",DPWW3!NW11) | PCD_DPWW3_MBT1_DSCS |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX11),"",DPWW3!NX11) | PCD_DPWW3_MBT1_DPP |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY11),"",DPWW3!NY11) | PCD_DPWW3_MBT1_DTPI |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ11),"",DPWW3!NZ11) | PCD_DPWW3_MBT1_DCI |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA11),"",DPWW3!OA11) | PCD_DPWW3_MBT1_DSI |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB11),"",DPWW3!OB11) | PCD_DPWW3_MBT1_DER |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC11),"",DPWW3!OC11) | PCD_DPWW3_MBT1_DPLE |  | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) |  | ¬¬IF(ISBLANK(DPWW3!I11),"",DPWW3!I11) | [7 empty] | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW12),"",DPWW3!GW12) | PCD_DPWW3_SSCP_NR |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY12),"",DPWW3!GY12) | PCD_DPWW3_SSCP_S0 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU12),"",DPWW3!HU12) | PCD_DPWW3_SSCP_S1 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ12),"",DPWW3!IQ12) | PCD_DPWW3_SSCP_S2 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM12),"",DPWW3!JM12) | PCD_DPWW3_SSCP_S3 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI12),"",DPWW3!KI12) | PCD_DPWW3_SSCP_S4 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE12),"",DPWW3!LE12) | PCD_DPWW3_SSCP_S5 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA12),"",DPWW3!MA12) | PCD_DPWW3_SSCP_S6 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW12),"",DPWW3!MW12) | PCD_DPWW3_SSCP_S7 |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS12),"",DPWW3!NS12) | PCD_DPWW3_SSCP_DLY |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT12),"",DPWW3!NT12) | PCD_DPWW3_SSCP_DIR |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU12),"",DPWW3!NU12) | PCD_DPWW3_SSCP_DSCR |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV12),"",DPWW3!NV12) | PCD_DPWW3_SSCP_DCS |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW12),"",DPWW3!NW12) | PCD_DPWW3_SSCP_DSCS |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX12),"",DPWW3!NX12) | PCD_DPWW3_SSCP_DPP |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY12),"",DPWW3!NY12) | PCD_DPWW3_SSCP_DTPI |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ12),"",DPWW3!NZ12) | PCD_DPWW3_SSCP_DCI |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA12),"",DPWW3!OA12) | PCD_DPWW3_SSCP_DSI |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB12),"",DPWW3!OB12) | PCD_DPWW3_SSCP_DER |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC12),"",DPWW3!OC12) | PCD_DPWW3_SSCP_DPLE |  | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) |  | ¬¬IF(ISBLANK(DPWW3!I12),"",DPWW3!I12) | [7 empty] | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW13),"",DPWW3!GW13) | PCD_DPWW3_STOTH1_NR |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY13),"",DPWW3!GY13) | PCD_DPWW3_STOTH1_S0 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU13),"",DPWW3!HU13) | PCD_DPWW3_STOTH1_S1 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ13),"",DPWW3!IQ13) | PCD_DPWW3_STOTH1_S2 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM13),"",DPWW3!JM13) | PCD_DPWW3_STOTH1_S3 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI13),"",DPWW3!KI13) | PCD_DPWW3_STOTH1_S4 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE13),"",DPWW3!LE13) | PCD_DPWW3_STOTH1_S5 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA13),"",DPWW3!MA13) | PCD_DPWW3_STOTH1_S6 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW13),"",DPWW3!MW13) | PCD_DPWW3_STOTH1_S7 |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS13),"",DPWW3!NS13) | PCD_DPWW3_STOTH1_DLY |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT13),"",DPWW3!NT13) | PCD_DPWW3_STOTH1_DIR |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU13),"",DPWW3!NU13) | PCD_DPWW3_STOTH1_DSCR |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV13),"",DPWW3!NV13) | PCD_DPWW3_STOTH1_DCS |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW13),"",DPWW3!NW13) | PCD_DPWW3_STOTH1_DSCS |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX13),"",DPWW3!NX13) | PCD_DPWW3_STOTH1_DPP |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY13),"",DPWW3!NY13) | PCD_DPWW3_STOTH1_DTPI |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ13),"",DPWW3!NZ13) | PCD_DPWW3_STOTH1_DCI |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA13),"",DPWW3!OA13) | PCD_DPWW3_STOTH1_DSI |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB13),"",DPWW3!OB13) | PCD_DPWW3_STOTH1_DER |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC13),"",DPWW3!OC13) | PCD_DPWW3_STOTH1_DPLE |  | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) |  | ¬¬IF(ISBLANK(DPWW3!I13),"",DPWW3!I13) | [7 empty] | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW14),"",DPWW3!GW14) | PCD_DPWW3_STOTH2_NR |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY14),"",DPWW3!GY14) | PCD_DPWW3_STOTH2_S0 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU14),"",DPWW3!HU14) | PCD_DPWW3_STOTH2_S1 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ14),"",DPWW3!IQ14) | PCD_DPWW3_STOTH2_S2 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM14),"",DPWW3!JM14) | PCD_DPWW3_STOTH2_S3 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI14),"",DPWW3!KI14) | PCD_DPWW3_STOTH2_S4 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE14),"",DPWW3!LE14) | PCD_DPWW3_STOTH2_S5 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA14),"",DPWW3!MA14) | PCD_DPWW3_STOTH2_S6 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW14),"",DPWW3!MW14) | PCD_DPWW3_STOTH2_S7 |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS14),"",DPWW3!NS14) | PCD_DPWW3_STOTH2_DLY |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT14),"",DPWW3!NT14) | PCD_DPWW3_STOTH2_DIR |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU14),"",DPWW3!NU14) | PCD_DPWW3_STOTH2_DSCR |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV14),"",DPWW3!NV14) | PCD_DPWW3_STOTH2_DCS |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW14),"",DPWW3!NW14) | PCD_DPWW3_STOTH2_DSCS |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX14),"",DPWW3!NX14) | PCD_DPWW3_STOTH2_DPP |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY14),"",DPWW3!NY14) | PCD_DPWW3_STOTH2_DTPI |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ14),"",DPWW3!NZ14) | PCD_DPWW3_STOTH2_DCI |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA14),"",DPWW3!OA14) | PCD_DPWW3_STOTH2_DSI |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB14),"",DPWW3!OB14) | PCD_DPWW3_STOTH2_DER |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC14),"",DPWW3!OC14) | PCD_DPWW3_STOTH2_DPLE |  | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) |  | ¬¬IF(ISBLANK(DPWW3!I14),"",DPWW3!I14) | [7 empty] | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW15),"",DPWW3!GW15) | PCD_DPWW3_BIO_IED_NR |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY15),"",DPWW3!GY15) | PCD_DPWW3_BIO_IED_S0 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU15),"",DPWW3!HU15) | PCD_DPWW3_BIO_IED_S1 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ15),"",DPWW3!IQ15) | PCD_DPWW3_BIO_IED_S2 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM15),"",DPWW3!JM15) | PCD_DPWW3_BIO_IED_S3 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI15),"",DPWW3!KI15) | PCD_DPWW3_BIO_IED_S4 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE15),"",DPWW3!LE15) | PCD_DPWW3_BIO_IED_S5 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA15),"",DPWW3!MA15) | PCD_DPWW3_BIO_IED_S6 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW15),"",DPWW3!MW15) | PCD_DPWW3_BIO_IED_S7 |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS15),"",DPWW3!NS15) | PCD_DPWW3_BIO_IED_DLY |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT15),"",DPWW3!NT15) | PCD_DPWW3_BIO_IED_DIR |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU15),"",DPWW3!NU15) | PCD_DPWW3_BIO_IED_DSCR |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV15),"",DPWW3!NV15) | PCD_DPWW3_BIO_IED_DCS |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW15),"",DPWW3!NW15) | PCD_DPWW3_BIO_IED_DSCS |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX15),"",DPWW3!NX15) | PCD_DPWW3_BIO_IED_DPP |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY15),"",DPWW3!NY15) | PCD_DPWW3_BIO_IED_DTPI |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ15),"",DPWW3!NZ15) | PCD_DPWW3_BIO_IED_DCI |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA15),"",DPWW3!OA15) | PCD_DPWW3_BIO_IED_DSI |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB15),"",DPWW3!OB15) | PCD_DPWW3_BIO_IED_DER |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC15),"",DPWW3!OC15) | PCD_DPWW3_BIO_IED_DPLE |  | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) |  | ¬¬IF(ISBLANK(DPWW3!I15),"",DPWW3!I15) | [7 empty] | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW16),"",DPWW3!GW16) | PCD_DPWW3_SOES_NR |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY16),"",DPWW3!GY16) | PCD_DPWW3_SOES_S0 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU16),"",DPWW3!HU16) | PCD_DPWW3_SOES_S1 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ16),"",DPWW3!IQ16) | PCD_DPWW3_SOES_S2 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM16),"",DPWW3!JM16) | PCD_DPWW3_SOES_S3 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI16),"",DPWW3!KI16) | PCD_DPWW3_SOES_S4 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE16),"",DPWW3!LE16) | PCD_DPWW3_SOES_S5 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA16),"",DPWW3!MA16) | PCD_DPWW3_SOES_S6 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW16),"",DPWW3!MW16) | PCD_DPWW3_SOES_S7 |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS16),"",DPWW3!NS16) | PCD_DPWW3_SOES_DLY |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT16),"",DPWW3!NT16) | PCD_DPWW3_SOES_DIR |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU16),"",DPWW3!NU16) | PCD_DPWW3_SOES_DSCR |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV16),"",DPWW3!NV16) | PCD_DPWW3_SOES_DCS |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW16),"",DPWW3!NW16) | PCD_DPWW3_SOES_DSCS |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX16),"",DPWW3!NX16) | PCD_DPWW3_SOES_DPP |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY16),"",DPWW3!NY16) | PCD_DPWW3_SOES_DTPI |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ16),"",DPWW3!NZ16) | PCD_DPWW3_SOES_DCI |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA16),"",DPWW3!OA16) | PCD_DPWW3_SOES_DSI |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB16),"",DPWW3!OB16) | PCD_DPWW3_SOES_DER |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC16),"",DPWW3!OC16) | PCD_DPWW3_SOES_DPLE |  | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) |  | ¬¬IF(ISBLANK(DPWW3!I16),"",DPWW3!I16) | [7 empty] | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW17),"",DPWW3!GW17) | PCD_DPWW3_FTFT_NR |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY17),"",DPWW3!GY17) | PCD_DPWW3_FTFT_S0 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU17),"",DPWW3!HU17) | PCD_DPWW3_FTFT_S1 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ17),"",DPWW3!IQ17) | PCD_DPWW3_FTFT_S2 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM17),"",DPWW3!JM17) | PCD_DPWW3_FTFT_S3 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI17),"",DPWW3!KI17) | PCD_DPWW3_FTFT_S4 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE17),"",DPWW3!LE17) | PCD_DPWW3_FTFT_S5 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA17),"",DPWW3!MA17) | PCD_DPWW3_FTFT_S6 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW17),"",DPWW3!MW17) | PCD_DPWW3_FTFT_S7 |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS17),"",DPWW3!NS17) | PCD_DPWW3_FTFT_DLY |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT17),"",DPWW3!NT17) | PCD_DPWW3_FTFT_DIR |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU17),"",DPWW3!NU17) | PCD_DPWW3_FTFT_DSCR |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV17),"",DPWW3!NV17) | PCD_DPWW3_FTFT_DCS |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW17),"",DPWW3!NW17) | PCD_DPWW3_FTFT_DSCS |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX17),"",DPWW3!NX17) | PCD_DPWW3_FTFT_DPP |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY17),"",DPWW3!NY17) | PCD_DPWW3_FTFT_DTPI |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ17),"",DPWW3!NZ17) | PCD_DPWW3_FTFT_DCI |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA17),"",DPWW3!OA17) | PCD_DPWW3_FTFT_DSI |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB17),"",DPWW3!OB17) | PCD_DPWW3_FTFT_DER |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC17),"",DPWW3!OC17) | PCD_DPWW3_FTFT_DPLE |  | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) |  | ¬¬IF(ISBLANK(DPWW3!I17),"",DPWW3!I17) | [7 empty] | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW18),"",DPWW3!GW18) | PCD_DPWW3_PRMVL_NR |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY18),"",DPWW3!GY18) | PCD_DPWW3_PRMVL_S0 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU18),"",DPWW3!HU18) | PCD_DPWW3_PRMVL_S1 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ18),"",DPWW3!IQ18) | PCD_DPWW3_PRMVL_S2 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM18),"",DPWW3!JM18) | PCD_DPWW3_PRMVL_S3 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI18),"",DPWW3!KI18) | PCD_DPWW3_PRMVL_S4 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE18),"",DPWW3!LE18) | PCD_DPWW3_PRMVL_S5 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA18),"",DPWW3!MA18) | PCD_DPWW3_PRMVL_S6 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW18),"",DPWW3!MW18) | PCD_DPWW3_PRMVL_S7 |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS18),"",DPWW3!NS18) | PCD_DPWW3_PRMVL_DLY |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT18),"",DPWW3!NT18) | PCD_DPWW3_PRMVL_DIR |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU18),"",DPWW3!NU18) | PCD_DPWW3_PRMVL_DSCR |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV18),"",DPWW3!NV18) | PCD_DPWW3_PRMVL_DCS |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW18),"",DPWW3!NW18) | PCD_DPWW3_PRMVL_DSCS |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX18),"",DPWW3!NX18) | PCD_DPWW3_PRMVL_DPP |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY18),"",DPWW3!NY18) | PCD_DPWW3_PRMVL_DTPI |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ18),"",DPWW3!NZ18) | PCD_DPWW3_PRMVL_DCI |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA18),"",DPWW3!OA18) | PCD_DPWW3_PRMVL_DSI |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB18),"",DPWW3!OB18) | PCD_DPWW3_PRMVL_DER |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC18),"",DPWW3!OC18) | PCD_DPWW3_PRMVL_DPLE |  | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) |  | ¬¬IF(ISBLANK(DPWW3!I18),"",DPWW3!I18) | [7 empty] | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW19),"",DPWW3!GW19) | PCD_DPWW3_GSTW_NR |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY19),"",DPWW3!GY19) | PCD_DPWW3_GSTW_S0 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU19),"",DPWW3!HU19) | PCD_DPWW3_GSTW_S1 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ19),"",DPWW3!IQ19) | PCD_DPWW3_GSTW_S2 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM19),"",DPWW3!JM19) | PCD_DPWW3_GSTW_S3 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI19),"",DPWW3!KI19) | PCD_DPWW3_GSTW_S4 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE19),"",DPWW3!LE19) | PCD_DPWW3_GSTW_S5 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA19),"",DPWW3!MA19) | PCD_DPWW3_GSTW_S6 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW19),"",DPWW3!MW19) | PCD_DPWW3_GSTW_S7 |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS19),"",DPWW3!NS19) | PCD_DPWW3_GSTW_DLY |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT19),"",DPWW3!NT19) | PCD_DPWW3_GSTW_DIR |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU19),"",DPWW3!NU19) | PCD_DPWW3_GSTW_DSCR |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV19),"",DPWW3!NV19) | PCD_DPWW3_GSTW_DCS |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW19),"",DPWW3!NW19) | PCD_DPWW3_GSTW_DSCS |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX19),"",DPWW3!NX19) | PCD_DPWW3_GSTW_DPP |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY19),"",DPWW3!NY19) | PCD_DPWW3_GSTW_DTPI |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ19),"",DPWW3!NZ19) | PCD_DPWW3_GSTW_DCI |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA19),"",DPWW3!OA19) | PCD_DPWW3_GSTW_DSI |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB19),"",DPWW3!OB19) | PCD_DPWW3_GSTW_DER |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC19),"",DPWW3!OC19) | PCD_DPWW3_GSTW_DPLE |  | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) |  | ¬¬IF(ISBLANK(DPWW3!I19),"",DPWW3!I19) | [7 empty] | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW20),"",DPWW3!GW20) | PCD_DPWW3_TTSP_NR |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY20),"",DPWW3!GY20) | PCD_DPWW3_TTSP_S0 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU20),"",DPWW3!HU20) | PCD_DPWW3_TTSP_S1 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ20),"",DPWW3!IQ20) | PCD_DPWW3_TTSP_S2 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM20),"",DPWW3!JM20) | PCD_DPWW3_TTSP_S3 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI20),"",DPWW3!KI20) | PCD_DPWW3_TTSP_S4 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE20),"",DPWW3!LE20) | PCD_DPWW3_TTSP_S5 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA20),"",DPWW3!MA20) | PCD_DPWW3_TTSP_S6 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW20),"",DPWW3!MW20) | PCD_DPWW3_TTSP_S7 |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS20),"",DPWW3!NS20) | PCD_DPWW3_TTSP_DLY |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT20),"",DPWW3!NT20) | PCD_DPWW3_TTSP_DIR |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU20),"",DPWW3!NU20) | PCD_DPWW3_TTSP_DSCR |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV20),"",DPWW3!NV20) | PCD_DPWW3_TTSP_DCS |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW20),"",DPWW3!NW20) | PCD_DPWW3_TTSP_DSCS |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX20),"",DPWW3!NX20) | PCD_DPWW3_TTSP_DPP |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY20),"",DPWW3!NY20) | PCD_DPWW3_TTSP_DTPI |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ20),"",DPWW3!NZ20) | PCD_DPWW3_TTSP_DCI |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA20),"",DPWW3!OA20) | PCD_DPWW3_TTSP_DSI |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB20),"",DPWW3!OB20) | PCD_DPWW3_TTSP_DER |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC20),"",DPWW3!OC20) | PCD_DPWW3_TTSP_DPLE |  | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) |  | ¬¬IF(ISBLANK(DPWW3!I20),"",DPWW3!I20) | [7 empty] | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW21),"",DPWW3!GW21) | PCD_DPWW3_PR19WINCA_NR |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY21),"",DPWW3!GY21) | PCD_DPWW3_PR19WINCA_S0 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU21),"",DPWW3!HU21) | PCD_DPWW3_PR19WINCA_S1 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ21),"",DPWW3!IQ21) | PCD_DPWW3_PR19WINCA_S2 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM21),"",DPWW3!JM21) | PCD_DPWW3_PR19WINCA_S3 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI21),"",DPWW3!KI21) | PCD_DPWW3_PR19WINCA_S4 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE21),"",DPWW3!LE21) | PCD_DPWW3_PR19WINCA_S5 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA21),"",DPWW3!MA21) | PCD_DPWW3_PR19WINCA_S6 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW21),"",DPWW3!MW21) | PCD_DPWW3_PR19WINCA_S7 |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS21),"",DPWW3!NS21) | PCD_DPWW3_PR19WINCA_DLY |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT21),"",DPWW3!NT21) | PCD_DPWW3_PR19WINCA_DIR |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU21),"",DPWW3!NU21) | PCD_DPWW3_PR19WINCA_DSCR |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV21),"",DPWW3!NV21) | PCD_DPWW3_PR19WINCA_DCS |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW21),"",DPWW3!NW21) | PCD_DPWW3_PR19WINCA_DSCS |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX21),"",DPWW3!NX21) | PCD_DPWW3_PR19WINCA_DPP |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY21),"",DPWW3!NY21) | PCD_DPWW3_PR19WINCA_DTPI |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ21),"",DPWW3!NZ21) | PCD_DPWW3_PR19WINCA_DCI |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA21),"",DPWW3!OA21) | PCD_DPWW3_PR19WINCA_DSI |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB21),"",DPWW3!OB21) | PCD_DPWW3_PR19WINCA_DER |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC21),"",DPWW3!OC21) | PCD_DPWW3_PR19WINCA_DPLE |  | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) |  | ¬¬IF(ISBLANK(DPWW3!I21),"",DPWW3!I21) | [7 empty] | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OC5
¬¬IF(ISBLANK(DPWW3!GW22),"",DPWW3!GW22) | PCD_DPWW3_GGR1_NR |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!GW5
¬¬IF(ISBLANK(DPWW3!GY22),"",DPWW3!GY22) | PCD_DPWW3_GGR1_S0 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!GY5
¬¬IF(ISBLANK(DPWW3!HU22),"",DPWW3!HU22) | PCD_DPWW3_GGR1_S1 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!HU5
¬¬IF(ISBLANK(DPWW3!IQ22),"",DPWW3!IQ22) | PCD_DPWW3_GGR1_S2 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!IQ5
¬¬IF(ISBLANK(DPWW3!JM22),"",DPWW3!JM22) | PCD_DPWW3_GGR1_S3 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!JM5
¬¬IF(ISBLANK(DPWW3!KI22),"",DPWW3!KI22) | PCD_DPWW3_GGR1_S4 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!KI5
¬¬IF(ISBLANK(DPWW3!LE22),"",DPWW3!LE22) | PCD_DPWW3_GGR1_S5 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!LE5
¬¬IF(ISBLANK(DPWW3!MA22),"",DPWW3!MA22) | PCD_DPWW3_GGR1_S6 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!MA5
¬¬IF(ISBLANK(DPWW3!MW22),"",DPWW3!MW22) | PCD_DPWW3_GGR1_S7 |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!MW5
¬¬IF(ISBLANK(DPWW3!NS22),"",DPWW3!NS22) | PCD_DPWW3_GGR1_DLY |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NS5
¬¬IF(ISBLANK(DPWW3!NT22),"",DPWW3!NT22) | PCD_DPWW3_GGR1_DIR |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NT5
¬¬IF(ISBLANK(DPWW3!NU22),"",DPWW3!NU22) | PCD_DPWW3_GGR1_DSCR |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NU5
¬¬IF(ISBLANK(DPWW3!NV22),"",DPWW3!NV22) | PCD_DPWW3_GGR1_DCS |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NV5
¬¬IF(ISBLANK(DPWW3!NW22),"",DPWW3!NW22) | PCD_DPWW3_GGR1_DSCS |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NW5
¬¬IF(ISBLANK(DPWW3!NX22),"",DPWW3!NX22) | PCD_DPWW3_GGR1_DPP |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NX5
¬¬IF(ISBLANK(DPWW3!NY22),"",DPWW3!NY22) | PCD_DPWW3_GGR1_DTPI |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NY5
¬¬IF(ISBLANK(DPWW3!NZ22),"",DPWW3!NZ22) | PCD_DPWW3_GGR1_DCI |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NZ5
¬¬IF(ISBLANK(DPWW3!OA22),"",DPWW3!OA22) | PCD_DPWW3_GGR1_DSI |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OA5
¬¬IF(ISBLANK(DPWW3!OB22),"",DPWW3!OB22) | PCD_DPWW3_GGR1_DER |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OB5
¬¬IF(ISBLANK(DPWW3!OC22),"",DPWW3!OC22) | PCD_DPWW3_GGR1_DPLE |  | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) |  | ¬¬IF(ISBLANK(DPWW3!I22),"",DPWW3!I22) | [7 empty] | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OC5
¬¬IF(ISBLANK('DPW1'!AW8),"",'DPW1'!AW8) | PCD_DPW1_BIOCON1 |  | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) |  | ¬¬IF(ISBLANK('DPW1'!I8),"",'DPW1'!I8) | [7 empty] | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI8),"",'DPW1'!BI8) | PCD_DPW1_BIOCON1_T |  | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) |  | ¬¬IF(ISBLANK('DPW1'!I8),"",'DPW1'!I8) | [7 empty] | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL8),"",'DPW1'!BL8) | PCD_DPW1_BIOCON1_O |  | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) |  | ¬¬IF(ISBLANK('DPW1'!I8),"",'DPW1'!I8) | [7 empty] | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX8),"",'DPW1'!BX8) | PCD_DPW1_BIOCON1_OT |  | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) |  | ¬¬IF(ISBLANK('DPW1'!I8),"",'DPW1'!I8) | [7 empty] | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA8),"",'DPW1'!CA8) | PCD_DPW1_BIOCON1_P |  | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) |  | ¬¬IF(ISBLANK('DPW1'!I8),"",'DPW1'!I8) | [7 empty] | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW9),"",'DPW1'!AW9) | PCD_DPW1_BIOCON2 |  | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) |  | ¬¬IF(ISBLANK('DPW1'!I9),"",'DPW1'!I9) | [7 empty] | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI9),"",'DPW1'!BI9) | PCD_DPW1_BIOCON2_T |  | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) |  | ¬¬IF(ISBLANK('DPW1'!I9),"",'DPW1'!I9) | [7 empty] | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL9),"",'DPW1'!BL9) | PCD_DPW1_BIOCON2_O |  | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) |  | ¬¬IF(ISBLANK('DPW1'!I9),"",'DPW1'!I9) | [7 empty] | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX9),"",'DPW1'!BX9) | PCD_DPW1_BIOCON2_OT |  | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) |  | ¬¬IF(ISBLANK('DPW1'!I9),"",'DPW1'!I9) | [7 empty] | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA9),"",'DPW1'!CA9) | PCD_DPW1_BIOCON2_P |  | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) |  | ¬¬IF(ISBLANK('DPW1'!I9),"",'DPW1'!I9) | [7 empty] | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW10),"",'DPW1'!AW10) | PCD_DPW1_DWPA |  | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) |  | ¬¬IF(ISBLANK('DPW1'!I10),"",'DPW1'!I10) | [7 empty] | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI10),"",'DPW1'!BI10) | PCD_DPW1_DWPA_T |  | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) |  | ¬¬IF(ISBLANK('DPW1'!I10),"",'DPW1'!I10) | [7 empty] | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL10),"",'DPW1'!BL10) | PCD_DPW1_DWPA_O |  | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) |  | ¬¬IF(ISBLANK('DPW1'!I10),"",'DPW1'!I10) | [7 empty] | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX10),"",'DPW1'!BX10) | PCD_DPW1_DWPA_OT |  | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) |  | ¬¬IF(ISBLANK('DPW1'!I10),"",'DPW1'!I10) | [7 empty] | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA10),"",'DPW1'!CA10) | PCD_DPW1_DWPA_P |  | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) |  | ¬¬IF(ISBLANK('DPW1'!I10),"",'DPW1'!I10) | [7 empty] | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW11),"",'DPW1'!AW11) | PCD_DPW1_WFDI |  | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) |  | ¬¬IF(ISBLANK('DPW1'!I11),"",'DPW1'!I11) | [7 empty] | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI11),"",'DPW1'!BI11) | PCD_DPW1_WFDI_T |  | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) |  | ¬¬IF(ISBLANK('DPW1'!I11),"",'DPW1'!I11) | [7 empty] | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL11),"",'DPW1'!BL11) | PCD_DPW1_WFDI_O |  | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) |  | ¬¬IF(ISBLANK('DPW1'!I11),"",'DPW1'!I11) | [7 empty] | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX11),"",'DPW1'!BX11) | PCD_DPW1_WFDI_OT |  | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) |  | ¬¬IF(ISBLANK('DPW1'!I11),"",'DPW1'!I11) | [7 empty] | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA11),"",'DPW1'!CA11) | PCD_DPW1_WFDI_P |  | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) |  | ¬¬IF(ISBLANK('DPW1'!I11),"",'DPW1'!I11) | [7 empty] | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW12),"",'DPW1'!AW12) | PCD_DPW1_WFDA |  | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) |  | ¬¬IF(ISBLANK('DPW1'!I12),"",'DPW1'!I12) | [7 empty] | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI12),"",'DPW1'!BI12) | PCD_DPW1_WFDA_T |  | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) |  | ¬¬IF(ISBLANK('DPW1'!I12),"",'DPW1'!I12) | [7 empty] | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL12),"",'DPW1'!BL12) | PCD_DPW1_WFDA_O |  | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) |  | ¬¬IF(ISBLANK('DPW1'!I12),"",'DPW1'!I12) | [7 empty] | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX12),"",'DPW1'!BX12) | PCD_DPW1_WFDA_OT |  | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) |  | ¬¬IF(ISBLANK('DPW1'!I12),"",'DPW1'!I12) | [7 empty] | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA12),"",'DPW1'!CA12) | PCD_DPW1_WFDA_P |  | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) |  | ¬¬IF(ISBLANK('DPW1'!I12),"",'DPW1'!I12) | [7 empty] | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW13),"",'DPW1'!AW13) | PCD_DPW1_WIVG |  | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) |  | ¬¬IF(ISBLANK('DPW1'!I13),"",'DPW1'!I13) | [7 empty] | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI13),"",'DPW1'!BI13) | PCD_DPW1_WIVG_T |  | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) |  | ¬¬IF(ISBLANK('DPW1'!I13),"",'DPW1'!I13) | [7 empty] | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL13),"",'DPW1'!BL13) | PCD_DPW1_WIVG_O |  | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) |  | ¬¬IF(ISBLANK('DPW1'!I13),"",'DPW1'!I13) | [7 empty] | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX13),"",'DPW1'!BX13) | PCD_DPW1_WIVG_OT |  | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) |  | ¬¬IF(ISBLANK('DPW1'!I13),"",'DPW1'!I13) | [7 empty] | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA13),"",'DPW1'!CA13) | PCD_DPW1_WIVG_P |  | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) |  | ¬¬IF(ISBLANK('DPW1'!I13),"",'DPW1'!I13) | [7 empty] | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW14),"",'DPW1'!AW14) | PCD_DPW1_RWD |  | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) |  | ¬¬IF(ISBLANK('DPW1'!I14),"",'DPW1'!I14) | [7 empty] | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI14),"",'DPW1'!BI14) | PCD_DPW1_RWD_T |  | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) |  | ¬¬IF(ISBLANK('DPW1'!I14),"",'DPW1'!I14) | [7 empty] | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL14),"",'DPW1'!BL14) | PCD_DPW1_RWD_O |  | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) |  | ¬¬IF(ISBLANK('DPW1'!I14),"",'DPW1'!I14) | [7 empty] | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX14),"",'DPW1'!BX14) | PCD_DPW1_RWD_OT |  | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) |  | ¬¬IF(ISBLANK('DPW1'!I14),"",'DPW1'!I14) | [7 empty] | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA14),"",'DPW1'!CA14) | PCD_DPW1_RWD_P |  | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) |  | ¬¬IF(ISBLANK('DPW1'!I14),"",'DPW1'!I14) | [7 empty] | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW15),"",'DPW1'!AW15) | PCD_DPW1_LEAD1 |  | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) |  | ¬¬IF(ISBLANK('DPW1'!I15),"",'DPW1'!I15) | [7 empty] | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI15),"",'DPW1'!BI15) | PCD_DPW1_LEAD1_T |  | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) |  | ¬¬IF(ISBLANK('DPW1'!I15),"",'DPW1'!I15) | [7 empty] | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL15),"",'DPW1'!BL15) | PCD_DPW1_LEAD1_O |  | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) |  | ¬¬IF(ISBLANK('DPW1'!I15),"",'DPW1'!I15) | [7 empty] | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX15),"",'DPW1'!BX15) | PCD_DPW1_LEAD1_OT |  | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) |  | ¬¬IF(ISBLANK('DPW1'!I15),"",'DPW1'!I15) | [7 empty] | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA15),"",'DPW1'!CA15) | PCD_DPW1_LEAD1_P |  | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) |  | ¬¬IF(ISBLANK('DPW1'!I15),"",'DPW1'!I15) | [7 empty] | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW16),"",'DPW1'!AW16) | PCD_DPW1_LEAD2 |  | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) |  | ¬¬IF(ISBLANK('DPW1'!I16),"",'DPW1'!I16) | [7 empty] | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI16),"",'DPW1'!BI16) | PCD_DPW1_LEAD2_T |  | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) |  | ¬¬IF(ISBLANK('DPW1'!I16),"",'DPW1'!I16) | [7 empty] | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL16),"",'DPW1'!BL16) | PCD_DPW1_LEAD2_O |  | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) |  | ¬¬IF(ISBLANK('DPW1'!I16),"",'DPW1'!I16) | [7 empty] | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX16),"",'DPW1'!BX16) | PCD_DPW1_LEAD2_OT |  | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) |  | ¬¬IF(ISBLANK('DPW1'!I16),"",'DPW1'!I16) | [7 empty] | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA16),"",'DPW1'!CA16) | PCD_DPW1_LEAD2_P |  | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) |  | ¬¬IF(ISBLANK('DPW1'!I16),"",'DPW1'!I16) | [7 empty] | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW17),"",'DPW1'!AW17) | PCD_DPW1_LEAD3 |  | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) |  | ¬¬IF(ISBLANK('DPW1'!I17),"",'DPW1'!I17) | [7 empty] | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI17),"",'DPW1'!BI17) | PCD_DPW1_LEAD3_T |  | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) |  | ¬¬IF(ISBLANK('DPW1'!I17),"",'DPW1'!I17) | [7 empty] | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL17),"",'DPW1'!BL17) | PCD_DPW1_LEAD3_O |  | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) |  | ¬¬IF(ISBLANK('DPW1'!I17),"",'DPW1'!I17) | [7 empty] | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX17),"",'DPW1'!BX17) | PCD_DPW1_LEAD3_OT |  | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) |  | ¬¬IF(ISBLANK('DPW1'!I17),"",'DPW1'!I17) | [7 empty] | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA17),"",'DPW1'!CA17) | PCD_DPW1_LEAD3_P |  | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) |  | ¬¬IF(ISBLANK('DPW1'!I17),"",'DPW1'!I17) | [7 empty] | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW18),"",'DPW1'!AW18) | PCD_DPW1_LEAD4 |  | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) |  | ¬¬IF(ISBLANK('DPW1'!I18),"",'DPW1'!I18) | [7 empty] | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI18),"",'DPW1'!BI18) | PCD_DPW1_LEAD4_T |  | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) |  | ¬¬IF(ISBLANK('DPW1'!I18),"",'DPW1'!I18) | [7 empty] | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL18),"",'DPW1'!BL18) | PCD_DPW1_LEAD4_O |  | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) |  | ¬¬IF(ISBLANK('DPW1'!I18),"",'DPW1'!I18) | [7 empty] | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX18),"",'DPW1'!BX18) | PCD_DPW1_LEAD4_OT |  | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) |  | ¬¬IF(ISBLANK('DPW1'!I18),"",'DPW1'!I18) | [7 empty] | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA18),"",'DPW1'!CA18) | PCD_DPW1_LEAD4_P |  | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) |  | ¬¬IF(ISBLANK('DPW1'!I18),"",'DPW1'!I18) | [7 empty] | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW19),"",'DPW1'!AW19) | PCD_DPW1_LEAD5 |  | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) |  | ¬¬IF(ISBLANK('DPW1'!I19),"",'DPW1'!I19) | [7 empty] | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI19),"",'DPW1'!BI19) | PCD_DPW1_LEAD5_T |  | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) |  | ¬¬IF(ISBLANK('DPW1'!I19),"",'DPW1'!I19) | [7 empty] | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL19),"",'DPW1'!BL19) | PCD_DPW1_LEAD5_O |  | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) |  | ¬¬IF(ISBLANK('DPW1'!I19),"",'DPW1'!I19) | [7 empty] | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX19),"",'DPW1'!BX19) | PCD_DPW1_LEAD5_OT |  | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) |  | ¬¬IF(ISBLANK('DPW1'!I19),"",'DPW1'!I19) | [7 empty] | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA19),"",'DPW1'!CA19) | PCD_DPW1_LEAD5_P |  | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) |  | ¬¬IF(ISBLANK('DPW1'!I19),"",'DPW1'!I19) | [7 empty] | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW20),"",'DPW1'!AW20) | PCD_DPW1_WRESUP |  | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) |  | ¬¬IF(ISBLANK('DPW1'!I20),"",'DPW1'!I20) | [7 empty] | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI20),"",'DPW1'!BI20) | PCD_DPW1_WRESUP_T |  | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) |  | ¬¬IF(ISBLANK('DPW1'!I20),"",'DPW1'!I20) | [7 empty] | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL20),"",'DPW1'!BL20) | PCD_DPW1_WRESUP_O |  | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) |  | ¬¬IF(ISBLANK('DPW1'!I20),"",'DPW1'!I20) | [7 empty] | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX20),"",'DPW1'!BX20) | PCD_DPW1_WRESUP_OT |  | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) |  | ¬¬IF(ISBLANK('DPW1'!I20),"",'DPW1'!I20) | [7 empty] | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA20),"",'DPW1'!CA20) | PCD_DPW1_WRESUP_P |  | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) |  | ¬¬IF(ISBLANK('DPW1'!I20),"",'DPW1'!I20) | [7 empty] | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW21),"",'DPW1'!AW21) | PCD_DPW1_MTR1 |  | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) |  | ¬¬IF(ISBLANK('DPW1'!I21),"",'DPW1'!I21) | [7 empty] | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI21),"",'DPW1'!BI21) | PCD_DPW1_MTR1_T |  | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) |  | ¬¬IF(ISBLANK('DPW1'!I21),"",'DPW1'!I21) | [7 empty] | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL21),"",'DPW1'!BL21) | PCD_DPW1_MTR1_O |  | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) |  | ¬¬IF(ISBLANK('DPW1'!I21),"",'DPW1'!I21) | [7 empty] | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX21),"",'DPW1'!BX21) | PCD_DPW1_MTR1_OT |  | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) |  | ¬¬IF(ISBLANK('DPW1'!I21),"",'DPW1'!I21) | [7 empty] | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA21),"",'DPW1'!CA21) | PCD_DPW1_MTR1_P |  | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) |  | ¬¬IF(ISBLANK('DPW1'!I21),"",'DPW1'!I21) | [7 empty] | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW22),"",'DPW1'!AW22) | PCD_DPW1_MTR2 |  | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) |  | ¬¬IF(ISBLANK('DPW1'!I22),"",'DPW1'!I22) | [7 empty] | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI22),"",'DPW1'!BI22) | PCD_DPW1_MTR2_T |  | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) |  | ¬¬IF(ISBLANK('DPW1'!I22),"",'DPW1'!I22) | [7 empty] | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL22),"",'DPW1'!BL22) | PCD_DPW1_MTR2_O |  | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) |  | ¬¬IF(ISBLANK('DPW1'!I22),"",'DPW1'!I22) | [7 empty] | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX22),"",'DPW1'!BX22) | PCD_DPW1_MTR2_OT |  | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) |  | ¬¬IF(ISBLANK('DPW1'!I22),"",'DPW1'!I22) | [7 empty] | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA22),"",'DPW1'!CA22) | PCD_DPW1_MTR2_P |  | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) |  | ¬¬IF(ISBLANK('DPW1'!I22),"",'DPW1'!I22) | [7 empty] | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW23),"",'DPW1'!AW23) | PCD_DPW1_MTR3 |  | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) |  | ¬¬IF(ISBLANK('DPW1'!I23),"",'DPW1'!I23) | [7 empty] | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI23),"",'DPW1'!BI23) | PCD_DPW1_MTR3_T |  | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) |  | ¬¬IF(ISBLANK('DPW1'!I23),"",'DPW1'!I23) | [7 empty] | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL23),"",'DPW1'!BL23) | PCD_DPW1_MTR3_O |  | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) |  | ¬¬IF(ISBLANK('DPW1'!I23),"",'DPW1'!I23) | [7 empty] | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX23),"",'DPW1'!BX23) | PCD_DPW1_MTR3_OT |  | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) |  | ¬¬IF(ISBLANK('DPW1'!I23),"",'DPW1'!I23) | [7 empty] | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA23),"",'DPW1'!CA23) | PCD_DPW1_MTR3_P |  | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) |  | ¬¬IF(ISBLANK('DPW1'!I23),"",'DPW1'!I23) | [7 empty] | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW24),"",'DPW1'!AW24) | PCD_DPW1_MTR4 |  | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) |  | ¬¬IF(ISBLANK('DPW1'!I24),"",'DPW1'!I24) | [7 empty] | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI24),"",'DPW1'!BI24) | PCD_DPW1_MTR4_T |  | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) |  | ¬¬IF(ISBLANK('DPW1'!I24),"",'DPW1'!I24) | [7 empty] | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL24),"",'DPW1'!BL24) | PCD_DPW1_MTR4_O |  | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) |  | ¬¬IF(ISBLANK('DPW1'!I24),"",'DPW1'!I24) | [7 empty] | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX24),"",'DPW1'!BX24) | PCD_DPW1_MTR4_OT |  | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) |  | ¬¬IF(ISBLANK('DPW1'!I24),"",'DPW1'!I24) | [7 empty] | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA24),"",'DPW1'!CA24) | PCD_DPW1_MTR4_P |  | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) |  | ¬¬IF(ISBLANK('DPW1'!I24),"",'DPW1'!I24) | [7 empty] | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW25),"",'DPW1'!AW25) | PCD_DPW1_MTR5 |  | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) |  | ¬¬IF(ISBLANK('DPW1'!I25),"",'DPW1'!I25) | [7 empty] | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI25),"",'DPW1'!BI25) | PCD_DPW1_MTR5_T |  | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) |  | ¬¬IF(ISBLANK('DPW1'!I25),"",'DPW1'!I25) | [7 empty] | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL25),"",'DPW1'!BL25) | PCD_DPW1_MTR5_O |  | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) |  | ¬¬IF(ISBLANK('DPW1'!I25),"",'DPW1'!I25) | [7 empty] | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX25),"",'DPW1'!BX25) | PCD_DPW1_MTR5_OT |  | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) |  | ¬¬IF(ISBLANK('DPW1'!I25),"",'DPW1'!I25) | [7 empty] | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA25),"",'DPW1'!CA25) | PCD_DPW1_MTR5_P |  | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) |  | ¬¬IF(ISBLANK('DPW1'!I25),"",'DPW1'!I25) | [7 empty] | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW26),"",'DPW1'!AW26) | PCD_DPW1_MTR6 |  | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) |  | ¬¬IF(ISBLANK('DPW1'!I26),"",'DPW1'!I26) | [7 empty] | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI26),"",'DPW1'!BI26) | PCD_DPW1_MTR6_T |  | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) |  | ¬¬IF(ISBLANK('DPW1'!I26),"",'DPW1'!I26) | [7 empty] | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL26),"",'DPW1'!BL26) | PCD_DPW1_MTR6_O |  | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) |  | ¬¬IF(ISBLANK('DPW1'!I26),"",'DPW1'!I26) | [7 empty] | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX26),"",'DPW1'!BX26) | PCD_DPW1_MTR6_OT |  | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) |  | ¬¬IF(ISBLANK('DPW1'!I26),"",'DPW1'!I26) | [7 empty] | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA26),"",'DPW1'!CA26) | PCD_DPW1_MTR6_P |  | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) |  | ¬¬IF(ISBLANK('DPW1'!I26),"",'DPW1'!I26) | [7 empty] | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW27),"",'DPW1'!AW27) | PCD_DPW1_MTR7 |  | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) |  | ¬¬IF(ISBLANK('DPW1'!I27),"",'DPW1'!I27) | [7 empty] | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI27),"",'DPW1'!BI27) | PCD_DPW1_MTR7_T |  | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) |  | ¬¬IF(ISBLANK('DPW1'!I27),"",'DPW1'!I27) | [7 empty] | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL27),"",'DPW1'!BL27) | PCD_DPW1_MTR7_O |  | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) |  | ¬¬IF(ISBLANK('DPW1'!I27),"",'DPW1'!I27) | [7 empty] | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX27),"",'DPW1'!BX27) | PCD_DPW1_MTR7_OT |  | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) |  | ¬¬IF(ISBLANK('DPW1'!I27),"",'DPW1'!I27) | [7 empty] | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA27),"",'DPW1'!CA27) | PCD_DPW1_MTR7_P |  | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) |  | ¬¬IF(ISBLANK('DPW1'!I27),"",'DPW1'!I27) | [7 empty] | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW28),"",'DPW1'!AW28) | PCD_DPW1_SPL1 |  | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) |  | ¬¬IF(ISBLANK('DPW1'!I28),"",'DPW1'!I28) | [7 empty] | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI28),"",'DPW1'!BI28) | PCD_DPW1_SPL1_T |  | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) |  | ¬¬IF(ISBLANK('DPW1'!I28),"",'DPW1'!I28) | [7 empty] | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL28),"",'DPW1'!BL28) | PCD_DPW1_SPL1_O |  | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) |  | ¬¬IF(ISBLANK('DPW1'!I28),"",'DPW1'!I28) | [7 empty] | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX28),"",'DPW1'!BX28) | PCD_DPW1_SPL1_OT |  | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) |  | ¬¬IF(ISBLANK('DPW1'!I28),"",'DPW1'!I28) | [7 empty] | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA28),"",'DPW1'!CA28) | PCD_DPW1_SPL1_P |  | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) |  | ¬¬IF(ISBLANK('DPW1'!I28),"",'DPW1'!I28) | [7 empty] | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW29),"",'DPW1'!AW29) | PCD_DPW1_SPL2 |  | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) |  | ¬¬IF(ISBLANK('DPW1'!I29),"",'DPW1'!I29) | [7 empty] | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI29),"",'DPW1'!BI29) | PCD_DPW1_SPL2_T |  | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) |  | ¬¬IF(ISBLANK('DPW1'!I29),"",'DPW1'!I29) | [7 empty] | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL29),"",'DPW1'!BL29) | PCD_DPW1_SPL2_O |  | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) |  | ¬¬IF(ISBLANK('DPW1'!I29),"",'DPW1'!I29) | [7 empty] | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX29),"",'DPW1'!BX29) | PCD_DPW1_SPL2_OT |  | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) |  | ¬¬IF(ISBLANK('DPW1'!I29),"",'DPW1'!I29) | [7 empty] | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA29),"",'DPW1'!CA29) | PCD_DPW1_SPL2_P |  | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) |  | ¬¬IF(ISBLANK('DPW1'!I29),"",'DPW1'!I29) | [7 empty] | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW30),"",'DPW1'!AW30) | PCD_DPW1_SPL3 |  | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) |  | ¬¬IF(ISBLANK('DPW1'!I30),"",'DPW1'!I30) | [7 empty] | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI30),"",'DPW1'!BI30) | PCD_DPW1_SPL3_T |  | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) |  | ¬¬IF(ISBLANK('DPW1'!I30),"",'DPW1'!I30) | [7 empty] | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL30),"",'DPW1'!BL30) | PCD_DPW1_SPL3_O |  | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) |  | ¬¬IF(ISBLANK('DPW1'!I30),"",'DPW1'!I30) | [7 empty] | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX30),"",'DPW1'!BX30) | PCD_DPW1_SPL3_OT |  | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) |  | ¬¬IF(ISBLANK('DPW1'!I30),"",'DPW1'!I30) | [7 empty] | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA30),"",'DPW1'!CA30) | PCD_DPW1_SPL3_P |  | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) |  | ¬¬IF(ISBLANK('DPW1'!I30),"",'DPW1'!I30) | [7 empty] | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW31),"",'DPW1'!AW31) | PCD_DPW1_SPL4 |  | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) |  | ¬¬IF(ISBLANK('DPW1'!I31),"",'DPW1'!I31) | [7 empty] | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI31),"",'DPW1'!BI31) | PCD_DPW1_SPL4_T |  | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) |  | ¬¬IF(ISBLANK('DPW1'!I31),"",'DPW1'!I31) | [7 empty] | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL31),"",'DPW1'!BL31) | PCD_DPW1_SPL4_O |  | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) |  | ¬¬IF(ISBLANK('DPW1'!I31),"",'DPW1'!I31) | [7 empty] | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX31),"",'DPW1'!BX31) | PCD_DPW1_SPL4_OT |  | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) |  | ¬¬IF(ISBLANK('DPW1'!I31),"",'DPW1'!I31) | [7 empty] | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA31),"",'DPW1'!CA31) | PCD_DPW1_SPL4_P |  | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) |  | ¬¬IF(ISBLANK('DPW1'!I31),"",'DPW1'!I31) | [7 empty] | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW32),"",'DPW1'!AW32) | PCD_DPW1_SPL5 |  | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) |  | ¬¬IF(ISBLANK('DPW1'!I32),"",'DPW1'!I32) | [7 empty] | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI32),"",'DPW1'!BI32) | PCD_DPW1_SPL5_T |  | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) |  | ¬¬IF(ISBLANK('DPW1'!I32),"",'DPW1'!I32) | [7 empty] | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL32),"",'DPW1'!BL32) | PCD_DPW1_SPL5_O |  | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) |  | ¬¬IF(ISBLANK('DPW1'!I32),"",'DPW1'!I32) | [7 empty] | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX32),"",'DPW1'!BX32) | PCD_DPW1_SPL5_OT |  | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) |  | ¬¬IF(ISBLANK('DPW1'!I32),"",'DPW1'!I32) | [7 empty] | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA32),"",'DPW1'!CA32) | PCD_DPW1_SPL5_P |  | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) |  | ¬¬IF(ISBLANK('DPW1'!I32),"",'DPW1'!I32) | [7 empty] | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW33),"",'DPW1'!AW33) | PCD_DPW1_SPLIN1 |  | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) |  | ¬¬IF(ISBLANK('DPW1'!I33),"",'DPW1'!I33) | [7 empty] | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI33),"",'DPW1'!BI33) | PCD_DPW1_SPLIN1_T |  | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) |  | ¬¬IF(ISBLANK('DPW1'!I33),"",'DPW1'!I33) | [7 empty] | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL33),"",'DPW1'!BL33) | PCD_DPW1_SPLIN1_O |  | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) |  | ¬¬IF(ISBLANK('DPW1'!I33),"",'DPW1'!I33) | [7 empty] | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX33),"",'DPW1'!BX33) | PCD_DPW1_SPLIN1_OT |  | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) |  | ¬¬IF(ISBLANK('DPW1'!I33),"",'DPW1'!I33) | [7 empty] | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA33),"",'DPW1'!CA33) | PCD_DPW1_SPLIN1_P |  | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) |  | ¬¬IF(ISBLANK('DPW1'!I33),"",'DPW1'!I33) | [7 empty] | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW34),"",'DPW1'!AW34) | PCD_DPW1_SPLIN2 |  | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) |  | ¬¬IF(ISBLANK('DPW1'!I34),"",'DPW1'!I34) | [7 empty] | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI34),"",'DPW1'!BI34) | PCD_DPW1_SPLIN2_T |  | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) |  | ¬¬IF(ISBLANK('DPW1'!I34),"",'DPW1'!I34) | [7 empty] | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL34),"",'DPW1'!BL34) | PCD_DPW1_SPLIN2_O |  | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) |  | ¬¬IF(ISBLANK('DPW1'!I34),"",'DPW1'!I34) | [7 empty] | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX34),"",'DPW1'!BX34) | PCD_DPW1_SPLIN2_OT |  | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) |  | ¬¬IF(ISBLANK('DPW1'!I34),"",'DPW1'!I34) | [7 empty] | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA34),"",'DPW1'!CA34) | PCD_DPW1_SPLIN2_P |  | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) |  | ¬¬IF(ISBLANK('DPW1'!I34),"",'DPW1'!I34) | [7 empty] | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW35),"",'DPW1'!AW35) | PCD_DPW1_EFCY |  | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) |  | ¬¬IF(ISBLANK('DPW1'!I35),"",'DPW1'!I35) | [7 empty] | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI35),"",'DPW1'!BI35) | PCD_DPW1_EFCY_T |  | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) |  | ¬¬IF(ISBLANK('DPW1'!I35),"",'DPW1'!I35) | [7 empty] | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL35),"",'DPW1'!BL35) | PCD_DPW1_EFCY_O |  | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) |  | ¬¬IF(ISBLANK('DPW1'!I35),"",'DPW1'!I35) | [7 empty] | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX35),"",'DPW1'!BX35) | PCD_DPW1_EFCY_OT |  | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) |  | ¬¬IF(ISBLANK('DPW1'!I35),"",'DPW1'!I35) | [7 empty] | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA35),"",'DPW1'!CA35) | PCD_DPW1_EFCY_P |  | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) |  | ¬¬IF(ISBLANK('DPW1'!I35),"",'DPW1'!I35) | [7 empty] | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW36),"",'DPW1'!AW36) | PCD_DPW1_RESIN1 |  | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) |  | ¬¬IF(ISBLANK('DPW1'!I36),"",'DPW1'!I36) | [7 empty] | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI36),"",'DPW1'!BI36) | PCD_DPW1_RESIN1_T |  | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) |  | ¬¬IF(ISBLANK('DPW1'!I36),"",'DPW1'!I36) | [7 empty] | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL36),"",'DPW1'!BL36) | PCD_DPW1_RESIN1_O |  | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) |  | ¬¬IF(ISBLANK('DPW1'!I36),"",'DPW1'!I36) | [7 empty] | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX36),"",'DPW1'!BX36) | PCD_DPW1_RESIN1_OT |  | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) |  | ¬¬IF(ISBLANK('DPW1'!I36),"",'DPW1'!I36) | [7 empty] | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA36),"",'DPW1'!CA36) | PCD_DPW1_RESIN1_P |  | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) |  | ¬¬IF(ISBLANK('DPW1'!I36),"",'DPW1'!I36) | [7 empty] | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW37),"",'DPW1'!AW37) | PCD_DPW1_RESIN2 |  | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) |  | ¬¬IF(ISBLANK('DPW1'!I37),"",'DPW1'!I37) | [7 empty] | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI37),"",'DPW1'!BI37) | PCD_DPW1_RESIN2_T |  | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) |  | ¬¬IF(ISBLANK('DPW1'!I37),"",'DPW1'!I37) | [7 empty] | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL37),"",'DPW1'!BL37) | PCD_DPW1_RESIN2_O |  | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) |  | ¬¬IF(ISBLANK('DPW1'!I37),"",'DPW1'!I37) | [7 empty] | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX37),"",'DPW1'!BX37) | PCD_DPW1_RESIN2_OT |  | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) |  | ¬¬IF(ISBLANK('DPW1'!I37),"",'DPW1'!I37) | [7 empty] | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA37),"",'DPW1'!CA37) | PCD_DPW1_RESIN2_P |  | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) |  | ¬¬IF(ISBLANK('DPW1'!I37),"",'DPW1'!I37) | [7 empty] | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW38),"",'DPW1'!AW38) | PCD_DPW1_RESIN3 |  | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) |  | ¬¬IF(ISBLANK('DPW1'!I38),"",'DPW1'!I38) | [7 empty] | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI38),"",'DPW1'!BI38) | PCD_DPW1_RESIN3_T |  | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) |  | ¬¬IF(ISBLANK('DPW1'!I38),"",'DPW1'!I38) | [7 empty] | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL38),"",'DPW1'!BL38) | PCD_DPW1_RESIN3_O |  | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) |  | ¬¬IF(ISBLANK('DPW1'!I38),"",'DPW1'!I38) | [7 empty] | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX38),"",'DPW1'!BX38) | PCD_DPW1_RESIN3_OT |  | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) |  | ¬¬IF(ISBLANK('DPW1'!I38),"",'DPW1'!I38) | [7 empty] | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA38),"",'DPW1'!CA38) | PCD_DPW1_RESIN3_P |  | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) |  | ¬¬IF(ISBLANK('DPW1'!I38),"",'DPW1'!I38) | [7 empty] | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW39),"",'DPW1'!AW39) | PCD_DPW1_RESIN4 |  | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) |  | ¬¬IF(ISBLANK('DPW1'!I39),"",'DPW1'!I39) | [7 empty] | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI39),"",'DPW1'!BI39) | PCD_DPW1_RESIN4_T |  | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) |  | ¬¬IF(ISBLANK('DPW1'!I39),"",'DPW1'!I39) | [7 empty] | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL39),"",'DPW1'!BL39) | PCD_DPW1_RESIN4_O |  | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) |  | ¬¬IF(ISBLANK('DPW1'!I39),"",'DPW1'!I39) | [7 empty] | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX39),"",'DPW1'!BX39) | PCD_DPW1_RESIN4_OT |  | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) |  | ¬¬IF(ISBLANK('DPW1'!I39),"",'DPW1'!I39) | [7 empty] | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA39),"",'DPW1'!CA39) | PCD_DPW1_RESIN4_P |  | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) |  | ¬¬IF(ISBLANK('DPW1'!I39),"",'DPW1'!I39) | [7 empty] | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW40),"",'DPW1'!AW40) | PCD_DPW1_RES1 |  | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) |  | ¬¬IF(ISBLANK('DPW1'!I40),"",'DPW1'!I40) | [7 empty] | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI40),"",'DPW1'!BI40) | PCD_DPW1_RES1_T |  | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) |  | ¬¬IF(ISBLANK('DPW1'!I40),"",'DPW1'!I40) | [7 empty] | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL40),"",'DPW1'!BL40) | PCD_DPW1_RES1_O |  | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) |  | ¬¬IF(ISBLANK('DPW1'!I40),"",'DPW1'!I40) | [7 empty] | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX40),"",'DPW1'!BX40) | PCD_DPW1_RES1_OT |  | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) |  | ¬¬IF(ISBLANK('DPW1'!I40),"",'DPW1'!I40) | [7 empty] | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA40),"",'DPW1'!CA40) | PCD_DPW1_RES1_P |  | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) |  | ¬¬IF(ISBLANK('DPW1'!I40),"",'DPW1'!I40) | [7 empty] | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW41),"",'DPW1'!AW41) | PCD_DPW1_RES2 |  | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) |  | ¬¬IF(ISBLANK('DPW1'!I41),"",'DPW1'!I41) | [7 empty] | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI41),"",'DPW1'!BI41) | PCD_DPW1_RES2_T |  | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) |  | ¬¬IF(ISBLANK('DPW1'!I41),"",'DPW1'!I41) | [7 empty] | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL41),"",'DPW1'!BL41) | PCD_DPW1_RES2_O |  | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) |  | ¬¬IF(ISBLANK('DPW1'!I41),"",'DPW1'!I41) | [7 empty] | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX41),"",'DPW1'!BX41) | PCD_DPW1_RES2_OT |  | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) |  | ¬¬IF(ISBLANK('DPW1'!I41),"",'DPW1'!I41) | [7 empty] | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA41),"",'DPW1'!CA41) | PCD_DPW1_RES2_P |  | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) |  | ¬¬IF(ISBLANK('DPW1'!I41),"",'DPW1'!I41) | [7 empty] | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW42),"",'DPW1'!AW42) | PCD_DPW1_RES3 |  | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) |  | ¬¬IF(ISBLANK('DPW1'!I42),"",'DPW1'!I42) | [7 empty] | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI42),"",'DPW1'!BI42) | PCD_DPW1_RES3_T |  | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) |  | ¬¬IF(ISBLANK('DPW1'!I42),"",'DPW1'!I42) | [7 empty] | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL42),"",'DPW1'!BL42) | PCD_DPW1_RES3_O |  | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) |  | ¬¬IF(ISBLANK('DPW1'!I42),"",'DPW1'!I42) | [7 empty] | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX42),"",'DPW1'!BX42) | PCD_DPW1_RES3_OT |  | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) |  | ¬¬IF(ISBLANK('DPW1'!I42),"",'DPW1'!I42) | [7 empty] | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA42),"",'DPW1'!CA42) | PCD_DPW1_RES3_P |  | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) |  | ¬¬IF(ISBLANK('DPW1'!I42),"",'DPW1'!I42) | [7 empty] | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW43),"",'DPW1'!AW43) | PCD_DPW1_RES4 |  | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) |  | ¬¬IF(ISBLANK('DPW1'!I43),"",'DPW1'!I43) | [7 empty] | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI43),"",'DPW1'!BI43) | PCD_DPW1_RES4_T |  | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) |  | ¬¬IF(ISBLANK('DPW1'!I43),"",'DPW1'!I43) | [7 empty] | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL43),"",'DPW1'!BL43) | PCD_DPW1_RES4_O |  | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) |  | ¬¬IF(ISBLANK('DPW1'!I43),"",'DPW1'!I43) | [7 empty] | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX43),"",'DPW1'!BX43) | PCD_DPW1_RES4_OT |  | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) |  | ¬¬IF(ISBLANK('DPW1'!I43),"",'DPW1'!I43) | [7 empty] | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA43),"",'DPW1'!CA43) | PCD_DPW1_RES4_P |  | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) |  | ¬¬IF(ISBLANK('DPW1'!I43),"",'DPW1'!I43) | [7 empty] | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW44),"",'DPW1'!AW44) | PCD_DPW1_RES5 |  | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) |  | ¬¬IF(ISBLANK('DPW1'!I44),"",'DPW1'!I44) | [7 empty] | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI44),"",'DPW1'!BI44) | PCD_DPW1_RES5_T |  | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) |  | ¬¬IF(ISBLANK('DPW1'!I44),"",'DPW1'!I44) | [7 empty] | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL44),"",'DPW1'!BL44) | PCD_DPW1_RES5_O |  | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) |  | ¬¬IF(ISBLANK('DPW1'!I44),"",'DPW1'!I44) | [7 empty] | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX44),"",'DPW1'!BX44) | PCD_DPW1_RES5_OT |  | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) |  | ¬¬IF(ISBLANK('DPW1'!I44),"",'DPW1'!I44) | [7 empty] | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA44),"",'DPW1'!CA44) | PCD_DPW1_RES5_P |  | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) |  | ¬¬IF(ISBLANK('DPW1'!I44),"",'DPW1'!I44) | [7 empty] | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW45),"",'DPW1'!AW45) | PCD_DPW1_SEMD |  | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H45),"",'DPW1'!H45) |  | ¬¬IF(ISBLANK('DPW1'!I45),"",'DPW1'!I45) | [7 empty] | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI45),"",'DPW1'!BI45) | PCD_DPW1_SEMD_T |  | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H45),"",'DPW1'!H45) |  | ¬¬IF(ISBLANK('DPW1'!I45),"",'DPW1'!I45) | [7 empty] | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL45),"",'DPW1'!BL45) | PCD_DPW1_SEMD_O |  | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H45),"",'DPW1'!H45) |  | ¬¬IF(ISBLANK('DPW1'!I45),"",'DPW1'!I45) | [7 empty] | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX45),"",'DPW1'!BX45) | PCD_DPW1_SEMD_OT |  | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H45),"",'DPW1'!H45) |  | ¬¬IF(ISBLANK('DPW1'!I45),"",'DPW1'!I45) | [7 empty] | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA45),"",'DPW1'!CA45) | PCD_DPW1_SEMD_P |  | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H45),"",'DPW1'!H45) |  | ¬¬IF(ISBLANK('DPW1'!I45),"",'DPW1'!I45) | [7 empty] | ¬¬'DPW1'!F45 & "," & 'DPW1'!G45 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW46),"",'DPW1'!AW46) | PCD_DPW1_RES6 |  | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) |  | ¬¬IF(ISBLANK('DPW1'!I46),"",'DPW1'!I46) | [7 empty] | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI46),"",'DPW1'!BI46) | PCD_DPW1_RES6_T |  | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) |  | ¬¬IF(ISBLANK('DPW1'!I46),"",'DPW1'!I46) | [7 empty] | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL46),"",'DPW1'!BL46) | PCD_DPW1_RES6_O |  | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) |  | ¬¬IF(ISBLANK('DPW1'!I46),"",'DPW1'!I46) | [7 empty] | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX46),"",'DPW1'!BX46) | PCD_DPW1_RES6_OT |  | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) |  | ¬¬IF(ISBLANK('DPW1'!I46),"",'DPW1'!I46) | [7 empty] | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA46),"",'DPW1'!CA46) | PCD_DPW1_RES6_P |  | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) |  | ¬¬IF(ISBLANK('DPW1'!I46),"",'DPW1'!I46) | [7 empty] | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW47),"",'DPW1'!AW47) | PCD_DPW1_CYBR |  | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) |  | ¬¬IF(ISBLANK('DPW1'!I47),"",'DPW1'!I47) | [7 empty] | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI47),"",'DPW1'!BI47) | PCD_DPW1_CYBR_T |  | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) |  | ¬¬IF(ISBLANK('DPW1'!I47),"",'DPW1'!I47) | [7 empty] | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL47),"",'DPW1'!BL47) | PCD_DPW1_CYBR_O |  | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) |  | ¬¬IF(ISBLANK('DPW1'!I47),"",'DPW1'!I47) | [7 empty] | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX47),"",'DPW1'!BX47) | PCD_DPW1_CYBR_OT |  | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) |  | ¬¬IF(ISBLANK('DPW1'!I47),"",'DPW1'!I47) | [7 empty] | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA47),"",'DPW1'!CA47) | PCD_DPW1_CYBR_P |  | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) |  | ¬¬IF(ISBLANK('DPW1'!I47),"",'DPW1'!I47) | [7 empty] | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW48),"",'DPW1'!AW48) | PCD_DPW1_SEMD |  | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) |  | ¬¬IF(ISBLANK('DPW1'!I48),"",'DPW1'!I48) | [7 empty] | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI48),"",'DPW1'!BI48) | PCD_DPW1_SEMD_T |  | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) |  | ¬¬IF(ISBLANK('DPW1'!I48),"",'DPW1'!I48) | [7 empty] | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL48),"",'DPW1'!BL48) | PCD_DPW1_SEMD_O |  | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) |  | ¬¬IF(ISBLANK('DPW1'!I48),"",'DPW1'!I48) | [7 empty] | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX48),"",'DPW1'!BX48) | PCD_DPW1_SEMD_OT |  | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) |  | ¬¬IF(ISBLANK('DPW1'!I48),"",'DPW1'!I48) | [7 empty] | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA48),"",'DPW1'!CA48) | PCD_DPW1_SEMD_P |  | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) |  | ¬¬IF(ISBLANK('DPW1'!I48),"",'DPW1'!I48) | [7 empty] | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW49),"",'DPW1'!AW49) | PCD_DPW1_SEMD |  | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) |  | ¬¬IF(ISBLANK('DPW1'!I49),"",'DPW1'!I49) | [7 empty] | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI49),"",'DPW1'!BI49) | PCD_DPW1_SEMD_T |  | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) |  | ¬¬IF(ISBLANK('DPW1'!I49),"",'DPW1'!I49) | [7 empty] | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL49),"",'DPW1'!BL49) | PCD_DPW1_SEMD_O |  | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) |  | ¬¬IF(ISBLANK('DPW1'!I49),"",'DPW1'!I49) | [7 empty] | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX49),"",'DPW1'!BX49) | PCD_DPW1_SEMD_OT |  | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) |  | ¬¬IF(ISBLANK('DPW1'!I49),"",'DPW1'!I49) | [7 empty] | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA49),"",'DPW1'!CA49) | PCD_DPW1_SEMD_P |  | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) |  | ¬¬IF(ISBLANK('DPW1'!I49),"",'DPW1'!I49) | [7 empty] | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW1'!AW50),"",'DPW1'!AW50) | PCD_DPW1_SEMD |  | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H50),"",'DPW1'!H50) |  | ¬¬IF(ISBLANK('DPW1'!I50),"",'DPW1'!I50) | [7 empty] | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!AT5
¬¬IF(ISBLANK('DPW1'!BI50),"",'DPW1'!BI50) | PCD_DPW1_SEMD_T |  | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H50),"",'DPW1'!H50) |  | ¬¬IF(ISBLANK('DPW1'!I50),"",'DPW1'!I50) | [7 empty] | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!BI5
¬¬IF(ISBLANK('DPW1'!BL50),"",'DPW1'!BL50) | PCD_DPW1_SEMD_O |  | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H50),"",'DPW1'!H50) |  | ¬¬IF(ISBLANK('DPW1'!I50),"",'DPW1'!I50) | [7 empty] | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!BJ5
¬¬IF(ISBLANK('DPW1'!BX50),"",'DPW1'!BX50) | PCD_DPW1_SEMD_OT |  | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H50),"",'DPW1'!H50) |  | ¬¬IF(ISBLANK('DPW1'!I50),"",'DPW1'!I50) | [7 empty] | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!BX5
¬¬IF(ISBLANK('DPW1'!CA50),"",'DPW1'!CA50) | PCD_DPW1_SEMD_P |  | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H50),"",'DPW1'!H50) |  | ¬¬IF(ISBLANK('DPW1'!I50),"",'DPW1'!I50) | [7 empty] | ¬¬'DPW1'!F50 & "," & 'DPW1'!G50 & "," & 'DPW1'!CA5
¬¬IF(ISBLANK('DPW2'!AV8),"",'DPW2'!AV8) | PCD_DPW2_BIOCON1_NP |  | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) |  | ¬¬IF(ISBLANK('DPW2'!I8),"",'DPW2'!I8) | [7 empty] | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX8),"",'DPW2'!AX8) | PCD_DPW2_BIOCON1 |  | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) |  | ¬¬IF(ISBLANK('DPW2'!I8),"",'DPW2'!I8) | [7 empty] | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ8),"",'DPW2'!BJ8) | PCD_DPW2_BIOCON1_T |  | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) |  | ¬¬IF(ISBLANK('DPW2'!I8),"",'DPW2'!I8) | [7 empty] | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM8),"",'DPW2'!BM8) | PCD_DPW2_BIOCON1_O |  | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) |  | ¬¬IF(ISBLANK('DPW2'!I8),"",'DPW2'!I8) | [7 empty] | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY8),"",'DPW2'!BY8) | PCD_DPW2_BIOCON1_OT |  | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) |  | ¬¬IF(ISBLANK('DPW2'!I8),"",'DPW2'!I8) | [7 empty] | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB8),"",'DPW2'!CB8) | PCD_DPW2_BIOCON1_P |  | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) |  | ¬¬IF(ISBLANK('DPW2'!I8),"",'DPW2'!I8) | [7 empty] | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV9),"",'DPW2'!AV9) | PCD_DPW2_BIOCON2_NP |  | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) |  | ¬¬IF(ISBLANK('DPW2'!I9),"",'DPW2'!I9) | [7 empty] | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX9),"",'DPW2'!AX9) | PCD_DPW2_BIOCON2 |  | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) |  | ¬¬IF(ISBLANK('DPW2'!I9),"",'DPW2'!I9) | [7 empty] | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ9),"",'DPW2'!BJ9) | PCD_DPW2_BIOCON2_T |  | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) |  | ¬¬IF(ISBLANK('DPW2'!I9),"",'DPW2'!I9) | [7 empty] | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM9),"",'DPW2'!BM9) | PCD_DPW2_BIOCON2_O |  | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) |  | ¬¬IF(ISBLANK('DPW2'!I9),"",'DPW2'!I9) | [7 empty] | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY9),"",'DPW2'!BY9) | PCD_DPW2_BIOCON2_OT |  | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) |  | ¬¬IF(ISBLANK('DPW2'!I9),"",'DPW2'!I9) | [7 empty] | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB9),"",'DPW2'!CB9) | PCD_DPW2_BIOCON2_P |  | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) |  | ¬¬IF(ISBLANK('DPW2'!I9),"",'DPW2'!I9) | [7 empty] | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV10),"",'DPW2'!AV10) | PCD_DPW2_DWPA_NP |  | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) |  | ¬¬IF(ISBLANK('DPW2'!I10),"",'DPW2'!I10) | [7 empty] | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX10),"",'DPW2'!AX10) | PCD_DPW2_DWPA |  | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) |  | ¬¬IF(ISBLANK('DPW2'!I10),"",'DPW2'!I10) | [7 empty] | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ10),"",'DPW2'!BJ10) | PCD_DPW2_DWPA_T |  | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) |  | ¬¬IF(ISBLANK('DPW2'!I10),"",'DPW2'!I10) | [7 empty] | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM10),"",'DPW2'!BM10) | PCD_DPW2_DWPA_O |  | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) |  | ¬¬IF(ISBLANK('DPW2'!I10),"",'DPW2'!I10) | [7 empty] | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY10),"",'DPW2'!BY10) | PCD_DPW2_DWPA_OT |  | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) |  | ¬¬IF(ISBLANK('DPW2'!I10),"",'DPW2'!I10) | [7 empty] | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB10),"",'DPW2'!CB10) | PCD_DPW2_DWPA_P |  | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) |  | ¬¬IF(ISBLANK('DPW2'!I10),"",'DPW2'!I10) | [7 empty] | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV11),"",'DPW2'!AV11) | PCD_DPW2_WFDI_NP |  | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) |  | ¬¬IF(ISBLANK('DPW2'!I11),"",'DPW2'!I11) | [7 empty] | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX11),"",'DPW2'!AX11) | PCD_DPW2_WFDI |  | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) |  | ¬¬IF(ISBLANK('DPW2'!I11),"",'DPW2'!I11) | [7 empty] | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ11),"",'DPW2'!BJ11) | PCD_DPW2_WFDI_T |  | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) |  | ¬¬IF(ISBLANK('DPW2'!I11),"",'DPW2'!I11) | [7 empty] | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM11),"",'DPW2'!BM11) | PCD_DPW2_WFDI_O |  | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) |  | ¬¬IF(ISBLANK('DPW2'!I11),"",'DPW2'!I11) | [7 empty] | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY11),"",'DPW2'!BY11) | PCD_DPW2_WFDI_OT |  | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) |  | ¬¬IF(ISBLANK('DPW2'!I11),"",'DPW2'!I11) | [7 empty] | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB11),"",'DPW2'!CB11) | PCD_DPW2_WFDI_P |  | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) |  | ¬¬IF(ISBLANK('DPW2'!I11),"",'DPW2'!I11) | [7 empty] | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV12),"",'DPW2'!AV12) | PCD_DPW2_WFDA_NP |  | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) |  | ¬¬IF(ISBLANK('DPW2'!I12),"",'DPW2'!I12) | [7 empty] | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX12),"",'DPW2'!AX12) | PCD_DPW2_WFDA |  | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) |  | ¬¬IF(ISBLANK('DPW2'!I12),"",'DPW2'!I12) | [7 empty] | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ12),"",'DPW2'!BJ12) | PCD_DPW2_WFDA_T |  | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) |  | ¬¬IF(ISBLANK('DPW2'!I12),"",'DPW2'!I12) | [7 empty] | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM12),"",'DPW2'!BM12) | PCD_DPW2_WFDA_O |  | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) |  | ¬¬IF(ISBLANK('DPW2'!I12),"",'DPW2'!I12) | [7 empty] | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY12),"",'DPW2'!BY12) | PCD_DPW2_WFDA_OT |  | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) |  | ¬¬IF(ISBLANK('DPW2'!I12),"",'DPW2'!I12) | [7 empty] | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB12),"",'DPW2'!CB12) | PCD_DPW2_WFDA_P |  | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) |  | ¬¬IF(ISBLANK('DPW2'!I12),"",'DPW2'!I12) | [7 empty] | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV13),"",'DPW2'!AV13) | PCD_DPW2_WIVG_NP |  | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) |  | ¬¬IF(ISBLANK('DPW2'!I13),"",'DPW2'!I13) | [7 empty] | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX13),"",'DPW2'!AX13) | PCD_DPW2_WIVG |  | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) |  | ¬¬IF(ISBLANK('DPW2'!I13),"",'DPW2'!I13) | [7 empty] | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ13),"",'DPW2'!BJ13) | PCD_DPW2_WIVG_T |  | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) |  | ¬¬IF(ISBLANK('DPW2'!I13),"",'DPW2'!I13) | [7 empty] | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM13),"",'DPW2'!BM13) | PCD_DPW2_WIVG_O |  | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) |  | ¬¬IF(ISBLANK('DPW2'!I13),"",'DPW2'!I13) | [7 empty] | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY13),"",'DPW2'!BY13) | PCD_DPW2_WIVG_OT |  | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) |  | ¬¬IF(ISBLANK('DPW2'!I13),"",'DPW2'!I13) | [7 empty] | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB13),"",'DPW2'!CB13) | PCD_DPW2_WIVG_P |  | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) |  | ¬¬IF(ISBLANK('DPW2'!I13),"",'DPW2'!I13) | [7 empty] | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV14),"",'DPW2'!AV14) | PCD_DPW2_RWD_NP |  | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) |  | ¬¬IF(ISBLANK('DPW2'!I14),"",'DPW2'!I14) | [7 empty] | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX14),"",'DPW2'!AX14) | PCD_DPW2_RWD |  | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) |  | ¬¬IF(ISBLANK('DPW2'!I14),"",'DPW2'!I14) | [7 empty] | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ14),"",'DPW2'!BJ14) | PCD_DPW2_RWD_T |  | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) |  | ¬¬IF(ISBLANK('DPW2'!I14),"",'DPW2'!I14) | [7 empty] | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM14),"",'DPW2'!BM14) | PCD_DPW2_RWD_O |  | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) |  | ¬¬IF(ISBLANK('DPW2'!I14),"",'DPW2'!I14) | [7 empty] | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY14),"",'DPW2'!BY14) | PCD_DPW2_RWD_OT |  | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) |  | ¬¬IF(ISBLANK('DPW2'!I14),"",'DPW2'!I14) | [7 empty] | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB14),"",'DPW2'!CB14) | PCD_DPW2_RWD_P |  | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) |  | ¬¬IF(ISBLANK('DPW2'!I14),"",'DPW2'!I14) | [7 empty] | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV15),"",'DPW2'!AV15) | PCD_DPW2_LEAD1_NP |  | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) |  | ¬¬IF(ISBLANK('DPW2'!I15),"",'DPW2'!I15) | [7 empty] | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX15),"",'DPW2'!AX15) | PCD_DPW2_LEAD1 |  | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) |  | ¬¬IF(ISBLANK('DPW2'!I15),"",'DPW2'!I15) | [7 empty] | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ15),"",'DPW2'!BJ15) | PCD_DPW2_LEAD1_T |  | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) |  | ¬¬IF(ISBLANK('DPW2'!I15),"",'DPW2'!I15) | [7 empty] | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM15),"",'DPW2'!BM15) | PCD_DPW2_LEAD1_O |  | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) |  | ¬¬IF(ISBLANK('DPW2'!I15),"",'DPW2'!I15) | [7 empty] | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY15),"",'DPW2'!BY15) | PCD_DPW2_LEAD1_OT |  | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) |  | ¬¬IF(ISBLANK('DPW2'!I15),"",'DPW2'!I15) | [7 empty] | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB15),"",'DPW2'!CB15) | PCD_DPW2_LEAD1_P |  | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) |  | ¬¬IF(ISBLANK('DPW2'!I15),"",'DPW2'!I15) | [7 empty] | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV16),"",'DPW2'!AV16) | PCD_DPW2_LEAD2_NP |  | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) |  | ¬¬IF(ISBLANK('DPW2'!I16),"",'DPW2'!I16) | [7 empty] | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX16),"",'DPW2'!AX16) | PCD_DPW2_LEAD2 |  | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) |  | ¬¬IF(ISBLANK('DPW2'!I16),"",'DPW2'!I16) | [7 empty] | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ16),"",'DPW2'!BJ16) | PCD_DPW2_LEAD2_T |  | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) |  | ¬¬IF(ISBLANK('DPW2'!I16),"",'DPW2'!I16) | [7 empty] | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM16),"",'DPW2'!BM16) | PCD_DPW2_LEAD2_O |  | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) |  | ¬¬IF(ISBLANK('DPW2'!I16),"",'DPW2'!I16) | [7 empty] | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY16),"",'DPW2'!BY16) | PCD_DPW2_LEAD2_OT |  | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) |  | ¬¬IF(ISBLANK('DPW2'!I16),"",'DPW2'!I16) | [7 empty] | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB16),"",'DPW2'!CB16) | PCD_DPW2_LEAD2_P |  | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) |  | ¬¬IF(ISBLANK('DPW2'!I16),"",'DPW2'!I16) | [7 empty] | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV17),"",'DPW2'!AV17) | PCD_DPW2_LEAD3_NP |  | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) |  | ¬¬IF(ISBLANK('DPW2'!I17),"",'DPW2'!I17) | [7 empty] | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX17),"",'DPW2'!AX17) | PCD_DPW2_LEAD3 |  | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) |  | ¬¬IF(ISBLANK('DPW2'!I17),"",'DPW2'!I17) | [7 empty] | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ17),"",'DPW2'!BJ17) | PCD_DPW2_LEAD3_T |  | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) |  | ¬¬IF(ISBLANK('DPW2'!I17),"",'DPW2'!I17) | [7 empty] | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM17),"",'DPW2'!BM17) | PCD_DPW2_LEAD3_O |  | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) |  | ¬¬IF(ISBLANK('DPW2'!I17),"",'DPW2'!I17) | [7 empty] | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY17),"",'DPW2'!BY17) | PCD_DPW2_LEAD3_OT |  | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) |  | ¬¬IF(ISBLANK('DPW2'!I17),"",'DPW2'!I17) | [7 empty] | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB17),"",'DPW2'!CB17) | PCD_DPW2_LEAD3_P |  | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) |  | ¬¬IF(ISBLANK('DPW2'!I17),"",'DPW2'!I17) | [7 empty] | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV18),"",'DPW2'!AV18) | PCD_DPW2_LEAD4_NP |  | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) |  | ¬¬IF(ISBLANK('DPW2'!I18),"",'DPW2'!I18) | [7 empty] | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX18),"",'DPW2'!AX18) | PCD_DPW2_LEAD4 |  | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) |  | ¬¬IF(ISBLANK('DPW2'!I18),"",'DPW2'!I18) | [7 empty] | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ18),"",'DPW2'!BJ18) | PCD_DPW2_LEAD4_T |  | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) |  | ¬¬IF(ISBLANK('DPW2'!I18),"",'DPW2'!I18) | [7 empty] | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM18),"",'DPW2'!BM18) | PCD_DPW2_LEAD4_O |  | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) |  | ¬¬IF(ISBLANK('DPW2'!I18),"",'DPW2'!I18) | [7 empty] | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY18),"",'DPW2'!BY18) | PCD_DPW2_LEAD4_OT |  | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) |  | ¬¬IF(ISBLANK('DPW2'!I18),"",'DPW2'!I18) | [7 empty] | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB18),"",'DPW2'!CB18) | PCD_DPW2_LEAD4_P |  | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) |  | ¬¬IF(ISBLANK('DPW2'!I18),"",'DPW2'!I18) | [7 empty] | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV19),"",'DPW2'!AV19) | PCD_DPW2_LEAD5_NP |  | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) |  | ¬¬IF(ISBLANK('DPW2'!I19),"",'DPW2'!I19) | [7 empty] | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX19),"",'DPW2'!AX19) | PCD_DPW2_LEAD5 |  | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) |  | ¬¬IF(ISBLANK('DPW2'!I19),"",'DPW2'!I19) | [7 empty] | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ19),"",'DPW2'!BJ19) | PCD_DPW2_LEAD5_T |  | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) |  | ¬¬IF(ISBLANK('DPW2'!I19),"",'DPW2'!I19) | [7 empty] | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM19),"",'DPW2'!BM19) | PCD_DPW2_LEAD5_O |  | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) |  | ¬¬IF(ISBLANK('DPW2'!I19),"",'DPW2'!I19) | [7 empty] | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY19),"",'DPW2'!BY19) | PCD_DPW2_LEAD5_OT |  | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) |  | ¬¬IF(ISBLANK('DPW2'!I19),"",'DPW2'!I19) | [7 empty] | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB19),"",'DPW2'!CB19) | PCD_DPW2_LEAD5_P |  | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) |  | ¬¬IF(ISBLANK('DPW2'!I19),"",'DPW2'!I19) | [7 empty] | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV20),"",'DPW2'!AV20) | PCD_DPW2_WRESUP_NP |  | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) |  | ¬¬IF(ISBLANK('DPW2'!I20),"",'DPW2'!I20) | [7 empty] | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX20),"",'DPW2'!AX20) | PCD_DPW2_WRESUP |  | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) |  | ¬¬IF(ISBLANK('DPW2'!I20),"",'DPW2'!I20) | [7 empty] | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ20),"",'DPW2'!BJ20) | PCD_DPW2_WRESUP_T |  | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) |  | ¬¬IF(ISBLANK('DPW2'!I20),"",'DPW2'!I20) | [7 empty] | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM20),"",'DPW2'!BM20) | PCD_DPW2_WRESUP_O |  | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) |  | ¬¬IF(ISBLANK('DPW2'!I20),"",'DPW2'!I20) | [7 empty] | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY20),"",'DPW2'!BY20) | PCD_DPW2_WRESUP_OT |  | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) |  | ¬¬IF(ISBLANK('DPW2'!I20),"",'DPW2'!I20) | [7 empty] | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB20),"",'DPW2'!CB20) | PCD_DPW2_WRESUP_P |  | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) |  | ¬¬IF(ISBLANK('DPW2'!I20),"",'DPW2'!I20) | [7 empty] | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV21),"",'DPW2'!AV21) | PCD_DPW2_MTR1_NP |  | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) |  | ¬¬IF(ISBLANK('DPW2'!I21),"",'DPW2'!I21) | [7 empty] | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX21),"",'DPW2'!AX21) | PCD_DPW2_MTR1 |  | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) |  | ¬¬IF(ISBLANK('DPW2'!I21),"",'DPW2'!I21) | [7 empty] | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ21),"",'DPW2'!BJ21) | PCD_DPW2_MTR1_T |  | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) |  | ¬¬IF(ISBLANK('DPW2'!I21),"",'DPW2'!I21) | [7 empty] | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM21),"",'DPW2'!BM21) | PCD_DPW2_MTR1_O |  | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) |  | ¬¬IF(ISBLANK('DPW2'!I21),"",'DPW2'!I21) | [7 empty] | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY21),"",'DPW2'!BY21) | PCD_DPW2_MTR1_OT |  | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) |  | ¬¬IF(ISBLANK('DPW2'!I21),"",'DPW2'!I21) | [7 empty] | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB21),"",'DPW2'!CB21) | PCD_DPW2_MTR1_P |  | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) |  | ¬¬IF(ISBLANK('DPW2'!I21),"",'DPW2'!I21) | [7 empty] | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV22),"",'DPW2'!AV22) | PCD_DPW2_MTR2_NP |  | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) |  | ¬¬IF(ISBLANK('DPW2'!I22),"",'DPW2'!I22) | [7 empty] | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX22),"",'DPW2'!AX22) | PCD_DPW2_MTR2 |  | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) |  | ¬¬IF(ISBLANK('DPW2'!I22),"",'DPW2'!I22) | [7 empty] | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ22),"",'DPW2'!BJ22) | PCD_DPW2_MTR2_T |  | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) |  | ¬¬IF(ISBLANK('DPW2'!I22),"",'DPW2'!I22) | [7 empty] | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM22),"",'DPW2'!BM22) | PCD_DPW2_MTR2_O |  | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) |  | ¬¬IF(ISBLANK('DPW2'!I22),"",'DPW2'!I22) | [7 empty] | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY22),"",'DPW2'!BY22) | PCD_DPW2_MTR2_OT |  | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) |  | ¬¬IF(ISBLANK('DPW2'!I22),"",'DPW2'!I22) | [7 empty] | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB22),"",'DPW2'!CB22) | PCD_DPW2_MTR2_P |  | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) |  | ¬¬IF(ISBLANK('DPW2'!I22),"",'DPW2'!I22) | [7 empty] | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV23),"",'DPW2'!AV23) | PCD_DPW2_MTR3_NP |  | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) |  | ¬¬IF(ISBLANK('DPW2'!I23),"",'DPW2'!I23) | [7 empty] | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX23),"",'DPW2'!AX23) | PCD_DPW2_MTR3 |  | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) |  | ¬¬IF(ISBLANK('DPW2'!I23),"",'DPW2'!I23) | [7 empty] | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ23),"",'DPW2'!BJ23) | PCD_DPW2_MTR3_T |  | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) |  | ¬¬IF(ISBLANK('DPW2'!I23),"",'DPW2'!I23) | [7 empty] | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM23),"",'DPW2'!BM23) | PCD_DPW2_MTR3_O |  | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) |  | ¬¬IF(ISBLANK('DPW2'!I23),"",'DPW2'!I23) | [7 empty] | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY23),"",'DPW2'!BY23) | PCD_DPW2_MTR3_OT |  | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) |  | ¬¬IF(ISBLANK('DPW2'!I23),"",'DPW2'!I23) | [7 empty] | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB23),"",'DPW2'!CB23) | PCD_DPW2_MTR3_P |  | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) |  | ¬¬IF(ISBLANK('DPW2'!I23),"",'DPW2'!I23) | [7 empty] | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV24),"",'DPW2'!AV24) | PCD_DPW2_MTR4_NP |  | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) |  | ¬¬IF(ISBLANK('DPW2'!I24),"",'DPW2'!I24) | [7 empty] | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX24),"",'DPW2'!AX24) | PCD_DPW2_MTR4 |  | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) |  | ¬¬IF(ISBLANK('DPW2'!I24),"",'DPW2'!I24) | [7 empty] | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ24),"",'DPW2'!BJ24) | PCD_DPW2_MTR4_T |  | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) |  | ¬¬IF(ISBLANK('DPW2'!I24),"",'DPW2'!I24) | [7 empty] | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM24),"",'DPW2'!BM24) | PCD_DPW2_MTR4_O |  | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) |  | ¬¬IF(ISBLANK('DPW2'!I24),"",'DPW2'!I24) | [7 empty] | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY24),"",'DPW2'!BY24) | PCD_DPW2_MTR4_OT |  | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) |  | ¬¬IF(ISBLANK('DPW2'!I24),"",'DPW2'!I24) | [7 empty] | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB24),"",'DPW2'!CB24) | PCD_DPW2_MTR4_P |  | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) |  | ¬¬IF(ISBLANK('DPW2'!I24),"",'DPW2'!I24) | [7 empty] | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV25),"",'DPW2'!AV25) | PCD_DPW2_MTR5_NP |  | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) |  | ¬¬IF(ISBLANK('DPW2'!I25),"",'DPW2'!I25) | [7 empty] | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX25),"",'DPW2'!AX25) | PCD_DPW2_MTR5 |  | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) |  | ¬¬IF(ISBLANK('DPW2'!I25),"",'DPW2'!I25) | [7 empty] | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ25),"",'DPW2'!BJ25) | PCD_DPW2_MTR5_T |  | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) |  | ¬¬IF(ISBLANK('DPW2'!I25),"",'DPW2'!I25) | [7 empty] | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM25),"",'DPW2'!BM25) | PCD_DPW2_MTR5_O |  | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) |  | ¬¬IF(ISBLANK('DPW2'!I25),"",'DPW2'!I25) | [7 empty] | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY25),"",'DPW2'!BY25) | PCD_DPW2_MTR5_OT |  | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) |  | ¬¬IF(ISBLANK('DPW2'!I25),"",'DPW2'!I25) | [7 empty] | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB25),"",'DPW2'!CB25) | PCD_DPW2_MTR5_P |  | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) |  | ¬¬IF(ISBLANK('DPW2'!I25),"",'DPW2'!I25) | [7 empty] | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV26),"",'DPW2'!AV26) | PCD_DPW2_MTR6_NP |  | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) |  | ¬¬IF(ISBLANK('DPW2'!I26),"",'DPW2'!I26) | [7 empty] | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX26),"",'DPW2'!AX26) | PCD_DPW2_MTR6 |  | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) |  | ¬¬IF(ISBLANK('DPW2'!I26),"",'DPW2'!I26) | [7 empty] | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ26),"",'DPW2'!BJ26) | PCD_DPW2_MTR6_T |  | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) |  | ¬¬IF(ISBLANK('DPW2'!I26),"",'DPW2'!I26) | [7 empty] | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM26),"",'DPW2'!BM26) | PCD_DPW2_MTR6_O |  | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) |  | ¬¬IF(ISBLANK('DPW2'!I26),"",'DPW2'!I26) | [7 empty] | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY26),"",'DPW2'!BY26) | PCD_DPW2_MTR6_OT |  | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) |  | ¬¬IF(ISBLANK('DPW2'!I26),"",'DPW2'!I26) | [7 empty] | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB26),"",'DPW2'!CB26) | PCD_DPW2_MTR6_P |  | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) |  | ¬¬IF(ISBLANK('DPW2'!I26),"",'DPW2'!I26) | [7 empty] | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV27),"",'DPW2'!AV27) | PCD_DPW2_MTR7_NP |  | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) |  | ¬¬IF(ISBLANK('DPW2'!I27),"",'DPW2'!I27) | [7 empty] | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX27),"",'DPW2'!AX27) | PCD_DPW2_MTR7 |  | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) |  | ¬¬IF(ISBLANK('DPW2'!I27),"",'DPW2'!I27) | [7 empty] | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ27),"",'DPW2'!BJ27) | PCD_DPW2_MTR7_T |  | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) |  | ¬¬IF(ISBLANK('DPW2'!I27),"",'DPW2'!I27) | [7 empty] | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM27),"",'DPW2'!BM27) | PCD_DPW2_MTR7_O |  | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) |  | ¬¬IF(ISBLANK('DPW2'!I27),"",'DPW2'!I27) | [7 empty] | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY27),"",'DPW2'!BY27) | PCD_DPW2_MTR7_OT |  | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) |  | ¬¬IF(ISBLANK('DPW2'!I27),"",'DPW2'!I27) | [7 empty] | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB27),"",'DPW2'!CB27) | PCD_DPW2_MTR7_P |  | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) |  | ¬¬IF(ISBLANK('DPW2'!I27),"",'DPW2'!I27) | [7 empty] | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV28),"",'DPW2'!AV28) | PCD_DPW2_SPL1_NP |  | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) |  | ¬¬IF(ISBLANK('DPW2'!I28),"",'DPW2'!I28) | [7 empty] | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX28),"",'DPW2'!AX28) | PCD_DPW2_SPL1 |  | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) |  | ¬¬IF(ISBLANK('DPW2'!I28),"",'DPW2'!I28) | [7 empty] | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ28),"",'DPW2'!BJ28) | PCD_DPW2_SPL1_T |  | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) |  | ¬¬IF(ISBLANK('DPW2'!I28),"",'DPW2'!I28) | [7 empty] | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM28),"",'DPW2'!BM28) | PCD_DPW2_SPL1_O |  | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) |  | ¬¬IF(ISBLANK('DPW2'!I28),"",'DPW2'!I28) | [7 empty] | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY28),"",'DPW2'!BY28) | PCD_DPW2_SPL1_OT |  | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) |  | ¬¬IF(ISBLANK('DPW2'!I28),"",'DPW2'!I28) | [7 empty] | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB28),"",'DPW2'!CB28) | PCD_DPW2_SPL1_P |  | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) |  | ¬¬IF(ISBLANK('DPW2'!I28),"",'DPW2'!I28) | [7 empty] | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV29),"",'DPW2'!AV29) | PCD_DPW2_SPL2_NP |  | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) |  | ¬¬IF(ISBLANK('DPW2'!I29),"",'DPW2'!I29) | [7 empty] | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX29),"",'DPW2'!AX29) | PCD_DPW2_SPL2 |  | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) |  | ¬¬IF(ISBLANK('DPW2'!I29),"",'DPW2'!I29) | [7 empty] | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ29),"",'DPW2'!BJ29) | PCD_DPW2_SPL2_T |  | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) |  | ¬¬IF(ISBLANK('DPW2'!I29),"",'DPW2'!I29) | [7 empty] | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM29),"",'DPW2'!BM29) | PCD_DPW2_SPL2_O |  | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) |  | ¬¬IF(ISBLANK('DPW2'!I29),"",'DPW2'!I29) | [7 empty] | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY29),"",'DPW2'!BY29) | PCD_DPW2_SPL2_OT |  | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) |  | ¬¬IF(ISBLANK('DPW2'!I29),"",'DPW2'!I29) | [7 empty] | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB29),"",'DPW2'!CB29) | PCD_DPW2_SPL2_P |  | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) |  | ¬¬IF(ISBLANK('DPW2'!I29),"",'DPW2'!I29) | [7 empty] | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV30),"",'DPW2'!AV30) | PCD_DPW2_SPL3_NP |  | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) |  | ¬¬IF(ISBLANK('DPW2'!I30),"",'DPW2'!I30) | [7 empty] | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX30),"",'DPW2'!AX30) | PCD_DPW2_SPL3 |  | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) |  | ¬¬IF(ISBLANK('DPW2'!I30),"",'DPW2'!I30) | [7 empty] | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ30),"",'DPW2'!BJ30) | PCD_DPW2_SPL3_T |  | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) |  | ¬¬IF(ISBLANK('DPW2'!I30),"",'DPW2'!I30) | [7 empty] | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM30),"",'DPW2'!BM30) | PCD_DPW2_SPL3_O |  | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) |  | ¬¬IF(ISBLANK('DPW2'!I30),"",'DPW2'!I30) | [7 empty] | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY30),"",'DPW2'!BY30) | PCD_DPW2_SPL3_OT |  | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) |  | ¬¬IF(ISBLANK('DPW2'!I30),"",'DPW2'!I30) | [7 empty] | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB30),"",'DPW2'!CB30) | PCD_DPW2_SPL3_P |  | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) |  | ¬¬IF(ISBLANK('DPW2'!I30),"",'DPW2'!I30) | [7 empty] | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV31),"",'DPW2'!AV31) | PCD_DPW2_SPL4_NP |  | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) |  | ¬¬IF(ISBLANK('DPW2'!I31),"",'DPW2'!I31) | [7 empty] | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX31),"",'DPW2'!AX31) | PCD_DPW2_SPL4 |  | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) |  | ¬¬IF(ISBLANK('DPW2'!I31),"",'DPW2'!I31) | [7 empty] | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ31),"",'DPW2'!BJ31) | PCD_DPW2_SPL4_T |  | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) |  | ¬¬IF(ISBLANK('DPW2'!I31),"",'DPW2'!I31) | [7 empty] | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM31),"",'DPW2'!BM31) | PCD_DPW2_SPL4_O |  | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) |  | ¬¬IF(ISBLANK('DPW2'!I31),"",'DPW2'!I31) | [7 empty] | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY31),"",'DPW2'!BY31) | PCD_DPW2_SPL4_OT |  | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) |  | ¬¬IF(ISBLANK('DPW2'!I31),"",'DPW2'!I31) | [7 empty] | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB31),"",'DPW2'!CB31) | PCD_DPW2_SPL4_P |  | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) |  | ¬¬IF(ISBLANK('DPW2'!I31),"",'DPW2'!I31) | [7 empty] | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV32),"",'DPW2'!AV32) | PCD_DPW2_SPL5_NP |  | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) |  | ¬¬IF(ISBLANK('DPW2'!I32),"",'DPW2'!I32) | [7 empty] | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX32),"",'DPW2'!AX32) | PCD_DPW2_SPL5 |  | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) |  | ¬¬IF(ISBLANK('DPW2'!I32),"",'DPW2'!I32) | [7 empty] | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ32),"",'DPW2'!BJ32) | PCD_DPW2_SPL5_T |  | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) |  | ¬¬IF(ISBLANK('DPW2'!I32),"",'DPW2'!I32) | [7 empty] | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM32),"",'DPW2'!BM32) | PCD_DPW2_SPL5_O |  | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) |  | ¬¬IF(ISBLANK('DPW2'!I32),"",'DPW2'!I32) | [7 empty] | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY32),"",'DPW2'!BY32) | PCD_DPW2_SPL5_OT |  | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) |  | ¬¬IF(ISBLANK('DPW2'!I32),"",'DPW2'!I32) | [7 empty] | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB32),"",'DPW2'!CB32) | PCD_DPW2_SPL5_P |  | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) |  | ¬¬IF(ISBLANK('DPW2'!I32),"",'DPW2'!I32) | [7 empty] | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV33),"",'DPW2'!AV33) | PCD_DPW2_SPLIN1_NP |  | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) |  | ¬¬IF(ISBLANK('DPW2'!I33),"",'DPW2'!I33) | [7 empty] | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX33),"",'DPW2'!AX33) | PCD_DPW2_SPLIN1 |  | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) |  | ¬¬IF(ISBLANK('DPW2'!I33),"",'DPW2'!I33) | [7 empty] | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ33),"",'DPW2'!BJ33) | PCD_DPW2_SPLIN1_T |  | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) |  | ¬¬IF(ISBLANK('DPW2'!I33),"",'DPW2'!I33) | [7 empty] | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM33),"",'DPW2'!BM33) | PCD_DPW2_SPLIN1_O |  | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) |  | ¬¬IF(ISBLANK('DPW2'!I33),"",'DPW2'!I33) | [7 empty] | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY33),"",'DPW2'!BY33) | PCD_DPW2_SPLIN1_OT |  | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) |  | ¬¬IF(ISBLANK('DPW2'!I33),"",'DPW2'!I33) | [7 empty] | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB33),"",'DPW2'!CB33) | PCD_DPW2_SPLIN1_P |  | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) |  | ¬¬IF(ISBLANK('DPW2'!I33),"",'DPW2'!I33) | [7 empty] | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV34),"",'DPW2'!AV34) | PCD_DPW2_SPLIN2_NP |  | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) |  | ¬¬IF(ISBLANK('DPW2'!I34),"",'DPW2'!I34) | [7 empty] | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX34),"",'DPW2'!AX34) | PCD_DPW2_SPLIN2 |  | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) |  | ¬¬IF(ISBLANK('DPW2'!I34),"",'DPW2'!I34) | [7 empty] | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ34),"",'DPW2'!BJ34) | PCD_DPW2_SPLIN2_T |  | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) |  | ¬¬IF(ISBLANK('DPW2'!I34),"",'DPW2'!I34) | [7 empty] | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM34),"",'DPW2'!BM34) | PCD_DPW2_SPLIN2_O |  | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) |  | ¬¬IF(ISBLANK('DPW2'!I34),"",'DPW2'!I34) | [7 empty] | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY34),"",'DPW2'!BY34) | PCD_DPW2_SPLIN2_OT |  | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) |  | ¬¬IF(ISBLANK('DPW2'!I34),"",'DPW2'!I34) | [7 empty] | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB34),"",'DPW2'!CB34) | PCD_DPW2_SPLIN2_P |  | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) |  | ¬¬IF(ISBLANK('DPW2'!I34),"",'DPW2'!I34) | [7 empty] | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV35),"",'DPW2'!AV35) | PCD_DPW2_EFCY_NP |  | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) |  | ¬¬IF(ISBLANK('DPW2'!I35),"",'DPW2'!I35) | [7 empty] | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX35),"",'DPW2'!AX35) | PCD_DPW2_EFCY |  | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) |  | ¬¬IF(ISBLANK('DPW2'!I35),"",'DPW2'!I35) | [7 empty] | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ35),"",'DPW2'!BJ35) | PCD_DPW2_EFCY_T |  | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) |  | ¬¬IF(ISBLANK('DPW2'!I35),"",'DPW2'!I35) | [7 empty] | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM35),"",'DPW2'!BM35) | PCD_DPW2_EFCY_O |  | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) |  | ¬¬IF(ISBLANK('DPW2'!I35),"",'DPW2'!I35) | [7 empty] | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY35),"",'DPW2'!BY35) | PCD_DPW2_EFCY_OT |  | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) |  | ¬¬IF(ISBLANK('DPW2'!I35),"",'DPW2'!I35) | [7 empty] | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB35),"",'DPW2'!CB35) | PCD_DPW2_EFCY_P |  | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) |  | ¬¬IF(ISBLANK('DPW2'!I35),"",'DPW2'!I35) | [7 empty] | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV36),"",'DPW2'!AV36) | PCD_DPW2_RESIN1_NP |  | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) |  | ¬¬IF(ISBLANK('DPW2'!I36),"",'DPW2'!I36) | [7 empty] | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX36),"",'DPW2'!AX36) | PCD_DPW2_RESIN1 |  | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) |  | ¬¬IF(ISBLANK('DPW2'!I36),"",'DPW2'!I36) | [7 empty] | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ36),"",'DPW2'!BJ36) | PCD_DPW2_RESIN1_T |  | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) |  | ¬¬IF(ISBLANK('DPW2'!I36),"",'DPW2'!I36) | [7 empty] | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM36),"",'DPW2'!BM36) | PCD_DPW2_RESIN1_O |  | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) |  | ¬¬IF(ISBLANK('DPW2'!I36),"",'DPW2'!I36) | [7 empty] | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY36),"",'DPW2'!BY36) | PCD_DPW2_RESIN1_OT |  | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) |  | ¬¬IF(ISBLANK('DPW2'!I36),"",'DPW2'!I36) | [7 empty] | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB36),"",'DPW2'!CB36) | PCD_DPW2_RESIN1_P |  | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) |  | ¬¬IF(ISBLANK('DPW2'!I36),"",'DPW2'!I36) | [7 empty] | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV37),"",'DPW2'!AV37) | PCD_DPW2_RESIN2_NP |  | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) |  | ¬¬IF(ISBLANK('DPW2'!I37),"",'DPW2'!I37) | [7 empty] | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX37),"",'DPW2'!AX37) | PCD_DPW2_RESIN2 |  | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) |  | ¬¬IF(ISBLANK('DPW2'!I37),"",'DPW2'!I37) | [7 empty] | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ37),"",'DPW2'!BJ37) | PCD_DPW2_RESIN2_T |  | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) |  | ¬¬IF(ISBLANK('DPW2'!I37),"",'DPW2'!I37) | [7 empty] | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM37),"",'DPW2'!BM37) | PCD_DPW2_RESIN2_O |  | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) |  | ¬¬IF(ISBLANK('DPW2'!I37),"",'DPW2'!I37) | [7 empty] | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY37),"",'DPW2'!BY37) | PCD_DPW2_RESIN2_OT |  | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) |  | ¬¬IF(ISBLANK('DPW2'!I37),"",'DPW2'!I37) | [7 empty] | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB37),"",'DPW2'!CB37) | PCD_DPW2_RESIN2_P |  | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) |  | ¬¬IF(ISBLANK('DPW2'!I37),"",'DPW2'!I37) | [7 empty] | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV38),"",'DPW2'!AV38) | PCD_DPW2_RESIN3_NP |  | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) |  | ¬¬IF(ISBLANK('DPW2'!I38),"",'DPW2'!I38) | [7 empty] | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX38),"",'DPW2'!AX38) | PCD_DPW2_RESIN3 |  | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) |  | ¬¬IF(ISBLANK('DPW2'!I38),"",'DPW2'!I38) | [7 empty] | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ38),"",'DPW2'!BJ38) | PCD_DPW2_RESIN3_T |  | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) |  | ¬¬IF(ISBLANK('DPW2'!I38),"",'DPW2'!I38) | [7 empty] | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM38),"",'DPW2'!BM38) | PCD_DPW2_RESIN3_O |  | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) |  | ¬¬IF(ISBLANK('DPW2'!I38),"",'DPW2'!I38) | [7 empty] | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY38),"",'DPW2'!BY38) | PCD_DPW2_RESIN3_OT |  | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) |  | ¬¬IF(ISBLANK('DPW2'!I38),"",'DPW2'!I38) | [7 empty] | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB38),"",'DPW2'!CB38) | PCD_DPW2_RESIN3_P |  | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) |  | ¬¬IF(ISBLANK('DPW2'!I38),"",'DPW2'!I38) | [7 empty] | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV39),"",'DPW2'!AV39) | PCD_DPW2_RESIN4_NP |  | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) |  | ¬¬IF(ISBLANK('DPW2'!I39),"",'DPW2'!I39) | [7 empty] | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX39),"",'DPW2'!AX39) | PCD_DPW2_RESIN4 |  | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) |  | ¬¬IF(ISBLANK('DPW2'!I39),"",'DPW2'!I39) | [7 empty] | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ39),"",'DPW2'!BJ39) | PCD_DPW2_RESIN4_T |  | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) |  | ¬¬IF(ISBLANK('DPW2'!I39),"",'DPW2'!I39) | [7 empty] | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM39),"",'DPW2'!BM39) | PCD_DPW2_RESIN4_O |  | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) |  | ¬¬IF(ISBLANK('DPW2'!I39),"",'DPW2'!I39) | [7 empty] | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY39),"",'DPW2'!BY39) | PCD_DPW2_RESIN4_OT |  | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) |  | ¬¬IF(ISBLANK('DPW2'!I39),"",'DPW2'!I39) | [7 empty] | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB39),"",'DPW2'!CB39) | PCD_DPW2_RESIN4_P |  | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) |  | ¬¬IF(ISBLANK('DPW2'!I39),"",'DPW2'!I39) | [7 empty] | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV40),"",'DPW2'!AV40) | PCD_DPW2_RES1_NP |  | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) |  | ¬¬IF(ISBLANK('DPW2'!I40),"",'DPW2'!I40) | [7 empty] | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX40),"",'DPW2'!AX40) | PCD_DPW2_RES1 |  | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) |  | ¬¬IF(ISBLANK('DPW2'!I40),"",'DPW2'!I40) | [7 empty] | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ40),"",'DPW2'!BJ40) | PCD_DPW2_RES1_T |  | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) |  | ¬¬IF(ISBLANK('DPW2'!I40),"",'DPW2'!I40) | [7 empty] | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM40),"",'DPW2'!BM40) | PCD_DPW2_RES1_O |  | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) |  | ¬¬IF(ISBLANK('DPW2'!I40),"",'DPW2'!I40) | [7 empty] | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY40),"",'DPW2'!BY40) | PCD_DPW2_RES1_OT |  | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) |  | ¬¬IF(ISBLANK('DPW2'!I40),"",'DPW2'!I40) | [7 empty] | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB40),"",'DPW2'!CB40) | PCD_DPW2_RES1_P |  | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) |  | ¬¬IF(ISBLANK('DPW2'!I40),"",'DPW2'!I40) | [7 empty] | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV41),"",'DPW2'!AV41) | PCD_DPW2_RES2_NP |  | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) |  | ¬¬IF(ISBLANK('DPW2'!I41),"",'DPW2'!I41) | [7 empty] | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX41),"",'DPW2'!AX41) | PCD_DPW2_RES2 |  | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) |  | ¬¬IF(ISBLANK('DPW2'!I41),"",'DPW2'!I41) | [7 empty] | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ41),"",'DPW2'!BJ41) | PCD_DPW2_RES2_T |  | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) |  | ¬¬IF(ISBLANK('DPW2'!I41),"",'DPW2'!I41) | [7 empty] | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM41),"",'DPW2'!BM41) | PCD_DPW2_RES2_O |  | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) |  | ¬¬IF(ISBLANK('DPW2'!I41),"",'DPW2'!I41) | [7 empty] | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY41),"",'DPW2'!BY41) | PCD_DPW2_RES2_OT |  | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) |  | ¬¬IF(ISBLANK('DPW2'!I41),"",'DPW2'!I41) | [7 empty] | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB41),"",'DPW2'!CB41) | PCD_DPW2_RES2_P |  | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) |  | ¬¬IF(ISBLANK('DPW2'!I41),"",'DPW2'!I41) | [7 empty] | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV42),"",'DPW2'!AV42) | PCD_DPW2_RES3_NP |  | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) |  | ¬¬IF(ISBLANK('DPW2'!I42),"",'DPW2'!I42) | [7 empty] | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX42),"",'DPW2'!AX42) | PCD_DPW2_RES3 |  | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) |  | ¬¬IF(ISBLANK('DPW2'!I42),"",'DPW2'!I42) | [7 empty] | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ42),"",'DPW2'!BJ42) | PCD_DPW2_RES3_T |  | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) |  | ¬¬IF(ISBLANK('DPW2'!I42),"",'DPW2'!I42) | [7 empty] | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM42),"",'DPW2'!BM42) | PCD_DPW2_RES3_O |  | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) |  | ¬¬IF(ISBLANK('DPW2'!I42),"",'DPW2'!I42) | [7 empty] | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY42),"",'DPW2'!BY42) | PCD_DPW2_RES3_OT |  | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) |  | ¬¬IF(ISBLANK('DPW2'!I42),"",'DPW2'!I42) | [7 empty] | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB42),"",'DPW2'!CB42) | PCD_DPW2_RES3_P |  | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) |  | ¬¬IF(ISBLANK('DPW2'!I42),"",'DPW2'!I42) | [7 empty] | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV43),"",'DPW2'!AV43) | PCD_DPW2_RES4_NP |  | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) |  | ¬¬IF(ISBLANK('DPW2'!I43),"",'DPW2'!I43) | [7 empty] | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX43),"",'DPW2'!AX43) | PCD_DPW2_RES4 |  | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) |  | ¬¬IF(ISBLANK('DPW2'!I43),"",'DPW2'!I43) | [7 empty] | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ43),"",'DPW2'!BJ43) | PCD_DPW2_RES4_T |  | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) |  | ¬¬IF(ISBLANK('DPW2'!I43),"",'DPW2'!I43) | [7 empty] | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM43),"",'DPW2'!BM43) | PCD_DPW2_RES4_O |  | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) |  | ¬¬IF(ISBLANK('DPW2'!I43),"",'DPW2'!I43) | [7 empty] | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY43),"",'DPW2'!BY43) | PCD_DPW2_RES4_OT |  | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) |  | ¬¬IF(ISBLANK('DPW2'!I43),"",'DPW2'!I43) | [7 empty] | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB43),"",'DPW2'!CB43) | PCD_DPW2_RES4_P |  | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) |  | ¬¬IF(ISBLANK('DPW2'!I43),"",'DPW2'!I43) | [7 empty] | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV44),"",'DPW2'!AV44) | PCD_DPW2_RES5_NP |  | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) |  | ¬¬IF(ISBLANK('DPW2'!I44),"",'DPW2'!I44) | [7 empty] | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX44),"",'DPW2'!AX44) | PCD_DPW2_RES5 |  | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) |  | ¬¬IF(ISBLANK('DPW2'!I44),"",'DPW2'!I44) | [7 empty] | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ44),"",'DPW2'!BJ44) | PCD_DPW2_RES5_T |  | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) |  | ¬¬IF(ISBLANK('DPW2'!I44),"",'DPW2'!I44) | [7 empty] | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM44),"",'DPW2'!BM44) | PCD_DPW2_RES5_O |  | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) |  | ¬¬IF(ISBLANK('DPW2'!I44),"",'DPW2'!I44) | [7 empty] | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY44),"",'DPW2'!BY44) | PCD_DPW2_RES5_OT |  | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) |  | ¬¬IF(ISBLANK('DPW2'!I44),"",'DPW2'!I44) | [7 empty] | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB44),"",'DPW2'!CB44) | PCD_DPW2_RES5_P |  | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) |  | ¬¬IF(ISBLANK('DPW2'!I44),"",'DPW2'!I44) | [7 empty] | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV45),"",'DPW2'!AV45) | PCD_DPW2_RES5_NP |  | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H45),"",'DPW2'!H45) |  | ¬¬IF(ISBLANK('DPW2'!I45),"",'DPW2'!I45) | [7 empty] | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX45),"",'DPW2'!AX45) | PCD_DPW2_RES5 |  | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H45),"",'DPW2'!H45) |  | ¬¬IF(ISBLANK('DPW2'!I45),"",'DPW2'!I45) | [7 empty] | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ45),"",'DPW2'!BJ45) | PCD_DPW2_RES5_T |  | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H45),"",'DPW2'!H45) |  | ¬¬IF(ISBLANK('DPW2'!I45),"",'DPW2'!I45) | [7 empty] | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM45),"",'DPW2'!BM45) | PCD_DPW2_RES5_O |  | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H45),"",'DPW2'!H45) |  | ¬¬IF(ISBLANK('DPW2'!I45),"",'DPW2'!I45) | [7 empty] | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY45),"",'DPW2'!BY45) | PCD_DPW2_RES5_OT |  | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H45),"",'DPW2'!H45) |  | ¬¬IF(ISBLANK('DPW2'!I45),"",'DPW2'!I45) | [7 empty] | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB45),"",'DPW2'!CB45) | PCD_DPW2_RES5_P |  | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H45),"",'DPW2'!H45) |  | ¬¬IF(ISBLANK('DPW2'!I45),"",'DPW2'!I45) | [7 empty] | ¬¬'DPW2'!F45 & "," & 'DPW2'!G45 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV46),"",'DPW2'!AV46) | PCD_DPW2_RES6_NP |  | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) |  | ¬¬IF(ISBLANK('DPW2'!I46),"",'DPW2'!I46) | [7 empty] | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX46),"",'DPW2'!AX46) | PCD_DPW2_RES6 |  | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) |  | ¬¬IF(ISBLANK('DPW2'!I46),"",'DPW2'!I46) | [7 empty] | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ46),"",'DPW2'!BJ46) | PCD_DPW2_RES6_T |  | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) |  | ¬¬IF(ISBLANK('DPW2'!I46),"",'DPW2'!I46) | [7 empty] | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM46),"",'DPW2'!BM46) | PCD_DPW2_RES6_O |  | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) |  | ¬¬IF(ISBLANK('DPW2'!I46),"",'DPW2'!I46) | [7 empty] | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY46),"",'DPW2'!BY46) | PCD_DPW2_RES6_OT |  | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) |  | ¬¬IF(ISBLANK('DPW2'!I46),"",'DPW2'!I46) | [7 empty] | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB46),"",'DPW2'!CB46) | PCD_DPW2_RES6_P |  | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) |  | ¬¬IF(ISBLANK('DPW2'!I46),"",'DPW2'!I46) | [7 empty] | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV47),"",'DPW2'!AV47) | PCD_DPW2_RES7_NP |  | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) |  | ¬¬IF(ISBLANK('DPW2'!I47),"",'DPW2'!I47) | [7 empty] | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX47),"",'DPW2'!AX47) | PCD_DPW2_RES7 |  | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) |  | ¬¬IF(ISBLANK('DPW2'!I47),"",'DPW2'!I47) | [7 empty] | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ47),"",'DPW2'!BJ47) | PCD_DPW2_RES7_T |  | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) |  | ¬¬IF(ISBLANK('DPW2'!I47),"",'DPW2'!I47) | [7 empty] | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM47),"",'DPW2'!BM47) | PCD_DPW2_RES7_O |  | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) |  | ¬¬IF(ISBLANK('DPW2'!I47),"",'DPW2'!I47) | [7 empty] | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY47),"",'DPW2'!BY47) | PCD_DPW2_RES7_OT |  | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) |  | ¬¬IF(ISBLANK('DPW2'!I47),"",'DPW2'!I47) | [7 empty] | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB47),"",'DPW2'!CB47) | PCD_DPW2_RES7_P |  | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) |  | ¬¬IF(ISBLANK('DPW2'!I47),"",'DPW2'!I47) | [7 empty] | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV48),"",'DPW2'!AV48) | PCD_DPW2_CYBR_NP |  | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) |  | ¬¬IF(ISBLANK('DPW2'!I48),"",'DPW2'!I48) | [7 empty] | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX48),"",'DPW2'!AX48) | PCD_DPW2_CYBR |  | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) |  | ¬¬IF(ISBLANK('DPW2'!I48),"",'DPW2'!I48) | [7 empty] | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ48),"",'DPW2'!BJ48) | PCD_DPW2_CYBR_T |  | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) |  | ¬¬IF(ISBLANK('DPW2'!I48),"",'DPW2'!I48) | [7 empty] | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM48),"",'DPW2'!BM48) | PCD_DPW2_CYBR_O |  | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) |  | ¬¬IF(ISBLANK('DPW2'!I48),"",'DPW2'!I48) | [7 empty] | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY48),"",'DPW2'!BY48) | PCD_DPW2_CYBR_OT |  | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) |  | ¬¬IF(ISBLANK('DPW2'!I48),"",'DPW2'!I48) | [7 empty] | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB48),"",'DPW2'!CB48) | PCD_DPW2_CYBR_P |  | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) |  | ¬¬IF(ISBLANK('DPW2'!I48),"",'DPW2'!I48) | [7 empty] | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV49),"",'DPW2'!AV49) | PCD_DPW2_SEMD_NP |  | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) |  | ¬¬IF(ISBLANK('DPW2'!I49),"",'DPW2'!I49) | [7 empty] | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX49),"",'DPW2'!AX49) | PCD_DPW2_SEMD |  | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) |  | ¬¬IF(ISBLANK('DPW2'!I49),"",'DPW2'!I49) | [7 empty] | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ49),"",'DPW2'!BJ49) | PCD_DPW2_SEMD_T |  | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) |  | ¬¬IF(ISBLANK('DPW2'!I49),"",'DPW2'!I49) | [7 empty] | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM49),"",'DPW2'!BM49) | PCD_DPW2_SEMD_O |  | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) |  | ¬¬IF(ISBLANK('DPW2'!I49),"",'DPW2'!I49) | [7 empty] | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY49),"",'DPW2'!BY49) | PCD_DPW2_SEMD_OT |  | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) |  | ¬¬IF(ISBLANK('DPW2'!I49),"",'DPW2'!I49) | [7 empty] | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB49),"",'DPW2'!CB49) | PCD_DPW2_SEMD_P |  | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) |  | ¬¬IF(ISBLANK('DPW2'!I49),"",'DPW2'!I49) | [7 empty] | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV50),"",'DPW2'!AV50) | PCD_DPW2_TNPCD1_NP |  | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) |  | ¬¬IF(ISBLANK('DPW2'!I50),"",'DPW2'!I50) | [7 empty] | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX50),"",'DPW2'!AX50) | PCD_DPW2_TNPCD1 |  | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) |  | ¬¬IF(ISBLANK('DPW2'!I50),"",'DPW2'!I50) | [7 empty] | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ50),"",'DPW2'!BJ50) | PCD_DPW2_TNPCD1_T |  | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) |  | ¬¬IF(ISBLANK('DPW2'!I50),"",'DPW2'!I50) | [7 empty] | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM50),"",'DPW2'!BM50) | PCD_DPW2_TNPCD1_O |  | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) |  | ¬¬IF(ISBLANK('DPW2'!I50),"",'DPW2'!I50) | [7 empty] | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY50),"",'DPW2'!BY50) | PCD_DPW2_TNPCD1_OT |  | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) |  | ¬¬IF(ISBLANK('DPW2'!I50),"",'DPW2'!I50) | [7 empty] | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB50),"",'DPW2'!CB50) | PCD_DPW2_TNPCD1_P |  | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) |  | ¬¬IF(ISBLANK('DPW2'!I50),"",'DPW2'!I50) | [7 empty] | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV51),"",'DPW2'!AV51) | PCD_DPW2_TNPCD2_NP |  | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H51),"",'DPW2'!H51) |  | ¬¬IF(ISBLANK('DPW2'!I51),"",'DPW2'!I51) | [7 empty] | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX51),"",'DPW2'!AX51) | PCD_DPW2_TNPCD2 |  | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H51),"",'DPW2'!H51) |  | ¬¬IF(ISBLANK('DPW2'!I51),"",'DPW2'!I51) | [7 empty] | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ51),"",'DPW2'!BJ51) | PCD_DPW2_TNPCD2_T |  | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H51),"",'DPW2'!H51) |  | ¬¬IF(ISBLANK('DPW2'!I51),"",'DPW2'!I51) | [7 empty] | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM51),"",'DPW2'!BM51) | PCD_DPW2_TNPCD2_O |  | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H51),"",'DPW2'!H51) |  | ¬¬IF(ISBLANK('DPW2'!I51),"",'DPW2'!I51) | [7 empty] | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY51),"",'DPW2'!BY51) | PCD_DPW2_TNPCD2_OT |  | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H51),"",'DPW2'!H51) |  | ¬¬IF(ISBLANK('DPW2'!I51),"",'DPW2'!I51) | [7 empty] | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB51),"",'DPW2'!CB51) | PCD_DPW2_TNPCD2_P |  | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H51),"",'DPW2'!H51) |  | ¬¬IF(ISBLANK('DPW2'!I51),"",'DPW2'!I51) | [7 empty] | ¬¬'DPW2'!F51 & "," & 'DPW2'!G51 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW2'!AV52),"",'DPW2'!AV52) | PCD_DPW2_TNPCD2_NP |  | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H52),"",'DPW2'!H52) |  | ¬¬IF(ISBLANK('DPW2'!I52),"",'DPW2'!I52) | [7 empty] | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!AX52),"",'DPW2'!AX52) | PCD_DPW2_TNPCD2 |  | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H52),"",'DPW2'!H52) |  | ¬¬IF(ISBLANK('DPW2'!I52),"",'DPW2'!I52) | [7 empty] | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!AV5
¬¬IF(ISBLANK('DPW2'!BJ52),"",'DPW2'!BJ52) | PCD_DPW2_TNPCD2_T |  | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H52),"",'DPW2'!H52) |  | ¬¬IF(ISBLANK('DPW2'!I52),"",'DPW2'!I52) | [7 empty] | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!BJ5
¬¬IF(ISBLANK('DPW2'!BM52),"",'DPW2'!BM52) | PCD_DPW2_TNPCD2_O |  | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H52),"",'DPW2'!H52) |  | ¬¬IF(ISBLANK('DPW2'!I52),"",'DPW2'!I52) | [7 empty] | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!BK5
¬¬IF(ISBLANK('DPW2'!BY52),"",'DPW2'!BY52) | PCD_DPW2_TNPCD2_OT |  | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H52),"",'DPW2'!H52) |  | ¬¬IF(ISBLANK('DPW2'!I52),"",'DPW2'!I52) | [7 empty] | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!BY5
¬¬IF(ISBLANK('DPW2'!CB52),"",'DPW2'!CB52) | PCD_DPW2_TNPCD2_P |  | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H52),"",'DPW2'!H52) |  | ¬¬IF(ISBLANK('DPW2'!I52),"",'DPW2'!I52) | [7 empty] | ¬¬'DPW2'!F52 & "," & 'DPW2'!G52 & "," & 'DPW2'!CB5
¬¬IF(ISBLANK('DPW3'!MT8),"",'DPW3'!MT8) | PCD_DPW3_WFDI1_NR |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV8),"",'DPW3'!MV8) | PCD_DPW3_WFDI1_S0 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK8),"",'DPW3'!OK8) | PCD_DPW3_WFDI1_S1 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ8),"",'DPW3'!PZ8) | PCD_DPW3_WFDI1_S2 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO8),"",'DPW3'!RO8) | PCD_DPW3_WFDI1_S3 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD8),"",'DPW3'!TD8) | PCD_DPW3_WFDI1_S4 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US8),"",'DPW3'!US8) | PCD_DPW3_WFDI1_S5 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH8),"",'DPW3'!WH8) | PCD_DPW3_WFDI1_S6 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW8),"",'DPW3'!XW8) | PCD_DPW3_WFDI1_S7 |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL8),"",'DPW3'!ZL8) | PCD_DPW3_WFDI1_DLY |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM8),"",'DPW3'!ZM8) | PCD_DPW3_WFDI1_DIR |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN8),"",'DPW3'!ZN8) | PCD_DPW3_WFDI1_DER |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO8),"",'DPW3'!ZO8) | PCD_DPW3_WFDI1_DCS |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP8),"",'DPW3'!ZP8) | PCD_DPW3_WFDI1_DSPC |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ8),"",'DPW3'!ZQ8) | PCD_DPW3_WFDI1_DPP |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR8),"",'DPW3'!ZR8) | PCD_DPW3_WFDI1_DTPI |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS8),"",'DPW3'!ZS8) | PCD_DPW3_WFDI1_DCI |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT8),"",'DPW3'!ZT8) | PCD_DPW3_WFDI1_DSI |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV8),"",'DPW3'!ZV8) | PCD_DPW3_WFDI1_DPLE |  | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) |  | ¬¬IF(ISBLANK('DPW3'!I8),"",'DPW3'!I8) | [7 empty] | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT9),"",'DPW3'!MT9) | PCD_DPW3_WFDI1_NR |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV9),"",'DPW3'!MV9) | PCD_DPW3_WFDI1_S0 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK9),"",'DPW3'!OK9) | PCD_DPW3_WFDI1_S1 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ9),"",'DPW3'!PZ9) | PCD_DPW3_WFDI1_S2 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO9),"",'DPW3'!RO9) | PCD_DPW3_WFDI1_S3 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD9),"",'DPW3'!TD9) | PCD_DPW3_WFDI1_S4 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US9),"",'DPW3'!US9) | PCD_DPW3_WFDI1_S5 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH9),"",'DPW3'!WH9) | PCD_DPW3_WFDI1_S6 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW9),"",'DPW3'!XW9) | PCD_DPW3_WFDI1_S7 |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL9),"",'DPW3'!ZL9) | PCD_DPW3_WFDI1_DLY |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM9),"",'DPW3'!ZM9) | PCD_DPW3_WFDI1_DIR |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN9),"",'DPW3'!ZN9) | PCD_DPW3_WFDI1_DER |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO9),"",'DPW3'!ZO9) | PCD_DPW3_WFDI1_DCS |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP9),"",'DPW3'!ZP9) | PCD_DPW3_WFDI1_DSPC |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ9),"",'DPW3'!ZQ9) | PCD_DPW3_WFDI1_DPP |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR9),"",'DPW3'!ZR9) | PCD_DPW3_WFDI1_DTPI |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS9),"",'DPW3'!ZS9) | PCD_DPW3_WFDI1_DCI |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT9),"",'DPW3'!ZT9) | PCD_DPW3_WFDI1_DSI |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV9),"",'DPW3'!ZV9) | PCD_DPW3_WFDI1_DPLE |  | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) |  | ¬¬IF(ISBLANK('DPW3'!I9),"",'DPW3'!I9) | [7 empty] | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT10),"",'DPW3'!MT10) | PCD_DPW3_WFDI1_NR |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV10),"",'DPW3'!MV10) | PCD_DPW3_WFDI1_S0 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK10),"",'DPW3'!OK10) | PCD_DPW3_WFDI1_S1 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ10),"",'DPW3'!PZ10) | PCD_DPW3_WFDI1_S2 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO10),"",'DPW3'!RO10) | PCD_DPW3_WFDI1_S3 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD10),"",'DPW3'!TD10) | PCD_DPW3_WFDI1_S4 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US10),"",'DPW3'!US10) | PCD_DPW3_WFDI1_S5 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH10),"",'DPW3'!WH10) | PCD_DPW3_WFDI1_S6 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW10),"",'DPW3'!XW10) | PCD_DPW3_WFDI1_S7 |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL10),"",'DPW3'!ZL10) | PCD_DPW3_WFDI1_DLY |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM10),"",'DPW3'!ZM10) | PCD_DPW3_WFDI1_DIR |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN10),"",'DPW3'!ZN10) | PCD_DPW3_WFDI1_DER |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO10),"",'DPW3'!ZO10) | PCD_DPW3_WFDI1_DCS |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP10),"",'DPW3'!ZP10) | PCD_DPW3_WFDI1_DSPC |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ10),"",'DPW3'!ZQ10) | PCD_DPW3_WFDI1_DPP |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR10),"",'DPW3'!ZR10) | PCD_DPW3_WFDI1_DTPI |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS10),"",'DPW3'!ZS10) | PCD_DPW3_WFDI1_DCI |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT10),"",'DPW3'!ZT10) | PCD_DPW3_WFDI1_DSI |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV10),"",'DPW3'!ZV10) | PCD_DPW3_WFDI1_DPLE |  | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) |  | ¬¬IF(ISBLANK('DPW3'!I10),"",'DPW3'!I10) | [7 empty] | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT11),"",'DPW3'!MT11) | PCD_DPW3_WFDI1_NR |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV11),"",'DPW3'!MV11) | PCD_DPW3_WFDI1_S0 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK11),"",'DPW3'!OK11) | PCD_DPW3_WFDI1_S1 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ11),"",'DPW3'!PZ11) | PCD_DPW3_WFDI1_S2 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO11),"",'DPW3'!RO11) | PCD_DPW3_WFDI1_S3 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD11),"",'DPW3'!TD11) | PCD_DPW3_WFDI1_S4 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US11),"",'DPW3'!US11) | PCD_DPW3_WFDI1_S5 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH11),"",'DPW3'!WH11) | PCD_DPW3_WFDI1_S6 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW11),"",'DPW3'!XW11) | PCD_DPW3_WFDI1_S7 |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL11),"",'DPW3'!ZL11) | PCD_DPW3_WFDI1_DLY |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM11),"",'DPW3'!ZM11) | PCD_DPW3_WFDI1_DIR |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN11),"",'DPW3'!ZN11) | PCD_DPW3_WFDI1_DER |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO11),"",'DPW3'!ZO11) | PCD_DPW3_WFDI1_DCS |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP11),"",'DPW3'!ZP11) | PCD_DPW3_WFDI1_DSPC |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ11),"",'DPW3'!ZQ11) | PCD_DPW3_WFDI1_DPP |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR11),"",'DPW3'!ZR11) | PCD_DPW3_WFDI1_DTPI |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS11),"",'DPW3'!ZS11) | PCD_DPW3_WFDI1_DCI |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT11),"",'DPW3'!ZT11) | PCD_DPW3_WFDI1_DSI |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV11),"",'DPW3'!ZV11) | PCD_DPW3_WFDI1_DPLE |  | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) |  | ¬¬IF(ISBLANK('DPW3'!I11),"",'DPW3'!I11) | [7 empty] | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT12),"",'DPW3'!MT12) | PCD_DPW3_WFDI1_NR |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV12),"",'DPW3'!MV12) | PCD_DPW3_WFDI1_S0 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK12),"",'DPW3'!OK12) | PCD_DPW3_WFDI1_S1 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ12),"",'DPW3'!PZ12) | PCD_DPW3_WFDI1_S2 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO12),"",'DPW3'!RO12) | PCD_DPW3_WFDI1_S3 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD12),"",'DPW3'!TD12) | PCD_DPW3_WFDI1_S4 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US12),"",'DPW3'!US12) | PCD_DPW3_WFDI1_S5 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH12),"",'DPW3'!WH12) | PCD_DPW3_WFDI1_S6 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW12),"",'DPW3'!XW12) | PCD_DPW3_WFDI1_S7 |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL12),"",'DPW3'!ZL12) | PCD_DPW3_WFDI1_DLY |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM12),"",'DPW3'!ZM12) | PCD_DPW3_WFDI1_DIR |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN12),"",'DPW3'!ZN12) | PCD_DPW3_WFDI1_DER |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO12),"",'DPW3'!ZO12) | PCD_DPW3_WFDI1_DCS |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP12),"",'DPW3'!ZP12) | PCD_DPW3_WFDI1_DSPC |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ12),"",'DPW3'!ZQ12) | PCD_DPW3_WFDI1_DPP |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR12),"",'DPW3'!ZR12) | PCD_DPW3_WFDI1_DTPI |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS12),"",'DPW3'!ZS12) | PCD_DPW3_WFDI1_DCI |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT12),"",'DPW3'!ZT12) | PCD_DPW3_WFDI1_DSI |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV12),"",'DPW3'!ZV12) | PCD_DPW3_WFDI1_DPLE |  | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) |  | ¬¬IF(ISBLANK('DPW3'!I12),"",'DPW3'!I12) | [7 empty] | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT13),"",'DPW3'!MT13) | PCD_DPW3_WFDI1_NR |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV13),"",'DPW3'!MV13) | PCD_DPW3_WFDI1_S0 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK13),"",'DPW3'!OK13) | PCD_DPW3_WFDI1_S1 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ13),"",'DPW3'!PZ13) | PCD_DPW3_WFDI1_S2 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO13),"",'DPW3'!RO13) | PCD_DPW3_WFDI1_S3 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD13),"",'DPW3'!TD13) | PCD_DPW3_WFDI1_S4 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US13),"",'DPW3'!US13) | PCD_DPW3_WFDI1_S5 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH13),"",'DPW3'!WH13) | PCD_DPW3_WFDI1_S6 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW13),"",'DPW3'!XW13) | PCD_DPW3_WFDI1_S7 |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL13),"",'DPW3'!ZL13) | PCD_DPW3_WFDI1_DLY |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM13),"",'DPW3'!ZM13) | PCD_DPW3_WFDI1_DIR |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN13),"",'DPW3'!ZN13) | PCD_DPW3_WFDI1_DER |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO13),"",'DPW3'!ZO13) | PCD_DPW3_WFDI1_DCS |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP13),"",'DPW3'!ZP13) | PCD_DPW3_WFDI1_DSPC |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ13),"",'DPW3'!ZQ13) | PCD_DPW3_WFDI1_DPP |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR13),"",'DPW3'!ZR13) | PCD_DPW3_WFDI1_DTPI |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS13),"",'DPW3'!ZS13) | PCD_DPW3_WFDI1_DCI |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT13),"",'DPW3'!ZT13) | PCD_DPW3_WFDI1_DSI |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV13),"",'DPW3'!ZV13) | PCD_DPW3_WFDI1_DPLE |  | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) |  | ¬¬IF(ISBLANK('DPW3'!I13),"",'DPW3'!I13) | [7 empty] | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT14),"",'DPW3'!MT14) | PCD_DPW3_RWD_NR |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV14),"",'DPW3'!MV14) | PCD_DPW3_RWD_S0 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK14),"",'DPW3'!OK14) | PCD_DPW3_RWD_S1 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ14),"",'DPW3'!PZ14) | PCD_DPW3_RWD_S2 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO14),"",'DPW3'!RO14) | PCD_DPW3_RWD_S3 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD14),"",'DPW3'!TD14) | PCD_DPW3_RWD_S4 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US14),"",'DPW3'!US14) | PCD_DPW3_RWD_S5 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH14),"",'DPW3'!WH14) | PCD_DPW3_RWD_S6 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW14),"",'DPW3'!XW14) | PCD_DPW3_RWD_S7 |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL14),"",'DPW3'!ZL14) | PCD_DPW3_RWD_DLY |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM14),"",'DPW3'!ZM14) | PCD_DPW3_RWD_DIR |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN14),"",'DPW3'!ZN14) | PCD_DPW3_RWD_DER |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO14),"",'DPW3'!ZO14) | PCD_DPW3_RWD_DCS |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP14),"",'DPW3'!ZP14) | PCD_DPW3_RWD_DSPC |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ14),"",'DPW3'!ZQ14) | PCD_DPW3_RWD_DPP |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR14),"",'DPW3'!ZR14) | PCD_DPW3_RWD_DTPI |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS14),"",'DPW3'!ZS14) | PCD_DPW3_RWD_DCI |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT14),"",'DPW3'!ZT14) | PCD_DPW3_RWD_DSI |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV14),"",'DPW3'!ZV14) | PCD_DPW3_RWD_DPLE |  | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) |  | ¬¬IF(ISBLANK('DPW3'!I14),"",'DPW3'!I14) | [7 empty] | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT15),"",'DPW3'!MT15) | PCD_DPW3_RWD_NR |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV15),"",'DPW3'!MV15) | PCD_DPW3_RWD_S0 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK15),"",'DPW3'!OK15) | PCD_DPW3_RWD_S1 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ15),"",'DPW3'!PZ15) | PCD_DPW3_RWD_S2 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO15),"",'DPW3'!RO15) | PCD_DPW3_RWD_S3 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD15),"",'DPW3'!TD15) | PCD_DPW3_RWD_S4 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US15),"",'DPW3'!US15) | PCD_DPW3_RWD_S5 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH15),"",'DPW3'!WH15) | PCD_DPW3_RWD_S6 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW15),"",'DPW3'!XW15) | PCD_DPW3_RWD_S7 |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL15),"",'DPW3'!ZL15) | PCD_DPW3_RWD_DLY |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM15),"",'DPW3'!ZM15) | PCD_DPW3_RWD_DIR |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN15),"",'DPW3'!ZN15) | PCD_DPW3_RWD_DER |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO15),"",'DPW3'!ZO15) | PCD_DPW3_RWD_DCS |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP15),"",'DPW3'!ZP15) | PCD_DPW3_RWD_DSPC |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ15),"",'DPW3'!ZQ15) | PCD_DPW3_RWD_DPP |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR15),"",'DPW3'!ZR15) | PCD_DPW3_RWD_DTPI |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS15),"",'DPW3'!ZS15) | PCD_DPW3_RWD_DCI |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT15),"",'DPW3'!ZT15) | PCD_DPW3_RWD_DSI |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV15),"",'DPW3'!ZV15) | PCD_DPW3_RWD_DPLE |  | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) |  | ¬¬IF(ISBLANK('DPW3'!I15),"",'DPW3'!I15) | [7 empty] | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT16),"",'DPW3'!MT16) | PCD_DPW3_RWD_NR |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV16),"",'DPW3'!MV16) | PCD_DPW3_RWD_S0 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK16),"",'DPW3'!OK16) | PCD_DPW3_RWD_S1 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ16),"",'DPW3'!PZ16) | PCD_DPW3_RWD_S2 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO16),"",'DPW3'!RO16) | PCD_DPW3_RWD_S3 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD16),"",'DPW3'!TD16) | PCD_DPW3_RWD_S4 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US16),"",'DPW3'!US16) | PCD_DPW3_RWD_S5 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH16),"",'DPW3'!WH16) | PCD_DPW3_RWD_S6 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW16),"",'DPW3'!XW16) | PCD_DPW3_RWD_S7 |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL16),"",'DPW3'!ZL16) | PCD_DPW3_RWD_DLY |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM16),"",'DPW3'!ZM16) | PCD_DPW3_RWD_DIR |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN16),"",'DPW3'!ZN16) | PCD_DPW3_RWD_DER |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO16),"",'DPW3'!ZO16) | PCD_DPW3_RWD_DCS |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP16),"",'DPW3'!ZP16) | PCD_DPW3_RWD_DSPC |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ16),"",'DPW3'!ZQ16) | PCD_DPW3_RWD_DPP |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR16),"",'DPW3'!ZR16) | PCD_DPW3_RWD_DTPI |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS16),"",'DPW3'!ZS16) | PCD_DPW3_RWD_DCI |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT16),"",'DPW3'!ZT16) | PCD_DPW3_RWD_DSI |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV16),"",'DPW3'!ZV16) | PCD_DPW3_RWD_DPLE |  | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) |  | ¬¬IF(ISBLANK('DPW3'!I16),"",'DPW3'!I16) | [7 empty] | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT17),"",'DPW3'!MT17) | PCD_DPW3_RWD_NR |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV17),"",'DPW3'!MV17) | PCD_DPW3_RWD_S0 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK17),"",'DPW3'!OK17) | PCD_DPW3_RWD_S1 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ17),"",'DPW3'!PZ17) | PCD_DPW3_RWD_S2 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO17),"",'DPW3'!RO17) | PCD_DPW3_RWD_S3 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD17),"",'DPW3'!TD17) | PCD_DPW3_RWD_S4 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US17),"",'DPW3'!US17) | PCD_DPW3_RWD_S5 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH17),"",'DPW3'!WH17) | PCD_DPW3_RWD_S6 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW17),"",'DPW3'!XW17) | PCD_DPW3_RWD_S7 |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL17),"",'DPW3'!ZL17) | PCD_DPW3_RWD_DLY |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM17),"",'DPW3'!ZM17) | PCD_DPW3_RWD_DIR |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN17),"",'DPW3'!ZN17) | PCD_DPW3_RWD_DER |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO17),"",'DPW3'!ZO17) | PCD_DPW3_RWD_DCS |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP17),"",'DPW3'!ZP17) | PCD_DPW3_RWD_DSPC |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ17),"",'DPW3'!ZQ17) | PCD_DPW3_RWD_DPP |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR17),"",'DPW3'!ZR17) | PCD_DPW3_RWD_DTPI |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS17),"",'DPW3'!ZS17) | PCD_DPW3_RWD_DCI |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT17),"",'DPW3'!ZT17) | PCD_DPW3_RWD_DSI |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV17),"",'DPW3'!ZV17) | PCD_DPW3_RWD_DPLE |  | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) |  | ¬¬IF(ISBLANK('DPW3'!I17),"",'DPW3'!I17) | [7 empty] | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT18),"",'DPW3'!MT18) | PCD_DPW3_RWD_NR |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV18),"",'DPW3'!MV18) | PCD_DPW3_RWD_S0 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK18),"",'DPW3'!OK18) | PCD_DPW3_RWD_S1 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ18),"",'DPW3'!PZ18) | PCD_DPW3_RWD_S2 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO18),"",'DPW3'!RO18) | PCD_DPW3_RWD_S3 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD18),"",'DPW3'!TD18) | PCD_DPW3_RWD_S4 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US18),"",'DPW3'!US18) | PCD_DPW3_RWD_S5 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH18),"",'DPW3'!WH18) | PCD_DPW3_RWD_S6 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW18),"",'DPW3'!XW18) | PCD_DPW3_RWD_S7 |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL18),"",'DPW3'!ZL18) | PCD_DPW3_RWD_DLY |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM18),"",'DPW3'!ZM18) | PCD_DPW3_RWD_DIR |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN18),"",'DPW3'!ZN18) | PCD_DPW3_RWD_DER |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO18),"",'DPW3'!ZO18) | PCD_DPW3_RWD_DCS |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP18),"",'DPW3'!ZP18) | PCD_DPW3_RWD_DSPC |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ18),"",'DPW3'!ZQ18) | PCD_DPW3_RWD_DPP |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR18),"",'DPW3'!ZR18) | PCD_DPW3_RWD_DTPI |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS18),"",'DPW3'!ZS18) | PCD_DPW3_RWD_DCI |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT18),"",'DPW3'!ZT18) | PCD_DPW3_RWD_DSI |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV18),"",'DPW3'!ZV18) | PCD_DPW3_RWD_DPLE |  | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) |  | ¬¬IF(ISBLANK('DPW3'!I18),"",'DPW3'!I18) | [7 empty] | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT19),"",'DPW3'!MT19) | PCD_DPW3_RWD_NR |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV19),"",'DPW3'!MV19) | PCD_DPW3_RWD_S0 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK19),"",'DPW3'!OK19) | PCD_DPW3_RWD_S1 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ19),"",'DPW3'!PZ19) | PCD_DPW3_RWD_S2 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO19),"",'DPW3'!RO19) | PCD_DPW3_RWD_S3 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD19),"",'DPW3'!TD19) | PCD_DPW3_RWD_S4 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US19),"",'DPW3'!US19) | PCD_DPW3_RWD_S5 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH19),"",'DPW3'!WH19) | PCD_DPW3_RWD_S6 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW19),"",'DPW3'!XW19) | PCD_DPW3_RWD_S7 |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL19),"",'DPW3'!ZL19) | PCD_DPW3_RWD_DLY |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM19),"",'DPW3'!ZM19) | PCD_DPW3_RWD_DIR |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN19),"",'DPW3'!ZN19) | PCD_DPW3_RWD_DER |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO19),"",'DPW3'!ZO19) | PCD_DPW3_RWD_DCS |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP19),"",'DPW3'!ZP19) | PCD_DPW3_RWD_DSPC |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ19),"",'DPW3'!ZQ19) | PCD_DPW3_RWD_DPP |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR19),"",'DPW3'!ZR19) | PCD_DPW3_RWD_DTPI |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS19),"",'DPW3'!ZS19) | PCD_DPW3_RWD_DCI |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT19),"",'DPW3'!ZT19) | PCD_DPW3_RWD_DSI |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV19),"",'DPW3'!ZV19) | PCD_DPW3_RWD_DPLE |  | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H19),"",'DPW3'!H19) |  | ¬¬IF(ISBLANK('DPW3'!I19),"",'DPW3'!I19) | [7 empty] | ¬¬'DPW3'!F19 & "," & 'DPW3'!G19 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT20),"",'DPW3'!MT20) | PCD_DPW3_WRESUP_NR |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV20),"",'DPW3'!MV20) | PCD_DPW3_WRESUP_S0 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK20),"",'DPW3'!OK20) | PCD_DPW3_WRESUP_S1 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ20),"",'DPW3'!PZ20) | PCD_DPW3_WRESUP_S2 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO20),"",'DPW3'!RO20) | PCD_DPW3_WRESUP_S3 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD20),"",'DPW3'!TD20) | PCD_DPW3_WRESUP_S4 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US20),"",'DPW3'!US20) | PCD_DPW3_WRESUP_S5 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH20),"",'DPW3'!WH20) | PCD_DPW3_WRESUP_S6 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW20),"",'DPW3'!XW20) | PCD_DPW3_WRESUP_S7 |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL20),"",'DPW3'!ZL20) | PCD_DPW3_WRESUP_DLY |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM20),"",'DPW3'!ZM20) | PCD_DPW3_WRESUP_DIR |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN20),"",'DPW3'!ZN20) | PCD_DPW3_WRESUP_DER |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO20),"",'DPW3'!ZO20) | PCD_DPW3_WRESUP_DCS |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP20),"",'DPW3'!ZP20) | PCD_DPW3_WRESUP_DSPC |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ20),"",'DPW3'!ZQ20) | PCD_DPW3_WRESUP_DPP |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR20),"",'DPW3'!ZR20) | PCD_DPW3_WRESUP_DTPI |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS20),"",'DPW3'!ZS20) | PCD_DPW3_WRESUP_DCI |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT20),"",'DPW3'!ZT20) | PCD_DPW3_WRESUP_DSI |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV20),"",'DPW3'!ZV20) | PCD_DPW3_WRESUP_DPLE |  | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) |  | ¬¬IF(ISBLANK('DPW3'!I20),"",'DPW3'!I20) | [7 empty] | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT21),"",'DPW3'!MT21) | PCD_DPW3_SPL5_NR |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV21),"",'DPW3'!MV21) | PCD_DPW3_SPL5_S0 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK21),"",'DPW3'!OK21) | PCD_DPW3_SPL5_S1 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ21),"",'DPW3'!PZ21) | PCD_DPW3_SPL5_S2 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO21),"",'DPW3'!RO21) | PCD_DPW3_SPL5_S3 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD21),"",'DPW3'!TD21) | PCD_DPW3_SPL5_S4 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US21),"",'DPW3'!US21) | PCD_DPW3_SPL5_S5 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH21),"",'DPW3'!WH21) | PCD_DPW3_SPL5_S6 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW21),"",'DPW3'!XW21) | PCD_DPW3_SPL5_S7 |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL21),"",'DPW3'!ZL21) | PCD_DPW3_SPL5_DLY |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM21),"",'DPW3'!ZM21) | PCD_DPW3_SPL5_DIR |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN21),"",'DPW3'!ZN21) | PCD_DPW3_SPL5_DER |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO21),"",'DPW3'!ZO21) | PCD_DPW3_SPL5_DCS |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP21),"",'DPW3'!ZP21) | PCD_DPW3_SPL5_DSPC |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ21),"",'DPW3'!ZQ21) | PCD_DPW3_SPL5_DPP |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR21),"",'DPW3'!ZR21) | PCD_DPW3_SPL5_DTPI |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS21),"",'DPW3'!ZS21) | PCD_DPW3_SPL5_DCI |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT21),"",'DPW3'!ZT21) | PCD_DPW3_SPL5_DSI |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV21),"",'DPW3'!ZV21) | PCD_DPW3_SPL5_DPLE |  | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) |  | ¬¬IF(ISBLANK('DPW3'!I21),"",'DPW3'!I21) | [7 empty] | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT22),"",'DPW3'!MT22) | PCD_DPW3_SPLIN1_NR |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV22),"",'DPW3'!MV22) | PCD_DPW3_SPLIN1_S0 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK22),"",'DPW3'!OK22) | PCD_DPW3_SPLIN1_S1 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ22),"",'DPW3'!PZ22) | PCD_DPW3_SPLIN1_S2 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO22),"",'DPW3'!RO22) | PCD_DPW3_SPLIN1_S3 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD22),"",'DPW3'!TD22) | PCD_DPW3_SPLIN1_S4 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US22),"",'DPW3'!US22) | PCD_DPW3_SPLIN1_S5 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH22),"",'DPW3'!WH22) | PCD_DPW3_SPLIN1_S6 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW22),"",'DPW3'!XW22) | PCD_DPW3_SPLIN1_S7 |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL22),"",'DPW3'!ZL22) | PCD_DPW3_SPLIN1_DLY |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM22),"",'DPW3'!ZM22) | PCD_DPW3_SPLIN1_DIR |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN22),"",'DPW3'!ZN22) | PCD_DPW3_SPLIN1_DER |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO22),"",'DPW3'!ZO22) | PCD_DPW3_SPLIN1_DCS |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP22),"",'DPW3'!ZP22) | PCD_DPW3_SPLIN1_DSPC |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ22),"",'DPW3'!ZQ22) | PCD_DPW3_SPLIN1_DPP |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR22),"",'DPW3'!ZR22) | PCD_DPW3_SPLIN1_DTPI |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS22),"",'DPW3'!ZS22) | PCD_DPW3_SPLIN1_DCI |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT22),"",'DPW3'!ZT22) | PCD_DPW3_SPLIN1_DSI |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV22),"",'DPW3'!ZV22) | PCD_DPW3_SPLIN1_DPLE |  | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) |  | ¬¬IF(ISBLANK('DPW3'!I22),"",'DPW3'!I22) | [7 empty] | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZV5
¬¬IF(ISBLANK('DPW3'!MT23),"",'DPW3'!MT23) | PCD_DPW3_SPLIN1_NR |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!MT5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!MT5
¬¬IF(ISBLANK('DPW3'!MV23),"",'DPW3'!MV23) | PCD_DPW3_SPLIN1_S0 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!MV5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!MV5
¬¬IF(ISBLANK('DPW3'!OK23),"",'DPW3'!OK23) | PCD_DPW3_SPLIN1_S1 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!OK5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!OK5
¬¬IF(ISBLANK('DPW3'!PZ23),"",'DPW3'!PZ23) | PCD_DPW3_SPLIN1_S2 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!PZ5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!PZ5
¬¬IF(ISBLANK('DPW3'!RO23),"",'DPW3'!RO23) | PCD_DPW3_SPLIN1_S3 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!RO5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!RO5
¬¬IF(ISBLANK('DPW3'!TD23),"",'DPW3'!TD23) | PCD_DPW3_SPLIN1_S4 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!TD5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!TD5
¬¬IF(ISBLANK('DPW3'!US23),"",'DPW3'!US23) | PCD_DPW3_SPLIN1_S5 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!US5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!US5
¬¬IF(ISBLANK('DPW3'!WH23),"",'DPW3'!WH23) | PCD_DPW3_SPLIN1_S6 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!WH5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!WH5
¬¬IF(ISBLANK('DPW3'!XW23),"",'DPW3'!XW23) | PCD_DPW3_SPLIN1_S7 |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!XW5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!XW5
¬¬IF(ISBLANK('DPW3'!ZL23),"",'DPW3'!ZL23) | PCD_DPW3_SPLIN1_DLY |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZL5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZL5
¬¬IF(ISBLANK('DPW3'!ZM23),"",'DPW3'!ZM23) | PCD_DPW3_SPLIN1_DIR |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZM5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZM5
¬¬IF(ISBLANK('DPW3'!ZN23),"",'DPW3'!ZN23) | PCD_DPW3_SPLIN1_DER |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZN5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZN5
¬¬IF(ISBLANK('DPW3'!ZO23),"",'DPW3'!ZO23) | PCD_DPW3_SPLIN1_DCS |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZO5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZO5
¬¬IF(ISBLANK('DPW3'!ZP23),"",'DPW3'!ZP23) | PCD_DPW3_SPLIN1_DSPC |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZP5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZP5
¬¬IF(ISBLANK('DPW3'!ZQ23),"",'DPW3'!ZQ23) | PCD_DPW3_SPLIN1_DPP |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZQ5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZQ5
¬¬IF(ISBLANK('DPW3'!ZR23),"",'DPW3'!ZR23) | PCD_DPW3_SPLIN1_DTPI |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZR5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZR5
¬¬IF(ISBLANK('DPW3'!ZS23),"",'DPW3'!ZS23) | PCD_DPW3_SPLIN1_DCI |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZS5
¬¬IF(ISBLANK('DPW3'!ZT23),"",'DPW3'!ZT23) | PCD_DPW3_SPLIN1_DSI |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZT5
¬¬IF(ISBLANK('DPW3'!ZV23),"",'DPW3'!ZV23) | PCD_DPW3_SPLIN1_DPLE |  | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) |  | ¬¬IF(ISBLANK('DPW3'!I23),"",'DPW3'!I23) | [7 empty] | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZV5

## F_Outputs OLD (hidden)
PCD Data
Acronym | Reference | Item description | Unit | Model | Constant | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2025-30 | 2024-25 Q4 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | 2030-31 Q1 | 2030-31 Q2 | 2030-31 Q3 | 2030-31 Q4 | 2031-32 Q1 | 2031-32 Q2 | 2031-32 Q3 | 2031-32 Q4 | 2032-33 Q1 | 2032-33 Q2 | 2032-33 Q3 | 2032-33 Q4 | 2033-34 Q1 | 2033-34 Q2 | 2033-34 Q3 | 2033-34 Q4 | 2034-35 Q1 | 2034-35 Q2 | 2034-35 Q3 | 2034-35 Q4
¬¬rngAcronym | ¬¬IF(ISBLANK('DPB1'!AT8),"",'DPB1'!AT8) | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!AP5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB1'!J8),"",'DPB1'!J8) | ¬¬IF(ISBLANK('DPB1'!K8),"",'DPB1'!K8) | ¬¬IF(ISBLANK('DPB1'!L8),"",'DPB1'!L8) | ¬¬IF(ISBLANK('DPB1'!M8),"",'DPB1'!M8) | ¬¬IF(ISBLANK('DPB1'!N8),"",'DPB1'!N8) | ¬¬IF(ISBLANK('DPB1'!O8),"",'DPB1'!O8) | ¬¬IF(ISBLANK('DPB1'!P8),"",'DPB1'!P8) | ¬¬IF(ISBLANK('DPB1'!Q8),"",'DPB1'!Q8) | ¬¬IF(ISBLANK('DPB1'!R8),"",'DPB1'!R8) | ¬¬IF(ISBLANK('DPB1'!S8),"",'DPB1'!S8)
¬¬A4 | ¬¬IF(ISBLANK('DPB1'!BD8),"",'DPB1'!BD8) | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BD5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!T8),"",'DPB1'!T8) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!U8),"",'DPB1'!U8)
¬¬A5 | ¬¬IF(ISBLANK('DPB1'!BH8),"",'DPB1'!BH8) | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BE5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB1'!X8),"",'DPB1'!X8) | ¬¬IF(ISBLANK('DPB1'!Y8),"",'DPB1'!Y8) | ¬¬IF(ISBLANK('DPB1'!Z8),"",'DPB1'!Z8) | ¬¬IF(ISBLANK('DPB1'!AA8),"",'DPB1'!AA8) | ¬¬IF(ISBLANK('DPB1'!AB8),"",'DPB1'!AB8) | ¬¬IF(ISBLANK('DPB1'!AC8),"",'DPB1'!AC8) | ¬¬IF(ISBLANK('DPB1'!AD8),"",'DPB1'!AD8) | ¬¬IF(ISBLANK('DPB1'!AE8),"",'DPB1'!AE8) | ¬¬IF(ISBLANK('DPB1'!AF8),"",'DPB1'!AF8) | ¬¬IF(ISBLANK('DPB1'!AG8),"",'DPB1'!AG8)
¬¬A6 | ¬¬IF(ISBLANK('DPB1'!BR8),"",'DPB1'!BR8) | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BR5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!AH8),"",'DPB1'!AH8) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!AI8),"",'DPB1'!AI8)
¬¬A7 | ¬¬IF(ISBLANK('DPB1'!BU8),"",'DPB1'!BU8) | ¬¬'DPB1'!E8 & "," & 'DPB1'!F8 & "," & 'DPB1'!BU5 | ¬¬IF(ISBLANK('DPB1'!G8),"",'DPB1'!G8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!AK8),"",'DPB1'!AK8) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!AL8),"",'DPB1'!AL8)
¬¬A8 | ¬¬IF(ISBLANK('DPB1'!AT9),"",'DPB1'!AT9) | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!AP5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB1'!J9),"",'DPB1'!J9) | ¬¬IF(ISBLANK('DPB1'!K9),"",'DPB1'!K9) | ¬¬IF(ISBLANK('DPB1'!L9),"",'DPB1'!L9) | ¬¬IF(ISBLANK('DPB1'!M9),"",'DPB1'!M9) | ¬¬IF(ISBLANK('DPB1'!N9),"",'DPB1'!N9) | ¬¬IF(ISBLANK('DPB1'!O9),"",'DPB1'!O9) | ¬¬IF(ISBLANK('DPB1'!P9),"",'DPB1'!P9) | ¬¬IF(ISBLANK('DPB1'!Q9),"",'DPB1'!Q9) | ¬¬IF(ISBLANK('DPB1'!R9),"",'DPB1'!R9) | ¬¬IF(ISBLANK('DPB1'!S9),"",'DPB1'!S9)
¬¬A9 | ¬¬IF(ISBLANK('DPB1'!BD9),"",'DPB1'!BD9) | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BD5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!T9),"",'DPB1'!T9) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!U9),"",'DPB1'!U9)
¬¬A10 | ¬¬IF(ISBLANK('DPB1'!BH9),"",'DPB1'!BH9) | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BE5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB1'!X9),"",'DPB1'!X9) | ¬¬IF(ISBLANK('DPB1'!Y9),"",'DPB1'!Y9) | ¬¬IF(ISBLANK('DPB1'!Z9),"",'DPB1'!Z9) | ¬¬IF(ISBLANK('DPB1'!AA9),"",'DPB1'!AA9) | ¬¬IF(ISBLANK('DPB1'!AB9),"",'DPB1'!AB9) | ¬¬IF(ISBLANK('DPB1'!AC9),"",'DPB1'!AC9) | ¬¬IF(ISBLANK('DPB1'!AD9),"",'DPB1'!AD9) | ¬¬IF(ISBLANK('DPB1'!AE9),"",'DPB1'!AE9) | ¬¬IF(ISBLANK('DPB1'!AF9),"",'DPB1'!AF9) | ¬¬IF(ISBLANK('DPB1'!AG9),"",'DPB1'!AG9)
¬¬A11 | ¬¬IF(ISBLANK('DPB1'!BR9),"",'DPB1'!BR9) | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BR5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!AH9),"",'DPB1'!AH9) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!AI9),"",'DPB1'!AI9)
¬¬A12 | ¬¬IF(ISBLANK('DPB1'!BU9),"",'DPB1'!BU9) | ¬¬'DPB1'!E9 & "," & 'DPB1'!F9 & "," & 'DPB1'!BU5 | ¬¬IF(ISBLANK('DPB1'!G9),"",'DPB1'!G9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!AK9),"",'DPB1'!AK9) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!AL9),"",'DPB1'!AL9)
¬¬A13 | ¬¬IF(ISBLANK('DPB1'!AT10),"",'DPB1'!AT10) | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!AP5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB1'!J10),"",'DPB1'!J10) | ¬¬IF(ISBLANK('DPB1'!K10),"",'DPB1'!K10) | ¬¬IF(ISBLANK('DPB1'!L10),"",'DPB1'!L10) | ¬¬IF(ISBLANK('DPB1'!M10),"",'DPB1'!M10) | ¬¬IF(ISBLANK('DPB1'!N10),"",'DPB1'!N10) | ¬¬IF(ISBLANK('DPB1'!O10),"",'DPB1'!O10) | ¬¬IF(ISBLANK('DPB1'!P10),"",'DPB1'!P10) | ¬¬IF(ISBLANK('DPB1'!Q10),"",'DPB1'!Q10) | ¬¬IF(ISBLANK('DPB1'!R10),"",'DPB1'!R10) | ¬¬IF(ISBLANK('DPB1'!S10),"",'DPB1'!S10)
¬¬A14 | ¬¬IF(ISBLANK('DPB1'!BD10),"",'DPB1'!BD10) | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BD5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!T10),"",'DPB1'!T10) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!U10),"",'DPB1'!U10)
¬¬A15 | ¬¬IF(ISBLANK('DPB1'!BH10),"",'DPB1'!BH10) | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BE5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB1'!X10),"",'DPB1'!X10) | ¬¬IF(ISBLANK('DPB1'!Y10),"",'DPB1'!Y10) | ¬¬IF(ISBLANK('DPB1'!Z10),"",'DPB1'!Z10) | ¬¬IF(ISBLANK('DPB1'!AA10),"",'DPB1'!AA10) | ¬¬IF(ISBLANK('DPB1'!AB10),"",'DPB1'!AB10) | ¬¬IF(ISBLANK('DPB1'!AC10),"",'DPB1'!AC10) | ¬¬IF(ISBLANK('DPB1'!AD10),"",'DPB1'!AD10) | ¬¬IF(ISBLANK('DPB1'!AE10),"",'DPB1'!AE10) | ¬¬IF(ISBLANK('DPB1'!AF10),"",'DPB1'!AF10) | ¬¬IF(ISBLANK('DPB1'!AG10),"",'DPB1'!AG10)
¬¬A16 | ¬¬IF(ISBLANK('DPB1'!BR10),"",'DPB1'!BR10) | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BR5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!AH10),"",'DPB1'!AH10) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!AI10),"",'DPB1'!AI10)
¬¬A17 | ¬¬IF(ISBLANK('DPB1'!BU10),"",'DPB1'!BU10) | ¬¬'DPB1'!E10 & "," & 'DPB1'!F10 & "," & 'DPB1'!BU5 | ¬¬IF(ISBLANK('DPB1'!G10),"",'DPB1'!G10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB1'!AK10),"",'DPB1'!AK10) |  |  |  |  | ¬¬IF(ISBLANK('DPB1'!AL10),"",'DPB1'!AL10)
¬¬A18 | ¬¬IF(ISBLANK('DPB2'!AV8),"",'DPB2'!AV8) | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!L8),"",'DPB2'!L8) | ¬¬IF(ISBLANK('DPB2'!M8),"",'DPB2'!M8) | ¬¬IF(ISBLANK('DPB2'!N8),"",'DPB2'!N8) | ¬¬IF(ISBLANK('DPB2'!O8),"",'DPB2'!O8) | ¬¬IF(ISBLANK('DPB2'!P8),"",'DPB2'!P8) | ¬¬IF(ISBLANK('DPB2'!Q8),"",'DPB2'!Q8) | ¬¬IF(ISBLANK('DPB2'!R8),"",'DPB2'!R8) | ¬¬IF(ISBLANK('DPB2'!S8),"",'DPB2'!S8) | ¬¬IF(ISBLANK('DPB2'!T8),"",'DPB2'!T8) | ¬¬IF(ISBLANK('DPB2'!U8),"",'DPB2'!U8)
¬¬A19 | ¬¬IF(ISBLANK('DPB2'!BF8),"",'DPB2'!BF8) | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!V8),"",'DPB2'!V8) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!W8),"",'DPB2'!W8)
¬¬A20 | ¬¬IF(ISBLANK('DPB2'!BJ8),"",'DPB2'!BJ8) | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!Z8),"",'DPB2'!Z8) | ¬¬IF(ISBLANK('DPB2'!AA8),"",'DPB2'!AA8) | ¬¬IF(ISBLANK('DPB2'!AB8),"",'DPB2'!AB8) | ¬¬IF(ISBLANK('DPB2'!AC8),"",'DPB2'!AC8) | ¬¬IF(ISBLANK('DPB2'!AD8),"",'DPB2'!AD8) | ¬¬IF(ISBLANK('DPB2'!AE8),"",'DPB2'!AE8) | ¬¬IF(ISBLANK('DPB2'!AF8),"",'DPB2'!AF8) | ¬¬IF(ISBLANK('DPB2'!AG8),"",'DPB2'!AG8) | ¬¬IF(ISBLANK('DPB2'!AH8),"",'DPB2'!AH8) | ¬¬IF(ISBLANK('DPB2'!AI8),"",'DPB2'!AI8)
¬¬A21 | ¬¬IF(ISBLANK('DPB2'!BT8),"",'DPB2'!BT8) | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AJ8),"",'DPB2'!AJ8) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AK8),"",'DPB2'!AK8)
¬¬A22 | ¬¬IF(ISBLANK('DPB2'!BW8),"",'DPB2'!BW8) | ¬¬'DPB2'!E8 & "," & 'DPB2'!F8 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G8),"",'DPB2'!G8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AM8),"",'DPB2'!AM8) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AN8),"",'DPB2'!AN8)
¬¬A23 | ¬¬IF(ISBLANK('DPB2'!AV9),"",'DPB2'!AV9) | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!L9),"",'DPB2'!L9) | ¬¬IF(ISBLANK('DPB2'!M9),"",'DPB2'!M9) | ¬¬IF(ISBLANK('DPB2'!N9),"",'DPB2'!N9) | ¬¬IF(ISBLANK('DPB2'!O9),"",'DPB2'!O9) | ¬¬IF(ISBLANK('DPB2'!P9),"",'DPB2'!P9) | ¬¬IF(ISBLANK('DPB2'!Q9),"",'DPB2'!Q9) | ¬¬IF(ISBLANK('DPB2'!R9),"",'DPB2'!R9) | ¬¬IF(ISBLANK('DPB2'!S9),"",'DPB2'!S9) | ¬¬IF(ISBLANK('DPB2'!T9),"",'DPB2'!T9) | ¬¬IF(ISBLANK('DPB2'!U9),"",'DPB2'!U9)
¬¬A24 | ¬¬IF(ISBLANK('DPB2'!BF9),"",'DPB2'!BF9) | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!V9),"",'DPB2'!V9) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!W9),"",'DPB2'!W9)
¬¬A25 | ¬¬IF(ISBLANK('DPB2'!BJ9),"",'DPB2'!BJ9) | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!Z9),"",'DPB2'!Z9) | ¬¬IF(ISBLANK('DPB2'!AA9),"",'DPB2'!AA9) | ¬¬IF(ISBLANK('DPB2'!AB9),"",'DPB2'!AB9) | ¬¬IF(ISBLANK('DPB2'!AC9),"",'DPB2'!AC9) | ¬¬IF(ISBLANK('DPB2'!AD9),"",'DPB2'!AD9) | ¬¬IF(ISBLANK('DPB2'!AE9),"",'DPB2'!AE9) | ¬¬IF(ISBLANK('DPB2'!AF9),"",'DPB2'!AF9) | ¬¬IF(ISBLANK('DPB2'!AG9),"",'DPB2'!AG9) | ¬¬IF(ISBLANK('DPB2'!AH9),"",'DPB2'!AH9) | ¬¬IF(ISBLANK('DPB2'!AI9),"",'DPB2'!AI9)
¬¬A26 | ¬¬IF(ISBLANK('DPB2'!BT9),"",'DPB2'!BT9) | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AJ9),"",'DPB2'!AJ9) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AK9),"",'DPB2'!AK9)
¬¬A27 | ¬¬IF(ISBLANK('DPB2'!BW9),"",'DPB2'!BW9) | ¬¬'DPB2'!E9 & "," & 'DPB2'!F9 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G9),"",'DPB2'!G9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AM9),"",'DPB2'!AM9) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AN9),"",'DPB2'!AN9)
¬¬A28 | ¬¬IF(ISBLANK('DPB2'!AV10),"",'DPB2'!AV10) | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!L10),"",'DPB2'!L10) | ¬¬IF(ISBLANK('DPB2'!M10),"",'DPB2'!M10) | ¬¬IF(ISBLANK('DPB2'!N10),"",'DPB2'!N10) | ¬¬IF(ISBLANK('DPB2'!O10),"",'DPB2'!O10) | ¬¬IF(ISBLANK('DPB2'!P10),"",'DPB2'!P10) | ¬¬IF(ISBLANK('DPB2'!Q10),"",'DPB2'!Q10) | ¬¬IF(ISBLANK('DPB2'!R10),"",'DPB2'!R10) | ¬¬IF(ISBLANK('DPB2'!S10),"",'DPB2'!S10) | ¬¬IF(ISBLANK('DPB2'!T10),"",'DPB2'!T10) | ¬¬IF(ISBLANK('DPB2'!U10),"",'DPB2'!U10)
¬¬A29 | ¬¬IF(ISBLANK('DPB2'!BF10),"",'DPB2'!BF10) | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!V10),"",'DPB2'!V10) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!W10),"",'DPB2'!W10)
¬¬A30 | ¬¬IF(ISBLANK('DPB2'!BJ10),"",'DPB2'!BJ10) | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!Z10),"",'DPB2'!Z10) | ¬¬IF(ISBLANK('DPB2'!AA10),"",'DPB2'!AA10) | ¬¬IF(ISBLANK('DPB2'!AB10),"",'DPB2'!AB10) | ¬¬IF(ISBLANK('DPB2'!AC10),"",'DPB2'!AC10) | ¬¬IF(ISBLANK('DPB2'!AD10),"",'DPB2'!AD10) | ¬¬IF(ISBLANK('DPB2'!AE10),"",'DPB2'!AE10) | ¬¬IF(ISBLANK('DPB2'!AF10),"",'DPB2'!AF10) | ¬¬IF(ISBLANK('DPB2'!AG10),"",'DPB2'!AG10) | ¬¬IF(ISBLANK('DPB2'!AH10),"",'DPB2'!AH10) | ¬¬IF(ISBLANK('DPB2'!AI10),"",'DPB2'!AI10)
¬¬A31 | ¬¬IF(ISBLANK('DPB2'!BT10),"",'DPB2'!BT10) | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AJ10),"",'DPB2'!AJ10) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AK10),"",'DPB2'!AK10)
¬¬A32 | ¬¬IF(ISBLANK('DPB2'!BW10),"",'DPB2'!BW10) | ¬¬'DPB2'!E10 & "," & 'DPB2'!F10 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G10),"",'DPB2'!G10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AM10),"",'DPB2'!AM10) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AN10),"",'DPB2'!AN10)
¬¬A33 | ¬¬IF(ISBLANK('DPB2'!AV11),"",'DPB2'!AV11) | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!L11),"",'DPB2'!L11) | ¬¬IF(ISBLANK('DPB2'!M11),"",'DPB2'!M11) | ¬¬IF(ISBLANK('DPB2'!N11),"",'DPB2'!N11) | ¬¬IF(ISBLANK('DPB2'!O11),"",'DPB2'!O11) | ¬¬IF(ISBLANK('DPB2'!P11),"",'DPB2'!P11) | ¬¬IF(ISBLANK('DPB2'!Q11),"",'DPB2'!Q11) | ¬¬IF(ISBLANK('DPB2'!R11),"",'DPB2'!R11) | ¬¬IF(ISBLANK('DPB2'!S11),"",'DPB2'!S11) | ¬¬IF(ISBLANK('DPB2'!T11),"",'DPB2'!T11) | ¬¬IF(ISBLANK('DPB2'!U11),"",'DPB2'!U11)
¬¬A34 | ¬¬IF(ISBLANK('DPB2'!BF11),"",'DPB2'!BF11) | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!V11),"",'DPB2'!V11) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!W11),"",'DPB2'!W11)
¬¬A35 | ¬¬IF(ISBLANK('DPB2'!BJ11),"",'DPB2'!BJ11) | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!Z11),"",'DPB2'!Z11) | ¬¬IF(ISBLANK('DPB2'!AA11),"",'DPB2'!AA11) | ¬¬IF(ISBLANK('DPB2'!AB11),"",'DPB2'!AB11) | ¬¬IF(ISBLANK('DPB2'!AC11),"",'DPB2'!AC11) | ¬¬IF(ISBLANK('DPB2'!AD11),"",'DPB2'!AD11) | ¬¬IF(ISBLANK('DPB2'!AE11),"",'DPB2'!AE11) | ¬¬IF(ISBLANK('DPB2'!AF11),"",'DPB2'!AF11) | ¬¬IF(ISBLANK('DPB2'!AG11),"",'DPB2'!AG11) | ¬¬IF(ISBLANK('DPB2'!AH11),"",'DPB2'!AH11) | ¬¬IF(ISBLANK('DPB2'!AI11),"",'DPB2'!AI11)
¬¬A36 | ¬¬IF(ISBLANK('DPB2'!BT11),"",'DPB2'!BT11) | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AJ11),"",'DPB2'!AJ11) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AK11),"",'DPB2'!AK11)
¬¬A37 | ¬¬IF(ISBLANK('DPB2'!BW11),"",'DPB2'!BW11) | ¬¬'DPB2'!E11 & "," & 'DPB2'!F11 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G11),"",'DPB2'!G11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AM11),"",'DPB2'!AM11) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AN11),"",'DPB2'!AN11)
¬¬A38 | ¬¬IF(ISBLANK('DPB2'!AV12),"",'DPB2'!AV12) | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!AS5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!L12),"",'DPB2'!L12) | ¬¬IF(ISBLANK('DPB2'!M12),"",'DPB2'!M12) | ¬¬IF(ISBLANK('DPB2'!N12),"",'DPB2'!N12) | ¬¬IF(ISBLANK('DPB2'!O12),"",'DPB2'!O12) | ¬¬IF(ISBLANK('DPB2'!P12),"",'DPB2'!P12) | ¬¬IF(ISBLANK('DPB2'!Q12),"",'DPB2'!Q12) | ¬¬IF(ISBLANK('DPB2'!R12),"",'DPB2'!R12) | ¬¬IF(ISBLANK('DPB2'!S12),"",'DPB2'!S12) | ¬¬IF(ISBLANK('DPB2'!T12),"",'DPB2'!T12) | ¬¬IF(ISBLANK('DPB2'!U12),"",'DPB2'!U12)
¬¬A39 | ¬¬IF(ISBLANK('DPB2'!BF12),"",'DPB2'!BF12) | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BF5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!V12),"",'DPB2'!V12) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!W12),"",'DPB2'!W12)
¬¬A40 | ¬¬IF(ISBLANK('DPB2'!BJ12),"",'DPB2'!BJ12) | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BG5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) | Delta |  |  |  | ¬¬IF(ISBLANK('DPB2'!Z12),"",'DPB2'!Z12) | ¬¬IF(ISBLANK('DPB2'!AA12),"",'DPB2'!AA12) | ¬¬IF(ISBLANK('DPB2'!AB12),"",'DPB2'!AB12) | ¬¬IF(ISBLANK('DPB2'!AC12),"",'DPB2'!AC12) | ¬¬IF(ISBLANK('DPB2'!AD12),"",'DPB2'!AD12) | ¬¬IF(ISBLANK('DPB2'!AE12),"",'DPB2'!AE12) | ¬¬IF(ISBLANK('DPB2'!AF12),"",'DPB2'!AF12) | ¬¬IF(ISBLANK('DPB2'!AG12),"",'DPB2'!AG12) | ¬¬IF(ISBLANK('DPB2'!AH12),"",'DPB2'!AH12) | ¬¬IF(ISBLANK('DPB2'!AI12),"",'DPB2'!AI12)
¬¬A41 | ¬¬IF(ISBLANK('DPB2'!BT12),"",'DPB2'!BT12) | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BT5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AJ12),"",'DPB2'!AJ12) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AK12),"",'DPB2'!AK12)
¬¬A42 | ¬¬IF(ISBLANK('DPB2'!BW12),"",'DPB2'!BW12) | ¬¬'DPB2'!E12 & "," & 'DPB2'!F12 & "," & 'DPB2'!BW5 | ¬¬IF(ISBLANK('DPB2'!G12),"",'DPB2'!G12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPB2'!AM12),"",'DPB2'!AM12) |  |  |  |  | ¬¬IF(ISBLANK('DPB2'!AN12),"",'DPB2'!AN12)
¬¬A43 | ¬¬IF(ISBLANK(DPWW1!AT8),"",DPWW1!AT8) | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J8),"",DPWW1!J8) | ¬¬IF(ISBLANK(DPWW1!K8),"",DPWW1!K8) | ¬¬IF(ISBLANK(DPWW1!L8),"",DPWW1!L8) | ¬¬IF(ISBLANK(DPWW1!M8),"",DPWW1!M8) | ¬¬IF(ISBLANK(DPWW1!N8),"",DPWW1!N8) | ¬¬IF(ISBLANK(DPWW1!O8),"",DPWW1!O8) | ¬¬IF(ISBLANK(DPWW1!P8),"",DPWW1!P8) | ¬¬IF(ISBLANK(DPWW1!Q8),"",DPWW1!Q8) | ¬¬IF(ISBLANK(DPWW1!R8),"",DPWW1!R8) | ¬¬IF(ISBLANK(DPWW1!S8),"",DPWW1!S8) | ¬¬IF(ISBLANK(DPWW1!T8),"",DPWW1!T8)
¬¬A44 | ¬¬IF(ISBLANK(DPWW1!BE8),"",DPWW1!BE8) | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U8),"",DPWW1!U8) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V8),"",DPWW1!V8)
¬¬A45 | ¬¬IF(ISBLANK(DPWW1!BH8),"",DPWW1!BH8) | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X8),"",DPWW1!X8) | ¬¬IF(ISBLANK(DPWW1!Y8),"",DPWW1!Y8) | ¬¬IF(ISBLANK(DPWW1!Z8),"",DPWW1!Z8) | ¬¬IF(ISBLANK(DPWW1!AA8),"",DPWW1!AA8) | ¬¬IF(ISBLANK(DPWW1!AB8),"",DPWW1!AB8) | ¬¬IF(ISBLANK(DPWW1!AC8),"",DPWW1!AC8) | ¬¬IF(ISBLANK(DPWW1!AD8),"",DPWW1!AD8) | ¬¬IF(ISBLANK(DPWW1!AE8),"",DPWW1!AE8) | ¬¬IF(ISBLANK(DPWW1!AF8),"",DPWW1!AF8) | ¬¬IF(ISBLANK(DPWW1!AG8),"",DPWW1!AG8) | ¬¬IF(ISBLANK(DPWW1!AH8),"",DPWW1!AH8)
¬¬A46 | ¬¬IF(ISBLANK(DPWW1!BS8),"",DPWW1!BS8) | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI8),"",DPWW1!AI8) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ8),"",DPWW1!AJ8)
¬¬A47 | ¬¬IF(ISBLANK(DPWW1!BV8),"",DPWW1!BV8) | ¬¬DPWW1!F8 & "," & DPWW1!G8 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H8),"",DPWW1!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL8),"",DPWW1!AL8) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM8),"",DPWW1!AM8)
¬¬A48 | ¬¬IF(ISBLANK(DPWW1!AT9),"",DPWW1!AT9) | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J9),"",DPWW1!J9) | ¬¬IF(ISBLANK(DPWW1!K9),"",DPWW1!K9) | ¬¬IF(ISBLANK(DPWW1!L9),"",DPWW1!L9) | ¬¬IF(ISBLANK(DPWW1!M9),"",DPWW1!M9) | ¬¬IF(ISBLANK(DPWW1!N9),"",DPWW1!N9) | ¬¬IF(ISBLANK(DPWW1!O9),"",DPWW1!O9) | ¬¬IF(ISBLANK(DPWW1!P9),"",DPWW1!P9) | ¬¬IF(ISBLANK(DPWW1!Q9),"",DPWW1!Q9) | ¬¬IF(ISBLANK(DPWW1!R9),"",DPWW1!R9) | ¬¬IF(ISBLANK(DPWW1!S9),"",DPWW1!S9) | ¬¬IF(ISBLANK(DPWW1!T9),"",DPWW1!T9)
¬¬A49 | ¬¬IF(ISBLANK(DPWW1!BE9),"",DPWW1!BE9) | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U9),"",DPWW1!U9) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V9),"",DPWW1!V9)
¬¬A50 | ¬¬IF(ISBLANK(DPWW1!BH9),"",DPWW1!BH9) | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X9),"",DPWW1!X9) | ¬¬IF(ISBLANK(DPWW1!Y9),"",DPWW1!Y9) | ¬¬IF(ISBLANK(DPWW1!Z9),"",DPWW1!Z9) | ¬¬IF(ISBLANK(DPWW1!AA9),"",DPWW1!AA9) | ¬¬IF(ISBLANK(DPWW1!AB9),"",DPWW1!AB9) | ¬¬IF(ISBLANK(DPWW1!AC9),"",DPWW1!AC9) | ¬¬IF(ISBLANK(DPWW1!AD9),"",DPWW1!AD9) | ¬¬IF(ISBLANK(DPWW1!AE9),"",DPWW1!AE9) | ¬¬IF(ISBLANK(DPWW1!AF9),"",DPWW1!AF9) | ¬¬IF(ISBLANK(DPWW1!AG9),"",DPWW1!AG9) | ¬¬IF(ISBLANK(DPWW1!AH9),"",DPWW1!AH9)
¬¬A51 | ¬¬IF(ISBLANK(DPWW1!BS9),"",DPWW1!BS9) | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI9),"",DPWW1!AI9) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ9),"",DPWW1!AJ9)
¬¬A52 | ¬¬IF(ISBLANK(DPWW1!BV9),"",DPWW1!BV9) | ¬¬DPWW1!F9 & "," & DPWW1!G9 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H9),"",DPWW1!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL9),"",DPWW1!AL9) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM9),"",DPWW1!AM9)
¬¬A53 | ¬¬IF(ISBLANK(DPWW1!AT10),"",DPWW1!AT10) | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J10),"",DPWW1!J10) | ¬¬IF(ISBLANK(DPWW1!K10),"",DPWW1!K10) | ¬¬IF(ISBLANK(DPWW1!L10),"",DPWW1!L10) | ¬¬IF(ISBLANK(DPWW1!M10),"",DPWW1!M10) | ¬¬IF(ISBLANK(DPWW1!N10),"",DPWW1!N10) | ¬¬IF(ISBLANK(DPWW1!O10),"",DPWW1!O10) | ¬¬IF(ISBLANK(DPWW1!P10),"",DPWW1!P10) | ¬¬IF(ISBLANK(DPWW1!Q10),"",DPWW1!Q10) | ¬¬IF(ISBLANK(DPWW1!R10),"",DPWW1!R10) | ¬¬IF(ISBLANK(DPWW1!S10),"",DPWW1!S10) | ¬¬IF(ISBLANK(DPWW1!T10),"",DPWW1!T10)
¬¬A54 | ¬¬IF(ISBLANK(DPWW1!BE10),"",DPWW1!BE10) | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U10),"",DPWW1!U10) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V10),"",DPWW1!V10)
¬¬A55 | ¬¬IF(ISBLANK(DPWW1!BH10),"",DPWW1!BH10) | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X10),"",DPWW1!X10) | ¬¬IF(ISBLANK(DPWW1!Y10),"",DPWW1!Y10) | ¬¬IF(ISBLANK(DPWW1!Z10),"",DPWW1!Z10) | ¬¬IF(ISBLANK(DPWW1!AA10),"",DPWW1!AA10) | ¬¬IF(ISBLANK(DPWW1!AB10),"",DPWW1!AB10) | ¬¬IF(ISBLANK(DPWW1!AC10),"",DPWW1!AC10) | ¬¬IF(ISBLANK(DPWW1!AD10),"",DPWW1!AD10) | ¬¬IF(ISBLANK(DPWW1!AE10),"",DPWW1!AE10) | ¬¬IF(ISBLANK(DPWW1!AF10),"",DPWW1!AF10) | ¬¬IF(ISBLANK(DPWW1!AG10),"",DPWW1!AG10) | ¬¬IF(ISBLANK(DPWW1!AH10),"",DPWW1!AH10)
¬¬A56 | ¬¬IF(ISBLANK(DPWW1!BS10),"",DPWW1!BS10) | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI10),"",DPWW1!AI10) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ10),"",DPWW1!AJ10)
¬¬A57 | ¬¬IF(ISBLANK(DPWW1!BV10),"",DPWW1!BV10) | ¬¬DPWW1!F10 & "," & DPWW1!G10 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H10),"",DPWW1!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL10),"",DPWW1!AL10) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM10),"",DPWW1!AM10)
¬¬A58 | ¬¬IF(ISBLANK(DPWW1!AT11),"",DPWW1!AT11) | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J11),"",DPWW1!J11) | ¬¬IF(ISBLANK(DPWW1!K11),"",DPWW1!K11) | ¬¬IF(ISBLANK(DPWW1!L11),"",DPWW1!L11) | ¬¬IF(ISBLANK(DPWW1!M11),"",DPWW1!M11) | ¬¬IF(ISBLANK(DPWW1!N11),"",DPWW1!N11) | ¬¬IF(ISBLANK(DPWW1!O11),"",DPWW1!O11) | ¬¬IF(ISBLANK(DPWW1!P11),"",DPWW1!P11) | ¬¬IF(ISBLANK(DPWW1!Q11),"",DPWW1!Q11) | ¬¬IF(ISBLANK(DPWW1!R11),"",DPWW1!R11) | ¬¬IF(ISBLANK(DPWW1!S11),"",DPWW1!S11) | ¬¬IF(ISBLANK(DPWW1!T11),"",DPWW1!T11)
¬¬A59 | ¬¬IF(ISBLANK(DPWW1!BE11),"",DPWW1!BE11) | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U11),"",DPWW1!U11) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V11),"",DPWW1!V11)
¬¬A60 | ¬¬IF(ISBLANK(DPWW1!BH11),"",DPWW1!BH11) | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X11),"",DPWW1!X11) | ¬¬IF(ISBLANK(DPWW1!Y11),"",DPWW1!Y11) | ¬¬IF(ISBLANK(DPWW1!Z11),"",DPWW1!Z11) | ¬¬IF(ISBLANK(DPWW1!AA11),"",DPWW1!AA11) | ¬¬IF(ISBLANK(DPWW1!AB11),"",DPWW1!AB11) | ¬¬IF(ISBLANK(DPWW1!AC11),"",DPWW1!AC11) | ¬¬IF(ISBLANK(DPWW1!AD11),"",DPWW1!AD11) | ¬¬IF(ISBLANK(DPWW1!AE11),"",DPWW1!AE11) | ¬¬IF(ISBLANK(DPWW1!AF11),"",DPWW1!AF11) | ¬¬IF(ISBLANK(DPWW1!AG11),"",DPWW1!AG11) | ¬¬IF(ISBLANK(DPWW1!AH11),"",DPWW1!AH11)
¬¬A61 | ¬¬IF(ISBLANK(DPWW1!BS11),"",DPWW1!BS11) | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI11),"",DPWW1!AI11) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ11),"",DPWW1!AJ11)
¬¬A62 | ¬¬IF(ISBLANK(DPWW1!BV11),"",DPWW1!BV11) | ¬¬DPWW1!F11 & "," & DPWW1!G11 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H11),"",DPWW1!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL11),"",DPWW1!AL11) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM11),"",DPWW1!AM11)
¬¬A63 | ¬¬IF(ISBLANK(DPWW1!AT12),"",DPWW1!AT12) | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J12),"",DPWW1!J12) | ¬¬IF(ISBLANK(DPWW1!K12),"",DPWW1!K12) | ¬¬IF(ISBLANK(DPWW1!L12),"",DPWW1!L12) | ¬¬IF(ISBLANK(DPWW1!M12),"",DPWW1!M12) | ¬¬IF(ISBLANK(DPWW1!N12),"",DPWW1!N12) | ¬¬IF(ISBLANK(DPWW1!O12),"",DPWW1!O12) | ¬¬IF(ISBLANK(DPWW1!P12),"",DPWW1!P12) | ¬¬IF(ISBLANK(DPWW1!Q12),"",DPWW1!Q12) | ¬¬IF(ISBLANK(DPWW1!R12),"",DPWW1!R12) | ¬¬IF(ISBLANK(DPWW1!S12),"",DPWW1!S12) | ¬¬IF(ISBLANK(DPWW1!T12),"",DPWW1!T12)
¬¬A64 | ¬¬IF(ISBLANK(DPWW1!BE12),"",DPWW1!BE12) | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U12),"",DPWW1!U12) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V12),"",DPWW1!V12)
¬¬A65 | ¬¬IF(ISBLANK(DPWW1!BH12),"",DPWW1!BH12) | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X12),"",DPWW1!X12) | ¬¬IF(ISBLANK(DPWW1!Y12),"",DPWW1!Y12) | ¬¬IF(ISBLANK(DPWW1!Z12),"",DPWW1!Z12) | ¬¬IF(ISBLANK(DPWW1!AA12),"",DPWW1!AA12) | ¬¬IF(ISBLANK(DPWW1!AB12),"",DPWW1!AB12) | ¬¬IF(ISBLANK(DPWW1!AC12),"",DPWW1!AC12) | ¬¬IF(ISBLANK(DPWW1!AD12),"",DPWW1!AD12) | ¬¬IF(ISBLANK(DPWW1!AE12),"",DPWW1!AE12) | ¬¬IF(ISBLANK(DPWW1!AF12),"",DPWW1!AF12) | ¬¬IF(ISBLANK(DPWW1!AG12),"",DPWW1!AG12) | ¬¬IF(ISBLANK(DPWW1!AH12),"",DPWW1!AH12)
¬¬A66 | ¬¬IF(ISBLANK(DPWW1!BS12),"",DPWW1!BS12) | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI12),"",DPWW1!AI12) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ12),"",DPWW1!AJ12)
¬¬A67 | ¬¬IF(ISBLANK(DPWW1!BV12),"",DPWW1!BV12) | ¬¬DPWW1!F12 & "," & DPWW1!G12 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H12),"",DPWW1!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL12),"",DPWW1!AL12) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM12),"",DPWW1!AM12)
¬¬A68 | ¬¬IF(ISBLANK(DPWW1!AT13),"",DPWW1!AT13) | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J13),"",DPWW1!J13) | ¬¬IF(ISBLANK(DPWW1!K13),"",DPWW1!K13) | ¬¬IF(ISBLANK(DPWW1!L13),"",DPWW1!L13) | ¬¬IF(ISBLANK(DPWW1!M13),"",DPWW1!M13) | ¬¬IF(ISBLANK(DPWW1!N13),"",DPWW1!N13) | ¬¬IF(ISBLANK(DPWW1!O13),"",DPWW1!O13) | ¬¬IF(ISBLANK(DPWW1!P13),"",DPWW1!P13) | ¬¬IF(ISBLANK(DPWW1!Q13),"",DPWW1!Q13) | ¬¬IF(ISBLANK(DPWW1!R13),"",DPWW1!R13) | ¬¬IF(ISBLANK(DPWW1!S13),"",DPWW1!S13) | ¬¬IF(ISBLANK(DPWW1!T13),"",DPWW1!T13)
¬¬A69 | ¬¬IF(ISBLANK(DPWW1!BE13),"",DPWW1!BE13) | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U13),"",DPWW1!U13) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V13),"",DPWW1!V13)
¬¬A70 | ¬¬IF(ISBLANK(DPWW1!BH13),"",DPWW1!BH13) | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X13),"",DPWW1!X13) | ¬¬IF(ISBLANK(DPWW1!Y13),"",DPWW1!Y13) | ¬¬IF(ISBLANK(DPWW1!Z13),"",DPWW1!Z13) | ¬¬IF(ISBLANK(DPWW1!AA13),"",DPWW1!AA13) | ¬¬IF(ISBLANK(DPWW1!AB13),"",DPWW1!AB13) | ¬¬IF(ISBLANK(DPWW1!AC13),"",DPWW1!AC13) | ¬¬IF(ISBLANK(DPWW1!AD13),"",DPWW1!AD13) | ¬¬IF(ISBLANK(DPWW1!AE13),"",DPWW1!AE13) | ¬¬IF(ISBLANK(DPWW1!AF13),"",DPWW1!AF13) | ¬¬IF(ISBLANK(DPWW1!AG13),"",DPWW1!AG13) | ¬¬IF(ISBLANK(DPWW1!AH13),"",DPWW1!AH13)
¬¬A71 | ¬¬IF(ISBLANK(DPWW1!BS13),"",DPWW1!BS13) | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI13),"",DPWW1!AI13) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ13),"",DPWW1!AJ13)
¬¬A72 | ¬¬IF(ISBLANK(DPWW1!BV13),"",DPWW1!BV13) | ¬¬DPWW1!F13 & "," & DPWW1!G13 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H13),"",DPWW1!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL13),"",DPWW1!AL13) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM13),"",DPWW1!AM13)
¬¬A73 | ¬¬IF(ISBLANK(DPWW1!AT14),"",DPWW1!AT14) | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J14),"",DPWW1!J14) | ¬¬IF(ISBLANK(DPWW1!K14),"",DPWW1!K14) | ¬¬IF(ISBLANK(DPWW1!L14),"",DPWW1!L14) | ¬¬IF(ISBLANK(DPWW1!M14),"",DPWW1!M14) | ¬¬IF(ISBLANK(DPWW1!N14),"",DPWW1!N14) | ¬¬IF(ISBLANK(DPWW1!O14),"",DPWW1!O14) | ¬¬IF(ISBLANK(DPWW1!P14),"",DPWW1!P14) | ¬¬IF(ISBLANK(DPWW1!Q14),"",DPWW1!Q14) | ¬¬IF(ISBLANK(DPWW1!R14),"",DPWW1!R14) | ¬¬IF(ISBLANK(DPWW1!S14),"",DPWW1!S14) | ¬¬IF(ISBLANK(DPWW1!T14),"",DPWW1!T14)
¬¬A74 | ¬¬IF(ISBLANK(DPWW1!BE14),"",DPWW1!BE14) | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U14),"",DPWW1!U14) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V14),"",DPWW1!V14)
¬¬A75 | ¬¬IF(ISBLANK(DPWW1!BH14),"",DPWW1!BH14) | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X14),"",DPWW1!X14) | ¬¬IF(ISBLANK(DPWW1!Y14),"",DPWW1!Y14) | ¬¬IF(ISBLANK(DPWW1!Z14),"",DPWW1!Z14) | ¬¬IF(ISBLANK(DPWW1!AA14),"",DPWW1!AA14) | ¬¬IF(ISBLANK(DPWW1!AB14),"",DPWW1!AB14) | ¬¬IF(ISBLANK(DPWW1!AC14),"",DPWW1!AC14) | ¬¬IF(ISBLANK(DPWW1!AD14),"",DPWW1!AD14) | ¬¬IF(ISBLANK(DPWW1!AE14),"",DPWW1!AE14) | ¬¬IF(ISBLANK(DPWW1!AF14),"",DPWW1!AF14) | ¬¬IF(ISBLANK(DPWW1!AG14),"",DPWW1!AG14) | ¬¬IF(ISBLANK(DPWW1!AH14),"",DPWW1!AH14)
¬¬A76 | ¬¬IF(ISBLANK(DPWW1!BS14),"",DPWW1!BS14) | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI14),"",DPWW1!AI14) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ14),"",DPWW1!AJ14)
¬¬A77 | ¬¬IF(ISBLANK(DPWW1!BV14),"",DPWW1!BV14) | ¬¬DPWW1!F14 & "," & DPWW1!G14 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H14),"",DPWW1!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL14),"",DPWW1!AL14) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM14),"",DPWW1!AM14)
¬¬A78 | ¬¬IF(ISBLANK(DPWW1!AT15),"",DPWW1!AT15) | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J15),"",DPWW1!J15) | ¬¬IF(ISBLANK(DPWW1!K15),"",DPWW1!K15) | ¬¬IF(ISBLANK(DPWW1!L15),"",DPWW1!L15) | ¬¬IF(ISBLANK(DPWW1!M15),"",DPWW1!M15) | ¬¬IF(ISBLANK(DPWW1!N15),"",DPWW1!N15) | ¬¬IF(ISBLANK(DPWW1!O15),"",DPWW1!O15) | ¬¬IF(ISBLANK(DPWW1!P15),"",DPWW1!P15) | ¬¬IF(ISBLANK(DPWW1!Q15),"",DPWW1!Q15) | ¬¬IF(ISBLANK(DPWW1!R15),"",DPWW1!R15) | ¬¬IF(ISBLANK(DPWW1!S15),"",DPWW1!S15) | ¬¬IF(ISBLANK(DPWW1!T15),"",DPWW1!T15)
¬¬A79 | ¬¬IF(ISBLANK(DPWW1!BE15),"",DPWW1!BE15) | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U15),"",DPWW1!U15) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V15),"",DPWW1!V15)
¬¬A80 | ¬¬IF(ISBLANK(DPWW1!BH15),"",DPWW1!BH15) | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X15),"",DPWW1!X15) | ¬¬IF(ISBLANK(DPWW1!Y15),"",DPWW1!Y15) | ¬¬IF(ISBLANK(DPWW1!Z15),"",DPWW1!Z15) | ¬¬IF(ISBLANK(DPWW1!AA15),"",DPWW1!AA15) | ¬¬IF(ISBLANK(DPWW1!AB15),"",DPWW1!AB15) | ¬¬IF(ISBLANK(DPWW1!AC15),"",DPWW1!AC15) | ¬¬IF(ISBLANK(DPWW1!AD15),"",DPWW1!AD15) | ¬¬IF(ISBLANK(DPWW1!AE15),"",DPWW1!AE15) | ¬¬IF(ISBLANK(DPWW1!AF15),"",DPWW1!AF15) | ¬¬IF(ISBLANK(DPWW1!AG15),"",DPWW1!AG15) | ¬¬IF(ISBLANK(DPWW1!AH15),"",DPWW1!AH15)
¬¬A81 | ¬¬IF(ISBLANK(DPWW1!BS15),"",DPWW1!BS15) | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI15),"",DPWW1!AI15) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ15),"",DPWW1!AJ15)
¬¬A82 | ¬¬IF(ISBLANK(DPWW1!BV15),"",DPWW1!BV15) | ¬¬DPWW1!F15 & "," & DPWW1!G15 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H15),"",DPWW1!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL15),"",DPWW1!AL15) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM15),"",DPWW1!AM15)
¬¬A83 | ¬¬IF(ISBLANK(DPWW1!AT16),"",DPWW1!AT16) | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J16),"",DPWW1!J16) | ¬¬IF(ISBLANK(DPWW1!K16),"",DPWW1!K16) | ¬¬IF(ISBLANK(DPWW1!L16),"",DPWW1!L16) | ¬¬IF(ISBLANK(DPWW1!M16),"",DPWW1!M16) | ¬¬IF(ISBLANK(DPWW1!N16),"",DPWW1!N16) | ¬¬IF(ISBLANK(DPWW1!O16),"",DPWW1!O16) | ¬¬IF(ISBLANK(DPWW1!P16),"",DPWW1!P16) | ¬¬IF(ISBLANK(DPWW1!Q16),"",DPWW1!Q16) | ¬¬IF(ISBLANK(DPWW1!R16),"",DPWW1!R16) | ¬¬IF(ISBLANK(DPWW1!S16),"",DPWW1!S16) | ¬¬IF(ISBLANK(DPWW1!T16),"",DPWW1!T16)
¬¬A84 | ¬¬IF(ISBLANK(DPWW1!BE16),"",DPWW1!BE16) | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U16),"",DPWW1!U16) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V16),"",DPWW1!V16)
¬¬A85 | ¬¬IF(ISBLANK(DPWW1!BH16),"",DPWW1!BH16) | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X16),"",DPWW1!X16) | ¬¬IF(ISBLANK(DPWW1!Y16),"",DPWW1!Y16) | ¬¬IF(ISBLANK(DPWW1!Z16),"",DPWW1!Z16) | ¬¬IF(ISBLANK(DPWW1!AA16),"",DPWW1!AA16) | ¬¬IF(ISBLANK(DPWW1!AB16),"",DPWW1!AB16) | ¬¬IF(ISBLANK(DPWW1!AC16),"",DPWW1!AC16) | ¬¬IF(ISBLANK(DPWW1!AD16),"",DPWW1!AD16) | ¬¬IF(ISBLANK(DPWW1!AE16),"",DPWW1!AE16) | ¬¬IF(ISBLANK(DPWW1!AF16),"",DPWW1!AF16) | ¬¬IF(ISBLANK(DPWW1!AG16),"",DPWW1!AG16) | ¬¬IF(ISBLANK(DPWW1!AH16),"",DPWW1!AH16)
¬¬A86 | ¬¬IF(ISBLANK(DPWW1!BS16),"",DPWW1!BS16) | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI16),"",DPWW1!AI16) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ16),"",DPWW1!AJ16)
¬¬A87 | ¬¬IF(ISBLANK(DPWW1!BV16),"",DPWW1!BV16) | ¬¬DPWW1!F16 & "," & DPWW1!G16 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H16),"",DPWW1!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL16),"",DPWW1!AL16) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM16),"",DPWW1!AM16)
¬¬A88 | ¬¬IF(ISBLANK(DPWW1!AT17),"",DPWW1!AT17) | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J17),"",DPWW1!J17) | ¬¬IF(ISBLANK(DPWW1!K17),"",DPWW1!K17) | ¬¬IF(ISBLANK(DPWW1!L17),"",DPWW1!L17) | ¬¬IF(ISBLANK(DPWW1!M17),"",DPWW1!M17) | ¬¬IF(ISBLANK(DPWW1!N17),"",DPWW1!N17) | ¬¬IF(ISBLANK(DPWW1!O17),"",DPWW1!O17) | ¬¬IF(ISBLANK(DPWW1!P17),"",DPWW1!P17) | ¬¬IF(ISBLANK(DPWW1!Q17),"",DPWW1!Q17) | ¬¬IF(ISBLANK(DPWW1!R17),"",DPWW1!R17) | ¬¬IF(ISBLANK(DPWW1!S17),"",DPWW1!S17) | ¬¬IF(ISBLANK(DPWW1!T17),"",DPWW1!T17)
¬¬A89 | ¬¬IF(ISBLANK(DPWW1!BE17),"",DPWW1!BE17) | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U17),"",DPWW1!U17) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V17),"",DPWW1!V17)
¬¬A90 | ¬¬IF(ISBLANK(DPWW1!BH17),"",DPWW1!BH17) | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X17),"",DPWW1!X17) | ¬¬IF(ISBLANK(DPWW1!Y17),"",DPWW1!Y17) | ¬¬IF(ISBLANK(DPWW1!Z17),"",DPWW1!Z17) | ¬¬IF(ISBLANK(DPWW1!AA17),"",DPWW1!AA17) | ¬¬IF(ISBLANK(DPWW1!AB17),"",DPWW1!AB17) | ¬¬IF(ISBLANK(DPWW1!AC17),"",DPWW1!AC17) | ¬¬IF(ISBLANK(DPWW1!AD17),"",DPWW1!AD17) | ¬¬IF(ISBLANK(DPWW1!AE17),"",DPWW1!AE17) | ¬¬IF(ISBLANK(DPWW1!AF17),"",DPWW1!AF17) | ¬¬IF(ISBLANK(DPWW1!AG17),"",DPWW1!AG17) | ¬¬IF(ISBLANK(DPWW1!AH17),"",DPWW1!AH17)
¬¬A91 | ¬¬IF(ISBLANK(DPWW1!BS17),"",DPWW1!BS17) | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI17),"",DPWW1!AI17) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ17),"",DPWW1!AJ17)
¬¬A92 | ¬¬IF(ISBLANK(DPWW1!BV17),"",DPWW1!BV17) | ¬¬DPWW1!F17 & "," & DPWW1!G17 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H17),"",DPWW1!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL17),"",DPWW1!AL17) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM17),"",DPWW1!AM17)
¬¬A93 | ¬¬IF(ISBLANK(DPWW1!AT18),"",DPWW1!AT18) | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J18),"",DPWW1!J18) | ¬¬IF(ISBLANK(DPWW1!K18),"",DPWW1!K18) | ¬¬IF(ISBLANK(DPWW1!L18),"",DPWW1!L18) | ¬¬IF(ISBLANK(DPWW1!M18),"",DPWW1!M18) | ¬¬IF(ISBLANK(DPWW1!N18),"",DPWW1!N18) | ¬¬IF(ISBLANK(DPWW1!O18),"",DPWW1!O18) | ¬¬IF(ISBLANK(DPWW1!P18),"",DPWW1!P18) | ¬¬IF(ISBLANK(DPWW1!Q18),"",DPWW1!Q18) | ¬¬IF(ISBLANK(DPWW1!R18),"",DPWW1!R18) | ¬¬IF(ISBLANK(DPWW1!S18),"",DPWW1!S18) | ¬¬IF(ISBLANK(DPWW1!T18),"",DPWW1!T18)
¬¬A94 | ¬¬IF(ISBLANK(DPWW1!BE18),"",DPWW1!BE18) | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U18),"",DPWW1!U18) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V18),"",DPWW1!V18)
¬¬A95 | ¬¬IF(ISBLANK(DPWW1!BH18),"",DPWW1!BH18) | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X18),"",DPWW1!X18) | ¬¬IF(ISBLANK(DPWW1!Y18),"",DPWW1!Y18) | ¬¬IF(ISBLANK(DPWW1!Z18),"",DPWW1!Z18) | ¬¬IF(ISBLANK(DPWW1!AA18),"",DPWW1!AA18) | ¬¬IF(ISBLANK(DPWW1!AB18),"",DPWW1!AB18) | ¬¬IF(ISBLANK(DPWW1!AC18),"",DPWW1!AC18) | ¬¬IF(ISBLANK(DPWW1!AD18),"",DPWW1!AD18) | ¬¬IF(ISBLANK(DPWW1!AE18),"",DPWW1!AE18) | ¬¬IF(ISBLANK(DPWW1!AF18),"",DPWW1!AF18) | ¬¬IF(ISBLANK(DPWW1!AG18),"",DPWW1!AG18) | ¬¬IF(ISBLANK(DPWW1!AH18),"",DPWW1!AH18)
¬¬A96 | ¬¬IF(ISBLANK(DPWW1!BS18),"",DPWW1!BS18) | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI18),"",DPWW1!AI18) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ18),"",DPWW1!AJ18)
¬¬A97 | ¬¬IF(ISBLANK(DPWW1!BV18),"",DPWW1!BV18) | ¬¬DPWW1!F18 & "," & DPWW1!G18 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H18),"",DPWW1!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL18),"",DPWW1!AL18) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM18),"",DPWW1!AM18)
¬¬A98 | ¬¬IF(ISBLANK(DPWW1!AT19),"",DPWW1!AT19) | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J19),"",DPWW1!J19) | ¬¬IF(ISBLANK(DPWW1!K19),"",DPWW1!K19) | ¬¬IF(ISBLANK(DPWW1!L19),"",DPWW1!L19) | ¬¬IF(ISBLANK(DPWW1!M19),"",DPWW1!M19) | ¬¬IF(ISBLANK(DPWW1!N19),"",DPWW1!N19) | ¬¬IF(ISBLANK(DPWW1!O19),"",DPWW1!O19) | ¬¬IF(ISBLANK(DPWW1!P19),"",DPWW1!P19) | ¬¬IF(ISBLANK(DPWW1!Q19),"",DPWW1!Q19) | ¬¬IF(ISBLANK(DPWW1!R19),"",DPWW1!R19) | ¬¬IF(ISBLANK(DPWW1!S19),"",DPWW1!S19) | ¬¬IF(ISBLANK(DPWW1!T19),"",DPWW1!T19)
¬¬A99 | ¬¬IF(ISBLANK(DPWW1!BE19),"",DPWW1!BE19) | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U19),"",DPWW1!U19) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V19),"",DPWW1!V19)
¬¬A100 | ¬¬IF(ISBLANK(DPWW1!BH19),"",DPWW1!BH19) | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X19),"",DPWW1!X19) | ¬¬IF(ISBLANK(DPWW1!Y19),"",DPWW1!Y19) | ¬¬IF(ISBLANK(DPWW1!Z19),"",DPWW1!Z19) | ¬¬IF(ISBLANK(DPWW1!AA19),"",DPWW1!AA19) | ¬¬IF(ISBLANK(DPWW1!AB19),"",DPWW1!AB19) | ¬¬IF(ISBLANK(DPWW1!AC19),"",DPWW1!AC19) | ¬¬IF(ISBLANK(DPWW1!AD19),"",DPWW1!AD19) | ¬¬IF(ISBLANK(DPWW1!AE19),"",DPWW1!AE19) | ¬¬IF(ISBLANK(DPWW1!AF19),"",DPWW1!AF19) | ¬¬IF(ISBLANK(DPWW1!AG19),"",DPWW1!AG19) | ¬¬IF(ISBLANK(DPWW1!AH19),"",DPWW1!AH19)
¬¬A101 | ¬¬IF(ISBLANK(DPWW1!BS19),"",DPWW1!BS19) | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI19),"",DPWW1!AI19) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ19),"",DPWW1!AJ19)
¬¬A102 | ¬¬IF(ISBLANK(DPWW1!BV19),"",DPWW1!BV19) | ¬¬DPWW1!F19 & "," & DPWW1!G19 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H19),"",DPWW1!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL19),"",DPWW1!AL19) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM19),"",DPWW1!AM19)
¬¬A103 | ¬¬IF(ISBLANK(DPWW1!AT20),"",DPWW1!AT20) | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J20),"",DPWW1!J20) | ¬¬IF(ISBLANK(DPWW1!K20),"",DPWW1!K20) | ¬¬IF(ISBLANK(DPWW1!L20),"",DPWW1!L20) | ¬¬IF(ISBLANK(DPWW1!M20),"",DPWW1!M20) | ¬¬IF(ISBLANK(DPWW1!N20),"",DPWW1!N20) | ¬¬IF(ISBLANK(DPWW1!O20),"",DPWW1!O20) | ¬¬IF(ISBLANK(DPWW1!P20),"",DPWW1!P20) | ¬¬IF(ISBLANK(DPWW1!Q20),"",DPWW1!Q20) | ¬¬IF(ISBLANK(DPWW1!R20),"",DPWW1!R20) | ¬¬IF(ISBLANK(DPWW1!S20),"",DPWW1!S20) | ¬¬IF(ISBLANK(DPWW1!T20),"",DPWW1!T20)
¬¬A104 | ¬¬IF(ISBLANK(DPWW1!BE20),"",DPWW1!BE20) | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U20),"",DPWW1!U20) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V20),"",DPWW1!V20)
¬¬A105 | ¬¬IF(ISBLANK(DPWW1!BH20),"",DPWW1!BH20) | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X20),"",DPWW1!X20) | ¬¬IF(ISBLANK(DPWW1!Y20),"",DPWW1!Y20) | ¬¬IF(ISBLANK(DPWW1!Z20),"",DPWW1!Z20) | ¬¬IF(ISBLANK(DPWW1!AA20),"",DPWW1!AA20) | ¬¬IF(ISBLANK(DPWW1!AB20),"",DPWW1!AB20) | ¬¬IF(ISBLANK(DPWW1!AC20),"",DPWW1!AC20) | ¬¬IF(ISBLANK(DPWW1!AD20),"",DPWW1!AD20) | ¬¬IF(ISBLANK(DPWW1!AE20),"",DPWW1!AE20) | ¬¬IF(ISBLANK(DPWW1!AF20),"",DPWW1!AF20) | ¬¬IF(ISBLANK(DPWW1!AG20),"",DPWW1!AG20) | ¬¬IF(ISBLANK(DPWW1!AH20),"",DPWW1!AH20)
¬¬A106 | ¬¬IF(ISBLANK(DPWW1!BS20),"",DPWW1!BS20) | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI20),"",DPWW1!AI20) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ20),"",DPWW1!AJ20)
¬¬A107 | ¬¬IF(ISBLANK(DPWW1!BV20),"",DPWW1!BV20) | ¬¬DPWW1!F20 & "," & DPWW1!G20 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H20),"",DPWW1!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL20),"",DPWW1!AL20) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM20),"",DPWW1!AM20)
¬¬A108 | ¬¬IF(ISBLANK(DPWW1!AT21),"",DPWW1!AT21) | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J21),"",DPWW1!J21) | ¬¬IF(ISBLANK(DPWW1!K21),"",DPWW1!K21) | ¬¬IF(ISBLANK(DPWW1!L21),"",DPWW1!L21) | ¬¬IF(ISBLANK(DPWW1!M21),"",DPWW1!M21) | ¬¬IF(ISBLANK(DPWW1!N21),"",DPWW1!N21) | ¬¬IF(ISBLANK(DPWW1!O21),"",DPWW1!O21) | ¬¬IF(ISBLANK(DPWW1!P21),"",DPWW1!P21) | ¬¬IF(ISBLANK(DPWW1!Q21),"",DPWW1!Q21) | ¬¬IF(ISBLANK(DPWW1!R21),"",DPWW1!R21) | ¬¬IF(ISBLANK(DPWW1!S21),"",DPWW1!S21) | ¬¬IF(ISBLANK(DPWW1!T21),"",DPWW1!T21)
¬¬A109 | ¬¬IF(ISBLANK(DPWW1!BE21),"",DPWW1!BE21) | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U21),"",DPWW1!U21) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V21),"",DPWW1!V21)
¬¬A110 | ¬¬IF(ISBLANK(DPWW1!BH21),"",DPWW1!BH21) | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X21),"",DPWW1!X21) | ¬¬IF(ISBLANK(DPWW1!Y21),"",DPWW1!Y21) | ¬¬IF(ISBLANK(DPWW1!Z21),"",DPWW1!Z21) | ¬¬IF(ISBLANK(DPWW1!AA21),"",DPWW1!AA21) | ¬¬IF(ISBLANK(DPWW1!AB21),"",DPWW1!AB21) | ¬¬IF(ISBLANK(DPWW1!AC21),"",DPWW1!AC21) | ¬¬IF(ISBLANK(DPWW1!AD21),"",DPWW1!AD21) | ¬¬IF(ISBLANK(DPWW1!AE21),"",DPWW1!AE21) | ¬¬IF(ISBLANK(DPWW1!AF21),"",DPWW1!AF21) | ¬¬IF(ISBLANK(DPWW1!AG21),"",DPWW1!AG21) | ¬¬IF(ISBLANK(DPWW1!AH21),"",DPWW1!AH21)
¬¬A111 | ¬¬IF(ISBLANK(DPWW1!BS21),"",DPWW1!BS21) | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI21),"",DPWW1!AI21) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ21),"",DPWW1!AJ21)
¬¬A112 | ¬¬IF(ISBLANK(DPWW1!BV21),"",DPWW1!BV21) | ¬¬DPWW1!F21 & "," & DPWW1!G21 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H21),"",DPWW1!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL21),"",DPWW1!AL21) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM21),"",DPWW1!AM21)
¬¬A113 | ¬¬IF(ISBLANK(DPWW1!AT22),"",DPWW1!AT22) | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J22),"",DPWW1!J22) | ¬¬IF(ISBLANK(DPWW1!K22),"",DPWW1!K22) | ¬¬IF(ISBLANK(DPWW1!L22),"",DPWW1!L22) | ¬¬IF(ISBLANK(DPWW1!M22),"",DPWW1!M22) | ¬¬IF(ISBLANK(DPWW1!N22),"",DPWW1!N22) | ¬¬IF(ISBLANK(DPWW1!O22),"",DPWW1!O22) | ¬¬IF(ISBLANK(DPWW1!P22),"",DPWW1!P22) | ¬¬IF(ISBLANK(DPWW1!Q22),"",DPWW1!Q22) | ¬¬IF(ISBLANK(DPWW1!R22),"",DPWW1!R22) | ¬¬IF(ISBLANK(DPWW1!S22),"",DPWW1!S22) | ¬¬IF(ISBLANK(DPWW1!T22),"",DPWW1!T22)
¬¬A114 | ¬¬IF(ISBLANK(DPWW1!BE22),"",DPWW1!BE22) | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U22),"",DPWW1!U22) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V22),"",DPWW1!V22)
¬¬A115 | ¬¬IF(ISBLANK(DPWW1!BH22),"",DPWW1!BH22) | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X22),"",DPWW1!X22) | ¬¬IF(ISBLANK(DPWW1!Y22),"",DPWW1!Y22) | ¬¬IF(ISBLANK(DPWW1!Z22),"",DPWW1!Z22) | ¬¬IF(ISBLANK(DPWW1!AA22),"",DPWW1!AA22) | ¬¬IF(ISBLANK(DPWW1!AB22),"",DPWW1!AB22) | ¬¬IF(ISBLANK(DPWW1!AC22),"",DPWW1!AC22) | ¬¬IF(ISBLANK(DPWW1!AD22),"",DPWW1!AD22) | ¬¬IF(ISBLANK(DPWW1!AE22),"",DPWW1!AE22) | ¬¬IF(ISBLANK(DPWW1!AF22),"",DPWW1!AF22) | ¬¬IF(ISBLANK(DPWW1!AG22),"",DPWW1!AG22) | ¬¬IF(ISBLANK(DPWW1!AH22),"",DPWW1!AH22)
¬¬A116 | ¬¬IF(ISBLANK(DPWW1!BS22),"",DPWW1!BS22) | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI22),"",DPWW1!AI22) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ22),"",DPWW1!AJ22)
¬¬A117 | ¬¬IF(ISBLANK(DPWW1!BV22),"",DPWW1!BV22) | ¬¬DPWW1!F22 & "," & DPWW1!G22 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H22),"",DPWW1!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL22),"",DPWW1!AL22) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM22),"",DPWW1!AM22)
¬¬A118 | ¬¬IF(ISBLANK(DPWW1!AT23),"",DPWW1!AT23) | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J23),"",DPWW1!J23) | ¬¬IF(ISBLANK(DPWW1!K23),"",DPWW1!K23) | ¬¬IF(ISBLANK(DPWW1!L23),"",DPWW1!L23) | ¬¬IF(ISBLANK(DPWW1!M23),"",DPWW1!M23) | ¬¬IF(ISBLANK(DPWW1!N23),"",DPWW1!N23) | ¬¬IF(ISBLANK(DPWW1!O23),"",DPWW1!O23) | ¬¬IF(ISBLANK(DPWW1!P23),"",DPWW1!P23) | ¬¬IF(ISBLANK(DPWW1!Q23),"",DPWW1!Q23) | ¬¬IF(ISBLANK(DPWW1!R23),"",DPWW1!R23) | ¬¬IF(ISBLANK(DPWW1!S23),"",DPWW1!S23) | ¬¬IF(ISBLANK(DPWW1!T23),"",DPWW1!T23)
¬¬A119 | ¬¬IF(ISBLANK(DPWW1!BE23),"",DPWW1!BE23) | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U23),"",DPWW1!U23) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V23),"",DPWW1!V23)
¬¬A120 | ¬¬IF(ISBLANK(DPWW1!BH23),"",DPWW1!BH23) | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X23),"",DPWW1!X23) | ¬¬IF(ISBLANK(DPWW1!Y23),"",DPWW1!Y23) | ¬¬IF(ISBLANK(DPWW1!Z23),"",DPWW1!Z23) | ¬¬IF(ISBLANK(DPWW1!AA23),"",DPWW1!AA23) | ¬¬IF(ISBLANK(DPWW1!AB23),"",DPWW1!AB23) | ¬¬IF(ISBLANK(DPWW1!AC23),"",DPWW1!AC23) | ¬¬IF(ISBLANK(DPWW1!AD23),"",DPWW1!AD23) | ¬¬IF(ISBLANK(DPWW1!AE23),"",DPWW1!AE23) | ¬¬IF(ISBLANK(DPWW1!AF23),"",DPWW1!AF23) | ¬¬IF(ISBLANK(DPWW1!AG23),"",DPWW1!AG23) | ¬¬IF(ISBLANK(DPWW1!AH23),"",DPWW1!AH23)
¬¬A121 | ¬¬IF(ISBLANK(DPWW1!BS23),"",DPWW1!BS23) | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI23),"",DPWW1!AI23) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ23),"",DPWW1!AJ23)
¬¬A122 | ¬¬IF(ISBLANK(DPWW1!BV23),"",DPWW1!BV23) | ¬¬DPWW1!F23 & "," & DPWW1!G23 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H23),"",DPWW1!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL23),"",DPWW1!AL23) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM23),"",DPWW1!AM23)
¬¬A123 | ¬¬IF(ISBLANK(DPWW1!AT24),"",DPWW1!AT24) | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J24),"",DPWW1!J24) | ¬¬IF(ISBLANK(DPWW1!K24),"",DPWW1!K24) | ¬¬IF(ISBLANK(DPWW1!L24),"",DPWW1!L24) | ¬¬IF(ISBLANK(DPWW1!M24),"",DPWW1!M24) | ¬¬IF(ISBLANK(DPWW1!N24),"",DPWW1!N24) | ¬¬IF(ISBLANK(DPWW1!O24),"",DPWW1!O24) | ¬¬IF(ISBLANK(DPWW1!P24),"",DPWW1!P24) | ¬¬IF(ISBLANK(DPWW1!Q24),"",DPWW1!Q24) | ¬¬IF(ISBLANK(DPWW1!R24),"",DPWW1!R24) | ¬¬IF(ISBLANK(DPWW1!S24),"",DPWW1!S24) | ¬¬IF(ISBLANK(DPWW1!T24),"",DPWW1!T24)
¬¬A124 | ¬¬IF(ISBLANK(DPWW1!BE24),"",DPWW1!BE24) | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U24),"",DPWW1!U24) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V24),"",DPWW1!V24)
¬¬A125 | ¬¬IF(ISBLANK(DPWW1!BH24),"",DPWW1!BH24) | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X24),"",DPWW1!X24) | ¬¬IF(ISBLANK(DPWW1!Y24),"",DPWW1!Y24) | ¬¬IF(ISBLANK(DPWW1!Z24),"",DPWW1!Z24) | ¬¬IF(ISBLANK(DPWW1!AA24),"",DPWW1!AA24) | ¬¬IF(ISBLANK(DPWW1!AB24),"",DPWW1!AB24) | ¬¬IF(ISBLANK(DPWW1!AC24),"",DPWW1!AC24) | ¬¬IF(ISBLANK(DPWW1!AD24),"",DPWW1!AD24) | ¬¬IF(ISBLANK(DPWW1!AE24),"",DPWW1!AE24) | ¬¬IF(ISBLANK(DPWW1!AF24),"",DPWW1!AF24) | ¬¬IF(ISBLANK(DPWW1!AG24),"",DPWW1!AG24) | ¬¬IF(ISBLANK(DPWW1!AH24),"",DPWW1!AH24)
¬¬A126 | ¬¬IF(ISBLANK(DPWW1!BS24),"",DPWW1!BS24) | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI24),"",DPWW1!AI24) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ24),"",DPWW1!AJ24)
¬¬A127 | ¬¬IF(ISBLANK(DPWW1!BV24),"",DPWW1!BV24) | ¬¬DPWW1!F24 & "," & DPWW1!G24 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H24),"",DPWW1!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL24),"",DPWW1!AL24) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM24),"",DPWW1!AM24)
¬¬A128 | ¬¬IF(ISBLANK(DPWW1!AT25),"",DPWW1!AT25) | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J25),"",DPWW1!J25) | ¬¬IF(ISBLANK(DPWW1!K25),"",DPWW1!K25) | ¬¬IF(ISBLANK(DPWW1!L25),"",DPWW1!L25) | ¬¬IF(ISBLANK(DPWW1!M25),"",DPWW1!M25) | ¬¬IF(ISBLANK(DPWW1!N25),"",DPWW1!N25) | ¬¬IF(ISBLANK(DPWW1!O25),"",DPWW1!O25) | ¬¬IF(ISBLANK(DPWW1!P25),"",DPWW1!P25) | ¬¬IF(ISBLANK(DPWW1!Q25),"",DPWW1!Q25) | ¬¬IF(ISBLANK(DPWW1!R25),"",DPWW1!R25) | ¬¬IF(ISBLANK(DPWW1!S25),"",DPWW1!S25) | ¬¬IF(ISBLANK(DPWW1!T25),"",DPWW1!T25)
¬¬A129 | ¬¬IF(ISBLANK(DPWW1!BE25),"",DPWW1!BE25) | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U25),"",DPWW1!U25) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V25),"",DPWW1!V25)
¬¬A130 | ¬¬IF(ISBLANK(DPWW1!BH25),"",DPWW1!BH25) | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X25),"",DPWW1!X25) | ¬¬IF(ISBLANK(DPWW1!Y25),"",DPWW1!Y25) | ¬¬IF(ISBLANK(DPWW1!Z25),"",DPWW1!Z25) | ¬¬IF(ISBLANK(DPWW1!AA25),"",DPWW1!AA25) | ¬¬IF(ISBLANK(DPWW1!AB25),"",DPWW1!AB25) | ¬¬IF(ISBLANK(DPWW1!AC25),"",DPWW1!AC25) | ¬¬IF(ISBLANK(DPWW1!AD25),"",DPWW1!AD25) | ¬¬IF(ISBLANK(DPWW1!AE25),"",DPWW1!AE25) | ¬¬IF(ISBLANK(DPWW1!AF25),"",DPWW1!AF25) | ¬¬IF(ISBLANK(DPWW1!AG25),"",DPWW1!AG25) | ¬¬IF(ISBLANK(DPWW1!AH25),"",DPWW1!AH25)
¬¬A131 | ¬¬IF(ISBLANK(DPWW1!BS25),"",DPWW1!BS25) | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI25),"",DPWW1!AI25) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ25),"",DPWW1!AJ25)
¬¬A132 | ¬¬IF(ISBLANK(DPWW1!BV25),"",DPWW1!BV25) | ¬¬DPWW1!F25 & "," & DPWW1!G25 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H25),"",DPWW1!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL25),"",DPWW1!AL25) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM25),"",DPWW1!AM25)
¬¬A133 | ¬¬IF(ISBLANK(DPWW1!AT26),"",DPWW1!AT26) | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J26),"",DPWW1!J26) | ¬¬IF(ISBLANK(DPWW1!K26),"",DPWW1!K26) | ¬¬IF(ISBLANK(DPWW1!L26),"",DPWW1!L26) | ¬¬IF(ISBLANK(DPWW1!M26),"",DPWW1!M26) | ¬¬IF(ISBLANK(DPWW1!N26),"",DPWW1!N26) | ¬¬IF(ISBLANK(DPWW1!O26),"",DPWW1!O26) | ¬¬IF(ISBLANK(DPWW1!P26),"",DPWW1!P26) | ¬¬IF(ISBLANK(DPWW1!Q26),"",DPWW1!Q26) | ¬¬IF(ISBLANK(DPWW1!R26),"",DPWW1!R26) | ¬¬IF(ISBLANK(DPWW1!S26),"",DPWW1!S26) | ¬¬IF(ISBLANK(DPWW1!T26),"",DPWW1!T26)
¬¬A134 | ¬¬IF(ISBLANK(DPWW1!BE26),"",DPWW1!BE26) | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U26),"",DPWW1!U26) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V26),"",DPWW1!V26)
¬¬A135 | ¬¬IF(ISBLANK(DPWW1!BH26),"",DPWW1!BH26) | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X26),"",DPWW1!X26) | ¬¬IF(ISBLANK(DPWW1!Y26),"",DPWW1!Y26) | ¬¬IF(ISBLANK(DPWW1!Z26),"",DPWW1!Z26) | ¬¬IF(ISBLANK(DPWW1!AA26),"",DPWW1!AA26) | ¬¬IF(ISBLANK(DPWW1!AB26),"",DPWW1!AB26) | ¬¬IF(ISBLANK(DPWW1!AC26),"",DPWW1!AC26) | ¬¬IF(ISBLANK(DPWW1!AD26),"",DPWW1!AD26) | ¬¬IF(ISBLANK(DPWW1!AE26),"",DPWW1!AE26) | ¬¬IF(ISBLANK(DPWW1!AF26),"",DPWW1!AF26) | ¬¬IF(ISBLANK(DPWW1!AG26),"",DPWW1!AG26) | ¬¬IF(ISBLANK(DPWW1!AH26),"",DPWW1!AH26)
¬¬A136 | ¬¬IF(ISBLANK(DPWW1!BS26),"",DPWW1!BS26) | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI26),"",DPWW1!AI26) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ26),"",DPWW1!AJ26)
¬¬A137 | ¬¬IF(ISBLANK(DPWW1!BV26),"",DPWW1!BV26) | ¬¬DPWW1!F26 & "," & DPWW1!G26 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H26),"",DPWW1!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL26),"",DPWW1!AL26) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM26),"",DPWW1!AM26)
¬¬A138 | ¬¬IF(ISBLANK(DPWW1!AT27),"",DPWW1!AT27) | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J27),"",DPWW1!J27) | ¬¬IF(ISBLANK(DPWW1!K27),"",DPWW1!K27) | ¬¬IF(ISBLANK(DPWW1!L27),"",DPWW1!L27) | ¬¬IF(ISBLANK(DPWW1!M27),"",DPWW1!M27) | ¬¬IF(ISBLANK(DPWW1!N27),"",DPWW1!N27) | ¬¬IF(ISBLANK(DPWW1!O27),"",DPWW1!O27) | ¬¬IF(ISBLANK(DPWW1!P27),"",DPWW1!P27) | ¬¬IF(ISBLANK(DPWW1!Q27),"",DPWW1!Q27) | ¬¬IF(ISBLANK(DPWW1!R27),"",DPWW1!R27) | ¬¬IF(ISBLANK(DPWW1!S27),"",DPWW1!S27) | ¬¬IF(ISBLANK(DPWW1!T27),"",DPWW1!T27)
¬¬A139 | ¬¬IF(ISBLANK(DPWW1!BE27),"",DPWW1!BE27) | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U27),"",DPWW1!U27) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V27),"",DPWW1!V27)
¬¬A140 | ¬¬IF(ISBLANK(DPWW1!BH27),"",DPWW1!BH27) | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X27),"",DPWW1!X27) | ¬¬IF(ISBLANK(DPWW1!Y27),"",DPWW1!Y27) | ¬¬IF(ISBLANK(DPWW1!Z27),"",DPWW1!Z27) | ¬¬IF(ISBLANK(DPWW1!AA27),"",DPWW1!AA27) | ¬¬IF(ISBLANK(DPWW1!AB27),"",DPWW1!AB27) | ¬¬IF(ISBLANK(DPWW1!AC27),"",DPWW1!AC27) | ¬¬IF(ISBLANK(DPWW1!AD27),"",DPWW1!AD27) | ¬¬IF(ISBLANK(DPWW1!AE27),"",DPWW1!AE27) | ¬¬IF(ISBLANK(DPWW1!AF27),"",DPWW1!AF27) | ¬¬IF(ISBLANK(DPWW1!AG27),"",DPWW1!AG27) | ¬¬IF(ISBLANK(DPWW1!AH27),"",DPWW1!AH27)
¬¬A141 | ¬¬IF(ISBLANK(DPWW1!BS27),"",DPWW1!BS27) | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI27),"",DPWW1!AI27) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ27),"",DPWW1!AJ27)
¬¬A142 | ¬¬IF(ISBLANK(DPWW1!BV27),"",DPWW1!BV27) | ¬¬DPWW1!F27 & "," & DPWW1!G27 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H27),"",DPWW1!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL27),"",DPWW1!AL27) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM27),"",DPWW1!AM27)
¬¬A143 | ¬¬IF(ISBLANK(DPWW1!AT28),"",DPWW1!AT28) | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J28),"",DPWW1!J28) | ¬¬IF(ISBLANK(DPWW1!K28),"",DPWW1!K28) | ¬¬IF(ISBLANK(DPWW1!L28),"",DPWW1!L28) | ¬¬IF(ISBLANK(DPWW1!M28),"",DPWW1!M28) | ¬¬IF(ISBLANK(DPWW1!N28),"",DPWW1!N28) | ¬¬IF(ISBLANK(DPWW1!O28),"",DPWW1!O28) | ¬¬IF(ISBLANK(DPWW1!P28),"",DPWW1!P28) | ¬¬IF(ISBLANK(DPWW1!Q28),"",DPWW1!Q28) | ¬¬IF(ISBLANK(DPWW1!R28),"",DPWW1!R28) | ¬¬IF(ISBLANK(DPWW1!S28),"",DPWW1!S28) | ¬¬IF(ISBLANK(DPWW1!T28),"",DPWW1!T28)
¬¬A144 | ¬¬IF(ISBLANK(DPWW1!BE28),"",DPWW1!BE28) | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U28),"",DPWW1!U28) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V28),"",DPWW1!V28)
¬¬A145 | ¬¬IF(ISBLANK(DPWW1!BH28),"",DPWW1!BH28) | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X28),"",DPWW1!X28) | ¬¬IF(ISBLANK(DPWW1!Y28),"",DPWW1!Y28) | ¬¬IF(ISBLANK(DPWW1!Z28),"",DPWW1!Z28) | ¬¬IF(ISBLANK(DPWW1!AA28),"",DPWW1!AA28) | ¬¬IF(ISBLANK(DPWW1!AB28),"",DPWW1!AB28) | ¬¬IF(ISBLANK(DPWW1!AC28),"",DPWW1!AC28) | ¬¬IF(ISBLANK(DPWW1!AD28),"",DPWW1!AD28) | ¬¬IF(ISBLANK(DPWW1!AE28),"",DPWW1!AE28) | ¬¬IF(ISBLANK(DPWW1!AF28),"",DPWW1!AF28) | ¬¬IF(ISBLANK(DPWW1!AG28),"",DPWW1!AG28) | ¬¬IF(ISBLANK(DPWW1!AH28),"",DPWW1!AH28)
¬¬A146 | ¬¬IF(ISBLANK(DPWW1!BS28),"",DPWW1!BS28) | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI28),"",DPWW1!AI28) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ28),"",DPWW1!AJ28)
¬¬A147 | ¬¬IF(ISBLANK(DPWW1!BV28),"",DPWW1!BV28) | ¬¬DPWW1!F28 & "," & DPWW1!G28 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H28),"",DPWW1!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL28),"",DPWW1!AL28) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM28),"",DPWW1!AM28)
¬¬A148 | ¬¬IF(ISBLANK(DPWW1!AT29),"",DPWW1!AT29) | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J29),"",DPWW1!J29) | ¬¬IF(ISBLANK(DPWW1!K29),"",DPWW1!K29) | ¬¬IF(ISBLANK(DPWW1!L29),"",DPWW1!L29) | ¬¬IF(ISBLANK(DPWW1!M29),"",DPWW1!M29) | ¬¬IF(ISBLANK(DPWW1!N29),"",DPWW1!N29) | ¬¬IF(ISBLANK(DPWW1!O29),"",DPWW1!O29) | ¬¬IF(ISBLANK(DPWW1!P29),"",DPWW1!P29) | ¬¬IF(ISBLANK(DPWW1!Q29),"",DPWW1!Q29) | ¬¬IF(ISBLANK(DPWW1!R29),"",DPWW1!R29) | ¬¬IF(ISBLANK(DPWW1!S29),"",DPWW1!S29) | ¬¬IF(ISBLANK(DPWW1!T29),"",DPWW1!T29)
¬¬A149 | ¬¬IF(ISBLANK(DPWW1!BE29),"",DPWW1!BE29) | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U29),"",DPWW1!U29) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V29),"",DPWW1!V29)
¬¬A150 | ¬¬IF(ISBLANK(DPWW1!BH29),"",DPWW1!BH29) | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X29),"",DPWW1!X29) | ¬¬IF(ISBLANK(DPWW1!Y29),"",DPWW1!Y29) | ¬¬IF(ISBLANK(DPWW1!Z29),"",DPWW1!Z29) | ¬¬IF(ISBLANK(DPWW1!AA29),"",DPWW1!AA29) | ¬¬IF(ISBLANK(DPWW1!AB29),"",DPWW1!AB29) | ¬¬IF(ISBLANK(DPWW1!AC29),"",DPWW1!AC29) | ¬¬IF(ISBLANK(DPWW1!AD29),"",DPWW1!AD29) | ¬¬IF(ISBLANK(DPWW1!AE29),"",DPWW1!AE29) | ¬¬IF(ISBLANK(DPWW1!AF29),"",DPWW1!AF29) | ¬¬IF(ISBLANK(DPWW1!AG29),"",DPWW1!AG29) | ¬¬IF(ISBLANK(DPWW1!AH29),"",DPWW1!AH29)
¬¬A151 | ¬¬IF(ISBLANK(DPWW1!BS29),"",DPWW1!BS29) | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI29),"",DPWW1!AI29) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ29),"",DPWW1!AJ29)
¬¬A152 | ¬¬IF(ISBLANK(DPWW1!BV29),"",DPWW1!BV29) | ¬¬DPWW1!F29 & "," & DPWW1!G29 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H29),"",DPWW1!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL29),"",DPWW1!AL29) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM29),"",DPWW1!AM29)
¬¬A153 | ¬¬IF(ISBLANK(DPWW1!AT30),"",DPWW1!AT30) | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J30),"",DPWW1!J30) | ¬¬IF(ISBLANK(DPWW1!K30),"",DPWW1!K30) | ¬¬IF(ISBLANK(DPWW1!L30),"",DPWW1!L30) | ¬¬IF(ISBLANK(DPWW1!M30),"",DPWW1!M30) | ¬¬IF(ISBLANK(DPWW1!N30),"",DPWW1!N30) | ¬¬IF(ISBLANK(DPWW1!O30),"",DPWW1!O30) | ¬¬IF(ISBLANK(DPWW1!P30),"",DPWW1!P30) | ¬¬IF(ISBLANK(DPWW1!Q30),"",DPWW1!Q30) | ¬¬IF(ISBLANK(DPWW1!R30),"",DPWW1!R30) | ¬¬IF(ISBLANK(DPWW1!S30),"",DPWW1!S30) | ¬¬IF(ISBLANK(DPWW1!T30),"",DPWW1!T30)
¬¬A154 | ¬¬IF(ISBLANK(DPWW1!BE30),"",DPWW1!BE30) | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U30),"",DPWW1!U30) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V30),"",DPWW1!V30)
¬¬A155 | ¬¬IF(ISBLANK(DPWW1!BH30),"",DPWW1!BH30) | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X30),"",DPWW1!X30) | ¬¬IF(ISBLANK(DPWW1!Y30),"",DPWW1!Y30) | ¬¬IF(ISBLANK(DPWW1!Z30),"",DPWW1!Z30) | ¬¬IF(ISBLANK(DPWW1!AA30),"",DPWW1!AA30) | ¬¬IF(ISBLANK(DPWW1!AB30),"",DPWW1!AB30) | ¬¬IF(ISBLANK(DPWW1!AC30),"",DPWW1!AC30) | ¬¬IF(ISBLANK(DPWW1!AD30),"",DPWW1!AD30) | ¬¬IF(ISBLANK(DPWW1!AE30),"",DPWW1!AE30) | ¬¬IF(ISBLANK(DPWW1!AF30),"",DPWW1!AF30) | ¬¬IF(ISBLANK(DPWW1!AG30),"",DPWW1!AG30) | ¬¬IF(ISBLANK(DPWW1!AH30),"",DPWW1!AH30)
¬¬A156 | ¬¬IF(ISBLANK(DPWW1!BS30),"",DPWW1!BS30) | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI30),"",DPWW1!AI30) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ30),"",DPWW1!AJ30)
¬¬A157 | ¬¬IF(ISBLANK(DPWW1!BV30),"",DPWW1!BV30) | ¬¬DPWW1!F30 & "," & DPWW1!G30 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H30),"",DPWW1!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL30),"",DPWW1!AL30) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM30),"",DPWW1!AM30)
¬¬A158 | ¬¬IF(ISBLANK(DPWW1!AT31),"",DPWW1!AT31) | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J31),"",DPWW1!J31) | ¬¬IF(ISBLANK(DPWW1!K31),"",DPWW1!K31) | ¬¬IF(ISBLANK(DPWW1!L31),"",DPWW1!L31) | ¬¬IF(ISBLANK(DPWW1!M31),"",DPWW1!M31) | ¬¬IF(ISBLANK(DPWW1!N31),"",DPWW1!N31) | ¬¬IF(ISBLANK(DPWW1!O31),"",DPWW1!O31) | ¬¬IF(ISBLANK(DPWW1!P31),"",DPWW1!P31) | ¬¬IF(ISBLANK(DPWW1!Q31),"",DPWW1!Q31) | ¬¬IF(ISBLANK(DPWW1!R31),"",DPWW1!R31) | ¬¬IF(ISBLANK(DPWW1!S31),"",DPWW1!S31) | ¬¬IF(ISBLANK(DPWW1!T31),"",DPWW1!T31)
¬¬A159 | ¬¬IF(ISBLANK(DPWW1!BE31),"",DPWW1!BE31) | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U31),"",DPWW1!U31) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V31),"",DPWW1!V31)
¬¬A160 | ¬¬IF(ISBLANK(DPWW1!BH31),"",DPWW1!BH31) | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X31),"",DPWW1!X31) | ¬¬IF(ISBLANK(DPWW1!Y31),"",DPWW1!Y31) | ¬¬IF(ISBLANK(DPWW1!Z31),"",DPWW1!Z31) | ¬¬IF(ISBLANK(DPWW1!AA31),"",DPWW1!AA31) | ¬¬IF(ISBLANK(DPWW1!AB31),"",DPWW1!AB31) | ¬¬IF(ISBLANK(DPWW1!AC31),"",DPWW1!AC31) | ¬¬IF(ISBLANK(DPWW1!AD31),"",DPWW1!AD31) | ¬¬IF(ISBLANK(DPWW1!AE31),"",DPWW1!AE31) | ¬¬IF(ISBLANK(DPWW1!AF31),"",DPWW1!AF31) | ¬¬IF(ISBLANK(DPWW1!AG31),"",DPWW1!AG31) | ¬¬IF(ISBLANK(DPWW1!AH31),"",DPWW1!AH31)
¬¬A161 | ¬¬IF(ISBLANK(DPWW1!BS31),"",DPWW1!BS31) | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI31),"",DPWW1!AI31) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ31),"",DPWW1!AJ31)
¬¬A162 | ¬¬IF(ISBLANK(DPWW1!BV31),"",DPWW1!BV31) | ¬¬DPWW1!F31 & "," & DPWW1!G31 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H31),"",DPWW1!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL31),"",DPWW1!AL31) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM31),"",DPWW1!AM31)
¬¬A163 | ¬¬IF(ISBLANK(DPWW1!AT32),"",DPWW1!AT32) | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J32),"",DPWW1!J32) | ¬¬IF(ISBLANK(DPWW1!K32),"",DPWW1!K32) | ¬¬IF(ISBLANK(DPWW1!L32),"",DPWW1!L32) | ¬¬IF(ISBLANK(DPWW1!M32),"",DPWW1!M32) | ¬¬IF(ISBLANK(DPWW1!N32),"",DPWW1!N32) | ¬¬IF(ISBLANK(DPWW1!O32),"",DPWW1!O32) | ¬¬IF(ISBLANK(DPWW1!P32),"",DPWW1!P32) | ¬¬IF(ISBLANK(DPWW1!Q32),"",DPWW1!Q32) | ¬¬IF(ISBLANK(DPWW1!R32),"",DPWW1!R32) | ¬¬IF(ISBLANK(DPWW1!S32),"",DPWW1!S32) | ¬¬IF(ISBLANK(DPWW1!T32),"",DPWW1!T32)
¬¬A164 | ¬¬IF(ISBLANK(DPWW1!BE32),"",DPWW1!BE32) | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U32),"",DPWW1!U32) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V32),"",DPWW1!V32)
¬¬A165 | ¬¬IF(ISBLANK(DPWW1!BH32),"",DPWW1!BH32) | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X32),"",DPWW1!X32) | ¬¬IF(ISBLANK(DPWW1!Y32),"",DPWW1!Y32) | ¬¬IF(ISBLANK(DPWW1!Z32),"",DPWW1!Z32) | ¬¬IF(ISBLANK(DPWW1!AA32),"",DPWW1!AA32) | ¬¬IF(ISBLANK(DPWW1!AB32),"",DPWW1!AB32) | ¬¬IF(ISBLANK(DPWW1!AC32),"",DPWW1!AC32) | ¬¬IF(ISBLANK(DPWW1!AD32),"",DPWW1!AD32) | ¬¬IF(ISBLANK(DPWW1!AE32),"",DPWW1!AE32) | ¬¬IF(ISBLANK(DPWW1!AF32),"",DPWW1!AF32) | ¬¬IF(ISBLANK(DPWW1!AG32),"",DPWW1!AG32) | ¬¬IF(ISBLANK(DPWW1!AH32),"",DPWW1!AH32)
¬¬A166 | ¬¬IF(ISBLANK(DPWW1!BS32),"",DPWW1!BS32) | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI32),"",DPWW1!AI32) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ32),"",DPWW1!AJ32)
¬¬A167 | ¬¬IF(ISBLANK(DPWW1!BV32),"",DPWW1!BV32) | ¬¬DPWW1!F32 & "," & DPWW1!G32 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H32),"",DPWW1!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL32),"",DPWW1!AL32) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM32),"",DPWW1!AM32)
¬¬A168 | ¬¬IF(ISBLANK(DPWW1!AT33),"",DPWW1!AT33) | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J33),"",DPWW1!J33) | ¬¬IF(ISBLANK(DPWW1!K33),"",DPWW1!K33) | ¬¬IF(ISBLANK(DPWW1!L33),"",DPWW1!L33) | ¬¬IF(ISBLANK(DPWW1!M33),"",DPWW1!M33) | ¬¬IF(ISBLANK(DPWW1!N33),"",DPWW1!N33) | ¬¬IF(ISBLANK(DPWW1!O33),"",DPWW1!O33) | ¬¬IF(ISBLANK(DPWW1!P33),"",DPWW1!P33) | ¬¬IF(ISBLANK(DPWW1!Q33),"",DPWW1!Q33) | ¬¬IF(ISBLANK(DPWW1!R33),"",DPWW1!R33) | ¬¬IF(ISBLANK(DPWW1!S33),"",DPWW1!S33) | ¬¬IF(ISBLANK(DPWW1!T33),"",DPWW1!T33)
¬¬A169 | ¬¬IF(ISBLANK(DPWW1!BE33),"",DPWW1!BE33) | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U33),"",DPWW1!U33) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V33),"",DPWW1!V33)
¬¬A170 | ¬¬IF(ISBLANK(DPWW1!BH33),"",DPWW1!BH33) | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X33),"",DPWW1!X33) | ¬¬IF(ISBLANK(DPWW1!Y33),"",DPWW1!Y33) | ¬¬IF(ISBLANK(DPWW1!Z33),"",DPWW1!Z33) | ¬¬IF(ISBLANK(DPWW1!AA33),"",DPWW1!AA33) | ¬¬IF(ISBLANK(DPWW1!AB33),"",DPWW1!AB33) | ¬¬IF(ISBLANK(DPWW1!AC33),"",DPWW1!AC33) | ¬¬IF(ISBLANK(DPWW1!AD33),"",DPWW1!AD33) | ¬¬IF(ISBLANK(DPWW1!AE33),"",DPWW1!AE33) | ¬¬IF(ISBLANK(DPWW1!AF33),"",DPWW1!AF33) | ¬¬IF(ISBLANK(DPWW1!AG33),"",DPWW1!AG33) | ¬¬IF(ISBLANK(DPWW1!AH33),"",DPWW1!AH33)
¬¬A171 | ¬¬IF(ISBLANK(DPWW1!BS33),"",DPWW1!BS33) | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI33),"",DPWW1!AI33) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ33),"",DPWW1!AJ33)
¬¬A172 | ¬¬IF(ISBLANK(DPWW1!BV33),"",DPWW1!BV33) | ¬¬DPWW1!F33 & "," & DPWW1!G33 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H33),"",DPWW1!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL33),"",DPWW1!AL33) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM33),"",DPWW1!AM33)
¬¬A173 | ¬¬IF(ISBLANK(DPWW1!AT34),"",DPWW1!AT34) | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J34),"",DPWW1!J34) | ¬¬IF(ISBLANK(DPWW1!K34),"",DPWW1!K34) | ¬¬IF(ISBLANK(DPWW1!L34),"",DPWW1!L34) | ¬¬IF(ISBLANK(DPWW1!M34),"",DPWW1!M34) | ¬¬IF(ISBLANK(DPWW1!N34),"",DPWW1!N34) | ¬¬IF(ISBLANK(DPWW1!O34),"",DPWW1!O34) | ¬¬IF(ISBLANK(DPWW1!P34),"",DPWW1!P34) | ¬¬IF(ISBLANK(DPWW1!Q34),"",DPWW1!Q34) | ¬¬IF(ISBLANK(DPWW1!R34),"",DPWW1!R34) | ¬¬IF(ISBLANK(DPWW1!S34),"",DPWW1!S34) | ¬¬IF(ISBLANK(DPWW1!T34),"",DPWW1!T34)
¬¬A174 | ¬¬IF(ISBLANK(DPWW1!BE34),"",DPWW1!BE34) | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U34),"",DPWW1!U34) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V34),"",DPWW1!V34)
¬¬A175 | ¬¬IF(ISBLANK(DPWW1!BH34),"",DPWW1!BH34) | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X34),"",DPWW1!X34) | ¬¬IF(ISBLANK(DPWW1!Y34),"",DPWW1!Y34) | ¬¬IF(ISBLANK(DPWW1!Z34),"",DPWW1!Z34) | ¬¬IF(ISBLANK(DPWW1!AA34),"",DPWW1!AA34) | ¬¬IF(ISBLANK(DPWW1!AB34),"",DPWW1!AB34) | ¬¬IF(ISBLANK(DPWW1!AC34),"",DPWW1!AC34) | ¬¬IF(ISBLANK(DPWW1!AD34),"",DPWW1!AD34) | ¬¬IF(ISBLANK(DPWW1!AE34),"",DPWW1!AE34) | ¬¬IF(ISBLANK(DPWW1!AF34),"",DPWW1!AF34) | ¬¬IF(ISBLANK(DPWW1!AG34),"",DPWW1!AG34) | ¬¬IF(ISBLANK(DPWW1!AH34),"",DPWW1!AH34)
¬¬A176 | ¬¬IF(ISBLANK(DPWW1!BS34),"",DPWW1!BS34) | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI34),"",DPWW1!AI34) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ34),"",DPWW1!AJ34)
¬¬A177 | ¬¬IF(ISBLANK(DPWW1!BV34),"",DPWW1!BV34) | ¬¬DPWW1!F34 & "," & DPWW1!G34 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H34),"",DPWW1!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL34),"",DPWW1!AL34) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM34),"",DPWW1!AM34)
¬¬A178 | ¬¬IF(ISBLANK(DPWW1!AT35),"",DPWW1!AT35) | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J35),"",DPWW1!J35) | ¬¬IF(ISBLANK(DPWW1!K35),"",DPWW1!K35) | ¬¬IF(ISBLANK(DPWW1!L35),"",DPWW1!L35) | ¬¬IF(ISBLANK(DPWW1!M35),"",DPWW1!M35) | ¬¬IF(ISBLANK(DPWW1!N35),"",DPWW1!N35) | ¬¬IF(ISBLANK(DPWW1!O35),"",DPWW1!O35) | ¬¬IF(ISBLANK(DPWW1!P35),"",DPWW1!P35) | ¬¬IF(ISBLANK(DPWW1!Q35),"",DPWW1!Q35) | ¬¬IF(ISBLANK(DPWW1!R35),"",DPWW1!R35) | ¬¬IF(ISBLANK(DPWW1!S35),"",DPWW1!S35) | ¬¬IF(ISBLANK(DPWW1!T35),"",DPWW1!T35)
¬¬A179 | ¬¬IF(ISBLANK(DPWW1!BE35),"",DPWW1!BE35) | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U35),"",DPWW1!U35) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V35),"",DPWW1!V35)
¬¬A180 | ¬¬IF(ISBLANK(DPWW1!BH35),"",DPWW1!BH35) | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X35),"",DPWW1!X35) | ¬¬IF(ISBLANK(DPWW1!Y35),"",DPWW1!Y35) | ¬¬IF(ISBLANK(DPWW1!Z35),"",DPWW1!Z35) | ¬¬IF(ISBLANK(DPWW1!AA35),"",DPWW1!AA35) | ¬¬IF(ISBLANK(DPWW1!AB35),"",DPWW1!AB35) | ¬¬IF(ISBLANK(DPWW1!AC35),"",DPWW1!AC35) | ¬¬IF(ISBLANK(DPWW1!AD35),"",DPWW1!AD35) | ¬¬IF(ISBLANK(DPWW1!AE35),"",DPWW1!AE35) | ¬¬IF(ISBLANK(DPWW1!AF35),"",DPWW1!AF35) | ¬¬IF(ISBLANK(DPWW1!AG35),"",DPWW1!AG35) | ¬¬IF(ISBLANK(DPWW1!AH35),"",DPWW1!AH35)
¬¬A181 | ¬¬IF(ISBLANK(DPWW1!BS35),"",DPWW1!BS35) | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI35),"",DPWW1!AI35) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ35),"",DPWW1!AJ35)
¬¬A182 | ¬¬IF(ISBLANK(DPWW1!BV35),"",DPWW1!BV35) | ¬¬DPWW1!F35 & "," & DPWW1!G35 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H35),"",DPWW1!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL35),"",DPWW1!AL35) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM35),"",DPWW1!AM35)
¬¬A183 | ¬¬IF(ISBLANK(DPWW1!AT36),"",DPWW1!AT36) | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J36),"",DPWW1!J36) | ¬¬IF(ISBLANK(DPWW1!K36),"",DPWW1!K36) | ¬¬IF(ISBLANK(DPWW1!L36),"",DPWW1!L36) | ¬¬IF(ISBLANK(DPWW1!M36),"",DPWW1!M36) | ¬¬IF(ISBLANK(DPWW1!N36),"",DPWW1!N36) | ¬¬IF(ISBLANK(DPWW1!O36),"",DPWW1!O36) | ¬¬IF(ISBLANK(DPWW1!P36),"",DPWW1!P36) | ¬¬IF(ISBLANK(DPWW1!Q36),"",DPWW1!Q36) | ¬¬IF(ISBLANK(DPWW1!R36),"",DPWW1!R36) | ¬¬IF(ISBLANK(DPWW1!S36),"",DPWW1!S36) | ¬¬IF(ISBLANK(DPWW1!T36),"",DPWW1!T36)
¬¬A184 | ¬¬IF(ISBLANK(DPWW1!BE36),"",DPWW1!BE36) | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U36),"",DPWW1!U36) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V36),"",DPWW1!V36)
¬¬A185 | ¬¬IF(ISBLANK(DPWW1!BH36),"",DPWW1!BH36) | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X36),"",DPWW1!X36) | ¬¬IF(ISBLANK(DPWW1!Y36),"",DPWW1!Y36) | ¬¬IF(ISBLANK(DPWW1!Z36),"",DPWW1!Z36) | ¬¬IF(ISBLANK(DPWW1!AA36),"",DPWW1!AA36) | ¬¬IF(ISBLANK(DPWW1!AB36),"",DPWW1!AB36) | ¬¬IF(ISBLANK(DPWW1!AC36),"",DPWW1!AC36) | ¬¬IF(ISBLANK(DPWW1!AD36),"",DPWW1!AD36) | ¬¬IF(ISBLANK(DPWW1!AE36),"",DPWW1!AE36) | ¬¬IF(ISBLANK(DPWW1!AF36),"",DPWW1!AF36) | ¬¬IF(ISBLANK(DPWW1!AG36),"",DPWW1!AG36) | ¬¬IF(ISBLANK(DPWW1!AH36),"",DPWW1!AH36)
¬¬A186 | ¬¬IF(ISBLANK(DPWW1!BS36),"",DPWW1!BS36) | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI36),"",DPWW1!AI36) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ36),"",DPWW1!AJ36)
¬¬A187 | ¬¬IF(ISBLANK(DPWW1!BV36),"",DPWW1!BV36) | ¬¬DPWW1!F36 & "," & DPWW1!G36 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H36),"",DPWW1!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL36),"",DPWW1!AL36) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM36),"",DPWW1!AM36)
¬¬A188 | ¬¬IF(ISBLANK(DPWW1!AT37),"",DPWW1!AT37) | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J37),"",DPWW1!J37) | ¬¬IF(ISBLANK(DPWW1!K37),"",DPWW1!K37) | ¬¬IF(ISBLANK(DPWW1!L37),"",DPWW1!L37) | ¬¬IF(ISBLANK(DPWW1!M37),"",DPWW1!M37) | ¬¬IF(ISBLANK(DPWW1!N37),"",DPWW1!N37) | ¬¬IF(ISBLANK(DPWW1!O37),"",DPWW1!O37) | ¬¬IF(ISBLANK(DPWW1!P37),"",DPWW1!P37) | ¬¬IF(ISBLANK(DPWW1!Q37),"",DPWW1!Q37) | ¬¬IF(ISBLANK(DPWW1!R37),"",DPWW1!R37) | ¬¬IF(ISBLANK(DPWW1!S37),"",DPWW1!S37) | ¬¬IF(ISBLANK(DPWW1!T37),"",DPWW1!T37)
¬¬A189 | ¬¬IF(ISBLANK(DPWW1!BE37),"",DPWW1!BE37) | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U37),"",DPWW1!U37) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V37),"",DPWW1!V37)
¬¬A190 | ¬¬IF(ISBLANK(DPWW1!BH37),"",DPWW1!BH37) | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X37),"",DPWW1!X37) | ¬¬IF(ISBLANK(DPWW1!Y37),"",DPWW1!Y37) | ¬¬IF(ISBLANK(DPWW1!Z37),"",DPWW1!Z37) | ¬¬IF(ISBLANK(DPWW1!AA37),"",DPWW1!AA37) | ¬¬IF(ISBLANK(DPWW1!AB37),"",DPWW1!AB37) | ¬¬IF(ISBLANK(DPWW1!AC37),"",DPWW1!AC37) | ¬¬IF(ISBLANK(DPWW1!AD37),"",DPWW1!AD37) | ¬¬IF(ISBLANK(DPWW1!AE37),"",DPWW1!AE37) | ¬¬IF(ISBLANK(DPWW1!AF37),"",DPWW1!AF37) | ¬¬IF(ISBLANK(DPWW1!AG37),"",DPWW1!AG37) | ¬¬IF(ISBLANK(DPWW1!AH37),"",DPWW1!AH37)
¬¬A191 | ¬¬IF(ISBLANK(DPWW1!BS37),"",DPWW1!BS37) | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI37),"",DPWW1!AI37) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ37),"",DPWW1!AJ37)
¬¬A192 | ¬¬IF(ISBLANK(DPWW1!BV37),"",DPWW1!BV37) | ¬¬DPWW1!F37 & "," & DPWW1!G37 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H37),"",DPWW1!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL37),"",DPWW1!AL37) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM37),"",DPWW1!AM37)
¬¬A193 | ¬¬IF(ISBLANK(DPWW1!AT38),"",DPWW1!AT38) | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J38),"",DPWW1!J38) | ¬¬IF(ISBLANK(DPWW1!K38),"",DPWW1!K38) | ¬¬IF(ISBLANK(DPWW1!L38),"",DPWW1!L38) | ¬¬IF(ISBLANK(DPWW1!M38),"",DPWW1!M38) | ¬¬IF(ISBLANK(DPWW1!N38),"",DPWW1!N38) | ¬¬IF(ISBLANK(DPWW1!O38),"",DPWW1!O38) | ¬¬IF(ISBLANK(DPWW1!P38),"",DPWW1!P38) | ¬¬IF(ISBLANK(DPWW1!Q38),"",DPWW1!Q38) | ¬¬IF(ISBLANK(DPWW1!R38),"",DPWW1!R38) | ¬¬IF(ISBLANK(DPWW1!S38),"",DPWW1!S38) | ¬¬IF(ISBLANK(DPWW1!T38),"",DPWW1!T38)
¬¬A194 | ¬¬IF(ISBLANK(DPWW1!BE38),"",DPWW1!BE38) | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U38),"",DPWW1!U38) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V38),"",DPWW1!V38)
¬¬A195 | ¬¬IF(ISBLANK(DPWW1!BH38),"",DPWW1!BH38) | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X38),"",DPWW1!X38) | ¬¬IF(ISBLANK(DPWW1!Y38),"",DPWW1!Y38) | ¬¬IF(ISBLANK(DPWW1!Z38),"",DPWW1!Z38) | ¬¬IF(ISBLANK(DPWW1!AA38),"",DPWW1!AA38) | ¬¬IF(ISBLANK(DPWW1!AB38),"",DPWW1!AB38) | ¬¬IF(ISBLANK(DPWW1!AC38),"",DPWW1!AC38) | ¬¬IF(ISBLANK(DPWW1!AD38),"",DPWW1!AD38) | ¬¬IF(ISBLANK(DPWW1!AE38),"",DPWW1!AE38) | ¬¬IF(ISBLANK(DPWW1!AF38),"",DPWW1!AF38) | ¬¬IF(ISBLANK(DPWW1!AG38),"",DPWW1!AG38) | ¬¬IF(ISBLANK(DPWW1!AH38),"",DPWW1!AH38)
¬¬A196 | ¬¬IF(ISBLANK(DPWW1!BS38),"",DPWW1!BS38) | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI38),"",DPWW1!AI38) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ38),"",DPWW1!AJ38)
¬¬A197 | ¬¬IF(ISBLANK(DPWW1!BV38),"",DPWW1!BV38) | ¬¬DPWW1!F38 & "," & DPWW1!G38 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H38),"",DPWW1!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL38),"",DPWW1!AL38) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM38),"",DPWW1!AM38)
¬¬A198 | ¬¬IF(ISBLANK(DPWW1!AT39),"",DPWW1!AT39) | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J39),"",DPWW1!J39) | ¬¬IF(ISBLANK(DPWW1!K39),"",DPWW1!K39) | ¬¬IF(ISBLANK(DPWW1!L39),"",DPWW1!L39) | ¬¬IF(ISBLANK(DPWW1!M39),"",DPWW1!M39) | ¬¬IF(ISBLANK(DPWW1!N39),"",DPWW1!N39) | ¬¬IF(ISBLANK(DPWW1!O39),"",DPWW1!O39) | ¬¬IF(ISBLANK(DPWW1!P39),"",DPWW1!P39) | ¬¬IF(ISBLANK(DPWW1!Q39),"",DPWW1!Q39) | ¬¬IF(ISBLANK(DPWW1!R39),"",DPWW1!R39) | ¬¬IF(ISBLANK(DPWW1!S39),"",DPWW1!S39) | ¬¬IF(ISBLANK(DPWW1!T39),"",DPWW1!T39)
¬¬A199 | ¬¬IF(ISBLANK(DPWW1!BE39),"",DPWW1!BE39) | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U39),"",DPWW1!U39) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V39),"",DPWW1!V39)
¬¬A200 | ¬¬IF(ISBLANK(DPWW1!BH39),"",DPWW1!BH39) | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X39),"",DPWW1!X39) | ¬¬IF(ISBLANK(DPWW1!Y39),"",DPWW1!Y39) | ¬¬IF(ISBLANK(DPWW1!Z39),"",DPWW1!Z39) | ¬¬IF(ISBLANK(DPWW1!AA39),"",DPWW1!AA39) | ¬¬IF(ISBLANK(DPWW1!AB39),"",DPWW1!AB39) | ¬¬IF(ISBLANK(DPWW1!AC39),"",DPWW1!AC39) | ¬¬IF(ISBLANK(DPWW1!AD39),"",DPWW1!AD39) | ¬¬IF(ISBLANK(DPWW1!AE39),"",DPWW1!AE39) | ¬¬IF(ISBLANK(DPWW1!AF39),"",DPWW1!AF39) | ¬¬IF(ISBLANK(DPWW1!AG39),"",DPWW1!AG39) | ¬¬IF(ISBLANK(DPWW1!AH39),"",DPWW1!AH39)
¬¬A201 | ¬¬IF(ISBLANK(DPWW1!BS39),"",DPWW1!BS39) | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI39),"",DPWW1!AI39) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ39),"",DPWW1!AJ39)
¬¬A202 | ¬¬IF(ISBLANK(DPWW1!BV39),"",DPWW1!BV39) | ¬¬DPWW1!F39 & "," & DPWW1!G39 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H39),"",DPWW1!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL39),"",DPWW1!AL39) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM39),"",DPWW1!AM39)
¬¬A203 | ¬¬IF(ISBLANK(DPWW1!AT40),"",DPWW1!AT40) | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J40),"",DPWW1!J40) | ¬¬IF(ISBLANK(DPWW1!K40),"",DPWW1!K40) | ¬¬IF(ISBLANK(DPWW1!L40),"",DPWW1!L40) | ¬¬IF(ISBLANK(DPWW1!M40),"",DPWW1!M40) | ¬¬IF(ISBLANK(DPWW1!N40),"",DPWW1!N40) | ¬¬IF(ISBLANK(DPWW1!O40),"",DPWW1!O40) | ¬¬IF(ISBLANK(DPWW1!P40),"",DPWW1!P40) | ¬¬IF(ISBLANK(DPWW1!Q40),"",DPWW1!Q40) | ¬¬IF(ISBLANK(DPWW1!R40),"",DPWW1!R40) | ¬¬IF(ISBLANK(DPWW1!S40),"",DPWW1!S40) | ¬¬IF(ISBLANK(DPWW1!T40),"",DPWW1!T40)
¬¬A204 | ¬¬IF(ISBLANK(DPWW1!BE40),"",DPWW1!BE40) | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U40),"",DPWW1!U40) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V40),"",DPWW1!V40)
¬¬A205 | ¬¬IF(ISBLANK(DPWW1!BH40),"",DPWW1!BH40) | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X40),"",DPWW1!X40) | ¬¬IF(ISBLANK(DPWW1!Y40),"",DPWW1!Y40) | ¬¬IF(ISBLANK(DPWW1!Z40),"",DPWW1!Z40) | ¬¬IF(ISBLANK(DPWW1!AA40),"",DPWW1!AA40) | ¬¬IF(ISBLANK(DPWW1!AB40),"",DPWW1!AB40) | ¬¬IF(ISBLANK(DPWW1!AC40),"",DPWW1!AC40) | ¬¬IF(ISBLANK(DPWW1!AD40),"",DPWW1!AD40) | ¬¬IF(ISBLANK(DPWW1!AE40),"",DPWW1!AE40) | ¬¬IF(ISBLANK(DPWW1!AF40),"",DPWW1!AF40) | ¬¬IF(ISBLANK(DPWW1!AG40),"",DPWW1!AG40) | ¬¬IF(ISBLANK(DPWW1!AH40),"",DPWW1!AH40)
¬¬A206 | ¬¬IF(ISBLANK(DPWW1!BS40),"",DPWW1!BS40) | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI40),"",DPWW1!AI40) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ40),"",DPWW1!AJ40)
¬¬A207 | ¬¬IF(ISBLANK(DPWW1!BV40),"",DPWW1!BV40) | ¬¬DPWW1!F40 & "," & DPWW1!G40 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H40),"",DPWW1!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL40),"",DPWW1!AL40) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM40),"",DPWW1!AM40)
¬¬A208 | ¬¬IF(ISBLANK(DPWW1!AT41),"",DPWW1!AT41) | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J41),"",DPWW1!J41) | ¬¬IF(ISBLANK(DPWW1!K41),"",DPWW1!K41) | ¬¬IF(ISBLANK(DPWW1!L41),"",DPWW1!L41) | ¬¬IF(ISBLANK(DPWW1!M41),"",DPWW1!M41) | ¬¬IF(ISBLANK(DPWW1!N41),"",DPWW1!N41) | ¬¬IF(ISBLANK(DPWW1!O41),"",DPWW1!O41) | ¬¬IF(ISBLANK(DPWW1!P41),"",DPWW1!P41) | ¬¬IF(ISBLANK(DPWW1!Q41),"",DPWW1!Q41) | ¬¬IF(ISBLANK(DPWW1!R41),"",DPWW1!R41) | ¬¬IF(ISBLANK(DPWW1!S41),"",DPWW1!S41) | ¬¬IF(ISBLANK(DPWW1!T41),"",DPWW1!T41)
¬¬A209 | ¬¬IF(ISBLANK(DPWW1!BE41),"",DPWW1!BE41) | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U41),"",DPWW1!U41) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V41),"",DPWW1!V41)
¬¬A210 | ¬¬IF(ISBLANK(DPWW1!BH41),"",DPWW1!BH41) | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X41),"",DPWW1!X41) | ¬¬IF(ISBLANK(DPWW1!Y41),"",DPWW1!Y41) | ¬¬IF(ISBLANK(DPWW1!Z41),"",DPWW1!Z41) | ¬¬IF(ISBLANK(DPWW1!AA41),"",DPWW1!AA41) | ¬¬IF(ISBLANK(DPWW1!AB41),"",DPWW1!AB41) | ¬¬IF(ISBLANK(DPWW1!AC41),"",DPWW1!AC41) | ¬¬IF(ISBLANK(DPWW1!AD41),"",DPWW1!AD41) | ¬¬IF(ISBLANK(DPWW1!AE41),"",DPWW1!AE41) | ¬¬IF(ISBLANK(DPWW1!AF41),"",DPWW1!AF41) | ¬¬IF(ISBLANK(DPWW1!AG41),"",DPWW1!AG41) | ¬¬IF(ISBLANK(DPWW1!AH41),"",DPWW1!AH41)
¬¬A211 | ¬¬IF(ISBLANK(DPWW1!BS41),"",DPWW1!BS41) | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI41),"",DPWW1!AI41) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ41),"",DPWW1!AJ41)
¬¬A212 | ¬¬IF(ISBLANK(DPWW1!BV41),"",DPWW1!BV41) | ¬¬DPWW1!F41 & "," & DPWW1!G41 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H41),"",DPWW1!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL41),"",DPWW1!AL41) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM41),"",DPWW1!AM41)
¬¬A213 | ¬¬IF(ISBLANK(DPWW1!AT42),"",DPWW1!AT42) | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J42),"",DPWW1!J42) | ¬¬IF(ISBLANK(DPWW1!K42),"",DPWW1!K42) | ¬¬IF(ISBLANK(DPWW1!L42),"",DPWW1!L42) | ¬¬IF(ISBLANK(DPWW1!M42),"",DPWW1!M42) | ¬¬IF(ISBLANK(DPWW1!N42),"",DPWW1!N42) | ¬¬IF(ISBLANK(DPWW1!O42),"",DPWW1!O42) | ¬¬IF(ISBLANK(DPWW1!P42),"",DPWW1!P42) | ¬¬IF(ISBLANK(DPWW1!Q42),"",DPWW1!Q42) | ¬¬IF(ISBLANK(DPWW1!R42),"",DPWW1!R42) | ¬¬IF(ISBLANK(DPWW1!S42),"",DPWW1!S42) | ¬¬IF(ISBLANK(DPWW1!T42),"",DPWW1!T42)
¬¬A214 | ¬¬IF(ISBLANK(DPWW1!BE42),"",DPWW1!BE42) | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U42),"",DPWW1!U42) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V42),"",DPWW1!V42)
¬¬A215 | ¬¬IF(ISBLANK(DPWW1!BH42),"",DPWW1!BH42) | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X42),"",DPWW1!X42) | ¬¬IF(ISBLANK(DPWW1!Y42),"",DPWW1!Y42) | ¬¬IF(ISBLANK(DPWW1!Z42),"",DPWW1!Z42) | ¬¬IF(ISBLANK(DPWW1!AA42),"",DPWW1!AA42) | ¬¬IF(ISBLANK(DPWW1!AB42),"",DPWW1!AB42) | ¬¬IF(ISBLANK(DPWW1!AC42),"",DPWW1!AC42) | ¬¬IF(ISBLANK(DPWW1!AD42),"",DPWW1!AD42) | ¬¬IF(ISBLANK(DPWW1!AE42),"",DPWW1!AE42) | ¬¬IF(ISBLANK(DPWW1!AF42),"",DPWW1!AF42) | ¬¬IF(ISBLANK(DPWW1!AG42),"",DPWW1!AG42) | ¬¬IF(ISBLANK(DPWW1!AH42),"",DPWW1!AH42)
¬¬A216 | ¬¬IF(ISBLANK(DPWW1!BS42),"",DPWW1!BS42) | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI42),"",DPWW1!AI42) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ42),"",DPWW1!AJ42)
¬¬A217 | ¬¬IF(ISBLANK(DPWW1!BV42),"",DPWW1!BV42) | ¬¬DPWW1!F42 & "," & DPWW1!G42 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H42),"",DPWW1!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL42),"",DPWW1!AL42) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM42),"",DPWW1!AM42)
¬¬A218 | ¬¬IF(ISBLANK(DPWW1!AT43),"",DPWW1!AT43) | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J43),"",DPWW1!J43) | ¬¬IF(ISBLANK(DPWW1!K43),"",DPWW1!K43) | ¬¬IF(ISBLANK(DPWW1!L43),"",DPWW1!L43) | ¬¬IF(ISBLANK(DPWW1!M43),"",DPWW1!M43) | ¬¬IF(ISBLANK(DPWW1!N43),"",DPWW1!N43) | ¬¬IF(ISBLANK(DPWW1!O43),"",DPWW1!O43) | ¬¬IF(ISBLANK(DPWW1!P43),"",DPWW1!P43) | ¬¬IF(ISBLANK(DPWW1!Q43),"",DPWW1!Q43) | ¬¬IF(ISBLANK(DPWW1!R43),"",DPWW1!R43) | ¬¬IF(ISBLANK(DPWW1!S43),"",DPWW1!S43) | ¬¬IF(ISBLANK(DPWW1!T43),"",DPWW1!T43)
¬¬A219 | ¬¬IF(ISBLANK(DPWW1!BE43),"",DPWW1!BE43) | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U43),"",DPWW1!U43) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V43),"",DPWW1!V43)
¬¬A220 | ¬¬IF(ISBLANK(DPWW1!BH43),"",DPWW1!BH43) | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X43),"",DPWW1!X43) | ¬¬IF(ISBLANK(DPWW1!Y43),"",DPWW1!Y43) | ¬¬IF(ISBLANK(DPWW1!Z43),"",DPWW1!Z43) | ¬¬IF(ISBLANK(DPWW1!AA43),"",DPWW1!AA43) | ¬¬IF(ISBLANK(DPWW1!AB43),"",DPWW1!AB43) | ¬¬IF(ISBLANK(DPWW1!AC43),"",DPWW1!AC43) | ¬¬IF(ISBLANK(DPWW1!AD43),"",DPWW1!AD43) | ¬¬IF(ISBLANK(DPWW1!AE43),"",DPWW1!AE43) | ¬¬IF(ISBLANK(DPWW1!AF43),"",DPWW1!AF43) | ¬¬IF(ISBLANK(DPWW1!AG43),"",DPWW1!AG43) | ¬¬IF(ISBLANK(DPWW1!AH43),"",DPWW1!AH43)
¬¬A221 | ¬¬IF(ISBLANK(DPWW1!BS43),"",DPWW1!BS43) | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI43),"",DPWW1!AI43) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ43),"",DPWW1!AJ43)
¬¬A222 | ¬¬IF(ISBLANK(DPWW1!BV43),"",DPWW1!BV43) | ¬¬DPWW1!F43 & "," & DPWW1!G43 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H43),"",DPWW1!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL43),"",DPWW1!AL43) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM43),"",DPWW1!AM43)
¬¬A223 | ¬¬IF(ISBLANK(DPWW1!AT44),"",DPWW1!AT44) | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J44),"",DPWW1!J44) | ¬¬IF(ISBLANK(DPWW1!K44),"",DPWW1!K44) | ¬¬IF(ISBLANK(DPWW1!L44),"",DPWW1!L44) | ¬¬IF(ISBLANK(DPWW1!M44),"",DPWW1!M44) | ¬¬IF(ISBLANK(DPWW1!N44),"",DPWW1!N44) | ¬¬IF(ISBLANK(DPWW1!O44),"",DPWW1!O44) | ¬¬IF(ISBLANK(DPWW1!P44),"",DPWW1!P44) | ¬¬IF(ISBLANK(DPWW1!Q44),"",DPWW1!Q44) | ¬¬IF(ISBLANK(DPWW1!R44),"",DPWW1!R44) | ¬¬IF(ISBLANK(DPWW1!S44),"",DPWW1!S44) | ¬¬IF(ISBLANK(DPWW1!T44),"",DPWW1!T44)
¬¬A224 | ¬¬IF(ISBLANK(DPWW1!BE44),"",DPWW1!BE44) | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U44),"",DPWW1!U44) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V44),"",DPWW1!V44)
¬¬A225 | ¬¬IF(ISBLANK(DPWW1!BH44),"",DPWW1!BH44) | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X44),"",DPWW1!X44) | ¬¬IF(ISBLANK(DPWW1!Y44),"",DPWW1!Y44) | ¬¬IF(ISBLANK(DPWW1!Z44),"",DPWW1!Z44) | ¬¬IF(ISBLANK(DPWW1!AA44),"",DPWW1!AA44) | ¬¬IF(ISBLANK(DPWW1!AB44),"",DPWW1!AB44) | ¬¬IF(ISBLANK(DPWW1!AC44),"",DPWW1!AC44) | ¬¬IF(ISBLANK(DPWW1!AD44),"",DPWW1!AD44) | ¬¬IF(ISBLANK(DPWW1!AE44),"",DPWW1!AE44) | ¬¬IF(ISBLANK(DPWW1!AF44),"",DPWW1!AF44) | ¬¬IF(ISBLANK(DPWW1!AG44),"",DPWW1!AG44) | ¬¬IF(ISBLANK(DPWW1!AH44),"",DPWW1!AH44)
¬¬A226 | ¬¬IF(ISBLANK(DPWW1!BS44),"",DPWW1!BS44) | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI44),"",DPWW1!AI44) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ44),"",DPWW1!AJ44)
¬¬A227 | ¬¬IF(ISBLANK(DPWW1!BV44),"",DPWW1!BV44) | ¬¬DPWW1!F44 & "," & DPWW1!G44 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H44),"",DPWW1!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL44),"",DPWW1!AL44) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM44),"",DPWW1!AM44)
¬¬A228 | ¬¬IF(ISBLANK(DPWW1!AT45),"",DPWW1!AT45) | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J45),"",DPWW1!J45) | ¬¬IF(ISBLANK(DPWW1!K45),"",DPWW1!K45) | ¬¬IF(ISBLANK(DPWW1!L45),"",DPWW1!L45) | ¬¬IF(ISBLANK(DPWW1!M45),"",DPWW1!M45) | ¬¬IF(ISBLANK(DPWW1!N45),"",DPWW1!N45) | ¬¬IF(ISBLANK(DPWW1!O45),"",DPWW1!O45) | ¬¬IF(ISBLANK(DPWW1!P45),"",DPWW1!P45) | ¬¬IF(ISBLANK(DPWW1!Q45),"",DPWW1!Q45) | ¬¬IF(ISBLANK(DPWW1!R45),"",DPWW1!R45) | ¬¬IF(ISBLANK(DPWW1!S45),"",DPWW1!S45) | ¬¬IF(ISBLANK(DPWW1!T45),"",DPWW1!T45)
¬¬A229 | ¬¬IF(ISBLANK(DPWW1!BE45),"",DPWW1!BE45) | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U45),"",DPWW1!U45) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V45),"",DPWW1!V45)
¬¬A230 | ¬¬IF(ISBLANK(DPWW1!BH45),"",DPWW1!BH45) | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X45),"",DPWW1!X45) | ¬¬IF(ISBLANK(DPWW1!Y45),"",DPWW1!Y45) | ¬¬IF(ISBLANK(DPWW1!Z45),"",DPWW1!Z45) | ¬¬IF(ISBLANK(DPWW1!AA45),"",DPWW1!AA45) | ¬¬IF(ISBLANK(DPWW1!AB45),"",DPWW1!AB45) | ¬¬IF(ISBLANK(DPWW1!AC45),"",DPWW1!AC45) | ¬¬IF(ISBLANK(DPWW1!AD45),"",DPWW1!AD45) | ¬¬IF(ISBLANK(DPWW1!AE45),"",DPWW1!AE45) | ¬¬IF(ISBLANK(DPWW1!AF45),"",DPWW1!AF45) | ¬¬IF(ISBLANK(DPWW1!AG45),"",DPWW1!AG45) | ¬¬IF(ISBLANK(DPWW1!AH45),"",DPWW1!AH45)
¬¬A231 | ¬¬IF(ISBLANK(DPWW1!BS45),"",DPWW1!BS45) | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI45),"",DPWW1!AI45) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ45),"",DPWW1!AJ45)
¬¬A232 | ¬¬IF(ISBLANK(DPWW1!BV45),"",DPWW1!BV45) | ¬¬DPWW1!F45 & "," & DPWW1!G45 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H45),"",DPWW1!H45) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL45),"",DPWW1!AL45) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM45),"",DPWW1!AM45)
¬¬A233 | ¬¬IF(ISBLANK(DPWW1!AT46),"",DPWW1!AT46) | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J46),"",DPWW1!J46) | ¬¬IF(ISBLANK(DPWW1!K46),"",DPWW1!K46) | ¬¬IF(ISBLANK(DPWW1!L46),"",DPWW1!L46) | ¬¬IF(ISBLANK(DPWW1!M46),"",DPWW1!M46) | ¬¬IF(ISBLANK(DPWW1!N46),"",DPWW1!N46) | ¬¬IF(ISBLANK(DPWW1!O46),"",DPWW1!O46) | ¬¬IF(ISBLANK(DPWW1!P46),"",DPWW1!P46) | ¬¬IF(ISBLANK(DPWW1!Q46),"",DPWW1!Q46) | ¬¬IF(ISBLANK(DPWW1!R46),"",DPWW1!R46) | ¬¬IF(ISBLANK(DPWW1!S46),"",DPWW1!S46) | ¬¬IF(ISBLANK(DPWW1!T46),"",DPWW1!T46)
¬¬A234 | ¬¬IF(ISBLANK(DPWW1!BE46),"",DPWW1!BE46) | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U46),"",DPWW1!U46) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V46),"",DPWW1!V46)
¬¬A235 | ¬¬IF(ISBLANK(DPWW1!BH46),"",DPWW1!BH46) | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X46),"",DPWW1!X46) | ¬¬IF(ISBLANK(DPWW1!Y46),"",DPWW1!Y46) | ¬¬IF(ISBLANK(DPWW1!Z46),"",DPWW1!Z46) | ¬¬IF(ISBLANK(DPWW1!AA46),"",DPWW1!AA46) | ¬¬IF(ISBLANK(DPWW1!AB46),"",DPWW1!AB46) | ¬¬IF(ISBLANK(DPWW1!AC46),"",DPWW1!AC46) | ¬¬IF(ISBLANK(DPWW1!AD46),"",DPWW1!AD46) | ¬¬IF(ISBLANK(DPWW1!AE46),"",DPWW1!AE46) | ¬¬IF(ISBLANK(DPWW1!AF46),"",DPWW1!AF46) | ¬¬IF(ISBLANK(DPWW1!AG46),"",DPWW1!AG46) | ¬¬IF(ISBLANK(DPWW1!AH46),"",DPWW1!AH46)
¬¬A236 | ¬¬IF(ISBLANK(DPWW1!BS46),"",DPWW1!BS46) | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI46),"",DPWW1!AI46) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ46),"",DPWW1!AJ46)
¬¬A237 | ¬¬IF(ISBLANK(DPWW1!BV46),"",DPWW1!BV46) | ¬¬DPWW1!F46 & "," & DPWW1!G46 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H46),"",DPWW1!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL46),"",DPWW1!AL46) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM46),"",DPWW1!AM46)
¬¬A238 | ¬¬IF(ISBLANK(DPWW1!AT47),"",DPWW1!AT47) | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J47),"",DPWW1!J47) | ¬¬IF(ISBLANK(DPWW1!K47),"",DPWW1!K47) | ¬¬IF(ISBLANK(DPWW1!L47),"",DPWW1!L47) | ¬¬IF(ISBLANK(DPWW1!M47),"",DPWW1!M47) | ¬¬IF(ISBLANK(DPWW1!N47),"",DPWW1!N47) | ¬¬IF(ISBLANK(DPWW1!O47),"",DPWW1!O47) | ¬¬IF(ISBLANK(DPWW1!P47),"",DPWW1!P47) | ¬¬IF(ISBLANK(DPWW1!Q47),"",DPWW1!Q47) | ¬¬IF(ISBLANK(DPWW1!R47),"",DPWW1!R47) | ¬¬IF(ISBLANK(DPWW1!S47),"",DPWW1!S47) | ¬¬IF(ISBLANK(DPWW1!T47),"",DPWW1!T47)
¬¬A239 | ¬¬IF(ISBLANK(DPWW1!BE47),"",DPWW1!BE47) | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U47),"",DPWW1!U47) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V47),"",DPWW1!V47)
¬¬A240 | ¬¬IF(ISBLANK(DPWW1!BH47),"",DPWW1!BH47) | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X47),"",DPWW1!X47) | ¬¬IF(ISBLANK(DPWW1!Y47),"",DPWW1!Y47) | ¬¬IF(ISBLANK(DPWW1!Z47),"",DPWW1!Z47) | ¬¬IF(ISBLANK(DPWW1!AA47),"",DPWW1!AA47) | ¬¬IF(ISBLANK(DPWW1!AB47),"",DPWW1!AB47) | ¬¬IF(ISBLANK(DPWW1!AC47),"",DPWW1!AC47) | ¬¬IF(ISBLANK(DPWW1!AD47),"",DPWW1!AD47) | ¬¬IF(ISBLANK(DPWW1!AE47),"",DPWW1!AE47) | ¬¬IF(ISBLANK(DPWW1!AF47),"",DPWW1!AF47) | ¬¬IF(ISBLANK(DPWW1!AG47),"",DPWW1!AG47) | ¬¬IF(ISBLANK(DPWW1!AH47),"",DPWW1!AH47)
¬¬A241 | ¬¬IF(ISBLANK(DPWW1!BS47),"",DPWW1!BS47) | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI47),"",DPWW1!AI47) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ47),"",DPWW1!AJ47)
¬¬A242 | ¬¬IF(ISBLANK(DPWW1!BV47),"",DPWW1!BV47) | ¬¬DPWW1!F47 & "," & DPWW1!G47 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H47),"",DPWW1!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL47),"",DPWW1!AL47) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM47),"",DPWW1!AM47)
¬¬A243 | ¬¬IF(ISBLANK(DPWW1!AT48),"",DPWW1!AT48) | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J48),"",DPWW1!J48) | ¬¬IF(ISBLANK(DPWW1!K48),"",DPWW1!K48) | ¬¬IF(ISBLANK(DPWW1!L48),"",DPWW1!L48) | ¬¬IF(ISBLANK(DPWW1!M48),"",DPWW1!M48) | ¬¬IF(ISBLANK(DPWW1!N48),"",DPWW1!N48) | ¬¬IF(ISBLANK(DPWW1!O48),"",DPWW1!O48) | ¬¬IF(ISBLANK(DPWW1!P48),"",DPWW1!P48) | ¬¬IF(ISBLANK(DPWW1!Q48),"",DPWW1!Q48) | ¬¬IF(ISBLANK(DPWW1!R48),"",DPWW1!R48) | ¬¬IF(ISBLANK(DPWW1!S48),"",DPWW1!S48) | ¬¬IF(ISBLANK(DPWW1!T48),"",DPWW1!T48)
¬¬A244 | ¬¬IF(ISBLANK(DPWW1!BE48),"",DPWW1!BE48) | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U48),"",DPWW1!U48) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V48),"",DPWW1!V48)
¬¬A245 | ¬¬IF(ISBLANK(DPWW1!BH48),"",DPWW1!BH48) | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X48),"",DPWW1!X48) | ¬¬IF(ISBLANK(DPWW1!Y48),"",DPWW1!Y48) | ¬¬IF(ISBLANK(DPWW1!Z48),"",DPWW1!Z48) | ¬¬IF(ISBLANK(DPWW1!AA48),"",DPWW1!AA48) | ¬¬IF(ISBLANK(DPWW1!AB48),"",DPWW1!AB48) | ¬¬IF(ISBLANK(DPWW1!AC48),"",DPWW1!AC48) | ¬¬IF(ISBLANK(DPWW1!AD48),"",DPWW1!AD48) | ¬¬IF(ISBLANK(DPWW1!AE48),"",DPWW1!AE48) | ¬¬IF(ISBLANK(DPWW1!AF48),"",DPWW1!AF48) | ¬¬IF(ISBLANK(DPWW1!AG48),"",DPWW1!AG48) | ¬¬IF(ISBLANK(DPWW1!AH48),"",DPWW1!AH48)
¬¬A246 | ¬¬IF(ISBLANK(DPWW1!BS48),"",DPWW1!BS48) | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI48),"",DPWW1!AI48) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ48),"",DPWW1!AJ48)
¬¬A247 | ¬¬IF(ISBLANK(DPWW1!BV48),"",DPWW1!BV48) | ¬¬DPWW1!F48 & "," & DPWW1!G48 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H48),"",DPWW1!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL48),"",DPWW1!AL48) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM48),"",DPWW1!AM48)
¬¬A248 | ¬¬IF(ISBLANK(DPWW1!AT49),"",DPWW1!AT49) | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J49),"",DPWW1!J49) | ¬¬IF(ISBLANK(DPWW1!K49),"",DPWW1!K49) | ¬¬IF(ISBLANK(DPWW1!L49),"",DPWW1!L49) | ¬¬IF(ISBLANK(DPWW1!M49),"",DPWW1!M49) | ¬¬IF(ISBLANK(DPWW1!N49),"",DPWW1!N49) | ¬¬IF(ISBLANK(DPWW1!O49),"",DPWW1!O49) | ¬¬IF(ISBLANK(DPWW1!P49),"",DPWW1!P49) | ¬¬IF(ISBLANK(DPWW1!Q49),"",DPWW1!Q49) | ¬¬IF(ISBLANK(DPWW1!R49),"",DPWW1!R49) | ¬¬IF(ISBLANK(DPWW1!S49),"",DPWW1!S49) | ¬¬IF(ISBLANK(DPWW1!T49),"",DPWW1!T49)
¬¬A249 | ¬¬IF(ISBLANK(DPWW1!BE49),"",DPWW1!BE49) | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U49),"",DPWW1!U49) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V49),"",DPWW1!V49)
¬¬A250 | ¬¬IF(ISBLANK(DPWW1!BH49),"",DPWW1!BH49) | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X49),"",DPWW1!X49) | ¬¬IF(ISBLANK(DPWW1!Y49),"",DPWW1!Y49) | ¬¬IF(ISBLANK(DPWW1!Z49),"",DPWW1!Z49) | ¬¬IF(ISBLANK(DPWW1!AA49),"",DPWW1!AA49) | ¬¬IF(ISBLANK(DPWW1!AB49),"",DPWW1!AB49) | ¬¬IF(ISBLANK(DPWW1!AC49),"",DPWW1!AC49) | ¬¬IF(ISBLANK(DPWW1!AD49),"",DPWW1!AD49) | ¬¬IF(ISBLANK(DPWW1!AE49),"",DPWW1!AE49) | ¬¬IF(ISBLANK(DPWW1!AF49),"",DPWW1!AF49) | ¬¬IF(ISBLANK(DPWW1!AG49),"",DPWW1!AG49) | ¬¬IF(ISBLANK(DPWW1!AH49),"",DPWW1!AH49)
¬¬A251 | ¬¬IF(ISBLANK(DPWW1!BS49),"",DPWW1!BS49) | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI49),"",DPWW1!AI49) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ49),"",DPWW1!AJ49)
¬¬A252 | ¬¬IF(ISBLANK(DPWW1!BV49),"",DPWW1!BV49) | ¬¬DPWW1!F49 & "," & DPWW1!G49 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H49),"",DPWW1!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL49),"",DPWW1!AL49) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM49),"",DPWW1!AM49)
¬¬A253 | ¬¬IF(ISBLANK(DPWW1!AT50),"",DPWW1!AT50) | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J50),"",DPWW1!J50) | ¬¬IF(ISBLANK(DPWW1!K50),"",DPWW1!K50) | ¬¬IF(ISBLANK(DPWW1!L50),"",DPWW1!L50) | ¬¬IF(ISBLANK(DPWW1!M50),"",DPWW1!M50) | ¬¬IF(ISBLANK(DPWW1!N50),"",DPWW1!N50) | ¬¬IF(ISBLANK(DPWW1!O50),"",DPWW1!O50) | ¬¬IF(ISBLANK(DPWW1!P50),"",DPWW1!P50) | ¬¬IF(ISBLANK(DPWW1!Q50),"",DPWW1!Q50) | ¬¬IF(ISBLANK(DPWW1!R50),"",DPWW1!R50) | ¬¬IF(ISBLANK(DPWW1!S50),"",DPWW1!S50) | ¬¬IF(ISBLANK(DPWW1!T50),"",DPWW1!T50)
¬¬A254 | ¬¬IF(ISBLANK(DPWW1!BE50),"",DPWW1!BE50) | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U50),"",DPWW1!U50) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V50),"",DPWW1!V50)
¬¬A255 | ¬¬IF(ISBLANK(DPWW1!BH50),"",DPWW1!BH50) | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X50),"",DPWW1!X50) | ¬¬IF(ISBLANK(DPWW1!Y50),"",DPWW1!Y50) | ¬¬IF(ISBLANK(DPWW1!Z50),"",DPWW1!Z50) | ¬¬IF(ISBLANK(DPWW1!AA50),"",DPWW1!AA50) | ¬¬IF(ISBLANK(DPWW1!AB50),"",DPWW1!AB50) | ¬¬IF(ISBLANK(DPWW1!AC50),"",DPWW1!AC50) | ¬¬IF(ISBLANK(DPWW1!AD50),"",DPWW1!AD50) | ¬¬IF(ISBLANK(DPWW1!AE50),"",DPWW1!AE50) | ¬¬IF(ISBLANK(DPWW1!AF50),"",DPWW1!AF50) | ¬¬IF(ISBLANK(DPWW1!AG50),"",DPWW1!AG50) | ¬¬IF(ISBLANK(DPWW1!AH50),"",DPWW1!AH50)
¬¬A256 | ¬¬IF(ISBLANK(DPWW1!BS50),"",DPWW1!BS50) | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI50),"",DPWW1!AI50) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ50),"",DPWW1!AJ50)
¬¬A257 | ¬¬IF(ISBLANK(DPWW1!BV50),"",DPWW1!BV50) | ¬¬DPWW1!F50 & "," & DPWW1!G50 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H50),"",DPWW1!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL50),"",DPWW1!AL50) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM50),"",DPWW1!AM50)
¬¬A258 | ¬¬IF(ISBLANK(DPWW1!AT51),"",DPWW1!AT51) | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J51),"",DPWW1!J51) | ¬¬IF(ISBLANK(DPWW1!K51),"",DPWW1!K51) | ¬¬IF(ISBLANK(DPWW1!L51),"",DPWW1!L51) | ¬¬IF(ISBLANK(DPWW1!M51),"",DPWW1!M51) | ¬¬IF(ISBLANK(DPWW1!N51),"",DPWW1!N51) | ¬¬IF(ISBLANK(DPWW1!O51),"",DPWW1!O51) | ¬¬IF(ISBLANK(DPWW1!P51),"",DPWW1!P51) | ¬¬IF(ISBLANK(DPWW1!Q51),"",DPWW1!Q51) | ¬¬IF(ISBLANK(DPWW1!R51),"",DPWW1!R51) | ¬¬IF(ISBLANK(DPWW1!S51),"",DPWW1!S51) | ¬¬IF(ISBLANK(DPWW1!T51),"",DPWW1!T51)
¬¬A259 | ¬¬IF(ISBLANK(DPWW1!BE51),"",DPWW1!BE51) | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U51),"",DPWW1!U51) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V51),"",DPWW1!V51)
¬¬A260 | ¬¬IF(ISBLANK(DPWW1!BH51),"",DPWW1!BH51) | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X51),"",DPWW1!X51) | ¬¬IF(ISBLANK(DPWW1!Y51),"",DPWW1!Y51) | ¬¬IF(ISBLANK(DPWW1!Z51),"",DPWW1!Z51) | ¬¬IF(ISBLANK(DPWW1!AA51),"",DPWW1!AA51) | ¬¬IF(ISBLANK(DPWW1!AB51),"",DPWW1!AB51) | ¬¬IF(ISBLANK(DPWW1!AC51),"",DPWW1!AC51) | ¬¬IF(ISBLANK(DPWW1!AD51),"",DPWW1!AD51) | ¬¬IF(ISBLANK(DPWW1!AE51),"",DPWW1!AE51) | ¬¬IF(ISBLANK(DPWW1!AF51),"",DPWW1!AF51) | ¬¬IF(ISBLANK(DPWW1!AG51),"",DPWW1!AG51) | ¬¬IF(ISBLANK(DPWW1!AH51),"",DPWW1!AH51)
¬¬A261 | ¬¬IF(ISBLANK(DPWW1!BS51),"",DPWW1!BS51) | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI51),"",DPWW1!AI51) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ51),"",DPWW1!AJ51)
¬¬A262 | ¬¬IF(ISBLANK(DPWW1!BV51),"",DPWW1!BV51) | ¬¬DPWW1!F51 & "," & DPWW1!G51 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H51),"",DPWW1!H51) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL51),"",DPWW1!AL51) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM51),"",DPWW1!AM51)
¬¬A263 | ¬¬IF(ISBLANK(DPWW1!AT52),"",DPWW1!AT52) | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J53),"",DPWW1!J53) | ¬¬IF(ISBLANK(DPWW1!K53),"",DPWW1!K53) | ¬¬IF(ISBLANK(DPWW1!L53),"",DPWW1!L53) | ¬¬IF(ISBLANK(DPWW1!M53),"",DPWW1!M53) | ¬¬IF(ISBLANK(DPWW1!N53),"",DPWW1!N53) | ¬¬IF(ISBLANK(DPWW1!O53),"",DPWW1!O53) | ¬¬IF(ISBLANK(DPWW1!P53),"",DPWW1!P53) | ¬¬IF(ISBLANK(DPWW1!Q53),"",DPWW1!Q53) | ¬¬IF(ISBLANK(DPWW1!R53),"",DPWW1!R53) | ¬¬IF(ISBLANK(DPWW1!S53),"",DPWW1!S53) | ¬¬IF(ISBLANK(DPWW1!T53),"",DPWW1!T53)
¬¬A264 | ¬¬IF(ISBLANK(DPWW1!BE52),"",DPWW1!BE52) | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U53),"",DPWW1!U53) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V53),"",DPWW1!V53)
¬¬A265 | ¬¬IF(ISBLANK(DPWW1!BH52),"",DPWW1!BH52) | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X53),"",DPWW1!X53) | ¬¬IF(ISBLANK(DPWW1!Y53),"",DPWW1!Y53) | ¬¬IF(ISBLANK(DPWW1!Z53),"",DPWW1!Z53) | ¬¬IF(ISBLANK(DPWW1!AA53),"",DPWW1!AA53) | ¬¬IF(ISBLANK(DPWW1!AB53),"",DPWW1!AB53) | ¬¬IF(ISBLANK(DPWW1!AC53),"",DPWW1!AC53) | ¬¬IF(ISBLANK(DPWW1!AD53),"",DPWW1!AD53) | ¬¬IF(ISBLANK(DPWW1!AE53),"",DPWW1!AE53) | ¬¬IF(ISBLANK(DPWW1!AF53),"",DPWW1!AF53) | ¬¬IF(ISBLANK(DPWW1!AG53),"",DPWW1!AG53) | ¬¬IF(ISBLANK(DPWW1!AH53),"",DPWW1!AH53)
¬¬A266 | ¬¬IF(ISBLANK(DPWW1!BS52),"",DPWW1!BS52) | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI53),"",DPWW1!AI53) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ53),"",DPWW1!AJ53)
¬¬A267 | ¬¬IF(ISBLANK(DPWW1!BV52),"",DPWW1!BV52) | ¬¬DPWW1!F52 & "," & DPWW1!G52 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H52),"",DPWW1!H52) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL53),"",DPWW1!AL53) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM53),"",DPWW1!AM53)
¬¬A268 | ¬¬IF(ISBLANK(DPWW1!AT54),"",DPWW1!AT54) | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J54),"",DPWW1!J54) | ¬¬IF(ISBLANK(DPWW1!K54),"",DPWW1!K54) | ¬¬IF(ISBLANK(DPWW1!L54),"",DPWW1!L54) | ¬¬IF(ISBLANK(DPWW1!M54),"",DPWW1!M54) | ¬¬IF(ISBLANK(DPWW1!N54),"",DPWW1!N54) | ¬¬IF(ISBLANK(DPWW1!O54),"",DPWW1!O54) | ¬¬IF(ISBLANK(DPWW1!P54),"",DPWW1!P54) | ¬¬IF(ISBLANK(DPWW1!Q54),"",DPWW1!Q54) | ¬¬IF(ISBLANK(DPWW1!R54),"",DPWW1!R54) | ¬¬IF(ISBLANK(DPWW1!S54),"",DPWW1!S54) | ¬¬IF(ISBLANK(DPWW1!T54),"",DPWW1!T54)
¬¬A269 | ¬¬IF(ISBLANK(DPWW1!BE54),"",DPWW1!BE54) | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U54),"",DPWW1!U54) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V54),"",DPWW1!V54)
¬¬A270 | ¬¬IF(ISBLANK(DPWW1!BH54),"",DPWW1!BH54) | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X54),"",DPWW1!X54) | ¬¬IF(ISBLANK(DPWW1!Y54),"",DPWW1!Y54) | ¬¬IF(ISBLANK(DPWW1!Z54),"",DPWW1!Z54) | ¬¬IF(ISBLANK(DPWW1!AA54),"",DPWW1!AA54) | ¬¬IF(ISBLANK(DPWW1!AB54),"",DPWW1!AB54) | ¬¬IF(ISBLANK(DPWW1!AC54),"",DPWW1!AC54) | ¬¬IF(ISBLANK(DPWW1!AD54),"",DPWW1!AD54) | ¬¬IF(ISBLANK(DPWW1!AE54),"",DPWW1!AE54) | ¬¬IF(ISBLANK(DPWW1!AF54),"",DPWW1!AF54) | ¬¬IF(ISBLANK(DPWW1!AG54),"",DPWW1!AG54) | ¬¬IF(ISBLANK(DPWW1!AH54),"",DPWW1!AH54)
¬¬A271 | ¬¬IF(ISBLANK(DPWW1!BS54),"",DPWW1!BS54) | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI54),"",DPWW1!AI54) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ54),"",DPWW1!AJ54)
¬¬A272 | ¬¬IF(ISBLANK(DPWW1!BV54),"",DPWW1!BV54) | ¬¬DPWW1!F54 & "," & DPWW1!G54 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H54),"",DPWW1!H54) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL54),"",DPWW1!AL54) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM54),"",DPWW1!AM54)
¬¬A273 | ¬¬IF(ISBLANK(DPWW1!AT55),"",DPWW1!AT55) | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J55),"",DPWW1!J55) | ¬¬IF(ISBLANK(DPWW1!K55),"",DPWW1!K55) | ¬¬IF(ISBLANK(DPWW1!L55),"",DPWW1!L55) | ¬¬IF(ISBLANK(DPWW1!M55),"",DPWW1!M55) | ¬¬IF(ISBLANK(DPWW1!N55),"",DPWW1!N55) | ¬¬IF(ISBLANK(DPWW1!O55),"",DPWW1!O55) | ¬¬IF(ISBLANK(DPWW1!P55),"",DPWW1!P55) | ¬¬IF(ISBLANK(DPWW1!Q55),"",DPWW1!Q55) | ¬¬IF(ISBLANK(DPWW1!R55),"",DPWW1!R55) | ¬¬IF(ISBLANK(DPWW1!S55),"",DPWW1!S55) | ¬¬IF(ISBLANK(DPWW1!T55),"",DPWW1!T55)
¬¬A274 | ¬¬IF(ISBLANK(DPWW1!BE55),"",DPWW1!BE55) | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U55),"",DPWW1!U55) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V55),"",DPWW1!V55)
¬¬A275 | ¬¬IF(ISBLANK(DPWW1!BH55),"",DPWW1!BH55) | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X55),"",DPWW1!X55) | ¬¬IF(ISBLANK(DPWW1!Y55),"",DPWW1!Y55) | ¬¬IF(ISBLANK(DPWW1!Z55),"",DPWW1!Z55) | ¬¬IF(ISBLANK(DPWW1!AA55),"",DPWW1!AA55) | ¬¬IF(ISBLANK(DPWW1!AB55),"",DPWW1!AB55) | ¬¬IF(ISBLANK(DPWW1!AC55),"",DPWW1!AC55) | ¬¬IF(ISBLANK(DPWW1!AD55),"",DPWW1!AD55) | ¬¬IF(ISBLANK(DPWW1!AE55),"",DPWW1!AE55) | ¬¬IF(ISBLANK(DPWW1!AF55),"",DPWW1!AF55) | ¬¬IF(ISBLANK(DPWW1!AG55),"",DPWW1!AG55) | ¬¬IF(ISBLANK(DPWW1!AH55),"",DPWW1!AH55)
¬¬A276 | ¬¬IF(ISBLANK(DPWW1!BS55),"",DPWW1!BS55) | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI55),"",DPWW1!AI55) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ55),"",DPWW1!AJ55)
¬¬A277 | ¬¬IF(ISBLANK(DPWW1!BV55),"",DPWW1!BV55) | ¬¬DPWW1!F55 & "," & DPWW1!G55 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H55),"",DPWW1!H55) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL55),"",DPWW1!AL55) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM55),"",DPWW1!AM55)
¬¬A278 | ¬¬IF(ISBLANK(DPWW1!AT56),"",DPWW1!AT56) | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J56),"",DPWW1!J56) | ¬¬IF(ISBLANK(DPWW1!K56),"",DPWW1!K56) | ¬¬IF(ISBLANK(DPWW1!L56),"",DPWW1!L56) | ¬¬IF(ISBLANK(DPWW1!M56),"",DPWW1!M56) | ¬¬IF(ISBLANK(DPWW1!N56),"",DPWW1!N56) | ¬¬IF(ISBLANK(DPWW1!O56),"",DPWW1!O56) | ¬¬IF(ISBLANK(DPWW1!P56),"",DPWW1!P56) | ¬¬IF(ISBLANK(DPWW1!Q56),"",DPWW1!Q56) | ¬¬IF(ISBLANK(DPWW1!R56),"",DPWW1!R56) | ¬¬IF(ISBLANK(DPWW1!S56),"",DPWW1!S56) | ¬¬IF(ISBLANK(DPWW1!T56),"",DPWW1!T56)
¬¬A279 | ¬¬IF(ISBLANK(DPWW1!BE56),"",DPWW1!BE56) | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U56),"",DPWW1!U56) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V56),"",DPWW1!V56)
¬¬A280 | ¬¬IF(ISBLANK(DPWW1!BH56),"",DPWW1!BH56) | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X56),"",DPWW1!X56) | ¬¬IF(ISBLANK(DPWW1!Y56),"",DPWW1!Y56) | ¬¬IF(ISBLANK(DPWW1!Z56),"",DPWW1!Z56) | ¬¬IF(ISBLANK(DPWW1!AA56),"",DPWW1!AA56) | ¬¬IF(ISBLANK(DPWW1!AB56),"",DPWW1!AB56) | ¬¬IF(ISBLANK(DPWW1!AC56),"",DPWW1!AC56) | ¬¬IF(ISBLANK(DPWW1!AD56),"",DPWW1!AD56) | ¬¬IF(ISBLANK(DPWW1!AE56),"",DPWW1!AE56) | ¬¬IF(ISBLANK(DPWW1!AF56),"",DPWW1!AF56) | ¬¬IF(ISBLANK(DPWW1!AG56),"",DPWW1!AG56) | ¬¬IF(ISBLANK(DPWW1!AH56),"",DPWW1!AH56)
¬¬A281 | ¬¬IF(ISBLANK(DPWW1!BS56),"",DPWW1!BS56) | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI56),"",DPWW1!AI56) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ56),"",DPWW1!AJ56)
¬¬A282 | ¬¬IF(ISBLANK(DPWW1!BV56),"",DPWW1!BV56) | ¬¬DPWW1!F56 & "," & DPWW1!G56 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H56),"",DPWW1!H56) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL56),"",DPWW1!AL56) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM56),"",DPWW1!AM56)
¬¬A283 | ¬¬IF(ISBLANK(DPWW1!AT57),"",DPWW1!AT57) | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J57),"",DPWW1!J57) | ¬¬IF(ISBLANK(DPWW1!K57),"",DPWW1!K57) | ¬¬IF(ISBLANK(DPWW1!L57),"",DPWW1!L57) | ¬¬IF(ISBLANK(DPWW1!M57),"",DPWW1!M57) | ¬¬IF(ISBLANK(DPWW1!N57),"",DPWW1!N57) | ¬¬IF(ISBLANK(DPWW1!O57),"",DPWW1!O57) | ¬¬IF(ISBLANK(DPWW1!P57),"",DPWW1!P57) | ¬¬IF(ISBLANK(DPWW1!Q57),"",DPWW1!Q57) | ¬¬IF(ISBLANK(DPWW1!R57),"",DPWW1!R57) | ¬¬IF(ISBLANK(DPWW1!S57),"",DPWW1!S57) | ¬¬IF(ISBLANK(DPWW1!T57),"",DPWW1!T57)
¬¬A284 | ¬¬IF(ISBLANK(DPWW1!BE57),"",DPWW1!BE57) | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U57),"",DPWW1!U57) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V57),"",DPWW1!V57)
¬¬A285 | ¬¬IF(ISBLANK(DPWW1!BH57),"",DPWW1!BH57) | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X57),"",DPWW1!X57) | ¬¬IF(ISBLANK(DPWW1!Y57),"",DPWW1!Y57) | ¬¬IF(ISBLANK(DPWW1!Z57),"",DPWW1!Z57) | ¬¬IF(ISBLANK(DPWW1!AA57),"",DPWW1!AA57) | ¬¬IF(ISBLANK(DPWW1!AB57),"",DPWW1!AB57) | ¬¬IF(ISBLANK(DPWW1!AC57),"",DPWW1!AC57) | ¬¬IF(ISBLANK(DPWW1!AD57),"",DPWW1!AD57) | ¬¬IF(ISBLANK(DPWW1!AE57),"",DPWW1!AE57) | ¬¬IF(ISBLANK(DPWW1!AF57),"",DPWW1!AF57) | ¬¬IF(ISBLANK(DPWW1!AG57),"",DPWW1!AG57) | ¬¬IF(ISBLANK(DPWW1!AH57),"",DPWW1!AH57)
¬¬A286 | ¬¬IF(ISBLANK(DPWW1!BS57),"",DPWW1!BS57) | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI57),"",DPWW1!AI57) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ57),"",DPWW1!AJ57)
¬¬A287 | ¬¬IF(ISBLANK(DPWW1!BV57),"",DPWW1!BV57) | ¬¬DPWW1!F57 & "," & DPWW1!G57 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H57),"",DPWW1!H57) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL57),"",DPWW1!AL57) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM57),"",DPWW1!AM57)
¬¬A288 | ¬¬IF(ISBLANK(DPWW1!AT58),"",DPWW1!AT58) | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J58),"",DPWW1!J58) | ¬¬IF(ISBLANK(DPWW1!K58),"",DPWW1!K58) | ¬¬IF(ISBLANK(DPWW1!L58),"",DPWW1!L58) | ¬¬IF(ISBLANK(DPWW1!M58),"",DPWW1!M58) | ¬¬IF(ISBLANK(DPWW1!N58),"",DPWW1!N58) | ¬¬IF(ISBLANK(DPWW1!O58),"",DPWW1!O58) | ¬¬IF(ISBLANK(DPWW1!P58),"",DPWW1!P58) | ¬¬IF(ISBLANK(DPWW1!Q58),"",DPWW1!Q58) | ¬¬IF(ISBLANK(DPWW1!R58),"",DPWW1!R58) | ¬¬IF(ISBLANK(DPWW1!S58),"",DPWW1!S58) | ¬¬IF(ISBLANK(DPWW1!T58),"",DPWW1!T58)
¬¬A289 | ¬¬IF(ISBLANK(DPWW1!BE58),"",DPWW1!BE58) | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U58),"",DPWW1!U58) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V58),"",DPWW1!V58)
¬¬A290 | ¬¬IF(ISBLANK(DPWW1!BH58),"",DPWW1!BH58) | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X58),"",DPWW1!X58) | ¬¬IF(ISBLANK(DPWW1!Y58),"",DPWW1!Y58) | ¬¬IF(ISBLANK(DPWW1!Z58),"",DPWW1!Z58) | ¬¬IF(ISBLANK(DPWW1!AA58),"",DPWW1!AA58) | ¬¬IF(ISBLANK(DPWW1!AB58),"",DPWW1!AB58) | ¬¬IF(ISBLANK(DPWW1!AC58),"",DPWW1!AC58) | ¬¬IF(ISBLANK(DPWW1!AD58),"",DPWW1!AD58) | ¬¬IF(ISBLANK(DPWW1!AE58),"",DPWW1!AE58) | ¬¬IF(ISBLANK(DPWW1!AF58),"",DPWW1!AF58) | ¬¬IF(ISBLANK(DPWW1!AG58),"",DPWW1!AG58) | ¬¬IF(ISBLANK(DPWW1!AH58),"",DPWW1!AH58)
¬¬A291 | ¬¬IF(ISBLANK(DPWW1!BS58),"",DPWW1!BS58) | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI58),"",DPWW1!AI58) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ58),"",DPWW1!AJ58)
¬¬A292 | ¬¬IF(ISBLANK(DPWW1!BV58),"",DPWW1!BV58) | ¬¬DPWW1!F58 & "," & DPWW1!G58 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H58),"",DPWW1!H58) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL58),"",DPWW1!AL58) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM58),"",DPWW1!AM58)
¬¬A293 | ¬¬IF(ISBLANK(DPWW1!AT59),"",DPWW1!AT59) | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J59),"",DPWW1!J59) | ¬¬IF(ISBLANK(DPWW1!K59),"",DPWW1!K59) | ¬¬IF(ISBLANK(DPWW1!L59),"",DPWW1!L59) | ¬¬IF(ISBLANK(DPWW1!M59),"",DPWW1!M59) | ¬¬IF(ISBLANK(DPWW1!N59),"",DPWW1!N59) | ¬¬IF(ISBLANK(DPWW1!O59),"",DPWW1!O59) | ¬¬IF(ISBLANK(DPWW1!P59),"",DPWW1!P59) | ¬¬IF(ISBLANK(DPWW1!Q59),"",DPWW1!Q59) | ¬¬IF(ISBLANK(DPWW1!R59),"",DPWW1!R59) | ¬¬IF(ISBLANK(DPWW1!S59),"",DPWW1!S59) | ¬¬IF(ISBLANK(DPWW1!T59),"",DPWW1!T59)
¬¬A294 | ¬¬IF(ISBLANK(DPWW1!BE59),"",DPWW1!BE59) | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U59),"",DPWW1!U59) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V59),"",DPWW1!V59)
¬¬A295 | ¬¬IF(ISBLANK(DPWW1!BH59),"",DPWW1!BH59) | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X59),"",DPWW1!X59) | ¬¬IF(ISBLANK(DPWW1!Y59),"",DPWW1!Y59) | ¬¬IF(ISBLANK(DPWW1!Z59),"",DPWW1!Z59) | ¬¬IF(ISBLANK(DPWW1!AA59),"",DPWW1!AA59) | ¬¬IF(ISBLANK(DPWW1!AB59),"",DPWW1!AB59) | ¬¬IF(ISBLANK(DPWW1!AC59),"",DPWW1!AC59) | ¬¬IF(ISBLANK(DPWW1!AD59),"",DPWW1!AD59) | ¬¬IF(ISBLANK(DPWW1!AE59),"",DPWW1!AE59) | ¬¬IF(ISBLANK(DPWW1!AF59),"",DPWW1!AF59) | ¬¬IF(ISBLANK(DPWW1!AG59),"",DPWW1!AG59) | ¬¬IF(ISBLANK(DPWW1!AH59),"",DPWW1!AH59)
¬¬A296 | ¬¬IF(ISBLANK(DPWW1!BS59),"",DPWW1!BS59) | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI59),"",DPWW1!AI59) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ59),"",DPWW1!AJ59)
¬¬A297 | ¬¬IF(ISBLANK(DPWW1!BV59),"",DPWW1!BV59) | ¬¬DPWW1!F59 & "," & DPWW1!G59 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H59),"",DPWW1!H59) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL59),"",DPWW1!AL59) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM59),"",DPWW1!AM59)
¬¬A298 | ¬¬IF(ISBLANK(DPWW1!AT60),"",DPWW1!AT60) | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J60),"",DPWW1!J60) | ¬¬IF(ISBLANK(DPWW1!K60),"",DPWW1!K60) | ¬¬IF(ISBLANK(DPWW1!L60),"",DPWW1!L60) | ¬¬IF(ISBLANK(DPWW1!M60),"",DPWW1!M60) | ¬¬IF(ISBLANK(DPWW1!N60),"",DPWW1!N60) | ¬¬IF(ISBLANK(DPWW1!O60),"",DPWW1!O60) | ¬¬IF(ISBLANK(DPWW1!P60),"",DPWW1!P60) | ¬¬IF(ISBLANK(DPWW1!Q60),"",DPWW1!Q60) | ¬¬IF(ISBLANK(DPWW1!R60),"",DPWW1!R60) | ¬¬IF(ISBLANK(DPWW1!S60),"",DPWW1!S60) | ¬¬IF(ISBLANK(DPWW1!T60),"",DPWW1!T60)
¬¬A299 | ¬¬IF(ISBLANK(DPWW1!BE60),"",DPWW1!BE60) | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U60),"",DPWW1!U60) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V60),"",DPWW1!V60)
¬¬A300 | ¬¬IF(ISBLANK(DPWW1!BH60),"",DPWW1!BH60) | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X60),"",DPWW1!X60) | ¬¬IF(ISBLANK(DPWW1!Y60),"",DPWW1!Y60) | ¬¬IF(ISBLANK(DPWW1!Z60),"",DPWW1!Z60) | ¬¬IF(ISBLANK(DPWW1!AA60),"",DPWW1!AA60) | ¬¬IF(ISBLANK(DPWW1!AB60),"",DPWW1!AB60) | ¬¬IF(ISBLANK(DPWW1!AC60),"",DPWW1!AC60) | ¬¬IF(ISBLANK(DPWW1!AD60),"",DPWW1!AD60) | ¬¬IF(ISBLANK(DPWW1!AE60),"",DPWW1!AE60) | ¬¬IF(ISBLANK(DPWW1!AF60),"",DPWW1!AF60) | ¬¬IF(ISBLANK(DPWW1!AG60),"",DPWW1!AG60) | ¬¬IF(ISBLANK(DPWW1!AH60),"",DPWW1!AH60)
¬¬A301 | ¬¬IF(ISBLANK(DPWW1!BS60),"",DPWW1!BS60) | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI60),"",DPWW1!AI60) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ60),"",DPWW1!AJ60)
¬¬A302 | ¬¬IF(ISBLANK(DPWW1!BV60),"",DPWW1!BV60) | ¬¬DPWW1!F60 & "," & DPWW1!G60 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H60),"",DPWW1!H60) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL60),"",DPWW1!AL60) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM60),"",DPWW1!AM60)
¬¬A303 | ¬¬IF(ISBLANK(DPWW1!AT61),"",DPWW1!AT61) | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J61),"",DPWW1!J61) | ¬¬IF(ISBLANK(DPWW1!K61),"",DPWW1!K61) | ¬¬IF(ISBLANK(DPWW1!L61),"",DPWW1!L61) | ¬¬IF(ISBLANK(DPWW1!M61),"",DPWW1!M61) | ¬¬IF(ISBLANK(DPWW1!N61),"",DPWW1!N61) | ¬¬IF(ISBLANK(DPWW1!O61),"",DPWW1!O61) | ¬¬IF(ISBLANK(DPWW1!P61),"",DPWW1!P61) | ¬¬IF(ISBLANK(DPWW1!Q61),"",DPWW1!Q61) | ¬¬IF(ISBLANK(DPWW1!R61),"",DPWW1!R61) | ¬¬IF(ISBLANK(DPWW1!S61),"",DPWW1!S61) | ¬¬IF(ISBLANK(DPWW1!T61),"",DPWW1!T61)
¬¬A304 | ¬¬IF(ISBLANK(DPWW1!BE61),"",DPWW1!BE61) | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U61),"",DPWW1!U61) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V61),"",DPWW1!V61)
¬¬A305 | ¬¬IF(ISBLANK(DPWW1!BH61),"",DPWW1!BH61) | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X61),"",DPWW1!X61) | ¬¬IF(ISBLANK(DPWW1!Y61),"",DPWW1!Y61) | ¬¬IF(ISBLANK(DPWW1!Z61),"",DPWW1!Z61) | ¬¬IF(ISBLANK(DPWW1!AA61),"",DPWW1!AA61) | ¬¬IF(ISBLANK(DPWW1!AB61),"",DPWW1!AB61) | ¬¬IF(ISBLANK(DPWW1!AC61),"",DPWW1!AC61) | ¬¬IF(ISBLANK(DPWW1!AD61),"",DPWW1!AD61) | ¬¬IF(ISBLANK(DPWW1!AE61),"",DPWW1!AE61) | ¬¬IF(ISBLANK(DPWW1!AF61),"",DPWW1!AF61) | ¬¬IF(ISBLANK(DPWW1!AG61),"",DPWW1!AG61) | ¬¬IF(ISBLANK(DPWW1!AH61),"",DPWW1!AH61)
¬¬A306 | ¬¬IF(ISBLANK(DPWW1!BS61),"",DPWW1!BS61) | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI61),"",DPWW1!AI61) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ61),"",DPWW1!AJ61)
¬¬A307 | ¬¬IF(ISBLANK(DPWW1!BV61),"",DPWW1!BV61) | ¬¬DPWW1!F61 & "," & DPWW1!G61 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H61),"",DPWW1!H61) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL61),"",DPWW1!AL61) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM61),"",DPWW1!AM61)
¬¬A308 | ¬¬IF(ISBLANK(DPWW1!AT62),"",DPWW1!AT62) | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J62),"",DPWW1!J62) | ¬¬IF(ISBLANK(DPWW1!K62),"",DPWW1!K62) | ¬¬IF(ISBLANK(DPWW1!L62),"",DPWW1!L62) | ¬¬IF(ISBLANK(DPWW1!M62),"",DPWW1!M62) | ¬¬IF(ISBLANK(DPWW1!N62),"",DPWW1!N62) | ¬¬IF(ISBLANK(DPWW1!O62),"",DPWW1!O62) | ¬¬IF(ISBLANK(DPWW1!P62),"",DPWW1!P62) | ¬¬IF(ISBLANK(DPWW1!Q62),"",DPWW1!Q62) | ¬¬IF(ISBLANK(DPWW1!R62),"",DPWW1!R62) | ¬¬IF(ISBLANK(DPWW1!S62),"",DPWW1!S62) | ¬¬IF(ISBLANK(DPWW1!T62),"",DPWW1!T62)
¬¬A309 | ¬¬IF(ISBLANK(DPWW1!BE62),"",DPWW1!BE62) | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U62),"",DPWW1!U62) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V62),"",DPWW1!V62)
¬¬A310 | ¬¬IF(ISBLANK(DPWW1!BH62),"",DPWW1!BH62) | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X62),"",DPWW1!X62) | ¬¬IF(ISBLANK(DPWW1!Y62),"",DPWW1!Y62) | ¬¬IF(ISBLANK(DPWW1!Z62),"",DPWW1!Z62) | ¬¬IF(ISBLANK(DPWW1!AA62),"",DPWW1!AA62) | ¬¬IF(ISBLANK(DPWW1!AB62),"",DPWW1!AB62) | ¬¬IF(ISBLANK(DPWW1!AC62),"",DPWW1!AC62) | ¬¬IF(ISBLANK(DPWW1!AD62),"",DPWW1!AD62) | ¬¬IF(ISBLANK(DPWW1!AE62),"",DPWW1!AE62) | ¬¬IF(ISBLANK(DPWW1!AF62),"",DPWW1!AF62) | ¬¬IF(ISBLANK(DPWW1!AG62),"",DPWW1!AG62) | ¬¬IF(ISBLANK(DPWW1!AH62),"",DPWW1!AH62)
¬¬A311 | ¬¬IF(ISBLANK(DPWW1!BS62),"",DPWW1!BS62) | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI62),"",DPWW1!AI62) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ62),"",DPWW1!AJ62)
¬¬A312 | ¬¬IF(ISBLANK(DPWW1!BV62),"",DPWW1!BV62) | ¬¬DPWW1!F62 & "," & DPWW1!G62 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H62),"",DPWW1!H62) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL62),"",DPWW1!AL62) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM62),"",DPWW1!AM62)
¬¬A313 | ¬¬IF(ISBLANK(DPWW1!AT63),"",DPWW1!AT63) | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J63),"",DPWW1!J63) | ¬¬IF(ISBLANK(DPWW1!K63),"",DPWW1!K63) | ¬¬IF(ISBLANK(DPWW1!L63),"",DPWW1!L63) | ¬¬IF(ISBLANK(DPWW1!M63),"",DPWW1!M63) | ¬¬IF(ISBLANK(DPWW1!N63),"",DPWW1!N63) | ¬¬IF(ISBLANK(DPWW1!O63),"",DPWW1!O63) | ¬¬IF(ISBLANK(DPWW1!P63),"",DPWW1!P63) | ¬¬IF(ISBLANK(DPWW1!Q63),"",DPWW1!Q63) | ¬¬IF(ISBLANK(DPWW1!R63),"",DPWW1!R63) | ¬¬IF(ISBLANK(DPWW1!S63),"",DPWW1!S63) | ¬¬IF(ISBLANK(DPWW1!T63),"",DPWW1!T63)
¬¬A314 | ¬¬IF(ISBLANK(DPWW1!BE63),"",DPWW1!BE63) | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U63),"",DPWW1!U63) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V63),"",DPWW1!V63)
¬¬A315 | ¬¬IF(ISBLANK(DPWW1!BH63),"",DPWW1!BH63) | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X63),"",DPWW1!X63) | ¬¬IF(ISBLANK(DPWW1!Y63),"",DPWW1!Y63) | ¬¬IF(ISBLANK(DPWW1!Z63),"",DPWW1!Z63) | ¬¬IF(ISBLANK(DPWW1!AA63),"",DPWW1!AA63) | ¬¬IF(ISBLANK(DPWW1!AB63),"",DPWW1!AB63) | ¬¬IF(ISBLANK(DPWW1!AC63),"",DPWW1!AC63) | ¬¬IF(ISBLANK(DPWW1!AD63),"",DPWW1!AD63) | ¬¬IF(ISBLANK(DPWW1!AE63),"",DPWW1!AE63) | ¬¬IF(ISBLANK(DPWW1!AF63),"",DPWW1!AF63) | ¬¬IF(ISBLANK(DPWW1!AG63),"",DPWW1!AG63) | ¬¬IF(ISBLANK(DPWW1!AH63),"",DPWW1!AH63)
¬¬A316 | ¬¬IF(ISBLANK(DPWW1!BS63),"",DPWW1!BS63) | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI63),"",DPWW1!AI63) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ63),"",DPWW1!AJ63)
¬¬A317 | ¬¬IF(ISBLANK(DPWW1!BV63),"",DPWW1!BV63) | ¬¬DPWW1!F63 & "," & DPWW1!G63 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H63),"",DPWW1!H63) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL63),"",DPWW1!AL63) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM63),"",DPWW1!AM63)
¬¬A318 | ¬¬IF(ISBLANK(DPWW1!AT64),"",DPWW1!AT64) | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!AQ5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!J64),"",DPWW1!J64) | ¬¬IF(ISBLANK(DPWW1!K64),"",DPWW1!K64) | ¬¬IF(ISBLANK(DPWW1!L64),"",DPWW1!L64) | ¬¬IF(ISBLANK(DPWW1!M64),"",DPWW1!M64) | ¬¬IF(ISBLANK(DPWW1!N64),"",DPWW1!N64) | ¬¬IF(ISBLANK(DPWW1!O64),"",DPWW1!O64) | ¬¬IF(ISBLANK(DPWW1!P64),"",DPWW1!P64) | ¬¬IF(ISBLANK(DPWW1!Q64),"",DPWW1!Q64) | ¬¬IF(ISBLANK(DPWW1!R64),"",DPWW1!R64) | ¬¬IF(ISBLANK(DPWW1!S64),"",DPWW1!S64) | ¬¬IF(ISBLANK(DPWW1!T64),"",DPWW1!T64)
¬¬A319 | ¬¬IF(ISBLANK(DPWW1!BE64),"",DPWW1!BE64) | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BE5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!U64),"",DPWW1!U64) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!V64),"",DPWW1!V64)
¬¬A320 | ¬¬IF(ISBLANK(DPWW1!BH64),"",DPWW1!BH64) | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BF5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) | Delta |  |  | ¬¬IF(ISBLANK(DPWW1!X64),"",DPWW1!X64) | ¬¬IF(ISBLANK(DPWW1!Y64),"",DPWW1!Y64) | ¬¬IF(ISBLANK(DPWW1!Z64),"",DPWW1!Z64) | ¬¬IF(ISBLANK(DPWW1!AA64),"",DPWW1!AA64) | ¬¬IF(ISBLANK(DPWW1!AB64),"",DPWW1!AB64) | ¬¬IF(ISBLANK(DPWW1!AC64),"",DPWW1!AC64) | ¬¬IF(ISBLANK(DPWW1!AD64),"",DPWW1!AD64) | ¬¬IF(ISBLANK(DPWW1!AE64),"",DPWW1!AE64) | ¬¬IF(ISBLANK(DPWW1!AF64),"",DPWW1!AF64) | ¬¬IF(ISBLANK(DPWW1!AG64),"",DPWW1!AG64) | ¬¬IF(ISBLANK(DPWW1!AH64),"",DPWW1!AH64)
¬¬A321 | ¬¬IF(ISBLANK(DPWW1!BS64),"",DPWW1!BS64) | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BS5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AI64),"",DPWW1!AI64) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AJ64),"",DPWW1!AJ64)
¬¬A322 | ¬¬IF(ISBLANK(DPWW1!BV64),"",DPWW1!BV64) | ¬¬DPWW1!F64 & "," & DPWW1!G64 & "," & DPWW1!BV5 | ¬¬IF(ISBLANK(DPWW1!H64),"",DPWW1!H64) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW1!AL64),"",DPWW1!AL64) |  |  |  |  | ¬¬IF(ISBLANK(DPWW1!AM64),"",DPWW1!AM64)
¬¬A323 | ¬¬IF(ISBLANK(DPWW2!AT8),"",DPWW2!AT8) | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J8),"",DPWW2!J8)
¬¬A324 | ¬¬IF(ISBLANK(DPWW2!AV8),"",DPWW2!AV8) | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L8),"",DPWW2!L8) | ¬¬IF(ISBLANK(DPWW2!M8),"",DPWW2!M8) | ¬¬IF(ISBLANK(DPWW2!N8),"",DPWW2!N8) | ¬¬IF(ISBLANK(DPWW2!O8),"",DPWW2!O8) | ¬¬IF(ISBLANK(DPWW2!P8),"",DPWW2!P8) | ¬¬IF(ISBLANK(DPWW2!Q8),"",DPWW2!Q8) | ¬¬IF(ISBLANK(DPWW2!R8),"",DPWW2!R8) | ¬¬IF(ISBLANK(DPWW2!S8),"",DPWW2!S8) | ¬¬IF(ISBLANK(DPWW2!T8),"",DPWW2!T8) | ¬¬IF(ISBLANK(DPWW2!U8),"",DPWW2!U8) | ¬¬IF(ISBLANK(DPWW2!V8),"",DPWW2!V8)
¬¬A325 | ¬¬IF(ISBLANK(DPWW2!BG8),"",DPWW2!BG8) | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W8),"",DPWW2!W8) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X8),"",DPWW2!X8)
¬¬A326 | ¬¬IF(ISBLANK(DPWW2!BJ8),"",DPWW2!BJ8) | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z8),"",DPWW2!Z8) | ¬¬IF(ISBLANK(DPWW2!AA8),"",DPWW2!AA8) | ¬¬IF(ISBLANK(DPWW2!AB8),"",DPWW2!AB8) | ¬¬IF(ISBLANK(DPWW2!AC8),"",DPWW2!AC8) | ¬¬IF(ISBLANK(DPWW2!AD8),"",DPWW2!AD8) | ¬¬IF(ISBLANK(DPWW2!AE8),"",DPWW2!AE8) | ¬¬IF(ISBLANK(DPWW2!AF8),"",DPWW2!AF8) | ¬¬IF(ISBLANK(DPWW2!AG8),"",DPWW2!AG8) | ¬¬IF(ISBLANK(DPWW2!AH8),"",DPWW2!AH8) | ¬¬IF(ISBLANK(DPWW2!AI8),"",DPWW2!AI8) | ¬¬IF(ISBLANK(DPWW2!AJ8),"",DPWW2!AJ8)
¬¬A327 | ¬¬IF(ISBLANK(DPWW2!BU8),"",DPWW2!BU8) | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK8),"",DPWW2!AK8) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL8),"",DPWW2!AL8)
¬¬A328 | ¬¬IF(ISBLANK(DPWW2!BX8),"",DPWW2!BX8) | ¬¬DPWW2!F8 & "," & DPWW2!G8 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H8),"",DPWW2!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN8),"",DPWW2!AN8) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO8),"",DPWW2!AO8)
¬¬A329 | ¬¬IF(ISBLANK(DPWW2!AT9),"",DPWW2!AT9) | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J9),"",DPWW2!J9)
¬¬A330 | ¬¬IF(ISBLANK(DPWW2!AV9),"",DPWW2!AV9) | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L9),"",DPWW2!L9) | ¬¬IF(ISBLANK(DPWW2!M9),"",DPWW2!M9) | ¬¬IF(ISBLANK(DPWW2!N9),"",DPWW2!N9) | ¬¬IF(ISBLANK(DPWW2!O9),"",DPWW2!O9) | ¬¬IF(ISBLANK(DPWW2!P9),"",DPWW2!P9) | ¬¬IF(ISBLANK(DPWW2!Q9),"",DPWW2!Q9) | ¬¬IF(ISBLANK(DPWW2!R9),"",DPWW2!R9) | ¬¬IF(ISBLANK(DPWW2!S9),"",DPWW2!S9) | ¬¬IF(ISBLANK(DPWW2!T9),"",DPWW2!T9) | ¬¬IF(ISBLANK(DPWW2!U9),"",DPWW2!U9) | ¬¬IF(ISBLANK(DPWW2!V9),"",DPWW2!V9)
¬¬A331 | ¬¬IF(ISBLANK(DPWW2!BG9),"",DPWW2!BG9) | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W9),"",DPWW2!W9) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X9),"",DPWW2!X9)
¬¬A332 | ¬¬IF(ISBLANK(DPWW2!BJ9),"",DPWW2!BJ9) | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z9),"",DPWW2!Z9) | ¬¬IF(ISBLANK(DPWW2!AA9),"",DPWW2!AA9) | ¬¬IF(ISBLANK(DPWW2!AB9),"",DPWW2!AB9) | ¬¬IF(ISBLANK(DPWW2!AC9),"",DPWW2!AC9) | ¬¬IF(ISBLANK(DPWW2!AD9),"",DPWW2!AD9) | ¬¬IF(ISBLANK(DPWW2!AE9),"",DPWW2!AE9) | ¬¬IF(ISBLANK(DPWW2!AF9),"",DPWW2!AF9) | ¬¬IF(ISBLANK(DPWW2!AG9),"",DPWW2!AG9) | ¬¬IF(ISBLANK(DPWW2!AH9),"",DPWW2!AH9) | ¬¬IF(ISBLANK(DPWW2!AI9),"",DPWW2!AI9) | ¬¬IF(ISBLANK(DPWW2!AJ9),"",DPWW2!AJ9)
¬¬A333 | ¬¬IF(ISBLANK(DPWW2!BU9),"",DPWW2!BU9) | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK9),"",DPWW2!AK9) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL9),"",DPWW2!AL9)
¬¬A334 | ¬¬IF(ISBLANK(DPWW2!BX9),"",DPWW2!BX9) | ¬¬DPWW2!F9 & "," & DPWW2!G9 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H9),"",DPWW2!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN9),"",DPWW2!AN9) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO9),"",DPWW2!AO9)
¬¬A335 | ¬¬IF(ISBLANK(DPWW2!AT10),"",DPWW2!AT10) | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J10),"",DPWW2!J10)
¬¬A336 | ¬¬IF(ISBLANK(DPWW2!AV10),"",DPWW2!AV10) | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L10),"",DPWW2!L10) | ¬¬IF(ISBLANK(DPWW2!M10),"",DPWW2!M10) | ¬¬IF(ISBLANK(DPWW2!N10),"",DPWW2!N10) | ¬¬IF(ISBLANK(DPWW2!O10),"",DPWW2!O10) | ¬¬IF(ISBLANK(DPWW2!P10),"",DPWW2!P10) | ¬¬IF(ISBLANK(DPWW2!Q10),"",DPWW2!Q10) | ¬¬IF(ISBLANK(DPWW2!R10),"",DPWW2!R10) | ¬¬IF(ISBLANK(DPWW2!S10),"",DPWW2!S10) | ¬¬IF(ISBLANK(DPWW2!T10),"",DPWW2!T10) | ¬¬IF(ISBLANK(DPWW2!U10),"",DPWW2!U10) | ¬¬IF(ISBLANK(DPWW2!V10),"",DPWW2!V10)
¬¬A337 | ¬¬IF(ISBLANK(DPWW2!BG10),"",DPWW2!BG10) | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W10),"",DPWW2!W10) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X10),"",DPWW2!X10)
¬¬A338 | ¬¬IF(ISBLANK(DPWW2!BJ10),"",DPWW2!BJ10) | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z10),"",DPWW2!Z10) | ¬¬IF(ISBLANK(DPWW2!AA10),"",DPWW2!AA10) | ¬¬IF(ISBLANK(DPWW2!AB10),"",DPWW2!AB10) | ¬¬IF(ISBLANK(DPWW2!AC10),"",DPWW2!AC10) | ¬¬IF(ISBLANK(DPWW2!AD10),"",DPWW2!AD10) | ¬¬IF(ISBLANK(DPWW2!AE10),"",DPWW2!AE10) | ¬¬IF(ISBLANK(DPWW2!AF10),"",DPWW2!AF10) | ¬¬IF(ISBLANK(DPWW2!AG10),"",DPWW2!AG10) | ¬¬IF(ISBLANK(DPWW2!AH10),"",DPWW2!AH10) | ¬¬IF(ISBLANK(DPWW2!AI10),"",DPWW2!AI10) | ¬¬IF(ISBLANK(DPWW2!AJ10),"",DPWW2!AJ10)
¬¬A339 | ¬¬IF(ISBLANK(DPWW2!BU10),"",DPWW2!BU10) | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK10),"",DPWW2!AK10) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL10),"",DPWW2!AL10)
¬¬A340 | ¬¬IF(ISBLANK(DPWW2!BX10),"",DPWW2!BX10) | ¬¬DPWW2!F10 & "," & DPWW2!G10 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H10),"",DPWW2!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN10),"",DPWW2!AN10) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO10),"",DPWW2!AO10)
¬¬A341 | ¬¬IF(ISBLANK(DPWW2!AT11),"",DPWW2!AT11) | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J11),"",DPWW2!J11)
¬¬A342 | ¬¬IF(ISBLANK(DPWW2!AV11),"",DPWW2!AV11) | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L11),"",DPWW2!L11) | ¬¬IF(ISBLANK(DPWW2!M11),"",DPWW2!M11) | ¬¬IF(ISBLANK(DPWW2!N11),"",DPWW2!N11) | ¬¬IF(ISBLANK(DPWW2!O11),"",DPWW2!O11) | ¬¬IF(ISBLANK(DPWW2!P11),"",DPWW2!P11) | ¬¬IF(ISBLANK(DPWW2!Q11),"",DPWW2!Q11) | ¬¬IF(ISBLANK(DPWW2!R11),"",DPWW2!R11) | ¬¬IF(ISBLANK(DPWW2!S11),"",DPWW2!S11) | ¬¬IF(ISBLANK(DPWW2!T11),"",DPWW2!T11) | ¬¬IF(ISBLANK(DPWW2!U11),"",DPWW2!U11) | ¬¬IF(ISBLANK(DPWW2!V11),"",DPWW2!V11)
¬¬A343 | ¬¬IF(ISBLANK(DPWW2!BG11),"",DPWW2!BG11) | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W11),"",DPWW2!W11) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X11),"",DPWW2!X11)
¬¬A344 | ¬¬IF(ISBLANK(DPWW2!BJ11),"",DPWW2!BJ11) | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z11),"",DPWW2!Z11) | ¬¬IF(ISBLANK(DPWW2!AA11),"",DPWW2!AA11) | ¬¬IF(ISBLANK(DPWW2!AB11),"",DPWW2!AB11) | ¬¬IF(ISBLANK(DPWW2!AC11),"",DPWW2!AC11) | ¬¬IF(ISBLANK(DPWW2!AD11),"",DPWW2!AD11) | ¬¬IF(ISBLANK(DPWW2!AE11),"",DPWW2!AE11) | ¬¬IF(ISBLANK(DPWW2!AF11),"",DPWW2!AF11) | ¬¬IF(ISBLANK(DPWW2!AG11),"",DPWW2!AG11) | ¬¬IF(ISBLANK(DPWW2!AH11),"",DPWW2!AH11) | ¬¬IF(ISBLANK(DPWW2!AI11),"",DPWW2!AI11) | ¬¬IF(ISBLANK(DPWW2!AJ11),"",DPWW2!AJ11)
¬¬A345 | ¬¬IF(ISBLANK(DPWW2!BU11),"",DPWW2!BU11) | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK11),"",DPWW2!AK11) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL11),"",DPWW2!AL11)
¬¬A346 | ¬¬IF(ISBLANK(DPWW2!BX11),"",DPWW2!BX11) | ¬¬DPWW2!F11 & "," & DPWW2!G11 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H11),"",DPWW2!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN11),"",DPWW2!AN11) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO11),"",DPWW2!AO11)
¬¬A347 | ¬¬IF(ISBLANK(DPWW2!AT12),"",DPWW2!AT12) | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J12),"",DPWW2!J12)
¬¬A348 | ¬¬IF(ISBLANK(DPWW2!AV12),"",DPWW2!AV12) | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L12),"",DPWW2!L12) | ¬¬IF(ISBLANK(DPWW2!M12),"",DPWW2!M12) | ¬¬IF(ISBLANK(DPWW2!N12),"",DPWW2!N12) | ¬¬IF(ISBLANK(DPWW2!O12),"",DPWW2!O12) | ¬¬IF(ISBLANK(DPWW2!P12),"",DPWW2!P12) | ¬¬IF(ISBLANK(DPWW2!Q12),"",DPWW2!Q12) | ¬¬IF(ISBLANK(DPWW2!R12),"",DPWW2!R12) | ¬¬IF(ISBLANK(DPWW2!S12),"",DPWW2!S12) | ¬¬IF(ISBLANK(DPWW2!T12),"",DPWW2!T12) | ¬¬IF(ISBLANK(DPWW2!U12),"",DPWW2!U12) | ¬¬IF(ISBLANK(DPWW2!V12),"",DPWW2!V12)
¬¬A349 | ¬¬IF(ISBLANK(DPWW2!BG12),"",DPWW2!BG12) | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W12),"",DPWW2!W12) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X12),"",DPWW2!X12)
¬¬A350 | ¬¬IF(ISBLANK(DPWW2!BJ12),"",DPWW2!BJ12) | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z12),"",DPWW2!Z12) | ¬¬IF(ISBLANK(DPWW2!AA12),"",DPWW2!AA12) | ¬¬IF(ISBLANK(DPWW2!AB12),"",DPWW2!AB12) | ¬¬IF(ISBLANK(DPWW2!AC12),"",DPWW2!AC12) | ¬¬IF(ISBLANK(DPWW2!AD12),"",DPWW2!AD12) | ¬¬IF(ISBLANK(DPWW2!AE12),"",DPWW2!AE12) | ¬¬IF(ISBLANK(DPWW2!AF12),"",DPWW2!AF12) | ¬¬IF(ISBLANK(DPWW2!AG12),"",DPWW2!AG12) | ¬¬IF(ISBLANK(DPWW2!AH12),"",DPWW2!AH12) | ¬¬IF(ISBLANK(DPWW2!AI12),"",DPWW2!AI12) | ¬¬IF(ISBLANK(DPWW2!AJ12),"",DPWW2!AJ12)
¬¬A351 | ¬¬IF(ISBLANK(DPWW2!BU12),"",DPWW2!BU12) | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK12),"",DPWW2!AK12) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL12),"",DPWW2!AL12)
¬¬A352 | ¬¬IF(ISBLANK(DPWW2!BX12),"",DPWW2!BX12) | ¬¬DPWW2!F12 & "," & DPWW2!G12 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H12),"",DPWW2!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN12),"",DPWW2!AN12) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO12),"",DPWW2!AO12)
¬¬A353 | ¬¬IF(ISBLANK(DPWW2!AT13),"",DPWW2!AT13) | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J13),"",DPWW2!J13)
¬¬A354 | ¬¬IF(ISBLANK(DPWW2!AV13),"",DPWW2!AV13) | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L13),"",DPWW2!L13) | ¬¬IF(ISBLANK(DPWW2!M13),"",DPWW2!M13) | ¬¬IF(ISBLANK(DPWW2!N13),"",DPWW2!N13) | ¬¬IF(ISBLANK(DPWW2!O13),"",DPWW2!O13) | ¬¬IF(ISBLANK(DPWW2!P13),"",DPWW2!P13) | ¬¬IF(ISBLANK(DPWW2!Q13),"",DPWW2!Q13) | ¬¬IF(ISBLANK(DPWW2!R13),"",DPWW2!R13) | ¬¬IF(ISBLANK(DPWW2!S13),"",DPWW2!S13) | ¬¬IF(ISBLANK(DPWW2!T13),"",DPWW2!T13) | ¬¬IF(ISBLANK(DPWW2!U13),"",DPWW2!U13) | ¬¬IF(ISBLANK(DPWW2!V13),"",DPWW2!V13)
¬¬A355 | ¬¬IF(ISBLANK(DPWW2!BG13),"",DPWW2!BG13) | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W13),"",DPWW2!W13) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X13),"",DPWW2!X13)
¬¬A356 | ¬¬IF(ISBLANK(DPWW2!BJ13),"",DPWW2!BJ13) | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z13),"",DPWW2!Z13) | ¬¬IF(ISBLANK(DPWW2!AA13),"",DPWW2!AA13) | ¬¬IF(ISBLANK(DPWW2!AB13),"",DPWW2!AB13) | ¬¬IF(ISBLANK(DPWW2!AC13),"",DPWW2!AC13) | ¬¬IF(ISBLANK(DPWW2!AD13),"",DPWW2!AD13) | ¬¬IF(ISBLANK(DPWW2!AE13),"",DPWW2!AE13) | ¬¬IF(ISBLANK(DPWW2!AF13),"",DPWW2!AF13) | ¬¬IF(ISBLANK(DPWW2!AG13),"",DPWW2!AG13) | ¬¬IF(ISBLANK(DPWW2!AH13),"",DPWW2!AH13) | ¬¬IF(ISBLANK(DPWW2!AI13),"",DPWW2!AI13) | ¬¬IF(ISBLANK(DPWW2!AJ13),"",DPWW2!AJ13)
¬¬A357 | ¬¬IF(ISBLANK(DPWW2!BU13),"",DPWW2!BU13) | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK13),"",DPWW2!AK13) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL13),"",DPWW2!AL13)
¬¬A358 | ¬¬IF(ISBLANK(DPWW2!BX13),"",DPWW2!BX13) | ¬¬DPWW2!F13 & "," & DPWW2!G13 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H13),"",DPWW2!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN13),"",DPWW2!AN13) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO13),"",DPWW2!AO13)
¬¬A359 | ¬¬IF(ISBLANK(DPWW2!AT14),"",DPWW2!AT14) | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J14),"",DPWW2!J14)
¬¬A360 | ¬¬IF(ISBLANK(DPWW2!AV14),"",DPWW2!AV14) | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L14),"",DPWW2!L14) | ¬¬IF(ISBLANK(DPWW2!M14),"",DPWW2!M14) | ¬¬IF(ISBLANK(DPWW2!N14),"",DPWW2!N14) | ¬¬IF(ISBLANK(DPWW2!O14),"",DPWW2!O14) | ¬¬IF(ISBLANK(DPWW2!P14),"",DPWW2!P14) | ¬¬IF(ISBLANK(DPWW2!Q14),"",DPWW2!Q14) | ¬¬IF(ISBLANK(DPWW2!R14),"",DPWW2!R14) | ¬¬IF(ISBLANK(DPWW2!S14),"",DPWW2!S14) | ¬¬IF(ISBLANK(DPWW2!T14),"",DPWW2!T14) | ¬¬IF(ISBLANK(DPWW2!U14),"",DPWW2!U14) | ¬¬IF(ISBLANK(DPWW2!V14),"",DPWW2!V14)
¬¬A361 | ¬¬IF(ISBLANK(DPWW2!BG14),"",DPWW2!BG14) | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W14),"",DPWW2!W14) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X14),"",DPWW2!X14)
¬¬A362 | ¬¬IF(ISBLANK(DPWW2!BJ14),"",DPWW2!BJ14) | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z14),"",DPWW2!Z14) | ¬¬IF(ISBLANK(DPWW2!AA14),"",DPWW2!AA14) | ¬¬IF(ISBLANK(DPWW2!AB14),"",DPWW2!AB14) | ¬¬IF(ISBLANK(DPWW2!AC14),"",DPWW2!AC14) | ¬¬IF(ISBLANK(DPWW2!AD14),"",DPWW2!AD14) | ¬¬IF(ISBLANK(DPWW2!AE14),"",DPWW2!AE14) | ¬¬IF(ISBLANK(DPWW2!AF14),"",DPWW2!AF14) | ¬¬IF(ISBLANK(DPWW2!AG14),"",DPWW2!AG14) | ¬¬IF(ISBLANK(DPWW2!AH14),"",DPWW2!AH14) | ¬¬IF(ISBLANK(DPWW2!AI14),"",DPWW2!AI14) | ¬¬IF(ISBLANK(DPWW2!AJ14),"",DPWW2!AJ14)
¬¬A363 | ¬¬IF(ISBLANK(DPWW2!BU14),"",DPWW2!BU14) | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK14),"",DPWW2!AK14) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL14),"",DPWW2!AL14)
¬¬A364 | ¬¬IF(ISBLANK(DPWW2!BX14),"",DPWW2!BX14) | ¬¬DPWW2!F14 & "," & DPWW2!G14 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H14),"",DPWW2!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN14),"",DPWW2!AN14) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO14),"",DPWW2!AO14)
¬¬A365 | ¬¬IF(ISBLANK(DPWW2!AT15),"",DPWW2!AT15) | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J15),"",DPWW2!J15)
¬¬A366 | ¬¬IF(ISBLANK(DPWW2!AV15),"",DPWW2!AV15) | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L15),"",DPWW2!L15) | ¬¬IF(ISBLANK(DPWW2!M15),"",DPWW2!M15) | ¬¬IF(ISBLANK(DPWW2!N15),"",DPWW2!N15) | ¬¬IF(ISBLANK(DPWW2!O15),"",DPWW2!O15) | ¬¬IF(ISBLANK(DPWW2!P15),"",DPWW2!P15) | ¬¬IF(ISBLANK(DPWW2!Q15),"",DPWW2!Q15) | ¬¬IF(ISBLANK(DPWW2!R15),"",DPWW2!R15) | ¬¬IF(ISBLANK(DPWW2!S15),"",DPWW2!S15) | ¬¬IF(ISBLANK(DPWW2!T15),"",DPWW2!T15) | ¬¬IF(ISBLANK(DPWW2!U15),"",DPWW2!U15) | ¬¬IF(ISBLANK(DPWW2!V15),"",DPWW2!V15)
¬¬A367 | ¬¬IF(ISBLANK(DPWW2!BG15),"",DPWW2!BG15) | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W15),"",DPWW2!W15) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X15),"",DPWW2!X15)
¬¬A368 | ¬¬IF(ISBLANK(DPWW2!BJ15),"",DPWW2!BJ15) | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z15),"",DPWW2!Z15) | ¬¬IF(ISBLANK(DPWW2!AA15),"",DPWW2!AA15) | ¬¬IF(ISBLANK(DPWW2!AB15),"",DPWW2!AB15) | ¬¬IF(ISBLANK(DPWW2!AC15),"",DPWW2!AC15) | ¬¬IF(ISBLANK(DPWW2!AD15),"",DPWW2!AD15) | ¬¬IF(ISBLANK(DPWW2!AE15),"",DPWW2!AE15) | ¬¬IF(ISBLANK(DPWW2!AF15),"",DPWW2!AF15) | ¬¬IF(ISBLANK(DPWW2!AG15),"",DPWW2!AG15) | ¬¬IF(ISBLANK(DPWW2!AH15),"",DPWW2!AH15) | ¬¬IF(ISBLANK(DPWW2!AI15),"",DPWW2!AI15) | ¬¬IF(ISBLANK(DPWW2!AJ15),"",DPWW2!AJ15)
¬¬A369 | ¬¬IF(ISBLANK(DPWW2!BU15),"",DPWW2!BU15) | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK15),"",DPWW2!AK15) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL15),"",DPWW2!AL15)
¬¬A370 | ¬¬IF(ISBLANK(DPWW2!BX15),"",DPWW2!BX15) | ¬¬DPWW2!F15 & "," & DPWW2!G15 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H15),"",DPWW2!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN15),"",DPWW2!AN15) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO15),"",DPWW2!AO15)
¬¬A371 | ¬¬IF(ISBLANK(DPWW2!AT16),"",DPWW2!AT16) | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J16),"",DPWW2!J16)
¬¬A372 | ¬¬IF(ISBLANK(DPWW2!AV16),"",DPWW2!AV16) | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L16),"",DPWW2!L16) | ¬¬IF(ISBLANK(DPWW2!M16),"",DPWW2!M16) | ¬¬IF(ISBLANK(DPWW2!N16),"",DPWW2!N16) | ¬¬IF(ISBLANK(DPWW2!O16),"",DPWW2!O16) | ¬¬IF(ISBLANK(DPWW2!P16),"",DPWW2!P16) | ¬¬IF(ISBLANK(DPWW2!Q16),"",DPWW2!Q16) | ¬¬IF(ISBLANK(DPWW2!R16),"",DPWW2!R16) | ¬¬IF(ISBLANK(DPWW2!S16),"",DPWW2!S16) | ¬¬IF(ISBLANK(DPWW2!T16),"",DPWW2!T16) | ¬¬IF(ISBLANK(DPWW2!U16),"",DPWW2!U16) | ¬¬IF(ISBLANK(DPWW2!V16),"",DPWW2!V16)
¬¬A373 | ¬¬IF(ISBLANK(DPWW2!BG16),"",DPWW2!BG16) | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W16),"",DPWW2!W16) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X16),"",DPWW2!X16)
¬¬A374 | ¬¬IF(ISBLANK(DPWW2!BJ16),"",DPWW2!BJ16) | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z16),"",DPWW2!Z16) | ¬¬IF(ISBLANK(DPWW2!AA16),"",DPWW2!AA16) | ¬¬IF(ISBLANK(DPWW2!AB16),"",DPWW2!AB16) | ¬¬IF(ISBLANK(DPWW2!AC16),"",DPWW2!AC16) | ¬¬IF(ISBLANK(DPWW2!AD16),"",DPWW2!AD16) | ¬¬IF(ISBLANK(DPWW2!AE16),"",DPWW2!AE16) | ¬¬IF(ISBLANK(DPWW2!AF16),"",DPWW2!AF16) | ¬¬IF(ISBLANK(DPWW2!AG16),"",DPWW2!AG16) | ¬¬IF(ISBLANK(DPWW2!AH16),"",DPWW2!AH16) | ¬¬IF(ISBLANK(DPWW2!AI16),"",DPWW2!AI16) | ¬¬IF(ISBLANK(DPWW2!AJ16),"",DPWW2!AJ16)
¬¬A375 | ¬¬IF(ISBLANK(DPWW2!BU16),"",DPWW2!BU16) | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK16),"",DPWW2!AK16) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL16),"",DPWW2!AL16)
¬¬A376 | ¬¬IF(ISBLANK(DPWW2!BX16),"",DPWW2!BX16) | ¬¬DPWW2!F16 & "," & DPWW2!G16 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H16),"",DPWW2!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN16),"",DPWW2!AN16) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO16),"",DPWW2!AO16)
¬¬A377 | ¬¬IF(ISBLANK(DPWW2!AT17),"",DPWW2!AT17) | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J17),"",DPWW2!J17)
¬¬A378 | ¬¬IF(ISBLANK(DPWW2!AV17),"",DPWW2!AV17) | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L17),"",DPWW2!L17) | ¬¬IF(ISBLANK(DPWW2!M17),"",DPWW2!M17) | ¬¬IF(ISBLANK(DPWW2!N17),"",DPWW2!N17) | ¬¬IF(ISBLANK(DPWW2!O17),"",DPWW2!O17) | ¬¬IF(ISBLANK(DPWW2!P17),"",DPWW2!P17) | ¬¬IF(ISBLANK(DPWW2!Q17),"",DPWW2!Q17) | ¬¬IF(ISBLANK(DPWW2!R17),"",DPWW2!R17) | ¬¬IF(ISBLANK(DPWW2!S17),"",DPWW2!S17) | ¬¬IF(ISBLANK(DPWW2!T17),"",DPWW2!T17) | ¬¬IF(ISBLANK(DPWW2!U17),"",DPWW2!U17) | ¬¬IF(ISBLANK(DPWW2!V17),"",DPWW2!V17)
¬¬A379 | ¬¬IF(ISBLANK(DPWW2!BG17),"",DPWW2!BG17) | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W17),"",DPWW2!W17) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X17),"",DPWW2!X17)
¬¬A380 | ¬¬IF(ISBLANK(DPWW2!BJ17),"",DPWW2!BJ17) | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z17),"",DPWW2!Z17) | ¬¬IF(ISBLANK(DPWW2!AA17),"",DPWW2!AA17) | ¬¬IF(ISBLANK(DPWW2!AB17),"",DPWW2!AB17) | ¬¬IF(ISBLANK(DPWW2!AC17),"",DPWW2!AC17) | ¬¬IF(ISBLANK(DPWW2!AD17),"",DPWW2!AD17) | ¬¬IF(ISBLANK(DPWW2!AE17),"",DPWW2!AE17) | ¬¬IF(ISBLANK(DPWW2!AF17),"",DPWW2!AF17) | ¬¬IF(ISBLANK(DPWW2!AG17),"",DPWW2!AG17) | ¬¬IF(ISBLANK(DPWW2!AH17),"",DPWW2!AH17) | ¬¬IF(ISBLANK(DPWW2!AI17),"",DPWW2!AI17) | ¬¬IF(ISBLANK(DPWW2!AJ17),"",DPWW2!AJ17)
¬¬A381 | ¬¬IF(ISBLANK(DPWW2!BU17),"",DPWW2!BU17) | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK17),"",DPWW2!AK17) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL17),"",DPWW2!AL17)
¬¬A382 | ¬¬IF(ISBLANK(DPWW2!BX17),"",DPWW2!BX17) | ¬¬DPWW2!F17 & "," & DPWW2!G17 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H17),"",DPWW2!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN17),"",DPWW2!AN17) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO17),"",DPWW2!AO17)
¬¬A383 | ¬¬IF(ISBLANK(DPWW2!AT18),"",DPWW2!AT18) | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J18),"",DPWW2!J18)
¬¬A384 | ¬¬IF(ISBLANK(DPWW2!AV18),"",DPWW2!AV18) | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L18),"",DPWW2!L18) | ¬¬IF(ISBLANK(DPWW2!M18),"",DPWW2!M18) | ¬¬IF(ISBLANK(DPWW2!N18),"",DPWW2!N18) | ¬¬IF(ISBLANK(DPWW2!O18),"",DPWW2!O18) | ¬¬IF(ISBLANK(DPWW2!P18),"",DPWW2!P18) | ¬¬IF(ISBLANK(DPWW2!Q18),"",DPWW2!Q18) | ¬¬IF(ISBLANK(DPWW2!R18),"",DPWW2!R18) | ¬¬IF(ISBLANK(DPWW2!S18),"",DPWW2!S18) | ¬¬IF(ISBLANK(DPWW2!T18),"",DPWW2!T18) | ¬¬IF(ISBLANK(DPWW2!U18),"",DPWW2!U18) | ¬¬IF(ISBLANK(DPWW2!V18),"",DPWW2!V18)
¬¬A385 | ¬¬IF(ISBLANK(DPWW2!BG18),"",DPWW2!BG18) | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W18),"",DPWW2!W18) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X18),"",DPWW2!X18)
¬¬A386 | ¬¬IF(ISBLANK(DPWW2!BJ18),"",DPWW2!BJ18) | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z18),"",DPWW2!Z18) | ¬¬IF(ISBLANK(DPWW2!AA18),"",DPWW2!AA18) | ¬¬IF(ISBLANK(DPWW2!AB18),"",DPWW2!AB18) | ¬¬IF(ISBLANK(DPWW2!AC18),"",DPWW2!AC18) | ¬¬IF(ISBLANK(DPWW2!AD18),"",DPWW2!AD18) | ¬¬IF(ISBLANK(DPWW2!AE18),"",DPWW2!AE18) | ¬¬IF(ISBLANK(DPWW2!AF18),"",DPWW2!AF18) | ¬¬IF(ISBLANK(DPWW2!AG18),"",DPWW2!AG18) | ¬¬IF(ISBLANK(DPWW2!AH18),"",DPWW2!AH18) | ¬¬IF(ISBLANK(DPWW2!AI18),"",DPWW2!AI18) | ¬¬IF(ISBLANK(DPWW2!AJ18),"",DPWW2!AJ18)
¬¬A387 | ¬¬IF(ISBLANK(DPWW2!BU18),"",DPWW2!BU18) | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK18),"",DPWW2!AK18) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL18),"",DPWW2!AL18)
¬¬A388 | ¬¬IF(ISBLANK(DPWW2!BX18),"",DPWW2!BX18) | ¬¬DPWW2!F18 & "," & DPWW2!G18 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H18),"",DPWW2!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN18),"",DPWW2!AN18) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO18),"",DPWW2!AO18)
¬¬A389 | ¬¬IF(ISBLANK(DPWW2!AT19),"",DPWW2!AT19) | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J19),"",DPWW2!J19)
¬¬A390 | ¬¬IF(ISBLANK(DPWW2!AV19),"",DPWW2!AV19) | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L19),"",DPWW2!L19) | ¬¬IF(ISBLANK(DPWW2!M19),"",DPWW2!M19) | ¬¬IF(ISBLANK(DPWW2!N19),"",DPWW2!N19) | ¬¬IF(ISBLANK(DPWW2!O19),"",DPWW2!O19) | ¬¬IF(ISBLANK(DPWW2!P19),"",DPWW2!P19) | ¬¬IF(ISBLANK(DPWW2!Q19),"",DPWW2!Q19) | ¬¬IF(ISBLANK(DPWW2!R19),"",DPWW2!R19) | ¬¬IF(ISBLANK(DPWW2!S19),"",DPWW2!S19) | ¬¬IF(ISBLANK(DPWW2!T19),"",DPWW2!T19) | ¬¬IF(ISBLANK(DPWW2!U19),"",DPWW2!U19) | ¬¬IF(ISBLANK(DPWW2!V19),"",DPWW2!V19)
¬¬A391 | ¬¬IF(ISBLANK(DPWW2!BG19),"",DPWW2!BG19) | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W19),"",DPWW2!W19) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X19),"",DPWW2!X19)
¬¬A392 | ¬¬IF(ISBLANK(DPWW2!BJ19),"",DPWW2!BJ19) | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z19),"",DPWW2!Z19) | ¬¬IF(ISBLANK(DPWW2!AA19),"",DPWW2!AA19) | ¬¬IF(ISBLANK(DPWW2!AB19),"",DPWW2!AB19) | ¬¬IF(ISBLANK(DPWW2!AC19),"",DPWW2!AC19) | ¬¬IF(ISBLANK(DPWW2!AD19),"",DPWW2!AD19) | ¬¬IF(ISBLANK(DPWW2!AE19),"",DPWW2!AE19) | ¬¬IF(ISBLANK(DPWW2!AF19),"",DPWW2!AF19) | ¬¬IF(ISBLANK(DPWW2!AG19),"",DPWW2!AG19) | ¬¬IF(ISBLANK(DPWW2!AH19),"",DPWW2!AH19) | ¬¬IF(ISBLANK(DPWW2!AI19),"",DPWW2!AI19) | ¬¬IF(ISBLANK(DPWW2!AJ19),"",DPWW2!AJ19)
¬¬A393 | ¬¬IF(ISBLANK(DPWW2!BU19),"",DPWW2!BU19) | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK19),"",DPWW2!AK19) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL19),"",DPWW2!AL19)
¬¬A394 | ¬¬IF(ISBLANK(DPWW2!BX19),"",DPWW2!BX19) | ¬¬DPWW2!F19 & "," & DPWW2!G19 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H19),"",DPWW2!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN19),"",DPWW2!AN19) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO19),"",DPWW2!AO19)
¬¬A395 | ¬¬IF(ISBLANK(DPWW2!AT20),"",DPWW2!AT20) | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J20),"",DPWW2!J20)
¬¬A396 | ¬¬IF(ISBLANK(DPWW2!AV20),"",DPWW2!AV20) | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L20),"",DPWW2!L20) | ¬¬IF(ISBLANK(DPWW2!M20),"",DPWW2!M20) | ¬¬IF(ISBLANK(DPWW2!N20),"",DPWW2!N20) | ¬¬IF(ISBLANK(DPWW2!O20),"",DPWW2!O20) | ¬¬IF(ISBLANK(DPWW2!P20),"",DPWW2!P20) | ¬¬IF(ISBLANK(DPWW2!Q20),"",DPWW2!Q20) | ¬¬IF(ISBLANK(DPWW2!R20),"",DPWW2!R20) | ¬¬IF(ISBLANK(DPWW2!S20),"",DPWW2!S20) | ¬¬IF(ISBLANK(DPWW2!T20),"",DPWW2!T20) | ¬¬IF(ISBLANK(DPWW2!U20),"",DPWW2!U20) | ¬¬IF(ISBLANK(DPWW2!V20),"",DPWW2!V20)
¬¬A397 | ¬¬IF(ISBLANK(DPWW2!BG20),"",DPWW2!BG20) | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W20),"",DPWW2!W20) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X20),"",DPWW2!X20)
¬¬A398 | ¬¬IF(ISBLANK(DPWW2!BJ20),"",DPWW2!BJ20) | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z20),"",DPWW2!Z20) | ¬¬IF(ISBLANK(DPWW2!AA20),"",DPWW2!AA20) | ¬¬IF(ISBLANK(DPWW2!AB20),"",DPWW2!AB20) | ¬¬IF(ISBLANK(DPWW2!AC20),"",DPWW2!AC20) | ¬¬IF(ISBLANK(DPWW2!AD20),"",DPWW2!AD20) | ¬¬IF(ISBLANK(DPWW2!AE20),"",DPWW2!AE20) | ¬¬IF(ISBLANK(DPWW2!AF20),"",DPWW2!AF20) | ¬¬IF(ISBLANK(DPWW2!AG20),"",DPWW2!AG20) | ¬¬IF(ISBLANK(DPWW2!AH20),"",DPWW2!AH20) | ¬¬IF(ISBLANK(DPWW2!AI20),"",DPWW2!AI20) | ¬¬IF(ISBLANK(DPWW2!AJ20),"",DPWW2!AJ20)
¬¬A399 | ¬¬IF(ISBLANK(DPWW2!BU20),"",DPWW2!BU20) | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK20),"",DPWW2!AK20) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL20),"",DPWW2!AL20)
¬¬A400 | ¬¬IF(ISBLANK(DPWW2!BX20),"",DPWW2!BX20) | ¬¬DPWW2!F20 & "," & DPWW2!G20 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H20),"",DPWW2!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN20),"",DPWW2!AN20) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO20),"",DPWW2!AO20)
¬¬A401 | ¬¬IF(ISBLANK(DPWW2!AT21),"",DPWW2!AT21) | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J21),"",DPWW2!J21)
¬¬A402 | ¬¬IF(ISBLANK(DPWW2!AV21),"",DPWW2!AV21) | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L21),"",DPWW2!L21) | ¬¬IF(ISBLANK(DPWW2!M21),"",DPWW2!M21) | ¬¬IF(ISBLANK(DPWW2!N21),"",DPWW2!N21) | ¬¬IF(ISBLANK(DPWW2!O21),"",DPWW2!O21) | ¬¬IF(ISBLANK(DPWW2!P21),"",DPWW2!P21) | ¬¬IF(ISBLANK(DPWW2!Q21),"",DPWW2!Q21) | ¬¬IF(ISBLANK(DPWW2!R21),"",DPWW2!R21) | ¬¬IF(ISBLANK(DPWW2!S21),"",DPWW2!S21) | ¬¬IF(ISBLANK(DPWW2!T21),"",DPWW2!T21) | ¬¬IF(ISBLANK(DPWW2!U21),"",DPWW2!U21) | ¬¬IF(ISBLANK(DPWW2!V21),"",DPWW2!V21)
¬¬A403 | ¬¬IF(ISBLANK(DPWW2!BG21),"",DPWW2!BG21) | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W21),"",DPWW2!W21) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X21),"",DPWW2!X21)
¬¬A404 | ¬¬IF(ISBLANK(DPWW2!BJ21),"",DPWW2!BJ21) | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z21),"",DPWW2!Z21) | ¬¬IF(ISBLANK(DPWW2!AA21),"",DPWW2!AA21) | ¬¬IF(ISBLANK(DPWW2!AB21),"",DPWW2!AB21) | ¬¬IF(ISBLANK(DPWW2!AC21),"",DPWW2!AC21) | ¬¬IF(ISBLANK(DPWW2!AD21),"",DPWW2!AD21) | ¬¬IF(ISBLANK(DPWW2!AE21),"",DPWW2!AE21) | ¬¬IF(ISBLANK(DPWW2!AF21),"",DPWW2!AF21) | ¬¬IF(ISBLANK(DPWW2!AG21),"",DPWW2!AG21) | ¬¬IF(ISBLANK(DPWW2!AH21),"",DPWW2!AH21) | ¬¬IF(ISBLANK(DPWW2!AI21),"",DPWW2!AI21) | ¬¬IF(ISBLANK(DPWW2!AJ21),"",DPWW2!AJ21)
¬¬A405 | ¬¬IF(ISBLANK(DPWW2!BU21),"",DPWW2!BU21) | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK21),"",DPWW2!AK21) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL21),"",DPWW2!AL21)
¬¬A406 | ¬¬IF(ISBLANK(DPWW2!BX21),"",DPWW2!BX21) | ¬¬DPWW2!F21 & "," & DPWW2!G21 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H21),"",DPWW2!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN21),"",DPWW2!AN21) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO21),"",DPWW2!AO21)
¬¬A407 | ¬¬IF(ISBLANK(DPWW2!AT22),"",DPWW2!AT22) | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J22),"",DPWW2!J22)
¬¬A408 | ¬¬IF(ISBLANK(DPWW2!AV22),"",DPWW2!AV22) | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L22),"",DPWW2!L22) | ¬¬IF(ISBLANK(DPWW2!M22),"",DPWW2!M22) | ¬¬IF(ISBLANK(DPWW2!N22),"",DPWW2!N22) | ¬¬IF(ISBLANK(DPWW2!O22),"",DPWW2!O22) | ¬¬IF(ISBLANK(DPWW2!P22),"",DPWW2!P22) | ¬¬IF(ISBLANK(DPWW2!Q22),"",DPWW2!Q22) | ¬¬IF(ISBLANK(DPWW2!R22),"",DPWW2!R22) | ¬¬IF(ISBLANK(DPWW2!S22),"",DPWW2!S22) | ¬¬IF(ISBLANK(DPWW2!T22),"",DPWW2!T22) | ¬¬IF(ISBLANK(DPWW2!U22),"",DPWW2!U22) | ¬¬IF(ISBLANK(DPWW2!V22),"",DPWW2!V22)
¬¬A409 | ¬¬IF(ISBLANK(DPWW2!BG22),"",DPWW2!BG22) | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W22),"",DPWW2!W22) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X22),"",DPWW2!X22)
¬¬A410 | ¬¬IF(ISBLANK(DPWW2!BJ22),"",DPWW2!BJ22) | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z22),"",DPWW2!Z22) | ¬¬IF(ISBLANK(DPWW2!AA22),"",DPWW2!AA22) | ¬¬IF(ISBLANK(DPWW2!AB22),"",DPWW2!AB22) | ¬¬IF(ISBLANK(DPWW2!AC22),"",DPWW2!AC22) | ¬¬IF(ISBLANK(DPWW2!AD22),"",DPWW2!AD22) | ¬¬IF(ISBLANK(DPWW2!AE22),"",DPWW2!AE22) | ¬¬IF(ISBLANK(DPWW2!AF22),"",DPWW2!AF22) | ¬¬IF(ISBLANK(DPWW2!AG22),"",DPWW2!AG22) | ¬¬IF(ISBLANK(DPWW2!AH22),"",DPWW2!AH22) | ¬¬IF(ISBLANK(DPWW2!AI22),"",DPWW2!AI22) | ¬¬IF(ISBLANK(DPWW2!AJ22),"",DPWW2!AJ22)
¬¬A411 | ¬¬IF(ISBLANK(DPWW2!BU22),"",DPWW2!BU22) | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK22),"",DPWW2!AK22) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL22),"",DPWW2!AL22)
¬¬A412 | ¬¬IF(ISBLANK(DPWW2!BX22),"",DPWW2!BX22) | ¬¬DPWW2!F22 & "," & DPWW2!G22 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H22),"",DPWW2!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN22),"",DPWW2!AN22) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO22),"",DPWW2!AO22)
¬¬A413 | ¬¬IF(ISBLANK(DPWW2!AT23),"",DPWW2!AT23) | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J23),"",DPWW2!J23)
¬¬A414 | ¬¬IF(ISBLANK(DPWW2!AV23),"",DPWW2!AV23) | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L23),"",DPWW2!L23) | ¬¬IF(ISBLANK(DPWW2!M23),"",DPWW2!M23) | ¬¬IF(ISBLANK(DPWW2!N23),"",DPWW2!N23) | ¬¬IF(ISBLANK(DPWW2!O23),"",DPWW2!O23) | ¬¬IF(ISBLANK(DPWW2!P23),"",DPWW2!P23) | ¬¬IF(ISBLANK(DPWW2!Q23),"",DPWW2!Q23) | ¬¬IF(ISBLANK(DPWW2!R23),"",DPWW2!R23) | ¬¬IF(ISBLANK(DPWW2!S23),"",DPWW2!S23) | ¬¬IF(ISBLANK(DPWW2!T23),"",DPWW2!T23) | ¬¬IF(ISBLANK(DPWW2!U23),"",DPWW2!U23) | ¬¬IF(ISBLANK(DPWW2!V23),"",DPWW2!V23)
¬¬A415 | ¬¬IF(ISBLANK(DPWW2!BG23),"",DPWW2!BG23) | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W23),"",DPWW2!W23) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X23),"",DPWW2!X23)
¬¬A416 | ¬¬IF(ISBLANK(DPWW2!BJ23),"",DPWW2!BJ23) | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z23),"",DPWW2!Z23) | ¬¬IF(ISBLANK(DPWW2!AA23),"",DPWW2!AA23) | ¬¬IF(ISBLANK(DPWW2!AB23),"",DPWW2!AB23) | ¬¬IF(ISBLANK(DPWW2!AC23),"",DPWW2!AC23) | ¬¬IF(ISBLANK(DPWW2!AD23),"",DPWW2!AD23) | ¬¬IF(ISBLANK(DPWW2!AE23),"",DPWW2!AE23) | ¬¬IF(ISBLANK(DPWW2!AF23),"",DPWW2!AF23) | ¬¬IF(ISBLANK(DPWW2!AG23),"",DPWW2!AG23) | ¬¬IF(ISBLANK(DPWW2!AH23),"",DPWW2!AH23) | ¬¬IF(ISBLANK(DPWW2!AI23),"",DPWW2!AI23) | ¬¬IF(ISBLANK(DPWW2!AJ23),"",DPWW2!AJ23)
¬¬A417 | ¬¬IF(ISBLANK(DPWW2!BU23),"",DPWW2!BU23) | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK23),"",DPWW2!AK23) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL23),"",DPWW2!AL23)
¬¬A418 | ¬¬IF(ISBLANK(DPWW2!BX23),"",DPWW2!BX23) | ¬¬DPWW2!F23 & "," & DPWW2!G23 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H23),"",DPWW2!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN23),"",DPWW2!AN23) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO23),"",DPWW2!AO23)
¬¬A419 | ¬¬IF(ISBLANK(DPWW2!AT24),"",DPWW2!AT24) | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J24),"",DPWW2!J24)
¬¬A420 | ¬¬IF(ISBLANK(DPWW2!AV24),"",DPWW2!AV24) | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L24),"",DPWW2!L24) | ¬¬IF(ISBLANK(DPWW2!M24),"",DPWW2!M24) | ¬¬IF(ISBLANK(DPWW2!N24),"",DPWW2!N24) | ¬¬IF(ISBLANK(DPWW2!O24),"",DPWW2!O24) | ¬¬IF(ISBLANK(DPWW2!P24),"",DPWW2!P24) | ¬¬IF(ISBLANK(DPWW2!Q24),"",DPWW2!Q24) | ¬¬IF(ISBLANK(DPWW2!R24),"",DPWW2!R24) | ¬¬IF(ISBLANK(DPWW2!S24),"",DPWW2!S24) | ¬¬IF(ISBLANK(DPWW2!T24),"",DPWW2!T24) | ¬¬IF(ISBLANK(DPWW2!U24),"",DPWW2!U24) | ¬¬IF(ISBLANK(DPWW2!V24),"",DPWW2!V24)
¬¬A421 | ¬¬IF(ISBLANK(DPWW2!BG24),"",DPWW2!BG24) | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W24),"",DPWW2!W24) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X24),"",DPWW2!X24)
¬¬A422 | ¬¬IF(ISBLANK(DPWW2!BJ24),"",DPWW2!BJ24) | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z24),"",DPWW2!Z24) | ¬¬IF(ISBLANK(DPWW2!AA24),"",DPWW2!AA24) | ¬¬IF(ISBLANK(DPWW2!AB24),"",DPWW2!AB24) | ¬¬IF(ISBLANK(DPWW2!AC24),"",DPWW2!AC24) | ¬¬IF(ISBLANK(DPWW2!AD24),"",DPWW2!AD24) | ¬¬IF(ISBLANK(DPWW2!AE24),"",DPWW2!AE24) | ¬¬IF(ISBLANK(DPWW2!AF24),"",DPWW2!AF24) | ¬¬IF(ISBLANK(DPWW2!AG24),"",DPWW2!AG24) | ¬¬IF(ISBLANK(DPWW2!AH24),"",DPWW2!AH24) | ¬¬IF(ISBLANK(DPWW2!AI24),"",DPWW2!AI24) | ¬¬IF(ISBLANK(DPWW2!AJ24),"",DPWW2!AJ24)
¬¬A423 | ¬¬IF(ISBLANK(DPWW2!BU24),"",DPWW2!BU24) | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK24),"",DPWW2!AK24) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL24),"",DPWW2!AL24)
¬¬A424 | ¬¬IF(ISBLANK(DPWW2!BX24),"",DPWW2!BX24) | ¬¬DPWW2!F24 & "," & DPWW2!G24 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H24),"",DPWW2!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN24),"",DPWW2!AN24) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO24),"",DPWW2!AO24)
¬¬A425 | ¬¬IF(ISBLANK(DPWW2!AT25),"",DPWW2!AT25) | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J25),"",DPWW2!J25)
¬¬A426 | ¬¬IF(ISBLANK(DPWW2!AV25),"",DPWW2!AV25) | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L25),"",DPWW2!L25) | ¬¬IF(ISBLANK(DPWW2!M25),"",DPWW2!M25) | ¬¬IF(ISBLANK(DPWW2!N25),"",DPWW2!N25) | ¬¬IF(ISBLANK(DPWW2!O25),"",DPWW2!O25) | ¬¬IF(ISBLANK(DPWW2!P25),"",DPWW2!P25) | ¬¬IF(ISBLANK(DPWW2!Q25),"",DPWW2!Q25) | ¬¬IF(ISBLANK(DPWW2!R25),"",DPWW2!R25) | ¬¬IF(ISBLANK(DPWW2!S25),"",DPWW2!S25) | ¬¬IF(ISBLANK(DPWW2!T25),"",DPWW2!T25) | ¬¬IF(ISBLANK(DPWW2!U25),"",DPWW2!U25) | ¬¬IF(ISBLANK(DPWW2!V25),"",DPWW2!V25)
¬¬A427 | ¬¬IF(ISBLANK(DPWW2!BG25),"",DPWW2!BG25) | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W25),"",DPWW2!W25) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X25),"",DPWW2!X25)
¬¬A428 | ¬¬IF(ISBLANK(DPWW2!BJ25),"",DPWW2!BJ25) | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z25),"",DPWW2!Z25) | ¬¬IF(ISBLANK(DPWW2!AA25),"",DPWW2!AA25) | ¬¬IF(ISBLANK(DPWW2!AB25),"",DPWW2!AB25) | ¬¬IF(ISBLANK(DPWW2!AC25),"",DPWW2!AC25) | ¬¬IF(ISBLANK(DPWW2!AD25),"",DPWW2!AD25) | ¬¬IF(ISBLANK(DPWW2!AE25),"",DPWW2!AE25) | ¬¬IF(ISBLANK(DPWW2!AF25),"",DPWW2!AF25) | ¬¬IF(ISBLANK(DPWW2!AG25),"",DPWW2!AG25) | ¬¬IF(ISBLANK(DPWW2!AH25),"",DPWW2!AH25) | ¬¬IF(ISBLANK(DPWW2!AI25),"",DPWW2!AI25) | ¬¬IF(ISBLANK(DPWW2!AJ25),"",DPWW2!AJ25)
¬¬A429 | ¬¬IF(ISBLANK(DPWW2!BU25),"",DPWW2!BU25) | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK25),"",DPWW2!AK25) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL25),"",DPWW2!AL25)
¬¬A430 | ¬¬IF(ISBLANK(DPWW2!BX25),"",DPWW2!BX25) | ¬¬DPWW2!F25 & "," & DPWW2!G25 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H25),"",DPWW2!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN25),"",DPWW2!AN25) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO25),"",DPWW2!AO25)
¬¬A431 | ¬¬IF(ISBLANK(DPWW2!AT26),"",DPWW2!AT26) | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J26),"",DPWW2!J26)
¬¬A432 | ¬¬IF(ISBLANK(DPWW2!AV26),"",DPWW2!AV26) | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L26),"",DPWW2!L26) | ¬¬IF(ISBLANK(DPWW2!M26),"",DPWW2!M26) | ¬¬IF(ISBLANK(DPWW2!N26),"",DPWW2!N26) | ¬¬IF(ISBLANK(DPWW2!O26),"",DPWW2!O26) | ¬¬IF(ISBLANK(DPWW2!P26),"",DPWW2!P26) | ¬¬IF(ISBLANK(DPWW2!Q26),"",DPWW2!Q26) | ¬¬IF(ISBLANK(DPWW2!R26),"",DPWW2!R26) | ¬¬IF(ISBLANK(DPWW2!S26),"",DPWW2!S26) | ¬¬IF(ISBLANK(DPWW2!T26),"",DPWW2!T26) | ¬¬IF(ISBLANK(DPWW2!U26),"",DPWW2!U26) | ¬¬IF(ISBLANK(DPWW2!V26),"",DPWW2!V26)
¬¬A433 | ¬¬IF(ISBLANK(DPWW2!BG26),"",DPWW2!BG26) | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W26),"",DPWW2!W26) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X26),"",DPWW2!X26)
¬¬A434 | ¬¬IF(ISBLANK(DPWW2!BJ26),"",DPWW2!BJ26) | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z26),"",DPWW2!Z26) | ¬¬IF(ISBLANK(DPWW2!AA26),"",DPWW2!AA26) | ¬¬IF(ISBLANK(DPWW2!AB26),"",DPWW2!AB26) | ¬¬IF(ISBLANK(DPWW2!AC26),"",DPWW2!AC26) | ¬¬IF(ISBLANK(DPWW2!AD26),"",DPWW2!AD26) | ¬¬IF(ISBLANK(DPWW2!AE26),"",DPWW2!AE26) | ¬¬IF(ISBLANK(DPWW2!AF26),"",DPWW2!AF26) | ¬¬IF(ISBLANK(DPWW2!AG26),"",DPWW2!AG26) | ¬¬IF(ISBLANK(DPWW2!AH26),"",DPWW2!AH26) | ¬¬IF(ISBLANK(DPWW2!AI26),"",DPWW2!AI26) | ¬¬IF(ISBLANK(DPWW2!AJ26),"",DPWW2!AJ26)
¬¬A435 | ¬¬IF(ISBLANK(DPWW2!BU26),"",DPWW2!BU26) | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK26),"",DPWW2!AK26) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL26),"",DPWW2!AL26)
¬¬A436 | ¬¬IF(ISBLANK(DPWW2!BX26),"",DPWW2!BX26) | ¬¬DPWW2!F26 & "," & DPWW2!G26 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H26),"",DPWW2!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN26),"",DPWW2!AN26) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO26),"",DPWW2!AO26)
¬¬A437 | ¬¬IF(ISBLANK(DPWW2!AT27),"",DPWW2!AT27) | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J27),"",DPWW2!J27)
¬¬A438 | ¬¬IF(ISBLANK(DPWW2!AV27),"",DPWW2!AV27) | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L27),"",DPWW2!L27) | ¬¬IF(ISBLANK(DPWW2!M27),"",DPWW2!M27) | ¬¬IF(ISBLANK(DPWW2!N27),"",DPWW2!N27) | ¬¬IF(ISBLANK(DPWW2!O27),"",DPWW2!O27) | ¬¬IF(ISBLANK(DPWW2!P27),"",DPWW2!P27) | ¬¬IF(ISBLANK(DPWW2!Q27),"",DPWW2!Q27) | ¬¬IF(ISBLANK(DPWW2!R27),"",DPWW2!R27) | ¬¬IF(ISBLANK(DPWW2!S27),"",DPWW2!S27) | ¬¬IF(ISBLANK(DPWW2!T27),"",DPWW2!T27) | ¬¬IF(ISBLANK(DPWW2!U27),"",DPWW2!U27) | ¬¬IF(ISBLANK(DPWW2!V27),"",DPWW2!V27)
¬¬A439 | ¬¬IF(ISBLANK(DPWW2!BG27),"",DPWW2!BG27) | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W27),"",DPWW2!W27) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X27),"",DPWW2!X27)
¬¬A440 | ¬¬IF(ISBLANK(DPWW2!BJ27),"",DPWW2!BJ27) | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z27),"",DPWW2!Z27) | ¬¬IF(ISBLANK(DPWW2!AA27),"",DPWW2!AA27) | ¬¬IF(ISBLANK(DPWW2!AB27),"",DPWW2!AB27) | ¬¬IF(ISBLANK(DPWW2!AC27),"",DPWW2!AC27) | ¬¬IF(ISBLANK(DPWW2!AD27),"",DPWW2!AD27) | ¬¬IF(ISBLANK(DPWW2!AE27),"",DPWW2!AE27) | ¬¬IF(ISBLANK(DPWW2!AF27),"",DPWW2!AF27) | ¬¬IF(ISBLANK(DPWW2!AG27),"",DPWW2!AG27) | ¬¬IF(ISBLANK(DPWW2!AH27),"",DPWW2!AH27) | ¬¬IF(ISBLANK(DPWW2!AI27),"",DPWW2!AI27) | ¬¬IF(ISBLANK(DPWW2!AJ27),"",DPWW2!AJ27)
¬¬A441 | ¬¬IF(ISBLANK(DPWW2!BU27),"",DPWW2!BU27) | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK27),"",DPWW2!AK27) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL27),"",DPWW2!AL27)
¬¬A442 | ¬¬IF(ISBLANK(DPWW2!BX27),"",DPWW2!BX27) | ¬¬DPWW2!F27 & "," & DPWW2!G27 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H27),"",DPWW2!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN27),"",DPWW2!AN27) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO27),"",DPWW2!AO27)
¬¬A443 | ¬¬IF(ISBLANK(DPWW2!AT28),"",DPWW2!AT28) | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J28),"",DPWW2!J28)
¬¬A444 | ¬¬IF(ISBLANK(DPWW2!AV28),"",DPWW2!AV28) | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L28),"",DPWW2!L28) | ¬¬IF(ISBLANK(DPWW2!M28),"",DPWW2!M28) | ¬¬IF(ISBLANK(DPWW2!N28),"",DPWW2!N28) | ¬¬IF(ISBLANK(DPWW2!O28),"",DPWW2!O28) | ¬¬IF(ISBLANK(DPWW2!P28),"",DPWW2!P28) | ¬¬IF(ISBLANK(DPWW2!Q28),"",DPWW2!Q28) | ¬¬IF(ISBLANK(DPWW2!R28),"",DPWW2!R28) | ¬¬IF(ISBLANK(DPWW2!S28),"",DPWW2!S28) | ¬¬IF(ISBLANK(DPWW2!T28),"",DPWW2!T28) | ¬¬IF(ISBLANK(DPWW2!U28),"",DPWW2!U28) | ¬¬IF(ISBLANK(DPWW2!V28),"",DPWW2!V28)
¬¬A445 | ¬¬IF(ISBLANK(DPWW2!BG28),"",DPWW2!BG28) | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W28),"",DPWW2!W28) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X28),"",DPWW2!X28)
¬¬A446 | ¬¬IF(ISBLANK(DPWW2!BJ28),"",DPWW2!BJ28) | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z28),"",DPWW2!Z28) | ¬¬IF(ISBLANK(DPWW2!AA28),"",DPWW2!AA28) | ¬¬IF(ISBLANK(DPWW2!AB28),"",DPWW2!AB28) | ¬¬IF(ISBLANK(DPWW2!AC28),"",DPWW2!AC28) | ¬¬IF(ISBLANK(DPWW2!AD28),"",DPWW2!AD28) | ¬¬IF(ISBLANK(DPWW2!AE28),"",DPWW2!AE28) | ¬¬IF(ISBLANK(DPWW2!AF28),"",DPWW2!AF28) | ¬¬IF(ISBLANK(DPWW2!AG28),"",DPWW2!AG28) | ¬¬IF(ISBLANK(DPWW2!AH28),"",DPWW2!AH28) | ¬¬IF(ISBLANK(DPWW2!AI28),"",DPWW2!AI28) | ¬¬IF(ISBLANK(DPWW2!AJ28),"",DPWW2!AJ28)
¬¬A447 | ¬¬IF(ISBLANK(DPWW2!BU28),"",DPWW2!BU28) | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK28),"",DPWW2!AK28) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL28),"",DPWW2!AL28)
¬¬A448 | ¬¬IF(ISBLANK(DPWW2!BX28),"",DPWW2!BX28) | ¬¬DPWW2!F28 & "," & DPWW2!G28 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H28),"",DPWW2!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN28),"",DPWW2!AN28) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO28),"",DPWW2!AO28)
¬¬A449 | ¬¬IF(ISBLANK(DPWW2!AT29),"",DPWW2!AT29) | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J29),"",DPWW2!J29)
¬¬A450 | ¬¬IF(ISBLANK(DPWW2!AV29),"",DPWW2!AV29) | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L29),"",DPWW2!L29) | ¬¬IF(ISBLANK(DPWW2!M29),"",DPWW2!M29) | ¬¬IF(ISBLANK(DPWW2!N29),"",DPWW2!N29) | ¬¬IF(ISBLANK(DPWW2!O29),"",DPWW2!O29) | ¬¬IF(ISBLANK(DPWW2!P29),"",DPWW2!P29) | ¬¬IF(ISBLANK(DPWW2!Q29),"",DPWW2!Q29) | ¬¬IF(ISBLANK(DPWW2!R29),"",DPWW2!R29) | ¬¬IF(ISBLANK(DPWW2!S29),"",DPWW2!S29) | ¬¬IF(ISBLANK(DPWW2!T29),"",DPWW2!T29) | ¬¬IF(ISBLANK(DPWW2!U29),"",DPWW2!U29) | ¬¬IF(ISBLANK(DPWW2!V29),"",DPWW2!V29)
¬¬A451 | ¬¬IF(ISBLANK(DPWW2!BG29),"",DPWW2!BG29) | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W29),"",DPWW2!W29) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X29),"",DPWW2!X29)
¬¬A452 | ¬¬IF(ISBLANK(DPWW2!BJ29),"",DPWW2!BJ29) | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z29),"",DPWW2!Z29) | ¬¬IF(ISBLANK(DPWW2!AA29),"",DPWW2!AA29) | ¬¬IF(ISBLANK(DPWW2!AB29),"",DPWW2!AB29) | ¬¬IF(ISBLANK(DPWW2!AC29),"",DPWW2!AC29) | ¬¬IF(ISBLANK(DPWW2!AD29),"",DPWW2!AD29) | ¬¬IF(ISBLANK(DPWW2!AE29),"",DPWW2!AE29) | ¬¬IF(ISBLANK(DPWW2!AF29),"",DPWW2!AF29) | ¬¬IF(ISBLANK(DPWW2!AG29),"",DPWW2!AG29) | ¬¬IF(ISBLANK(DPWW2!AH29),"",DPWW2!AH29) | ¬¬IF(ISBLANK(DPWW2!AI29),"",DPWW2!AI29) | ¬¬IF(ISBLANK(DPWW2!AJ29),"",DPWW2!AJ29)
¬¬A453 | ¬¬IF(ISBLANK(DPWW2!BU29),"",DPWW2!BU29) | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK29),"",DPWW2!AK29) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL29),"",DPWW2!AL29)
¬¬A454 | ¬¬IF(ISBLANK(DPWW2!BX29),"",DPWW2!BX29) | ¬¬DPWW2!F29 & "," & DPWW2!G29 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H29),"",DPWW2!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN29),"",DPWW2!AN29) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO29),"",DPWW2!AO29)
¬¬A455 | ¬¬IF(ISBLANK(DPWW2!AT30),"",DPWW2!AT30) | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J30),"",DPWW2!J30)
¬¬A456 | ¬¬IF(ISBLANK(DPWW2!AV30),"",DPWW2!AV30) | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L30),"",DPWW2!L30) | ¬¬IF(ISBLANK(DPWW2!M30),"",DPWW2!M30) | ¬¬IF(ISBLANK(DPWW2!N30),"",DPWW2!N30) | ¬¬IF(ISBLANK(DPWW2!O30),"",DPWW2!O30) | ¬¬IF(ISBLANK(DPWW2!P30),"",DPWW2!P30) | ¬¬IF(ISBLANK(DPWW2!Q30),"",DPWW2!Q30) | ¬¬IF(ISBLANK(DPWW2!R30),"",DPWW2!R30) | ¬¬IF(ISBLANK(DPWW2!S30),"",DPWW2!S30) | ¬¬IF(ISBLANK(DPWW2!T30),"",DPWW2!T30) | ¬¬IF(ISBLANK(DPWW2!U30),"",DPWW2!U30) | ¬¬IF(ISBLANK(DPWW2!V30),"",DPWW2!V30)
¬¬A457 | ¬¬IF(ISBLANK(DPWW2!BG30),"",DPWW2!BG30) | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W30),"",DPWW2!W30) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X30),"",DPWW2!X30)
¬¬A458 | ¬¬IF(ISBLANK(DPWW2!BJ30),"",DPWW2!BJ30) | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z30),"",DPWW2!Z30) | ¬¬IF(ISBLANK(DPWW2!AA30),"",DPWW2!AA30) | ¬¬IF(ISBLANK(DPWW2!AB30),"",DPWW2!AB30) | ¬¬IF(ISBLANK(DPWW2!AC30),"",DPWW2!AC30) | ¬¬IF(ISBLANK(DPWW2!AD30),"",DPWW2!AD30) | ¬¬IF(ISBLANK(DPWW2!AE30),"",DPWW2!AE30) | ¬¬IF(ISBLANK(DPWW2!AF30),"",DPWW2!AF30) | ¬¬IF(ISBLANK(DPWW2!AG30),"",DPWW2!AG30) | ¬¬IF(ISBLANK(DPWW2!AH30),"",DPWW2!AH30) | ¬¬IF(ISBLANK(DPWW2!AI30),"",DPWW2!AI30) | ¬¬IF(ISBLANK(DPWW2!AJ30),"",DPWW2!AJ30)
¬¬A459 | ¬¬IF(ISBLANK(DPWW2!BU30),"",DPWW2!BU30) | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK30),"",DPWW2!AK30) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL30),"",DPWW2!AL30)
¬¬A460 | ¬¬IF(ISBLANK(DPWW2!BX30),"",DPWW2!BX30) | ¬¬DPWW2!F30 & "," & DPWW2!G30 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H30),"",DPWW2!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN30),"",DPWW2!AN30) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO30),"",DPWW2!AO30)
¬¬A461 | ¬¬IF(ISBLANK(DPWW2!AT31),"",DPWW2!AT31) | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J31),"",DPWW2!J31)
¬¬A462 | ¬¬IF(ISBLANK(DPWW2!AV31),"",DPWW2!AV31) | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L31),"",DPWW2!L31) | ¬¬IF(ISBLANK(DPWW2!M31),"",DPWW2!M31) | ¬¬IF(ISBLANK(DPWW2!N31),"",DPWW2!N31) | ¬¬IF(ISBLANK(DPWW2!O31),"",DPWW2!O31) | ¬¬IF(ISBLANK(DPWW2!P31),"",DPWW2!P31) | ¬¬IF(ISBLANK(DPWW2!Q31),"",DPWW2!Q31) | ¬¬IF(ISBLANK(DPWW2!R31),"",DPWW2!R31) | ¬¬IF(ISBLANK(DPWW2!S31),"",DPWW2!S31) | ¬¬IF(ISBLANK(DPWW2!T31),"",DPWW2!T31) | ¬¬IF(ISBLANK(DPWW2!U31),"",DPWW2!U31) | ¬¬IF(ISBLANK(DPWW2!V31),"",DPWW2!V31)
¬¬A463 | ¬¬IF(ISBLANK(DPWW2!BG31),"",DPWW2!BG31) | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W31),"",DPWW2!W31) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X31),"",DPWW2!X31)
¬¬A464 | ¬¬IF(ISBLANK(DPWW2!BJ31),"",DPWW2!BJ31) | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z31),"",DPWW2!Z31) | ¬¬IF(ISBLANK(DPWW2!AA31),"",DPWW2!AA31) | ¬¬IF(ISBLANK(DPWW2!AB31),"",DPWW2!AB31) | ¬¬IF(ISBLANK(DPWW2!AC31),"",DPWW2!AC31) | ¬¬IF(ISBLANK(DPWW2!AD31),"",DPWW2!AD31) | ¬¬IF(ISBLANK(DPWW2!AE31),"",DPWW2!AE31) | ¬¬IF(ISBLANK(DPWW2!AF31),"",DPWW2!AF31) | ¬¬IF(ISBLANK(DPWW2!AG31),"",DPWW2!AG31) | ¬¬IF(ISBLANK(DPWW2!AH31),"",DPWW2!AH31) | ¬¬IF(ISBLANK(DPWW2!AI31),"",DPWW2!AI31) | ¬¬IF(ISBLANK(DPWW2!AJ31),"",DPWW2!AJ31)
¬¬A465 | ¬¬IF(ISBLANK(DPWW2!BU31),"",DPWW2!BU31) | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK31),"",DPWW2!AK31) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL31),"",DPWW2!AL31)
¬¬A466 | ¬¬IF(ISBLANK(DPWW2!BX31),"",DPWW2!BX31) | ¬¬DPWW2!F31 & "," & DPWW2!G31 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H31),"",DPWW2!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN31),"",DPWW2!AN31) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO31),"",DPWW2!AO31)
¬¬A467 | ¬¬IF(ISBLANK(DPWW2!AT32),"",DPWW2!AT32) | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J32),"",DPWW2!J32)
¬¬A468 | ¬¬IF(ISBLANK(DPWW2!AV32),"",DPWW2!AV32) | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L32),"",DPWW2!L32) | ¬¬IF(ISBLANK(DPWW2!M32),"",DPWW2!M32) | ¬¬IF(ISBLANK(DPWW2!N32),"",DPWW2!N32) | ¬¬IF(ISBLANK(DPWW2!O32),"",DPWW2!O32) | ¬¬IF(ISBLANK(DPWW2!P32),"",DPWW2!P32) | ¬¬IF(ISBLANK(DPWW2!Q32),"",DPWW2!Q32) | ¬¬IF(ISBLANK(DPWW2!R32),"",DPWW2!R32) | ¬¬IF(ISBLANK(DPWW2!S32),"",DPWW2!S32) | ¬¬IF(ISBLANK(DPWW2!T32),"",DPWW2!T32) | ¬¬IF(ISBLANK(DPWW2!U32),"",DPWW2!U32) | ¬¬IF(ISBLANK(DPWW2!V32),"",DPWW2!V32)
¬¬A469 | ¬¬IF(ISBLANK(DPWW2!BG32),"",DPWW2!BG32) | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W32),"",DPWW2!W32) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X32),"",DPWW2!X32)
¬¬A470 | ¬¬IF(ISBLANK(DPWW2!BJ32),"",DPWW2!BJ32) | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z32),"",DPWW2!Z32) | ¬¬IF(ISBLANK(DPWW2!AA32),"",DPWW2!AA32) | ¬¬IF(ISBLANK(DPWW2!AB32),"",DPWW2!AB32) | ¬¬IF(ISBLANK(DPWW2!AC32),"",DPWW2!AC32) | ¬¬IF(ISBLANK(DPWW2!AD32),"",DPWW2!AD32) | ¬¬IF(ISBLANK(DPWW2!AE32),"",DPWW2!AE32) | ¬¬IF(ISBLANK(DPWW2!AF32),"",DPWW2!AF32) | ¬¬IF(ISBLANK(DPWW2!AG32),"",DPWW2!AG32) | ¬¬IF(ISBLANK(DPWW2!AH32),"",DPWW2!AH32) | ¬¬IF(ISBLANK(DPWW2!AI32),"",DPWW2!AI32) | ¬¬IF(ISBLANK(DPWW2!AJ32),"",DPWW2!AJ32)
¬¬A471 | ¬¬IF(ISBLANK(DPWW2!BU32),"",DPWW2!BU32) | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK32),"",DPWW2!AK32) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL32),"",DPWW2!AL32)
¬¬A472 | ¬¬IF(ISBLANK(DPWW2!BX32),"",DPWW2!BX32) | ¬¬DPWW2!F32 & "," & DPWW2!G32 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H32),"",DPWW2!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN32),"",DPWW2!AN32) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO32),"",DPWW2!AO32)
¬¬A473 | ¬¬IF(ISBLANK(DPWW2!AT33),"",DPWW2!AT33) | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J33),"",DPWW2!J33)
¬¬A474 | ¬¬IF(ISBLANK(DPWW2!AV33),"",DPWW2!AV33) | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L33),"",DPWW2!L33) | ¬¬IF(ISBLANK(DPWW2!M33),"",DPWW2!M33) | ¬¬IF(ISBLANK(DPWW2!N33),"",DPWW2!N33) | ¬¬IF(ISBLANK(DPWW2!O33),"",DPWW2!O33) | ¬¬IF(ISBLANK(DPWW2!P33),"",DPWW2!P33) | ¬¬IF(ISBLANK(DPWW2!Q33),"",DPWW2!Q33) | ¬¬IF(ISBLANK(DPWW2!R33),"",DPWW2!R33) | ¬¬IF(ISBLANK(DPWW2!S33),"",DPWW2!S33) | ¬¬IF(ISBLANK(DPWW2!T33),"",DPWW2!T33) | ¬¬IF(ISBLANK(DPWW2!U33),"",DPWW2!U33) | ¬¬IF(ISBLANK(DPWW2!V33),"",DPWW2!V33)
¬¬A475 | ¬¬IF(ISBLANK(DPWW2!BG33),"",DPWW2!BG33) | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W33),"",DPWW2!W33) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X33),"",DPWW2!X33)
¬¬A476 | ¬¬IF(ISBLANK(DPWW2!BJ33),"",DPWW2!BJ33) | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z33),"",DPWW2!Z33) | ¬¬IF(ISBLANK(DPWW2!AA33),"",DPWW2!AA33) | ¬¬IF(ISBLANK(DPWW2!AB33),"",DPWW2!AB33) | ¬¬IF(ISBLANK(DPWW2!AC33),"",DPWW2!AC33) | ¬¬IF(ISBLANK(DPWW2!AD33),"",DPWW2!AD33) | ¬¬IF(ISBLANK(DPWW2!AE33),"",DPWW2!AE33) | ¬¬IF(ISBLANK(DPWW2!AF33),"",DPWW2!AF33) | ¬¬IF(ISBLANK(DPWW2!AG33),"",DPWW2!AG33) | ¬¬IF(ISBLANK(DPWW2!AH33),"",DPWW2!AH33) | ¬¬IF(ISBLANK(DPWW2!AI33),"",DPWW2!AI33) | ¬¬IF(ISBLANK(DPWW2!AJ33),"",DPWW2!AJ33)
¬¬A477 | ¬¬IF(ISBLANK(DPWW2!BU33),"",DPWW2!BU33) | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK33),"",DPWW2!AK33) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL33),"",DPWW2!AL33)
¬¬A478 | ¬¬IF(ISBLANK(DPWW2!BX33),"",DPWW2!BX33) | ¬¬DPWW2!F33 & "," & DPWW2!G33 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H33),"",DPWW2!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN33),"",DPWW2!AN33) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO33),"",DPWW2!AO33)
¬¬A479 | ¬¬IF(ISBLANK(DPWW2!AT34),"",DPWW2!AT34) | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J34),"",DPWW2!J34)
¬¬A480 | ¬¬IF(ISBLANK(DPWW2!AV34),"",DPWW2!AV34) | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L34),"",DPWW2!L34) | ¬¬IF(ISBLANK(DPWW2!M34),"",DPWW2!M34) | ¬¬IF(ISBLANK(DPWW2!N34),"",DPWW2!N34) | ¬¬IF(ISBLANK(DPWW2!O34),"",DPWW2!O34) | ¬¬IF(ISBLANK(DPWW2!P34),"",DPWW2!P34) | ¬¬IF(ISBLANK(DPWW2!Q34),"",DPWW2!Q34) | ¬¬IF(ISBLANK(DPWW2!R34),"",DPWW2!R34) | ¬¬IF(ISBLANK(DPWW2!S34),"",DPWW2!S34) | ¬¬IF(ISBLANK(DPWW2!T34),"",DPWW2!T34) | ¬¬IF(ISBLANK(DPWW2!U34),"",DPWW2!U34) | ¬¬IF(ISBLANK(DPWW2!V34),"",DPWW2!V34)
¬¬A481 | ¬¬IF(ISBLANK(DPWW2!BG34),"",DPWW2!BG34) | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W34),"",DPWW2!W34) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X34),"",DPWW2!X34)
¬¬A482 | ¬¬IF(ISBLANK(DPWW2!BJ34),"",DPWW2!BJ34) | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z34),"",DPWW2!Z34) | ¬¬IF(ISBLANK(DPWW2!AA34),"",DPWW2!AA34) | ¬¬IF(ISBLANK(DPWW2!AB34),"",DPWW2!AB34) | ¬¬IF(ISBLANK(DPWW2!AC34),"",DPWW2!AC34) | ¬¬IF(ISBLANK(DPWW2!AD34),"",DPWW2!AD34) | ¬¬IF(ISBLANK(DPWW2!AE34),"",DPWW2!AE34) | ¬¬IF(ISBLANK(DPWW2!AF34),"",DPWW2!AF34) | ¬¬IF(ISBLANK(DPWW2!AG34),"",DPWW2!AG34) | ¬¬IF(ISBLANK(DPWW2!AH34),"",DPWW2!AH34) | ¬¬IF(ISBLANK(DPWW2!AI34),"",DPWW2!AI34) | ¬¬IF(ISBLANK(DPWW2!AJ34),"",DPWW2!AJ34)
¬¬A483 | ¬¬IF(ISBLANK(DPWW2!BU34),"",DPWW2!BU34) | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK34),"",DPWW2!AK34) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL34),"",DPWW2!AL34)
¬¬A484 | ¬¬IF(ISBLANK(DPWW2!BX34),"",DPWW2!BX34) | ¬¬DPWW2!F34 & "," & DPWW2!G34 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H34),"",DPWW2!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN34),"",DPWW2!AN34) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO34),"",DPWW2!AO34)
¬¬A485 | ¬¬IF(ISBLANK(DPWW2!AT35),"",DPWW2!AT35) | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J35),"",DPWW2!J35)
¬¬A486 | ¬¬IF(ISBLANK(DPWW2!AV35),"",DPWW2!AV35) | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L35),"",DPWW2!L35) | ¬¬IF(ISBLANK(DPWW2!M35),"",DPWW2!M35) | ¬¬IF(ISBLANK(DPWW2!N35),"",DPWW2!N35) | ¬¬IF(ISBLANK(DPWW2!O35),"",DPWW2!O35) | ¬¬IF(ISBLANK(DPWW2!P35),"",DPWW2!P35) | ¬¬IF(ISBLANK(DPWW2!Q35),"",DPWW2!Q35) | ¬¬IF(ISBLANK(DPWW2!R35),"",DPWW2!R35) | ¬¬IF(ISBLANK(DPWW2!S35),"",DPWW2!S35) | ¬¬IF(ISBLANK(DPWW2!T35),"",DPWW2!T35) | ¬¬IF(ISBLANK(DPWW2!U35),"",DPWW2!U35) | ¬¬IF(ISBLANK(DPWW2!V35),"",DPWW2!V35)
¬¬A487 | ¬¬IF(ISBLANK(DPWW2!BG35),"",DPWW2!BG35) | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W35),"",DPWW2!W35) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X35),"",DPWW2!X35)
¬¬A488 | ¬¬IF(ISBLANK(DPWW2!BJ35),"",DPWW2!BJ35) | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z35),"",DPWW2!Z35) | ¬¬IF(ISBLANK(DPWW2!AA35),"",DPWW2!AA35) | ¬¬IF(ISBLANK(DPWW2!AB35),"",DPWW2!AB35) | ¬¬IF(ISBLANK(DPWW2!AC35),"",DPWW2!AC35) | ¬¬IF(ISBLANK(DPWW2!AD35),"",DPWW2!AD35) | ¬¬IF(ISBLANK(DPWW2!AE35),"",DPWW2!AE35) | ¬¬IF(ISBLANK(DPWW2!AF35),"",DPWW2!AF35) | ¬¬IF(ISBLANK(DPWW2!AG35),"",DPWW2!AG35) | ¬¬IF(ISBLANK(DPWW2!AH35),"",DPWW2!AH35) | ¬¬IF(ISBLANK(DPWW2!AI35),"",DPWW2!AI35) | ¬¬IF(ISBLANK(DPWW2!AJ35),"",DPWW2!AJ35)
¬¬A489 | ¬¬IF(ISBLANK(DPWW2!BU35),"",DPWW2!BU35) | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK35),"",DPWW2!AK35) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL35),"",DPWW2!AL35)
¬¬A490 | ¬¬IF(ISBLANK(DPWW2!BX35),"",DPWW2!BX35) | ¬¬DPWW2!F35 & "," & DPWW2!G35 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H35),"",DPWW2!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN35),"",DPWW2!AN35) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO35),"",DPWW2!AO35)
¬¬A491 | ¬¬IF(ISBLANK(DPWW2!AT36),"",DPWW2!AT36) | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J36),"",DPWW2!J36)
¬¬A492 | ¬¬IF(ISBLANK(DPWW2!AV36),"",DPWW2!AV36) | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L36),"",DPWW2!L36) | ¬¬IF(ISBLANK(DPWW2!M36),"",DPWW2!M36) | ¬¬IF(ISBLANK(DPWW2!N36),"",DPWW2!N36) | ¬¬IF(ISBLANK(DPWW2!O36),"",DPWW2!O36) | ¬¬IF(ISBLANK(DPWW2!P36),"",DPWW2!P36) | ¬¬IF(ISBLANK(DPWW2!Q36),"",DPWW2!Q36) | ¬¬IF(ISBLANK(DPWW2!R36),"",DPWW2!R36) | ¬¬IF(ISBLANK(DPWW2!S36),"",DPWW2!S36) | ¬¬IF(ISBLANK(DPWW2!T36),"",DPWW2!T36) | ¬¬IF(ISBLANK(DPWW2!U36),"",DPWW2!U36) | ¬¬IF(ISBLANK(DPWW2!V36),"",DPWW2!V36)
¬¬A493 | ¬¬IF(ISBLANK(DPWW2!BG36),"",DPWW2!BG36) | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W36),"",DPWW2!W36) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X36),"",DPWW2!X36)
¬¬A494 | ¬¬IF(ISBLANK(DPWW2!BJ36),"",DPWW2!BJ36) | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z36),"",DPWW2!Z36) | ¬¬IF(ISBLANK(DPWW2!AA36),"",DPWW2!AA36) | ¬¬IF(ISBLANK(DPWW2!AB36),"",DPWW2!AB36) | ¬¬IF(ISBLANK(DPWW2!AC36),"",DPWW2!AC36) | ¬¬IF(ISBLANK(DPWW2!AD36),"",DPWW2!AD36) | ¬¬IF(ISBLANK(DPWW2!AE36),"",DPWW2!AE36) | ¬¬IF(ISBLANK(DPWW2!AF36),"",DPWW2!AF36) | ¬¬IF(ISBLANK(DPWW2!AG36),"",DPWW2!AG36) | ¬¬IF(ISBLANK(DPWW2!AH36),"",DPWW2!AH36) | ¬¬IF(ISBLANK(DPWW2!AI36),"",DPWW2!AI36) | ¬¬IF(ISBLANK(DPWW2!AJ36),"",DPWW2!AJ36)
¬¬A495 | ¬¬IF(ISBLANK(DPWW2!BU36),"",DPWW2!BU36) | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK36),"",DPWW2!AK36) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL36),"",DPWW2!AL36)
¬¬A496 | ¬¬IF(ISBLANK(DPWW2!BX36),"",DPWW2!BX36) | ¬¬DPWW2!F36 & "," & DPWW2!G36 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H36),"",DPWW2!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN36),"",DPWW2!AN36) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO36),"",DPWW2!AO36)
¬¬A497 | ¬¬IF(ISBLANK(DPWW2!AT37),"",DPWW2!AT37) | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J37),"",DPWW2!J37)
¬¬A498 | ¬¬IF(ISBLANK(DPWW2!AV37),"",DPWW2!AV37) | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L37),"",DPWW2!L37) | ¬¬IF(ISBLANK(DPWW2!M37),"",DPWW2!M37) | ¬¬IF(ISBLANK(DPWW2!N37),"",DPWW2!N37) | ¬¬IF(ISBLANK(DPWW2!O37),"",DPWW2!O37) | ¬¬IF(ISBLANK(DPWW2!P37),"",DPWW2!P37) | ¬¬IF(ISBLANK(DPWW2!Q37),"",DPWW2!Q37) | ¬¬IF(ISBLANK(DPWW2!R37),"",DPWW2!R37) | ¬¬IF(ISBLANK(DPWW2!S37),"",DPWW2!S37) | ¬¬IF(ISBLANK(DPWW2!T37),"",DPWW2!T37) | ¬¬IF(ISBLANK(DPWW2!U37),"",DPWW2!U37) | ¬¬IF(ISBLANK(DPWW2!V37),"",DPWW2!V37)
¬¬A499 | ¬¬IF(ISBLANK(DPWW2!BG37),"",DPWW2!BG37) | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W37),"",DPWW2!W37) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X37),"",DPWW2!X37)
¬¬A500 | ¬¬IF(ISBLANK(DPWW2!BJ37),"",DPWW2!BJ37) | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z37),"",DPWW2!Z37) | ¬¬IF(ISBLANK(DPWW2!AA37),"",DPWW2!AA37) | ¬¬IF(ISBLANK(DPWW2!AB37),"",DPWW2!AB37) | ¬¬IF(ISBLANK(DPWW2!AC37),"",DPWW2!AC37) | ¬¬IF(ISBLANK(DPWW2!AD37),"",DPWW2!AD37) | ¬¬IF(ISBLANK(DPWW2!AE37),"",DPWW2!AE37) | ¬¬IF(ISBLANK(DPWW2!AF37),"",DPWW2!AF37) | ¬¬IF(ISBLANK(DPWW2!AG37),"",DPWW2!AG37) | ¬¬IF(ISBLANK(DPWW2!AH37),"",DPWW2!AH37) | ¬¬IF(ISBLANK(DPWW2!AI37),"",DPWW2!AI37) | ¬¬IF(ISBLANK(DPWW2!AJ37),"",DPWW2!AJ37)
¬¬A501 | ¬¬IF(ISBLANK(DPWW2!BU37),"",DPWW2!BU37) | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK37),"",DPWW2!AK37) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL37),"",DPWW2!AL37)
¬¬A502 | ¬¬IF(ISBLANK(DPWW2!BX37),"",DPWW2!BX37) | ¬¬DPWW2!F37 & "," & DPWW2!G37 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H37),"",DPWW2!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN37),"",DPWW2!AN37) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO37),"",DPWW2!AO37)
¬¬A503 | ¬¬IF(ISBLANK(DPWW2!AT38),"",DPWW2!AT38) | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J38),"",DPWW2!J38)
¬¬A504 | ¬¬IF(ISBLANK(DPWW2!AV38),"",DPWW2!AV38) | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L38),"",DPWW2!L38) | ¬¬IF(ISBLANK(DPWW2!M38),"",DPWW2!M38) | ¬¬IF(ISBLANK(DPWW2!N38),"",DPWW2!N38) | ¬¬IF(ISBLANK(DPWW2!O38),"",DPWW2!O38) | ¬¬IF(ISBLANK(DPWW2!P38),"",DPWW2!P38) | ¬¬IF(ISBLANK(DPWW2!Q38),"",DPWW2!Q38) | ¬¬IF(ISBLANK(DPWW2!R38),"",DPWW2!R38) | ¬¬IF(ISBLANK(DPWW2!S38),"",DPWW2!S38) | ¬¬IF(ISBLANK(DPWW2!T38),"",DPWW2!T38) | ¬¬IF(ISBLANK(DPWW2!U38),"",DPWW2!U38) | ¬¬IF(ISBLANK(DPWW2!V38),"",DPWW2!V38)
¬¬A505 | ¬¬IF(ISBLANK(DPWW2!BG38),"",DPWW2!BG38) | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W38),"",DPWW2!W38) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X38),"",DPWW2!X38)
¬¬A506 | ¬¬IF(ISBLANK(DPWW2!BJ38),"",DPWW2!BJ38) | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z38),"",DPWW2!Z38) | ¬¬IF(ISBLANK(DPWW2!AA38),"",DPWW2!AA38) | ¬¬IF(ISBLANK(DPWW2!AB38),"",DPWW2!AB38) | ¬¬IF(ISBLANK(DPWW2!AC38),"",DPWW2!AC38) | ¬¬IF(ISBLANK(DPWW2!AD38),"",DPWW2!AD38) | ¬¬IF(ISBLANK(DPWW2!AE38),"",DPWW2!AE38) | ¬¬IF(ISBLANK(DPWW2!AF38),"",DPWW2!AF38) | ¬¬IF(ISBLANK(DPWW2!AG38),"",DPWW2!AG38) | ¬¬IF(ISBLANK(DPWW2!AH38),"",DPWW2!AH38) | ¬¬IF(ISBLANK(DPWW2!AI38),"",DPWW2!AI38) | ¬¬IF(ISBLANK(DPWW2!AJ38),"",DPWW2!AJ38)
¬¬A507 | ¬¬IF(ISBLANK(DPWW2!BU38),"",DPWW2!BU38) | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK38),"",DPWW2!AK38) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL38),"",DPWW2!AL38)
¬¬A508 | ¬¬IF(ISBLANK(DPWW2!BX38),"",DPWW2!BX38) | ¬¬DPWW2!F38 & "," & DPWW2!G38 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H38),"",DPWW2!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN38),"",DPWW2!AN38) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO38),"",DPWW2!AO38)
¬¬A509 | ¬¬IF(ISBLANK(DPWW2!AT39),"",DPWW2!AT39) | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J39),"",DPWW2!J39)
¬¬A510 | ¬¬IF(ISBLANK(DPWW2!AV39),"",DPWW2!AV39) | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L39),"",DPWW2!L39) | ¬¬IF(ISBLANK(DPWW2!M39),"",DPWW2!M39) | ¬¬IF(ISBLANK(DPWW2!N39),"",DPWW2!N39) | ¬¬IF(ISBLANK(DPWW2!O39),"",DPWW2!O39) | ¬¬IF(ISBLANK(DPWW2!P39),"",DPWW2!P39) | ¬¬IF(ISBLANK(DPWW2!Q39),"",DPWW2!Q39) | ¬¬IF(ISBLANK(DPWW2!R39),"",DPWW2!R39) | ¬¬IF(ISBLANK(DPWW2!S39),"",DPWW2!S39) | ¬¬IF(ISBLANK(DPWW2!T39),"",DPWW2!T39) | ¬¬IF(ISBLANK(DPWW2!U39),"",DPWW2!U39) | ¬¬IF(ISBLANK(DPWW2!V39),"",DPWW2!V39)
¬¬A511 | ¬¬IF(ISBLANK(DPWW2!BG39),"",DPWW2!BG39) | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W39),"",DPWW2!W39) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X39),"",DPWW2!X39)
¬¬A512 | ¬¬IF(ISBLANK(DPWW2!BJ39),"",DPWW2!BJ39) | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z39),"",DPWW2!Z39) | ¬¬IF(ISBLANK(DPWW2!AA39),"",DPWW2!AA39) | ¬¬IF(ISBLANK(DPWW2!AB39),"",DPWW2!AB39) | ¬¬IF(ISBLANK(DPWW2!AC39),"",DPWW2!AC39) | ¬¬IF(ISBLANK(DPWW2!AD39),"",DPWW2!AD39) | ¬¬IF(ISBLANK(DPWW2!AE39),"",DPWW2!AE39) | ¬¬IF(ISBLANK(DPWW2!AF39),"",DPWW2!AF39) | ¬¬IF(ISBLANK(DPWW2!AG39),"",DPWW2!AG39) | ¬¬IF(ISBLANK(DPWW2!AH39),"",DPWW2!AH39) | ¬¬IF(ISBLANK(DPWW2!AI39),"",DPWW2!AI39) | ¬¬IF(ISBLANK(DPWW2!AJ39),"",DPWW2!AJ39)
¬¬A513 | ¬¬IF(ISBLANK(DPWW2!BU39),"",DPWW2!BU39) | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK39),"",DPWW2!AK39) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL39),"",DPWW2!AL39)
¬¬A514 | ¬¬IF(ISBLANK(DPWW2!BX39),"",DPWW2!BX39) | ¬¬DPWW2!F39 & "," & DPWW2!G39 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H39),"",DPWW2!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN39),"",DPWW2!AN39) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO39),"",DPWW2!AO39)
¬¬A515 | ¬¬IF(ISBLANK(DPWW2!AT40),"",DPWW2!AT40) | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J41),"",DPWW2!J41)
¬¬A516 | ¬¬IF(ISBLANK(DPWW2!AV40),"",DPWW2!AV40) | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L41),"",DPWW2!L41) | ¬¬IF(ISBLANK(DPWW2!M41),"",DPWW2!M41) | ¬¬IF(ISBLANK(DPWW2!N41),"",DPWW2!N41) | ¬¬IF(ISBLANK(DPWW2!O41),"",DPWW2!O41) | ¬¬IF(ISBLANK(DPWW2!P41),"",DPWW2!P41) | ¬¬IF(ISBLANK(DPWW2!Q41),"",DPWW2!Q41) | ¬¬IF(ISBLANK(DPWW2!R41),"",DPWW2!R41) | ¬¬IF(ISBLANK(DPWW2!S41),"",DPWW2!S41) | ¬¬IF(ISBLANK(DPWW2!T41),"",DPWW2!T41) | ¬¬IF(ISBLANK(DPWW2!U41),"",DPWW2!U41) | ¬¬IF(ISBLANK(DPWW2!V41),"",DPWW2!V41)
¬¬A517 | ¬¬IF(ISBLANK(DPWW2!BG40),"",DPWW2!BG40) | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W41),"",DPWW2!W41) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X41),"",DPWW2!X41)
¬¬A518 | ¬¬IF(ISBLANK(DPWW2!BJ40),"",DPWW2!BJ40) | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z41),"",DPWW2!Z41) | ¬¬IF(ISBLANK(DPWW2!AA41),"",DPWW2!AA41) | ¬¬IF(ISBLANK(DPWW2!AB41),"",DPWW2!AB41) | ¬¬IF(ISBLANK(DPWW2!AC41),"",DPWW2!AC41) | ¬¬IF(ISBLANK(DPWW2!AD41),"",DPWW2!AD41) | ¬¬IF(ISBLANK(DPWW2!AE41),"",DPWW2!AE41) | ¬¬IF(ISBLANK(DPWW2!AF41),"",DPWW2!AF41) | ¬¬IF(ISBLANK(DPWW2!AG41),"",DPWW2!AG41) | ¬¬IF(ISBLANK(DPWW2!AH41),"",DPWW2!AH41) | ¬¬IF(ISBLANK(DPWW2!AI41),"",DPWW2!AI41) | ¬¬IF(ISBLANK(DPWW2!AJ41),"",DPWW2!AJ41)
¬¬A519 | ¬¬IF(ISBLANK(DPWW2!BU40),"",DPWW2!BU40) | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK41),"",DPWW2!AK41) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL41),"",DPWW2!AL41)
¬¬A520 | ¬¬IF(ISBLANK(DPWW2!BX40),"",DPWW2!BX40) | ¬¬DPWW2!F40 & "," & DPWW2!G40 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H40),"",DPWW2!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN41),"",DPWW2!AN41) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO41),"",DPWW2!AO41)
¬¬A521 | ¬¬IF(ISBLANK(DPWW2!AT42),"",DPWW2!AT42) | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J42),"",DPWW2!J42)
¬¬A522 | ¬¬IF(ISBLANK(DPWW2!AV42),"",DPWW2!AV42) | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L42),"",DPWW2!L42) | ¬¬IF(ISBLANK(DPWW2!M42),"",DPWW2!M42) | ¬¬IF(ISBLANK(DPWW2!N42),"",DPWW2!N42) | ¬¬IF(ISBLANK(DPWW2!O42),"",DPWW2!O42) | ¬¬IF(ISBLANK(DPWW2!P42),"",DPWW2!P42) | ¬¬IF(ISBLANK(DPWW2!Q42),"",DPWW2!Q42) | ¬¬IF(ISBLANK(DPWW2!R42),"",DPWW2!R42) | ¬¬IF(ISBLANK(DPWW2!S42),"",DPWW2!S42) | ¬¬IF(ISBLANK(DPWW2!T42),"",DPWW2!T42) | ¬¬IF(ISBLANK(DPWW2!U42),"",DPWW2!U42) | ¬¬IF(ISBLANK(DPWW2!V42),"",DPWW2!V42)
¬¬A523 | ¬¬IF(ISBLANK(DPWW2!BG42),"",DPWW2!BG42) | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W42),"",DPWW2!W42) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X42),"",DPWW2!X42)
¬¬A524 | ¬¬IF(ISBLANK(DPWW2!BJ42),"",DPWW2!BJ42) | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z42),"",DPWW2!Z42) | ¬¬IF(ISBLANK(DPWW2!AA42),"",DPWW2!AA42) | ¬¬IF(ISBLANK(DPWW2!AB42),"",DPWW2!AB42) | ¬¬IF(ISBLANK(DPWW2!AC42),"",DPWW2!AC42) | ¬¬IF(ISBLANK(DPWW2!AD42),"",DPWW2!AD42) | ¬¬IF(ISBLANK(DPWW2!AE42),"",DPWW2!AE42) | ¬¬IF(ISBLANK(DPWW2!AF42),"",DPWW2!AF42) | ¬¬IF(ISBLANK(DPWW2!AG42),"",DPWW2!AG42) | ¬¬IF(ISBLANK(DPWW2!AH42),"",DPWW2!AH42) | ¬¬IF(ISBLANK(DPWW2!AI42),"",DPWW2!AI42) | ¬¬IF(ISBLANK(DPWW2!AJ42),"",DPWW2!AJ42)
¬¬A525 | ¬¬IF(ISBLANK(DPWW2!BU42),"",DPWW2!BU42) | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK42),"",DPWW2!AK42) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL42),"",DPWW2!AL42)
¬¬A526 | ¬¬IF(ISBLANK(DPWW2!BX42),"",DPWW2!BX42) | ¬¬DPWW2!F42 & "," & DPWW2!G42 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H42),"",DPWW2!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN42),"",DPWW2!AN42) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO42),"",DPWW2!AO42)
¬¬A527 | ¬¬IF(ISBLANK(DPWW2!AT43),"",DPWW2!AT43) | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J43),"",DPWW2!J43)
¬¬A528 | ¬¬IF(ISBLANK(DPWW2!AV43),"",DPWW2!AV43) | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L43),"",DPWW2!L43) | ¬¬IF(ISBLANK(DPWW2!M43),"",DPWW2!M43) | ¬¬IF(ISBLANK(DPWW2!N43),"",DPWW2!N43) | ¬¬IF(ISBLANK(DPWW2!O43),"",DPWW2!O43) | ¬¬IF(ISBLANK(DPWW2!P43),"",DPWW2!P43) | ¬¬IF(ISBLANK(DPWW2!Q43),"",DPWW2!Q43) | ¬¬IF(ISBLANK(DPWW2!R43),"",DPWW2!R43) | ¬¬IF(ISBLANK(DPWW2!S43),"",DPWW2!S43) | ¬¬IF(ISBLANK(DPWW2!T43),"",DPWW2!T43) | ¬¬IF(ISBLANK(DPWW2!U43),"",DPWW2!U43) | ¬¬IF(ISBLANK(DPWW2!V43),"",DPWW2!V43)
¬¬A529 | ¬¬IF(ISBLANK(DPWW2!BG43),"",DPWW2!BG43) | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W43),"",DPWW2!W43) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X43),"",DPWW2!X43)
¬¬A530 | ¬¬IF(ISBLANK(DPWW2!BJ43),"",DPWW2!BJ43) | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z43),"",DPWW2!Z43) | ¬¬IF(ISBLANK(DPWW2!AA43),"",DPWW2!AA43) | ¬¬IF(ISBLANK(DPWW2!AB43),"",DPWW2!AB43) | ¬¬IF(ISBLANK(DPWW2!AC43),"",DPWW2!AC43) | ¬¬IF(ISBLANK(DPWW2!AD43),"",DPWW2!AD43) | ¬¬IF(ISBLANK(DPWW2!AE43),"",DPWW2!AE43) | ¬¬IF(ISBLANK(DPWW2!AF43),"",DPWW2!AF43) | ¬¬IF(ISBLANK(DPWW2!AG43),"",DPWW2!AG43) | ¬¬IF(ISBLANK(DPWW2!AH43),"",DPWW2!AH43) | ¬¬IF(ISBLANK(DPWW2!AI43),"",DPWW2!AI43) | ¬¬IF(ISBLANK(DPWW2!AJ43),"",DPWW2!AJ43)
¬¬A531 | ¬¬IF(ISBLANK(DPWW2!BU43),"",DPWW2!BU43) | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK43),"",DPWW2!AK43) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL43),"",DPWW2!AL43)
¬¬A532 | ¬¬IF(ISBLANK(DPWW2!BX43),"",DPWW2!BX43) | ¬¬DPWW2!F43 & "," & DPWW2!G43 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H43),"",DPWW2!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN43),"",DPWW2!AN43) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO43),"",DPWW2!AO43)
¬¬A533 | ¬¬IF(ISBLANK(DPWW2!AT44),"",DPWW2!AT44) | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J44),"",DPWW2!J44)
¬¬A534 | ¬¬IF(ISBLANK(DPWW2!AV44),"",DPWW2!AV44) | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L44),"",DPWW2!L44) | ¬¬IF(ISBLANK(DPWW2!M44),"",DPWW2!M44) | ¬¬IF(ISBLANK(DPWW2!N44),"",DPWW2!N44) | ¬¬IF(ISBLANK(DPWW2!O44),"",DPWW2!O44) | ¬¬IF(ISBLANK(DPWW2!P44),"",DPWW2!P44) | ¬¬IF(ISBLANK(DPWW2!Q44),"",DPWW2!Q44) | ¬¬IF(ISBLANK(DPWW2!R44),"",DPWW2!R44) | ¬¬IF(ISBLANK(DPWW2!S44),"",DPWW2!S44) | ¬¬IF(ISBLANK(DPWW2!T44),"",DPWW2!T44) | ¬¬IF(ISBLANK(DPWW2!U44),"",DPWW2!U44) | ¬¬IF(ISBLANK(DPWW2!V44),"",DPWW2!V44)
¬¬A535 | ¬¬IF(ISBLANK(DPWW2!BG44),"",DPWW2!BG44) | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W44),"",DPWW2!W44) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X44),"",DPWW2!X44)
¬¬A536 | ¬¬IF(ISBLANK(DPWW2!BJ44),"",DPWW2!BJ44) | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z44),"",DPWW2!Z44) | ¬¬IF(ISBLANK(DPWW2!AA44),"",DPWW2!AA44) | ¬¬IF(ISBLANK(DPWW2!AB44),"",DPWW2!AB44) | ¬¬IF(ISBLANK(DPWW2!AC44),"",DPWW2!AC44) | ¬¬IF(ISBLANK(DPWW2!AD44),"",DPWW2!AD44) | ¬¬IF(ISBLANK(DPWW2!AE44),"",DPWW2!AE44) | ¬¬IF(ISBLANK(DPWW2!AF44),"",DPWW2!AF44) | ¬¬IF(ISBLANK(DPWW2!AG44),"",DPWW2!AG44) | ¬¬IF(ISBLANK(DPWW2!AH44),"",DPWW2!AH44) | ¬¬IF(ISBLANK(DPWW2!AI44),"",DPWW2!AI44) | ¬¬IF(ISBLANK(DPWW2!AJ44),"",DPWW2!AJ44)
¬¬A537 | ¬¬IF(ISBLANK(DPWW2!BU44),"",DPWW2!BU44) | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK44),"",DPWW2!AK44) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL44),"",DPWW2!AL44)
¬¬A538 | ¬¬IF(ISBLANK(DPWW2!BX44),"",DPWW2!BX44) | ¬¬DPWW2!F44 & "," & DPWW2!G44 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H44),"",DPWW2!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN44),"",DPWW2!AN44) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO44),"",DPWW2!AO44)
¬¬A539 | ¬¬IF(ISBLANK(DPWW2!AT45),"",DPWW2!AT45) | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J45),"",DPWW2!J45)
¬¬A540 | ¬¬IF(ISBLANK(DPWW2!AV45),"",DPWW2!AV45) | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L45),"",DPWW2!L45) | ¬¬IF(ISBLANK(DPWW2!M45),"",DPWW2!M45) | ¬¬IF(ISBLANK(DPWW2!N45),"",DPWW2!N45) | ¬¬IF(ISBLANK(DPWW2!O45),"",DPWW2!O45) | ¬¬IF(ISBLANK(DPWW2!P45),"",DPWW2!P45) | ¬¬IF(ISBLANK(DPWW2!Q45),"",DPWW2!Q45) | ¬¬IF(ISBLANK(DPWW2!R45),"",DPWW2!R45) | ¬¬IF(ISBLANK(DPWW2!S45),"",DPWW2!S45) | ¬¬IF(ISBLANK(DPWW2!T45),"",DPWW2!T45) | ¬¬IF(ISBLANK(DPWW2!U45),"",DPWW2!U45) | ¬¬IF(ISBLANK(DPWW2!V45),"",DPWW2!V45)
¬¬A541 | ¬¬IF(ISBLANK(DPWW2!BG45),"",DPWW2!BG45) | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W45),"",DPWW2!W45) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X45),"",DPWW2!X45)
¬¬A542 | ¬¬IF(ISBLANK(DPWW2!BJ45),"",DPWW2!BJ45) | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z45),"",DPWW2!Z45) | ¬¬IF(ISBLANK(DPWW2!AA45),"",DPWW2!AA45) | ¬¬IF(ISBLANK(DPWW2!AB45),"",DPWW2!AB45) | ¬¬IF(ISBLANK(DPWW2!AC45),"",DPWW2!AC45) | ¬¬IF(ISBLANK(DPWW2!AD45),"",DPWW2!AD45) | ¬¬IF(ISBLANK(DPWW2!AE45),"",DPWW2!AE45) | ¬¬IF(ISBLANK(DPWW2!AF45),"",DPWW2!AF45) | ¬¬IF(ISBLANK(DPWW2!AG45),"",DPWW2!AG45) | ¬¬IF(ISBLANK(DPWW2!AH45),"",DPWW2!AH45) | ¬¬IF(ISBLANK(DPWW2!AI45),"",DPWW2!AI45) | ¬¬IF(ISBLANK(DPWW2!AJ45),"",DPWW2!AJ45)
¬¬A543 | ¬¬IF(ISBLANK(DPWW2!BU45),"",DPWW2!BU45) | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK45),"",DPWW2!AK45) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL45),"",DPWW2!AL45)
¬¬A544 | ¬¬IF(ISBLANK(DPWW2!BX45),"",DPWW2!BX45) | ¬¬DPWW2!F45 & "," & DPWW2!G45 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H45),"",DPWW2!H45) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN45),"",DPWW2!AN45) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO45),"",DPWW2!AO45)
¬¬A545 | ¬¬IF(ISBLANK(DPWW2!AT46),"",DPWW2!AT46) | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J46),"",DPWW2!J46)
¬¬A546 | ¬¬IF(ISBLANK(DPWW2!AV46),"",DPWW2!AV46) | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L46),"",DPWW2!L46) | ¬¬IF(ISBLANK(DPWW2!M46),"",DPWW2!M46) | ¬¬IF(ISBLANK(DPWW2!N46),"",DPWW2!N46) | ¬¬IF(ISBLANK(DPWW2!O46),"",DPWW2!O46) | ¬¬IF(ISBLANK(DPWW2!P46),"",DPWW2!P46) | ¬¬IF(ISBLANK(DPWW2!Q46),"",DPWW2!Q46) | ¬¬IF(ISBLANK(DPWW2!R46),"",DPWW2!R46) | ¬¬IF(ISBLANK(DPWW2!S46),"",DPWW2!S46) | ¬¬IF(ISBLANK(DPWW2!T46),"",DPWW2!T46) | ¬¬IF(ISBLANK(DPWW2!U46),"",DPWW2!U46) | ¬¬IF(ISBLANK(DPWW2!V46),"",DPWW2!V46)
¬¬A547 | ¬¬IF(ISBLANK(DPWW2!BG46),"",DPWW2!BG46) | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W46),"",DPWW2!W46) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X46),"",DPWW2!X46)
¬¬A548 | ¬¬IF(ISBLANK(DPWW2!BJ46),"",DPWW2!BJ46) | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z46),"",DPWW2!Z46) | ¬¬IF(ISBLANK(DPWW2!AA46),"",DPWW2!AA46) | ¬¬IF(ISBLANK(DPWW2!AB46),"",DPWW2!AB46) | ¬¬IF(ISBLANK(DPWW2!AC46),"",DPWW2!AC46) | ¬¬IF(ISBLANK(DPWW2!AD46),"",DPWW2!AD46) | ¬¬IF(ISBLANK(DPWW2!AE46),"",DPWW2!AE46) | ¬¬IF(ISBLANK(DPWW2!AF46),"",DPWW2!AF46) | ¬¬IF(ISBLANK(DPWW2!AG46),"",DPWW2!AG46) | ¬¬IF(ISBLANK(DPWW2!AH46),"",DPWW2!AH46) | ¬¬IF(ISBLANK(DPWW2!AI46),"",DPWW2!AI46) | ¬¬IF(ISBLANK(DPWW2!AJ46),"",DPWW2!AJ46)
¬¬A549 | ¬¬IF(ISBLANK(DPWW2!BU46),"",DPWW2!BU46) | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK46),"",DPWW2!AK46) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL46),"",DPWW2!AL46)
¬¬A550 | ¬¬IF(ISBLANK(DPWW2!BX46),"",DPWW2!BX46) | ¬¬DPWW2!F46 & "," & DPWW2!G46 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H46),"",DPWW2!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN46),"",DPWW2!AN46) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO46),"",DPWW2!AO46)
¬¬A551 | ¬¬IF(ISBLANK(DPWW2!AT47),"",DPWW2!AT47) | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J47),"",DPWW2!J47)
¬¬A552 | ¬¬IF(ISBLANK(DPWW2!AV47),"",DPWW2!AV47) | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L47),"",DPWW2!L47) | ¬¬IF(ISBLANK(DPWW2!M47),"",DPWW2!M47) | ¬¬IF(ISBLANK(DPWW2!N47),"",DPWW2!N47) | ¬¬IF(ISBLANK(DPWW2!O47),"",DPWW2!O47) | ¬¬IF(ISBLANK(DPWW2!P47),"",DPWW2!P47) | ¬¬IF(ISBLANK(DPWW2!Q47),"",DPWW2!Q47) | ¬¬IF(ISBLANK(DPWW2!R47),"",DPWW2!R47) | ¬¬IF(ISBLANK(DPWW2!S47),"",DPWW2!S47) | ¬¬IF(ISBLANK(DPWW2!T47),"",DPWW2!T47) | ¬¬IF(ISBLANK(DPWW2!U47),"",DPWW2!U47) | ¬¬IF(ISBLANK(DPWW2!V47),"",DPWW2!V47)
¬¬A553 | ¬¬IF(ISBLANK(DPWW2!BG47),"",DPWW2!BG47) | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W47),"",DPWW2!W47) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X47),"",DPWW2!X47)
¬¬A554 | ¬¬IF(ISBLANK(DPWW2!BJ47),"",DPWW2!BJ47) | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z47),"",DPWW2!Z47) | ¬¬IF(ISBLANK(DPWW2!AA47),"",DPWW2!AA47) | ¬¬IF(ISBLANK(DPWW2!AB47),"",DPWW2!AB47) | ¬¬IF(ISBLANK(DPWW2!AC47),"",DPWW2!AC47) | ¬¬IF(ISBLANK(DPWW2!AD47),"",DPWW2!AD47) | ¬¬IF(ISBLANK(DPWW2!AE47),"",DPWW2!AE47) | ¬¬IF(ISBLANK(DPWW2!AF47),"",DPWW2!AF47) | ¬¬IF(ISBLANK(DPWW2!AG47),"",DPWW2!AG47) | ¬¬IF(ISBLANK(DPWW2!AH47),"",DPWW2!AH47) | ¬¬IF(ISBLANK(DPWW2!AI47),"",DPWW2!AI47) | ¬¬IF(ISBLANK(DPWW2!AJ47),"",DPWW2!AJ47)
¬¬A555 | ¬¬IF(ISBLANK(DPWW2!BU47),"",DPWW2!BU47) | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK47),"",DPWW2!AK47) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL47),"",DPWW2!AL47)
¬¬A556 | ¬¬IF(ISBLANK(DPWW2!BX47),"",DPWW2!BX47) | ¬¬DPWW2!F47 & "," & DPWW2!G47 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H47),"",DPWW2!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN47),"",DPWW2!AN47) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO47),"",DPWW2!AO47)
¬¬A557 | ¬¬IF(ISBLANK(DPWW2!AT48),"",DPWW2!AT48) | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J48),"",DPWW2!J48)
¬¬A558 | ¬¬IF(ISBLANK(DPWW2!AV48),"",DPWW2!AV48) | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L48),"",DPWW2!L48) | ¬¬IF(ISBLANK(DPWW2!M48),"",DPWW2!M48) | ¬¬IF(ISBLANK(DPWW2!N48),"",DPWW2!N48) | ¬¬IF(ISBLANK(DPWW2!O48),"",DPWW2!O48) | ¬¬IF(ISBLANK(DPWW2!P48),"",DPWW2!P48) | ¬¬IF(ISBLANK(DPWW2!Q48),"",DPWW2!Q48) | ¬¬IF(ISBLANK(DPWW2!R48),"",DPWW2!R48) | ¬¬IF(ISBLANK(DPWW2!S48),"",DPWW2!S48) | ¬¬IF(ISBLANK(DPWW2!T48),"",DPWW2!T48) | ¬¬IF(ISBLANK(DPWW2!U48),"",DPWW2!U48) | ¬¬IF(ISBLANK(DPWW2!V48),"",DPWW2!V48)
¬¬A559 | ¬¬IF(ISBLANK(DPWW2!BG48),"",DPWW2!BG48) | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W48),"",DPWW2!W48) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X48),"",DPWW2!X48)
¬¬A560 | ¬¬IF(ISBLANK(DPWW2!BJ48),"",DPWW2!BJ48) | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z48),"",DPWW2!Z48) | ¬¬IF(ISBLANK(DPWW2!AA48),"",DPWW2!AA48) | ¬¬IF(ISBLANK(DPWW2!AB48),"",DPWW2!AB48) | ¬¬IF(ISBLANK(DPWW2!AC48),"",DPWW2!AC48) | ¬¬IF(ISBLANK(DPWW2!AD48),"",DPWW2!AD48) | ¬¬IF(ISBLANK(DPWW2!AE48),"",DPWW2!AE48) | ¬¬IF(ISBLANK(DPWW2!AF48),"",DPWW2!AF48) | ¬¬IF(ISBLANK(DPWW2!AG48),"",DPWW2!AG48) | ¬¬IF(ISBLANK(DPWW2!AH48),"",DPWW2!AH48) | ¬¬IF(ISBLANK(DPWW2!AI48),"",DPWW2!AI48) | ¬¬IF(ISBLANK(DPWW2!AJ48),"",DPWW2!AJ48)
¬¬A561 | ¬¬IF(ISBLANK(DPWW2!BU48),"",DPWW2!BU48) | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK48),"",DPWW2!AK48) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL48),"",DPWW2!AL48)
¬¬A562 | ¬¬IF(ISBLANK(DPWW2!BX48),"",DPWW2!BX48) | ¬¬DPWW2!F48 & "," & DPWW2!G48 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H48),"",DPWW2!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN48),"",DPWW2!AN48) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO48),"",DPWW2!AO48)
¬¬A563 | ¬¬IF(ISBLANK(DPWW2!AT49),"",DPWW2!AT49) | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J49),"",DPWW2!J49)
¬¬A564 | ¬¬IF(ISBLANK(DPWW2!AV49),"",DPWW2!AV49) | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L49),"",DPWW2!L49) | ¬¬IF(ISBLANK(DPWW2!M49),"",DPWW2!M49) | ¬¬IF(ISBLANK(DPWW2!N49),"",DPWW2!N49) | ¬¬IF(ISBLANK(DPWW2!O49),"",DPWW2!O49) | ¬¬IF(ISBLANK(DPWW2!P49),"",DPWW2!P49) | ¬¬IF(ISBLANK(DPWW2!Q49),"",DPWW2!Q49) | ¬¬IF(ISBLANK(DPWW2!R49),"",DPWW2!R49) | ¬¬IF(ISBLANK(DPWW2!S49),"",DPWW2!S49) | ¬¬IF(ISBLANK(DPWW2!T49),"",DPWW2!T49) | ¬¬IF(ISBLANK(DPWW2!U49),"",DPWW2!U49) | ¬¬IF(ISBLANK(DPWW2!V49),"",DPWW2!V49)
¬¬A565 | ¬¬IF(ISBLANK(DPWW2!BG49),"",DPWW2!BG49) | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W49),"",DPWW2!W49) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X49),"",DPWW2!X49)
¬¬A566 | ¬¬IF(ISBLANK(DPWW2!BJ49),"",DPWW2!BJ49) | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z49),"",DPWW2!Z49) | ¬¬IF(ISBLANK(DPWW2!AA49),"",DPWW2!AA49) | ¬¬IF(ISBLANK(DPWW2!AB49),"",DPWW2!AB49) | ¬¬IF(ISBLANK(DPWW2!AC49),"",DPWW2!AC49) | ¬¬IF(ISBLANK(DPWW2!AD49),"",DPWW2!AD49) | ¬¬IF(ISBLANK(DPWW2!AE49),"",DPWW2!AE49) | ¬¬IF(ISBLANK(DPWW2!AF49),"",DPWW2!AF49) | ¬¬IF(ISBLANK(DPWW2!AG49),"",DPWW2!AG49) | ¬¬IF(ISBLANK(DPWW2!AH49),"",DPWW2!AH49) | ¬¬IF(ISBLANK(DPWW2!AI49),"",DPWW2!AI49) | ¬¬IF(ISBLANK(DPWW2!AJ49),"",DPWW2!AJ49)
¬¬A567 | ¬¬IF(ISBLANK(DPWW2!BU49),"",DPWW2!BU49) | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK49),"",DPWW2!AK49) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL49),"",DPWW2!AL49)
¬¬A568 | ¬¬IF(ISBLANK(DPWW2!BX49),"",DPWW2!BX49) | ¬¬DPWW2!F49 & "," & DPWW2!G49 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H49),"",DPWW2!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN49),"",DPWW2!AN49) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO49),"",DPWW2!AO49)
¬¬A569 | ¬¬IF(ISBLANK(DPWW2!AT50),"",DPWW2!AT50) | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J50),"",DPWW2!J50)
¬¬A570 | ¬¬IF(ISBLANK(DPWW2!AV50),"",DPWW2!AV50) | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L50),"",DPWW2!L50) | ¬¬IF(ISBLANK(DPWW2!M50),"",DPWW2!M50) | ¬¬IF(ISBLANK(DPWW2!N50),"",DPWW2!N50) | ¬¬IF(ISBLANK(DPWW2!O50),"",DPWW2!O50) | ¬¬IF(ISBLANK(DPWW2!P50),"",DPWW2!P50) | ¬¬IF(ISBLANK(DPWW2!Q50),"",DPWW2!Q50) | ¬¬IF(ISBLANK(DPWW2!R50),"",DPWW2!R50) | ¬¬IF(ISBLANK(DPWW2!S50),"",DPWW2!S50) | ¬¬IF(ISBLANK(DPWW2!T50),"",DPWW2!T50) | ¬¬IF(ISBLANK(DPWW2!U50),"",DPWW2!U50) | ¬¬IF(ISBLANK(DPWW2!V50),"",DPWW2!V50)
¬¬A571 | ¬¬IF(ISBLANK(DPWW2!BG50),"",DPWW2!BG50) | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W50),"",DPWW2!W50) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X50),"",DPWW2!X50)
¬¬A572 | ¬¬IF(ISBLANK(DPWW2!BJ50),"",DPWW2!BJ50) | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z50),"",DPWW2!Z50) | ¬¬IF(ISBLANK(DPWW2!AA50),"",DPWW2!AA50) | ¬¬IF(ISBLANK(DPWW2!AB50),"",DPWW2!AB50) | ¬¬IF(ISBLANK(DPWW2!AC50),"",DPWW2!AC50) | ¬¬IF(ISBLANK(DPWW2!AD50),"",DPWW2!AD50) | ¬¬IF(ISBLANK(DPWW2!AE50),"",DPWW2!AE50) | ¬¬IF(ISBLANK(DPWW2!AF50),"",DPWW2!AF50) | ¬¬IF(ISBLANK(DPWW2!AG50),"",DPWW2!AG50) | ¬¬IF(ISBLANK(DPWW2!AH50),"",DPWW2!AH50) | ¬¬IF(ISBLANK(DPWW2!AI50),"",DPWW2!AI50) | ¬¬IF(ISBLANK(DPWW2!AJ50),"",DPWW2!AJ50)
¬¬A573 | ¬¬IF(ISBLANK(DPWW2!BU50),"",DPWW2!BU50) | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK50),"",DPWW2!AK50) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL50),"",DPWW2!AL50)
¬¬A574 | ¬¬IF(ISBLANK(DPWW2!BX50),"",DPWW2!BX50) | ¬¬DPWW2!F50 & "," & DPWW2!G50 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H50),"",DPWW2!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN50),"",DPWW2!AN50) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO50),"",DPWW2!AO50)
¬¬A575 | ¬¬IF(ISBLANK(DPWW2!AT52),"",DPWW2!AT52) | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J52),"",DPWW2!J52)
¬¬A576 | ¬¬IF(ISBLANK(DPWW2!AV52),"",DPWW2!AV52) | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L52),"",DPWW2!L52) | ¬¬IF(ISBLANK(DPWW2!M52),"",DPWW2!M52) | ¬¬IF(ISBLANK(DPWW2!N52),"",DPWW2!N52) | ¬¬IF(ISBLANK(DPWW2!O52),"",DPWW2!O52) | ¬¬IF(ISBLANK(DPWW2!P52),"",DPWW2!P52) | ¬¬IF(ISBLANK(DPWW2!Q52),"",DPWW2!Q52) | ¬¬IF(ISBLANK(DPWW2!R52),"",DPWW2!R52) | ¬¬IF(ISBLANK(DPWW2!S52),"",DPWW2!S52) | ¬¬IF(ISBLANK(DPWW2!T52),"",DPWW2!T52) | ¬¬IF(ISBLANK(DPWW2!U52),"",DPWW2!U52) | ¬¬IF(ISBLANK(DPWW2!V52),"",DPWW2!V52)
¬¬A577 | ¬¬IF(ISBLANK(DPWW2!BG52),"",DPWW2!BG52) | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W52),"",DPWW2!W52) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X52),"",DPWW2!X52)
¬¬A578 | ¬¬IF(ISBLANK(DPWW2!BJ52),"",DPWW2!BJ52) | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z52),"",DPWW2!Z52) | ¬¬IF(ISBLANK(DPWW2!AA52),"",DPWW2!AA52) | ¬¬IF(ISBLANK(DPWW2!AB52),"",DPWW2!AB52) | ¬¬IF(ISBLANK(DPWW2!AC52),"",DPWW2!AC52) | ¬¬IF(ISBLANK(DPWW2!AD52),"",DPWW2!AD52) | ¬¬IF(ISBLANK(DPWW2!AE52),"",DPWW2!AE52) | ¬¬IF(ISBLANK(DPWW2!AF52),"",DPWW2!AF52) | ¬¬IF(ISBLANK(DPWW2!AG52),"",DPWW2!AG52) | ¬¬IF(ISBLANK(DPWW2!AH52),"",DPWW2!AH52) | ¬¬IF(ISBLANK(DPWW2!AI52),"",DPWW2!AI52) | ¬¬IF(ISBLANK(DPWW2!AJ52),"",DPWW2!AJ52)
¬¬A579 | ¬¬IF(ISBLANK(DPWW2!BU52),"",DPWW2!BU52) | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK52),"",DPWW2!AK52) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL52),"",DPWW2!AL52)
¬¬A580 | ¬¬IF(ISBLANK(DPWW2!BX52),"",DPWW2!BX52) | ¬¬DPWW2!F52 & "," & DPWW2!G52 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H52),"",DPWW2!H52) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN52),"",DPWW2!AN52) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO52),"",DPWW2!AO52)
¬¬A581 | ¬¬IF(ISBLANK(DPWW2!AT53),"",DPWW2!AT53) | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) | Delta | [13 empty] | ¬¬IF(ISBLANK(DPWW2!J53),"",DPWW2!J53)
¬¬A582 | ¬¬IF(ISBLANK(DPWW2!AV53),"",DPWW2!AV53) | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!AT5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!L53),"",DPWW2!L53) | ¬¬IF(ISBLANK(DPWW2!M53),"",DPWW2!M53) | ¬¬IF(ISBLANK(DPWW2!N53),"",DPWW2!N53) | ¬¬IF(ISBLANK(DPWW2!O53),"",DPWW2!O53) | ¬¬IF(ISBLANK(DPWW2!P53),"",DPWW2!P53) | ¬¬IF(ISBLANK(DPWW2!Q53),"",DPWW2!Q53) | ¬¬IF(ISBLANK(DPWW2!R53),"",DPWW2!R53) | ¬¬IF(ISBLANK(DPWW2!S53),"",DPWW2!S53) | ¬¬IF(ISBLANK(DPWW2!T53),"",DPWW2!T53) | ¬¬IF(ISBLANK(DPWW2!U53),"",DPWW2!U53) | ¬¬IF(ISBLANK(DPWW2!V53),"",DPWW2!V53)
¬¬A583 | ¬¬IF(ISBLANK(DPWW2!BG53),"",DPWW2!BG53) | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BG5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!W53),"",DPWW2!W53) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!X53),"",DPWW2!X53)
¬¬A584 | ¬¬IF(ISBLANK(DPWW2!BJ53),"",DPWW2!BJ53) | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BH5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) | Delta |  |  | ¬¬IF(ISBLANK(DPWW2!Z53),"",DPWW2!Z53) | ¬¬IF(ISBLANK(DPWW2!AA53),"",DPWW2!AA53) | ¬¬IF(ISBLANK(DPWW2!AB53),"",DPWW2!AB53) | ¬¬IF(ISBLANK(DPWW2!AC53),"",DPWW2!AC53) | ¬¬IF(ISBLANK(DPWW2!AD53),"",DPWW2!AD53) | ¬¬IF(ISBLANK(DPWW2!AE53),"",DPWW2!AE53) | ¬¬IF(ISBLANK(DPWW2!AF53),"",DPWW2!AF53) | ¬¬IF(ISBLANK(DPWW2!AG53),"",DPWW2!AG53) | ¬¬IF(ISBLANK(DPWW2!AH53),"",DPWW2!AH53) | ¬¬IF(ISBLANK(DPWW2!AI53),"",DPWW2!AI53) | ¬¬IF(ISBLANK(DPWW2!AJ53),"",DPWW2!AJ53)
¬¬A585 | ¬¬IF(ISBLANK(DPWW2!BU53),"",DPWW2!BU53) | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BU5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AK53),"",DPWW2!AK53) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AL53),"",DPWW2!AL53)
¬¬A586 | ¬¬IF(ISBLANK(DPWW2!BX53),"",DPWW2!BX53) | ¬¬DPWW2!F53 & "," & DPWW2!G53 & "," & DPWW2!BX5 | ¬¬IF(ISBLANK(DPWW2!H53),"",DPWW2!H53) | Delta | [7 empty] | ¬¬IF(ISBLANK(DPWW2!AN53),"",DPWW2!AN53) |  |  |  |  | ¬¬IF(ISBLANK(DPWW2!AO53),"",DPWW2!AO53)
¬¬A587 | ¬¬IF(ISBLANK(DPWW3!GW7),"",DPWW3!GW7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!K7),"",DPWW3!K7)
¬¬A588 | ¬¬IF(ISBLANK(DPWW3!GY7),"",DPWW3!GY7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M7),"",DPWW3!M7) | ¬¬IF(ISBLANK(DPWW3!N7),"",DPWW3!N7) | ¬¬IF(ISBLANK(DPWW3!O7),"",DPWW3!O7) | ¬¬IF(ISBLANK(DPWW3!P7),"",DPWW3!P7) | ¬¬IF(ISBLANK(DPWW3!Q7),"",DPWW3!Q7) | ¬¬IF(ISBLANK(DPWW3!R7),"",DPWW3!R7) | ¬¬IF(ISBLANK(DPWW3!S7),"",DPWW3!S7) | ¬¬IF(ISBLANK(DPWW3!T7),"",DPWW3!T7) | ¬¬IF(ISBLANK(DPWW3!U7),"",DPWW3!U7) | ¬¬IF(ISBLANK(DPWW3!V7),"",DPWW3!V7) | ¬¬IF(ISBLANK(DPWW3!W7),"",DPWW3!W7) | ¬¬IF(ISBLANK(DPWW3!X7),"",DPWW3!X7) | ¬¬IF(ISBLANK(DPWW3!Y7),"",DPWW3!Y7) | ¬¬IF(ISBLANK(DPWW3!Z7),"",DPWW3!Z7) | ¬¬IF(ISBLANK(DPWW3!AA7),"",DPWW3!AA7) | ¬¬IF(ISBLANK(DPWW3!AB7),"",DPWW3!AB7) | ¬¬IF(ISBLANK(DPWW3!AC7),"",DPWW3!AC7) | ¬¬IF(ISBLANK(DPWW3!AD7),"",DPWW3!AD7) | ¬¬IF(ISBLANK(DPWW3!AE7),"",DPWW3!AE7) | ¬¬IF(ISBLANK(DPWW3!AF7),"",DPWW3!AF7) | ¬¬IF(ISBLANK(DPWW3!AG7),"",DPWW3!AG7)
¬¬A589 | ¬¬IF(ISBLANK(DPWW3!HU7),"",DPWW3!HU7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI7),"",DPWW3!AI7) | ¬¬IF(ISBLANK(DPWW3!AJ7),"",DPWW3!AJ7) | ¬¬IF(ISBLANK(DPWW3!AK7),"",DPWW3!AK7) | ¬¬IF(ISBLANK(DPWW3!AL7),"",DPWW3!AL7) | ¬¬IF(ISBLANK(DPWW3!AM7),"",DPWW3!AM7) | ¬¬IF(ISBLANK(DPWW3!AN7),"",DPWW3!AN7) | ¬¬IF(ISBLANK(DPWW3!AO7),"",DPWW3!AO7) | ¬¬IF(ISBLANK(DPWW3!AP7),"",DPWW3!AP7) | ¬¬IF(ISBLANK(DPWW3!AQ7),"",DPWW3!AQ7) | ¬¬IF(ISBLANK(DPWW3!AR7),"",DPWW3!AR7) | ¬¬IF(ISBLANK(DPWW3!AS7),"",DPWW3!AS7) | ¬¬IF(ISBLANK(DPWW3!AT7),"",DPWW3!AT7) | ¬¬IF(ISBLANK(DPWW3!AU7),"",DPWW3!AU7) | ¬¬IF(ISBLANK(DPWW3!AV7),"",DPWW3!AV7) | ¬¬IF(ISBLANK(DPWW3!AW7),"",DPWW3!AW7) | ¬¬IF(ISBLANK(DPWW3!AX7),"",DPWW3!AX7) | ¬¬IF(ISBLANK(DPWW3!AY7),"",DPWW3!AY7) | ¬¬IF(ISBLANK(DPWW3!AZ7),"",DPWW3!AZ7) | ¬¬IF(ISBLANK(DPWW3!BA7),"",DPWW3!BA7) | ¬¬IF(ISBLANK(DPWW3!BB7),"",DPWW3!BB7) | ¬¬IF(ISBLANK(DPWW3!BC7),"",DPWW3!BC7)
¬¬A590 | ¬¬IF(ISBLANK(DPWW3!IQ7),"",DPWW3!IQ7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE7),"",DPWW3!BE7) | ¬¬IF(ISBLANK(DPWW3!BF7),"",DPWW3!BF7) | ¬¬IF(ISBLANK(DPWW3!BG7),"",DPWW3!BG7) | ¬¬IF(ISBLANK(DPWW3!BH7),"",DPWW3!BH7) | ¬¬IF(ISBLANK(DPWW3!BI7),"",DPWW3!BI7) | ¬¬IF(ISBLANK(DPWW3!BJ7),"",DPWW3!BJ7) | ¬¬IF(ISBLANK(DPWW3!BK7),"",DPWW3!BK7) | ¬¬IF(ISBLANK(DPWW3!BL7),"",DPWW3!BL7) | ¬¬IF(ISBLANK(DPWW3!BM7),"",DPWW3!BM7) | ¬¬IF(ISBLANK(DPWW3!BN7),"",DPWW3!BN7) | ¬¬IF(ISBLANK(DPWW3!BO7),"",DPWW3!BO7) | ¬¬IF(ISBLANK(DPWW3!BP7),"",DPWW3!BP7) | ¬¬IF(ISBLANK(DPWW3!BQ7),"",DPWW3!BQ7) | ¬¬IF(ISBLANK(DPWW3!BR7),"",DPWW3!BR7) | ¬¬IF(ISBLANK(DPWW3!BS7),"",DPWW3!BS7) | ¬¬IF(ISBLANK(DPWW3!BT7),"",DPWW3!BT7) | ¬¬IF(ISBLANK(DPWW3!BU7),"",DPWW3!BU7) | ¬¬IF(ISBLANK(DPWW3!BV7),"",DPWW3!BV7) | ¬¬IF(ISBLANK(DPWW3!BW7),"",DPWW3!BW7) | ¬¬IF(ISBLANK(DPWW3!BX7),"",DPWW3!BX7) | ¬¬IF(ISBLANK(DPWW3!BY7),"",DPWW3!BY7)
¬¬A591 | ¬¬IF(ISBLANK(DPWW3!JM7),"",DPWW3!JM7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA7),"",DPWW3!CA7) | ¬¬IF(ISBLANK(DPWW3!CB7),"",DPWW3!CB7) | ¬¬IF(ISBLANK(DPWW3!CC7),"",DPWW3!CC7) | ¬¬IF(ISBLANK(DPWW3!CD7),"",DPWW3!CD7) | ¬¬IF(ISBLANK(DPWW3!CE7),"",DPWW3!CE7) | ¬¬IF(ISBLANK(DPWW3!CF7),"",DPWW3!CF7) | ¬¬IF(ISBLANK(DPWW3!CG7),"",DPWW3!CG7) | ¬¬IF(ISBLANK(DPWW3!CH7),"",DPWW3!CH7) | ¬¬IF(ISBLANK(DPWW3!CI7),"",DPWW3!CI7) | ¬¬IF(ISBLANK(DPWW3!CJ7),"",DPWW3!CJ7) | ¬¬IF(ISBLANK(DPWW3!CK7),"",DPWW3!CK7) | ¬¬IF(ISBLANK(DPWW3!CL7),"",DPWW3!CL7) | ¬¬IF(ISBLANK(DPWW3!CM7),"",DPWW3!CM7) | ¬¬IF(ISBLANK(DPWW3!CN7),"",DPWW3!CN7) | ¬¬IF(ISBLANK(DPWW3!CO7),"",DPWW3!CO7) | ¬¬IF(ISBLANK(DPWW3!CP7),"",DPWW3!CP7) | ¬¬IF(ISBLANK(DPWW3!CQ7),"",DPWW3!CQ7) | ¬¬IF(ISBLANK(DPWW3!CR7),"",DPWW3!CR7) | ¬¬IF(ISBLANK(DPWW3!CS7),"",DPWW3!CS7) | ¬¬IF(ISBLANK(DPWW3!CT7),"",DPWW3!CT7) | ¬¬IF(ISBLANK(DPWW3!CU7),"",DPWW3!CU7)
¬¬A592 | ¬¬IF(ISBLANK(DPWW3!KI7),"",DPWW3!KI7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW7),"",DPWW3!CW7) | ¬¬IF(ISBLANK(DPWW3!CX7),"",DPWW3!CX7) | ¬¬IF(ISBLANK(DPWW3!CY7),"",DPWW3!CY7) | ¬¬IF(ISBLANK(DPWW3!CZ7),"",DPWW3!CZ7) | ¬¬IF(ISBLANK(DPWW3!DA7),"",DPWW3!DA7) | ¬¬IF(ISBLANK(DPWW3!DB7),"",DPWW3!DB7) | ¬¬IF(ISBLANK(DPWW3!DC7),"",DPWW3!DC7) | ¬¬IF(ISBLANK(DPWW3!DD7),"",DPWW3!DD7) | ¬¬IF(ISBLANK(DPWW3!DE7),"",DPWW3!DE7) | ¬¬IF(ISBLANK(DPWW3!DF7),"",DPWW3!DF7) | ¬¬IF(ISBLANK(DPWW3!DG7),"",DPWW3!DG7) | ¬¬IF(ISBLANK(DPWW3!DH7),"",DPWW3!DH7) | ¬¬IF(ISBLANK(DPWW3!DI7),"",DPWW3!DI7) | ¬¬IF(ISBLANK(DPWW3!DJ7),"",DPWW3!DJ7) | ¬¬IF(ISBLANK(DPWW3!DK7),"",DPWW3!DK7) | ¬¬IF(ISBLANK(DPWW3!DL7),"",DPWW3!DL7) | ¬¬IF(ISBLANK(DPWW3!DM7),"",DPWW3!DM7) | ¬¬IF(ISBLANK(DPWW3!DN7),"",DPWW3!DN7) | ¬¬IF(ISBLANK(DPWW3!DO7),"",DPWW3!DO7) | ¬¬IF(ISBLANK(DPWW3!DP7),"",DPWW3!DP7) | ¬¬IF(ISBLANK(DPWW3!DQ7),"",DPWW3!DQ7)
¬¬A593 | ¬¬IF(ISBLANK(DPWW3!LE7),"",DPWW3!LE7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS7),"",DPWW3!DS7) | ¬¬IF(ISBLANK(DPWW3!DT7),"",DPWW3!DT7) | ¬¬IF(ISBLANK(DPWW3!DU7),"",DPWW3!DU7) | ¬¬IF(ISBLANK(DPWW3!DV7),"",DPWW3!DV7) | ¬¬IF(ISBLANK(DPWW3!DW7),"",DPWW3!DW7) | ¬¬IF(ISBLANK(DPWW3!DX7),"",DPWW3!DX7) | ¬¬IF(ISBLANK(DPWW3!DY7),"",DPWW3!DY7) | ¬¬IF(ISBLANK(DPWW3!DZ7),"",DPWW3!DZ7) | ¬¬IF(ISBLANK(DPWW3!EA7),"",DPWW3!EA7) | ¬¬IF(ISBLANK(DPWW3!EB7),"",DPWW3!EB7) | ¬¬IF(ISBLANK(DPWW3!EC7),"",DPWW3!EC7) | ¬¬IF(ISBLANK(DPWW3!ED7),"",DPWW3!ED7) | ¬¬IF(ISBLANK(DPWW3!EE7),"",DPWW3!EE7) | ¬¬IF(ISBLANK(DPWW3!EF7),"",DPWW3!EF7) | ¬¬IF(ISBLANK(DPWW3!EG7),"",DPWW3!EG7) | ¬¬IF(ISBLANK(DPWW3!EH7),"",DPWW3!EH7) | ¬¬IF(ISBLANK(DPWW3!EI7),"",DPWW3!EI7) | ¬¬IF(ISBLANK(DPWW3!EJ7),"",DPWW3!EJ7) | ¬¬IF(ISBLANK(DPWW3!EK7),"",DPWW3!EK7) | ¬¬IF(ISBLANK(DPWW3!EL7),"",DPWW3!EL7) | ¬¬IF(ISBLANK(DPWW3!EM7),"",DPWW3!EM7)
¬¬A594 | ¬¬IF(ISBLANK(DPWW3!MA7),"",DPWW3!MA7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO7),"",DPWW3!EO7) | ¬¬IF(ISBLANK(DPWW3!EP7),"",DPWW3!EP7) | ¬¬IF(ISBLANK(DPWW3!EQ7),"",DPWW3!EQ7) | ¬¬IF(ISBLANK(DPWW3!ER7),"",DPWW3!ER7) | ¬¬IF(ISBLANK(DPWW3!ES7),"",DPWW3!ES7) | ¬¬IF(ISBLANK(DPWW3!ET7),"",DPWW3!ET7) | ¬¬IF(ISBLANK(DPWW3!EU7),"",DPWW3!EU7) | ¬¬IF(ISBLANK(DPWW3!EV7),"",DPWW3!EV7) | ¬¬IF(ISBLANK(DPWW3!EW7),"",DPWW3!EW7) | ¬¬IF(ISBLANK(DPWW3!EX7),"",DPWW3!EX7) | ¬¬IF(ISBLANK(DPWW3!EY7),"",DPWW3!EY7) | ¬¬IF(ISBLANK(DPWW3!EZ7),"",DPWW3!EZ7) | ¬¬IF(ISBLANK(DPWW3!FA7),"",DPWW3!FA7) | ¬¬IF(ISBLANK(DPWW3!FB7),"",DPWW3!FB7) | ¬¬IF(ISBLANK(DPWW3!FC7),"",DPWW3!FC7) | ¬¬IF(ISBLANK(DPWW3!FD7),"",DPWW3!FD7) | ¬¬IF(ISBLANK(DPWW3!FE7),"",DPWW3!FE7) | ¬¬IF(ISBLANK(DPWW3!FF7),"",DPWW3!FF7) | ¬¬IF(ISBLANK(DPWW3!FG7),"",DPWW3!FG7) | ¬¬IF(ISBLANK(DPWW3!FH7),"",DPWW3!FH7) | ¬¬IF(ISBLANK(DPWW3!FI7),"",DPWW3!FI7)
¬¬A595 | ¬¬IF(ISBLANK(DPWW3!MW7),"",DPWW3!MW7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK7),"",DPWW3!FK7) | ¬¬IF(ISBLANK(DPWW3!FL7),"",DPWW3!FL7) | ¬¬IF(ISBLANK(DPWW3!FM7),"",DPWW3!FM7) | ¬¬IF(ISBLANK(DPWW3!FN7),"",DPWW3!FN7) | ¬¬IF(ISBLANK(DPWW3!FO7),"",DPWW3!FO7) | ¬¬IF(ISBLANK(DPWW3!FP7),"",DPWW3!FP7) | ¬¬IF(ISBLANK(DPWW3!FQ7),"",DPWW3!FQ7) | ¬¬IF(ISBLANK(DPWW3!FR7),"",DPWW3!FR7) | ¬¬IF(ISBLANK(DPWW3!FS7),"",DPWW3!FS7) | ¬¬IF(ISBLANK(DPWW3!FT7),"",DPWW3!FT7) | ¬¬IF(ISBLANK(DPWW3!FU7),"",DPWW3!FU7) | ¬¬IF(ISBLANK(DPWW3!FV7),"",DPWW3!FV7) | ¬¬IF(ISBLANK(DPWW3!FW7),"",DPWW3!FW7) | ¬¬IF(ISBLANK(DPWW3!FX7),"",DPWW3!FX7) | ¬¬IF(ISBLANK(DPWW3!FY7),"",DPWW3!FY7) | ¬¬IF(ISBLANK(DPWW3!FZ7),"",DPWW3!FZ7) | ¬¬IF(ISBLANK(DPWW3!GA7),"",DPWW3!GA7) | ¬¬IF(ISBLANK(DPWW3!GB7),"",DPWW3!GB7) | ¬¬IF(ISBLANK(DPWW3!GC7),"",DPWW3!GC7) | ¬¬IF(ISBLANK(DPWW3!GD7),"",DPWW3!GD7) | ¬¬IF(ISBLANK(DPWW3!GE7),"",DPWW3!GE7)
¬¬A596 | ¬¬IF(ISBLANK(DPWW3!NS7),"",DPWW3!NS7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GG7),"",DPWW3!GG7)
¬¬A597 | ¬¬IF(ISBLANK(DPWW3!NT7),"",DPWW3!NT7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GH7),"",DPWW3!GH7)
¬¬A598 | ¬¬IF(ISBLANK(DPWW3!NU7),"",DPWW3!NU7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GI7),"",DPWW3!GI7)
¬¬A599 | ¬¬IF(ISBLANK(DPWW3!NV7),"",DPWW3!NV7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ7),"",DPWW3!GJ7)
¬¬A600 | ¬¬IF(ISBLANK(DPWW3!NW7),"",DPWW3!NW7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GK7),"",DPWW3!GK7)
¬¬A601 | ¬¬IF(ISBLANK(DPWW3!NX7),"",DPWW3!NX7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GL7),"",DPWW3!GL7)
¬¬A602 | ¬¬IF(ISBLANK(DPWW3!NY7),"",DPWW3!NY7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GM7),"",DPWW3!GM7)
¬¬A603 | ¬¬IF(ISBLANK(DPWW3!NZ7),"",DPWW3!NZ7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GN7),"",DPWW3!GN7)
¬¬A604 | ¬¬IF(ISBLANK(DPWW3!OA7),"",DPWW3!OA7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GO7),"",DPWW3!GO7)
¬¬A605 | ¬¬IF(ISBLANK(DPWW3!OB7),"",DPWW3!OB7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GP7),"",DPWW3!GP7)
¬¬A606 | ¬¬IF(ISBLANK(DPWW3!OC7),"",DPWW3!OC7) | ¬¬DPWW3!F7 & "," & DPWW3!G7 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H7),"",DPWW3!H7) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ7),"",DPWW3!GQ7)
¬¬A607 | ¬¬IF(ISBLANK(DPWW3!GW8),"",DPWW3!GW8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!K8),"",DPWW3!K8)
¬¬A608 | ¬¬IF(ISBLANK(DPWW3!GY8),"",DPWW3!GY8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M8),"",DPWW3!M8) | ¬¬IF(ISBLANK(DPWW3!N8),"",DPWW3!N8) | ¬¬IF(ISBLANK(DPWW3!O8),"",DPWW3!O8) | ¬¬IF(ISBLANK(DPWW3!P8),"",DPWW3!P8) | ¬¬IF(ISBLANK(DPWW3!Q8),"",DPWW3!Q8) | ¬¬IF(ISBLANK(DPWW3!R8),"",DPWW3!R8) | ¬¬IF(ISBLANK(DPWW3!S8),"",DPWW3!S8) | ¬¬IF(ISBLANK(DPWW3!T8),"",DPWW3!T8) | ¬¬IF(ISBLANK(DPWW3!U8),"",DPWW3!U8) | ¬¬IF(ISBLANK(DPWW3!V8),"",DPWW3!V8) | ¬¬IF(ISBLANK(DPWW3!W8),"",DPWW3!W8) | ¬¬IF(ISBLANK(DPWW3!X8),"",DPWW3!X8) | ¬¬IF(ISBLANK(DPWW3!Y8),"",DPWW3!Y8) | ¬¬IF(ISBLANK(DPWW3!Z8),"",DPWW3!Z8) | ¬¬IF(ISBLANK(DPWW3!AA8),"",DPWW3!AA8) | ¬¬IF(ISBLANK(DPWW3!AB8),"",DPWW3!AB8) | ¬¬IF(ISBLANK(DPWW3!AC8),"",DPWW3!AC8) | ¬¬IF(ISBLANK(DPWW3!AD8),"",DPWW3!AD8) | ¬¬IF(ISBLANK(DPWW3!AE8),"",DPWW3!AE8) | ¬¬IF(ISBLANK(DPWW3!AF8),"",DPWW3!AF8) | ¬¬IF(ISBLANK(DPWW3!AG8),"",DPWW3!AG8)
¬¬A609 | ¬¬IF(ISBLANK(DPWW3!HU8),"",DPWW3!HU8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI8),"",DPWW3!AI8) | ¬¬IF(ISBLANK(DPWW3!AJ8),"",DPWW3!AJ8) | ¬¬IF(ISBLANK(DPWW3!AK8),"",DPWW3!AK8) | ¬¬IF(ISBLANK(DPWW3!AL8),"",DPWW3!AL8) | ¬¬IF(ISBLANK(DPWW3!AM8),"",DPWW3!AM8) | ¬¬IF(ISBLANK(DPWW3!AN8),"",DPWW3!AN8) | ¬¬IF(ISBLANK(DPWW3!AO8),"",DPWW3!AO8) | ¬¬IF(ISBLANK(DPWW3!AP8),"",DPWW3!AP8) | ¬¬IF(ISBLANK(DPWW3!AQ8),"",DPWW3!AQ8) | ¬¬IF(ISBLANK(DPWW3!AR8),"",DPWW3!AR8) | ¬¬IF(ISBLANK(DPWW3!AS8),"",DPWW3!AS8) | ¬¬IF(ISBLANK(DPWW3!AT8),"",DPWW3!AT8) | ¬¬IF(ISBLANK(DPWW3!AU8),"",DPWW3!AU8) | ¬¬IF(ISBLANK(DPWW3!AV8),"",DPWW3!AV8) | ¬¬IF(ISBLANK(DPWW3!AW8),"",DPWW3!AW8) | ¬¬IF(ISBLANK(DPWW3!AX8),"",DPWW3!AX8) | ¬¬IF(ISBLANK(DPWW3!AY8),"",DPWW3!AY8) | ¬¬IF(ISBLANK(DPWW3!AZ8),"",DPWW3!AZ8) | ¬¬IF(ISBLANK(DPWW3!BA8),"",DPWW3!BA8) | ¬¬IF(ISBLANK(DPWW3!BB8),"",DPWW3!BB8) | ¬¬IF(ISBLANK(DPWW3!BC8),"",DPWW3!BC8)
¬¬A610 | ¬¬IF(ISBLANK(DPWW3!IQ8),"",DPWW3!IQ8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE8),"",DPWW3!BE8) | ¬¬IF(ISBLANK(DPWW3!BF8),"",DPWW3!BF8) | ¬¬IF(ISBLANK(DPWW3!BG8),"",DPWW3!BG8) | ¬¬IF(ISBLANK(DPWW3!BH8),"",DPWW3!BH8) | ¬¬IF(ISBLANK(DPWW3!BI8),"",DPWW3!BI8) | ¬¬IF(ISBLANK(DPWW3!BJ8),"",DPWW3!BJ8) | ¬¬IF(ISBLANK(DPWW3!BK8),"",DPWW3!BK8) | ¬¬IF(ISBLANK(DPWW3!BL8),"",DPWW3!BL8) | ¬¬IF(ISBLANK(DPWW3!BM8),"",DPWW3!BM8) | ¬¬IF(ISBLANK(DPWW3!BN8),"",DPWW3!BN8) | ¬¬IF(ISBLANK(DPWW3!BO8),"",DPWW3!BO8) | ¬¬IF(ISBLANK(DPWW3!BP8),"",DPWW3!BP8) | ¬¬IF(ISBLANK(DPWW3!BQ8),"",DPWW3!BQ8) | ¬¬IF(ISBLANK(DPWW3!BR8),"",DPWW3!BR8) | ¬¬IF(ISBLANK(DPWW3!BS8),"",DPWW3!BS8) | ¬¬IF(ISBLANK(DPWW3!BT8),"",DPWW3!BT8) | ¬¬IF(ISBLANK(DPWW3!BU8),"",DPWW3!BU8) | ¬¬IF(ISBLANK(DPWW3!BV8),"",DPWW3!BV8) | ¬¬IF(ISBLANK(DPWW3!BW8),"",DPWW3!BW8) | ¬¬IF(ISBLANK(DPWW3!BX8),"",DPWW3!BX8) | ¬¬IF(ISBLANK(DPWW3!BY8),"",DPWW3!BY8)
¬¬A611 | ¬¬IF(ISBLANK(DPWW3!JM8),"",DPWW3!JM8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA8),"",DPWW3!CA8) | ¬¬IF(ISBLANK(DPWW3!CB8),"",DPWW3!CB8) | ¬¬IF(ISBLANK(DPWW3!CC8),"",DPWW3!CC8) | ¬¬IF(ISBLANK(DPWW3!CD8),"",DPWW3!CD8) | ¬¬IF(ISBLANK(DPWW3!CE8),"",DPWW3!CE8) | ¬¬IF(ISBLANK(DPWW3!CF8),"",DPWW3!CF8) | ¬¬IF(ISBLANK(DPWW3!CG8),"",DPWW3!CG8) | ¬¬IF(ISBLANK(DPWW3!CH8),"",DPWW3!CH8) | ¬¬IF(ISBLANK(DPWW3!CI8),"",DPWW3!CI8) | ¬¬IF(ISBLANK(DPWW3!CJ8),"",DPWW3!CJ8) | ¬¬IF(ISBLANK(DPWW3!CK8),"",DPWW3!CK8) | ¬¬IF(ISBLANK(DPWW3!CL8),"",DPWW3!CL8) | ¬¬IF(ISBLANK(DPWW3!CM8),"",DPWW3!CM8) | ¬¬IF(ISBLANK(DPWW3!CN8),"",DPWW3!CN8) | ¬¬IF(ISBLANK(DPWW3!CO8),"",DPWW3!CO8) | ¬¬IF(ISBLANK(DPWW3!CP8),"",DPWW3!CP8) | ¬¬IF(ISBLANK(DPWW3!CQ8),"",DPWW3!CQ8) | ¬¬IF(ISBLANK(DPWW3!CR8),"",DPWW3!CR8) | ¬¬IF(ISBLANK(DPWW3!CS8),"",DPWW3!CS8) | ¬¬IF(ISBLANK(DPWW3!CT8),"",DPWW3!CT8) | ¬¬IF(ISBLANK(DPWW3!CU8),"",DPWW3!CU8)
¬¬A612 | ¬¬IF(ISBLANK(DPWW3!KI8),"",DPWW3!KI8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW8),"",DPWW3!CW8) | ¬¬IF(ISBLANK(DPWW3!CX8),"",DPWW3!CX8) | ¬¬IF(ISBLANK(DPWW3!CY8),"",DPWW3!CY8) | ¬¬IF(ISBLANK(DPWW3!CZ8),"",DPWW3!CZ8) | ¬¬IF(ISBLANK(DPWW3!DA8),"",DPWW3!DA8) | ¬¬IF(ISBLANK(DPWW3!DB8),"",DPWW3!DB8) | ¬¬IF(ISBLANK(DPWW3!DC8),"",DPWW3!DC8) | ¬¬IF(ISBLANK(DPWW3!DD8),"",DPWW3!DD8) | ¬¬IF(ISBLANK(DPWW3!DE8),"",DPWW3!DE8) | ¬¬IF(ISBLANK(DPWW3!DF8),"",DPWW3!DF8) | ¬¬IF(ISBLANK(DPWW3!DG8),"",DPWW3!DG8) | ¬¬IF(ISBLANK(DPWW3!DH8),"",DPWW3!DH8) | ¬¬IF(ISBLANK(DPWW3!DI8),"",DPWW3!DI8) | ¬¬IF(ISBLANK(DPWW3!DJ8),"",DPWW3!DJ8) | ¬¬IF(ISBLANK(DPWW3!DK8),"",DPWW3!DK8) | ¬¬IF(ISBLANK(DPWW3!DL8),"",DPWW3!DL8) | ¬¬IF(ISBLANK(DPWW3!DM8),"",DPWW3!DM8) | ¬¬IF(ISBLANK(DPWW3!DN8),"",DPWW3!DN8) | ¬¬IF(ISBLANK(DPWW3!DO8),"",DPWW3!DO8) | ¬¬IF(ISBLANK(DPWW3!DP8),"",DPWW3!DP8) | ¬¬IF(ISBLANK(DPWW3!DQ8),"",DPWW3!DQ8)
¬¬A613 | ¬¬IF(ISBLANK(DPWW3!LE8),"",DPWW3!LE8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS8),"",DPWW3!DS8) | ¬¬IF(ISBLANK(DPWW3!DT8),"",DPWW3!DT8) | ¬¬IF(ISBLANK(DPWW3!DU8),"",DPWW3!DU8) | ¬¬IF(ISBLANK(DPWW3!DV8),"",DPWW3!DV8) | ¬¬IF(ISBLANK(DPWW3!DW8),"",DPWW3!DW8) | ¬¬IF(ISBLANK(DPWW3!DX8),"",DPWW3!DX8) | ¬¬IF(ISBLANK(DPWW3!DY8),"",DPWW3!DY8) | ¬¬IF(ISBLANK(DPWW3!DZ8),"",DPWW3!DZ8) | ¬¬IF(ISBLANK(DPWW3!EA8),"",DPWW3!EA8) | ¬¬IF(ISBLANK(DPWW3!EB8),"",DPWW3!EB8) | ¬¬IF(ISBLANK(DPWW3!EC8),"",DPWW3!EC8) | ¬¬IF(ISBLANK(DPWW3!ED8),"",DPWW3!ED8) | ¬¬IF(ISBLANK(DPWW3!EE8),"",DPWW3!EE8) | ¬¬IF(ISBLANK(DPWW3!EF8),"",DPWW3!EF8) | ¬¬IF(ISBLANK(DPWW3!EG8),"",DPWW3!EG8) | ¬¬IF(ISBLANK(DPWW3!EH8),"",DPWW3!EH8) | ¬¬IF(ISBLANK(DPWW3!EI8),"",DPWW3!EI8) | ¬¬IF(ISBLANK(DPWW3!EJ8),"",DPWW3!EJ8) | ¬¬IF(ISBLANK(DPWW3!EK8),"",DPWW3!EK8) | ¬¬IF(ISBLANK(DPWW3!EL8),"",DPWW3!EL8) | ¬¬IF(ISBLANK(DPWW3!EM8),"",DPWW3!EM8)
¬¬A614 | ¬¬IF(ISBLANK(DPWW3!MA8),"",DPWW3!MA8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO8),"",DPWW3!EO8) | ¬¬IF(ISBLANK(DPWW3!EP8),"",DPWW3!EP8) | ¬¬IF(ISBLANK(DPWW3!EQ8),"",DPWW3!EQ8) | ¬¬IF(ISBLANK(DPWW3!ER8),"",DPWW3!ER8) | ¬¬IF(ISBLANK(DPWW3!ES8),"",DPWW3!ES8) | ¬¬IF(ISBLANK(DPWW3!ET8),"",DPWW3!ET8) | ¬¬IF(ISBLANK(DPWW3!EU8),"",DPWW3!EU8) | ¬¬IF(ISBLANK(DPWW3!EV8),"",DPWW3!EV8) | ¬¬IF(ISBLANK(DPWW3!EW8),"",DPWW3!EW8) | ¬¬IF(ISBLANK(DPWW3!EX8),"",DPWW3!EX8) | ¬¬IF(ISBLANK(DPWW3!EY8),"",DPWW3!EY8) | ¬¬IF(ISBLANK(DPWW3!EZ8),"",DPWW3!EZ8) | ¬¬IF(ISBLANK(DPWW3!FA8),"",DPWW3!FA8) | ¬¬IF(ISBLANK(DPWW3!FB8),"",DPWW3!FB8) | ¬¬IF(ISBLANK(DPWW3!FC8),"",DPWW3!FC8) | ¬¬IF(ISBLANK(DPWW3!FD8),"",DPWW3!FD8) | ¬¬IF(ISBLANK(DPWW3!FE8),"",DPWW3!FE8) | ¬¬IF(ISBLANK(DPWW3!FF8),"",DPWW3!FF8) | ¬¬IF(ISBLANK(DPWW3!FG8),"",DPWW3!FG8) | ¬¬IF(ISBLANK(DPWW3!FH8),"",DPWW3!FH8) | ¬¬IF(ISBLANK(DPWW3!FI8),"",DPWW3!FI8)
¬¬A615 | ¬¬IF(ISBLANK(DPWW3!MW8),"",DPWW3!MW8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK8),"",DPWW3!FK8) | ¬¬IF(ISBLANK(DPWW3!FL8),"",DPWW3!FL8) | ¬¬IF(ISBLANK(DPWW3!FM8),"",DPWW3!FM8) | ¬¬IF(ISBLANK(DPWW3!FN8),"",DPWW3!FN8) | ¬¬IF(ISBLANK(DPWW3!FO8),"",DPWW3!FO8) | ¬¬IF(ISBLANK(DPWW3!FP8),"",DPWW3!FP8) | ¬¬IF(ISBLANK(DPWW3!FQ8),"",DPWW3!FQ8) | ¬¬IF(ISBLANK(DPWW3!FR8),"",DPWW3!FR8) | ¬¬IF(ISBLANK(DPWW3!FS8),"",DPWW3!FS8) | ¬¬IF(ISBLANK(DPWW3!FT8),"",DPWW3!FT8) | ¬¬IF(ISBLANK(DPWW3!FU8),"",DPWW3!FU8) | ¬¬IF(ISBLANK(DPWW3!FV8),"",DPWW3!FV8) | ¬¬IF(ISBLANK(DPWW3!FW8),"",DPWW3!FW8) | ¬¬IF(ISBLANK(DPWW3!FX8),"",DPWW3!FX8) | ¬¬IF(ISBLANK(DPWW3!FY8),"",DPWW3!FY8) | ¬¬IF(ISBLANK(DPWW3!FZ8),"",DPWW3!FZ8) | ¬¬IF(ISBLANK(DPWW3!GA8),"",DPWW3!GA8) | ¬¬IF(ISBLANK(DPWW3!GB8),"",DPWW3!GB8) | ¬¬IF(ISBLANK(DPWW3!GC8),"",DPWW3!GC8) | ¬¬IF(ISBLANK(DPWW3!GD8),"",DPWW3!GD8) | ¬¬IF(ISBLANK(DPWW3!GE8),"",DPWW3!GE8)
¬¬A616 | ¬¬IF(ISBLANK(DPWW3!NS8),"",DPWW3!NS8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GG8),"",DPWW3!GG8)
¬¬A617 | ¬¬IF(ISBLANK(DPWW3!NT8),"",DPWW3!NT8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GH8),"",DPWW3!GH8)
¬¬A618 | ¬¬IF(ISBLANK(DPWW3!NU8),"",DPWW3!NU8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GI8),"",DPWW3!GI8)
¬¬A619 | ¬¬IF(ISBLANK(DPWW3!NV8),"",DPWW3!NV8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ8),"",DPWW3!GJ8)
¬¬A620 | ¬¬IF(ISBLANK(DPWW3!NW8),"",DPWW3!NW8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GK8),"",DPWW3!GK8)
¬¬A621 | ¬¬IF(ISBLANK(DPWW3!NX8),"",DPWW3!NX8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GL8),"",DPWW3!GL8)
¬¬A622 | ¬¬IF(ISBLANK(DPWW3!NY8),"",DPWW3!NY8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GM8),"",DPWW3!GM8)
¬¬A623 | ¬¬IF(ISBLANK(DPWW3!NZ8),"",DPWW3!NZ8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GN8),"",DPWW3!GN8)
¬¬A624 | ¬¬IF(ISBLANK(DPWW3!OA8),"",DPWW3!OA8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GO8),"",DPWW3!GO8)
¬¬A625 | ¬¬IF(ISBLANK(DPWW3!OB8),"",DPWW3!OB8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GP8),"",DPWW3!GP8)
¬¬A626 | ¬¬IF(ISBLANK(DPWW3!OC8),"",DPWW3!OC8) | ¬¬DPWW3!F8 & "," & DPWW3!G8 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H8),"",DPWW3!H8) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ8),"",DPWW3!GQ8)
¬¬A627 | ¬¬IF(ISBLANK(DPWW3!GW9),"",DPWW3!GW9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!K9),"",DPWW3!K9)
¬¬A628 | ¬¬IF(ISBLANK(DPWW3!GY9),"",DPWW3!GY9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M9),"",DPWW3!M9) | ¬¬IF(ISBLANK(DPWW3!N9),"",DPWW3!N9) | ¬¬IF(ISBLANK(DPWW3!O9),"",DPWW3!O9) | ¬¬IF(ISBLANK(DPWW3!P9),"",DPWW3!P9) | ¬¬IF(ISBLANK(DPWW3!Q9),"",DPWW3!Q9) | ¬¬IF(ISBLANK(DPWW3!R9),"",DPWW3!R9) | ¬¬IF(ISBLANK(DPWW3!S9),"",DPWW3!S9) | ¬¬IF(ISBLANK(DPWW3!T9),"",DPWW3!T9) | ¬¬IF(ISBLANK(DPWW3!U9),"",DPWW3!U9) | ¬¬IF(ISBLANK(DPWW3!V9),"",DPWW3!V9) | ¬¬IF(ISBLANK(DPWW3!W9),"",DPWW3!W9) | ¬¬IF(ISBLANK(DPWW3!X9),"",DPWW3!X9) | ¬¬IF(ISBLANK(DPWW3!Y9),"",DPWW3!Y9) | ¬¬IF(ISBLANK(DPWW3!Z9),"",DPWW3!Z9) | ¬¬IF(ISBLANK(DPWW3!AA9),"",DPWW3!AA9) | ¬¬IF(ISBLANK(DPWW3!AB9),"",DPWW3!AB9) | ¬¬IF(ISBLANK(DPWW3!AC9),"",DPWW3!AC9) | ¬¬IF(ISBLANK(DPWW3!AD9),"",DPWW3!AD9) | ¬¬IF(ISBLANK(DPWW3!AE9),"",DPWW3!AE9) | ¬¬IF(ISBLANK(DPWW3!AF9),"",DPWW3!AF9) | ¬¬IF(ISBLANK(DPWW3!AG9),"",DPWW3!AG9)
¬¬A629 | ¬¬IF(ISBLANK(DPWW3!HU9),"",DPWW3!HU9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI9),"",DPWW3!AI9) | ¬¬IF(ISBLANK(DPWW3!AJ9),"",DPWW3!AJ9) | ¬¬IF(ISBLANK(DPWW3!AK9),"",DPWW3!AK9) | ¬¬IF(ISBLANK(DPWW3!AL9),"",DPWW3!AL9) | ¬¬IF(ISBLANK(DPWW3!AM9),"",DPWW3!AM9) | ¬¬IF(ISBLANK(DPWW3!AN9),"",DPWW3!AN9) | ¬¬IF(ISBLANK(DPWW3!AO9),"",DPWW3!AO9) | ¬¬IF(ISBLANK(DPWW3!AP9),"",DPWW3!AP9) | ¬¬IF(ISBLANK(DPWW3!AQ9),"",DPWW3!AQ9) | ¬¬IF(ISBLANK(DPWW3!AR9),"",DPWW3!AR9) | ¬¬IF(ISBLANK(DPWW3!AS9),"",DPWW3!AS9) | ¬¬IF(ISBLANK(DPWW3!AT9),"",DPWW3!AT9) | ¬¬IF(ISBLANK(DPWW3!AU9),"",DPWW3!AU9) | ¬¬IF(ISBLANK(DPWW3!AV9),"",DPWW3!AV9) | ¬¬IF(ISBLANK(DPWW3!AW9),"",DPWW3!AW9) | ¬¬IF(ISBLANK(DPWW3!AX9),"",DPWW3!AX9) | ¬¬IF(ISBLANK(DPWW3!AY9),"",DPWW3!AY9) | ¬¬IF(ISBLANK(DPWW3!AZ9),"",DPWW3!AZ9) | ¬¬IF(ISBLANK(DPWW3!BA9),"",DPWW3!BA9) | ¬¬IF(ISBLANK(DPWW3!BB9),"",DPWW3!BB9) | ¬¬IF(ISBLANK(DPWW3!BC9),"",DPWW3!BC9)
¬¬A630 | ¬¬IF(ISBLANK(DPWW3!IQ9),"",DPWW3!IQ9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE9),"",DPWW3!BE9) | ¬¬IF(ISBLANK(DPWW3!BF9),"",DPWW3!BF9) | ¬¬IF(ISBLANK(DPWW3!BG9),"",DPWW3!BG9) | ¬¬IF(ISBLANK(DPWW3!BH9),"",DPWW3!BH9) | ¬¬IF(ISBLANK(DPWW3!BI9),"",DPWW3!BI9) | ¬¬IF(ISBLANK(DPWW3!BJ9),"",DPWW3!BJ9) | ¬¬IF(ISBLANK(DPWW3!BK9),"",DPWW3!BK9) | ¬¬IF(ISBLANK(DPWW3!BL9),"",DPWW3!BL9) | ¬¬IF(ISBLANK(DPWW3!BM9),"",DPWW3!BM9) | ¬¬IF(ISBLANK(DPWW3!BN9),"",DPWW3!BN9) | ¬¬IF(ISBLANK(DPWW3!BO9),"",DPWW3!BO9) | ¬¬IF(ISBLANK(DPWW3!BP9),"",DPWW3!BP9) | ¬¬IF(ISBLANK(DPWW3!BQ9),"",DPWW3!BQ9) | ¬¬IF(ISBLANK(DPWW3!BR9),"",DPWW3!BR9) | ¬¬IF(ISBLANK(DPWW3!BS9),"",DPWW3!BS9) | ¬¬IF(ISBLANK(DPWW3!BT9),"",DPWW3!BT9) | ¬¬IF(ISBLANK(DPWW3!BU9),"",DPWW3!BU9) | ¬¬IF(ISBLANK(DPWW3!BV9),"",DPWW3!BV9) | ¬¬IF(ISBLANK(DPWW3!BW9),"",DPWW3!BW9) | ¬¬IF(ISBLANK(DPWW3!BX9),"",DPWW3!BX9) | ¬¬IF(ISBLANK(DPWW3!BY9),"",DPWW3!BY9)
¬¬A631 | ¬¬IF(ISBLANK(DPWW3!JM9),"",DPWW3!JM9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA9),"",DPWW3!CA9) | ¬¬IF(ISBLANK(DPWW3!CB9),"",DPWW3!CB9) | ¬¬IF(ISBLANK(DPWW3!CC9),"",DPWW3!CC9) | ¬¬IF(ISBLANK(DPWW3!CD9),"",DPWW3!CD9) | ¬¬IF(ISBLANK(DPWW3!CE9),"",DPWW3!CE9) | ¬¬IF(ISBLANK(DPWW3!CF9),"",DPWW3!CF9) | ¬¬IF(ISBLANK(DPWW3!CG9),"",DPWW3!CG9) | ¬¬IF(ISBLANK(DPWW3!CH9),"",DPWW3!CH9) | ¬¬IF(ISBLANK(DPWW3!CI9),"",DPWW3!CI9) | ¬¬IF(ISBLANK(DPWW3!CJ9),"",DPWW3!CJ9) | ¬¬IF(ISBLANK(DPWW3!CK9),"",DPWW3!CK9) | ¬¬IF(ISBLANK(DPWW3!CL9),"",DPWW3!CL9) | ¬¬IF(ISBLANK(DPWW3!CM9),"",DPWW3!CM9) | ¬¬IF(ISBLANK(DPWW3!CN9),"",DPWW3!CN9) | ¬¬IF(ISBLANK(DPWW3!CO9),"",DPWW3!CO9) | ¬¬IF(ISBLANK(DPWW3!CP9),"",DPWW3!CP9) | ¬¬IF(ISBLANK(DPWW3!CQ9),"",DPWW3!CQ9) | ¬¬IF(ISBLANK(DPWW3!CR9),"",DPWW3!CR9) | ¬¬IF(ISBLANK(DPWW3!CS9),"",DPWW3!CS9) | ¬¬IF(ISBLANK(DPWW3!CT9),"",DPWW3!CT9) | ¬¬IF(ISBLANK(DPWW3!CU9),"",DPWW3!CU9)
¬¬A632 | ¬¬IF(ISBLANK(DPWW3!KI9),"",DPWW3!KI9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW9),"",DPWW3!CW9) | ¬¬IF(ISBLANK(DPWW3!CX9),"",DPWW3!CX9) | ¬¬IF(ISBLANK(DPWW3!CY9),"",DPWW3!CY9) | ¬¬IF(ISBLANK(DPWW3!CZ9),"",DPWW3!CZ9) | ¬¬IF(ISBLANK(DPWW3!DA9),"",DPWW3!DA9) | ¬¬IF(ISBLANK(DPWW3!DB9),"",DPWW3!DB9) | ¬¬IF(ISBLANK(DPWW3!DC9),"",DPWW3!DC9) | ¬¬IF(ISBLANK(DPWW3!DD9),"",DPWW3!DD9) | ¬¬IF(ISBLANK(DPWW3!DE9),"",DPWW3!DE9) | ¬¬IF(ISBLANK(DPWW3!DF9),"",DPWW3!DF9) | ¬¬IF(ISBLANK(DPWW3!DG9),"",DPWW3!DG9) | ¬¬IF(ISBLANK(DPWW3!DH9),"",DPWW3!DH9) | ¬¬IF(ISBLANK(DPWW3!DI9),"",DPWW3!DI9) | ¬¬IF(ISBLANK(DPWW3!DJ9),"",DPWW3!DJ9) | ¬¬IF(ISBLANK(DPWW3!DK9),"",DPWW3!DK9) | ¬¬IF(ISBLANK(DPWW3!DL9),"",DPWW3!DL9) | ¬¬IF(ISBLANK(DPWW3!DM9),"",DPWW3!DM9) | ¬¬IF(ISBLANK(DPWW3!DN9),"",DPWW3!DN9) | ¬¬IF(ISBLANK(DPWW3!DO9),"",DPWW3!DO9) | ¬¬IF(ISBLANK(DPWW3!DP9),"",DPWW3!DP9) | ¬¬IF(ISBLANK(DPWW3!DQ9),"",DPWW3!DQ9)
¬¬A633 | ¬¬IF(ISBLANK(DPWW3!LE9),"",DPWW3!LE9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS9),"",DPWW3!DS9) | ¬¬IF(ISBLANK(DPWW3!DT9),"",DPWW3!DT9) | ¬¬IF(ISBLANK(DPWW3!DU9),"",DPWW3!DU9) | ¬¬IF(ISBLANK(DPWW3!DV9),"",DPWW3!DV9) | ¬¬IF(ISBLANK(DPWW3!DW9),"",DPWW3!DW9) | ¬¬IF(ISBLANK(DPWW3!DX9),"",DPWW3!DX9) | ¬¬IF(ISBLANK(DPWW3!DY9),"",DPWW3!DY9) | ¬¬IF(ISBLANK(DPWW3!DZ9),"",DPWW3!DZ9) | ¬¬IF(ISBLANK(DPWW3!EA9),"",DPWW3!EA9) | ¬¬IF(ISBLANK(DPWW3!EB9),"",DPWW3!EB9) | ¬¬IF(ISBLANK(DPWW3!EC9),"",DPWW3!EC9) | ¬¬IF(ISBLANK(DPWW3!ED9),"",DPWW3!ED9) | ¬¬IF(ISBLANK(DPWW3!EE9),"",DPWW3!EE9) | ¬¬IF(ISBLANK(DPWW3!EF9),"",DPWW3!EF9) | ¬¬IF(ISBLANK(DPWW3!EG9),"",DPWW3!EG9) | ¬¬IF(ISBLANK(DPWW3!EH9),"",DPWW3!EH9) | ¬¬IF(ISBLANK(DPWW3!EI9),"",DPWW3!EI9) | ¬¬IF(ISBLANK(DPWW3!EJ9),"",DPWW3!EJ9) | ¬¬IF(ISBLANK(DPWW3!EK9),"",DPWW3!EK9) | ¬¬IF(ISBLANK(DPWW3!EL9),"",DPWW3!EL9) | ¬¬IF(ISBLANK(DPWW3!EM9),"",DPWW3!EM9)
¬¬A634 | ¬¬IF(ISBLANK(DPWW3!MA9),"",DPWW3!MA9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO9),"",DPWW3!EO9) | ¬¬IF(ISBLANK(DPWW3!EP9),"",DPWW3!EP9) | ¬¬IF(ISBLANK(DPWW3!EQ9),"",DPWW3!EQ9) | ¬¬IF(ISBLANK(DPWW3!ER9),"",DPWW3!ER9) | ¬¬IF(ISBLANK(DPWW3!ES9),"",DPWW3!ES9) | ¬¬IF(ISBLANK(DPWW3!ET9),"",DPWW3!ET9) | ¬¬IF(ISBLANK(DPWW3!EU9),"",DPWW3!EU9) | ¬¬IF(ISBLANK(DPWW3!EV9),"",DPWW3!EV9) | ¬¬IF(ISBLANK(DPWW3!EW9),"",DPWW3!EW9) | ¬¬IF(ISBLANK(DPWW3!EX9),"",DPWW3!EX9) | ¬¬IF(ISBLANK(DPWW3!EY9),"",DPWW3!EY9) | ¬¬IF(ISBLANK(DPWW3!EZ9),"",DPWW3!EZ9) | ¬¬IF(ISBLANK(DPWW3!FA9),"",DPWW3!FA9) | ¬¬IF(ISBLANK(DPWW3!FB9),"",DPWW3!FB9) | ¬¬IF(ISBLANK(DPWW3!FC9),"",DPWW3!FC9) | ¬¬IF(ISBLANK(DPWW3!FD9),"",DPWW3!FD9) | ¬¬IF(ISBLANK(DPWW3!FE9),"",DPWW3!FE9) | ¬¬IF(ISBLANK(DPWW3!FF9),"",DPWW3!FF9) | ¬¬IF(ISBLANK(DPWW3!FG9),"",DPWW3!FG9) | ¬¬IF(ISBLANK(DPWW3!FH9),"",DPWW3!FH9) | ¬¬IF(ISBLANK(DPWW3!FI9),"",DPWW3!FI9)
¬¬A635 | ¬¬IF(ISBLANK(DPWW3!MW9),"",DPWW3!MW9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK9),"",DPWW3!FK9) | ¬¬IF(ISBLANK(DPWW3!FL9),"",DPWW3!FL9) | ¬¬IF(ISBLANK(DPWW3!FM9),"",DPWW3!FM9) | ¬¬IF(ISBLANK(DPWW3!FN9),"",DPWW3!FN9) | ¬¬IF(ISBLANK(DPWW3!FO9),"",DPWW3!FO9) | ¬¬IF(ISBLANK(DPWW3!FP9),"",DPWW3!FP9) | ¬¬IF(ISBLANK(DPWW3!FQ9),"",DPWW3!FQ9) | ¬¬IF(ISBLANK(DPWW3!FR9),"",DPWW3!FR9) | ¬¬IF(ISBLANK(DPWW3!FS9),"",DPWW3!FS9) | ¬¬IF(ISBLANK(DPWW3!FT9),"",DPWW3!FT9) | ¬¬IF(ISBLANK(DPWW3!FU9),"",DPWW3!FU9) | ¬¬IF(ISBLANK(DPWW3!FV9),"",DPWW3!FV9) | ¬¬IF(ISBLANK(DPWW3!FW9),"",DPWW3!FW9) | ¬¬IF(ISBLANK(DPWW3!FX9),"",DPWW3!FX9) | ¬¬IF(ISBLANK(DPWW3!FY9),"",DPWW3!FY9) | ¬¬IF(ISBLANK(DPWW3!FZ9),"",DPWW3!FZ9) | ¬¬IF(ISBLANK(DPWW3!GA9),"",DPWW3!GA9) | ¬¬IF(ISBLANK(DPWW3!GB9),"",DPWW3!GB9) | ¬¬IF(ISBLANK(DPWW3!GC9),"",DPWW3!GC9) | ¬¬IF(ISBLANK(DPWW3!GD9),"",DPWW3!GD9) | ¬¬IF(ISBLANK(DPWW3!GE9),"",DPWW3!GE9)
¬¬A636 | ¬¬IF(ISBLANK(DPWW3!NS9),"",DPWW3!NS9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GG9),"",DPWW3!GG9)
¬¬A637 | ¬¬IF(ISBLANK(DPWW3!NT9),"",DPWW3!NT9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GH9),"",DPWW3!GH9)
¬¬A638 | ¬¬IF(ISBLANK(DPWW3!NU9),"",DPWW3!NU9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GI9),"",DPWW3!GI9)
¬¬A639 | ¬¬IF(ISBLANK(DPWW3!NV9),"",DPWW3!NV9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ9),"",DPWW3!GJ9)
¬¬A640 | ¬¬IF(ISBLANK(DPWW3!NW9),"",DPWW3!NW9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GK9),"",DPWW3!GK9)
¬¬A641 | ¬¬IF(ISBLANK(DPWW3!NX9),"",DPWW3!NX9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GL9),"",DPWW3!GL9)
¬¬A642 | ¬¬IF(ISBLANK(DPWW3!NY9),"",DPWW3!NY9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GM9),"",DPWW3!GM9)
¬¬A643 | ¬¬IF(ISBLANK(DPWW3!NZ9),"",DPWW3!NZ9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GN9),"",DPWW3!GN9)
¬¬A644 | ¬¬IF(ISBLANK(DPWW3!OA9),"",DPWW3!OA9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GO9),"",DPWW3!GO9)
¬¬A645 | ¬¬IF(ISBLANK(DPWW3!OB9),"",DPWW3!OB9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GP9),"",DPWW3!GP9)
¬¬A646 | ¬¬IF(ISBLANK(DPWW3!OC9),"",DPWW3!OC9) | ¬¬DPWW3!F9 & "," & DPWW3!G9 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H9),"",DPWW3!H9) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ9),"",DPWW3!GQ9)
¬¬A647 | ¬¬IF(ISBLANK(DPWW3!GW10),"",DPWW3!GW10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!K10),"",DPWW3!K10)
¬¬A648 | ¬¬IF(ISBLANK(DPWW3!GY10),"",DPWW3!GY10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M10),"",DPWW3!M10) | ¬¬IF(ISBLANK(DPWW3!N10),"",DPWW3!N10) | ¬¬IF(ISBLANK(DPWW3!O10),"",DPWW3!O10) | ¬¬IF(ISBLANK(DPWW3!P10),"",DPWW3!P10) | ¬¬IF(ISBLANK(DPWW3!Q10),"",DPWW3!Q10) | ¬¬IF(ISBLANK(DPWW3!R10),"",DPWW3!R10) | ¬¬IF(ISBLANK(DPWW3!S10),"",DPWW3!S10) | ¬¬IF(ISBLANK(DPWW3!T10),"",DPWW3!T10) | ¬¬IF(ISBLANK(DPWW3!U10),"",DPWW3!U10) | ¬¬IF(ISBLANK(DPWW3!V10),"",DPWW3!V10) | ¬¬IF(ISBLANK(DPWW3!W10),"",DPWW3!W10) | ¬¬IF(ISBLANK(DPWW3!X10),"",DPWW3!X10) | ¬¬IF(ISBLANK(DPWW3!Y10),"",DPWW3!Y10) | ¬¬IF(ISBLANK(DPWW3!Z10),"",DPWW3!Z10) | ¬¬IF(ISBLANK(DPWW3!AA10),"",DPWW3!AA10) | ¬¬IF(ISBLANK(DPWW3!AB10),"",DPWW3!AB10) | ¬¬IF(ISBLANK(DPWW3!AC10),"",DPWW3!AC10) | ¬¬IF(ISBLANK(DPWW3!AD10),"",DPWW3!AD10) | ¬¬IF(ISBLANK(DPWW3!AE10),"",DPWW3!AE10) | ¬¬IF(ISBLANK(DPWW3!AF10),"",DPWW3!AF10) | ¬¬IF(ISBLANK(DPWW3!AG10),"",DPWW3!AG10)
¬¬A649 | ¬¬IF(ISBLANK(DPWW3!HU10),"",DPWW3!HU10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI10),"",DPWW3!AI10) | ¬¬IF(ISBLANK(DPWW3!AJ10),"",DPWW3!AJ10) | ¬¬IF(ISBLANK(DPWW3!AK10),"",DPWW3!AK10) | ¬¬IF(ISBLANK(DPWW3!AL10),"",DPWW3!AL10) | ¬¬IF(ISBLANK(DPWW3!AM10),"",DPWW3!AM10) | ¬¬IF(ISBLANK(DPWW3!AN10),"",DPWW3!AN10) | ¬¬IF(ISBLANK(DPWW3!AO10),"",DPWW3!AO10) | ¬¬IF(ISBLANK(DPWW3!AP10),"",DPWW3!AP10) | ¬¬IF(ISBLANK(DPWW3!AQ10),"",DPWW3!AQ10) | ¬¬IF(ISBLANK(DPWW3!AR10),"",DPWW3!AR10) | ¬¬IF(ISBLANK(DPWW3!AS10),"",DPWW3!AS10) | ¬¬IF(ISBLANK(DPWW3!AT10),"",DPWW3!AT10) | ¬¬IF(ISBLANK(DPWW3!AU10),"",DPWW3!AU10) | ¬¬IF(ISBLANK(DPWW3!AV10),"",DPWW3!AV10) | ¬¬IF(ISBLANK(DPWW3!AW10),"",DPWW3!AW10) | ¬¬IF(ISBLANK(DPWW3!AX10),"",DPWW3!AX10) | ¬¬IF(ISBLANK(DPWW3!AY10),"",DPWW3!AY10) | ¬¬IF(ISBLANK(DPWW3!AZ10),"",DPWW3!AZ10) | ¬¬IF(ISBLANK(DPWW3!BA10),"",DPWW3!BA10) | ¬¬IF(ISBLANK(DPWW3!BB10),"",DPWW3!BB10) | ¬¬IF(ISBLANK(DPWW3!BC10),"",DPWW3!BC10)
¬¬A650 | ¬¬IF(ISBLANK(DPWW3!IQ10),"",DPWW3!IQ10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE10),"",DPWW3!BE10) | ¬¬IF(ISBLANK(DPWW3!BF10),"",DPWW3!BF10) | ¬¬IF(ISBLANK(DPWW3!BG10),"",DPWW3!BG10) | ¬¬IF(ISBLANK(DPWW3!BH10),"",DPWW3!BH10) | ¬¬IF(ISBLANK(DPWW3!BI10),"",DPWW3!BI10) | ¬¬IF(ISBLANK(DPWW3!BJ10),"",DPWW3!BJ10) | ¬¬IF(ISBLANK(DPWW3!BK10),"",DPWW3!BK10) | ¬¬IF(ISBLANK(DPWW3!BL10),"",DPWW3!BL10) | ¬¬IF(ISBLANK(DPWW3!BM10),"",DPWW3!BM10) | ¬¬IF(ISBLANK(DPWW3!BN10),"",DPWW3!BN10) | ¬¬IF(ISBLANK(DPWW3!BO10),"",DPWW3!BO10) | ¬¬IF(ISBLANK(DPWW3!BP10),"",DPWW3!BP10) | ¬¬IF(ISBLANK(DPWW3!BQ10),"",DPWW3!BQ10) | ¬¬IF(ISBLANK(DPWW3!BR10),"",DPWW3!BR10) | ¬¬IF(ISBLANK(DPWW3!BS10),"",DPWW3!BS10) | ¬¬IF(ISBLANK(DPWW3!BT10),"",DPWW3!BT10) | ¬¬IF(ISBLANK(DPWW3!BU10),"",DPWW3!BU10) | ¬¬IF(ISBLANK(DPWW3!BV10),"",DPWW3!BV10) | ¬¬IF(ISBLANK(DPWW3!BW10),"",DPWW3!BW10) | ¬¬IF(ISBLANK(DPWW3!BX10),"",DPWW3!BX10) | ¬¬IF(ISBLANK(DPWW3!BY10),"",DPWW3!BY10)
¬¬A651 | ¬¬IF(ISBLANK(DPWW3!JM10),"",DPWW3!JM10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA10),"",DPWW3!CA10) | ¬¬IF(ISBLANK(DPWW3!CB10),"",DPWW3!CB10) | ¬¬IF(ISBLANK(DPWW3!CC10),"",DPWW3!CC10) | ¬¬IF(ISBLANK(DPWW3!CD10),"",DPWW3!CD10) | ¬¬IF(ISBLANK(DPWW3!CE10),"",DPWW3!CE10) | ¬¬IF(ISBLANK(DPWW3!CF10),"",DPWW3!CF10) | ¬¬IF(ISBLANK(DPWW3!CG10),"",DPWW3!CG10) | ¬¬IF(ISBLANK(DPWW3!CH10),"",DPWW3!CH10) | ¬¬IF(ISBLANK(DPWW3!CI10),"",DPWW3!CI10) | ¬¬IF(ISBLANK(DPWW3!CJ10),"",DPWW3!CJ10) | ¬¬IF(ISBLANK(DPWW3!CK10),"",DPWW3!CK10) | ¬¬IF(ISBLANK(DPWW3!CL10),"",DPWW3!CL10) | ¬¬IF(ISBLANK(DPWW3!CM10),"",DPWW3!CM10) | ¬¬IF(ISBLANK(DPWW3!CN10),"",DPWW3!CN10) | ¬¬IF(ISBLANK(DPWW3!CO10),"",DPWW3!CO10) | ¬¬IF(ISBLANK(DPWW3!CP10),"",DPWW3!CP10) | ¬¬IF(ISBLANK(DPWW3!CQ10),"",DPWW3!CQ10) | ¬¬IF(ISBLANK(DPWW3!CR10),"",DPWW3!CR10) | ¬¬IF(ISBLANK(DPWW3!CS10),"",DPWW3!CS10) | ¬¬IF(ISBLANK(DPWW3!CT10),"",DPWW3!CT10) | ¬¬IF(ISBLANK(DPWW3!CU10),"",DPWW3!CU10)
¬¬A652 | ¬¬IF(ISBLANK(DPWW3!KI10),"",DPWW3!KI10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW10),"",DPWW3!CW10) | ¬¬IF(ISBLANK(DPWW3!CX10),"",DPWW3!CX10) | ¬¬IF(ISBLANK(DPWW3!CY10),"",DPWW3!CY10) | ¬¬IF(ISBLANK(DPWW3!CZ10),"",DPWW3!CZ10) | ¬¬IF(ISBLANK(DPWW3!DA10),"",DPWW3!DA10) | ¬¬IF(ISBLANK(DPWW3!DB10),"",DPWW3!DB10) | ¬¬IF(ISBLANK(DPWW3!DC10),"",DPWW3!DC10) | ¬¬IF(ISBLANK(DPWW3!DD10),"",DPWW3!DD10) | ¬¬IF(ISBLANK(DPWW3!DE10),"",DPWW3!DE10) | ¬¬IF(ISBLANK(DPWW3!DF10),"",DPWW3!DF10) | ¬¬IF(ISBLANK(DPWW3!DG10),"",DPWW3!DG10) | ¬¬IF(ISBLANK(DPWW3!DH10),"",DPWW3!DH10) | ¬¬IF(ISBLANK(DPWW3!DI10),"",DPWW3!DI10) | ¬¬IF(ISBLANK(DPWW3!DJ10),"",DPWW3!DJ10) | ¬¬IF(ISBLANK(DPWW3!DK10),"",DPWW3!DK10) | ¬¬IF(ISBLANK(DPWW3!DL10),"",DPWW3!DL10) | ¬¬IF(ISBLANK(DPWW3!DM10),"",DPWW3!DM10) | ¬¬IF(ISBLANK(DPWW3!DN10),"",DPWW3!DN10) | ¬¬IF(ISBLANK(DPWW3!DO10),"",DPWW3!DO10) | ¬¬IF(ISBLANK(DPWW3!DP10),"",DPWW3!DP10) | ¬¬IF(ISBLANK(DPWW3!DQ10),"",DPWW3!DQ10)
¬¬A653 | ¬¬IF(ISBLANK(DPWW3!LE10),"",DPWW3!LE10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS10),"",DPWW3!DS10) | ¬¬IF(ISBLANK(DPWW3!DT10),"",DPWW3!DT10) | ¬¬IF(ISBLANK(DPWW3!DU10),"",DPWW3!DU10) | ¬¬IF(ISBLANK(DPWW3!DV10),"",DPWW3!DV10) | ¬¬IF(ISBLANK(DPWW3!DW10),"",DPWW3!DW10) | ¬¬IF(ISBLANK(DPWW3!DX10),"",DPWW3!DX10) | ¬¬IF(ISBLANK(DPWW3!DY10),"",DPWW3!DY10) | ¬¬IF(ISBLANK(DPWW3!DZ10),"",DPWW3!DZ10) | ¬¬IF(ISBLANK(DPWW3!EA10),"",DPWW3!EA10) | ¬¬IF(ISBLANK(DPWW3!EB10),"",DPWW3!EB10) | ¬¬IF(ISBLANK(DPWW3!EC10),"",DPWW3!EC10) | ¬¬IF(ISBLANK(DPWW3!ED10),"",DPWW3!ED10) | ¬¬IF(ISBLANK(DPWW3!EE10),"",DPWW3!EE10) | ¬¬IF(ISBLANK(DPWW3!EF10),"",DPWW3!EF10) | ¬¬IF(ISBLANK(DPWW3!EG10),"",DPWW3!EG10) | ¬¬IF(ISBLANK(DPWW3!EH10),"",DPWW3!EH10) | ¬¬IF(ISBLANK(DPWW3!EI10),"",DPWW3!EI10) | ¬¬IF(ISBLANK(DPWW3!EJ10),"",DPWW3!EJ10) | ¬¬IF(ISBLANK(DPWW3!EK10),"",DPWW3!EK10) | ¬¬IF(ISBLANK(DPWW3!EL10),"",DPWW3!EL10) | ¬¬IF(ISBLANK(DPWW3!EM10),"",DPWW3!EM10)
¬¬A654 | ¬¬IF(ISBLANK(DPWW3!MA10),"",DPWW3!MA10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO10),"",DPWW3!EO10) | ¬¬IF(ISBLANK(DPWW3!EP10),"",DPWW3!EP10) | ¬¬IF(ISBLANK(DPWW3!EQ10),"",DPWW3!EQ10) | ¬¬IF(ISBLANK(DPWW3!ER10),"",DPWW3!ER10) | ¬¬IF(ISBLANK(DPWW3!ES10),"",DPWW3!ES10) | ¬¬IF(ISBLANK(DPWW3!ET10),"",DPWW3!ET10) | ¬¬IF(ISBLANK(DPWW3!EU10),"",DPWW3!EU10) | ¬¬IF(ISBLANK(DPWW3!EV10),"",DPWW3!EV10) | ¬¬IF(ISBLANK(DPWW3!EW10),"",DPWW3!EW10) | ¬¬IF(ISBLANK(DPWW3!EX10),"",DPWW3!EX10) | ¬¬IF(ISBLANK(DPWW3!EY10),"",DPWW3!EY10) | ¬¬IF(ISBLANK(DPWW3!EZ10),"",DPWW3!EZ10) | ¬¬IF(ISBLANK(DPWW3!FA10),"",DPWW3!FA10) | ¬¬IF(ISBLANK(DPWW3!FB10),"",DPWW3!FB10) | ¬¬IF(ISBLANK(DPWW3!FC10),"",DPWW3!FC10) | ¬¬IF(ISBLANK(DPWW3!FD10),"",DPWW3!FD10) | ¬¬IF(ISBLANK(DPWW3!FE10),"",DPWW3!FE10) | ¬¬IF(ISBLANK(DPWW3!FF10),"",DPWW3!FF10) | ¬¬IF(ISBLANK(DPWW3!FG10),"",DPWW3!FG10) | ¬¬IF(ISBLANK(DPWW3!FH10),"",DPWW3!FH10) | ¬¬IF(ISBLANK(DPWW3!FI10),"",DPWW3!FI10)
¬¬A655 | ¬¬IF(ISBLANK(DPWW3!MW10),"",DPWW3!MW10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK10),"",DPWW3!FK10) | ¬¬IF(ISBLANK(DPWW3!FL10),"",DPWW3!FL10) | ¬¬IF(ISBLANK(DPWW3!FM10),"",DPWW3!FM10) | ¬¬IF(ISBLANK(DPWW3!FN10),"",DPWW3!FN10) | ¬¬IF(ISBLANK(DPWW3!FO10),"",DPWW3!FO10) | ¬¬IF(ISBLANK(DPWW3!FP10),"",DPWW3!FP10) | ¬¬IF(ISBLANK(DPWW3!FQ10),"",DPWW3!FQ10) | ¬¬IF(ISBLANK(DPWW3!FR10),"",DPWW3!FR10) | ¬¬IF(ISBLANK(DPWW3!FS10),"",DPWW3!FS10) | ¬¬IF(ISBLANK(DPWW3!FT10),"",DPWW3!FT10) | ¬¬IF(ISBLANK(DPWW3!FU10),"",DPWW3!FU10) | ¬¬IF(ISBLANK(DPWW3!FV10),"",DPWW3!FV10) | ¬¬IF(ISBLANK(DPWW3!FW10),"",DPWW3!FW10) | ¬¬IF(ISBLANK(DPWW3!FX10),"",DPWW3!FX10) | ¬¬IF(ISBLANK(DPWW3!FY10),"",DPWW3!FY10) | ¬¬IF(ISBLANK(DPWW3!FZ10),"",DPWW3!FZ10) | ¬¬IF(ISBLANK(DPWW3!GA10),"",DPWW3!GA10) | ¬¬IF(ISBLANK(DPWW3!GB10),"",DPWW3!GB10) | ¬¬IF(ISBLANK(DPWW3!GC10),"",DPWW3!GC10) | ¬¬IF(ISBLANK(DPWW3!GD10),"",DPWW3!GD10) | ¬¬IF(ISBLANK(DPWW3!GE10),"",DPWW3!GE10)
¬¬A656 | ¬¬IF(ISBLANK(DPWW3!NS10),"",DPWW3!NS10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GG10),"",DPWW3!GG10)
¬¬A657 | ¬¬IF(ISBLANK(DPWW3!NT10),"",DPWW3!NT10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GH10),"",DPWW3!GH10)
¬¬A658 | ¬¬IF(ISBLANK(DPWW3!NU10),"",DPWW3!NU10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GI10),"",DPWW3!GI10)
¬¬A659 | ¬¬IF(ISBLANK(DPWW3!NV10),"",DPWW3!NV10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ10),"",DPWW3!GJ10)
¬¬A660 | ¬¬IF(ISBLANK(DPWW3!NW10),"",DPWW3!NW10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GK10),"",DPWW3!GK10)
¬¬A661 | ¬¬IF(ISBLANK(DPWW3!NX10),"",DPWW3!NX10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GL10),"",DPWW3!GL10)
¬¬A662 | ¬¬IF(ISBLANK(DPWW3!NY10),"",DPWW3!NY10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GM10),"",DPWW3!GM10)
¬¬A663 | ¬¬IF(ISBLANK(DPWW3!NZ10),"",DPWW3!NZ10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GN10),"",DPWW3!GN10)
¬¬A664 | ¬¬IF(ISBLANK(DPWW3!OA10),"",DPWW3!OA10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GO10),"",DPWW3!GO10)
¬¬A665 | ¬¬IF(ISBLANK(DPWW3!OB10),"",DPWW3!OB10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GP10),"",DPWW3!GP10)
¬¬A666 | ¬¬IF(ISBLANK(DPWW3!OC10),"",DPWW3!OC10) | ¬¬DPWW3!F10 & "," & DPWW3!G10 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H10),"",DPWW3!H10) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ10),"",DPWW3!GQ10)
¬¬A667 | ¬¬IF(ISBLANK(DPWW3!GW11),"",DPWW3!GW11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!K11),"",DPWW3!K11)
¬¬A668 | ¬¬IF(ISBLANK(DPWW3!GY11),"",DPWW3!GY11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M11),"",DPWW3!M11) | ¬¬IF(ISBLANK(DPWW3!N11),"",DPWW3!N11) | ¬¬IF(ISBLANK(DPWW3!O11),"",DPWW3!O11) | ¬¬IF(ISBLANK(DPWW3!P11),"",DPWW3!P11) | ¬¬IF(ISBLANK(DPWW3!Q11),"",DPWW3!Q11) | ¬¬IF(ISBLANK(DPWW3!R11),"",DPWW3!R11) | ¬¬IF(ISBLANK(DPWW3!S11),"",DPWW3!S11) | ¬¬IF(ISBLANK(DPWW3!T11),"",DPWW3!T11) | ¬¬IF(ISBLANK(DPWW3!U11),"",DPWW3!U11) | ¬¬IF(ISBLANK(DPWW3!V11),"",DPWW3!V11) | ¬¬IF(ISBLANK(DPWW3!W11),"",DPWW3!W11) | ¬¬IF(ISBLANK(DPWW3!X11),"",DPWW3!X11) | ¬¬IF(ISBLANK(DPWW3!Y11),"",DPWW3!Y11) | ¬¬IF(ISBLANK(DPWW3!Z11),"",DPWW3!Z11) | ¬¬IF(ISBLANK(DPWW3!AA11),"",DPWW3!AA11) | ¬¬IF(ISBLANK(DPWW3!AB11),"",DPWW3!AB11) | ¬¬IF(ISBLANK(DPWW3!AC11),"",DPWW3!AC11) | ¬¬IF(ISBLANK(DPWW3!AD11),"",DPWW3!AD11) | ¬¬IF(ISBLANK(DPWW3!AE11),"",DPWW3!AE11) | ¬¬IF(ISBLANK(DPWW3!AF11),"",DPWW3!AF11) | ¬¬IF(ISBLANK(DPWW3!AG11),"",DPWW3!AG11)
¬¬A669 | ¬¬IF(ISBLANK(DPWW3!HU11),"",DPWW3!HU11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI11),"",DPWW3!AI11) | ¬¬IF(ISBLANK(DPWW3!AJ11),"",DPWW3!AJ11) | ¬¬IF(ISBLANK(DPWW3!AK11),"",DPWW3!AK11) | ¬¬IF(ISBLANK(DPWW3!AL11),"",DPWW3!AL11) | ¬¬IF(ISBLANK(DPWW3!AM11),"",DPWW3!AM11) | ¬¬IF(ISBLANK(DPWW3!AN11),"",DPWW3!AN11) | ¬¬IF(ISBLANK(DPWW3!AO11),"",DPWW3!AO11) | ¬¬IF(ISBLANK(DPWW3!AP11),"",DPWW3!AP11) | ¬¬IF(ISBLANK(DPWW3!AQ11),"",DPWW3!AQ11) | ¬¬IF(ISBLANK(DPWW3!AR11),"",DPWW3!AR11) | ¬¬IF(ISBLANK(DPWW3!AS11),"",DPWW3!AS11) | ¬¬IF(ISBLANK(DPWW3!AT11),"",DPWW3!AT11) | ¬¬IF(ISBLANK(DPWW3!AU11),"",DPWW3!AU11) | ¬¬IF(ISBLANK(DPWW3!AV11),"",DPWW3!AV11) | ¬¬IF(ISBLANK(DPWW3!AW11),"",DPWW3!AW11) | ¬¬IF(ISBLANK(DPWW3!AX11),"",DPWW3!AX11) | ¬¬IF(ISBLANK(DPWW3!AY11),"",DPWW3!AY11) | ¬¬IF(ISBLANK(DPWW3!AZ11),"",DPWW3!AZ11) | ¬¬IF(ISBLANK(DPWW3!BA11),"",DPWW3!BA11) | ¬¬IF(ISBLANK(DPWW3!BB11),"",DPWW3!BB11) | ¬¬IF(ISBLANK(DPWW3!BC11),"",DPWW3!BC11)
¬¬A670 | ¬¬IF(ISBLANK(DPWW3!IQ11),"",DPWW3!IQ11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE11),"",DPWW3!BE11) | ¬¬IF(ISBLANK(DPWW3!BF11),"",DPWW3!BF11) | ¬¬IF(ISBLANK(DPWW3!BG11),"",DPWW3!BG11) | ¬¬IF(ISBLANK(DPWW3!BH11),"",DPWW3!BH11) | ¬¬IF(ISBLANK(DPWW3!BI11),"",DPWW3!BI11) | ¬¬IF(ISBLANK(DPWW3!BJ11),"",DPWW3!BJ11) | ¬¬IF(ISBLANK(DPWW3!BK11),"",DPWW3!BK11) | ¬¬IF(ISBLANK(DPWW3!BL11),"",DPWW3!BL11) | ¬¬IF(ISBLANK(DPWW3!BM11),"",DPWW3!BM11) | ¬¬IF(ISBLANK(DPWW3!BN11),"",DPWW3!BN11) | ¬¬IF(ISBLANK(DPWW3!BO11),"",DPWW3!BO11) | ¬¬IF(ISBLANK(DPWW3!BP11),"",DPWW3!BP11) | ¬¬IF(ISBLANK(DPWW3!BQ11),"",DPWW3!BQ11) | ¬¬IF(ISBLANK(DPWW3!BR11),"",DPWW3!BR11) | ¬¬IF(ISBLANK(DPWW3!BS11),"",DPWW3!BS11) | ¬¬IF(ISBLANK(DPWW3!BT11),"",DPWW3!BT11) | ¬¬IF(ISBLANK(DPWW3!BU11),"",DPWW3!BU11) | ¬¬IF(ISBLANK(DPWW3!BV11),"",DPWW3!BV11) | ¬¬IF(ISBLANK(DPWW3!BW11),"",DPWW3!BW11) | ¬¬IF(ISBLANK(DPWW3!BX11),"",DPWW3!BX11) | ¬¬IF(ISBLANK(DPWW3!BY11),"",DPWW3!BY11)
¬¬A671 | ¬¬IF(ISBLANK(DPWW3!JM11),"",DPWW3!JM11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA11),"",DPWW3!CA11) | ¬¬IF(ISBLANK(DPWW3!CB11),"",DPWW3!CB11) | ¬¬IF(ISBLANK(DPWW3!CC11),"",DPWW3!CC11) | ¬¬IF(ISBLANK(DPWW3!CD11),"",DPWW3!CD11) | ¬¬IF(ISBLANK(DPWW3!CE11),"",DPWW3!CE11) | ¬¬IF(ISBLANK(DPWW3!CF11),"",DPWW3!CF11) | ¬¬IF(ISBLANK(DPWW3!CG11),"",DPWW3!CG11) | ¬¬IF(ISBLANK(DPWW3!CH11),"",DPWW3!CH11) | ¬¬IF(ISBLANK(DPWW3!CI11),"",DPWW3!CI11) | ¬¬IF(ISBLANK(DPWW3!CJ11),"",DPWW3!CJ11) | ¬¬IF(ISBLANK(DPWW3!CK11),"",DPWW3!CK11) | ¬¬IF(ISBLANK(DPWW3!CL11),"",DPWW3!CL11) | ¬¬IF(ISBLANK(DPWW3!CM11),"",DPWW3!CM11) | ¬¬IF(ISBLANK(DPWW3!CN11),"",DPWW3!CN11) | ¬¬IF(ISBLANK(DPWW3!CO11),"",DPWW3!CO11) | ¬¬IF(ISBLANK(DPWW3!CP11),"",DPWW3!CP11) | ¬¬IF(ISBLANK(DPWW3!CQ11),"",DPWW3!CQ11) | ¬¬IF(ISBLANK(DPWW3!CR11),"",DPWW3!CR11) | ¬¬IF(ISBLANK(DPWW3!CS11),"",DPWW3!CS11) | ¬¬IF(ISBLANK(DPWW3!CT11),"",DPWW3!CT11) | ¬¬IF(ISBLANK(DPWW3!CU11),"",DPWW3!CU11)
¬¬A672 | ¬¬IF(ISBLANK(DPWW3!KI11),"",DPWW3!KI11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW11),"",DPWW3!CW11) | ¬¬IF(ISBLANK(DPWW3!CX11),"",DPWW3!CX11) | ¬¬IF(ISBLANK(DPWW3!CY11),"",DPWW3!CY11) | ¬¬IF(ISBLANK(DPWW3!CZ11),"",DPWW3!CZ11) | ¬¬IF(ISBLANK(DPWW3!DA11),"",DPWW3!DA11) | ¬¬IF(ISBLANK(DPWW3!DB11),"",DPWW3!DB11) | ¬¬IF(ISBLANK(DPWW3!DC11),"",DPWW3!DC11) | ¬¬IF(ISBLANK(DPWW3!DD11),"",DPWW3!DD11) | ¬¬IF(ISBLANK(DPWW3!DE11),"",DPWW3!DE11) | ¬¬IF(ISBLANK(DPWW3!DF11),"",DPWW3!DF11) | ¬¬IF(ISBLANK(DPWW3!DG11),"",DPWW3!DG11) | ¬¬IF(ISBLANK(DPWW3!DH11),"",DPWW3!DH11) | ¬¬IF(ISBLANK(DPWW3!DI11),"",DPWW3!DI11) | ¬¬IF(ISBLANK(DPWW3!DJ11),"",DPWW3!DJ11) | ¬¬IF(ISBLANK(DPWW3!DK11),"",DPWW3!DK11) | ¬¬IF(ISBLANK(DPWW3!DL11),"",DPWW3!DL11) | ¬¬IF(ISBLANK(DPWW3!DM11),"",DPWW3!DM11) | ¬¬IF(ISBLANK(DPWW3!DN11),"",DPWW3!DN11) | ¬¬IF(ISBLANK(DPWW3!DO11),"",DPWW3!DO11) | ¬¬IF(ISBLANK(DPWW3!DP11),"",DPWW3!DP11) | ¬¬IF(ISBLANK(DPWW3!DQ11),"",DPWW3!DQ11)
¬¬A673 | ¬¬IF(ISBLANK(DPWW3!LE11),"",DPWW3!LE11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS11),"",DPWW3!DS11) | ¬¬IF(ISBLANK(DPWW3!DT11),"",DPWW3!DT11) | ¬¬IF(ISBLANK(DPWW3!DU11),"",DPWW3!DU11) | ¬¬IF(ISBLANK(DPWW3!DV11),"",DPWW3!DV11) | ¬¬IF(ISBLANK(DPWW3!DW11),"",DPWW3!DW11) | ¬¬IF(ISBLANK(DPWW3!DX11),"",DPWW3!DX11) | ¬¬IF(ISBLANK(DPWW3!DY11),"",DPWW3!DY11) | ¬¬IF(ISBLANK(DPWW3!DZ11),"",DPWW3!DZ11) | ¬¬IF(ISBLANK(DPWW3!EA11),"",DPWW3!EA11) | ¬¬IF(ISBLANK(DPWW3!EB11),"",DPWW3!EB11) | ¬¬IF(ISBLANK(DPWW3!EC11),"",DPWW3!EC11) | ¬¬IF(ISBLANK(DPWW3!ED11),"",DPWW3!ED11) | ¬¬IF(ISBLANK(DPWW3!EE11),"",DPWW3!EE11) | ¬¬IF(ISBLANK(DPWW3!EF11),"",DPWW3!EF11) | ¬¬IF(ISBLANK(DPWW3!EG11),"",DPWW3!EG11) | ¬¬IF(ISBLANK(DPWW3!EH11),"",DPWW3!EH11) | ¬¬IF(ISBLANK(DPWW3!EI11),"",DPWW3!EI11) | ¬¬IF(ISBLANK(DPWW3!EJ11),"",DPWW3!EJ11) | ¬¬IF(ISBLANK(DPWW3!EK11),"",DPWW3!EK11) | ¬¬IF(ISBLANK(DPWW3!EL11),"",DPWW3!EL11) | ¬¬IF(ISBLANK(DPWW3!EM11),"",DPWW3!EM11)
¬¬A674 | ¬¬IF(ISBLANK(DPWW3!MA11),"",DPWW3!MA11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO11),"",DPWW3!EO11) | ¬¬IF(ISBLANK(DPWW3!EP11),"",DPWW3!EP11) | ¬¬IF(ISBLANK(DPWW3!EQ11),"",DPWW3!EQ11) | ¬¬IF(ISBLANK(DPWW3!ER11),"",DPWW3!ER11) | ¬¬IF(ISBLANK(DPWW3!ES11),"",DPWW3!ES11) | ¬¬IF(ISBLANK(DPWW3!ET11),"",DPWW3!ET11) | ¬¬IF(ISBLANK(DPWW3!EU11),"",DPWW3!EU11) | ¬¬IF(ISBLANK(DPWW3!EV11),"",DPWW3!EV11) | ¬¬IF(ISBLANK(DPWW3!EW11),"",DPWW3!EW11) | ¬¬IF(ISBLANK(DPWW3!EX11),"",DPWW3!EX11) | ¬¬IF(ISBLANK(DPWW3!EY11),"",DPWW3!EY11) | ¬¬IF(ISBLANK(DPWW3!EZ11),"",DPWW3!EZ11) | ¬¬IF(ISBLANK(DPWW3!FA11),"",DPWW3!FA11) | ¬¬IF(ISBLANK(DPWW3!FB11),"",DPWW3!FB11) | ¬¬IF(ISBLANK(DPWW3!FC11),"",DPWW3!FC11) | ¬¬IF(ISBLANK(DPWW3!FD11),"",DPWW3!FD11) | ¬¬IF(ISBLANK(DPWW3!FE11),"",DPWW3!FE11) | ¬¬IF(ISBLANK(DPWW3!FF11),"",DPWW3!FF11) | ¬¬IF(ISBLANK(DPWW3!FG11),"",DPWW3!FG11) | ¬¬IF(ISBLANK(DPWW3!FH11),"",DPWW3!FH11) | ¬¬IF(ISBLANK(DPWW3!FI11),"",DPWW3!FI11)
¬¬A675 | ¬¬IF(ISBLANK(DPWW3!MW11),"",DPWW3!MW11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK11),"",DPWW3!FK11) | ¬¬IF(ISBLANK(DPWW3!FL11),"",DPWW3!FL11) | ¬¬IF(ISBLANK(DPWW3!FM11),"",DPWW3!FM11) | ¬¬IF(ISBLANK(DPWW3!FN11),"",DPWW3!FN11) | ¬¬IF(ISBLANK(DPWW3!FO11),"",DPWW3!FO11) | ¬¬IF(ISBLANK(DPWW3!FP11),"",DPWW3!FP11) | ¬¬IF(ISBLANK(DPWW3!FQ11),"",DPWW3!FQ11) | ¬¬IF(ISBLANK(DPWW3!FR11),"",DPWW3!FR11) | ¬¬IF(ISBLANK(DPWW3!FS11),"",DPWW3!FS11) | ¬¬IF(ISBLANK(DPWW3!FT11),"",DPWW3!FT11) | ¬¬IF(ISBLANK(DPWW3!FU11),"",DPWW3!FU11) | ¬¬IF(ISBLANK(DPWW3!FV11),"",DPWW3!FV11) | ¬¬IF(ISBLANK(DPWW3!FW11),"",DPWW3!FW11) | ¬¬IF(ISBLANK(DPWW3!FX11),"",DPWW3!FX11) | ¬¬IF(ISBLANK(DPWW3!FY11),"",DPWW3!FY11) | ¬¬IF(ISBLANK(DPWW3!FZ11),"",DPWW3!FZ11) | ¬¬IF(ISBLANK(DPWW3!GA11),"",DPWW3!GA11) | ¬¬IF(ISBLANK(DPWW3!GB11),"",DPWW3!GB11) | ¬¬IF(ISBLANK(DPWW3!GC11),"",DPWW3!GC11) | ¬¬IF(ISBLANK(DPWW3!GD11),"",DPWW3!GD11) | ¬¬IF(ISBLANK(DPWW3!GE11),"",DPWW3!GE11)
¬¬A676 | ¬¬IF(ISBLANK(DPWW3!NS11),"",DPWW3!NS11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GG11),"",DPWW3!GG11)
¬¬A677 | ¬¬IF(ISBLANK(DPWW3!NT11),"",DPWW3!NT11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GH11),"",DPWW3!GH11)
¬¬A678 | ¬¬IF(ISBLANK(DPWW3!NU11),"",DPWW3!NU11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GI11),"",DPWW3!GI11)
¬¬A679 | ¬¬IF(ISBLANK(DPWW3!NV11),"",DPWW3!NV11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ11),"",DPWW3!GJ11)
¬¬A680 | ¬¬IF(ISBLANK(DPWW3!NW11),"",DPWW3!NW11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GK11),"",DPWW3!GK11)
¬¬A681 | ¬¬IF(ISBLANK(DPWW3!NX11),"",DPWW3!NX11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GL11),"",DPWW3!GL11)
¬¬A682 | ¬¬IF(ISBLANK(DPWW3!NY11),"",DPWW3!NY11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GM11),"",DPWW3!GM11)
¬¬A683 | ¬¬IF(ISBLANK(DPWW3!NZ11),"",DPWW3!NZ11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GN11),"",DPWW3!GN11)
¬¬A684 | ¬¬IF(ISBLANK(DPWW3!OA11),"",DPWW3!OA11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GO11),"",DPWW3!GO11)
¬¬A685 | ¬¬IF(ISBLANK(DPWW3!OB11),"",DPWW3!OB11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GP11),"",DPWW3!GP11)
¬¬A686 | ¬¬IF(ISBLANK(DPWW3!OC11),"",DPWW3!OC11) | ¬¬DPWW3!F11 & "," & DPWW3!G11 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H11),"",DPWW3!H11) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ11),"",DPWW3!GQ11)
¬¬A687 | ¬¬IF(ISBLANK(DPWW3!GW12),"",DPWW3!GW12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!K12),"",DPWW3!K12)
¬¬A688 | ¬¬IF(ISBLANK(DPWW3!GY12),"",DPWW3!GY12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M12),"",DPWW3!M12) | ¬¬IF(ISBLANK(DPWW3!N12),"",DPWW3!N12) | ¬¬IF(ISBLANK(DPWW3!O12),"",DPWW3!O12) | ¬¬IF(ISBLANK(DPWW3!P12),"",DPWW3!P12) | ¬¬IF(ISBLANK(DPWW3!Q12),"",DPWW3!Q12) | ¬¬IF(ISBLANK(DPWW3!R12),"",DPWW3!R12) | ¬¬IF(ISBLANK(DPWW3!S12),"",DPWW3!S12) | ¬¬IF(ISBLANK(DPWW3!T12),"",DPWW3!T12) | ¬¬IF(ISBLANK(DPWW3!U12),"",DPWW3!U12) | ¬¬IF(ISBLANK(DPWW3!V12),"",DPWW3!V12) | ¬¬IF(ISBLANK(DPWW3!W12),"",DPWW3!W12) | ¬¬IF(ISBLANK(DPWW3!X12),"",DPWW3!X12) | ¬¬IF(ISBLANK(DPWW3!Y12),"",DPWW3!Y12) | ¬¬IF(ISBLANK(DPWW3!Z12),"",DPWW3!Z12) | ¬¬IF(ISBLANK(DPWW3!AA12),"",DPWW3!AA12) | ¬¬IF(ISBLANK(DPWW3!AB12),"",DPWW3!AB12) | ¬¬IF(ISBLANK(DPWW3!AC12),"",DPWW3!AC12) | ¬¬IF(ISBLANK(DPWW3!AD12),"",DPWW3!AD12) | ¬¬IF(ISBLANK(DPWW3!AE12),"",DPWW3!AE12) | ¬¬IF(ISBLANK(DPWW3!AF12),"",DPWW3!AF12) | ¬¬IF(ISBLANK(DPWW3!AG12),"",DPWW3!AG12)
¬¬A689 | ¬¬IF(ISBLANK(DPWW3!HU12),"",DPWW3!HU12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI12),"",DPWW3!AI12) | ¬¬IF(ISBLANK(DPWW3!AJ12),"",DPWW3!AJ12) | ¬¬IF(ISBLANK(DPWW3!AK12),"",DPWW3!AK12) | ¬¬IF(ISBLANK(DPWW3!AL12),"",DPWW3!AL12) | ¬¬IF(ISBLANK(DPWW3!AM12),"",DPWW3!AM12) | ¬¬IF(ISBLANK(DPWW3!AN12),"",DPWW3!AN12) | ¬¬IF(ISBLANK(DPWW3!AO12),"",DPWW3!AO12) | ¬¬IF(ISBLANK(DPWW3!AP12),"",DPWW3!AP12) | ¬¬IF(ISBLANK(DPWW3!AQ12),"",DPWW3!AQ12) | ¬¬IF(ISBLANK(DPWW3!AR12),"",DPWW3!AR12) | ¬¬IF(ISBLANK(DPWW3!AS12),"",DPWW3!AS12) | ¬¬IF(ISBLANK(DPWW3!AT12),"",DPWW3!AT12) | ¬¬IF(ISBLANK(DPWW3!AU12),"",DPWW3!AU12) | ¬¬IF(ISBLANK(DPWW3!AV12),"",DPWW3!AV12) | ¬¬IF(ISBLANK(DPWW3!AW12),"",DPWW3!AW12) | ¬¬IF(ISBLANK(DPWW3!AX12),"",DPWW3!AX12) | ¬¬IF(ISBLANK(DPWW3!AY12),"",DPWW3!AY12) | ¬¬IF(ISBLANK(DPWW3!AZ12),"",DPWW3!AZ12) | ¬¬IF(ISBLANK(DPWW3!BA12),"",DPWW3!BA12) | ¬¬IF(ISBLANK(DPWW3!BB12),"",DPWW3!BB12) | ¬¬IF(ISBLANK(DPWW3!BC12),"",DPWW3!BC12)
¬¬A690 | ¬¬IF(ISBLANK(DPWW3!IQ12),"",DPWW3!IQ12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE12),"",DPWW3!BE12) | ¬¬IF(ISBLANK(DPWW3!BF12),"",DPWW3!BF12) | ¬¬IF(ISBLANK(DPWW3!BG12),"",DPWW3!BG12) | ¬¬IF(ISBLANK(DPWW3!BH12),"",DPWW3!BH12) | ¬¬IF(ISBLANK(DPWW3!BI12),"",DPWW3!BI12) | ¬¬IF(ISBLANK(DPWW3!BJ12),"",DPWW3!BJ12) | ¬¬IF(ISBLANK(DPWW3!BK12),"",DPWW3!BK12) | ¬¬IF(ISBLANK(DPWW3!BL12),"",DPWW3!BL12) | ¬¬IF(ISBLANK(DPWW3!BM12),"",DPWW3!BM12) | ¬¬IF(ISBLANK(DPWW3!BN12),"",DPWW3!BN12) | ¬¬IF(ISBLANK(DPWW3!BO12),"",DPWW3!BO12) | ¬¬IF(ISBLANK(DPWW3!BP12),"",DPWW3!BP12) | ¬¬IF(ISBLANK(DPWW3!BQ12),"",DPWW3!BQ12) | ¬¬IF(ISBLANK(DPWW3!BR12),"",DPWW3!BR12) | ¬¬IF(ISBLANK(DPWW3!BS12),"",DPWW3!BS12) | ¬¬IF(ISBLANK(DPWW3!BT12),"",DPWW3!BT12) | ¬¬IF(ISBLANK(DPWW3!BU12),"",DPWW3!BU12) | ¬¬IF(ISBLANK(DPWW3!BV12),"",DPWW3!BV12) | ¬¬IF(ISBLANK(DPWW3!BW12),"",DPWW3!BW12) | ¬¬IF(ISBLANK(DPWW3!BX12),"",DPWW3!BX12) | ¬¬IF(ISBLANK(DPWW3!BY12),"",DPWW3!BY12)
¬¬A691 | ¬¬IF(ISBLANK(DPWW3!JM12),"",DPWW3!JM12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA12),"",DPWW3!CA12) | ¬¬IF(ISBLANK(DPWW3!CB12),"",DPWW3!CB12) | ¬¬IF(ISBLANK(DPWW3!CC12),"",DPWW3!CC12) | ¬¬IF(ISBLANK(DPWW3!CD12),"",DPWW3!CD12) | ¬¬IF(ISBLANK(DPWW3!CE12),"",DPWW3!CE12) | ¬¬IF(ISBLANK(DPWW3!CF12),"",DPWW3!CF12) | ¬¬IF(ISBLANK(DPWW3!CG12),"",DPWW3!CG12) | ¬¬IF(ISBLANK(DPWW3!CH12),"",DPWW3!CH12) | ¬¬IF(ISBLANK(DPWW3!CI12),"",DPWW3!CI12) | ¬¬IF(ISBLANK(DPWW3!CJ12),"",DPWW3!CJ12) | ¬¬IF(ISBLANK(DPWW3!CK12),"",DPWW3!CK12) | ¬¬IF(ISBLANK(DPWW3!CL12),"",DPWW3!CL12) | ¬¬IF(ISBLANK(DPWW3!CM12),"",DPWW3!CM12) | ¬¬IF(ISBLANK(DPWW3!CN12),"",DPWW3!CN12) | ¬¬IF(ISBLANK(DPWW3!CO12),"",DPWW3!CO12) | ¬¬IF(ISBLANK(DPWW3!CP12),"",DPWW3!CP12) | ¬¬IF(ISBLANK(DPWW3!CQ12),"",DPWW3!CQ12) | ¬¬IF(ISBLANK(DPWW3!CR12),"",DPWW3!CR12) | ¬¬IF(ISBLANK(DPWW3!CS12),"",DPWW3!CS12) | ¬¬IF(ISBLANK(DPWW3!CT12),"",DPWW3!CT12) | ¬¬IF(ISBLANK(DPWW3!CU12),"",DPWW3!CU12)
¬¬A692 | ¬¬IF(ISBLANK(DPWW3!KI12),"",DPWW3!KI12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW12),"",DPWW3!CW12) | ¬¬IF(ISBLANK(DPWW3!CX12),"",DPWW3!CX12) | ¬¬IF(ISBLANK(DPWW3!CY12),"",DPWW3!CY12) | ¬¬IF(ISBLANK(DPWW3!CZ12),"",DPWW3!CZ12) | ¬¬IF(ISBLANK(DPWW3!DA12),"",DPWW3!DA12) | ¬¬IF(ISBLANK(DPWW3!DB12),"",DPWW3!DB12) | ¬¬IF(ISBLANK(DPWW3!DC12),"",DPWW3!DC12) | ¬¬IF(ISBLANK(DPWW3!DD12),"",DPWW3!DD12) | ¬¬IF(ISBLANK(DPWW3!DE12),"",DPWW3!DE12) | ¬¬IF(ISBLANK(DPWW3!DF12),"",DPWW3!DF12) | ¬¬IF(ISBLANK(DPWW3!DG12),"",DPWW3!DG12) | ¬¬IF(ISBLANK(DPWW3!DH12),"",DPWW3!DH12) | ¬¬IF(ISBLANK(DPWW3!DI12),"",DPWW3!DI12) | ¬¬IF(ISBLANK(DPWW3!DJ12),"",DPWW3!DJ12) | ¬¬IF(ISBLANK(DPWW3!DK12),"",DPWW3!DK12) | ¬¬IF(ISBLANK(DPWW3!DL12),"",DPWW3!DL12) | ¬¬IF(ISBLANK(DPWW3!DM12),"",DPWW3!DM12) | ¬¬IF(ISBLANK(DPWW3!DN12),"",DPWW3!DN12) | ¬¬IF(ISBLANK(DPWW3!DO12),"",DPWW3!DO12) | ¬¬IF(ISBLANK(DPWW3!DP12),"",DPWW3!DP12) | ¬¬IF(ISBLANK(DPWW3!DQ12),"",DPWW3!DQ12)
¬¬A693 | ¬¬IF(ISBLANK(DPWW3!LE12),"",DPWW3!LE12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS12),"",DPWW3!DS12) | ¬¬IF(ISBLANK(DPWW3!DT12),"",DPWW3!DT12) | ¬¬IF(ISBLANK(DPWW3!DU12),"",DPWW3!DU12) | ¬¬IF(ISBLANK(DPWW3!DV12),"",DPWW3!DV12) | ¬¬IF(ISBLANK(DPWW3!DW12),"",DPWW3!DW12) | ¬¬IF(ISBLANK(DPWW3!DX12),"",DPWW3!DX12) | ¬¬IF(ISBLANK(DPWW3!DY12),"",DPWW3!DY12) | ¬¬IF(ISBLANK(DPWW3!DZ12),"",DPWW3!DZ12) | ¬¬IF(ISBLANK(DPWW3!EA12),"",DPWW3!EA12) | ¬¬IF(ISBLANK(DPWW3!EB12),"",DPWW3!EB12) | ¬¬IF(ISBLANK(DPWW3!EC12),"",DPWW3!EC12) | ¬¬IF(ISBLANK(DPWW3!ED12),"",DPWW3!ED12) | ¬¬IF(ISBLANK(DPWW3!EE12),"",DPWW3!EE12) | ¬¬IF(ISBLANK(DPWW3!EF12),"",DPWW3!EF12) | ¬¬IF(ISBLANK(DPWW3!EG12),"",DPWW3!EG12) | ¬¬IF(ISBLANK(DPWW3!EH12),"",DPWW3!EH12) | ¬¬IF(ISBLANK(DPWW3!EI12),"",DPWW3!EI12) | ¬¬IF(ISBLANK(DPWW3!EJ12),"",DPWW3!EJ12) | ¬¬IF(ISBLANK(DPWW3!EK12),"",DPWW3!EK12) | ¬¬IF(ISBLANK(DPWW3!EL12),"",DPWW3!EL12) | ¬¬IF(ISBLANK(DPWW3!EM12),"",DPWW3!EM12)
¬¬A694 | ¬¬IF(ISBLANK(DPWW3!MA12),"",DPWW3!MA12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO12),"",DPWW3!EO12) | ¬¬IF(ISBLANK(DPWW3!EP12),"",DPWW3!EP12) | ¬¬IF(ISBLANK(DPWW3!EQ12),"",DPWW3!EQ12) | ¬¬IF(ISBLANK(DPWW3!ER12),"",DPWW3!ER12) | ¬¬IF(ISBLANK(DPWW3!ES12),"",DPWW3!ES12) | ¬¬IF(ISBLANK(DPWW3!ET12),"",DPWW3!ET12) | ¬¬IF(ISBLANK(DPWW3!EU12),"",DPWW3!EU12) | ¬¬IF(ISBLANK(DPWW3!EV12),"",DPWW3!EV12) | ¬¬IF(ISBLANK(DPWW3!EW12),"",DPWW3!EW12) | ¬¬IF(ISBLANK(DPWW3!EX12),"",DPWW3!EX12) | ¬¬IF(ISBLANK(DPWW3!EY12),"",DPWW3!EY12) | ¬¬IF(ISBLANK(DPWW3!EZ12),"",DPWW3!EZ12) | ¬¬IF(ISBLANK(DPWW3!FA12),"",DPWW3!FA12) | ¬¬IF(ISBLANK(DPWW3!FB12),"",DPWW3!FB12) | ¬¬IF(ISBLANK(DPWW3!FC12),"",DPWW3!FC12) | ¬¬IF(ISBLANK(DPWW3!FD12),"",DPWW3!FD12) | ¬¬IF(ISBLANK(DPWW3!FE12),"",DPWW3!FE12) | ¬¬IF(ISBLANK(DPWW3!FF12),"",DPWW3!FF12) | ¬¬IF(ISBLANK(DPWW3!FG12),"",DPWW3!FG12) | ¬¬IF(ISBLANK(DPWW3!FH12),"",DPWW3!FH12) | ¬¬IF(ISBLANK(DPWW3!FI12),"",DPWW3!FI12)
¬¬A695 | ¬¬IF(ISBLANK(DPWW3!MW12),"",DPWW3!MW12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK12),"",DPWW3!FK12) | ¬¬IF(ISBLANK(DPWW3!FL12),"",DPWW3!FL12) | ¬¬IF(ISBLANK(DPWW3!FM12),"",DPWW3!FM12) | ¬¬IF(ISBLANK(DPWW3!FN12),"",DPWW3!FN12) | ¬¬IF(ISBLANK(DPWW3!FO12),"",DPWW3!FO12) | ¬¬IF(ISBLANK(DPWW3!FP12),"",DPWW3!FP12) | ¬¬IF(ISBLANK(DPWW3!FQ12),"",DPWW3!FQ12) | ¬¬IF(ISBLANK(DPWW3!FR12),"",DPWW3!FR12) | ¬¬IF(ISBLANK(DPWW3!FS12),"",DPWW3!FS12) | ¬¬IF(ISBLANK(DPWW3!FT12),"",DPWW3!FT12) | ¬¬IF(ISBLANK(DPWW3!FU12),"",DPWW3!FU12) | ¬¬IF(ISBLANK(DPWW3!FV12),"",DPWW3!FV12) | ¬¬IF(ISBLANK(DPWW3!FW12),"",DPWW3!FW12) | ¬¬IF(ISBLANK(DPWW3!FX12),"",DPWW3!FX12) | ¬¬IF(ISBLANK(DPWW3!FY12),"",DPWW3!FY12) | ¬¬IF(ISBLANK(DPWW3!FZ12),"",DPWW3!FZ12) | ¬¬IF(ISBLANK(DPWW3!GA12),"",DPWW3!GA12) | ¬¬IF(ISBLANK(DPWW3!GB12),"",DPWW3!GB12) | ¬¬IF(ISBLANK(DPWW3!GC12),"",DPWW3!GC12) | ¬¬IF(ISBLANK(DPWW3!GD12),"",DPWW3!GD12) | ¬¬IF(ISBLANK(DPWW3!GE12),"",DPWW3!GE12)
¬¬A696 | ¬¬IF(ISBLANK(DPWW3!NS12),"",DPWW3!NS12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GG12),"",DPWW3!GG12)
¬¬A697 | ¬¬IF(ISBLANK(DPWW3!NT12),"",DPWW3!NT12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GH12),"",DPWW3!GH12)
¬¬A698 | ¬¬IF(ISBLANK(DPWW3!NU12),"",DPWW3!NU12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GI12),"",DPWW3!GI12)
¬¬A699 | ¬¬IF(ISBLANK(DPWW3!NV12),"",DPWW3!NV12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ12),"",DPWW3!GJ12)
¬¬A700 | ¬¬IF(ISBLANK(DPWW3!NW12),"",DPWW3!NW12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GK12),"",DPWW3!GK12)
¬¬A701 | ¬¬IF(ISBLANK(DPWW3!NX12),"",DPWW3!NX12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GL12),"",DPWW3!GL12)
¬¬A702 | ¬¬IF(ISBLANK(DPWW3!NY12),"",DPWW3!NY12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GM12),"",DPWW3!GM12)
¬¬A703 | ¬¬IF(ISBLANK(DPWW3!NZ12),"",DPWW3!NZ12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GN12),"",DPWW3!GN12)
¬¬A704 | ¬¬IF(ISBLANK(DPWW3!OA12),"",DPWW3!OA12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GO12),"",DPWW3!GO12)
¬¬A705 | ¬¬IF(ISBLANK(DPWW3!OB12),"",DPWW3!OB12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GP12),"",DPWW3!GP12)
¬¬A706 | ¬¬IF(ISBLANK(DPWW3!OC12),"",DPWW3!OC12) | ¬¬DPWW3!F12 & "," & DPWW3!G12 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H12),"",DPWW3!H12) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ12),"",DPWW3!GQ12)
¬¬A707 | ¬¬IF(ISBLANK(DPWW3!GW13),"",DPWW3!GW13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!K13),"",DPWW3!K13)
¬¬A708 | ¬¬IF(ISBLANK(DPWW3!GY13),"",DPWW3!GY13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M13),"",DPWW3!M13) | ¬¬IF(ISBLANK(DPWW3!N13),"",DPWW3!N13) | ¬¬IF(ISBLANK(DPWW3!O13),"",DPWW3!O13) | ¬¬IF(ISBLANK(DPWW3!P13),"",DPWW3!P13) | ¬¬IF(ISBLANK(DPWW3!Q13),"",DPWW3!Q13) | ¬¬IF(ISBLANK(DPWW3!R13),"",DPWW3!R13) | ¬¬IF(ISBLANK(DPWW3!S13),"",DPWW3!S13) | ¬¬IF(ISBLANK(DPWW3!T13),"",DPWW3!T13) | ¬¬IF(ISBLANK(DPWW3!U13),"",DPWW3!U13) | ¬¬IF(ISBLANK(DPWW3!V13),"",DPWW3!V13) | ¬¬IF(ISBLANK(DPWW3!W13),"",DPWW3!W13) | ¬¬IF(ISBLANK(DPWW3!X13),"",DPWW3!X13) | ¬¬IF(ISBLANK(DPWW3!Y13),"",DPWW3!Y13) | ¬¬IF(ISBLANK(DPWW3!Z13),"",DPWW3!Z13) | ¬¬IF(ISBLANK(DPWW3!AA13),"",DPWW3!AA13) | ¬¬IF(ISBLANK(DPWW3!AB13),"",DPWW3!AB13) | ¬¬IF(ISBLANK(DPWW3!AC13),"",DPWW3!AC13) | ¬¬IF(ISBLANK(DPWW3!AD13),"",DPWW3!AD13) | ¬¬IF(ISBLANK(DPWW3!AE13),"",DPWW3!AE13) | ¬¬IF(ISBLANK(DPWW3!AF13),"",DPWW3!AF13) | ¬¬IF(ISBLANK(DPWW3!AG13),"",DPWW3!AG13)
¬¬A709 | ¬¬IF(ISBLANK(DPWW3!HU13),"",DPWW3!HU13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI13),"",DPWW3!AI13) | ¬¬IF(ISBLANK(DPWW3!AJ13),"",DPWW3!AJ13) | ¬¬IF(ISBLANK(DPWW3!AK13),"",DPWW3!AK13) | ¬¬IF(ISBLANK(DPWW3!AL13),"",DPWW3!AL13) | ¬¬IF(ISBLANK(DPWW3!AM13),"",DPWW3!AM13) | ¬¬IF(ISBLANK(DPWW3!AN13),"",DPWW3!AN13) | ¬¬IF(ISBLANK(DPWW3!AO13),"",DPWW3!AO13) | ¬¬IF(ISBLANK(DPWW3!AP13),"",DPWW3!AP13) | ¬¬IF(ISBLANK(DPWW3!AQ13),"",DPWW3!AQ13) | ¬¬IF(ISBLANK(DPWW3!AR13),"",DPWW3!AR13) | ¬¬IF(ISBLANK(DPWW3!AS13),"",DPWW3!AS13) | ¬¬IF(ISBLANK(DPWW3!AT13),"",DPWW3!AT13) | ¬¬IF(ISBLANK(DPWW3!AU13),"",DPWW3!AU13) | ¬¬IF(ISBLANK(DPWW3!AV13),"",DPWW3!AV13) | ¬¬IF(ISBLANK(DPWW3!AW13),"",DPWW3!AW13) | ¬¬IF(ISBLANK(DPWW3!AX13),"",DPWW3!AX13) | ¬¬IF(ISBLANK(DPWW3!AY13),"",DPWW3!AY13) | ¬¬IF(ISBLANK(DPWW3!AZ13),"",DPWW3!AZ13) | ¬¬IF(ISBLANK(DPWW3!BA13),"",DPWW3!BA13) | ¬¬IF(ISBLANK(DPWW3!BB13),"",DPWW3!BB13) | ¬¬IF(ISBLANK(DPWW3!BC13),"",DPWW3!BC13)
¬¬A710 | ¬¬IF(ISBLANK(DPWW3!IQ13),"",DPWW3!IQ13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE13),"",DPWW3!BE13) | ¬¬IF(ISBLANK(DPWW3!BF13),"",DPWW3!BF13) | ¬¬IF(ISBLANK(DPWW3!BG13),"",DPWW3!BG13) | ¬¬IF(ISBLANK(DPWW3!BH13),"",DPWW3!BH13) | ¬¬IF(ISBLANK(DPWW3!BI13),"",DPWW3!BI13) | ¬¬IF(ISBLANK(DPWW3!BJ13),"",DPWW3!BJ13) | ¬¬IF(ISBLANK(DPWW3!BK13),"",DPWW3!BK13) | ¬¬IF(ISBLANK(DPWW3!BL13),"",DPWW3!BL13) | ¬¬IF(ISBLANK(DPWW3!BM13),"",DPWW3!BM13) | ¬¬IF(ISBLANK(DPWW3!BN13),"",DPWW3!BN13) | ¬¬IF(ISBLANK(DPWW3!BO13),"",DPWW3!BO13) | ¬¬IF(ISBLANK(DPWW3!BP13),"",DPWW3!BP13) | ¬¬IF(ISBLANK(DPWW3!BQ13),"",DPWW3!BQ13) | ¬¬IF(ISBLANK(DPWW3!BR13),"",DPWW3!BR13) | ¬¬IF(ISBLANK(DPWW3!BS13),"",DPWW3!BS13) | ¬¬IF(ISBLANK(DPWW3!BT13),"",DPWW3!BT13) | ¬¬IF(ISBLANK(DPWW3!BU13),"",DPWW3!BU13) | ¬¬IF(ISBLANK(DPWW3!BV13),"",DPWW3!BV13) | ¬¬IF(ISBLANK(DPWW3!BW13),"",DPWW3!BW13) | ¬¬IF(ISBLANK(DPWW3!BX13),"",DPWW3!BX13) | ¬¬IF(ISBLANK(DPWW3!BY13),"",DPWW3!BY13)
¬¬A711 | ¬¬IF(ISBLANK(DPWW3!JM13),"",DPWW3!JM13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA13),"",DPWW3!CA13) | ¬¬IF(ISBLANK(DPWW3!CB13),"",DPWW3!CB13) | ¬¬IF(ISBLANK(DPWW3!CC13),"",DPWW3!CC13) | ¬¬IF(ISBLANK(DPWW3!CD13),"",DPWW3!CD13) | ¬¬IF(ISBLANK(DPWW3!CE13),"",DPWW3!CE13) | ¬¬IF(ISBLANK(DPWW3!CF13),"",DPWW3!CF13) | ¬¬IF(ISBLANK(DPWW3!CG13),"",DPWW3!CG13) | ¬¬IF(ISBLANK(DPWW3!CH13),"",DPWW3!CH13) | ¬¬IF(ISBLANK(DPWW3!CI13),"",DPWW3!CI13) | ¬¬IF(ISBLANK(DPWW3!CJ13),"",DPWW3!CJ13) | ¬¬IF(ISBLANK(DPWW3!CK13),"",DPWW3!CK13) | ¬¬IF(ISBLANK(DPWW3!CL13),"",DPWW3!CL13) | ¬¬IF(ISBLANK(DPWW3!CM13),"",DPWW3!CM13) | ¬¬IF(ISBLANK(DPWW3!CN13),"",DPWW3!CN13) | ¬¬IF(ISBLANK(DPWW3!CO13),"",DPWW3!CO13) | ¬¬IF(ISBLANK(DPWW3!CP13),"",DPWW3!CP13) | ¬¬IF(ISBLANK(DPWW3!CQ13),"",DPWW3!CQ13) | ¬¬IF(ISBLANK(DPWW3!CR13),"",DPWW3!CR13) | ¬¬IF(ISBLANK(DPWW3!CS13),"",DPWW3!CS13) | ¬¬IF(ISBLANK(DPWW3!CT13),"",DPWW3!CT13) | ¬¬IF(ISBLANK(DPWW3!CU13),"",DPWW3!CU13)
¬¬A712 | ¬¬IF(ISBLANK(DPWW3!KI13),"",DPWW3!KI13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW13),"",DPWW3!CW13) | ¬¬IF(ISBLANK(DPWW3!CX13),"",DPWW3!CX13) | ¬¬IF(ISBLANK(DPWW3!CY13),"",DPWW3!CY13) | ¬¬IF(ISBLANK(DPWW3!CZ13),"",DPWW3!CZ13) | ¬¬IF(ISBLANK(DPWW3!DA13),"",DPWW3!DA13) | ¬¬IF(ISBLANK(DPWW3!DB13),"",DPWW3!DB13) | ¬¬IF(ISBLANK(DPWW3!DC13),"",DPWW3!DC13) | ¬¬IF(ISBLANK(DPWW3!DD13),"",DPWW3!DD13) | ¬¬IF(ISBLANK(DPWW3!DE13),"",DPWW3!DE13) | ¬¬IF(ISBLANK(DPWW3!DF13),"",DPWW3!DF13) | ¬¬IF(ISBLANK(DPWW3!DG13),"",DPWW3!DG13) | ¬¬IF(ISBLANK(DPWW3!DH13),"",DPWW3!DH13) | ¬¬IF(ISBLANK(DPWW3!DI13),"",DPWW3!DI13) | ¬¬IF(ISBLANK(DPWW3!DJ13),"",DPWW3!DJ13) | ¬¬IF(ISBLANK(DPWW3!DK13),"",DPWW3!DK13) | ¬¬IF(ISBLANK(DPWW3!DL13),"",DPWW3!DL13) | ¬¬IF(ISBLANK(DPWW3!DM13),"",DPWW3!DM13) | ¬¬IF(ISBLANK(DPWW3!DN13),"",DPWW3!DN13) | ¬¬IF(ISBLANK(DPWW3!DO13),"",DPWW3!DO13) | ¬¬IF(ISBLANK(DPWW3!DP13),"",DPWW3!DP13) | ¬¬IF(ISBLANK(DPWW3!DQ13),"",DPWW3!DQ13)
¬¬A713 | ¬¬IF(ISBLANK(DPWW3!LE13),"",DPWW3!LE13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS13),"",DPWW3!DS13) | ¬¬IF(ISBLANK(DPWW3!DT13),"",DPWW3!DT13) | ¬¬IF(ISBLANK(DPWW3!DU13),"",DPWW3!DU13) | ¬¬IF(ISBLANK(DPWW3!DV13),"",DPWW3!DV13) | ¬¬IF(ISBLANK(DPWW3!DW13),"",DPWW3!DW13) | ¬¬IF(ISBLANK(DPWW3!DX13),"",DPWW3!DX13) | ¬¬IF(ISBLANK(DPWW3!DY13),"",DPWW3!DY13) | ¬¬IF(ISBLANK(DPWW3!DZ13),"",DPWW3!DZ13) | ¬¬IF(ISBLANK(DPWW3!EA13),"",DPWW3!EA13) | ¬¬IF(ISBLANK(DPWW3!EB13),"",DPWW3!EB13) | ¬¬IF(ISBLANK(DPWW3!EC13),"",DPWW3!EC13) | ¬¬IF(ISBLANK(DPWW3!ED13),"",DPWW3!ED13) | ¬¬IF(ISBLANK(DPWW3!EE13),"",DPWW3!EE13) | ¬¬IF(ISBLANK(DPWW3!EF13),"",DPWW3!EF13) | ¬¬IF(ISBLANK(DPWW3!EG13),"",DPWW3!EG13) | ¬¬IF(ISBLANK(DPWW3!EH13),"",DPWW3!EH13) | ¬¬IF(ISBLANK(DPWW3!EI13),"",DPWW3!EI13) | ¬¬IF(ISBLANK(DPWW3!EJ13),"",DPWW3!EJ13) | ¬¬IF(ISBLANK(DPWW3!EK13),"",DPWW3!EK13) | ¬¬IF(ISBLANK(DPWW3!EL13),"",DPWW3!EL13) | ¬¬IF(ISBLANK(DPWW3!EM13),"",DPWW3!EM13)
¬¬A714 | ¬¬IF(ISBLANK(DPWW3!MA13),"",DPWW3!MA13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO13),"",DPWW3!EO13) | ¬¬IF(ISBLANK(DPWW3!EP13),"",DPWW3!EP13) | ¬¬IF(ISBLANK(DPWW3!EQ13),"",DPWW3!EQ13) | ¬¬IF(ISBLANK(DPWW3!ER13),"",DPWW3!ER13) | ¬¬IF(ISBLANK(DPWW3!ES13),"",DPWW3!ES13) | ¬¬IF(ISBLANK(DPWW3!ET13),"",DPWW3!ET13) | ¬¬IF(ISBLANK(DPWW3!EU13),"",DPWW3!EU13) | ¬¬IF(ISBLANK(DPWW3!EV13),"",DPWW3!EV13) | ¬¬IF(ISBLANK(DPWW3!EW13),"",DPWW3!EW13) | ¬¬IF(ISBLANK(DPWW3!EX13),"",DPWW3!EX13) | ¬¬IF(ISBLANK(DPWW3!EY13),"",DPWW3!EY13) | ¬¬IF(ISBLANK(DPWW3!EZ13),"",DPWW3!EZ13) | ¬¬IF(ISBLANK(DPWW3!FA13),"",DPWW3!FA13) | ¬¬IF(ISBLANK(DPWW3!FB13),"",DPWW3!FB13) | ¬¬IF(ISBLANK(DPWW3!FC13),"",DPWW3!FC13) | ¬¬IF(ISBLANK(DPWW3!FD13),"",DPWW3!FD13) | ¬¬IF(ISBLANK(DPWW3!FE13),"",DPWW3!FE13) | ¬¬IF(ISBLANK(DPWW3!FF13),"",DPWW3!FF13) | ¬¬IF(ISBLANK(DPWW3!FG13),"",DPWW3!FG13) | ¬¬IF(ISBLANK(DPWW3!FH13),"",DPWW3!FH13) | ¬¬IF(ISBLANK(DPWW3!FI13),"",DPWW3!FI13)
¬¬A715 | ¬¬IF(ISBLANK(DPWW3!MW13),"",DPWW3!MW13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK13),"",DPWW3!FK13) | ¬¬IF(ISBLANK(DPWW3!FL13),"",DPWW3!FL13) | ¬¬IF(ISBLANK(DPWW3!FM13),"",DPWW3!FM13) | ¬¬IF(ISBLANK(DPWW3!FN13),"",DPWW3!FN13) | ¬¬IF(ISBLANK(DPWW3!FO13),"",DPWW3!FO13) | ¬¬IF(ISBLANK(DPWW3!FP13),"",DPWW3!FP13) | ¬¬IF(ISBLANK(DPWW3!FQ13),"",DPWW3!FQ13) | ¬¬IF(ISBLANK(DPWW3!FR13),"",DPWW3!FR13) | ¬¬IF(ISBLANK(DPWW3!FS13),"",DPWW3!FS13) | ¬¬IF(ISBLANK(DPWW3!FT13),"",DPWW3!FT13) | ¬¬IF(ISBLANK(DPWW3!FU13),"",DPWW3!FU13) | ¬¬IF(ISBLANK(DPWW3!FV13),"",DPWW3!FV13) | ¬¬IF(ISBLANK(DPWW3!FW13),"",DPWW3!FW13) | ¬¬IF(ISBLANK(DPWW3!FX13),"",DPWW3!FX13) | ¬¬IF(ISBLANK(DPWW3!FY13),"",DPWW3!FY13) | ¬¬IF(ISBLANK(DPWW3!FZ13),"",DPWW3!FZ13) | ¬¬IF(ISBLANK(DPWW3!GA13),"",DPWW3!GA13) | ¬¬IF(ISBLANK(DPWW3!GB13),"",DPWW3!GB13) | ¬¬IF(ISBLANK(DPWW3!GC13),"",DPWW3!GC13) | ¬¬IF(ISBLANK(DPWW3!GD13),"",DPWW3!GD13) | ¬¬IF(ISBLANK(DPWW3!GE13),"",DPWW3!GE13)
¬¬A716 | ¬¬IF(ISBLANK(DPWW3!NS13),"",DPWW3!NS13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GG13),"",DPWW3!GG13)
¬¬A717 | ¬¬IF(ISBLANK(DPWW3!NT13),"",DPWW3!NT13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GH13),"",DPWW3!GH13)
¬¬A718 | ¬¬IF(ISBLANK(DPWW3!NU13),"",DPWW3!NU13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GI13),"",DPWW3!GI13)
¬¬A719 | ¬¬IF(ISBLANK(DPWW3!NV13),"",DPWW3!NV13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ13),"",DPWW3!GJ13)
¬¬A720 | ¬¬IF(ISBLANK(DPWW3!NW13),"",DPWW3!NW13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GK13),"",DPWW3!GK13)
¬¬A721 | ¬¬IF(ISBLANK(DPWW3!NX13),"",DPWW3!NX13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GL13),"",DPWW3!GL13)
¬¬A722 | ¬¬IF(ISBLANK(DPWW3!NY13),"",DPWW3!NY13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GM13),"",DPWW3!GM13)
¬¬A723 | ¬¬IF(ISBLANK(DPWW3!NZ13),"",DPWW3!NZ13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GN13),"",DPWW3!GN13)
¬¬A724 | ¬¬IF(ISBLANK(DPWW3!OA13),"",DPWW3!OA13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GO13),"",DPWW3!GO13)
¬¬A725 | ¬¬IF(ISBLANK(DPWW3!OB13),"",DPWW3!OB13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GP13),"",DPWW3!GP13)
¬¬A726 | ¬¬IF(ISBLANK(DPWW3!OC13),"",DPWW3!OC13) | ¬¬DPWW3!F13 & "," & DPWW3!G13 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H13),"",DPWW3!H13) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ13),"",DPWW3!GQ13)
¬¬A727 | ¬¬IF(ISBLANK(DPWW3!GW14),"",DPWW3!GW14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!K14),"",DPWW3!K14)
¬¬A728 | ¬¬IF(ISBLANK(DPWW3!GY14),"",DPWW3!GY14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M14),"",DPWW3!M14) | ¬¬IF(ISBLANK(DPWW3!N14),"",DPWW3!N14) | ¬¬IF(ISBLANK(DPWW3!O14),"",DPWW3!O14) | ¬¬IF(ISBLANK(DPWW3!P14),"",DPWW3!P14) | ¬¬IF(ISBLANK(DPWW3!Q14),"",DPWW3!Q14) | ¬¬IF(ISBLANK(DPWW3!R14),"",DPWW3!R14) | ¬¬IF(ISBLANK(DPWW3!S14),"",DPWW3!S14) | ¬¬IF(ISBLANK(DPWW3!T14),"",DPWW3!T14) | ¬¬IF(ISBLANK(DPWW3!U14),"",DPWW3!U14) | ¬¬IF(ISBLANK(DPWW3!V14),"",DPWW3!V14) | ¬¬IF(ISBLANK(DPWW3!W14),"",DPWW3!W14) | ¬¬IF(ISBLANK(DPWW3!X14),"",DPWW3!X14) | ¬¬IF(ISBLANK(DPWW3!Y14),"",DPWW3!Y14) | ¬¬IF(ISBLANK(DPWW3!Z14),"",DPWW3!Z14) | ¬¬IF(ISBLANK(DPWW3!AA14),"",DPWW3!AA14) | ¬¬IF(ISBLANK(DPWW3!AB14),"",DPWW3!AB14) | ¬¬IF(ISBLANK(DPWW3!AC14),"",DPWW3!AC14) | ¬¬IF(ISBLANK(DPWW3!AD14),"",DPWW3!AD14) | ¬¬IF(ISBLANK(DPWW3!AE14),"",DPWW3!AE14) | ¬¬IF(ISBLANK(DPWW3!AF14),"",DPWW3!AF14) | ¬¬IF(ISBLANK(DPWW3!AG14),"",DPWW3!AG14)
¬¬A729 | ¬¬IF(ISBLANK(DPWW3!HU14),"",DPWW3!HU14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI14),"",DPWW3!AI14) | ¬¬IF(ISBLANK(DPWW3!AJ14),"",DPWW3!AJ14) | ¬¬IF(ISBLANK(DPWW3!AK14),"",DPWW3!AK14) | ¬¬IF(ISBLANK(DPWW3!AL14),"",DPWW3!AL14) | ¬¬IF(ISBLANK(DPWW3!AM14),"",DPWW3!AM14) | ¬¬IF(ISBLANK(DPWW3!AN14),"",DPWW3!AN14) | ¬¬IF(ISBLANK(DPWW3!AO14),"",DPWW3!AO14) | ¬¬IF(ISBLANK(DPWW3!AP14),"",DPWW3!AP14) | ¬¬IF(ISBLANK(DPWW3!AQ14),"",DPWW3!AQ14) | ¬¬IF(ISBLANK(DPWW3!AR14),"",DPWW3!AR14) | ¬¬IF(ISBLANK(DPWW3!AS14),"",DPWW3!AS14) | ¬¬IF(ISBLANK(DPWW3!AT14),"",DPWW3!AT14) | ¬¬IF(ISBLANK(DPWW3!AU14),"",DPWW3!AU14) | ¬¬IF(ISBLANK(DPWW3!AV14),"",DPWW3!AV14) | ¬¬IF(ISBLANK(DPWW3!AW14),"",DPWW3!AW14) | ¬¬IF(ISBLANK(DPWW3!AX14),"",DPWW3!AX14) | ¬¬IF(ISBLANK(DPWW3!AY14),"",DPWW3!AY14) | ¬¬IF(ISBLANK(DPWW3!AZ14),"",DPWW3!AZ14) | ¬¬IF(ISBLANK(DPWW3!BA14),"",DPWW3!BA14) | ¬¬IF(ISBLANK(DPWW3!BB14),"",DPWW3!BB14) | ¬¬IF(ISBLANK(DPWW3!BC14),"",DPWW3!BC14)
¬¬A730 | ¬¬IF(ISBLANK(DPWW3!IQ14),"",DPWW3!IQ14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE14),"",DPWW3!BE14) | ¬¬IF(ISBLANK(DPWW3!BF14),"",DPWW3!BF14) | ¬¬IF(ISBLANK(DPWW3!BG14),"",DPWW3!BG14) | ¬¬IF(ISBLANK(DPWW3!BH14),"",DPWW3!BH14) | ¬¬IF(ISBLANK(DPWW3!BI14),"",DPWW3!BI14) | ¬¬IF(ISBLANK(DPWW3!BJ14),"",DPWW3!BJ14) | ¬¬IF(ISBLANK(DPWW3!BK14),"",DPWW3!BK14) | ¬¬IF(ISBLANK(DPWW3!BL14),"",DPWW3!BL14) | ¬¬IF(ISBLANK(DPWW3!BM14),"",DPWW3!BM14) | ¬¬IF(ISBLANK(DPWW3!BN14),"",DPWW3!BN14) | ¬¬IF(ISBLANK(DPWW3!BO14),"",DPWW3!BO14) | ¬¬IF(ISBLANK(DPWW3!BP14),"",DPWW3!BP14) | ¬¬IF(ISBLANK(DPWW3!BQ14),"",DPWW3!BQ14) | ¬¬IF(ISBLANK(DPWW3!BR14),"",DPWW3!BR14) | ¬¬IF(ISBLANK(DPWW3!BS14),"",DPWW3!BS14) | ¬¬IF(ISBLANK(DPWW3!BT14),"",DPWW3!BT14) | ¬¬IF(ISBLANK(DPWW3!BU14),"",DPWW3!BU14) | ¬¬IF(ISBLANK(DPWW3!BV14),"",DPWW3!BV14) | ¬¬IF(ISBLANK(DPWW3!BW14),"",DPWW3!BW14) | ¬¬IF(ISBLANK(DPWW3!BX14),"",DPWW3!BX14) | ¬¬IF(ISBLANK(DPWW3!BY14),"",DPWW3!BY14)
¬¬A731 | ¬¬IF(ISBLANK(DPWW3!JM14),"",DPWW3!JM14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA14),"",DPWW3!CA14) | ¬¬IF(ISBLANK(DPWW3!CB14),"",DPWW3!CB14) | ¬¬IF(ISBLANK(DPWW3!CC14),"",DPWW3!CC14) | ¬¬IF(ISBLANK(DPWW3!CD14),"",DPWW3!CD14) | ¬¬IF(ISBLANK(DPWW3!CE14),"",DPWW3!CE14) | ¬¬IF(ISBLANK(DPWW3!CF14),"",DPWW3!CF14) | ¬¬IF(ISBLANK(DPWW3!CG14),"",DPWW3!CG14) | ¬¬IF(ISBLANK(DPWW3!CH14),"",DPWW3!CH14) | ¬¬IF(ISBLANK(DPWW3!CI14),"",DPWW3!CI14) | ¬¬IF(ISBLANK(DPWW3!CJ14),"",DPWW3!CJ14) | ¬¬IF(ISBLANK(DPWW3!CK14),"",DPWW3!CK14) | ¬¬IF(ISBLANK(DPWW3!CL14),"",DPWW3!CL14) | ¬¬IF(ISBLANK(DPWW3!CM14),"",DPWW3!CM14) | ¬¬IF(ISBLANK(DPWW3!CN14),"",DPWW3!CN14) | ¬¬IF(ISBLANK(DPWW3!CO14),"",DPWW3!CO14) | ¬¬IF(ISBLANK(DPWW3!CP14),"",DPWW3!CP14) | ¬¬IF(ISBLANK(DPWW3!CQ14),"",DPWW3!CQ14) | ¬¬IF(ISBLANK(DPWW3!CR14),"",DPWW3!CR14) | ¬¬IF(ISBLANK(DPWW3!CS14),"",DPWW3!CS14) | ¬¬IF(ISBLANK(DPWW3!CT14),"",DPWW3!CT14) | ¬¬IF(ISBLANK(DPWW3!CU14),"",DPWW3!CU14)
¬¬A732 | ¬¬IF(ISBLANK(DPWW3!KI14),"",DPWW3!KI14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW14),"",DPWW3!CW14) | ¬¬IF(ISBLANK(DPWW3!CX14),"",DPWW3!CX14) | ¬¬IF(ISBLANK(DPWW3!CY14),"",DPWW3!CY14) | ¬¬IF(ISBLANK(DPWW3!CZ14),"",DPWW3!CZ14) | ¬¬IF(ISBLANK(DPWW3!DA14),"",DPWW3!DA14) | ¬¬IF(ISBLANK(DPWW3!DB14),"",DPWW3!DB14) | ¬¬IF(ISBLANK(DPWW3!DC14),"",DPWW3!DC14) | ¬¬IF(ISBLANK(DPWW3!DD14),"",DPWW3!DD14) | ¬¬IF(ISBLANK(DPWW3!DE14),"",DPWW3!DE14) | ¬¬IF(ISBLANK(DPWW3!DF14),"",DPWW3!DF14) | ¬¬IF(ISBLANK(DPWW3!DG14),"",DPWW3!DG14) | ¬¬IF(ISBLANK(DPWW3!DH14),"",DPWW3!DH14) | ¬¬IF(ISBLANK(DPWW3!DI14),"",DPWW3!DI14) | ¬¬IF(ISBLANK(DPWW3!DJ14),"",DPWW3!DJ14) | ¬¬IF(ISBLANK(DPWW3!DK14),"",DPWW3!DK14) | ¬¬IF(ISBLANK(DPWW3!DL14),"",DPWW3!DL14) | ¬¬IF(ISBLANK(DPWW3!DM14),"",DPWW3!DM14) | ¬¬IF(ISBLANK(DPWW3!DN14),"",DPWW3!DN14) | ¬¬IF(ISBLANK(DPWW3!DO14),"",DPWW3!DO14) | ¬¬IF(ISBLANK(DPWW3!DP14),"",DPWW3!DP14) | ¬¬IF(ISBLANK(DPWW3!DQ14),"",DPWW3!DQ14)
¬¬A733 | ¬¬IF(ISBLANK(DPWW3!LE14),"",DPWW3!LE14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS14),"",DPWW3!DS14) | ¬¬IF(ISBLANK(DPWW3!DT14),"",DPWW3!DT14) | ¬¬IF(ISBLANK(DPWW3!DU14),"",DPWW3!DU14) | ¬¬IF(ISBLANK(DPWW3!DV14),"",DPWW3!DV14) | ¬¬IF(ISBLANK(DPWW3!DW14),"",DPWW3!DW14) | ¬¬IF(ISBLANK(DPWW3!DX14),"",DPWW3!DX14) | ¬¬IF(ISBLANK(DPWW3!DY14),"",DPWW3!DY14) | ¬¬IF(ISBLANK(DPWW3!DZ14),"",DPWW3!DZ14) | ¬¬IF(ISBLANK(DPWW3!EA14),"",DPWW3!EA14) | ¬¬IF(ISBLANK(DPWW3!EB14),"",DPWW3!EB14) | ¬¬IF(ISBLANK(DPWW3!EC14),"",DPWW3!EC14) | ¬¬IF(ISBLANK(DPWW3!ED14),"",DPWW3!ED14) | ¬¬IF(ISBLANK(DPWW3!EE14),"",DPWW3!EE14) | ¬¬IF(ISBLANK(DPWW3!EF14),"",DPWW3!EF14) | ¬¬IF(ISBLANK(DPWW3!EG14),"",DPWW3!EG14) | ¬¬IF(ISBLANK(DPWW3!EH14),"",DPWW3!EH14) | ¬¬IF(ISBLANK(DPWW3!EI14),"",DPWW3!EI14) | ¬¬IF(ISBLANK(DPWW3!EJ14),"",DPWW3!EJ14) | ¬¬IF(ISBLANK(DPWW3!EK14),"",DPWW3!EK14) | ¬¬IF(ISBLANK(DPWW3!EL14),"",DPWW3!EL14) | ¬¬IF(ISBLANK(DPWW3!EM14),"",DPWW3!EM14)
¬¬A734 | ¬¬IF(ISBLANK(DPWW3!MA14),"",DPWW3!MA14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO14),"",DPWW3!EO14) | ¬¬IF(ISBLANK(DPWW3!EP14),"",DPWW3!EP14) | ¬¬IF(ISBLANK(DPWW3!EQ14),"",DPWW3!EQ14) | ¬¬IF(ISBLANK(DPWW3!ER14),"",DPWW3!ER14) | ¬¬IF(ISBLANK(DPWW3!ES14),"",DPWW3!ES14) | ¬¬IF(ISBLANK(DPWW3!ET14),"",DPWW3!ET14) | ¬¬IF(ISBLANK(DPWW3!EU14),"",DPWW3!EU14) | ¬¬IF(ISBLANK(DPWW3!EV14),"",DPWW3!EV14) | ¬¬IF(ISBLANK(DPWW3!EW14),"",DPWW3!EW14) | ¬¬IF(ISBLANK(DPWW3!EX14),"",DPWW3!EX14) | ¬¬IF(ISBLANK(DPWW3!EY14),"",DPWW3!EY14) | ¬¬IF(ISBLANK(DPWW3!EZ14),"",DPWW3!EZ14) | ¬¬IF(ISBLANK(DPWW3!FA14),"",DPWW3!FA14) | ¬¬IF(ISBLANK(DPWW3!FB14),"",DPWW3!FB14) | ¬¬IF(ISBLANK(DPWW3!FC14),"",DPWW3!FC14) | ¬¬IF(ISBLANK(DPWW3!FD14),"",DPWW3!FD14) | ¬¬IF(ISBLANK(DPWW3!FE14),"",DPWW3!FE14) | ¬¬IF(ISBLANK(DPWW3!FF14),"",DPWW3!FF14) | ¬¬IF(ISBLANK(DPWW3!FG14),"",DPWW3!FG14) | ¬¬IF(ISBLANK(DPWW3!FH14),"",DPWW3!FH14) | ¬¬IF(ISBLANK(DPWW3!FI14),"",DPWW3!FI14)
¬¬A735 | ¬¬IF(ISBLANK(DPWW3!MW14),"",DPWW3!MW14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK14),"",DPWW3!FK14) | ¬¬IF(ISBLANK(DPWW3!FL14),"",DPWW3!FL14) | ¬¬IF(ISBLANK(DPWW3!FM14),"",DPWW3!FM14) | ¬¬IF(ISBLANK(DPWW3!FN14),"",DPWW3!FN14) | ¬¬IF(ISBLANK(DPWW3!FO14),"",DPWW3!FO14) | ¬¬IF(ISBLANK(DPWW3!FP14),"",DPWW3!FP14) | ¬¬IF(ISBLANK(DPWW3!FQ14),"",DPWW3!FQ14) | ¬¬IF(ISBLANK(DPWW3!FR14),"",DPWW3!FR14) | ¬¬IF(ISBLANK(DPWW3!FS14),"",DPWW3!FS14) | ¬¬IF(ISBLANK(DPWW3!FT14),"",DPWW3!FT14) | ¬¬IF(ISBLANK(DPWW3!FU14),"",DPWW3!FU14) | ¬¬IF(ISBLANK(DPWW3!FV14),"",DPWW3!FV14) | ¬¬IF(ISBLANK(DPWW3!FW14),"",DPWW3!FW14) | ¬¬IF(ISBLANK(DPWW3!FX14),"",DPWW3!FX14) | ¬¬IF(ISBLANK(DPWW3!FY14),"",DPWW3!FY14) | ¬¬IF(ISBLANK(DPWW3!FZ14),"",DPWW3!FZ14) | ¬¬IF(ISBLANK(DPWW3!GA14),"",DPWW3!GA14) | ¬¬IF(ISBLANK(DPWW3!GB14),"",DPWW3!GB14) | ¬¬IF(ISBLANK(DPWW3!GC14),"",DPWW3!GC14) | ¬¬IF(ISBLANK(DPWW3!GD14),"",DPWW3!GD14) | ¬¬IF(ISBLANK(DPWW3!GE14),"",DPWW3!GE14)
¬¬A736 | ¬¬IF(ISBLANK(DPWW3!NS14),"",DPWW3!NS14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GG14),"",DPWW3!GG14)
¬¬A737 | ¬¬IF(ISBLANK(DPWW3!NT14),"",DPWW3!NT14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GH14),"",DPWW3!GH14)
¬¬A738 | ¬¬IF(ISBLANK(DPWW3!NU14),"",DPWW3!NU14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GI14),"",DPWW3!GI14)
¬¬A739 | ¬¬IF(ISBLANK(DPWW3!NV14),"",DPWW3!NV14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ14),"",DPWW3!GJ14)
¬¬A740 | ¬¬IF(ISBLANK(DPWW3!NW14),"",DPWW3!NW14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GK14),"",DPWW3!GK14)
¬¬A741 | ¬¬IF(ISBLANK(DPWW3!NX14),"",DPWW3!NX14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GL14),"",DPWW3!GL14)
¬¬A742 | ¬¬IF(ISBLANK(DPWW3!NY14),"",DPWW3!NY14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GM14),"",DPWW3!GM14)
¬¬A743 | ¬¬IF(ISBLANK(DPWW3!NZ14),"",DPWW3!NZ14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GN14),"",DPWW3!GN14)
¬¬A744 | ¬¬IF(ISBLANK(DPWW3!OA14),"",DPWW3!OA14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GO14),"",DPWW3!GO14)
¬¬A745 | ¬¬IF(ISBLANK(DPWW3!OB14),"",DPWW3!OB14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GP14),"",DPWW3!GP14)
¬¬A746 | ¬¬IF(ISBLANK(DPWW3!OC14),"",DPWW3!OC14) | ¬¬DPWW3!F14 & "," & DPWW3!G14 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H14),"",DPWW3!H14) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ14),"",DPWW3!GQ14)
¬¬A747 | ¬¬IF(ISBLANK(DPWW3!GW15),"",DPWW3!GW15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!K15),"",DPWW3!K15)
¬¬A748 | ¬¬IF(ISBLANK(DPWW3!GY15),"",DPWW3!GY15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M15),"",DPWW3!M15) | ¬¬IF(ISBLANK(DPWW3!N15),"",DPWW3!N15) | ¬¬IF(ISBLANK(DPWW3!O15),"",DPWW3!O15) | ¬¬IF(ISBLANK(DPWW3!P15),"",DPWW3!P15) | ¬¬IF(ISBLANK(DPWW3!Q15),"",DPWW3!Q15) | ¬¬IF(ISBLANK(DPWW3!R15),"",DPWW3!R15) | ¬¬IF(ISBLANK(DPWW3!S15),"",DPWW3!S15) | ¬¬IF(ISBLANK(DPWW3!T15),"",DPWW3!T15) | ¬¬IF(ISBLANK(DPWW3!U15),"",DPWW3!U15) | ¬¬IF(ISBLANK(DPWW3!V15),"",DPWW3!V15) | ¬¬IF(ISBLANK(DPWW3!W15),"",DPWW3!W15) | ¬¬IF(ISBLANK(DPWW3!X15),"",DPWW3!X15) | ¬¬IF(ISBLANK(DPWW3!Y15),"",DPWW3!Y15) | ¬¬IF(ISBLANK(DPWW3!Z15),"",DPWW3!Z15) | ¬¬IF(ISBLANK(DPWW3!AA15),"",DPWW3!AA15) | ¬¬IF(ISBLANK(DPWW3!AB15),"",DPWW3!AB15) | ¬¬IF(ISBLANK(DPWW3!AC15),"",DPWW3!AC15) | ¬¬IF(ISBLANK(DPWW3!AD15),"",DPWW3!AD15) | ¬¬IF(ISBLANK(DPWW3!AE15),"",DPWW3!AE15) | ¬¬IF(ISBLANK(DPWW3!AF15),"",DPWW3!AF15) | ¬¬IF(ISBLANK(DPWW3!AG15),"",DPWW3!AG15)
¬¬A749 | ¬¬IF(ISBLANK(DPWW3!HU15),"",DPWW3!HU15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI15),"",DPWW3!AI15) | ¬¬IF(ISBLANK(DPWW3!AJ15),"",DPWW3!AJ15) | ¬¬IF(ISBLANK(DPWW3!AK15),"",DPWW3!AK15) | ¬¬IF(ISBLANK(DPWW3!AL15),"",DPWW3!AL15) | ¬¬IF(ISBLANK(DPWW3!AM15),"",DPWW3!AM15) | ¬¬IF(ISBLANK(DPWW3!AN15),"",DPWW3!AN15) | ¬¬IF(ISBLANK(DPWW3!AO15),"",DPWW3!AO15) | ¬¬IF(ISBLANK(DPWW3!AP15),"",DPWW3!AP15) | ¬¬IF(ISBLANK(DPWW3!AQ15),"",DPWW3!AQ15) | ¬¬IF(ISBLANK(DPWW3!AR15),"",DPWW3!AR15) | ¬¬IF(ISBLANK(DPWW3!AS15),"",DPWW3!AS15) | ¬¬IF(ISBLANK(DPWW3!AT15),"",DPWW3!AT15) | ¬¬IF(ISBLANK(DPWW3!AU15),"",DPWW3!AU15) | ¬¬IF(ISBLANK(DPWW3!AV15),"",DPWW3!AV15) | ¬¬IF(ISBLANK(DPWW3!AW15),"",DPWW3!AW15) | ¬¬IF(ISBLANK(DPWW3!AX15),"",DPWW3!AX15) | ¬¬IF(ISBLANK(DPWW3!AY15),"",DPWW3!AY15) | ¬¬IF(ISBLANK(DPWW3!AZ15),"",DPWW3!AZ15) | ¬¬IF(ISBLANK(DPWW3!BA15),"",DPWW3!BA15) | ¬¬IF(ISBLANK(DPWW3!BB15),"",DPWW3!BB15) | ¬¬IF(ISBLANK(DPWW3!BC15),"",DPWW3!BC15)
¬¬A750 | ¬¬IF(ISBLANK(DPWW3!IQ15),"",DPWW3!IQ15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE15),"",DPWW3!BE15) | ¬¬IF(ISBLANK(DPWW3!BF15),"",DPWW3!BF15) | ¬¬IF(ISBLANK(DPWW3!BG15),"",DPWW3!BG15) | ¬¬IF(ISBLANK(DPWW3!BH15),"",DPWW3!BH15) | ¬¬IF(ISBLANK(DPWW3!BI15),"",DPWW3!BI15) | ¬¬IF(ISBLANK(DPWW3!BJ15),"",DPWW3!BJ15) | ¬¬IF(ISBLANK(DPWW3!BK15),"",DPWW3!BK15) | ¬¬IF(ISBLANK(DPWW3!BL15),"",DPWW3!BL15) | ¬¬IF(ISBLANK(DPWW3!BM15),"",DPWW3!BM15) | ¬¬IF(ISBLANK(DPWW3!BN15),"",DPWW3!BN15) | ¬¬IF(ISBLANK(DPWW3!BO15),"",DPWW3!BO15) | ¬¬IF(ISBLANK(DPWW3!BP15),"",DPWW3!BP15) | ¬¬IF(ISBLANK(DPWW3!BQ15),"",DPWW3!BQ15) | ¬¬IF(ISBLANK(DPWW3!BR15),"",DPWW3!BR15) | ¬¬IF(ISBLANK(DPWW3!BS15),"",DPWW3!BS15) | ¬¬IF(ISBLANK(DPWW3!BT15),"",DPWW3!BT15) | ¬¬IF(ISBLANK(DPWW3!BU15),"",DPWW3!BU15) | ¬¬IF(ISBLANK(DPWW3!BV15),"",DPWW3!BV15) | ¬¬IF(ISBLANK(DPWW3!BW15),"",DPWW3!BW15) | ¬¬IF(ISBLANK(DPWW3!BX15),"",DPWW3!BX15) | ¬¬IF(ISBLANK(DPWW3!BY15),"",DPWW3!BY15)
¬¬A751 | ¬¬IF(ISBLANK(DPWW3!JM15),"",DPWW3!JM15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA15),"",DPWW3!CA15) | ¬¬IF(ISBLANK(DPWW3!CB15),"",DPWW3!CB15) | ¬¬IF(ISBLANK(DPWW3!CC15),"",DPWW3!CC15) | ¬¬IF(ISBLANK(DPWW3!CD15),"",DPWW3!CD15) | ¬¬IF(ISBLANK(DPWW3!CE15),"",DPWW3!CE15) | ¬¬IF(ISBLANK(DPWW3!CF15),"",DPWW3!CF15) | ¬¬IF(ISBLANK(DPWW3!CG15),"",DPWW3!CG15) | ¬¬IF(ISBLANK(DPWW3!CH15),"",DPWW3!CH15) | ¬¬IF(ISBLANK(DPWW3!CI15),"",DPWW3!CI15) | ¬¬IF(ISBLANK(DPWW3!CJ15),"",DPWW3!CJ15) | ¬¬IF(ISBLANK(DPWW3!CK15),"",DPWW3!CK15) | ¬¬IF(ISBLANK(DPWW3!CL15),"",DPWW3!CL15) | ¬¬IF(ISBLANK(DPWW3!CM15),"",DPWW3!CM15) | ¬¬IF(ISBLANK(DPWW3!CN15),"",DPWW3!CN15) | ¬¬IF(ISBLANK(DPWW3!CO15),"",DPWW3!CO15) | ¬¬IF(ISBLANK(DPWW3!CP15),"",DPWW3!CP15) | ¬¬IF(ISBLANK(DPWW3!CQ15),"",DPWW3!CQ15) | ¬¬IF(ISBLANK(DPWW3!CR15),"",DPWW3!CR15) | ¬¬IF(ISBLANK(DPWW3!CS15),"",DPWW3!CS15) | ¬¬IF(ISBLANK(DPWW3!CT15),"",DPWW3!CT15) | ¬¬IF(ISBLANK(DPWW3!CU15),"",DPWW3!CU15)
¬¬A752 | ¬¬IF(ISBLANK(DPWW3!KI15),"",DPWW3!KI15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW15),"",DPWW3!CW15) | ¬¬IF(ISBLANK(DPWW3!CX15),"",DPWW3!CX15) | ¬¬IF(ISBLANK(DPWW3!CY15),"",DPWW3!CY15) | ¬¬IF(ISBLANK(DPWW3!CZ15),"",DPWW3!CZ15) | ¬¬IF(ISBLANK(DPWW3!DA15),"",DPWW3!DA15) | ¬¬IF(ISBLANK(DPWW3!DB15),"",DPWW3!DB15) | ¬¬IF(ISBLANK(DPWW3!DC15),"",DPWW3!DC15) | ¬¬IF(ISBLANK(DPWW3!DD15),"",DPWW3!DD15) | ¬¬IF(ISBLANK(DPWW3!DE15),"",DPWW3!DE15) | ¬¬IF(ISBLANK(DPWW3!DF15),"",DPWW3!DF15) | ¬¬IF(ISBLANK(DPWW3!DG15),"",DPWW3!DG15) | ¬¬IF(ISBLANK(DPWW3!DH15),"",DPWW3!DH15) | ¬¬IF(ISBLANK(DPWW3!DI15),"",DPWW3!DI15) | ¬¬IF(ISBLANK(DPWW3!DJ15),"",DPWW3!DJ15) | ¬¬IF(ISBLANK(DPWW3!DK15),"",DPWW3!DK15) | ¬¬IF(ISBLANK(DPWW3!DL15),"",DPWW3!DL15) | ¬¬IF(ISBLANK(DPWW3!DM15),"",DPWW3!DM15) | ¬¬IF(ISBLANK(DPWW3!DN15),"",DPWW3!DN15) | ¬¬IF(ISBLANK(DPWW3!DO15),"",DPWW3!DO15) | ¬¬IF(ISBLANK(DPWW3!DP15),"",DPWW3!DP15) | ¬¬IF(ISBLANK(DPWW3!DQ15),"",DPWW3!DQ15)
¬¬A753 | ¬¬IF(ISBLANK(DPWW3!LE15),"",DPWW3!LE15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS15),"",DPWW3!DS15) | ¬¬IF(ISBLANK(DPWW3!DT15),"",DPWW3!DT15) | ¬¬IF(ISBLANK(DPWW3!DU15),"",DPWW3!DU15) | ¬¬IF(ISBLANK(DPWW3!DV15),"",DPWW3!DV15) | ¬¬IF(ISBLANK(DPWW3!DW15),"",DPWW3!DW15) | ¬¬IF(ISBLANK(DPWW3!DX15),"",DPWW3!DX15) | ¬¬IF(ISBLANK(DPWW3!DY15),"",DPWW3!DY15) | ¬¬IF(ISBLANK(DPWW3!DZ15),"",DPWW3!DZ15) | ¬¬IF(ISBLANK(DPWW3!EA15),"",DPWW3!EA15) | ¬¬IF(ISBLANK(DPWW3!EB15),"",DPWW3!EB15) | ¬¬IF(ISBLANK(DPWW3!EC15),"",DPWW3!EC15) | ¬¬IF(ISBLANK(DPWW3!ED15),"",DPWW3!ED15) | ¬¬IF(ISBLANK(DPWW3!EE15),"",DPWW3!EE15) | ¬¬IF(ISBLANK(DPWW3!EF15),"",DPWW3!EF15) | ¬¬IF(ISBLANK(DPWW3!EG15),"",DPWW3!EG15) | ¬¬IF(ISBLANK(DPWW3!EH15),"",DPWW3!EH15) | ¬¬IF(ISBLANK(DPWW3!EI15),"",DPWW3!EI15) | ¬¬IF(ISBLANK(DPWW3!EJ15),"",DPWW3!EJ15) | ¬¬IF(ISBLANK(DPWW3!EK15),"",DPWW3!EK15) | ¬¬IF(ISBLANK(DPWW3!EL15),"",DPWW3!EL15) | ¬¬IF(ISBLANK(DPWW3!EM15),"",DPWW3!EM15)
¬¬A754 | ¬¬IF(ISBLANK(DPWW3!MA15),"",DPWW3!MA15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO15),"",DPWW3!EO15) | ¬¬IF(ISBLANK(DPWW3!EP15),"",DPWW3!EP15) | ¬¬IF(ISBLANK(DPWW3!EQ15),"",DPWW3!EQ15) | ¬¬IF(ISBLANK(DPWW3!ER15),"",DPWW3!ER15) | ¬¬IF(ISBLANK(DPWW3!ES15),"",DPWW3!ES15) | ¬¬IF(ISBLANK(DPWW3!ET15),"",DPWW3!ET15) | ¬¬IF(ISBLANK(DPWW3!EU15),"",DPWW3!EU15) | ¬¬IF(ISBLANK(DPWW3!EV15),"",DPWW3!EV15) | ¬¬IF(ISBLANK(DPWW3!EW15),"",DPWW3!EW15) | ¬¬IF(ISBLANK(DPWW3!EX15),"",DPWW3!EX15) | ¬¬IF(ISBLANK(DPWW3!EY15),"",DPWW3!EY15) | ¬¬IF(ISBLANK(DPWW3!EZ15),"",DPWW3!EZ15) | ¬¬IF(ISBLANK(DPWW3!FA15),"",DPWW3!FA15) | ¬¬IF(ISBLANK(DPWW3!FB15),"",DPWW3!FB15) | ¬¬IF(ISBLANK(DPWW3!FC15),"",DPWW3!FC15) | ¬¬IF(ISBLANK(DPWW3!FD15),"",DPWW3!FD15) | ¬¬IF(ISBLANK(DPWW3!FE15),"",DPWW3!FE15) | ¬¬IF(ISBLANK(DPWW3!FF15),"",DPWW3!FF15) | ¬¬IF(ISBLANK(DPWW3!FG15),"",DPWW3!FG15) | ¬¬IF(ISBLANK(DPWW3!FH15),"",DPWW3!FH15) | ¬¬IF(ISBLANK(DPWW3!FI15),"",DPWW3!FI15)
¬¬A755 | ¬¬IF(ISBLANK(DPWW3!MW15),"",DPWW3!MW15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK15),"",DPWW3!FK15) | ¬¬IF(ISBLANK(DPWW3!FL15),"",DPWW3!FL15) | ¬¬IF(ISBLANK(DPWW3!FM15),"",DPWW3!FM15) | ¬¬IF(ISBLANK(DPWW3!FN15),"",DPWW3!FN15) | ¬¬IF(ISBLANK(DPWW3!FO15),"",DPWW3!FO15) | ¬¬IF(ISBLANK(DPWW3!FP15),"",DPWW3!FP15) | ¬¬IF(ISBLANK(DPWW3!FQ15),"",DPWW3!FQ15) | ¬¬IF(ISBLANK(DPWW3!FR15),"",DPWW3!FR15) | ¬¬IF(ISBLANK(DPWW3!FS15),"",DPWW3!FS15) | ¬¬IF(ISBLANK(DPWW3!FT15),"",DPWW3!FT15) | ¬¬IF(ISBLANK(DPWW3!FU15),"",DPWW3!FU15) | ¬¬IF(ISBLANK(DPWW3!FV15),"",DPWW3!FV15) | ¬¬IF(ISBLANK(DPWW3!FW15),"",DPWW3!FW15) | ¬¬IF(ISBLANK(DPWW3!FX15),"",DPWW3!FX15) | ¬¬IF(ISBLANK(DPWW3!FY15),"",DPWW3!FY15) | ¬¬IF(ISBLANK(DPWW3!FZ15),"",DPWW3!FZ15) | ¬¬IF(ISBLANK(DPWW3!GA15),"",DPWW3!GA15) | ¬¬IF(ISBLANK(DPWW3!GB15),"",DPWW3!GB15) | ¬¬IF(ISBLANK(DPWW3!GC15),"",DPWW3!GC15) | ¬¬IF(ISBLANK(DPWW3!GD15),"",DPWW3!GD15) | ¬¬IF(ISBLANK(DPWW3!GE15),"",DPWW3!GE15)
¬¬A756 | ¬¬IF(ISBLANK(DPWW3!NS15),"",DPWW3!NS15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GG15),"",DPWW3!GG15)
¬¬A757 | ¬¬IF(ISBLANK(DPWW3!NT15),"",DPWW3!NT15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GH15),"",DPWW3!GH15)
¬¬A758 | ¬¬IF(ISBLANK(DPWW3!NU15),"",DPWW3!NU15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GI15),"",DPWW3!GI15)
¬¬A759 | ¬¬IF(ISBLANK(DPWW3!NV15),"",DPWW3!NV15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ15),"",DPWW3!GJ15)
¬¬A760 | ¬¬IF(ISBLANK(DPWW3!NW15),"",DPWW3!NW15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GK15),"",DPWW3!GK15)
¬¬A761 | ¬¬IF(ISBLANK(DPWW3!NX15),"",DPWW3!NX15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GL15),"",DPWW3!GL15)
¬¬A762 | ¬¬IF(ISBLANK(DPWW3!NY15),"",DPWW3!NY15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GM15),"",DPWW3!GM15)
¬¬A763 | ¬¬IF(ISBLANK(DPWW3!NZ15),"",DPWW3!NZ15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GN15),"",DPWW3!GN15)
¬¬A764 | ¬¬IF(ISBLANK(DPWW3!OA15),"",DPWW3!OA15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GO15),"",DPWW3!GO15)
¬¬A765 | ¬¬IF(ISBLANK(DPWW3!OB15),"",DPWW3!OB15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GP15),"",DPWW3!GP15)
¬¬A766 | ¬¬IF(ISBLANK(DPWW3!OC15),"",DPWW3!OC15) | ¬¬DPWW3!F15 & "," & DPWW3!G15 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H15),"",DPWW3!H15) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ15),"",DPWW3!GQ15)
¬¬A767 | ¬¬IF(ISBLANK(DPWW3!GW16),"",DPWW3!GW16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!K16),"",DPWW3!K16)
¬¬A768 | ¬¬IF(ISBLANK(DPWW3!GY16),"",DPWW3!GY16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M16),"",DPWW3!M16) | ¬¬IF(ISBLANK(DPWW3!N16),"",DPWW3!N16) | ¬¬IF(ISBLANK(DPWW3!O16),"",DPWW3!O16) | ¬¬IF(ISBLANK(DPWW3!P16),"",DPWW3!P16) | ¬¬IF(ISBLANK(DPWW3!Q16),"",DPWW3!Q16) | ¬¬IF(ISBLANK(DPWW3!R16),"",DPWW3!R16) | ¬¬IF(ISBLANK(DPWW3!S16),"",DPWW3!S16) | ¬¬IF(ISBLANK(DPWW3!T16),"",DPWW3!T16) | ¬¬IF(ISBLANK(DPWW3!U16),"",DPWW3!U16) | ¬¬IF(ISBLANK(DPWW3!V16),"",DPWW3!V16) | ¬¬IF(ISBLANK(DPWW3!W16),"",DPWW3!W16) | ¬¬IF(ISBLANK(DPWW3!X16),"",DPWW3!X16) | ¬¬IF(ISBLANK(DPWW3!Y16),"",DPWW3!Y16) | ¬¬IF(ISBLANK(DPWW3!Z16),"",DPWW3!Z16) | ¬¬IF(ISBLANK(DPWW3!AA16),"",DPWW3!AA16) | ¬¬IF(ISBLANK(DPWW3!AB16),"",DPWW3!AB16) | ¬¬IF(ISBLANK(DPWW3!AC16),"",DPWW3!AC16) | ¬¬IF(ISBLANK(DPWW3!AD16),"",DPWW3!AD16) | ¬¬IF(ISBLANK(DPWW3!AE16),"",DPWW3!AE16) | ¬¬IF(ISBLANK(DPWW3!AF16),"",DPWW3!AF16) | ¬¬IF(ISBLANK(DPWW3!AG16),"",DPWW3!AG16)
¬¬A769 | ¬¬IF(ISBLANK(DPWW3!HU16),"",DPWW3!HU16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI16),"",DPWW3!AI16) | ¬¬IF(ISBLANK(DPWW3!AJ16),"",DPWW3!AJ16) | ¬¬IF(ISBLANK(DPWW3!AK16),"",DPWW3!AK16) | ¬¬IF(ISBLANK(DPWW3!AL16),"",DPWW3!AL16) | ¬¬IF(ISBLANK(DPWW3!AM16),"",DPWW3!AM16) | ¬¬IF(ISBLANK(DPWW3!AN16),"",DPWW3!AN16) | ¬¬IF(ISBLANK(DPWW3!AO16),"",DPWW3!AO16) | ¬¬IF(ISBLANK(DPWW3!AP16),"",DPWW3!AP16) | ¬¬IF(ISBLANK(DPWW3!AQ16),"",DPWW3!AQ16) | ¬¬IF(ISBLANK(DPWW3!AR16),"",DPWW3!AR16) | ¬¬IF(ISBLANK(DPWW3!AS16),"",DPWW3!AS16) | ¬¬IF(ISBLANK(DPWW3!AT16),"",DPWW3!AT16) | ¬¬IF(ISBLANK(DPWW3!AU16),"",DPWW3!AU16) | ¬¬IF(ISBLANK(DPWW3!AV16),"",DPWW3!AV16) | ¬¬IF(ISBLANK(DPWW3!AW16),"",DPWW3!AW16) | ¬¬IF(ISBLANK(DPWW3!AX16),"",DPWW3!AX16) | ¬¬IF(ISBLANK(DPWW3!AY16),"",DPWW3!AY16) | ¬¬IF(ISBLANK(DPWW3!AZ16),"",DPWW3!AZ16) | ¬¬IF(ISBLANK(DPWW3!BA16),"",DPWW3!BA16) | ¬¬IF(ISBLANK(DPWW3!BB16),"",DPWW3!BB16) | ¬¬IF(ISBLANK(DPWW3!BC16),"",DPWW3!BC16)
¬¬A770 | ¬¬IF(ISBLANK(DPWW3!IQ16),"",DPWW3!IQ16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE16),"",DPWW3!BE16) | ¬¬IF(ISBLANK(DPWW3!BF16),"",DPWW3!BF16) | ¬¬IF(ISBLANK(DPWW3!BG16),"",DPWW3!BG16) | ¬¬IF(ISBLANK(DPWW3!BH16),"",DPWW3!BH16) | ¬¬IF(ISBLANK(DPWW3!BI16),"",DPWW3!BI16) | ¬¬IF(ISBLANK(DPWW3!BJ16),"",DPWW3!BJ16) | ¬¬IF(ISBLANK(DPWW3!BK16),"",DPWW3!BK16) | ¬¬IF(ISBLANK(DPWW3!BL16),"",DPWW3!BL16) | ¬¬IF(ISBLANK(DPWW3!BM16),"",DPWW3!BM16) | ¬¬IF(ISBLANK(DPWW3!BN16),"",DPWW3!BN16) | ¬¬IF(ISBLANK(DPWW3!BO16),"",DPWW3!BO16) | ¬¬IF(ISBLANK(DPWW3!BP16),"",DPWW3!BP16) | ¬¬IF(ISBLANK(DPWW3!BQ16),"",DPWW3!BQ16) | ¬¬IF(ISBLANK(DPWW3!BR16),"",DPWW3!BR16) | ¬¬IF(ISBLANK(DPWW3!BS16),"",DPWW3!BS16) | ¬¬IF(ISBLANK(DPWW3!BT16),"",DPWW3!BT16) | ¬¬IF(ISBLANK(DPWW3!BU16),"",DPWW3!BU16) | ¬¬IF(ISBLANK(DPWW3!BV16),"",DPWW3!BV16) | ¬¬IF(ISBLANK(DPWW3!BW16),"",DPWW3!BW16) | ¬¬IF(ISBLANK(DPWW3!BX16),"",DPWW3!BX16) | ¬¬IF(ISBLANK(DPWW3!BY16),"",DPWW3!BY16)
¬¬A771 | ¬¬IF(ISBLANK(DPWW3!JM16),"",DPWW3!JM16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA16),"",DPWW3!CA16) | ¬¬IF(ISBLANK(DPWW3!CB16),"",DPWW3!CB16) | ¬¬IF(ISBLANK(DPWW3!CC16),"",DPWW3!CC16) | ¬¬IF(ISBLANK(DPWW3!CD16),"",DPWW3!CD16) | ¬¬IF(ISBLANK(DPWW3!CE16),"",DPWW3!CE16) | ¬¬IF(ISBLANK(DPWW3!CF16),"",DPWW3!CF16) | ¬¬IF(ISBLANK(DPWW3!CG16),"",DPWW3!CG16) | ¬¬IF(ISBLANK(DPWW3!CH16),"",DPWW3!CH16) | ¬¬IF(ISBLANK(DPWW3!CI16),"",DPWW3!CI16) | ¬¬IF(ISBLANK(DPWW3!CJ16),"",DPWW3!CJ16) | ¬¬IF(ISBLANK(DPWW3!CK16),"",DPWW3!CK16) | ¬¬IF(ISBLANK(DPWW3!CL16),"",DPWW3!CL16) | ¬¬IF(ISBLANK(DPWW3!CM16),"",DPWW3!CM16) | ¬¬IF(ISBLANK(DPWW3!CN16),"",DPWW3!CN16) | ¬¬IF(ISBLANK(DPWW3!CO16),"",DPWW3!CO16) | ¬¬IF(ISBLANK(DPWW3!CP16),"",DPWW3!CP16) | ¬¬IF(ISBLANK(DPWW3!CQ16),"",DPWW3!CQ16) | ¬¬IF(ISBLANK(DPWW3!CR16),"",DPWW3!CR16) | ¬¬IF(ISBLANK(DPWW3!CS16),"",DPWW3!CS16) | ¬¬IF(ISBLANK(DPWW3!CT16),"",DPWW3!CT16) | ¬¬IF(ISBLANK(DPWW3!CU16),"",DPWW3!CU16)
¬¬A772 | ¬¬IF(ISBLANK(DPWW3!KI16),"",DPWW3!KI16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW16),"",DPWW3!CW16) | ¬¬IF(ISBLANK(DPWW3!CX16),"",DPWW3!CX16) | ¬¬IF(ISBLANK(DPWW3!CY16),"",DPWW3!CY16) | ¬¬IF(ISBLANK(DPWW3!CZ16),"",DPWW3!CZ16) | ¬¬IF(ISBLANK(DPWW3!DA16),"",DPWW3!DA16) | ¬¬IF(ISBLANK(DPWW3!DB16),"",DPWW3!DB16) | ¬¬IF(ISBLANK(DPWW3!DC16),"",DPWW3!DC16) | ¬¬IF(ISBLANK(DPWW3!DD16),"",DPWW3!DD16) | ¬¬IF(ISBLANK(DPWW3!DE16),"",DPWW3!DE16) | ¬¬IF(ISBLANK(DPWW3!DF16),"",DPWW3!DF16) | ¬¬IF(ISBLANK(DPWW3!DG16),"",DPWW3!DG16) | ¬¬IF(ISBLANK(DPWW3!DH16),"",DPWW3!DH16) | ¬¬IF(ISBLANK(DPWW3!DI16),"",DPWW3!DI16) | ¬¬IF(ISBLANK(DPWW3!DJ16),"",DPWW3!DJ16) | ¬¬IF(ISBLANK(DPWW3!DK16),"",DPWW3!DK16) | ¬¬IF(ISBLANK(DPWW3!DL16),"",DPWW3!DL16) | ¬¬IF(ISBLANK(DPWW3!DM16),"",DPWW3!DM16) | ¬¬IF(ISBLANK(DPWW3!DN16),"",DPWW3!DN16) | ¬¬IF(ISBLANK(DPWW3!DO16),"",DPWW3!DO16) | ¬¬IF(ISBLANK(DPWW3!DP16),"",DPWW3!DP16) | ¬¬IF(ISBLANK(DPWW3!DQ16),"",DPWW3!DQ16)
¬¬A773 | ¬¬IF(ISBLANK(DPWW3!LE16),"",DPWW3!LE16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS16),"",DPWW3!DS16) | ¬¬IF(ISBLANK(DPWW3!DT16),"",DPWW3!DT16) | ¬¬IF(ISBLANK(DPWW3!DU16),"",DPWW3!DU16) | ¬¬IF(ISBLANK(DPWW3!DV16),"",DPWW3!DV16) | ¬¬IF(ISBLANK(DPWW3!DW16),"",DPWW3!DW16) | ¬¬IF(ISBLANK(DPWW3!DX16),"",DPWW3!DX16) | ¬¬IF(ISBLANK(DPWW3!DY16),"",DPWW3!DY16) | ¬¬IF(ISBLANK(DPWW3!DZ16),"",DPWW3!DZ16) | ¬¬IF(ISBLANK(DPWW3!EA16),"",DPWW3!EA16) | ¬¬IF(ISBLANK(DPWW3!EB16),"",DPWW3!EB16) | ¬¬IF(ISBLANK(DPWW3!EC16),"",DPWW3!EC16) | ¬¬IF(ISBLANK(DPWW3!ED16),"",DPWW3!ED16) | ¬¬IF(ISBLANK(DPWW3!EE16),"",DPWW3!EE16) | ¬¬IF(ISBLANK(DPWW3!EF16),"",DPWW3!EF16) | ¬¬IF(ISBLANK(DPWW3!EG16),"",DPWW3!EG16) | ¬¬IF(ISBLANK(DPWW3!EH16),"",DPWW3!EH16) | ¬¬IF(ISBLANK(DPWW3!EI16),"",DPWW3!EI16) | ¬¬IF(ISBLANK(DPWW3!EJ16),"",DPWW3!EJ16) | ¬¬IF(ISBLANK(DPWW3!EK16),"",DPWW3!EK16) | ¬¬IF(ISBLANK(DPWW3!EL16),"",DPWW3!EL16) | ¬¬IF(ISBLANK(DPWW3!EM16),"",DPWW3!EM16)
¬¬A774 | ¬¬IF(ISBLANK(DPWW3!MA16),"",DPWW3!MA16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO16),"",DPWW3!EO16) | ¬¬IF(ISBLANK(DPWW3!EP16),"",DPWW3!EP16) | ¬¬IF(ISBLANK(DPWW3!EQ16),"",DPWW3!EQ16) | ¬¬IF(ISBLANK(DPWW3!ER16),"",DPWW3!ER16) | ¬¬IF(ISBLANK(DPWW3!ES16),"",DPWW3!ES16) | ¬¬IF(ISBLANK(DPWW3!ET16),"",DPWW3!ET16) | ¬¬IF(ISBLANK(DPWW3!EU16),"",DPWW3!EU16) | ¬¬IF(ISBLANK(DPWW3!EV16),"",DPWW3!EV16) | ¬¬IF(ISBLANK(DPWW3!EW16),"",DPWW3!EW16) | ¬¬IF(ISBLANK(DPWW3!EX16),"",DPWW3!EX16) | ¬¬IF(ISBLANK(DPWW3!EY16),"",DPWW3!EY16) | ¬¬IF(ISBLANK(DPWW3!EZ16),"",DPWW3!EZ16) | ¬¬IF(ISBLANK(DPWW3!FA16),"",DPWW3!FA16) | ¬¬IF(ISBLANK(DPWW3!FB16),"",DPWW3!FB16) | ¬¬IF(ISBLANK(DPWW3!FC16),"",DPWW3!FC16) | ¬¬IF(ISBLANK(DPWW3!FD16),"",DPWW3!FD16) | ¬¬IF(ISBLANK(DPWW3!FE16),"",DPWW3!FE16) | ¬¬IF(ISBLANK(DPWW3!FF16),"",DPWW3!FF16) | ¬¬IF(ISBLANK(DPWW3!FG16),"",DPWW3!FG16) | ¬¬IF(ISBLANK(DPWW3!FH16),"",DPWW3!FH16) | ¬¬IF(ISBLANK(DPWW3!FI16),"",DPWW3!FI16)
¬¬A775 | ¬¬IF(ISBLANK(DPWW3!MW16),"",DPWW3!MW16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK16),"",DPWW3!FK16) | ¬¬IF(ISBLANK(DPWW3!FL16),"",DPWW3!FL16) | ¬¬IF(ISBLANK(DPWW3!FM16),"",DPWW3!FM16) | ¬¬IF(ISBLANK(DPWW3!FN16),"",DPWW3!FN16) | ¬¬IF(ISBLANK(DPWW3!FO16),"",DPWW3!FO16) | ¬¬IF(ISBLANK(DPWW3!FP16),"",DPWW3!FP16) | ¬¬IF(ISBLANK(DPWW3!FQ16),"",DPWW3!FQ16) | ¬¬IF(ISBLANK(DPWW3!FR16),"",DPWW3!FR16) | ¬¬IF(ISBLANK(DPWW3!FS16),"",DPWW3!FS16) | ¬¬IF(ISBLANK(DPWW3!FT16),"",DPWW3!FT16) | ¬¬IF(ISBLANK(DPWW3!FU16),"",DPWW3!FU16) | ¬¬IF(ISBLANK(DPWW3!FV16),"",DPWW3!FV16) | ¬¬IF(ISBLANK(DPWW3!FW16),"",DPWW3!FW16) | ¬¬IF(ISBLANK(DPWW3!FX16),"",DPWW3!FX16) | ¬¬IF(ISBLANK(DPWW3!FY16),"",DPWW3!FY16) | ¬¬IF(ISBLANK(DPWW3!FZ16),"",DPWW3!FZ16) | ¬¬IF(ISBLANK(DPWW3!GA16),"",DPWW3!GA16) | ¬¬IF(ISBLANK(DPWW3!GB16),"",DPWW3!GB16) | ¬¬IF(ISBLANK(DPWW3!GC16),"",DPWW3!GC16) | ¬¬IF(ISBLANK(DPWW3!GD16),"",DPWW3!GD16) | ¬¬IF(ISBLANK(DPWW3!GE16),"",DPWW3!GE16)
¬¬A776 | ¬¬IF(ISBLANK(DPWW3!NS16),"",DPWW3!NS16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GG16),"",DPWW3!GG16)
¬¬A777 | ¬¬IF(ISBLANK(DPWW3!NT16),"",DPWW3!NT16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GH16),"",DPWW3!GH16)
¬¬A778 | ¬¬IF(ISBLANK(DPWW3!NU16),"",DPWW3!NU16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GI16),"",DPWW3!GI16)
¬¬A779 | ¬¬IF(ISBLANK(DPWW3!NV16),"",DPWW3!NV16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ16),"",DPWW3!GJ16)
¬¬A780 | ¬¬IF(ISBLANK(DPWW3!NW16),"",DPWW3!NW16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GK16),"",DPWW3!GK16)
¬¬A781 | ¬¬IF(ISBLANK(DPWW3!NX16),"",DPWW3!NX16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GL16),"",DPWW3!GL16)
¬¬A782 | ¬¬IF(ISBLANK(DPWW3!NY16),"",DPWW3!NY16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GM16),"",DPWW3!GM16)
¬¬A783 | ¬¬IF(ISBLANK(DPWW3!NZ16),"",DPWW3!NZ16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GN16),"",DPWW3!GN16)
¬¬A784 | ¬¬IF(ISBLANK(DPWW3!OA16),"",DPWW3!OA16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GO16),"",DPWW3!GO16)
¬¬A785 | ¬¬IF(ISBLANK(DPWW3!OB16),"",DPWW3!OB16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GP16),"",DPWW3!GP16)
¬¬A786 | ¬¬IF(ISBLANK(DPWW3!OC16),"",DPWW3!OC16) | ¬¬DPWW3!F16 & "," & DPWW3!G16 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H16),"",DPWW3!H16) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ16),"",DPWW3!GQ16)
¬¬A787 | ¬¬IF(ISBLANK(DPWW3!GW17),"",DPWW3!GW17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!K17),"",DPWW3!K17)
¬¬A788 | ¬¬IF(ISBLANK(DPWW3!GY17),"",DPWW3!GY17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M17),"",DPWW3!M17) | ¬¬IF(ISBLANK(DPWW3!N17),"",DPWW3!N17) | ¬¬IF(ISBLANK(DPWW3!O17),"",DPWW3!O17) | ¬¬IF(ISBLANK(DPWW3!P17),"",DPWW3!P17) | ¬¬IF(ISBLANK(DPWW3!Q17),"",DPWW3!Q17) | ¬¬IF(ISBLANK(DPWW3!R17),"",DPWW3!R17) | ¬¬IF(ISBLANK(DPWW3!S17),"",DPWW3!S17) | ¬¬IF(ISBLANK(DPWW3!T17),"",DPWW3!T17) | ¬¬IF(ISBLANK(DPWW3!U17),"",DPWW3!U17) | ¬¬IF(ISBLANK(DPWW3!V17),"",DPWW3!V17) | ¬¬IF(ISBLANK(DPWW3!W17),"",DPWW3!W17) | ¬¬IF(ISBLANK(DPWW3!X17),"",DPWW3!X17) | ¬¬IF(ISBLANK(DPWW3!Y17),"",DPWW3!Y17) | ¬¬IF(ISBLANK(DPWW3!Z17),"",DPWW3!Z17) | ¬¬IF(ISBLANK(DPWW3!AA17),"",DPWW3!AA17) | ¬¬IF(ISBLANK(DPWW3!AB17),"",DPWW3!AB17) | ¬¬IF(ISBLANK(DPWW3!AC17),"",DPWW3!AC17) | ¬¬IF(ISBLANK(DPWW3!AD17),"",DPWW3!AD17) | ¬¬IF(ISBLANK(DPWW3!AE17),"",DPWW3!AE17) | ¬¬IF(ISBLANK(DPWW3!AF17),"",DPWW3!AF17) | ¬¬IF(ISBLANK(DPWW3!AG17),"",DPWW3!AG17)
¬¬A789 | ¬¬IF(ISBLANK(DPWW3!HU17),"",DPWW3!HU17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI17),"",DPWW3!AI17) | ¬¬IF(ISBLANK(DPWW3!AJ17),"",DPWW3!AJ17) | ¬¬IF(ISBLANK(DPWW3!AK17),"",DPWW3!AK17) | ¬¬IF(ISBLANK(DPWW3!AL17),"",DPWW3!AL17) | ¬¬IF(ISBLANK(DPWW3!AM17),"",DPWW3!AM17) | ¬¬IF(ISBLANK(DPWW3!AN17),"",DPWW3!AN17) | ¬¬IF(ISBLANK(DPWW3!AO17),"",DPWW3!AO17) | ¬¬IF(ISBLANK(DPWW3!AP17),"",DPWW3!AP17) | ¬¬IF(ISBLANK(DPWW3!AQ17),"",DPWW3!AQ17) | ¬¬IF(ISBLANK(DPWW3!AR17),"",DPWW3!AR17) | ¬¬IF(ISBLANK(DPWW3!AS17),"",DPWW3!AS17) | ¬¬IF(ISBLANK(DPWW3!AT17),"",DPWW3!AT17) | ¬¬IF(ISBLANK(DPWW3!AU17),"",DPWW3!AU17) | ¬¬IF(ISBLANK(DPWW3!AV17),"",DPWW3!AV17) | ¬¬IF(ISBLANK(DPWW3!AW17),"",DPWW3!AW17) | ¬¬IF(ISBLANK(DPWW3!AX17),"",DPWW3!AX17) | ¬¬IF(ISBLANK(DPWW3!AY17),"",DPWW3!AY17) | ¬¬IF(ISBLANK(DPWW3!AZ17),"",DPWW3!AZ17) | ¬¬IF(ISBLANK(DPWW3!BA17),"",DPWW3!BA17) | ¬¬IF(ISBLANK(DPWW3!BB17),"",DPWW3!BB17) | ¬¬IF(ISBLANK(DPWW3!BC17),"",DPWW3!BC17)
¬¬A790 | ¬¬IF(ISBLANK(DPWW3!IQ17),"",DPWW3!IQ17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE17),"",DPWW3!BE17) | ¬¬IF(ISBLANK(DPWW3!BF17),"",DPWW3!BF17) | ¬¬IF(ISBLANK(DPWW3!BG17),"",DPWW3!BG17) | ¬¬IF(ISBLANK(DPWW3!BH17),"",DPWW3!BH17) | ¬¬IF(ISBLANK(DPWW3!BI17),"",DPWW3!BI17) | ¬¬IF(ISBLANK(DPWW3!BJ17),"",DPWW3!BJ17) | ¬¬IF(ISBLANK(DPWW3!BK17),"",DPWW3!BK17) | ¬¬IF(ISBLANK(DPWW3!BL17),"",DPWW3!BL17) | ¬¬IF(ISBLANK(DPWW3!BM17),"",DPWW3!BM17) | ¬¬IF(ISBLANK(DPWW3!BN17),"",DPWW3!BN17) | ¬¬IF(ISBLANK(DPWW3!BO17),"",DPWW3!BO17) | ¬¬IF(ISBLANK(DPWW3!BP17),"",DPWW3!BP17) | ¬¬IF(ISBLANK(DPWW3!BQ17),"",DPWW3!BQ17) | ¬¬IF(ISBLANK(DPWW3!BR17),"",DPWW3!BR17) | ¬¬IF(ISBLANK(DPWW3!BS17),"",DPWW3!BS17) | ¬¬IF(ISBLANK(DPWW3!BT17),"",DPWW3!BT17) | ¬¬IF(ISBLANK(DPWW3!BU17),"",DPWW3!BU17) | ¬¬IF(ISBLANK(DPWW3!BV17),"",DPWW3!BV17) | ¬¬IF(ISBLANK(DPWW3!BW17),"",DPWW3!BW17) | ¬¬IF(ISBLANK(DPWW3!BX17),"",DPWW3!BX17) | ¬¬IF(ISBLANK(DPWW3!BY17),"",DPWW3!BY17)
¬¬A791 | ¬¬IF(ISBLANK(DPWW3!JM17),"",DPWW3!JM17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA17),"",DPWW3!CA17) | ¬¬IF(ISBLANK(DPWW3!CB17),"",DPWW3!CB17) | ¬¬IF(ISBLANK(DPWW3!CC17),"",DPWW3!CC17) | ¬¬IF(ISBLANK(DPWW3!CD17),"",DPWW3!CD17) | ¬¬IF(ISBLANK(DPWW3!CE17),"",DPWW3!CE17) | ¬¬IF(ISBLANK(DPWW3!CF17),"",DPWW3!CF17) | ¬¬IF(ISBLANK(DPWW3!CG17),"",DPWW3!CG17) | ¬¬IF(ISBLANK(DPWW3!CH17),"",DPWW3!CH17) | ¬¬IF(ISBLANK(DPWW3!CI17),"",DPWW3!CI17) | ¬¬IF(ISBLANK(DPWW3!CJ17),"",DPWW3!CJ17) | ¬¬IF(ISBLANK(DPWW3!CK17),"",DPWW3!CK17) | ¬¬IF(ISBLANK(DPWW3!CL17),"",DPWW3!CL17) | ¬¬IF(ISBLANK(DPWW3!CM17),"",DPWW3!CM17) | ¬¬IF(ISBLANK(DPWW3!CN17),"",DPWW3!CN17) | ¬¬IF(ISBLANK(DPWW3!CO17),"",DPWW3!CO17) | ¬¬IF(ISBLANK(DPWW3!CP17),"",DPWW3!CP17) | ¬¬IF(ISBLANK(DPWW3!CQ17),"",DPWW3!CQ17) | ¬¬IF(ISBLANK(DPWW3!CR17),"",DPWW3!CR17) | ¬¬IF(ISBLANK(DPWW3!CS17),"",DPWW3!CS17) | ¬¬IF(ISBLANK(DPWW3!CT17),"",DPWW3!CT17) | ¬¬IF(ISBLANK(DPWW3!CU17),"",DPWW3!CU17)
¬¬A792 | ¬¬IF(ISBLANK(DPWW3!KI17),"",DPWW3!KI17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW17),"",DPWW3!CW17) | ¬¬IF(ISBLANK(DPWW3!CX17),"",DPWW3!CX17) | ¬¬IF(ISBLANK(DPWW3!CY17),"",DPWW3!CY17) | ¬¬IF(ISBLANK(DPWW3!CZ17),"",DPWW3!CZ17) | ¬¬IF(ISBLANK(DPWW3!DA17),"",DPWW3!DA17) | ¬¬IF(ISBLANK(DPWW3!DB17),"",DPWW3!DB17) | ¬¬IF(ISBLANK(DPWW3!DC17),"",DPWW3!DC17) | ¬¬IF(ISBLANK(DPWW3!DD17),"",DPWW3!DD17) | ¬¬IF(ISBLANK(DPWW3!DE17),"",DPWW3!DE17) | ¬¬IF(ISBLANK(DPWW3!DF17),"",DPWW3!DF17) | ¬¬IF(ISBLANK(DPWW3!DG17),"",DPWW3!DG17) | ¬¬IF(ISBLANK(DPWW3!DH17),"",DPWW3!DH17) | ¬¬IF(ISBLANK(DPWW3!DI17),"",DPWW3!DI17) | ¬¬IF(ISBLANK(DPWW3!DJ17),"",DPWW3!DJ17) | ¬¬IF(ISBLANK(DPWW3!DK17),"",DPWW3!DK17) | ¬¬IF(ISBLANK(DPWW3!DL17),"",DPWW3!DL17) | ¬¬IF(ISBLANK(DPWW3!DM17),"",DPWW3!DM17) | ¬¬IF(ISBLANK(DPWW3!DN17),"",DPWW3!DN17) | ¬¬IF(ISBLANK(DPWW3!DO17),"",DPWW3!DO17) | ¬¬IF(ISBLANK(DPWW3!DP17),"",DPWW3!DP17) | ¬¬IF(ISBLANK(DPWW3!DQ17),"",DPWW3!DQ17)
¬¬A793 | ¬¬IF(ISBLANK(DPWW3!LE17),"",DPWW3!LE17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS17),"",DPWW3!DS17) | ¬¬IF(ISBLANK(DPWW3!DT17),"",DPWW3!DT17) | ¬¬IF(ISBLANK(DPWW3!DU17),"",DPWW3!DU17) | ¬¬IF(ISBLANK(DPWW3!DV17),"",DPWW3!DV17) | ¬¬IF(ISBLANK(DPWW3!DW17),"",DPWW3!DW17) | ¬¬IF(ISBLANK(DPWW3!DX17),"",DPWW3!DX17) | ¬¬IF(ISBLANK(DPWW3!DY17),"",DPWW3!DY17) | ¬¬IF(ISBLANK(DPWW3!DZ17),"",DPWW3!DZ17) | ¬¬IF(ISBLANK(DPWW3!EA17),"",DPWW3!EA17) | ¬¬IF(ISBLANK(DPWW3!EB17),"",DPWW3!EB17) | ¬¬IF(ISBLANK(DPWW3!EC17),"",DPWW3!EC17) | ¬¬IF(ISBLANK(DPWW3!ED17),"",DPWW3!ED17) | ¬¬IF(ISBLANK(DPWW3!EE17),"",DPWW3!EE17) | ¬¬IF(ISBLANK(DPWW3!EF17),"",DPWW3!EF17) | ¬¬IF(ISBLANK(DPWW3!EG17),"",DPWW3!EG17) | ¬¬IF(ISBLANK(DPWW3!EH17),"",DPWW3!EH17) | ¬¬IF(ISBLANK(DPWW3!EI17),"",DPWW3!EI17) | ¬¬IF(ISBLANK(DPWW3!EJ17),"",DPWW3!EJ17) | ¬¬IF(ISBLANK(DPWW3!EK17),"",DPWW3!EK17) | ¬¬IF(ISBLANK(DPWW3!EL17),"",DPWW3!EL17) | ¬¬IF(ISBLANK(DPWW3!EM17),"",DPWW3!EM17)
¬¬A794 | ¬¬IF(ISBLANK(DPWW3!MA17),"",DPWW3!MA17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO17),"",DPWW3!EO17) | ¬¬IF(ISBLANK(DPWW3!EP17),"",DPWW3!EP17) | ¬¬IF(ISBLANK(DPWW3!EQ17),"",DPWW3!EQ17) | ¬¬IF(ISBLANK(DPWW3!ER17),"",DPWW3!ER17) | ¬¬IF(ISBLANK(DPWW3!ES17),"",DPWW3!ES17) | ¬¬IF(ISBLANK(DPWW3!ET17),"",DPWW3!ET17) | ¬¬IF(ISBLANK(DPWW3!EU17),"",DPWW3!EU17) | ¬¬IF(ISBLANK(DPWW3!EV17),"",DPWW3!EV17) | ¬¬IF(ISBLANK(DPWW3!EW17),"",DPWW3!EW17) | ¬¬IF(ISBLANK(DPWW3!EX17),"",DPWW3!EX17) | ¬¬IF(ISBLANK(DPWW3!EY17),"",DPWW3!EY17) | ¬¬IF(ISBLANK(DPWW3!EZ17),"",DPWW3!EZ17) | ¬¬IF(ISBLANK(DPWW3!FA17),"",DPWW3!FA17) | ¬¬IF(ISBLANK(DPWW3!FB17),"",DPWW3!FB17) | ¬¬IF(ISBLANK(DPWW3!FC17),"",DPWW3!FC17) | ¬¬IF(ISBLANK(DPWW3!FD17),"",DPWW3!FD17) | ¬¬IF(ISBLANK(DPWW3!FE17),"",DPWW3!FE17) | ¬¬IF(ISBLANK(DPWW3!FF17),"",DPWW3!FF17) | ¬¬IF(ISBLANK(DPWW3!FG17),"",DPWW3!FG17) | ¬¬IF(ISBLANK(DPWW3!FH17),"",DPWW3!FH17) | ¬¬IF(ISBLANK(DPWW3!FI17),"",DPWW3!FI17)
¬¬A795 | ¬¬IF(ISBLANK(DPWW3!MW17),"",DPWW3!MW17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK17),"",DPWW3!FK17) | ¬¬IF(ISBLANK(DPWW3!FL17),"",DPWW3!FL17) | ¬¬IF(ISBLANK(DPWW3!FM17),"",DPWW3!FM17) | ¬¬IF(ISBLANK(DPWW3!FN17),"",DPWW3!FN17) | ¬¬IF(ISBLANK(DPWW3!FO17),"",DPWW3!FO17) | ¬¬IF(ISBLANK(DPWW3!FP17),"",DPWW3!FP17) | ¬¬IF(ISBLANK(DPWW3!FQ17),"",DPWW3!FQ17) | ¬¬IF(ISBLANK(DPWW3!FR17),"",DPWW3!FR17) | ¬¬IF(ISBLANK(DPWW3!FS17),"",DPWW3!FS17) | ¬¬IF(ISBLANK(DPWW3!FT17),"",DPWW3!FT17) | ¬¬IF(ISBLANK(DPWW3!FU17),"",DPWW3!FU17) | ¬¬IF(ISBLANK(DPWW3!FV17),"",DPWW3!FV17) | ¬¬IF(ISBLANK(DPWW3!FW17),"",DPWW3!FW17) | ¬¬IF(ISBLANK(DPWW3!FX17),"",DPWW3!FX17) | ¬¬IF(ISBLANK(DPWW3!FY17),"",DPWW3!FY17) | ¬¬IF(ISBLANK(DPWW3!FZ17),"",DPWW3!FZ17) | ¬¬IF(ISBLANK(DPWW3!GA17),"",DPWW3!GA17) | ¬¬IF(ISBLANK(DPWW3!GB17),"",DPWW3!GB17) | ¬¬IF(ISBLANK(DPWW3!GC17),"",DPWW3!GC17) | ¬¬IF(ISBLANK(DPWW3!GD17),"",DPWW3!GD17) | ¬¬IF(ISBLANK(DPWW3!GE17),"",DPWW3!GE17)
¬¬A796 | ¬¬IF(ISBLANK(DPWW3!NS17),"",DPWW3!NS17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GG17),"",DPWW3!GG17)
¬¬A797 | ¬¬IF(ISBLANK(DPWW3!NT17),"",DPWW3!NT17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GH17),"",DPWW3!GH17)
¬¬A798 | ¬¬IF(ISBLANK(DPWW3!NU17),"",DPWW3!NU17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GI17),"",DPWW3!GI17)
¬¬A799 | ¬¬IF(ISBLANK(DPWW3!NV17),"",DPWW3!NV17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ17),"",DPWW3!GJ17)
¬¬A800 | ¬¬IF(ISBLANK(DPWW3!NW17),"",DPWW3!NW17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GK17),"",DPWW3!GK17)
¬¬A801 | ¬¬IF(ISBLANK(DPWW3!NX17),"",DPWW3!NX17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GL17),"",DPWW3!GL17)
¬¬A802 | ¬¬IF(ISBLANK(DPWW3!NY17),"",DPWW3!NY17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GM17),"",DPWW3!GM17)
¬¬A803 | ¬¬IF(ISBLANK(DPWW3!NZ17),"",DPWW3!NZ17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GN17),"",DPWW3!GN17)
¬¬A804 | ¬¬IF(ISBLANK(DPWW3!OA17),"",DPWW3!OA17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GO17),"",DPWW3!GO17)
¬¬A805 | ¬¬IF(ISBLANK(DPWW3!OB17),"",DPWW3!OB17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GP17),"",DPWW3!GP17)
¬¬A806 | ¬¬IF(ISBLANK(DPWW3!OC17),"",DPWW3!OC17) | ¬¬DPWW3!F17 & "," & DPWW3!G17 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H17),"",DPWW3!H17) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ17),"",DPWW3!GQ17)
¬¬A807 | ¬¬IF(ISBLANK(DPWW3!GW18),"",DPWW3!GW18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!K18),"",DPWW3!K18)
¬¬A808 | ¬¬IF(ISBLANK(DPWW3!GY18),"",DPWW3!GY18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M18),"",DPWW3!M18) | ¬¬IF(ISBLANK(DPWW3!N18),"",DPWW3!N18) | ¬¬IF(ISBLANK(DPWW3!O18),"",DPWW3!O18) | ¬¬IF(ISBLANK(DPWW3!P18),"",DPWW3!P18) | ¬¬IF(ISBLANK(DPWW3!Q18),"",DPWW3!Q18) | ¬¬IF(ISBLANK(DPWW3!R18),"",DPWW3!R18) | ¬¬IF(ISBLANK(DPWW3!S18),"",DPWW3!S18) | ¬¬IF(ISBLANK(DPWW3!T18),"",DPWW3!T18) | ¬¬IF(ISBLANK(DPWW3!U18),"",DPWW3!U18) | ¬¬IF(ISBLANK(DPWW3!V18),"",DPWW3!V18) | ¬¬IF(ISBLANK(DPWW3!W18),"",DPWW3!W18) | ¬¬IF(ISBLANK(DPWW3!X18),"",DPWW3!X18) | ¬¬IF(ISBLANK(DPWW3!Y18),"",DPWW3!Y18) | ¬¬IF(ISBLANK(DPWW3!Z18),"",DPWW3!Z18) | ¬¬IF(ISBLANK(DPWW3!AA18),"",DPWW3!AA18) | ¬¬IF(ISBLANK(DPWW3!AB18),"",DPWW3!AB18) | ¬¬IF(ISBLANK(DPWW3!AC18),"",DPWW3!AC18) | ¬¬IF(ISBLANK(DPWW3!AD18),"",DPWW3!AD18) | ¬¬IF(ISBLANK(DPWW3!AE18),"",DPWW3!AE18) | ¬¬IF(ISBLANK(DPWW3!AF18),"",DPWW3!AF18) | ¬¬IF(ISBLANK(DPWW3!AG18),"",DPWW3!AG18)
¬¬A809 | ¬¬IF(ISBLANK(DPWW3!HU18),"",DPWW3!HU18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI18),"",DPWW3!AI18) | ¬¬IF(ISBLANK(DPWW3!AJ18),"",DPWW3!AJ18) | ¬¬IF(ISBLANK(DPWW3!AK18),"",DPWW3!AK18) | ¬¬IF(ISBLANK(DPWW3!AL18),"",DPWW3!AL18) | ¬¬IF(ISBLANK(DPWW3!AM18),"",DPWW3!AM18) | ¬¬IF(ISBLANK(DPWW3!AN18),"",DPWW3!AN18) | ¬¬IF(ISBLANK(DPWW3!AO18),"",DPWW3!AO18) | ¬¬IF(ISBLANK(DPWW3!AP18),"",DPWW3!AP18) | ¬¬IF(ISBLANK(DPWW3!AQ18),"",DPWW3!AQ18) | ¬¬IF(ISBLANK(DPWW3!AR18),"",DPWW3!AR18) | ¬¬IF(ISBLANK(DPWW3!AS18),"",DPWW3!AS18) | ¬¬IF(ISBLANK(DPWW3!AT18),"",DPWW3!AT18) | ¬¬IF(ISBLANK(DPWW3!AU18),"",DPWW3!AU18) | ¬¬IF(ISBLANK(DPWW3!AV18),"",DPWW3!AV18) | ¬¬IF(ISBLANK(DPWW3!AW18),"",DPWW3!AW18) | ¬¬IF(ISBLANK(DPWW3!AX18),"",DPWW3!AX18) | ¬¬IF(ISBLANK(DPWW3!AY18),"",DPWW3!AY18) | ¬¬IF(ISBLANK(DPWW3!AZ18),"",DPWW3!AZ18) | ¬¬IF(ISBLANK(DPWW3!BA18),"",DPWW3!BA18) | ¬¬IF(ISBLANK(DPWW3!BB18),"",DPWW3!BB18) | ¬¬IF(ISBLANK(DPWW3!BC18),"",DPWW3!BC18)
¬¬A810 | ¬¬IF(ISBLANK(DPWW3!IQ18),"",DPWW3!IQ18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE18),"",DPWW3!BE18) | ¬¬IF(ISBLANK(DPWW3!BF18),"",DPWW3!BF18) | ¬¬IF(ISBLANK(DPWW3!BG18),"",DPWW3!BG18) | ¬¬IF(ISBLANK(DPWW3!BH18),"",DPWW3!BH18) | ¬¬IF(ISBLANK(DPWW3!BI18),"",DPWW3!BI18) | ¬¬IF(ISBLANK(DPWW3!BJ18),"",DPWW3!BJ18) | ¬¬IF(ISBLANK(DPWW3!BK18),"",DPWW3!BK18) | ¬¬IF(ISBLANK(DPWW3!BL18),"",DPWW3!BL18) | ¬¬IF(ISBLANK(DPWW3!BM18),"",DPWW3!BM18) | ¬¬IF(ISBLANK(DPWW3!BN18),"",DPWW3!BN18) | ¬¬IF(ISBLANK(DPWW3!BO18),"",DPWW3!BO18) | ¬¬IF(ISBLANK(DPWW3!BP18),"",DPWW3!BP18) | ¬¬IF(ISBLANK(DPWW3!BQ18),"",DPWW3!BQ18) | ¬¬IF(ISBLANK(DPWW3!BR18),"",DPWW3!BR18) | ¬¬IF(ISBLANK(DPWW3!BS18),"",DPWW3!BS18) | ¬¬IF(ISBLANK(DPWW3!BT18),"",DPWW3!BT18) | ¬¬IF(ISBLANK(DPWW3!BU18),"",DPWW3!BU18) | ¬¬IF(ISBLANK(DPWW3!BV18),"",DPWW3!BV18) | ¬¬IF(ISBLANK(DPWW3!BW18),"",DPWW3!BW18) | ¬¬IF(ISBLANK(DPWW3!BX18),"",DPWW3!BX18) | ¬¬IF(ISBLANK(DPWW3!BY18),"",DPWW3!BY18)
¬¬A811 | ¬¬IF(ISBLANK(DPWW3!JM18),"",DPWW3!JM18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA18),"",DPWW3!CA18) | ¬¬IF(ISBLANK(DPWW3!CB18),"",DPWW3!CB18) | ¬¬IF(ISBLANK(DPWW3!CC18),"",DPWW3!CC18) | ¬¬IF(ISBLANK(DPWW3!CD18),"",DPWW3!CD18) | ¬¬IF(ISBLANK(DPWW3!CE18),"",DPWW3!CE18) | ¬¬IF(ISBLANK(DPWW3!CF18),"",DPWW3!CF18) | ¬¬IF(ISBLANK(DPWW3!CG18),"",DPWW3!CG18) | ¬¬IF(ISBLANK(DPWW3!CH18),"",DPWW3!CH18) | ¬¬IF(ISBLANK(DPWW3!CI18),"",DPWW3!CI18) | ¬¬IF(ISBLANK(DPWW3!CJ18),"",DPWW3!CJ18) | ¬¬IF(ISBLANK(DPWW3!CK18),"",DPWW3!CK18) | ¬¬IF(ISBLANK(DPWW3!CL18),"",DPWW3!CL18) | ¬¬IF(ISBLANK(DPWW3!CM18),"",DPWW3!CM18) | ¬¬IF(ISBLANK(DPWW3!CN18),"",DPWW3!CN18) | ¬¬IF(ISBLANK(DPWW3!CO18),"",DPWW3!CO18) | ¬¬IF(ISBLANK(DPWW3!CP18),"",DPWW3!CP18) | ¬¬IF(ISBLANK(DPWW3!CQ18),"",DPWW3!CQ18) | ¬¬IF(ISBLANK(DPWW3!CR18),"",DPWW3!CR18) | ¬¬IF(ISBLANK(DPWW3!CS18),"",DPWW3!CS18) | ¬¬IF(ISBLANK(DPWW3!CT18),"",DPWW3!CT18) | ¬¬IF(ISBLANK(DPWW3!CU18),"",DPWW3!CU18)
¬¬A812 | ¬¬IF(ISBLANK(DPWW3!KI18),"",DPWW3!KI18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW18),"",DPWW3!CW18) | ¬¬IF(ISBLANK(DPWW3!CX18),"",DPWW3!CX18) | ¬¬IF(ISBLANK(DPWW3!CY18),"",DPWW3!CY18) | ¬¬IF(ISBLANK(DPWW3!CZ18),"",DPWW3!CZ18) | ¬¬IF(ISBLANK(DPWW3!DA18),"",DPWW3!DA18) | ¬¬IF(ISBLANK(DPWW3!DB18),"",DPWW3!DB18) | ¬¬IF(ISBLANK(DPWW3!DC18),"",DPWW3!DC18) | ¬¬IF(ISBLANK(DPWW3!DD18),"",DPWW3!DD18) | ¬¬IF(ISBLANK(DPWW3!DE18),"",DPWW3!DE18) | ¬¬IF(ISBLANK(DPWW3!DF18),"",DPWW3!DF18) | ¬¬IF(ISBLANK(DPWW3!DG18),"",DPWW3!DG18) | ¬¬IF(ISBLANK(DPWW3!DH18),"",DPWW3!DH18) | ¬¬IF(ISBLANK(DPWW3!DI18),"",DPWW3!DI18) | ¬¬IF(ISBLANK(DPWW3!DJ18),"",DPWW3!DJ18) | ¬¬IF(ISBLANK(DPWW3!DK18),"",DPWW3!DK18) | ¬¬IF(ISBLANK(DPWW3!DL18),"",DPWW3!DL18) | ¬¬IF(ISBLANK(DPWW3!DM18),"",DPWW3!DM18) | ¬¬IF(ISBLANK(DPWW3!DN18),"",DPWW3!DN18) | ¬¬IF(ISBLANK(DPWW3!DO18),"",DPWW3!DO18) | ¬¬IF(ISBLANK(DPWW3!DP18),"",DPWW3!DP18) | ¬¬IF(ISBLANK(DPWW3!DQ18),"",DPWW3!DQ18)
¬¬A813 | ¬¬IF(ISBLANK(DPWW3!LE18),"",DPWW3!LE18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS18),"",DPWW3!DS18) | ¬¬IF(ISBLANK(DPWW3!DT18),"",DPWW3!DT18) | ¬¬IF(ISBLANK(DPWW3!DU18),"",DPWW3!DU18) | ¬¬IF(ISBLANK(DPWW3!DV18),"",DPWW3!DV18) | ¬¬IF(ISBLANK(DPWW3!DW18),"",DPWW3!DW18) | ¬¬IF(ISBLANK(DPWW3!DX18),"",DPWW3!DX18) | ¬¬IF(ISBLANK(DPWW3!DY18),"",DPWW3!DY18) | ¬¬IF(ISBLANK(DPWW3!DZ18),"",DPWW3!DZ18) | ¬¬IF(ISBLANK(DPWW3!EA18),"",DPWW3!EA18) | ¬¬IF(ISBLANK(DPWW3!EB18),"",DPWW3!EB18) | ¬¬IF(ISBLANK(DPWW3!EC18),"",DPWW3!EC18) | ¬¬IF(ISBLANK(DPWW3!ED18),"",DPWW3!ED18) | ¬¬IF(ISBLANK(DPWW3!EE18),"",DPWW3!EE18) | ¬¬IF(ISBLANK(DPWW3!EF18),"",DPWW3!EF18) | ¬¬IF(ISBLANK(DPWW3!EG18),"",DPWW3!EG18) | ¬¬IF(ISBLANK(DPWW3!EH18),"",DPWW3!EH18) | ¬¬IF(ISBLANK(DPWW3!EI18),"",DPWW3!EI18) | ¬¬IF(ISBLANK(DPWW3!EJ18),"",DPWW3!EJ18) | ¬¬IF(ISBLANK(DPWW3!EK18),"",DPWW3!EK18) | ¬¬IF(ISBLANK(DPWW3!EL18),"",DPWW3!EL18) | ¬¬IF(ISBLANK(DPWW3!EM18),"",DPWW3!EM18)
¬¬A814 | ¬¬IF(ISBLANK(DPWW3!MA18),"",DPWW3!MA18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO18),"",DPWW3!EO18) | ¬¬IF(ISBLANK(DPWW3!EP18),"",DPWW3!EP18) | ¬¬IF(ISBLANK(DPWW3!EQ18),"",DPWW3!EQ18) | ¬¬IF(ISBLANK(DPWW3!ER18),"",DPWW3!ER18) | ¬¬IF(ISBLANK(DPWW3!ES18),"",DPWW3!ES18) | ¬¬IF(ISBLANK(DPWW3!ET18),"",DPWW3!ET18) | ¬¬IF(ISBLANK(DPWW3!EU18),"",DPWW3!EU18) | ¬¬IF(ISBLANK(DPWW3!EV18),"",DPWW3!EV18) | ¬¬IF(ISBLANK(DPWW3!EW18),"",DPWW3!EW18) | ¬¬IF(ISBLANK(DPWW3!EX18),"",DPWW3!EX18) | ¬¬IF(ISBLANK(DPWW3!EY18),"",DPWW3!EY18) | ¬¬IF(ISBLANK(DPWW3!EZ18),"",DPWW3!EZ18) | ¬¬IF(ISBLANK(DPWW3!FA18),"",DPWW3!FA18) | ¬¬IF(ISBLANK(DPWW3!FB18),"",DPWW3!FB18) | ¬¬IF(ISBLANK(DPWW3!FC18),"",DPWW3!FC18) | ¬¬IF(ISBLANK(DPWW3!FD18),"",DPWW3!FD18) | ¬¬IF(ISBLANK(DPWW3!FE18),"",DPWW3!FE18) | ¬¬IF(ISBLANK(DPWW3!FF18),"",DPWW3!FF18) | ¬¬IF(ISBLANK(DPWW3!FG18),"",DPWW3!FG18) | ¬¬IF(ISBLANK(DPWW3!FH18),"",DPWW3!FH18) | ¬¬IF(ISBLANK(DPWW3!FI18),"",DPWW3!FI18)
¬¬A815 | ¬¬IF(ISBLANK(DPWW3!MW18),"",DPWW3!MW18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK18),"",DPWW3!FK18) | ¬¬IF(ISBLANK(DPWW3!FL18),"",DPWW3!FL18) | ¬¬IF(ISBLANK(DPWW3!FM18),"",DPWW3!FM18) | ¬¬IF(ISBLANK(DPWW3!FN18),"",DPWW3!FN18) | ¬¬IF(ISBLANK(DPWW3!FO18),"",DPWW3!FO18) | ¬¬IF(ISBLANK(DPWW3!FP18),"",DPWW3!FP18) | ¬¬IF(ISBLANK(DPWW3!FQ18),"",DPWW3!FQ18) | ¬¬IF(ISBLANK(DPWW3!FR18),"",DPWW3!FR18) | ¬¬IF(ISBLANK(DPWW3!FS18),"",DPWW3!FS18) | ¬¬IF(ISBLANK(DPWW3!FT18),"",DPWW3!FT18) | ¬¬IF(ISBLANK(DPWW3!FU18),"",DPWW3!FU18) | ¬¬IF(ISBLANK(DPWW3!FV18),"",DPWW3!FV18) | ¬¬IF(ISBLANK(DPWW3!FW18),"",DPWW3!FW18) | ¬¬IF(ISBLANK(DPWW3!FX18),"",DPWW3!FX18) | ¬¬IF(ISBLANK(DPWW3!FY18),"",DPWW3!FY18) | ¬¬IF(ISBLANK(DPWW3!FZ18),"",DPWW3!FZ18) | ¬¬IF(ISBLANK(DPWW3!GA18),"",DPWW3!GA18) | ¬¬IF(ISBLANK(DPWW3!GB18),"",DPWW3!GB18) | ¬¬IF(ISBLANK(DPWW3!GC18),"",DPWW3!GC18) | ¬¬IF(ISBLANK(DPWW3!GD18),"",DPWW3!GD18) | ¬¬IF(ISBLANK(DPWW3!GE18),"",DPWW3!GE18)
¬¬A816 | ¬¬IF(ISBLANK(DPWW3!NS18),"",DPWW3!NS18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GG18),"",DPWW3!GG18)
¬¬A817 | ¬¬IF(ISBLANK(DPWW3!NT18),"",DPWW3!NT18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GH18),"",DPWW3!GH18)
¬¬A818 | ¬¬IF(ISBLANK(DPWW3!NU18),"",DPWW3!NU18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GI18),"",DPWW3!GI18)
¬¬A819 | ¬¬IF(ISBLANK(DPWW3!NV18),"",DPWW3!NV18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ18),"",DPWW3!GJ18)
¬¬A820 | ¬¬IF(ISBLANK(DPWW3!NW18),"",DPWW3!NW18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GK18),"",DPWW3!GK18)
¬¬A821 | ¬¬IF(ISBLANK(DPWW3!NX18),"",DPWW3!NX18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GL18),"",DPWW3!GL18)
¬¬A822 | ¬¬IF(ISBLANK(DPWW3!NY18),"",DPWW3!NY18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GM18),"",DPWW3!GM18)
¬¬A823 | ¬¬IF(ISBLANK(DPWW3!NZ18),"",DPWW3!NZ18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GN18),"",DPWW3!GN18)
¬¬A824 | ¬¬IF(ISBLANK(DPWW3!OA18),"",DPWW3!OA18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GO18),"",DPWW3!GO18)
¬¬A825 | ¬¬IF(ISBLANK(DPWW3!OB18),"",DPWW3!OB18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GP18),"",DPWW3!GP18)
¬¬A826 | ¬¬IF(ISBLANK(DPWW3!OC18),"",DPWW3!OC18) | ¬¬DPWW3!F18 & "," & DPWW3!G18 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H18),"",DPWW3!H18) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ18),"",DPWW3!GQ18)
¬¬A827 | ¬¬IF(ISBLANK(DPWW3!GW19),"",DPWW3!GW19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!K19),"",DPWW3!K19)
¬¬A828 | ¬¬IF(ISBLANK(DPWW3!GY19),"",DPWW3!GY19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M19),"",DPWW3!M19) | ¬¬IF(ISBLANK(DPWW3!N19),"",DPWW3!N19) | ¬¬IF(ISBLANK(DPWW3!O19),"",DPWW3!O19) | ¬¬IF(ISBLANK(DPWW3!P19),"",DPWW3!P19) | ¬¬IF(ISBLANK(DPWW3!Q19),"",DPWW3!Q19) | ¬¬IF(ISBLANK(DPWW3!R19),"",DPWW3!R19) | ¬¬IF(ISBLANK(DPWW3!S19),"",DPWW3!S19) | ¬¬IF(ISBLANK(DPWW3!T19),"",DPWW3!T19) | ¬¬IF(ISBLANK(DPWW3!U19),"",DPWW3!U19) | ¬¬IF(ISBLANK(DPWW3!V19),"",DPWW3!V19) | ¬¬IF(ISBLANK(DPWW3!W19),"",DPWW3!W19) | ¬¬IF(ISBLANK(DPWW3!X19),"",DPWW3!X19) | ¬¬IF(ISBLANK(DPWW3!Y19),"",DPWW3!Y19) | ¬¬IF(ISBLANK(DPWW3!Z19),"",DPWW3!Z19) | ¬¬IF(ISBLANK(DPWW3!AA19),"",DPWW3!AA19) | ¬¬IF(ISBLANK(DPWW3!AB19),"",DPWW3!AB19) | ¬¬IF(ISBLANK(DPWW3!AC19),"",DPWW3!AC19) | ¬¬IF(ISBLANK(DPWW3!AD19),"",DPWW3!AD19) | ¬¬IF(ISBLANK(DPWW3!AE19),"",DPWW3!AE19) | ¬¬IF(ISBLANK(DPWW3!AF19),"",DPWW3!AF19) | ¬¬IF(ISBLANK(DPWW3!AG19),"",DPWW3!AG19)
¬¬A829 | ¬¬IF(ISBLANK(DPWW3!HU19),"",DPWW3!HU19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI19),"",DPWW3!AI19) | ¬¬IF(ISBLANK(DPWW3!AJ19),"",DPWW3!AJ19) | ¬¬IF(ISBLANK(DPWW3!AK19),"",DPWW3!AK19) | ¬¬IF(ISBLANK(DPWW3!AL19),"",DPWW3!AL19) | ¬¬IF(ISBLANK(DPWW3!AM19),"",DPWW3!AM19) | ¬¬IF(ISBLANK(DPWW3!AN19),"",DPWW3!AN19) | ¬¬IF(ISBLANK(DPWW3!AO19),"",DPWW3!AO19) | ¬¬IF(ISBLANK(DPWW3!AP19),"",DPWW3!AP19) | ¬¬IF(ISBLANK(DPWW3!AQ19),"",DPWW3!AQ19) | ¬¬IF(ISBLANK(DPWW3!AR19),"",DPWW3!AR19) | ¬¬IF(ISBLANK(DPWW3!AS19),"",DPWW3!AS19) | ¬¬IF(ISBLANK(DPWW3!AT19),"",DPWW3!AT19) | ¬¬IF(ISBLANK(DPWW3!AU19),"",DPWW3!AU19) | ¬¬IF(ISBLANK(DPWW3!AV19),"",DPWW3!AV19) | ¬¬IF(ISBLANK(DPWW3!AW19),"",DPWW3!AW19) | ¬¬IF(ISBLANK(DPWW3!AX19),"",DPWW3!AX19) | ¬¬IF(ISBLANK(DPWW3!AY19),"",DPWW3!AY19) | ¬¬IF(ISBLANK(DPWW3!AZ19),"",DPWW3!AZ19) | ¬¬IF(ISBLANK(DPWW3!BA19),"",DPWW3!BA19) | ¬¬IF(ISBLANK(DPWW3!BB19),"",DPWW3!BB19) | ¬¬IF(ISBLANK(DPWW3!BC19),"",DPWW3!BC19)
¬¬A830 | ¬¬IF(ISBLANK(DPWW3!IQ19),"",DPWW3!IQ19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE19),"",DPWW3!BE19) | ¬¬IF(ISBLANK(DPWW3!BF19),"",DPWW3!BF19) | ¬¬IF(ISBLANK(DPWW3!BG19),"",DPWW3!BG19) | ¬¬IF(ISBLANK(DPWW3!BH19),"",DPWW3!BH19) | ¬¬IF(ISBLANK(DPWW3!BI19),"",DPWW3!BI19) | ¬¬IF(ISBLANK(DPWW3!BJ19),"",DPWW3!BJ19) | ¬¬IF(ISBLANK(DPWW3!BK19),"",DPWW3!BK19) | ¬¬IF(ISBLANK(DPWW3!BL19),"",DPWW3!BL19) | ¬¬IF(ISBLANK(DPWW3!BM19),"",DPWW3!BM19) | ¬¬IF(ISBLANK(DPWW3!BN19),"",DPWW3!BN19) | ¬¬IF(ISBLANK(DPWW3!BO19),"",DPWW3!BO19) | ¬¬IF(ISBLANK(DPWW3!BP19),"",DPWW3!BP19) | ¬¬IF(ISBLANK(DPWW3!BQ19),"",DPWW3!BQ19) | ¬¬IF(ISBLANK(DPWW3!BR19),"",DPWW3!BR19) | ¬¬IF(ISBLANK(DPWW3!BS19),"",DPWW3!BS19) | ¬¬IF(ISBLANK(DPWW3!BT19),"",DPWW3!BT19) | ¬¬IF(ISBLANK(DPWW3!BU19),"",DPWW3!BU19) | ¬¬IF(ISBLANK(DPWW3!BV19),"",DPWW3!BV19) | ¬¬IF(ISBLANK(DPWW3!BW19),"",DPWW3!BW19) | ¬¬IF(ISBLANK(DPWW3!BX19),"",DPWW3!BX19) | ¬¬IF(ISBLANK(DPWW3!BY19),"",DPWW3!BY19)
¬¬A831 | ¬¬IF(ISBLANK(DPWW3!JM19),"",DPWW3!JM19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA19),"",DPWW3!CA19) | ¬¬IF(ISBLANK(DPWW3!CB19),"",DPWW3!CB19) | ¬¬IF(ISBLANK(DPWW3!CC19),"",DPWW3!CC19) | ¬¬IF(ISBLANK(DPWW3!CD19),"",DPWW3!CD19) | ¬¬IF(ISBLANK(DPWW3!CE19),"",DPWW3!CE19) | ¬¬IF(ISBLANK(DPWW3!CF19),"",DPWW3!CF19) | ¬¬IF(ISBLANK(DPWW3!CG19),"",DPWW3!CG19) | ¬¬IF(ISBLANK(DPWW3!CH19),"",DPWW3!CH19) | ¬¬IF(ISBLANK(DPWW3!CI19),"",DPWW3!CI19) | ¬¬IF(ISBLANK(DPWW3!CJ19),"",DPWW3!CJ19) | ¬¬IF(ISBLANK(DPWW3!CK19),"",DPWW3!CK19) | ¬¬IF(ISBLANK(DPWW3!CL19),"",DPWW3!CL19) | ¬¬IF(ISBLANK(DPWW3!CM19),"",DPWW3!CM19) | ¬¬IF(ISBLANK(DPWW3!CN19),"",DPWW3!CN19) | ¬¬IF(ISBLANK(DPWW3!CO19),"",DPWW3!CO19) | ¬¬IF(ISBLANK(DPWW3!CP19),"",DPWW3!CP19) | ¬¬IF(ISBLANK(DPWW3!CQ19),"",DPWW3!CQ19) | ¬¬IF(ISBLANK(DPWW3!CR19),"",DPWW3!CR19) | ¬¬IF(ISBLANK(DPWW3!CS19),"",DPWW3!CS19) | ¬¬IF(ISBLANK(DPWW3!CT19),"",DPWW3!CT19) | ¬¬IF(ISBLANK(DPWW3!CU19),"",DPWW3!CU19)
¬¬A832 | ¬¬IF(ISBLANK(DPWW3!KI19),"",DPWW3!KI19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW19),"",DPWW3!CW19) | ¬¬IF(ISBLANK(DPWW3!CX19),"",DPWW3!CX19) | ¬¬IF(ISBLANK(DPWW3!CY19),"",DPWW3!CY19) | ¬¬IF(ISBLANK(DPWW3!CZ19),"",DPWW3!CZ19) | ¬¬IF(ISBLANK(DPWW3!DA19),"",DPWW3!DA19) | ¬¬IF(ISBLANK(DPWW3!DB19),"",DPWW3!DB19) | ¬¬IF(ISBLANK(DPWW3!DC19),"",DPWW3!DC19) | ¬¬IF(ISBLANK(DPWW3!DD19),"",DPWW3!DD19) | ¬¬IF(ISBLANK(DPWW3!DE19),"",DPWW3!DE19) | ¬¬IF(ISBLANK(DPWW3!DF19),"",DPWW3!DF19) | ¬¬IF(ISBLANK(DPWW3!DG19),"",DPWW3!DG19) | ¬¬IF(ISBLANK(DPWW3!DH19),"",DPWW3!DH19) | ¬¬IF(ISBLANK(DPWW3!DI19),"",DPWW3!DI19) | ¬¬IF(ISBLANK(DPWW3!DJ19),"",DPWW3!DJ19) | ¬¬IF(ISBLANK(DPWW3!DK19),"",DPWW3!DK19) | ¬¬IF(ISBLANK(DPWW3!DL19),"",DPWW3!DL19) | ¬¬IF(ISBLANK(DPWW3!DM19),"",DPWW3!DM19) | ¬¬IF(ISBLANK(DPWW3!DN19),"",DPWW3!DN19) | ¬¬IF(ISBLANK(DPWW3!DO19),"",DPWW3!DO19) | ¬¬IF(ISBLANK(DPWW3!DP19),"",DPWW3!DP19) | ¬¬IF(ISBLANK(DPWW3!DQ19),"",DPWW3!DQ19)
¬¬A833 | ¬¬IF(ISBLANK(DPWW3!LE19),"",DPWW3!LE19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS19),"",DPWW3!DS19) | ¬¬IF(ISBLANK(DPWW3!DT19),"",DPWW3!DT19) | ¬¬IF(ISBLANK(DPWW3!DU19),"",DPWW3!DU19) | ¬¬IF(ISBLANK(DPWW3!DV19),"",DPWW3!DV19) | ¬¬IF(ISBLANK(DPWW3!DW19),"",DPWW3!DW19) | ¬¬IF(ISBLANK(DPWW3!DX19),"",DPWW3!DX19) | ¬¬IF(ISBLANK(DPWW3!DY19),"",DPWW3!DY19) | ¬¬IF(ISBLANK(DPWW3!DZ19),"",DPWW3!DZ19) | ¬¬IF(ISBLANK(DPWW3!EA19),"",DPWW3!EA19) | ¬¬IF(ISBLANK(DPWW3!EB19),"",DPWW3!EB19) | ¬¬IF(ISBLANK(DPWW3!EC19),"",DPWW3!EC19) | ¬¬IF(ISBLANK(DPWW3!ED19),"",DPWW3!ED19) | ¬¬IF(ISBLANK(DPWW3!EE19),"",DPWW3!EE19) | ¬¬IF(ISBLANK(DPWW3!EF19),"",DPWW3!EF19) | ¬¬IF(ISBLANK(DPWW3!EG19),"",DPWW3!EG19) | ¬¬IF(ISBLANK(DPWW3!EH19),"",DPWW3!EH19) | ¬¬IF(ISBLANK(DPWW3!EI19),"",DPWW3!EI19) | ¬¬IF(ISBLANK(DPWW3!EJ19),"",DPWW3!EJ19) | ¬¬IF(ISBLANK(DPWW3!EK19),"",DPWW3!EK19) | ¬¬IF(ISBLANK(DPWW3!EL19),"",DPWW3!EL19) | ¬¬IF(ISBLANK(DPWW3!EM19),"",DPWW3!EM19)
¬¬A834 | ¬¬IF(ISBLANK(DPWW3!MA19),"",DPWW3!MA19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO19),"",DPWW3!EO19) | ¬¬IF(ISBLANK(DPWW3!EP19),"",DPWW3!EP19) | ¬¬IF(ISBLANK(DPWW3!EQ19),"",DPWW3!EQ19) | ¬¬IF(ISBLANK(DPWW3!ER19),"",DPWW3!ER19) | ¬¬IF(ISBLANK(DPWW3!ES19),"",DPWW3!ES19) | ¬¬IF(ISBLANK(DPWW3!ET19),"",DPWW3!ET19) | ¬¬IF(ISBLANK(DPWW3!EU19),"",DPWW3!EU19) | ¬¬IF(ISBLANK(DPWW3!EV19),"",DPWW3!EV19) | ¬¬IF(ISBLANK(DPWW3!EW19),"",DPWW3!EW19) | ¬¬IF(ISBLANK(DPWW3!EX19),"",DPWW3!EX19) | ¬¬IF(ISBLANK(DPWW3!EY19),"",DPWW3!EY19) | ¬¬IF(ISBLANK(DPWW3!EZ19),"",DPWW3!EZ19) | ¬¬IF(ISBLANK(DPWW3!FA19),"",DPWW3!FA19) | ¬¬IF(ISBLANK(DPWW3!FB19),"",DPWW3!FB19) | ¬¬IF(ISBLANK(DPWW3!FC19),"",DPWW3!FC19) | ¬¬IF(ISBLANK(DPWW3!FD19),"",DPWW3!FD19) | ¬¬IF(ISBLANK(DPWW3!FE19),"",DPWW3!FE19) | ¬¬IF(ISBLANK(DPWW3!FF19),"",DPWW3!FF19) | ¬¬IF(ISBLANK(DPWW3!FG19),"",DPWW3!FG19) | ¬¬IF(ISBLANK(DPWW3!FH19),"",DPWW3!FH19) | ¬¬IF(ISBLANK(DPWW3!FI19),"",DPWW3!FI19)
¬¬A835 | ¬¬IF(ISBLANK(DPWW3!MW19),"",DPWW3!MW19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK19),"",DPWW3!FK19) | ¬¬IF(ISBLANK(DPWW3!FL19),"",DPWW3!FL19) | ¬¬IF(ISBLANK(DPWW3!FM19),"",DPWW3!FM19) | ¬¬IF(ISBLANK(DPWW3!FN19),"",DPWW3!FN19) | ¬¬IF(ISBLANK(DPWW3!FO19),"",DPWW3!FO19) | ¬¬IF(ISBLANK(DPWW3!FP19),"",DPWW3!FP19) | ¬¬IF(ISBLANK(DPWW3!FQ19),"",DPWW3!FQ19) | ¬¬IF(ISBLANK(DPWW3!FR19),"",DPWW3!FR19) | ¬¬IF(ISBLANK(DPWW3!FS19),"",DPWW3!FS19) | ¬¬IF(ISBLANK(DPWW3!FT19),"",DPWW3!FT19) | ¬¬IF(ISBLANK(DPWW3!FU19),"",DPWW3!FU19) | ¬¬IF(ISBLANK(DPWW3!FV19),"",DPWW3!FV19) | ¬¬IF(ISBLANK(DPWW3!FW19),"",DPWW3!FW19) | ¬¬IF(ISBLANK(DPWW3!FX19),"",DPWW3!FX19) | ¬¬IF(ISBLANK(DPWW3!FY19),"",DPWW3!FY19) | ¬¬IF(ISBLANK(DPWW3!FZ19),"",DPWW3!FZ19) | ¬¬IF(ISBLANK(DPWW3!GA19),"",DPWW3!GA19) | ¬¬IF(ISBLANK(DPWW3!GB19),"",DPWW3!GB19) | ¬¬IF(ISBLANK(DPWW3!GC19),"",DPWW3!GC19) | ¬¬IF(ISBLANK(DPWW3!GD19),"",DPWW3!GD19) | ¬¬IF(ISBLANK(DPWW3!GE19),"",DPWW3!GE19)
¬¬A836 | ¬¬IF(ISBLANK(DPWW3!NS19),"",DPWW3!NS19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GG19),"",DPWW3!GG19)
¬¬A837 | ¬¬IF(ISBLANK(DPWW3!NT19),"",DPWW3!NT19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GH19),"",DPWW3!GH19)
¬¬A838 | ¬¬IF(ISBLANK(DPWW3!NU19),"",DPWW3!NU19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GI19),"",DPWW3!GI19)
¬¬A839 | ¬¬IF(ISBLANK(DPWW3!NV19),"",DPWW3!NV19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ19),"",DPWW3!GJ19)
¬¬A840 | ¬¬IF(ISBLANK(DPWW3!NW19),"",DPWW3!NW19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GK19),"",DPWW3!GK19)
¬¬A841 | ¬¬IF(ISBLANK(DPWW3!NX19),"",DPWW3!NX19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GL19),"",DPWW3!GL19)
¬¬A842 | ¬¬IF(ISBLANK(DPWW3!NY19),"",DPWW3!NY19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GM19),"",DPWW3!GM19)
¬¬A843 | ¬¬IF(ISBLANK(DPWW3!NZ19),"",DPWW3!NZ19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GN19),"",DPWW3!GN19)
¬¬A844 | ¬¬IF(ISBLANK(DPWW3!OA19),"",DPWW3!OA19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GO19),"",DPWW3!GO19)
¬¬A845 | ¬¬IF(ISBLANK(DPWW3!OB19),"",DPWW3!OB19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GP19),"",DPWW3!GP19)
¬¬A846 | ¬¬IF(ISBLANK(DPWW3!OC19),"",DPWW3!OC19) | ¬¬DPWW3!F19 & "," & DPWW3!G19 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H19),"",DPWW3!H19) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ19),"",DPWW3!GQ19)
¬¬A847 | ¬¬IF(ISBLANK(DPWW3!GW20),"",DPWW3!GW20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!K20),"",DPWW3!K20)
¬¬A848 | ¬¬IF(ISBLANK(DPWW3!GY20),"",DPWW3!GY20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M20),"",DPWW3!M20) | ¬¬IF(ISBLANK(DPWW3!N20),"",DPWW3!N20) | ¬¬IF(ISBLANK(DPWW3!O20),"",DPWW3!O20) | ¬¬IF(ISBLANK(DPWW3!P20),"",DPWW3!P20) | ¬¬IF(ISBLANK(DPWW3!Q20),"",DPWW3!Q20) | ¬¬IF(ISBLANK(DPWW3!R20),"",DPWW3!R20) | ¬¬IF(ISBLANK(DPWW3!S20),"",DPWW3!S20) | ¬¬IF(ISBLANK(DPWW3!T20),"",DPWW3!T20) | ¬¬IF(ISBLANK(DPWW3!U20),"",DPWW3!U20) | ¬¬IF(ISBLANK(DPWW3!V20),"",DPWW3!V20) | ¬¬IF(ISBLANK(DPWW3!W20),"",DPWW3!W20) | ¬¬IF(ISBLANK(DPWW3!X20),"",DPWW3!X20) | ¬¬IF(ISBLANK(DPWW3!Y20),"",DPWW3!Y20) | ¬¬IF(ISBLANK(DPWW3!Z20),"",DPWW3!Z20) | ¬¬IF(ISBLANK(DPWW3!AA20),"",DPWW3!AA20) | ¬¬IF(ISBLANK(DPWW3!AB20),"",DPWW3!AB20) | ¬¬IF(ISBLANK(DPWW3!AC20),"",DPWW3!AC20) | ¬¬IF(ISBLANK(DPWW3!AD20),"",DPWW3!AD20) | ¬¬IF(ISBLANK(DPWW3!AE20),"",DPWW3!AE20) | ¬¬IF(ISBLANK(DPWW3!AF20),"",DPWW3!AF20) | ¬¬IF(ISBLANK(DPWW3!AG20),"",DPWW3!AG20)
¬¬A849 | ¬¬IF(ISBLANK(DPWW3!HU20),"",DPWW3!HU20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI20),"",DPWW3!AI20) | ¬¬IF(ISBLANK(DPWW3!AJ20),"",DPWW3!AJ20) | ¬¬IF(ISBLANK(DPWW3!AK20),"",DPWW3!AK20) | ¬¬IF(ISBLANK(DPWW3!AL20),"",DPWW3!AL20) | ¬¬IF(ISBLANK(DPWW3!AM20),"",DPWW3!AM20) | ¬¬IF(ISBLANK(DPWW3!AN20),"",DPWW3!AN20) | ¬¬IF(ISBLANK(DPWW3!AO20),"",DPWW3!AO20) | ¬¬IF(ISBLANK(DPWW3!AP20),"",DPWW3!AP20) | ¬¬IF(ISBLANK(DPWW3!AQ20),"",DPWW3!AQ20) | ¬¬IF(ISBLANK(DPWW3!AR20),"",DPWW3!AR20) | ¬¬IF(ISBLANK(DPWW3!AS20),"",DPWW3!AS20) | ¬¬IF(ISBLANK(DPWW3!AT20),"",DPWW3!AT20) | ¬¬IF(ISBLANK(DPWW3!AU20),"",DPWW3!AU20) | ¬¬IF(ISBLANK(DPWW3!AV20),"",DPWW3!AV20) | ¬¬IF(ISBLANK(DPWW3!AW20),"",DPWW3!AW20) | ¬¬IF(ISBLANK(DPWW3!AX20),"",DPWW3!AX20) | ¬¬IF(ISBLANK(DPWW3!AY20),"",DPWW3!AY20) | ¬¬IF(ISBLANK(DPWW3!AZ20),"",DPWW3!AZ20) | ¬¬IF(ISBLANK(DPWW3!BA20),"",DPWW3!BA20) | ¬¬IF(ISBLANK(DPWW3!BB20),"",DPWW3!BB20) | ¬¬IF(ISBLANK(DPWW3!BC20),"",DPWW3!BC20)
¬¬A850 | ¬¬IF(ISBLANK(DPWW3!IQ20),"",DPWW3!IQ20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE20),"",DPWW3!BE20) | ¬¬IF(ISBLANK(DPWW3!BF20),"",DPWW3!BF20) | ¬¬IF(ISBLANK(DPWW3!BG20),"",DPWW3!BG20) | ¬¬IF(ISBLANK(DPWW3!BH20),"",DPWW3!BH20) | ¬¬IF(ISBLANK(DPWW3!BI20),"",DPWW3!BI20) | ¬¬IF(ISBLANK(DPWW3!BJ20),"",DPWW3!BJ20) | ¬¬IF(ISBLANK(DPWW3!BK20),"",DPWW3!BK20) | ¬¬IF(ISBLANK(DPWW3!BL20),"",DPWW3!BL20) | ¬¬IF(ISBLANK(DPWW3!BM20),"",DPWW3!BM20) | ¬¬IF(ISBLANK(DPWW3!BN20),"",DPWW3!BN20) | ¬¬IF(ISBLANK(DPWW3!BO20),"",DPWW3!BO20) | ¬¬IF(ISBLANK(DPWW3!BP20),"",DPWW3!BP20) | ¬¬IF(ISBLANK(DPWW3!BQ20),"",DPWW3!BQ20) | ¬¬IF(ISBLANK(DPWW3!BR20),"",DPWW3!BR20) | ¬¬IF(ISBLANK(DPWW3!BS20),"",DPWW3!BS20) | ¬¬IF(ISBLANK(DPWW3!BT20),"",DPWW3!BT20) | ¬¬IF(ISBLANK(DPWW3!BU20),"",DPWW3!BU20) | ¬¬IF(ISBLANK(DPWW3!BV20),"",DPWW3!BV20) | ¬¬IF(ISBLANK(DPWW3!BW20),"",DPWW3!BW20) | ¬¬IF(ISBLANK(DPWW3!BX20),"",DPWW3!BX20) | ¬¬IF(ISBLANK(DPWW3!BY20),"",DPWW3!BY20)
¬¬A851 | ¬¬IF(ISBLANK(DPWW3!JM20),"",DPWW3!JM20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA20),"",DPWW3!CA20) | ¬¬IF(ISBLANK(DPWW3!CB20),"",DPWW3!CB20) | ¬¬IF(ISBLANK(DPWW3!CC20),"",DPWW3!CC20) | ¬¬IF(ISBLANK(DPWW3!CD20),"",DPWW3!CD20) | ¬¬IF(ISBLANK(DPWW3!CE20),"",DPWW3!CE20) | ¬¬IF(ISBLANK(DPWW3!CF20),"",DPWW3!CF20) | ¬¬IF(ISBLANK(DPWW3!CG20),"",DPWW3!CG20) | ¬¬IF(ISBLANK(DPWW3!CH20),"",DPWW3!CH20) | ¬¬IF(ISBLANK(DPWW3!CI20),"",DPWW3!CI20) | ¬¬IF(ISBLANK(DPWW3!CJ20),"",DPWW3!CJ20) | ¬¬IF(ISBLANK(DPWW3!CK20),"",DPWW3!CK20) | ¬¬IF(ISBLANK(DPWW3!CL20),"",DPWW3!CL20) | ¬¬IF(ISBLANK(DPWW3!CM20),"",DPWW3!CM20) | ¬¬IF(ISBLANK(DPWW3!CN20),"",DPWW3!CN20) | ¬¬IF(ISBLANK(DPWW3!CO20),"",DPWW3!CO20) | ¬¬IF(ISBLANK(DPWW3!CP20),"",DPWW3!CP20) | ¬¬IF(ISBLANK(DPWW3!CQ20),"",DPWW3!CQ20) | ¬¬IF(ISBLANK(DPWW3!CR20),"",DPWW3!CR20) | ¬¬IF(ISBLANK(DPWW3!CS20),"",DPWW3!CS20) | ¬¬IF(ISBLANK(DPWW3!CT20),"",DPWW3!CT20) | ¬¬IF(ISBLANK(DPWW3!CU20),"",DPWW3!CU20)
¬¬A852 | ¬¬IF(ISBLANK(DPWW3!KI20),"",DPWW3!KI20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW20),"",DPWW3!CW20) | ¬¬IF(ISBLANK(DPWW3!CX20),"",DPWW3!CX20) | ¬¬IF(ISBLANK(DPWW3!CY20),"",DPWW3!CY20) | ¬¬IF(ISBLANK(DPWW3!CZ20),"",DPWW3!CZ20) | ¬¬IF(ISBLANK(DPWW3!DA20),"",DPWW3!DA20) | ¬¬IF(ISBLANK(DPWW3!DB20),"",DPWW3!DB20) | ¬¬IF(ISBLANK(DPWW3!DC20),"",DPWW3!DC20) | ¬¬IF(ISBLANK(DPWW3!DD20),"",DPWW3!DD20) | ¬¬IF(ISBLANK(DPWW3!DE20),"",DPWW3!DE20) | ¬¬IF(ISBLANK(DPWW3!DF20),"",DPWW3!DF20) | ¬¬IF(ISBLANK(DPWW3!DG20),"",DPWW3!DG20) | ¬¬IF(ISBLANK(DPWW3!DH20),"",DPWW3!DH20) | ¬¬IF(ISBLANK(DPWW3!DI20),"",DPWW3!DI20) | ¬¬IF(ISBLANK(DPWW3!DJ20),"",DPWW3!DJ20) | ¬¬IF(ISBLANK(DPWW3!DK20),"",DPWW3!DK20) | ¬¬IF(ISBLANK(DPWW3!DL20),"",DPWW3!DL20) | ¬¬IF(ISBLANK(DPWW3!DM20),"",DPWW3!DM20) | ¬¬IF(ISBLANK(DPWW3!DN20),"",DPWW3!DN20) | ¬¬IF(ISBLANK(DPWW3!DO20),"",DPWW3!DO20) | ¬¬IF(ISBLANK(DPWW3!DP20),"",DPWW3!DP20) | ¬¬IF(ISBLANK(DPWW3!DQ20),"",DPWW3!DQ20)
¬¬A853 | ¬¬IF(ISBLANK(DPWW3!LE20),"",DPWW3!LE20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS20),"",DPWW3!DS20) | ¬¬IF(ISBLANK(DPWW3!DT20),"",DPWW3!DT20) | ¬¬IF(ISBLANK(DPWW3!DU20),"",DPWW3!DU20) | ¬¬IF(ISBLANK(DPWW3!DV20),"",DPWW3!DV20) | ¬¬IF(ISBLANK(DPWW3!DW20),"",DPWW3!DW20) | ¬¬IF(ISBLANK(DPWW3!DX20),"",DPWW3!DX20) | ¬¬IF(ISBLANK(DPWW3!DY20),"",DPWW3!DY20) | ¬¬IF(ISBLANK(DPWW3!DZ20),"",DPWW3!DZ20) | ¬¬IF(ISBLANK(DPWW3!EA20),"",DPWW3!EA20) | ¬¬IF(ISBLANK(DPWW3!EB20),"",DPWW3!EB20) | ¬¬IF(ISBLANK(DPWW3!EC20),"",DPWW3!EC20) | ¬¬IF(ISBLANK(DPWW3!ED20),"",DPWW3!ED20) | ¬¬IF(ISBLANK(DPWW3!EE20),"",DPWW3!EE20) | ¬¬IF(ISBLANK(DPWW3!EF20),"",DPWW3!EF20) | ¬¬IF(ISBLANK(DPWW3!EG20),"",DPWW3!EG20) | ¬¬IF(ISBLANK(DPWW3!EH20),"",DPWW3!EH20) | ¬¬IF(ISBLANK(DPWW3!EI20),"",DPWW3!EI20) | ¬¬IF(ISBLANK(DPWW3!EJ20),"",DPWW3!EJ20) | ¬¬IF(ISBLANK(DPWW3!EK20),"",DPWW3!EK20) | ¬¬IF(ISBLANK(DPWW3!EL20),"",DPWW3!EL20) | ¬¬IF(ISBLANK(DPWW3!EM20),"",DPWW3!EM20)
¬¬A854 | ¬¬IF(ISBLANK(DPWW3!MA20),"",DPWW3!MA20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO20),"",DPWW3!EO20) | ¬¬IF(ISBLANK(DPWW3!EP20),"",DPWW3!EP20) | ¬¬IF(ISBLANK(DPWW3!EQ20),"",DPWW3!EQ20) | ¬¬IF(ISBLANK(DPWW3!ER20),"",DPWW3!ER20) | ¬¬IF(ISBLANK(DPWW3!ES20),"",DPWW3!ES20) | ¬¬IF(ISBLANK(DPWW3!ET20),"",DPWW3!ET20) | ¬¬IF(ISBLANK(DPWW3!EU20),"",DPWW3!EU20) | ¬¬IF(ISBLANK(DPWW3!EV20),"",DPWW3!EV20) | ¬¬IF(ISBLANK(DPWW3!EW20),"",DPWW3!EW20) | ¬¬IF(ISBLANK(DPWW3!EX20),"",DPWW3!EX20) | ¬¬IF(ISBLANK(DPWW3!EY20),"",DPWW3!EY20) | ¬¬IF(ISBLANK(DPWW3!EZ20),"",DPWW3!EZ20) | ¬¬IF(ISBLANK(DPWW3!FA20),"",DPWW3!FA20) | ¬¬IF(ISBLANK(DPWW3!FB20),"",DPWW3!FB20) | ¬¬IF(ISBLANK(DPWW3!FC20),"",DPWW3!FC20) | ¬¬IF(ISBLANK(DPWW3!FD20),"",DPWW3!FD20) | ¬¬IF(ISBLANK(DPWW3!FE20),"",DPWW3!FE20) | ¬¬IF(ISBLANK(DPWW3!FF20),"",DPWW3!FF20) | ¬¬IF(ISBLANK(DPWW3!FG20),"",DPWW3!FG20) | ¬¬IF(ISBLANK(DPWW3!FH20),"",DPWW3!FH20) | ¬¬IF(ISBLANK(DPWW3!FI20),"",DPWW3!FI20)
¬¬A855 | ¬¬IF(ISBLANK(DPWW3!MW20),"",DPWW3!MW20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK20),"",DPWW3!FK20) | ¬¬IF(ISBLANK(DPWW3!FL20),"",DPWW3!FL20) | ¬¬IF(ISBLANK(DPWW3!FM20),"",DPWW3!FM20) | ¬¬IF(ISBLANK(DPWW3!FN20),"",DPWW3!FN20) | ¬¬IF(ISBLANK(DPWW3!FO20),"",DPWW3!FO20) | ¬¬IF(ISBLANK(DPWW3!FP20),"",DPWW3!FP20) | ¬¬IF(ISBLANK(DPWW3!FQ20),"",DPWW3!FQ20) | ¬¬IF(ISBLANK(DPWW3!FR20),"",DPWW3!FR20) | ¬¬IF(ISBLANK(DPWW3!FS20),"",DPWW3!FS20) | ¬¬IF(ISBLANK(DPWW3!FT20),"",DPWW3!FT20) | ¬¬IF(ISBLANK(DPWW3!FU20),"",DPWW3!FU20) | ¬¬IF(ISBLANK(DPWW3!FV20),"",DPWW3!FV20) | ¬¬IF(ISBLANK(DPWW3!FW20),"",DPWW3!FW20) | ¬¬IF(ISBLANK(DPWW3!FX20),"",DPWW3!FX20) | ¬¬IF(ISBLANK(DPWW3!FY20),"",DPWW3!FY20) | ¬¬IF(ISBLANK(DPWW3!FZ20),"",DPWW3!FZ20) | ¬¬IF(ISBLANK(DPWW3!GA20),"",DPWW3!GA20) | ¬¬IF(ISBLANK(DPWW3!GB20),"",DPWW3!GB20) | ¬¬IF(ISBLANK(DPWW3!GC20),"",DPWW3!GC20) | ¬¬IF(ISBLANK(DPWW3!GD20),"",DPWW3!GD20) | ¬¬IF(ISBLANK(DPWW3!GE20),"",DPWW3!GE20)
¬¬A856 | ¬¬IF(ISBLANK(DPWW3!NS20),"",DPWW3!NS20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GG20),"",DPWW3!GG20)
¬¬A857 | ¬¬IF(ISBLANK(DPWW3!NT20),"",DPWW3!NT20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GH20),"",DPWW3!GH20)
¬¬A858 | ¬¬IF(ISBLANK(DPWW3!NU20),"",DPWW3!NU20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GI20),"",DPWW3!GI20)
¬¬A859 | ¬¬IF(ISBLANK(DPWW3!NV20),"",DPWW3!NV20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ20),"",DPWW3!GJ20)
¬¬A860 | ¬¬IF(ISBLANK(DPWW3!NW20),"",DPWW3!NW20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GK20),"",DPWW3!GK20)
¬¬A861 | ¬¬IF(ISBLANK(DPWW3!NX20),"",DPWW3!NX20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GL20),"",DPWW3!GL20)
¬¬A862 | ¬¬IF(ISBLANK(DPWW3!NY20),"",DPWW3!NY20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GM20),"",DPWW3!GM20)
¬¬A863 | ¬¬IF(ISBLANK(DPWW3!NZ20),"",DPWW3!NZ20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GN20),"",DPWW3!GN20)
¬¬A864 | ¬¬IF(ISBLANK(DPWW3!OA20),"",DPWW3!OA20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GO20),"",DPWW3!GO20)
¬¬A865 | ¬¬IF(ISBLANK(DPWW3!OB20),"",DPWW3!OB20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GP20),"",DPWW3!GP20)
¬¬A866 | ¬¬IF(ISBLANK(DPWW3!OC20),"",DPWW3!OC20) | ¬¬DPWW3!F20 & "," & DPWW3!G20 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H20),"",DPWW3!H20) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ20),"",DPWW3!GQ20)
¬¬A867 | ¬¬IF(ISBLANK(DPWW3!GW21),"",DPWW3!GW21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!K21),"",DPWW3!K21)
¬¬A868 | ¬¬IF(ISBLANK(DPWW3!GY21),"",DPWW3!GY21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M21),"",DPWW3!M21) | ¬¬IF(ISBLANK(DPWW3!N21),"",DPWW3!N21) | ¬¬IF(ISBLANK(DPWW3!O21),"",DPWW3!O21) | ¬¬IF(ISBLANK(DPWW3!P21),"",DPWW3!P21) | ¬¬IF(ISBLANK(DPWW3!Q21),"",DPWW3!Q21) | ¬¬IF(ISBLANK(DPWW3!R21),"",DPWW3!R21) | ¬¬IF(ISBLANK(DPWW3!S21),"",DPWW3!S21) | ¬¬IF(ISBLANK(DPWW3!T21),"",DPWW3!T21) | ¬¬IF(ISBLANK(DPWW3!U21),"",DPWW3!U21) | ¬¬IF(ISBLANK(DPWW3!V21),"",DPWW3!V21) | ¬¬IF(ISBLANK(DPWW3!W21),"",DPWW3!W21) | ¬¬IF(ISBLANK(DPWW3!X21),"",DPWW3!X21) | ¬¬IF(ISBLANK(DPWW3!Y21),"",DPWW3!Y21) | ¬¬IF(ISBLANK(DPWW3!Z21),"",DPWW3!Z21) | ¬¬IF(ISBLANK(DPWW3!AA21),"",DPWW3!AA21) | ¬¬IF(ISBLANK(DPWW3!AB21),"",DPWW3!AB21) | ¬¬IF(ISBLANK(DPWW3!AC21),"",DPWW3!AC21) | ¬¬IF(ISBLANK(DPWW3!AD21),"",DPWW3!AD21) | ¬¬IF(ISBLANK(DPWW3!AE21),"",DPWW3!AE21) | ¬¬IF(ISBLANK(DPWW3!AF21),"",DPWW3!AF21) | ¬¬IF(ISBLANK(DPWW3!AG21),"",DPWW3!AG21)
¬¬A869 | ¬¬IF(ISBLANK(DPWW3!HU21),"",DPWW3!HU21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI21),"",DPWW3!AI21) | ¬¬IF(ISBLANK(DPWW3!AJ21),"",DPWW3!AJ21) | ¬¬IF(ISBLANK(DPWW3!AK21),"",DPWW3!AK21) | ¬¬IF(ISBLANK(DPWW3!AL21),"",DPWW3!AL21) | ¬¬IF(ISBLANK(DPWW3!AM21),"",DPWW3!AM21) | ¬¬IF(ISBLANK(DPWW3!AN21),"",DPWW3!AN21) | ¬¬IF(ISBLANK(DPWW3!AO21),"",DPWW3!AO21) | ¬¬IF(ISBLANK(DPWW3!AP21),"",DPWW3!AP21) | ¬¬IF(ISBLANK(DPWW3!AQ21),"",DPWW3!AQ21) | ¬¬IF(ISBLANK(DPWW3!AR21),"",DPWW3!AR21) | ¬¬IF(ISBLANK(DPWW3!AS21),"",DPWW3!AS21) | ¬¬IF(ISBLANK(DPWW3!AT21),"",DPWW3!AT21) | ¬¬IF(ISBLANK(DPWW3!AU21),"",DPWW3!AU21) | ¬¬IF(ISBLANK(DPWW3!AV21),"",DPWW3!AV21) | ¬¬IF(ISBLANK(DPWW3!AW21),"",DPWW3!AW21) | ¬¬IF(ISBLANK(DPWW3!AX21),"",DPWW3!AX21) | ¬¬IF(ISBLANK(DPWW3!AY21),"",DPWW3!AY21) | ¬¬IF(ISBLANK(DPWW3!AZ21),"",DPWW3!AZ21) | ¬¬IF(ISBLANK(DPWW3!BA21),"",DPWW3!BA21) | ¬¬IF(ISBLANK(DPWW3!BB21),"",DPWW3!BB21) | ¬¬IF(ISBLANK(DPWW3!BC21),"",DPWW3!BC21)
¬¬A870 | ¬¬IF(ISBLANK(DPWW3!IQ21),"",DPWW3!IQ21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE21),"",DPWW3!BE21) | ¬¬IF(ISBLANK(DPWW3!BF21),"",DPWW3!BF21) | ¬¬IF(ISBLANK(DPWW3!BG21),"",DPWW3!BG21) | ¬¬IF(ISBLANK(DPWW3!BH21),"",DPWW3!BH21) | ¬¬IF(ISBLANK(DPWW3!BI21),"",DPWW3!BI21) | ¬¬IF(ISBLANK(DPWW3!BJ21),"",DPWW3!BJ21) | ¬¬IF(ISBLANK(DPWW3!BK21),"",DPWW3!BK21) | ¬¬IF(ISBLANK(DPWW3!BL21),"",DPWW3!BL21) | ¬¬IF(ISBLANK(DPWW3!BM21),"",DPWW3!BM21) | ¬¬IF(ISBLANK(DPWW3!BN21),"",DPWW3!BN21) | ¬¬IF(ISBLANK(DPWW3!BO21),"",DPWW3!BO21) | ¬¬IF(ISBLANK(DPWW3!BP21),"",DPWW3!BP21) | ¬¬IF(ISBLANK(DPWW3!BQ21),"",DPWW3!BQ21) | ¬¬IF(ISBLANK(DPWW3!BR21),"",DPWW3!BR21) | ¬¬IF(ISBLANK(DPWW3!BS21),"",DPWW3!BS21) | ¬¬IF(ISBLANK(DPWW3!BT21),"",DPWW3!BT21) | ¬¬IF(ISBLANK(DPWW3!BU21),"",DPWW3!BU21) | ¬¬IF(ISBLANK(DPWW3!BV21),"",DPWW3!BV21) | ¬¬IF(ISBLANK(DPWW3!BW21),"",DPWW3!BW21) | ¬¬IF(ISBLANK(DPWW3!BX21),"",DPWW3!BX21) | ¬¬IF(ISBLANK(DPWW3!BY21),"",DPWW3!BY21)
¬¬A871 | ¬¬IF(ISBLANK(DPWW3!JM21),"",DPWW3!JM21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA21),"",DPWW3!CA21) | ¬¬IF(ISBLANK(DPWW3!CB21),"",DPWW3!CB21) | ¬¬IF(ISBLANK(DPWW3!CC21),"",DPWW3!CC21) | ¬¬IF(ISBLANK(DPWW3!CD21),"",DPWW3!CD21) | ¬¬IF(ISBLANK(DPWW3!CE21),"",DPWW3!CE21) | ¬¬IF(ISBLANK(DPWW3!CF21),"",DPWW3!CF21) | ¬¬IF(ISBLANK(DPWW3!CG21),"",DPWW3!CG21) | ¬¬IF(ISBLANK(DPWW3!CH21),"",DPWW3!CH21) | ¬¬IF(ISBLANK(DPWW3!CI21),"",DPWW3!CI21) | ¬¬IF(ISBLANK(DPWW3!CJ21),"",DPWW3!CJ21) | ¬¬IF(ISBLANK(DPWW3!CK21),"",DPWW3!CK21) | ¬¬IF(ISBLANK(DPWW3!CL21),"",DPWW3!CL21) | ¬¬IF(ISBLANK(DPWW3!CM21),"",DPWW3!CM21) | ¬¬IF(ISBLANK(DPWW3!CN21),"",DPWW3!CN21) | ¬¬IF(ISBLANK(DPWW3!CO21),"",DPWW3!CO21) | ¬¬IF(ISBLANK(DPWW3!CP21),"",DPWW3!CP21) | ¬¬IF(ISBLANK(DPWW3!CQ21),"",DPWW3!CQ21) | ¬¬IF(ISBLANK(DPWW3!CR21),"",DPWW3!CR21) | ¬¬IF(ISBLANK(DPWW3!CS21),"",DPWW3!CS21) | ¬¬IF(ISBLANK(DPWW3!CT21),"",DPWW3!CT21) | ¬¬IF(ISBLANK(DPWW3!CU21),"",DPWW3!CU21)
¬¬A872 | ¬¬IF(ISBLANK(DPWW3!KI21),"",DPWW3!KI21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW21),"",DPWW3!CW21) | ¬¬IF(ISBLANK(DPWW3!CX21),"",DPWW3!CX21) | ¬¬IF(ISBLANK(DPWW3!CY21),"",DPWW3!CY21) | ¬¬IF(ISBLANK(DPWW3!CZ21),"",DPWW3!CZ21) | ¬¬IF(ISBLANK(DPWW3!DA21),"",DPWW3!DA21) | ¬¬IF(ISBLANK(DPWW3!DB21),"",DPWW3!DB21) | ¬¬IF(ISBLANK(DPWW3!DC21),"",DPWW3!DC21) | ¬¬IF(ISBLANK(DPWW3!DD21),"",DPWW3!DD21) | ¬¬IF(ISBLANK(DPWW3!DE21),"",DPWW3!DE21) | ¬¬IF(ISBLANK(DPWW3!DF21),"",DPWW3!DF21) | ¬¬IF(ISBLANK(DPWW3!DG21),"",DPWW3!DG21) | ¬¬IF(ISBLANK(DPWW3!DH21),"",DPWW3!DH21) | ¬¬IF(ISBLANK(DPWW3!DI21),"",DPWW3!DI21) | ¬¬IF(ISBLANK(DPWW3!DJ21),"",DPWW3!DJ21) | ¬¬IF(ISBLANK(DPWW3!DK21),"",DPWW3!DK21) | ¬¬IF(ISBLANK(DPWW3!DL21),"",DPWW3!DL21) | ¬¬IF(ISBLANK(DPWW3!DM21),"",DPWW3!DM21) | ¬¬IF(ISBLANK(DPWW3!DN21),"",DPWW3!DN21) | ¬¬IF(ISBLANK(DPWW3!DO21),"",DPWW3!DO21) | ¬¬IF(ISBLANK(DPWW3!DP21),"",DPWW3!DP21) | ¬¬IF(ISBLANK(DPWW3!DQ21),"",DPWW3!DQ21)
¬¬A873 | ¬¬IF(ISBLANK(DPWW3!LE21),"",DPWW3!LE21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS21),"",DPWW3!DS21) | ¬¬IF(ISBLANK(DPWW3!DT21),"",DPWW3!DT21) | ¬¬IF(ISBLANK(DPWW3!DU21),"",DPWW3!DU21) | ¬¬IF(ISBLANK(DPWW3!DV21),"",DPWW3!DV21) | ¬¬IF(ISBLANK(DPWW3!DW21),"",DPWW3!DW21) | ¬¬IF(ISBLANK(DPWW3!DX21),"",DPWW3!DX21) | ¬¬IF(ISBLANK(DPWW3!DY21),"",DPWW3!DY21) | ¬¬IF(ISBLANK(DPWW3!DZ21),"",DPWW3!DZ21) | ¬¬IF(ISBLANK(DPWW3!EA21),"",DPWW3!EA21) | ¬¬IF(ISBLANK(DPWW3!EB21),"",DPWW3!EB21) | ¬¬IF(ISBLANK(DPWW3!EC21),"",DPWW3!EC21) | ¬¬IF(ISBLANK(DPWW3!ED21),"",DPWW3!ED21) | ¬¬IF(ISBLANK(DPWW3!EE21),"",DPWW3!EE21) | ¬¬IF(ISBLANK(DPWW3!EF21),"",DPWW3!EF21) | ¬¬IF(ISBLANK(DPWW3!EG21),"",DPWW3!EG21) | ¬¬IF(ISBLANK(DPWW3!EH21),"",DPWW3!EH21) | ¬¬IF(ISBLANK(DPWW3!EI21),"",DPWW3!EI21) | ¬¬IF(ISBLANK(DPWW3!EJ21),"",DPWW3!EJ21) | ¬¬IF(ISBLANK(DPWW3!EK21),"",DPWW3!EK21) | ¬¬IF(ISBLANK(DPWW3!EL21),"",DPWW3!EL21) | ¬¬IF(ISBLANK(DPWW3!EM21),"",DPWW3!EM21)
¬¬A874 | ¬¬IF(ISBLANK(DPWW3!MA21),"",DPWW3!MA21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO21),"",DPWW3!EO21) | ¬¬IF(ISBLANK(DPWW3!EP21),"",DPWW3!EP21) | ¬¬IF(ISBLANK(DPWW3!EQ21),"",DPWW3!EQ21) | ¬¬IF(ISBLANK(DPWW3!ER21),"",DPWW3!ER21) | ¬¬IF(ISBLANK(DPWW3!ES21),"",DPWW3!ES21) | ¬¬IF(ISBLANK(DPWW3!ET21),"",DPWW3!ET21) | ¬¬IF(ISBLANK(DPWW3!EU21),"",DPWW3!EU21) | ¬¬IF(ISBLANK(DPWW3!EV21),"",DPWW3!EV21) | ¬¬IF(ISBLANK(DPWW3!EW21),"",DPWW3!EW21) | ¬¬IF(ISBLANK(DPWW3!EX21),"",DPWW3!EX21) | ¬¬IF(ISBLANK(DPWW3!EY21),"",DPWW3!EY21) | ¬¬IF(ISBLANK(DPWW3!EZ21),"",DPWW3!EZ21) | ¬¬IF(ISBLANK(DPWW3!FA21),"",DPWW3!FA21) | ¬¬IF(ISBLANK(DPWW3!FB21),"",DPWW3!FB21) | ¬¬IF(ISBLANK(DPWW3!FC21),"",DPWW3!FC21) | ¬¬IF(ISBLANK(DPWW3!FD21),"",DPWW3!FD21) | ¬¬IF(ISBLANK(DPWW3!FE21),"",DPWW3!FE21) | ¬¬IF(ISBLANK(DPWW3!FF21),"",DPWW3!FF21) | ¬¬IF(ISBLANK(DPWW3!FG21),"",DPWW3!FG21) | ¬¬IF(ISBLANK(DPWW3!FH21),"",DPWW3!FH21) | ¬¬IF(ISBLANK(DPWW3!FI21),"",DPWW3!FI21)
¬¬A875 | ¬¬IF(ISBLANK(DPWW3!MW21),"",DPWW3!MW21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK21),"",DPWW3!FK21) | ¬¬IF(ISBLANK(DPWW3!FL21),"",DPWW3!FL21) | ¬¬IF(ISBLANK(DPWW3!FM21),"",DPWW3!FM21) | ¬¬IF(ISBLANK(DPWW3!FN21),"",DPWW3!FN21) | ¬¬IF(ISBLANK(DPWW3!FO21),"",DPWW3!FO21) | ¬¬IF(ISBLANK(DPWW3!FP21),"",DPWW3!FP21) | ¬¬IF(ISBLANK(DPWW3!FQ21),"",DPWW3!FQ21) | ¬¬IF(ISBLANK(DPWW3!FR21),"",DPWW3!FR21) | ¬¬IF(ISBLANK(DPWW3!FS21),"",DPWW3!FS21) | ¬¬IF(ISBLANK(DPWW3!FT21),"",DPWW3!FT21) | ¬¬IF(ISBLANK(DPWW3!FU21),"",DPWW3!FU21) | ¬¬IF(ISBLANK(DPWW3!FV21),"",DPWW3!FV21) | ¬¬IF(ISBLANK(DPWW3!FW21),"",DPWW3!FW21) | ¬¬IF(ISBLANK(DPWW3!FX21),"",DPWW3!FX21) | ¬¬IF(ISBLANK(DPWW3!FY21),"",DPWW3!FY21) | ¬¬IF(ISBLANK(DPWW3!FZ21),"",DPWW3!FZ21) | ¬¬IF(ISBLANK(DPWW3!GA21),"",DPWW3!GA21) | ¬¬IF(ISBLANK(DPWW3!GB21),"",DPWW3!GB21) | ¬¬IF(ISBLANK(DPWW3!GC21),"",DPWW3!GC21) | ¬¬IF(ISBLANK(DPWW3!GD21),"",DPWW3!GD21) | ¬¬IF(ISBLANK(DPWW3!GE21),"",DPWW3!GE21)
¬¬A876 | ¬¬IF(ISBLANK(DPWW3!NS21),"",DPWW3!NS21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GG21),"",DPWW3!GG21)
¬¬A877 | ¬¬IF(ISBLANK(DPWW3!NT21),"",DPWW3!NT21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GH21),"",DPWW3!GH21)
¬¬A878 | ¬¬IF(ISBLANK(DPWW3!NU21),"",DPWW3!NU21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GI21),"",DPWW3!GI21)
¬¬A879 | ¬¬IF(ISBLANK(DPWW3!NV21),"",DPWW3!NV21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ21),"",DPWW3!GJ21)
¬¬A880 | ¬¬IF(ISBLANK(DPWW3!NW21),"",DPWW3!NW21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GK21),"",DPWW3!GK21)
¬¬A881 | ¬¬IF(ISBLANK(DPWW3!NX21),"",DPWW3!NX21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GL21),"",DPWW3!GL21)
¬¬A882 | ¬¬IF(ISBLANK(DPWW3!NY21),"",DPWW3!NY21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GM21),"",DPWW3!GM21)
¬¬A883 | ¬¬IF(ISBLANK(DPWW3!NZ21),"",DPWW3!NZ21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GN21),"",DPWW3!GN21)
¬¬A884 | ¬¬IF(ISBLANK(DPWW3!OA21),"",DPWW3!OA21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GO21),"",DPWW3!GO21)
¬¬A885 | ¬¬IF(ISBLANK(DPWW3!OB21),"",DPWW3!OB21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GP21),"",DPWW3!GP21)
¬¬A886 | ¬¬IF(ISBLANK(DPWW3!OC21),"",DPWW3!OC21) | ¬¬DPWW3!F21 & "," & DPWW3!G21 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H21),"",DPWW3!H21) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ21),"",DPWW3!GQ21)
¬¬A887 | ¬¬IF(ISBLANK(DPWW3!GW22),"",DPWW3!GW22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!GW5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!K22),"",DPWW3!K22)
¬¬A888 | ¬¬IF(ISBLANK(DPWW3!GY22),"",DPWW3!GY22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!GY5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!M22),"",DPWW3!M22) | ¬¬IF(ISBLANK(DPWW3!N22),"",DPWW3!N22) | ¬¬IF(ISBLANK(DPWW3!O22),"",DPWW3!O22) | ¬¬IF(ISBLANK(DPWW3!P22),"",DPWW3!P22) | ¬¬IF(ISBLANK(DPWW3!Q22),"",DPWW3!Q22) | ¬¬IF(ISBLANK(DPWW3!R22),"",DPWW3!R22) | ¬¬IF(ISBLANK(DPWW3!S22),"",DPWW3!S22) | ¬¬IF(ISBLANK(DPWW3!T22),"",DPWW3!T22) | ¬¬IF(ISBLANK(DPWW3!U22),"",DPWW3!U22) | ¬¬IF(ISBLANK(DPWW3!V22),"",DPWW3!V22) | ¬¬IF(ISBLANK(DPWW3!W22),"",DPWW3!W22) | ¬¬IF(ISBLANK(DPWW3!X22),"",DPWW3!X22) | ¬¬IF(ISBLANK(DPWW3!Y22),"",DPWW3!Y22) | ¬¬IF(ISBLANK(DPWW3!Z22),"",DPWW3!Z22) | ¬¬IF(ISBLANK(DPWW3!AA22),"",DPWW3!AA22) | ¬¬IF(ISBLANK(DPWW3!AB22),"",DPWW3!AB22) | ¬¬IF(ISBLANK(DPWW3!AC22),"",DPWW3!AC22) | ¬¬IF(ISBLANK(DPWW3!AD22),"",DPWW3!AD22) | ¬¬IF(ISBLANK(DPWW3!AE22),"",DPWW3!AE22) | ¬¬IF(ISBLANK(DPWW3!AF22),"",DPWW3!AF22) | ¬¬IF(ISBLANK(DPWW3!AG22),"",DPWW3!AG22)
¬¬A889 | ¬¬IF(ISBLANK(DPWW3!HU22),"",DPWW3!HU22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!HU5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!AI22),"",DPWW3!AI22) | ¬¬IF(ISBLANK(DPWW3!AJ22),"",DPWW3!AJ22) | ¬¬IF(ISBLANK(DPWW3!AK22),"",DPWW3!AK22) | ¬¬IF(ISBLANK(DPWW3!AL22),"",DPWW3!AL22) | ¬¬IF(ISBLANK(DPWW3!AM22),"",DPWW3!AM22) | ¬¬IF(ISBLANK(DPWW3!AN22),"",DPWW3!AN22) | ¬¬IF(ISBLANK(DPWW3!AO22),"",DPWW3!AO22) | ¬¬IF(ISBLANK(DPWW3!AP22),"",DPWW3!AP22) | ¬¬IF(ISBLANK(DPWW3!AQ22),"",DPWW3!AQ22) | ¬¬IF(ISBLANK(DPWW3!AR22),"",DPWW3!AR22) | ¬¬IF(ISBLANK(DPWW3!AS22),"",DPWW3!AS22) | ¬¬IF(ISBLANK(DPWW3!AT22),"",DPWW3!AT22) | ¬¬IF(ISBLANK(DPWW3!AU22),"",DPWW3!AU22) | ¬¬IF(ISBLANK(DPWW3!AV22),"",DPWW3!AV22) | ¬¬IF(ISBLANK(DPWW3!AW22),"",DPWW3!AW22) | ¬¬IF(ISBLANK(DPWW3!AX22),"",DPWW3!AX22) | ¬¬IF(ISBLANK(DPWW3!AY22),"",DPWW3!AY22) | ¬¬IF(ISBLANK(DPWW3!AZ22),"",DPWW3!AZ22) | ¬¬IF(ISBLANK(DPWW3!BA22),"",DPWW3!BA22) | ¬¬IF(ISBLANK(DPWW3!BB22),"",DPWW3!BB22) | ¬¬IF(ISBLANK(DPWW3!BC22),"",DPWW3!BC22)
¬¬A890 | ¬¬IF(ISBLANK(DPWW3!IQ22),"",DPWW3!IQ22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!IQ5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!BE22),"",DPWW3!BE22) | ¬¬IF(ISBLANK(DPWW3!BF22),"",DPWW3!BF22) | ¬¬IF(ISBLANK(DPWW3!BG22),"",DPWW3!BG22) | ¬¬IF(ISBLANK(DPWW3!BH22),"",DPWW3!BH22) | ¬¬IF(ISBLANK(DPWW3!BI22),"",DPWW3!BI22) | ¬¬IF(ISBLANK(DPWW3!BJ22),"",DPWW3!BJ22) | ¬¬IF(ISBLANK(DPWW3!BK22),"",DPWW3!BK22) | ¬¬IF(ISBLANK(DPWW3!BL22),"",DPWW3!BL22) | ¬¬IF(ISBLANK(DPWW3!BM22),"",DPWW3!BM22) | ¬¬IF(ISBLANK(DPWW3!BN22),"",DPWW3!BN22) | ¬¬IF(ISBLANK(DPWW3!BO22),"",DPWW3!BO22) | ¬¬IF(ISBLANK(DPWW3!BP22),"",DPWW3!BP22) | ¬¬IF(ISBLANK(DPWW3!BQ22),"",DPWW3!BQ22) | ¬¬IF(ISBLANK(DPWW3!BR22),"",DPWW3!BR22) | ¬¬IF(ISBLANK(DPWW3!BS22),"",DPWW3!BS22) | ¬¬IF(ISBLANK(DPWW3!BT22),"",DPWW3!BT22) | ¬¬IF(ISBLANK(DPWW3!BU22),"",DPWW3!BU22) | ¬¬IF(ISBLANK(DPWW3!BV22),"",DPWW3!BV22) | ¬¬IF(ISBLANK(DPWW3!BW22),"",DPWW3!BW22) | ¬¬IF(ISBLANK(DPWW3!BX22),"",DPWW3!BX22) | ¬¬IF(ISBLANK(DPWW3!BY22),"",DPWW3!BY22)
¬¬A891 | ¬¬IF(ISBLANK(DPWW3!JM22),"",DPWW3!JM22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!JM5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CA22),"",DPWW3!CA22) | ¬¬IF(ISBLANK(DPWW3!CB22),"",DPWW3!CB22) | ¬¬IF(ISBLANK(DPWW3!CC22),"",DPWW3!CC22) | ¬¬IF(ISBLANK(DPWW3!CD22),"",DPWW3!CD22) | ¬¬IF(ISBLANK(DPWW3!CE22),"",DPWW3!CE22) | ¬¬IF(ISBLANK(DPWW3!CF22),"",DPWW3!CF22) | ¬¬IF(ISBLANK(DPWW3!CG22),"",DPWW3!CG22) | ¬¬IF(ISBLANK(DPWW3!CH22),"",DPWW3!CH22) | ¬¬IF(ISBLANK(DPWW3!CI22),"",DPWW3!CI22) | ¬¬IF(ISBLANK(DPWW3!CJ22),"",DPWW3!CJ22) | ¬¬IF(ISBLANK(DPWW3!CK22),"",DPWW3!CK22) | ¬¬IF(ISBLANK(DPWW3!CL22),"",DPWW3!CL22) | ¬¬IF(ISBLANK(DPWW3!CM22),"",DPWW3!CM22) | ¬¬IF(ISBLANK(DPWW3!CN22),"",DPWW3!CN22) | ¬¬IF(ISBLANK(DPWW3!CO22),"",DPWW3!CO22) | ¬¬IF(ISBLANK(DPWW3!CP22),"",DPWW3!CP22) | ¬¬IF(ISBLANK(DPWW3!CQ22),"",DPWW3!CQ22) | ¬¬IF(ISBLANK(DPWW3!CR22),"",DPWW3!CR22) | ¬¬IF(ISBLANK(DPWW3!CS22),"",DPWW3!CS22) | ¬¬IF(ISBLANK(DPWW3!CT22),"",DPWW3!CT22) | ¬¬IF(ISBLANK(DPWW3!CU22),"",DPWW3!CU22)
¬¬A892 | ¬¬IF(ISBLANK(DPWW3!KI22),"",DPWW3!KI22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!KI5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!CW22),"",DPWW3!CW22) | ¬¬IF(ISBLANK(DPWW3!CX22),"",DPWW3!CX22) | ¬¬IF(ISBLANK(DPWW3!CY22),"",DPWW3!CY22) | ¬¬IF(ISBLANK(DPWW3!CZ22),"",DPWW3!CZ22) | ¬¬IF(ISBLANK(DPWW3!DA22),"",DPWW3!DA22) | ¬¬IF(ISBLANK(DPWW3!DB22),"",DPWW3!DB22) | ¬¬IF(ISBLANK(DPWW3!DC22),"",DPWW3!DC22) | ¬¬IF(ISBLANK(DPWW3!DD22),"",DPWW3!DD22) | ¬¬IF(ISBLANK(DPWW3!DE22),"",DPWW3!DE22) | ¬¬IF(ISBLANK(DPWW3!DF22),"",DPWW3!DF22) | ¬¬IF(ISBLANK(DPWW3!DG22),"",DPWW3!DG22) | ¬¬IF(ISBLANK(DPWW3!DH22),"",DPWW3!DH22) | ¬¬IF(ISBLANK(DPWW3!DI22),"",DPWW3!DI22) | ¬¬IF(ISBLANK(DPWW3!DJ22),"",DPWW3!DJ22) | ¬¬IF(ISBLANK(DPWW3!DK22),"",DPWW3!DK22) | ¬¬IF(ISBLANK(DPWW3!DL22),"",DPWW3!DL22) | ¬¬IF(ISBLANK(DPWW3!DM22),"",DPWW3!DM22) | ¬¬IF(ISBLANK(DPWW3!DN22),"",DPWW3!DN22) | ¬¬IF(ISBLANK(DPWW3!DO22),"",DPWW3!DO22) | ¬¬IF(ISBLANK(DPWW3!DP22),"",DPWW3!DP22) | ¬¬IF(ISBLANK(DPWW3!DQ22),"",DPWW3!DQ22)
¬¬A893 | ¬¬IF(ISBLANK(DPWW3!LE22),"",DPWW3!LE22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!LE5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!DS22),"",DPWW3!DS22) | ¬¬IF(ISBLANK(DPWW3!DT22),"",DPWW3!DT22) | ¬¬IF(ISBLANK(DPWW3!DU22),"",DPWW3!DU22) | ¬¬IF(ISBLANK(DPWW3!DV22),"",DPWW3!DV22) | ¬¬IF(ISBLANK(DPWW3!DW22),"",DPWW3!DW22) | ¬¬IF(ISBLANK(DPWW3!DX22),"",DPWW3!DX22) | ¬¬IF(ISBLANK(DPWW3!DY22),"",DPWW3!DY22) | ¬¬IF(ISBLANK(DPWW3!DZ22),"",DPWW3!DZ22) | ¬¬IF(ISBLANK(DPWW3!EA22),"",DPWW3!EA22) | ¬¬IF(ISBLANK(DPWW3!EB22),"",DPWW3!EB22) | ¬¬IF(ISBLANK(DPWW3!EC22),"",DPWW3!EC22) | ¬¬IF(ISBLANK(DPWW3!ED22),"",DPWW3!ED22) | ¬¬IF(ISBLANK(DPWW3!EE22),"",DPWW3!EE22) | ¬¬IF(ISBLANK(DPWW3!EF22),"",DPWW3!EF22) | ¬¬IF(ISBLANK(DPWW3!EG22),"",DPWW3!EG22) | ¬¬IF(ISBLANK(DPWW3!EH22),"",DPWW3!EH22) | ¬¬IF(ISBLANK(DPWW3!EI22),"",DPWW3!EI22) | ¬¬IF(ISBLANK(DPWW3!EJ22),"",DPWW3!EJ22) | ¬¬IF(ISBLANK(DPWW3!EK22),"",DPWW3!EK22) | ¬¬IF(ISBLANK(DPWW3!EL22),"",DPWW3!EL22) | ¬¬IF(ISBLANK(DPWW3!EM22),"",DPWW3!EM22)
¬¬A894 | ¬¬IF(ISBLANK(DPWW3!MA22),"",DPWW3!MA22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!MA5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!EO22),"",DPWW3!EO22) | ¬¬IF(ISBLANK(DPWW3!EP22),"",DPWW3!EP22) | ¬¬IF(ISBLANK(DPWW3!EQ22),"",DPWW3!EQ22) | ¬¬IF(ISBLANK(DPWW3!ER22),"",DPWW3!ER22) | ¬¬IF(ISBLANK(DPWW3!ES22),"",DPWW3!ES22) | ¬¬IF(ISBLANK(DPWW3!ET22),"",DPWW3!ET22) | ¬¬IF(ISBLANK(DPWW3!EU22),"",DPWW3!EU22) | ¬¬IF(ISBLANK(DPWW3!EV22),"",DPWW3!EV22) | ¬¬IF(ISBLANK(DPWW3!EW22),"",DPWW3!EW22) | ¬¬IF(ISBLANK(DPWW3!EX22),"",DPWW3!EX22) | ¬¬IF(ISBLANK(DPWW3!EY22),"",DPWW3!EY22) | ¬¬IF(ISBLANK(DPWW3!EZ22),"",DPWW3!EZ22) | ¬¬IF(ISBLANK(DPWW3!FA22),"",DPWW3!FA22) | ¬¬IF(ISBLANK(DPWW3!FB22),"",DPWW3!FB22) | ¬¬IF(ISBLANK(DPWW3!FC22),"",DPWW3!FC22) | ¬¬IF(ISBLANK(DPWW3!FD22),"",DPWW3!FD22) | ¬¬IF(ISBLANK(DPWW3!FE22),"",DPWW3!FE22) | ¬¬IF(ISBLANK(DPWW3!FF22),"",DPWW3!FF22) | ¬¬IF(ISBLANK(DPWW3!FG22),"",DPWW3!FG22) | ¬¬IF(ISBLANK(DPWW3!FH22),"",DPWW3!FH22) | ¬¬IF(ISBLANK(DPWW3!FI22),"",DPWW3!FI22)
¬¬A895 | ¬¬IF(ISBLANK(DPWW3!MW22),"",DPWW3!MW22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!MW5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | [14 empty] | ¬¬IF(ISBLANK(DPWW3!FK22),"",DPWW3!FK22) | ¬¬IF(ISBLANK(DPWW3!FL22),"",DPWW3!FL22) | ¬¬IF(ISBLANK(DPWW3!FM22),"",DPWW3!FM22) | ¬¬IF(ISBLANK(DPWW3!FN22),"",DPWW3!FN22) | ¬¬IF(ISBLANK(DPWW3!FO22),"",DPWW3!FO22) | ¬¬IF(ISBLANK(DPWW3!FP22),"",DPWW3!FP22) | ¬¬IF(ISBLANK(DPWW3!FQ22),"",DPWW3!FQ22) | ¬¬IF(ISBLANK(DPWW3!FR22),"",DPWW3!FR22) | ¬¬IF(ISBLANK(DPWW3!FS22),"",DPWW3!FS22) | ¬¬IF(ISBLANK(DPWW3!FT22),"",DPWW3!FT22) | ¬¬IF(ISBLANK(DPWW3!FU22),"",DPWW3!FU22) | ¬¬IF(ISBLANK(DPWW3!FV22),"",DPWW3!FV22) | ¬¬IF(ISBLANK(DPWW3!FW22),"",DPWW3!FW22) | ¬¬IF(ISBLANK(DPWW3!FX22),"",DPWW3!FX22) | ¬¬IF(ISBLANK(DPWW3!FY22),"",DPWW3!FY22) | ¬¬IF(ISBLANK(DPWW3!FZ22),"",DPWW3!FZ22) | ¬¬IF(ISBLANK(DPWW3!GA22),"",DPWW3!GA22) | ¬¬IF(ISBLANK(DPWW3!GB22),"",DPWW3!GB22) | ¬¬IF(ISBLANK(DPWW3!GC22),"",DPWW3!GC22) | ¬¬IF(ISBLANK(DPWW3!GD22),"",DPWW3!GD22) | ¬¬IF(ISBLANK(DPWW3!GE22),"",DPWW3!GE22)
¬¬A896 | ¬¬IF(ISBLANK(DPWW3!NS22),"",DPWW3!NS22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NS5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GG22),"",DPWW3!GG22)
¬¬A897 | ¬¬IF(ISBLANK(DPWW3!NT22),"",DPWW3!NT22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NT5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GH22),"",DPWW3!GH22)
¬¬A898 | ¬¬IF(ISBLANK(DPWW3!NU22),"",DPWW3!NU22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NU5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GI22),"",DPWW3!GI22)
¬¬A899 | ¬¬IF(ISBLANK(DPWW3!NV22),"",DPWW3!NV22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NV5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GJ22),"",DPWW3!GJ22)
¬¬A900 | ¬¬IF(ISBLANK(DPWW3!NW22),"",DPWW3!NW22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NW5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GK22),"",DPWW3!GK22)
¬¬A901 | ¬¬IF(ISBLANK(DPWW3!NX22),"",DPWW3!NX22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NX5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GL22),"",DPWW3!GL22)
¬¬A902 | ¬¬IF(ISBLANK(DPWW3!NY22),"",DPWW3!NY22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NY5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GM22),"",DPWW3!GM22)
¬¬A903 | ¬¬IF(ISBLANK(DPWW3!NZ22),"",DPWW3!NZ22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!NZ5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GN22),"",DPWW3!GN22)
¬¬A904 | ¬¬IF(ISBLANK(DPWW3!OA22),"",DPWW3!OA22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OA5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GO22),"",DPWW3!GO22)
¬¬A905 | ¬¬IF(ISBLANK(DPWW3!OB22),"",DPWW3!OB22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OB5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GP22),"",DPWW3!GP22)
¬¬A906 | ¬¬IF(ISBLANK(DPWW3!OC22),"",DPWW3!OC22) | ¬¬DPWW3!F22 & "," & DPWW3!G22 & "," & DPWW3!OC5 | ¬¬IF(ISBLANK(DPWW3!H22),"",DPWW3!H22) | Delta | ¬¬IF(ISBLANK(DPWW3!GQ22),"",DPWW3!GQ22)
¬¬A907 | ¬¬IF(ISBLANK('DPW1'!AW8),"",'DPW1'!AW8) | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K8),"",'DPW1'!K8) | ¬¬IF(ISBLANK('DPW1'!L8),"",'DPW1'!L8) | ¬¬IF(ISBLANK('DPW1'!M8),"",'DPW1'!M8) | ¬¬IF(ISBLANK('DPW1'!N8),"",'DPW1'!N8) | ¬¬IF(ISBLANK('DPW1'!O8),"",'DPW1'!O8) | ¬¬IF(ISBLANK('DPW1'!P8),"",'DPW1'!P8) | ¬¬IF(ISBLANK('DPW1'!Q8),"",'DPW1'!Q8) | ¬¬IF(ISBLANK('DPW1'!R8),"",'DPW1'!R8) | ¬¬IF(ISBLANK('DPW1'!S8),"",'DPW1'!S8) | ¬¬IF(ISBLANK('DPW1'!T8),"",'DPW1'!T8) | ¬¬IF(ISBLANK('DPW1'!U8),"",'DPW1'!U8) | ¬¬IF(ISBLANK('DPW1'!V8),"",'DPW1'!V8)
¬¬A908 | ¬¬IF(ISBLANK('DPW1'!BI8),"",'DPW1'!BI8) | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W8),"",'DPW1'!W8) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X8),"",'DPW1'!X8)
¬¬A909 | ¬¬IF(ISBLANK('DPW1'!BL8),"",'DPW1'!BL8) | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z8),"",'DPW1'!Z8) | ¬¬IF(ISBLANK('DPW1'!AA8),"",'DPW1'!AA8) | ¬¬IF(ISBLANK('DPW1'!AB8),"",'DPW1'!AB8) | ¬¬IF(ISBLANK('DPW1'!AC8),"",'DPW1'!AC8) | ¬¬IF(ISBLANK('DPW1'!AD8),"",'DPW1'!AD8) | ¬¬IF(ISBLANK('DPW1'!AE8),"",'DPW1'!AE8) | ¬¬IF(ISBLANK('DPW1'!AF8),"",'DPW1'!AF8) | ¬¬IF(ISBLANK('DPW1'!AG8),"",'DPW1'!AG8) | ¬¬IF(ISBLANK('DPW1'!AH8),"",'DPW1'!AH8) | ¬¬IF(ISBLANK('DPW1'!AI8),"",'DPW1'!AI8) | ¬¬IF(ISBLANK('DPW1'!AJ8),"",'DPW1'!AJ8) | ¬¬IF(ISBLANK('DPW1'!AK8),"",'DPW1'!AK8)
¬¬A910 | ¬¬IF(ISBLANK('DPW1'!BX8),"",'DPW1'!BX8) | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL8),"",'DPW1'!AL8) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM8),"",'DPW1'!AM8)
¬¬A911 | ¬¬IF(ISBLANK('DPW1'!CA8),"",'DPW1'!CA8) | ¬¬'DPW1'!F8 & "," & 'DPW1'!G8 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H8),"",'DPW1'!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO8),"",'DPW1'!AO8) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP8),"",'DPW1'!AP8)
¬¬A912 | ¬¬IF(ISBLANK('DPW1'!AW9),"",'DPW1'!AW9) | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K9),"",'DPW1'!K9) | ¬¬IF(ISBLANK('DPW1'!L9),"",'DPW1'!L9) | ¬¬IF(ISBLANK('DPW1'!M9),"",'DPW1'!M9) | ¬¬IF(ISBLANK('DPW1'!N9),"",'DPW1'!N9) | ¬¬IF(ISBLANK('DPW1'!O9),"",'DPW1'!O9) | ¬¬IF(ISBLANK('DPW1'!P9),"",'DPW1'!P9) | ¬¬IF(ISBLANK('DPW1'!Q9),"",'DPW1'!Q9) | ¬¬IF(ISBLANK('DPW1'!R9),"",'DPW1'!R9) | ¬¬IF(ISBLANK('DPW1'!S9),"",'DPW1'!S9) | ¬¬IF(ISBLANK('DPW1'!T9),"",'DPW1'!T9) | ¬¬IF(ISBLANK('DPW1'!U9),"",'DPW1'!U9) | ¬¬IF(ISBLANK('DPW1'!V9),"",'DPW1'!V9)
¬¬A913 | ¬¬IF(ISBLANK('DPW1'!BI9),"",'DPW1'!BI9) | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W9),"",'DPW1'!W9) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X9),"",'DPW1'!X9)
¬¬A914 | ¬¬IF(ISBLANK('DPW1'!BL9),"",'DPW1'!BL9) | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z9),"",'DPW1'!Z9) | ¬¬IF(ISBLANK('DPW1'!AA9),"",'DPW1'!AA9) | ¬¬IF(ISBLANK('DPW1'!AB9),"",'DPW1'!AB9) | ¬¬IF(ISBLANK('DPW1'!AC9),"",'DPW1'!AC9) | ¬¬IF(ISBLANK('DPW1'!AD9),"",'DPW1'!AD9) | ¬¬IF(ISBLANK('DPW1'!AE9),"",'DPW1'!AE9) | ¬¬IF(ISBLANK('DPW1'!AF9),"",'DPW1'!AF9) | ¬¬IF(ISBLANK('DPW1'!AG9),"",'DPW1'!AG9) | ¬¬IF(ISBLANK('DPW1'!AH9),"",'DPW1'!AH9) | ¬¬IF(ISBLANK('DPW1'!AI9),"",'DPW1'!AI9) | ¬¬IF(ISBLANK('DPW1'!AJ9),"",'DPW1'!AJ9) | ¬¬IF(ISBLANK('DPW1'!AK9),"",'DPW1'!AK9)
¬¬A915 | ¬¬IF(ISBLANK('DPW1'!BX9),"",'DPW1'!BX9) | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL9),"",'DPW1'!AL9) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM9),"",'DPW1'!AM9)
¬¬A916 | ¬¬IF(ISBLANK('DPW1'!CA9),"",'DPW1'!CA9) | ¬¬'DPW1'!F9 & "," & 'DPW1'!G9 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H9),"",'DPW1'!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO9),"",'DPW1'!AO9) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP9),"",'DPW1'!AP9)
¬¬A917 | ¬¬IF(ISBLANK('DPW1'!AW10),"",'DPW1'!AW10) | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K10),"",'DPW1'!K10) | ¬¬IF(ISBLANK('DPW1'!L10),"",'DPW1'!L10) | ¬¬IF(ISBLANK('DPW1'!M10),"",'DPW1'!M10) | ¬¬IF(ISBLANK('DPW1'!N10),"",'DPW1'!N10) | ¬¬IF(ISBLANK('DPW1'!O10),"",'DPW1'!O10) | ¬¬IF(ISBLANK('DPW1'!P10),"",'DPW1'!P10) | ¬¬IF(ISBLANK('DPW1'!Q10),"",'DPW1'!Q10) | ¬¬IF(ISBLANK('DPW1'!R10),"",'DPW1'!R10) | ¬¬IF(ISBLANK('DPW1'!S10),"",'DPW1'!S10) | ¬¬IF(ISBLANK('DPW1'!T10),"",'DPW1'!T10) | ¬¬IF(ISBLANK('DPW1'!U10),"",'DPW1'!U10) | ¬¬IF(ISBLANK('DPW1'!V10),"",'DPW1'!V10)
¬¬A918 | ¬¬IF(ISBLANK('DPW1'!BI10),"",'DPW1'!BI10) | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W10),"",'DPW1'!W10) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X10),"",'DPW1'!X10)
¬¬A919 | ¬¬IF(ISBLANK('DPW1'!BL10),"",'DPW1'!BL10) | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z10),"",'DPW1'!Z10) | ¬¬IF(ISBLANK('DPW1'!AA10),"",'DPW1'!AA10) | ¬¬IF(ISBLANK('DPW1'!AB10),"",'DPW1'!AB10) | ¬¬IF(ISBLANK('DPW1'!AC10),"",'DPW1'!AC10) | ¬¬IF(ISBLANK('DPW1'!AD10),"",'DPW1'!AD10) | ¬¬IF(ISBLANK('DPW1'!AE10),"",'DPW1'!AE10) | ¬¬IF(ISBLANK('DPW1'!AF10),"",'DPW1'!AF10) | ¬¬IF(ISBLANK('DPW1'!AG10),"",'DPW1'!AG10) | ¬¬IF(ISBLANK('DPW1'!AH10),"",'DPW1'!AH10) | ¬¬IF(ISBLANK('DPW1'!AI10),"",'DPW1'!AI10) | ¬¬IF(ISBLANK('DPW1'!AJ10),"",'DPW1'!AJ10) | ¬¬IF(ISBLANK('DPW1'!AK10),"",'DPW1'!AK10)
¬¬A920 | ¬¬IF(ISBLANK('DPW1'!BX10),"",'DPW1'!BX10) | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL10),"",'DPW1'!AL10) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM10),"",'DPW1'!AM10)
¬¬A921 | ¬¬IF(ISBLANK('DPW1'!CA10),"",'DPW1'!CA10) | ¬¬'DPW1'!F10 & "," & 'DPW1'!G10 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H10),"",'DPW1'!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO10),"",'DPW1'!AO10) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP10),"",'DPW1'!AP10)
¬¬A922 | ¬¬IF(ISBLANK('DPW1'!AW11),"",'DPW1'!AW11) | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K11),"",'DPW1'!K11) | ¬¬IF(ISBLANK('DPW1'!L11),"",'DPW1'!L11) | ¬¬IF(ISBLANK('DPW1'!M11),"",'DPW1'!M11) | ¬¬IF(ISBLANK('DPW1'!N11),"",'DPW1'!N11) | ¬¬IF(ISBLANK('DPW1'!O11),"",'DPW1'!O11) | ¬¬IF(ISBLANK('DPW1'!P11),"",'DPW1'!P11) | ¬¬IF(ISBLANK('DPW1'!Q11),"",'DPW1'!Q11) | ¬¬IF(ISBLANK('DPW1'!R11),"",'DPW1'!R11) | ¬¬IF(ISBLANK('DPW1'!S11),"",'DPW1'!S11) | ¬¬IF(ISBLANK('DPW1'!T11),"",'DPW1'!T11) | ¬¬IF(ISBLANK('DPW1'!U11),"",'DPW1'!U11) | ¬¬IF(ISBLANK('DPW1'!V11),"",'DPW1'!V11)
¬¬A923 | ¬¬IF(ISBLANK('DPW1'!BI11),"",'DPW1'!BI11) | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W11),"",'DPW1'!W11) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X11),"",'DPW1'!X11)
¬¬A924 | ¬¬IF(ISBLANK('DPW1'!BL11),"",'DPW1'!BL11) | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z11),"",'DPW1'!Z11) | ¬¬IF(ISBLANK('DPW1'!AA11),"",'DPW1'!AA11) | ¬¬IF(ISBLANK('DPW1'!AB11),"",'DPW1'!AB11) | ¬¬IF(ISBLANK('DPW1'!AC11),"",'DPW1'!AC11) | ¬¬IF(ISBLANK('DPW1'!AD11),"",'DPW1'!AD11) | ¬¬IF(ISBLANK('DPW1'!AE11),"",'DPW1'!AE11) | ¬¬IF(ISBLANK('DPW1'!AF11),"",'DPW1'!AF11) | ¬¬IF(ISBLANK('DPW1'!AG11),"",'DPW1'!AG11) | ¬¬IF(ISBLANK('DPW1'!AH11),"",'DPW1'!AH11) | ¬¬IF(ISBLANK('DPW1'!AI11),"",'DPW1'!AI11) | ¬¬IF(ISBLANK('DPW1'!AJ11),"",'DPW1'!AJ11) | ¬¬IF(ISBLANK('DPW1'!AK11),"",'DPW1'!AK11)
¬¬A925 | ¬¬IF(ISBLANK('DPW1'!BX11),"",'DPW1'!BX11) | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL11),"",'DPW1'!AL11) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM11),"",'DPW1'!AM11)
¬¬A926 | ¬¬IF(ISBLANK('DPW1'!CA11),"",'DPW1'!CA11) | ¬¬'DPW1'!F11 & "," & 'DPW1'!G11 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H11),"",'DPW1'!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO11),"",'DPW1'!AO11) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP11),"",'DPW1'!AP11)
¬¬A927 | ¬¬IF(ISBLANK('DPW1'!AW12),"",'DPW1'!AW12) | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K12),"",'DPW1'!K12) | ¬¬IF(ISBLANK('DPW1'!L12),"",'DPW1'!L12) | ¬¬IF(ISBLANK('DPW1'!M12),"",'DPW1'!M12) | ¬¬IF(ISBLANK('DPW1'!N12),"",'DPW1'!N12) | ¬¬IF(ISBLANK('DPW1'!O12),"",'DPW1'!O12) | ¬¬IF(ISBLANK('DPW1'!P12),"",'DPW1'!P12) | ¬¬IF(ISBLANK('DPW1'!Q12),"",'DPW1'!Q12) | ¬¬IF(ISBLANK('DPW1'!R12),"",'DPW1'!R12) | ¬¬IF(ISBLANK('DPW1'!S12),"",'DPW1'!S12) | ¬¬IF(ISBLANK('DPW1'!T12),"",'DPW1'!T12) | ¬¬IF(ISBLANK('DPW1'!U12),"",'DPW1'!U12) | ¬¬IF(ISBLANK('DPW1'!V12),"",'DPW1'!V12)
¬¬A928 | ¬¬IF(ISBLANK('DPW1'!BI12),"",'DPW1'!BI12) | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W12),"",'DPW1'!W12) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X12),"",'DPW1'!X12)
¬¬A929 | ¬¬IF(ISBLANK('DPW1'!BL12),"",'DPW1'!BL12) | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z12),"",'DPW1'!Z12) | ¬¬IF(ISBLANK('DPW1'!AA12),"",'DPW1'!AA12) | ¬¬IF(ISBLANK('DPW1'!AB12),"",'DPW1'!AB12) | ¬¬IF(ISBLANK('DPW1'!AC12),"",'DPW1'!AC12) | ¬¬IF(ISBLANK('DPW1'!AD12),"",'DPW1'!AD12) | ¬¬IF(ISBLANK('DPW1'!AE12),"",'DPW1'!AE12) | ¬¬IF(ISBLANK('DPW1'!AF12),"",'DPW1'!AF12) | ¬¬IF(ISBLANK('DPW1'!AG12),"",'DPW1'!AG12) | ¬¬IF(ISBLANK('DPW1'!AH12),"",'DPW1'!AH12) | ¬¬IF(ISBLANK('DPW1'!AI12),"",'DPW1'!AI12) | ¬¬IF(ISBLANK('DPW1'!AJ12),"",'DPW1'!AJ12) | ¬¬IF(ISBLANK('DPW1'!AK12),"",'DPW1'!AK12)
¬¬A930 | ¬¬IF(ISBLANK('DPW1'!BX12),"",'DPW1'!BX12) | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL12),"",'DPW1'!AL12) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM12),"",'DPW1'!AM12)
¬¬A931 | ¬¬IF(ISBLANK('DPW1'!CA12),"",'DPW1'!CA12) | ¬¬'DPW1'!F12 & "," & 'DPW1'!G12 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H12),"",'DPW1'!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO12),"",'DPW1'!AO12) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP12),"",'DPW1'!AP12)
¬¬A932 | ¬¬IF(ISBLANK('DPW1'!AW13),"",'DPW1'!AW13) | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K13),"",'DPW1'!K13) | ¬¬IF(ISBLANK('DPW1'!L13),"",'DPW1'!L13) | ¬¬IF(ISBLANK('DPW1'!M13),"",'DPW1'!M13) | ¬¬IF(ISBLANK('DPW1'!N13),"",'DPW1'!N13) | ¬¬IF(ISBLANK('DPW1'!O13),"",'DPW1'!O13) | ¬¬IF(ISBLANK('DPW1'!P13),"",'DPW1'!P13) | ¬¬IF(ISBLANK('DPW1'!Q13),"",'DPW1'!Q13) | ¬¬IF(ISBLANK('DPW1'!R13),"",'DPW1'!R13) | ¬¬IF(ISBLANK('DPW1'!S13),"",'DPW1'!S13) | ¬¬IF(ISBLANK('DPW1'!T13),"",'DPW1'!T13) | ¬¬IF(ISBLANK('DPW1'!U13),"",'DPW1'!U13) | ¬¬IF(ISBLANK('DPW1'!V13),"",'DPW1'!V13)
¬¬A933 | ¬¬IF(ISBLANK('DPW1'!BI13),"",'DPW1'!BI13) | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W13),"",'DPW1'!W13) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X13),"",'DPW1'!X13)
¬¬A934 | ¬¬IF(ISBLANK('DPW1'!BL13),"",'DPW1'!BL13) | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z13),"",'DPW1'!Z13) | ¬¬IF(ISBLANK('DPW1'!AA13),"",'DPW1'!AA13) | ¬¬IF(ISBLANK('DPW1'!AB13),"",'DPW1'!AB13) | ¬¬IF(ISBLANK('DPW1'!AC13),"",'DPW1'!AC13) | ¬¬IF(ISBLANK('DPW1'!AD13),"",'DPW1'!AD13) | ¬¬IF(ISBLANK('DPW1'!AE13),"",'DPW1'!AE13) | ¬¬IF(ISBLANK('DPW1'!AF13),"",'DPW1'!AF13) | ¬¬IF(ISBLANK('DPW1'!AG13),"",'DPW1'!AG13) | ¬¬IF(ISBLANK('DPW1'!AH13),"",'DPW1'!AH13) | ¬¬IF(ISBLANK('DPW1'!AI13),"",'DPW1'!AI13) | ¬¬IF(ISBLANK('DPW1'!AJ13),"",'DPW1'!AJ13) | ¬¬IF(ISBLANK('DPW1'!AK13),"",'DPW1'!AK13)
¬¬A935 | ¬¬IF(ISBLANK('DPW1'!BX13),"",'DPW1'!BX13) | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL13),"",'DPW1'!AL13) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM13),"",'DPW1'!AM13)
¬¬A936 | ¬¬IF(ISBLANK('DPW1'!CA13),"",'DPW1'!CA13) | ¬¬'DPW1'!F13 & "," & 'DPW1'!G13 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H13),"",'DPW1'!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO13),"",'DPW1'!AO13) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP13),"",'DPW1'!AP13)
¬¬A937 | ¬¬IF(ISBLANK('DPW1'!AW14),"",'DPW1'!AW14) | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K14),"",'DPW1'!K14) | ¬¬IF(ISBLANK('DPW1'!L14),"",'DPW1'!L14) | ¬¬IF(ISBLANK('DPW1'!M14),"",'DPW1'!M14) | ¬¬IF(ISBLANK('DPW1'!N14),"",'DPW1'!N14) | ¬¬IF(ISBLANK('DPW1'!O14),"",'DPW1'!O14) | ¬¬IF(ISBLANK('DPW1'!P14),"",'DPW1'!P14) | ¬¬IF(ISBLANK('DPW1'!Q14),"",'DPW1'!Q14) | ¬¬IF(ISBLANK('DPW1'!R14),"",'DPW1'!R14) | ¬¬IF(ISBLANK('DPW1'!S14),"",'DPW1'!S14) | ¬¬IF(ISBLANK('DPW1'!T14),"",'DPW1'!T14) | ¬¬IF(ISBLANK('DPW1'!U14),"",'DPW1'!U14) | ¬¬IF(ISBLANK('DPW1'!V14),"",'DPW1'!V14)
¬¬A938 | ¬¬IF(ISBLANK('DPW1'!BI14),"",'DPW1'!BI14) | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W14),"",'DPW1'!W14) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X14),"",'DPW1'!X14)
¬¬A939 | ¬¬IF(ISBLANK('DPW1'!BL14),"",'DPW1'!BL14) | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z14),"",'DPW1'!Z14) | ¬¬IF(ISBLANK('DPW1'!AA14),"",'DPW1'!AA14) | ¬¬IF(ISBLANK('DPW1'!AB14),"",'DPW1'!AB14) | ¬¬IF(ISBLANK('DPW1'!AC14),"",'DPW1'!AC14) | ¬¬IF(ISBLANK('DPW1'!AD14),"",'DPW1'!AD14) | ¬¬IF(ISBLANK('DPW1'!AE14),"",'DPW1'!AE14) | ¬¬IF(ISBLANK('DPW1'!AF14),"",'DPW1'!AF14) | ¬¬IF(ISBLANK('DPW1'!AG14),"",'DPW1'!AG14) | ¬¬IF(ISBLANK('DPW1'!AH14),"",'DPW1'!AH14) | ¬¬IF(ISBLANK('DPW1'!AI14),"",'DPW1'!AI14) | ¬¬IF(ISBLANK('DPW1'!AJ14),"",'DPW1'!AJ14) | ¬¬IF(ISBLANK('DPW1'!AK14),"",'DPW1'!AK14)
¬¬A940 | ¬¬IF(ISBLANK('DPW1'!BX14),"",'DPW1'!BX14) | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL14),"",'DPW1'!AL14) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM14),"",'DPW1'!AM14)
¬¬A941 | ¬¬IF(ISBLANK('DPW1'!CA14),"",'DPW1'!CA14) | ¬¬'DPW1'!F14 & "," & 'DPW1'!G14 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H14),"",'DPW1'!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO14),"",'DPW1'!AO14) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP14),"",'DPW1'!AP14)
¬¬A942 | ¬¬IF(ISBLANK('DPW1'!AW15),"",'DPW1'!AW15) | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K15),"",'DPW1'!K15) | ¬¬IF(ISBLANK('DPW1'!L15),"",'DPW1'!L15) | ¬¬IF(ISBLANK('DPW1'!M15),"",'DPW1'!M15) | ¬¬IF(ISBLANK('DPW1'!N15),"",'DPW1'!N15) | ¬¬IF(ISBLANK('DPW1'!O15),"",'DPW1'!O15) | ¬¬IF(ISBLANK('DPW1'!P15),"",'DPW1'!P15) | ¬¬IF(ISBLANK('DPW1'!Q15),"",'DPW1'!Q15) | ¬¬IF(ISBLANK('DPW1'!R15),"",'DPW1'!R15) | ¬¬IF(ISBLANK('DPW1'!S15),"",'DPW1'!S15) | ¬¬IF(ISBLANK('DPW1'!T15),"",'DPW1'!T15) | ¬¬IF(ISBLANK('DPW1'!U15),"",'DPW1'!U15) | ¬¬IF(ISBLANK('DPW1'!V15),"",'DPW1'!V15)
¬¬A943 | ¬¬IF(ISBLANK('DPW1'!BI15),"",'DPW1'!BI15) | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W15),"",'DPW1'!W15) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X15),"",'DPW1'!X15)
¬¬A944 | ¬¬IF(ISBLANK('DPW1'!BL15),"",'DPW1'!BL15) | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z15),"",'DPW1'!Z15) | ¬¬IF(ISBLANK('DPW1'!AA15),"",'DPW1'!AA15) | ¬¬IF(ISBLANK('DPW1'!AB15),"",'DPW1'!AB15) | ¬¬IF(ISBLANK('DPW1'!AC15),"",'DPW1'!AC15) | ¬¬IF(ISBLANK('DPW1'!AD15),"",'DPW1'!AD15) | ¬¬IF(ISBLANK('DPW1'!AE15),"",'DPW1'!AE15) | ¬¬IF(ISBLANK('DPW1'!AF15),"",'DPW1'!AF15) | ¬¬IF(ISBLANK('DPW1'!AG15),"",'DPW1'!AG15) | ¬¬IF(ISBLANK('DPW1'!AH15),"",'DPW1'!AH15) | ¬¬IF(ISBLANK('DPW1'!AI15),"",'DPW1'!AI15) | ¬¬IF(ISBLANK('DPW1'!AJ15),"",'DPW1'!AJ15) | ¬¬IF(ISBLANK('DPW1'!AK15),"",'DPW1'!AK15)
¬¬A945 | ¬¬IF(ISBLANK('DPW1'!BX15),"",'DPW1'!BX15) | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL15),"",'DPW1'!AL15) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM15),"",'DPW1'!AM15)
¬¬A946 | ¬¬IF(ISBLANK('DPW1'!CA15),"",'DPW1'!CA15) | ¬¬'DPW1'!F15 & "," & 'DPW1'!G15 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H15),"",'DPW1'!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO15),"",'DPW1'!AO15) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP15),"",'DPW1'!AP15)
¬¬A947 | ¬¬IF(ISBLANK('DPW1'!AW16),"",'DPW1'!AW16) | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K16),"",'DPW1'!K16) | ¬¬IF(ISBLANK('DPW1'!L16),"",'DPW1'!L16) | ¬¬IF(ISBLANK('DPW1'!M16),"",'DPW1'!M16) | ¬¬IF(ISBLANK('DPW1'!N16),"",'DPW1'!N16) | ¬¬IF(ISBLANK('DPW1'!O16),"",'DPW1'!O16) | ¬¬IF(ISBLANK('DPW1'!P16),"",'DPW1'!P16) | ¬¬IF(ISBLANK('DPW1'!Q16),"",'DPW1'!Q16) | ¬¬IF(ISBLANK('DPW1'!R16),"",'DPW1'!R16) | ¬¬IF(ISBLANK('DPW1'!S16),"",'DPW1'!S16) | ¬¬IF(ISBLANK('DPW1'!T16),"",'DPW1'!T16) | ¬¬IF(ISBLANK('DPW1'!U16),"",'DPW1'!U16) | ¬¬IF(ISBLANK('DPW1'!V16),"",'DPW1'!V16)
¬¬A948 | ¬¬IF(ISBLANK('DPW1'!BI16),"",'DPW1'!BI16) | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W16),"",'DPW1'!W16) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X16),"",'DPW1'!X16)
¬¬A949 | ¬¬IF(ISBLANK('DPW1'!BL16),"",'DPW1'!BL16) | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z16),"",'DPW1'!Z16) | ¬¬IF(ISBLANK('DPW1'!AA16),"",'DPW1'!AA16) | ¬¬IF(ISBLANK('DPW1'!AB16),"",'DPW1'!AB16) | ¬¬IF(ISBLANK('DPW1'!AC16),"",'DPW1'!AC16) | ¬¬IF(ISBLANK('DPW1'!AD16),"",'DPW1'!AD16) | ¬¬IF(ISBLANK('DPW1'!AE16),"",'DPW1'!AE16) | ¬¬IF(ISBLANK('DPW1'!AF16),"",'DPW1'!AF16) | ¬¬IF(ISBLANK('DPW1'!AG16),"",'DPW1'!AG16) | ¬¬IF(ISBLANK('DPW1'!AH16),"",'DPW1'!AH16) | ¬¬IF(ISBLANK('DPW1'!AI16),"",'DPW1'!AI16) | ¬¬IF(ISBLANK('DPW1'!AJ16),"",'DPW1'!AJ16) | ¬¬IF(ISBLANK('DPW1'!AK16),"",'DPW1'!AK16)
¬¬A950 | ¬¬IF(ISBLANK('DPW1'!BX16),"",'DPW1'!BX16) | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL16),"",'DPW1'!AL16) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM16),"",'DPW1'!AM16)
¬¬A951 | ¬¬IF(ISBLANK('DPW1'!CA16),"",'DPW1'!CA16) | ¬¬'DPW1'!F16 & "," & 'DPW1'!G16 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H16),"",'DPW1'!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO16),"",'DPW1'!AO16) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP16),"",'DPW1'!AP16)
¬¬A952 | ¬¬IF(ISBLANK('DPW1'!AW17),"",'DPW1'!AW17) | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K17),"",'DPW1'!K17) | ¬¬IF(ISBLANK('DPW1'!L17),"",'DPW1'!L17) | ¬¬IF(ISBLANK('DPW1'!M17),"",'DPW1'!M17) | ¬¬IF(ISBLANK('DPW1'!N17),"",'DPW1'!N17) | ¬¬IF(ISBLANK('DPW1'!O17),"",'DPW1'!O17) | ¬¬IF(ISBLANK('DPW1'!P17),"",'DPW1'!P17) | ¬¬IF(ISBLANK('DPW1'!Q17),"",'DPW1'!Q17) | ¬¬IF(ISBLANK('DPW1'!R17),"",'DPW1'!R17) | ¬¬IF(ISBLANK('DPW1'!S17),"",'DPW1'!S17) | ¬¬IF(ISBLANK('DPW1'!T17),"",'DPW1'!T17) | ¬¬IF(ISBLANK('DPW1'!U17),"",'DPW1'!U17) | ¬¬IF(ISBLANK('DPW1'!V17),"",'DPW1'!V17)
¬¬A953 | ¬¬IF(ISBLANK('DPW1'!BI17),"",'DPW1'!BI17) | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W17),"",'DPW1'!W17) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X17),"",'DPW1'!X17)
¬¬A954 | ¬¬IF(ISBLANK('DPW1'!BL17),"",'DPW1'!BL17) | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z17),"",'DPW1'!Z17) | ¬¬IF(ISBLANK('DPW1'!AA17),"",'DPW1'!AA17) | ¬¬IF(ISBLANK('DPW1'!AB17),"",'DPW1'!AB17) | ¬¬IF(ISBLANK('DPW1'!AC17),"",'DPW1'!AC17) | ¬¬IF(ISBLANK('DPW1'!AD17),"",'DPW1'!AD17) | ¬¬IF(ISBLANK('DPW1'!AE17),"",'DPW1'!AE17) | ¬¬IF(ISBLANK('DPW1'!AF17),"",'DPW1'!AF17) | ¬¬IF(ISBLANK('DPW1'!AG17),"",'DPW1'!AG17) | ¬¬IF(ISBLANK('DPW1'!AH17),"",'DPW1'!AH17) | ¬¬IF(ISBLANK('DPW1'!AI17),"",'DPW1'!AI17) | ¬¬IF(ISBLANK('DPW1'!AJ17),"",'DPW1'!AJ17) | ¬¬IF(ISBLANK('DPW1'!AK17),"",'DPW1'!AK17)
¬¬A955 | ¬¬IF(ISBLANK('DPW1'!BX17),"",'DPW1'!BX17) | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL17),"",'DPW1'!AL17) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM17),"",'DPW1'!AM17)
¬¬A956 | ¬¬IF(ISBLANK('DPW1'!CA17),"",'DPW1'!CA17) | ¬¬'DPW1'!F17 & "," & 'DPW1'!G17 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H17),"",'DPW1'!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO17),"",'DPW1'!AO17) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP17),"",'DPW1'!AP17)
¬¬A957 | ¬¬IF(ISBLANK('DPW1'!AW18),"",'DPW1'!AW18) | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K18),"",'DPW1'!K18) | ¬¬IF(ISBLANK('DPW1'!L18),"",'DPW1'!L18) | ¬¬IF(ISBLANK('DPW1'!M18),"",'DPW1'!M18) | ¬¬IF(ISBLANK('DPW1'!N18),"",'DPW1'!N18) | ¬¬IF(ISBLANK('DPW1'!O18),"",'DPW1'!O18) | ¬¬IF(ISBLANK('DPW1'!P18),"",'DPW1'!P18) | ¬¬IF(ISBLANK('DPW1'!Q18),"",'DPW1'!Q18) | ¬¬IF(ISBLANK('DPW1'!R18),"",'DPW1'!R18) | ¬¬IF(ISBLANK('DPW1'!S18),"",'DPW1'!S18) | ¬¬IF(ISBLANK('DPW1'!T18),"",'DPW1'!T18) | ¬¬IF(ISBLANK('DPW1'!U18),"",'DPW1'!U18) | ¬¬IF(ISBLANK('DPW1'!V18),"",'DPW1'!V18)
¬¬A958 | ¬¬IF(ISBLANK('DPW1'!BI18),"",'DPW1'!BI18) | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W18),"",'DPW1'!W18) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X18),"",'DPW1'!X18)
¬¬A959 | ¬¬IF(ISBLANK('DPW1'!BL18),"",'DPW1'!BL18) | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z18),"",'DPW1'!Z18) | ¬¬IF(ISBLANK('DPW1'!AA18),"",'DPW1'!AA18) | ¬¬IF(ISBLANK('DPW1'!AB18),"",'DPW1'!AB18) | ¬¬IF(ISBLANK('DPW1'!AC18),"",'DPW1'!AC18) | ¬¬IF(ISBLANK('DPW1'!AD18),"",'DPW1'!AD18) | ¬¬IF(ISBLANK('DPW1'!AE18),"",'DPW1'!AE18) | ¬¬IF(ISBLANK('DPW1'!AF18),"",'DPW1'!AF18) | ¬¬IF(ISBLANK('DPW1'!AG18),"",'DPW1'!AG18) | ¬¬IF(ISBLANK('DPW1'!AH18),"",'DPW1'!AH18) | ¬¬IF(ISBLANK('DPW1'!AI18),"",'DPW1'!AI18) | ¬¬IF(ISBLANK('DPW1'!AJ18),"",'DPW1'!AJ18) | ¬¬IF(ISBLANK('DPW1'!AK18),"",'DPW1'!AK18)
¬¬A960 | ¬¬IF(ISBLANK('DPW1'!BX18),"",'DPW1'!BX18) | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL18),"",'DPW1'!AL18) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM18),"",'DPW1'!AM18)
¬¬A961 | ¬¬IF(ISBLANK('DPW1'!CA18),"",'DPW1'!CA18) | ¬¬'DPW1'!F18 & "," & 'DPW1'!G18 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H18),"",'DPW1'!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO18),"",'DPW1'!AO18) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP18),"",'DPW1'!AP18)
¬¬A962 | ¬¬IF(ISBLANK('DPW1'!AW19),"",'DPW1'!AW19) | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K19),"",'DPW1'!K19) | ¬¬IF(ISBLANK('DPW1'!L19),"",'DPW1'!L19) | ¬¬IF(ISBLANK('DPW1'!M19),"",'DPW1'!M19) | ¬¬IF(ISBLANK('DPW1'!N19),"",'DPW1'!N19) | ¬¬IF(ISBLANK('DPW1'!O19),"",'DPW1'!O19) | ¬¬IF(ISBLANK('DPW1'!P19),"",'DPW1'!P19) | ¬¬IF(ISBLANK('DPW1'!Q19),"",'DPW1'!Q19) | ¬¬IF(ISBLANK('DPW1'!R19),"",'DPW1'!R19) | ¬¬IF(ISBLANK('DPW1'!S19),"",'DPW1'!S19) | ¬¬IF(ISBLANK('DPW1'!T19),"",'DPW1'!T19) | ¬¬IF(ISBLANK('DPW1'!U19),"",'DPW1'!U19) | ¬¬IF(ISBLANK('DPW1'!V19),"",'DPW1'!V19)
¬¬A963 | ¬¬IF(ISBLANK('DPW1'!BI19),"",'DPW1'!BI19) | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W19),"",'DPW1'!W19) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X19),"",'DPW1'!X19)
¬¬A964 | ¬¬IF(ISBLANK('DPW1'!BL19),"",'DPW1'!BL19) | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z19),"",'DPW1'!Z19) | ¬¬IF(ISBLANK('DPW1'!AA19),"",'DPW1'!AA19) | ¬¬IF(ISBLANK('DPW1'!AB19),"",'DPW1'!AB19) | ¬¬IF(ISBLANK('DPW1'!AC19),"",'DPW1'!AC19) | ¬¬IF(ISBLANK('DPW1'!AD19),"",'DPW1'!AD19) | ¬¬IF(ISBLANK('DPW1'!AE19),"",'DPW1'!AE19) | ¬¬IF(ISBLANK('DPW1'!AF19),"",'DPW1'!AF19) | ¬¬IF(ISBLANK('DPW1'!AG19),"",'DPW1'!AG19) | ¬¬IF(ISBLANK('DPW1'!AH19),"",'DPW1'!AH19) | ¬¬IF(ISBLANK('DPW1'!AI19),"",'DPW1'!AI19) | ¬¬IF(ISBLANK('DPW1'!AJ19),"",'DPW1'!AJ19) | ¬¬IF(ISBLANK('DPW1'!AK19),"",'DPW1'!AK19)
¬¬A965 | ¬¬IF(ISBLANK('DPW1'!BX19),"",'DPW1'!BX19) | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL19),"",'DPW1'!AL19) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM19),"",'DPW1'!AM19)
¬¬A966 | ¬¬IF(ISBLANK('DPW1'!CA19),"",'DPW1'!CA19) | ¬¬'DPW1'!F19 & "," & 'DPW1'!G19 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H19),"",'DPW1'!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO19),"",'DPW1'!AO19) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP19),"",'DPW1'!AP19)
¬¬A967 | ¬¬IF(ISBLANK('DPW1'!AW20),"",'DPW1'!AW20) | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K20),"",'DPW1'!K20) | ¬¬IF(ISBLANK('DPW1'!L20),"",'DPW1'!L20) | ¬¬IF(ISBLANK('DPW1'!M20),"",'DPW1'!M20) | ¬¬IF(ISBLANK('DPW1'!N20),"",'DPW1'!N20) | ¬¬IF(ISBLANK('DPW1'!O20),"",'DPW1'!O20) | ¬¬IF(ISBLANK('DPW1'!P20),"",'DPW1'!P20) | ¬¬IF(ISBLANK('DPW1'!Q20),"",'DPW1'!Q20) | ¬¬IF(ISBLANK('DPW1'!R20),"",'DPW1'!R20) | ¬¬IF(ISBLANK('DPW1'!S20),"",'DPW1'!S20) | ¬¬IF(ISBLANK('DPW1'!T20),"",'DPW1'!T20) | ¬¬IF(ISBLANK('DPW1'!U20),"",'DPW1'!U20) | ¬¬IF(ISBLANK('DPW1'!V20),"",'DPW1'!V20)
¬¬A968 | ¬¬IF(ISBLANK('DPW1'!BI20),"",'DPW1'!BI20) | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W20),"",'DPW1'!W20) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X20),"",'DPW1'!X20)
¬¬A969 | ¬¬IF(ISBLANK('DPW1'!BL20),"",'DPW1'!BL20) | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z20),"",'DPW1'!Z20) | ¬¬IF(ISBLANK('DPW1'!AA20),"",'DPW1'!AA20) | ¬¬IF(ISBLANK('DPW1'!AB20),"",'DPW1'!AB20) | ¬¬IF(ISBLANK('DPW1'!AC20),"",'DPW1'!AC20) | ¬¬IF(ISBLANK('DPW1'!AD20),"",'DPW1'!AD20) | ¬¬IF(ISBLANK('DPW1'!AE20),"",'DPW1'!AE20) | ¬¬IF(ISBLANK('DPW1'!AF20),"",'DPW1'!AF20) | ¬¬IF(ISBLANK('DPW1'!AG20),"",'DPW1'!AG20) | ¬¬IF(ISBLANK('DPW1'!AH20),"",'DPW1'!AH20) | ¬¬IF(ISBLANK('DPW1'!AI20),"",'DPW1'!AI20) | ¬¬IF(ISBLANK('DPW1'!AJ20),"",'DPW1'!AJ20) | ¬¬IF(ISBLANK('DPW1'!AK20),"",'DPW1'!AK20)
¬¬A970 | ¬¬IF(ISBLANK('DPW1'!BX20),"",'DPW1'!BX20) | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL20),"",'DPW1'!AL20) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM20),"",'DPW1'!AM20)
¬¬A971 | ¬¬IF(ISBLANK('DPW1'!CA20),"",'DPW1'!CA20) | ¬¬'DPW1'!F20 & "," & 'DPW1'!G20 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H20),"",'DPW1'!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO20),"",'DPW1'!AO20) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP20),"",'DPW1'!AP20)
¬¬A972 | ¬¬IF(ISBLANK('DPW1'!AW21),"",'DPW1'!AW21) | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K21),"",'DPW1'!K21) | ¬¬IF(ISBLANK('DPW1'!L21),"",'DPW1'!L21) | ¬¬IF(ISBLANK('DPW1'!M21),"",'DPW1'!M21) | ¬¬IF(ISBLANK('DPW1'!N21),"",'DPW1'!N21) | ¬¬IF(ISBLANK('DPW1'!O21),"",'DPW1'!O21) | ¬¬IF(ISBLANK('DPW1'!P21),"",'DPW1'!P21) | ¬¬IF(ISBLANK('DPW1'!Q21),"",'DPW1'!Q21) | ¬¬IF(ISBLANK('DPW1'!R21),"",'DPW1'!R21) | ¬¬IF(ISBLANK('DPW1'!S21),"",'DPW1'!S21) | ¬¬IF(ISBLANK('DPW1'!T21),"",'DPW1'!T21) | ¬¬IF(ISBLANK('DPW1'!U21),"",'DPW1'!U21) | ¬¬IF(ISBLANK('DPW1'!V21),"",'DPW1'!V21)
¬¬A973 | ¬¬IF(ISBLANK('DPW1'!BI21),"",'DPW1'!BI21) | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W21),"",'DPW1'!W21) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X21),"",'DPW1'!X21)
¬¬A974 | ¬¬IF(ISBLANK('DPW1'!BL21),"",'DPW1'!BL21) | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z21),"",'DPW1'!Z21) | ¬¬IF(ISBLANK('DPW1'!AA21),"",'DPW1'!AA21) | ¬¬IF(ISBLANK('DPW1'!AB21),"",'DPW1'!AB21) | ¬¬IF(ISBLANK('DPW1'!AC21),"",'DPW1'!AC21) | ¬¬IF(ISBLANK('DPW1'!AD21),"",'DPW1'!AD21) | ¬¬IF(ISBLANK('DPW1'!AE21),"",'DPW1'!AE21) | ¬¬IF(ISBLANK('DPW1'!AF21),"",'DPW1'!AF21) | ¬¬IF(ISBLANK('DPW1'!AG21),"",'DPW1'!AG21) | ¬¬IF(ISBLANK('DPW1'!AH21),"",'DPW1'!AH21) | ¬¬IF(ISBLANK('DPW1'!AI21),"",'DPW1'!AI21) | ¬¬IF(ISBLANK('DPW1'!AJ21),"",'DPW1'!AJ21) | ¬¬IF(ISBLANK('DPW1'!AK21),"",'DPW1'!AK21)
¬¬A975 | ¬¬IF(ISBLANK('DPW1'!BX21),"",'DPW1'!BX21) | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL21),"",'DPW1'!AL21) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM21),"",'DPW1'!AM21)
¬¬A976 | ¬¬IF(ISBLANK('DPW1'!CA21),"",'DPW1'!CA21) | ¬¬'DPW1'!F21 & "," & 'DPW1'!G21 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H21),"",'DPW1'!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO21),"",'DPW1'!AO21) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP21),"",'DPW1'!AP21)
¬¬A977 | ¬¬IF(ISBLANK('DPW1'!AW22),"",'DPW1'!AW22) | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K22),"",'DPW1'!K22) | ¬¬IF(ISBLANK('DPW1'!L22),"",'DPW1'!L22) | ¬¬IF(ISBLANK('DPW1'!M22),"",'DPW1'!M22) | ¬¬IF(ISBLANK('DPW1'!N22),"",'DPW1'!N22) | ¬¬IF(ISBLANK('DPW1'!O22),"",'DPW1'!O22) | ¬¬IF(ISBLANK('DPW1'!P22),"",'DPW1'!P22) | ¬¬IF(ISBLANK('DPW1'!Q22),"",'DPW1'!Q22) | ¬¬IF(ISBLANK('DPW1'!R22),"",'DPW1'!R22) | ¬¬IF(ISBLANK('DPW1'!S22),"",'DPW1'!S22) | ¬¬IF(ISBLANK('DPW1'!T22),"",'DPW1'!T22) | ¬¬IF(ISBLANK('DPW1'!U22),"",'DPW1'!U22) | ¬¬IF(ISBLANK('DPW1'!V22),"",'DPW1'!V22)
¬¬A978 | ¬¬IF(ISBLANK('DPW1'!BI22),"",'DPW1'!BI22) | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W22),"",'DPW1'!W22) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X22),"",'DPW1'!X22)
¬¬A979 | ¬¬IF(ISBLANK('DPW1'!BL22),"",'DPW1'!BL22) | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z22),"",'DPW1'!Z22) | ¬¬IF(ISBLANK('DPW1'!AA22),"",'DPW1'!AA22) | ¬¬IF(ISBLANK('DPW1'!AB22),"",'DPW1'!AB22) | ¬¬IF(ISBLANK('DPW1'!AC22),"",'DPW1'!AC22) | ¬¬IF(ISBLANK('DPW1'!AD22),"",'DPW1'!AD22) | ¬¬IF(ISBLANK('DPW1'!AE22),"",'DPW1'!AE22) | ¬¬IF(ISBLANK('DPW1'!AF22),"",'DPW1'!AF22) | ¬¬IF(ISBLANK('DPW1'!AG22),"",'DPW1'!AG22) | ¬¬IF(ISBLANK('DPW1'!AH22),"",'DPW1'!AH22) | ¬¬IF(ISBLANK('DPW1'!AI22),"",'DPW1'!AI22) | ¬¬IF(ISBLANK('DPW1'!AJ22),"",'DPW1'!AJ22) | ¬¬IF(ISBLANK('DPW1'!AK22),"",'DPW1'!AK22)
¬¬A980 | ¬¬IF(ISBLANK('DPW1'!BX22),"",'DPW1'!BX22) | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL22),"",'DPW1'!AL22) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM22),"",'DPW1'!AM22)
¬¬A981 | ¬¬IF(ISBLANK('DPW1'!CA22),"",'DPW1'!CA22) | ¬¬'DPW1'!F22 & "," & 'DPW1'!G22 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H22),"",'DPW1'!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO22),"",'DPW1'!AO22) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP22),"",'DPW1'!AP22)
¬¬A982 | ¬¬IF(ISBLANK('DPW1'!AW23),"",'DPW1'!AW23) | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K23),"",'DPW1'!K23) | ¬¬IF(ISBLANK('DPW1'!L23),"",'DPW1'!L23) | ¬¬IF(ISBLANK('DPW1'!M23),"",'DPW1'!M23) | ¬¬IF(ISBLANK('DPW1'!N23),"",'DPW1'!N23) | ¬¬IF(ISBLANK('DPW1'!O23),"",'DPW1'!O23) | ¬¬IF(ISBLANK('DPW1'!P23),"",'DPW1'!P23) | ¬¬IF(ISBLANK('DPW1'!Q23),"",'DPW1'!Q23) | ¬¬IF(ISBLANK('DPW1'!R23),"",'DPW1'!R23) | ¬¬IF(ISBLANK('DPW1'!S23),"",'DPW1'!S23) | ¬¬IF(ISBLANK('DPW1'!T23),"",'DPW1'!T23) | ¬¬IF(ISBLANK('DPW1'!U23),"",'DPW1'!U23) | ¬¬IF(ISBLANK('DPW1'!V23),"",'DPW1'!V23)
¬¬A983 | ¬¬IF(ISBLANK('DPW1'!BI23),"",'DPW1'!BI23) | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W23),"",'DPW1'!W23) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X23),"",'DPW1'!X23)
¬¬A984 | ¬¬IF(ISBLANK('DPW1'!BL23),"",'DPW1'!BL23) | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z23),"",'DPW1'!Z23) | ¬¬IF(ISBLANK('DPW1'!AA23),"",'DPW1'!AA23) | ¬¬IF(ISBLANK('DPW1'!AB23),"",'DPW1'!AB23) | ¬¬IF(ISBLANK('DPW1'!AC23),"",'DPW1'!AC23) | ¬¬IF(ISBLANK('DPW1'!AD23),"",'DPW1'!AD23) | ¬¬IF(ISBLANK('DPW1'!AE23),"",'DPW1'!AE23) | ¬¬IF(ISBLANK('DPW1'!AF23),"",'DPW1'!AF23) | ¬¬IF(ISBLANK('DPW1'!AG23),"",'DPW1'!AG23) | ¬¬IF(ISBLANK('DPW1'!AH23),"",'DPW1'!AH23) | ¬¬IF(ISBLANK('DPW1'!AI23),"",'DPW1'!AI23) | ¬¬IF(ISBLANK('DPW1'!AJ23),"",'DPW1'!AJ23) | ¬¬IF(ISBLANK('DPW1'!AK23),"",'DPW1'!AK23)
¬¬A985 | ¬¬IF(ISBLANK('DPW1'!BX23),"",'DPW1'!BX23) | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL23),"",'DPW1'!AL23) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM23),"",'DPW1'!AM23)
¬¬A986 | ¬¬IF(ISBLANK('DPW1'!CA23),"",'DPW1'!CA23) | ¬¬'DPW1'!F23 & "," & 'DPW1'!G23 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H23),"",'DPW1'!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO23),"",'DPW1'!AO23) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP23),"",'DPW1'!AP23)
¬¬A987 | ¬¬IF(ISBLANK('DPW1'!AW24),"",'DPW1'!AW24) | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K24),"",'DPW1'!K24) | ¬¬IF(ISBLANK('DPW1'!L24),"",'DPW1'!L24) | ¬¬IF(ISBLANK('DPW1'!M24),"",'DPW1'!M24) | ¬¬IF(ISBLANK('DPW1'!N24),"",'DPW1'!N24) | ¬¬IF(ISBLANK('DPW1'!O24),"",'DPW1'!O24) | ¬¬IF(ISBLANK('DPW1'!P24),"",'DPW1'!P24) | ¬¬IF(ISBLANK('DPW1'!Q24),"",'DPW1'!Q24) | ¬¬IF(ISBLANK('DPW1'!R24),"",'DPW1'!R24) | ¬¬IF(ISBLANK('DPW1'!S24),"",'DPW1'!S24) | ¬¬IF(ISBLANK('DPW1'!T24),"",'DPW1'!T24) | ¬¬IF(ISBLANK('DPW1'!U24),"",'DPW1'!U24) | ¬¬IF(ISBLANK('DPW1'!V24),"",'DPW1'!V24)
¬¬A988 | ¬¬IF(ISBLANK('DPW1'!BI24),"",'DPW1'!BI24) | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W24),"",'DPW1'!W24) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X24),"",'DPW1'!X24)
¬¬A989 | ¬¬IF(ISBLANK('DPW1'!BL24),"",'DPW1'!BL24) | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z24),"",'DPW1'!Z24) | ¬¬IF(ISBLANK('DPW1'!AA24),"",'DPW1'!AA24) | ¬¬IF(ISBLANK('DPW1'!AB24),"",'DPW1'!AB24) | ¬¬IF(ISBLANK('DPW1'!AC24),"",'DPW1'!AC24) | ¬¬IF(ISBLANK('DPW1'!AD24),"",'DPW1'!AD24) | ¬¬IF(ISBLANK('DPW1'!AE24),"",'DPW1'!AE24) | ¬¬IF(ISBLANK('DPW1'!AF24),"",'DPW1'!AF24) | ¬¬IF(ISBLANK('DPW1'!AG24),"",'DPW1'!AG24) | ¬¬IF(ISBLANK('DPW1'!AH24),"",'DPW1'!AH24) | ¬¬IF(ISBLANK('DPW1'!AI24),"",'DPW1'!AI24) | ¬¬IF(ISBLANK('DPW1'!AJ24),"",'DPW1'!AJ24) | ¬¬IF(ISBLANK('DPW1'!AK24),"",'DPW1'!AK24)
¬¬A990 | ¬¬IF(ISBLANK('DPW1'!BX24),"",'DPW1'!BX24) | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL24),"",'DPW1'!AL24) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM24),"",'DPW1'!AM24)
¬¬A991 | ¬¬IF(ISBLANK('DPW1'!CA24),"",'DPW1'!CA24) | ¬¬'DPW1'!F24 & "," & 'DPW1'!G24 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H24),"",'DPW1'!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO24),"",'DPW1'!AO24) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP24),"",'DPW1'!AP24)
¬¬A992 | ¬¬IF(ISBLANK('DPW1'!AW25),"",'DPW1'!AW25) | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K25),"",'DPW1'!K25) | ¬¬IF(ISBLANK('DPW1'!L25),"",'DPW1'!L25) | ¬¬IF(ISBLANK('DPW1'!M25),"",'DPW1'!M25) | ¬¬IF(ISBLANK('DPW1'!N25),"",'DPW1'!N25) | ¬¬IF(ISBLANK('DPW1'!O25),"",'DPW1'!O25) | ¬¬IF(ISBLANK('DPW1'!P25),"",'DPW1'!P25) | ¬¬IF(ISBLANK('DPW1'!Q25),"",'DPW1'!Q25) | ¬¬IF(ISBLANK('DPW1'!R25),"",'DPW1'!R25) | ¬¬IF(ISBLANK('DPW1'!S25),"",'DPW1'!S25) | ¬¬IF(ISBLANK('DPW1'!T25),"",'DPW1'!T25) | ¬¬IF(ISBLANK('DPW1'!U25),"",'DPW1'!U25) | ¬¬IF(ISBLANK('DPW1'!V25),"",'DPW1'!V25)
¬¬A993 | ¬¬IF(ISBLANK('DPW1'!BI25),"",'DPW1'!BI25) | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W25),"",'DPW1'!W25) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X25),"",'DPW1'!X25)
¬¬A994 | ¬¬IF(ISBLANK('DPW1'!BL25),"",'DPW1'!BL25) | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z25),"",'DPW1'!Z25) | ¬¬IF(ISBLANK('DPW1'!AA25),"",'DPW1'!AA25) | ¬¬IF(ISBLANK('DPW1'!AB25),"",'DPW1'!AB25) | ¬¬IF(ISBLANK('DPW1'!AC25),"",'DPW1'!AC25) | ¬¬IF(ISBLANK('DPW1'!AD25),"",'DPW1'!AD25) | ¬¬IF(ISBLANK('DPW1'!AE25),"",'DPW1'!AE25) | ¬¬IF(ISBLANK('DPW1'!AF25),"",'DPW1'!AF25) | ¬¬IF(ISBLANK('DPW1'!AG25),"",'DPW1'!AG25) | ¬¬IF(ISBLANK('DPW1'!AH25),"",'DPW1'!AH25) | ¬¬IF(ISBLANK('DPW1'!AI25),"",'DPW1'!AI25) | ¬¬IF(ISBLANK('DPW1'!AJ25),"",'DPW1'!AJ25) | ¬¬IF(ISBLANK('DPW1'!AK25),"",'DPW1'!AK25)
¬¬A995 | ¬¬IF(ISBLANK('DPW1'!BX25),"",'DPW1'!BX25) | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL25),"",'DPW1'!AL25) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM25),"",'DPW1'!AM25)
¬¬A996 | ¬¬IF(ISBLANK('DPW1'!CA25),"",'DPW1'!CA25) | ¬¬'DPW1'!F25 & "," & 'DPW1'!G25 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H25),"",'DPW1'!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO25),"",'DPW1'!AO25) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP25),"",'DPW1'!AP25)
¬¬A997 | ¬¬IF(ISBLANK('DPW1'!AW26),"",'DPW1'!AW26) | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K26),"",'DPW1'!K26) | ¬¬IF(ISBLANK('DPW1'!L26),"",'DPW1'!L26) | ¬¬IF(ISBLANK('DPW1'!M26),"",'DPW1'!M26) | ¬¬IF(ISBLANK('DPW1'!N26),"",'DPW1'!N26) | ¬¬IF(ISBLANK('DPW1'!O26),"",'DPW1'!O26) | ¬¬IF(ISBLANK('DPW1'!P26),"",'DPW1'!P26) | ¬¬IF(ISBLANK('DPW1'!Q26),"",'DPW1'!Q26) | ¬¬IF(ISBLANK('DPW1'!R26),"",'DPW1'!R26) | ¬¬IF(ISBLANK('DPW1'!S26),"",'DPW1'!S26) | ¬¬IF(ISBLANK('DPW1'!T26),"",'DPW1'!T26) | ¬¬IF(ISBLANK('DPW1'!U26),"",'DPW1'!U26) | ¬¬IF(ISBLANK('DPW1'!V26),"",'DPW1'!V26)
¬¬A998 | ¬¬IF(ISBLANK('DPW1'!BI26),"",'DPW1'!BI26) | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W26),"",'DPW1'!W26) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X26),"",'DPW1'!X26)
¬¬A999 | ¬¬IF(ISBLANK('DPW1'!BL26),"",'DPW1'!BL26) | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z26),"",'DPW1'!Z26) | ¬¬IF(ISBLANK('DPW1'!AA26),"",'DPW1'!AA26) | ¬¬IF(ISBLANK('DPW1'!AB26),"",'DPW1'!AB26) | ¬¬IF(ISBLANK('DPW1'!AC26),"",'DPW1'!AC26) | ¬¬IF(ISBLANK('DPW1'!AD26),"",'DPW1'!AD26) | ¬¬IF(ISBLANK('DPW1'!AE26),"",'DPW1'!AE26) | ¬¬IF(ISBLANK('DPW1'!AF26),"",'DPW1'!AF26) | ¬¬IF(ISBLANK('DPW1'!AG26),"",'DPW1'!AG26) | ¬¬IF(ISBLANK('DPW1'!AH26),"",'DPW1'!AH26) | ¬¬IF(ISBLANK('DPW1'!AI26),"",'DPW1'!AI26) | ¬¬IF(ISBLANK('DPW1'!AJ26),"",'DPW1'!AJ26) | ¬¬IF(ISBLANK('DPW1'!AK26),"",'DPW1'!AK26)
¬¬A1000 | ¬¬IF(ISBLANK('DPW1'!BX26),"",'DPW1'!BX26) | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL26),"",'DPW1'!AL26) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM26),"",'DPW1'!AM26)
¬¬A1001 | ¬¬IF(ISBLANK('DPW1'!CA26),"",'DPW1'!CA26) | ¬¬'DPW1'!F26 & "," & 'DPW1'!G26 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H26),"",'DPW1'!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO26),"",'DPW1'!AO26) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP26),"",'DPW1'!AP26)
¬¬A1002 | ¬¬IF(ISBLANK('DPW1'!AW27),"",'DPW1'!AW27) | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K27),"",'DPW1'!K27) | ¬¬IF(ISBLANK('DPW1'!L27),"",'DPW1'!L27) | ¬¬IF(ISBLANK('DPW1'!M27),"",'DPW1'!M27) | ¬¬IF(ISBLANK('DPW1'!N27),"",'DPW1'!N27) | ¬¬IF(ISBLANK('DPW1'!O27),"",'DPW1'!O27) | ¬¬IF(ISBLANK('DPW1'!P27),"",'DPW1'!P27) | ¬¬IF(ISBLANK('DPW1'!Q27),"",'DPW1'!Q27) | ¬¬IF(ISBLANK('DPW1'!R27),"",'DPW1'!R27) | ¬¬IF(ISBLANK('DPW1'!S27),"",'DPW1'!S27) | ¬¬IF(ISBLANK('DPW1'!T27),"",'DPW1'!T27) | ¬¬IF(ISBLANK('DPW1'!U27),"",'DPW1'!U27) | ¬¬IF(ISBLANK('DPW1'!V27),"",'DPW1'!V27)
¬¬A1003 | ¬¬IF(ISBLANK('DPW1'!BI27),"",'DPW1'!BI27) | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W27),"",'DPW1'!W27) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X27),"",'DPW1'!X27)
¬¬A1004 | ¬¬IF(ISBLANK('DPW1'!BL27),"",'DPW1'!BL27) | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z27),"",'DPW1'!Z27) | ¬¬IF(ISBLANK('DPW1'!AA27),"",'DPW1'!AA27) | ¬¬IF(ISBLANK('DPW1'!AB27),"",'DPW1'!AB27) | ¬¬IF(ISBLANK('DPW1'!AC27),"",'DPW1'!AC27) | ¬¬IF(ISBLANK('DPW1'!AD27),"",'DPW1'!AD27) | ¬¬IF(ISBLANK('DPW1'!AE27),"",'DPW1'!AE27) | ¬¬IF(ISBLANK('DPW1'!AF27),"",'DPW1'!AF27) | ¬¬IF(ISBLANK('DPW1'!AG27),"",'DPW1'!AG27) | ¬¬IF(ISBLANK('DPW1'!AH27),"",'DPW1'!AH27) | ¬¬IF(ISBLANK('DPW1'!AI27),"",'DPW1'!AI27) | ¬¬IF(ISBLANK('DPW1'!AJ27),"",'DPW1'!AJ27) | ¬¬IF(ISBLANK('DPW1'!AK27),"",'DPW1'!AK27)
¬¬A1005 | ¬¬IF(ISBLANK('DPW1'!BX27),"",'DPW1'!BX27) | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL27),"",'DPW1'!AL27) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM27),"",'DPW1'!AM27)
¬¬A1006 | ¬¬IF(ISBLANK('DPW1'!CA27),"",'DPW1'!CA27) | ¬¬'DPW1'!F27 & "," & 'DPW1'!G27 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H27),"",'DPW1'!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO27),"",'DPW1'!AO27) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP27),"",'DPW1'!AP27)
¬¬A1007 | ¬¬IF(ISBLANK('DPW1'!AW28),"",'DPW1'!AW28) | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K28),"",'DPW1'!K28) | ¬¬IF(ISBLANK('DPW1'!L28),"",'DPW1'!L28) | ¬¬IF(ISBLANK('DPW1'!M28),"",'DPW1'!M28) | ¬¬IF(ISBLANK('DPW1'!N28),"",'DPW1'!N28) | ¬¬IF(ISBLANK('DPW1'!O28),"",'DPW1'!O28) | ¬¬IF(ISBLANK('DPW1'!P28),"",'DPW1'!P28) | ¬¬IF(ISBLANK('DPW1'!Q28),"",'DPW1'!Q28) | ¬¬IF(ISBLANK('DPW1'!R28),"",'DPW1'!R28) | ¬¬IF(ISBLANK('DPW1'!S28),"",'DPW1'!S28) | ¬¬IF(ISBLANK('DPW1'!T28),"",'DPW1'!T28) | ¬¬IF(ISBLANK('DPW1'!U28),"",'DPW1'!U28) | ¬¬IF(ISBLANK('DPW1'!V28),"",'DPW1'!V28)
¬¬A1008 | ¬¬IF(ISBLANK('DPW1'!BI28),"",'DPW1'!BI28) | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W28),"",'DPW1'!W28) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X28),"",'DPW1'!X28)
¬¬A1009 | ¬¬IF(ISBLANK('DPW1'!BL28),"",'DPW1'!BL28) | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z28),"",'DPW1'!Z28) | ¬¬IF(ISBLANK('DPW1'!AA28),"",'DPW1'!AA28) | ¬¬IF(ISBLANK('DPW1'!AB28),"",'DPW1'!AB28) | ¬¬IF(ISBLANK('DPW1'!AC28),"",'DPW1'!AC28) | ¬¬IF(ISBLANK('DPW1'!AD28),"",'DPW1'!AD28) | ¬¬IF(ISBLANK('DPW1'!AE28),"",'DPW1'!AE28) | ¬¬IF(ISBLANK('DPW1'!AF28),"",'DPW1'!AF28) | ¬¬IF(ISBLANK('DPW1'!AG28),"",'DPW1'!AG28) | ¬¬IF(ISBLANK('DPW1'!AH28),"",'DPW1'!AH28) | ¬¬IF(ISBLANK('DPW1'!AI28),"",'DPW1'!AI28) | ¬¬IF(ISBLANK('DPW1'!AJ28),"",'DPW1'!AJ28) | ¬¬IF(ISBLANK('DPW1'!AK28),"",'DPW1'!AK28)
¬¬A1010 | ¬¬IF(ISBLANK('DPW1'!BX28),"",'DPW1'!BX28) | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL28),"",'DPW1'!AL28) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM28),"",'DPW1'!AM28)
¬¬A1011 | ¬¬IF(ISBLANK('DPW1'!CA28),"",'DPW1'!CA28) | ¬¬'DPW1'!F28 & "," & 'DPW1'!G28 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H28),"",'DPW1'!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO28),"",'DPW1'!AO28) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP28),"",'DPW1'!AP28)
¬¬A1012 | ¬¬IF(ISBLANK('DPW1'!AW29),"",'DPW1'!AW29) | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K29),"",'DPW1'!K29) | ¬¬IF(ISBLANK('DPW1'!L29),"",'DPW1'!L29) | ¬¬IF(ISBLANK('DPW1'!M29),"",'DPW1'!M29) | ¬¬IF(ISBLANK('DPW1'!N29),"",'DPW1'!N29) | ¬¬IF(ISBLANK('DPW1'!O29),"",'DPW1'!O29) | ¬¬IF(ISBLANK('DPW1'!P29),"",'DPW1'!P29) | ¬¬IF(ISBLANK('DPW1'!Q29),"",'DPW1'!Q29) | ¬¬IF(ISBLANK('DPW1'!R29),"",'DPW1'!R29) | ¬¬IF(ISBLANK('DPW1'!S29),"",'DPW1'!S29) | ¬¬IF(ISBLANK('DPW1'!T29),"",'DPW1'!T29) | ¬¬IF(ISBLANK('DPW1'!U29),"",'DPW1'!U29) | ¬¬IF(ISBLANK('DPW1'!V29),"",'DPW1'!V29)
¬¬A1013 | ¬¬IF(ISBLANK('DPW1'!BI29),"",'DPW1'!BI29) | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W29),"",'DPW1'!W29) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X29),"",'DPW1'!X29)
¬¬A1014 | ¬¬IF(ISBLANK('DPW1'!BL29),"",'DPW1'!BL29) | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z29),"",'DPW1'!Z29) | ¬¬IF(ISBLANK('DPW1'!AA29),"",'DPW1'!AA29) | ¬¬IF(ISBLANK('DPW1'!AB29),"",'DPW1'!AB29) | ¬¬IF(ISBLANK('DPW1'!AC29),"",'DPW1'!AC29) | ¬¬IF(ISBLANK('DPW1'!AD29),"",'DPW1'!AD29) | ¬¬IF(ISBLANK('DPW1'!AE29),"",'DPW1'!AE29) | ¬¬IF(ISBLANK('DPW1'!AF29),"",'DPW1'!AF29) | ¬¬IF(ISBLANK('DPW1'!AG29),"",'DPW1'!AG29) | ¬¬IF(ISBLANK('DPW1'!AH29),"",'DPW1'!AH29) | ¬¬IF(ISBLANK('DPW1'!AI29),"",'DPW1'!AI29) | ¬¬IF(ISBLANK('DPW1'!AJ29),"",'DPW1'!AJ29) | ¬¬IF(ISBLANK('DPW1'!AK29),"",'DPW1'!AK29)
¬¬A1015 | ¬¬IF(ISBLANK('DPW1'!BX29),"",'DPW1'!BX29) | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL29),"",'DPW1'!AL29) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM29),"",'DPW1'!AM29)
¬¬A1016 | ¬¬IF(ISBLANK('DPW1'!CA29),"",'DPW1'!CA29) | ¬¬'DPW1'!F29 & "," & 'DPW1'!G29 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H29),"",'DPW1'!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO29),"",'DPW1'!AO29) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP29),"",'DPW1'!AP29)
¬¬A1017 | ¬¬IF(ISBLANK('DPW1'!AW30),"",'DPW1'!AW30) | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K30),"",'DPW1'!K30) | ¬¬IF(ISBLANK('DPW1'!L30),"",'DPW1'!L30) | ¬¬IF(ISBLANK('DPW1'!M30),"",'DPW1'!M30) | ¬¬IF(ISBLANK('DPW1'!N30),"",'DPW1'!N30) | ¬¬IF(ISBLANK('DPW1'!O30),"",'DPW1'!O30) | ¬¬IF(ISBLANK('DPW1'!P30),"",'DPW1'!P30) | ¬¬IF(ISBLANK('DPW1'!Q30),"",'DPW1'!Q30) | ¬¬IF(ISBLANK('DPW1'!R30),"",'DPW1'!R30) | ¬¬IF(ISBLANK('DPW1'!S30),"",'DPW1'!S30) | ¬¬IF(ISBLANK('DPW1'!T30),"",'DPW1'!T30) | ¬¬IF(ISBLANK('DPW1'!U30),"",'DPW1'!U30) | ¬¬IF(ISBLANK('DPW1'!V30),"",'DPW1'!V30)
¬¬A1018 | ¬¬IF(ISBLANK('DPW1'!BI30),"",'DPW1'!BI30) | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W30),"",'DPW1'!W30) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X30),"",'DPW1'!X30)
¬¬A1019 | ¬¬IF(ISBLANK('DPW1'!BL30),"",'DPW1'!BL30) | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z30),"",'DPW1'!Z30) | ¬¬IF(ISBLANK('DPW1'!AA30),"",'DPW1'!AA30) | ¬¬IF(ISBLANK('DPW1'!AB30),"",'DPW1'!AB30) | ¬¬IF(ISBLANK('DPW1'!AC30),"",'DPW1'!AC30) | ¬¬IF(ISBLANK('DPW1'!AD30),"",'DPW1'!AD30) | ¬¬IF(ISBLANK('DPW1'!AE30),"",'DPW1'!AE30) | ¬¬IF(ISBLANK('DPW1'!AF30),"",'DPW1'!AF30) | ¬¬IF(ISBLANK('DPW1'!AG30),"",'DPW1'!AG30) | ¬¬IF(ISBLANK('DPW1'!AH30),"",'DPW1'!AH30) | ¬¬IF(ISBLANK('DPW1'!AI30),"",'DPW1'!AI30) | ¬¬IF(ISBLANK('DPW1'!AJ30),"",'DPW1'!AJ30) | ¬¬IF(ISBLANK('DPW1'!AK30),"",'DPW1'!AK30)
¬¬A1020 | ¬¬IF(ISBLANK('DPW1'!BX30),"",'DPW1'!BX30) | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL30),"",'DPW1'!AL30) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM30),"",'DPW1'!AM30)
¬¬A1021 | ¬¬IF(ISBLANK('DPW1'!CA30),"",'DPW1'!CA30) | ¬¬'DPW1'!F30 & "," & 'DPW1'!G30 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H30),"",'DPW1'!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO30),"",'DPW1'!AO30) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP30),"",'DPW1'!AP30)
¬¬A1022 | ¬¬IF(ISBLANK('DPW1'!AW31),"",'DPW1'!AW31) | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K31),"",'DPW1'!K31) | ¬¬IF(ISBLANK('DPW1'!L31),"",'DPW1'!L31) | ¬¬IF(ISBLANK('DPW1'!M31),"",'DPW1'!M31) | ¬¬IF(ISBLANK('DPW1'!N31),"",'DPW1'!N31) | ¬¬IF(ISBLANK('DPW1'!O31),"",'DPW1'!O31) | ¬¬IF(ISBLANK('DPW1'!P31),"",'DPW1'!P31) | ¬¬IF(ISBLANK('DPW1'!Q31),"",'DPW1'!Q31) | ¬¬IF(ISBLANK('DPW1'!R31),"",'DPW1'!R31) | ¬¬IF(ISBLANK('DPW1'!S31),"",'DPW1'!S31) | ¬¬IF(ISBLANK('DPW1'!T31),"",'DPW1'!T31) | ¬¬IF(ISBLANK('DPW1'!U31),"",'DPW1'!U31) | ¬¬IF(ISBLANK('DPW1'!V31),"",'DPW1'!V31)
¬¬A1023 | ¬¬IF(ISBLANK('DPW1'!BI31),"",'DPW1'!BI31) | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W31),"",'DPW1'!W31) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X31),"",'DPW1'!X31)
¬¬A1024 | ¬¬IF(ISBLANK('DPW1'!BL31),"",'DPW1'!BL31) | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z31),"",'DPW1'!Z31) | ¬¬IF(ISBLANK('DPW1'!AA31),"",'DPW1'!AA31) | ¬¬IF(ISBLANK('DPW1'!AB31),"",'DPW1'!AB31) | ¬¬IF(ISBLANK('DPW1'!AC31),"",'DPW1'!AC31) | ¬¬IF(ISBLANK('DPW1'!AD31),"",'DPW1'!AD31) | ¬¬IF(ISBLANK('DPW1'!AE31),"",'DPW1'!AE31) | ¬¬IF(ISBLANK('DPW1'!AF31),"",'DPW1'!AF31) | ¬¬IF(ISBLANK('DPW1'!AG31),"",'DPW1'!AG31) | ¬¬IF(ISBLANK('DPW1'!AH31),"",'DPW1'!AH31) | ¬¬IF(ISBLANK('DPW1'!AI31),"",'DPW1'!AI31) | ¬¬IF(ISBLANK('DPW1'!AJ31),"",'DPW1'!AJ31) | ¬¬IF(ISBLANK('DPW1'!AK31),"",'DPW1'!AK31)
¬¬A1025 | ¬¬IF(ISBLANK('DPW1'!BX31),"",'DPW1'!BX31) | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL31),"",'DPW1'!AL31) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM31),"",'DPW1'!AM31)
¬¬A1026 | ¬¬IF(ISBLANK('DPW1'!CA31),"",'DPW1'!CA31) | ¬¬'DPW1'!F31 & "," & 'DPW1'!G31 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H31),"",'DPW1'!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO31),"",'DPW1'!AO31) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP31),"",'DPW1'!AP31)
¬¬A1027 | ¬¬IF(ISBLANK('DPW1'!AW32),"",'DPW1'!AW32) | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K32),"",'DPW1'!K32) | ¬¬IF(ISBLANK('DPW1'!L32),"",'DPW1'!L32) | ¬¬IF(ISBLANK('DPW1'!M32),"",'DPW1'!M32) | ¬¬IF(ISBLANK('DPW1'!N32),"",'DPW1'!N32) | ¬¬IF(ISBLANK('DPW1'!O32),"",'DPW1'!O32) | ¬¬IF(ISBLANK('DPW1'!P32),"",'DPW1'!P32) | ¬¬IF(ISBLANK('DPW1'!Q32),"",'DPW1'!Q32) | ¬¬IF(ISBLANK('DPW1'!R32),"",'DPW1'!R32) | ¬¬IF(ISBLANK('DPW1'!S32),"",'DPW1'!S32) | ¬¬IF(ISBLANK('DPW1'!T32),"",'DPW1'!T32) | ¬¬IF(ISBLANK('DPW1'!U32),"",'DPW1'!U32) | ¬¬IF(ISBLANK('DPW1'!V32),"",'DPW1'!V32)
¬¬A1028 | ¬¬IF(ISBLANK('DPW1'!BI32),"",'DPW1'!BI32) | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W32),"",'DPW1'!W32) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X32),"",'DPW1'!X32)
¬¬A1029 | ¬¬IF(ISBLANK('DPW1'!BL32),"",'DPW1'!BL32) | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z32),"",'DPW1'!Z32) | ¬¬IF(ISBLANK('DPW1'!AA32),"",'DPW1'!AA32) | ¬¬IF(ISBLANK('DPW1'!AB32),"",'DPW1'!AB32) | ¬¬IF(ISBLANK('DPW1'!AC32),"",'DPW1'!AC32) | ¬¬IF(ISBLANK('DPW1'!AD32),"",'DPW1'!AD32) | ¬¬IF(ISBLANK('DPW1'!AE32),"",'DPW1'!AE32) | ¬¬IF(ISBLANK('DPW1'!AF32),"",'DPW1'!AF32) | ¬¬IF(ISBLANK('DPW1'!AG32),"",'DPW1'!AG32) | ¬¬IF(ISBLANK('DPW1'!AH32),"",'DPW1'!AH32) | ¬¬IF(ISBLANK('DPW1'!AI32),"",'DPW1'!AI32) | ¬¬IF(ISBLANK('DPW1'!AJ32),"",'DPW1'!AJ32) | ¬¬IF(ISBLANK('DPW1'!AK32),"",'DPW1'!AK32)
¬¬A1030 | ¬¬IF(ISBLANK('DPW1'!BX32),"",'DPW1'!BX32) | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL32),"",'DPW1'!AL32) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM32),"",'DPW1'!AM32)
¬¬A1031 | ¬¬IF(ISBLANK('DPW1'!CA32),"",'DPW1'!CA32) | ¬¬'DPW1'!F32 & "," & 'DPW1'!G32 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H32),"",'DPW1'!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO32),"",'DPW1'!AO32) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP32),"",'DPW1'!AP32)
¬¬A1032 | ¬¬IF(ISBLANK('DPW1'!AW33),"",'DPW1'!AW33) | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K33),"",'DPW1'!K33) | ¬¬IF(ISBLANK('DPW1'!L33),"",'DPW1'!L33) | ¬¬IF(ISBLANK('DPW1'!M33),"",'DPW1'!M33) | ¬¬IF(ISBLANK('DPW1'!N33),"",'DPW1'!N33) | ¬¬IF(ISBLANK('DPW1'!O33),"",'DPW1'!O33) | ¬¬IF(ISBLANK('DPW1'!P33),"",'DPW1'!P33) | ¬¬IF(ISBLANK('DPW1'!Q33),"",'DPW1'!Q33) | ¬¬IF(ISBLANK('DPW1'!R33),"",'DPW1'!R33) | ¬¬IF(ISBLANK('DPW1'!S33),"",'DPW1'!S33) | ¬¬IF(ISBLANK('DPW1'!T33),"",'DPW1'!T33) | ¬¬IF(ISBLANK('DPW1'!U33),"",'DPW1'!U33) | ¬¬IF(ISBLANK('DPW1'!V33),"",'DPW1'!V33)
¬¬A1033 | ¬¬IF(ISBLANK('DPW1'!BI33),"",'DPW1'!BI33) | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W33),"",'DPW1'!W33) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X33),"",'DPW1'!X33)
¬¬A1034 | ¬¬IF(ISBLANK('DPW1'!BL33),"",'DPW1'!BL33) | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z33),"",'DPW1'!Z33) | ¬¬IF(ISBLANK('DPW1'!AA33),"",'DPW1'!AA33) | ¬¬IF(ISBLANK('DPW1'!AB33),"",'DPW1'!AB33) | ¬¬IF(ISBLANK('DPW1'!AC33),"",'DPW1'!AC33) | ¬¬IF(ISBLANK('DPW1'!AD33),"",'DPW1'!AD33) | ¬¬IF(ISBLANK('DPW1'!AE33),"",'DPW1'!AE33) | ¬¬IF(ISBLANK('DPW1'!AF33),"",'DPW1'!AF33) | ¬¬IF(ISBLANK('DPW1'!AG33),"",'DPW1'!AG33) | ¬¬IF(ISBLANK('DPW1'!AH33),"",'DPW1'!AH33) | ¬¬IF(ISBLANK('DPW1'!AI33),"",'DPW1'!AI33) | ¬¬IF(ISBLANK('DPW1'!AJ33),"",'DPW1'!AJ33) | ¬¬IF(ISBLANK('DPW1'!AK33),"",'DPW1'!AK33)
¬¬A1035 | ¬¬IF(ISBLANK('DPW1'!BX33),"",'DPW1'!BX33) | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL33),"",'DPW1'!AL33) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM33),"",'DPW1'!AM33)
¬¬A1036 | ¬¬IF(ISBLANK('DPW1'!CA33),"",'DPW1'!CA33) | ¬¬'DPW1'!F33 & "," & 'DPW1'!G33 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H33),"",'DPW1'!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO33),"",'DPW1'!AO33) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP33),"",'DPW1'!AP33)
¬¬A1037 | ¬¬IF(ISBLANK('DPW1'!AW34),"",'DPW1'!AW34) | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K34),"",'DPW1'!K34) | ¬¬IF(ISBLANK('DPW1'!L34),"",'DPW1'!L34) | ¬¬IF(ISBLANK('DPW1'!M34),"",'DPW1'!M34) | ¬¬IF(ISBLANK('DPW1'!N34),"",'DPW1'!N34) | ¬¬IF(ISBLANK('DPW1'!O34),"",'DPW1'!O34) | ¬¬IF(ISBLANK('DPW1'!P34),"",'DPW1'!P34) | ¬¬IF(ISBLANK('DPW1'!Q34),"",'DPW1'!Q34) | ¬¬IF(ISBLANK('DPW1'!R34),"",'DPW1'!R34) | ¬¬IF(ISBLANK('DPW1'!S34),"",'DPW1'!S34) | ¬¬IF(ISBLANK('DPW1'!T34),"",'DPW1'!T34) | ¬¬IF(ISBLANK('DPW1'!U34),"",'DPW1'!U34) | ¬¬IF(ISBLANK('DPW1'!V34),"",'DPW1'!V34)
¬¬A1038 | ¬¬IF(ISBLANK('DPW1'!BI34),"",'DPW1'!BI34) | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W34),"",'DPW1'!W34) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X34),"",'DPW1'!X34)
¬¬A1039 | ¬¬IF(ISBLANK('DPW1'!BL34),"",'DPW1'!BL34) | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z34),"",'DPW1'!Z34) | ¬¬IF(ISBLANK('DPW1'!AA34),"",'DPW1'!AA34) | ¬¬IF(ISBLANK('DPW1'!AB34),"",'DPW1'!AB34) | ¬¬IF(ISBLANK('DPW1'!AC34),"",'DPW1'!AC34) | ¬¬IF(ISBLANK('DPW1'!AD34),"",'DPW1'!AD34) | ¬¬IF(ISBLANK('DPW1'!AE34),"",'DPW1'!AE34) | ¬¬IF(ISBLANK('DPW1'!AF34),"",'DPW1'!AF34) | ¬¬IF(ISBLANK('DPW1'!AG34),"",'DPW1'!AG34) | ¬¬IF(ISBLANK('DPW1'!AH34),"",'DPW1'!AH34) | ¬¬IF(ISBLANK('DPW1'!AI34),"",'DPW1'!AI34) | ¬¬IF(ISBLANK('DPW1'!AJ34),"",'DPW1'!AJ34) | ¬¬IF(ISBLANK('DPW1'!AK34),"",'DPW1'!AK34)
¬¬A1040 | ¬¬IF(ISBLANK('DPW1'!BX34),"",'DPW1'!BX34) | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL34),"",'DPW1'!AL34) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM34),"",'DPW1'!AM34)
¬¬A1041 | ¬¬IF(ISBLANK('DPW1'!CA34),"",'DPW1'!CA34) | ¬¬'DPW1'!F34 & "," & 'DPW1'!G34 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H34),"",'DPW1'!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO34),"",'DPW1'!AO34) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP34),"",'DPW1'!AP34)
¬¬A1042 | ¬¬IF(ISBLANK('DPW1'!AW35),"",'DPW1'!AW35) | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K35),"",'DPW1'!K35) | ¬¬IF(ISBLANK('DPW1'!L35),"",'DPW1'!L35) | ¬¬IF(ISBLANK('DPW1'!M35),"",'DPW1'!M35) | ¬¬IF(ISBLANK('DPW1'!N35),"",'DPW1'!N35) | ¬¬IF(ISBLANK('DPW1'!O35),"",'DPW1'!O35) | ¬¬IF(ISBLANK('DPW1'!P35),"",'DPW1'!P35) | ¬¬IF(ISBLANK('DPW1'!Q35),"",'DPW1'!Q35) | ¬¬IF(ISBLANK('DPW1'!R35),"",'DPW1'!R35) | ¬¬IF(ISBLANK('DPW1'!S35),"",'DPW1'!S35) | ¬¬IF(ISBLANK('DPW1'!T35),"",'DPW1'!T35) | ¬¬IF(ISBLANK('DPW1'!U35),"",'DPW1'!U35) | ¬¬IF(ISBLANK('DPW1'!V35),"",'DPW1'!V35)
¬¬A1043 | ¬¬IF(ISBLANK('DPW1'!BI35),"",'DPW1'!BI35) | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W35),"",'DPW1'!W35) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X35),"",'DPW1'!X35)
¬¬A1044 | ¬¬IF(ISBLANK('DPW1'!BL35),"",'DPW1'!BL35) | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z35),"",'DPW1'!Z35) | ¬¬IF(ISBLANK('DPW1'!AA35),"",'DPW1'!AA35) | ¬¬IF(ISBLANK('DPW1'!AB35),"",'DPW1'!AB35) | ¬¬IF(ISBLANK('DPW1'!AC35),"",'DPW1'!AC35) | ¬¬IF(ISBLANK('DPW1'!AD35),"",'DPW1'!AD35) | ¬¬IF(ISBLANK('DPW1'!AE35),"",'DPW1'!AE35) | ¬¬IF(ISBLANK('DPW1'!AF35),"",'DPW1'!AF35) | ¬¬IF(ISBLANK('DPW1'!AG35),"",'DPW1'!AG35) | ¬¬IF(ISBLANK('DPW1'!AH35),"",'DPW1'!AH35) | ¬¬IF(ISBLANK('DPW1'!AI35),"",'DPW1'!AI35) | ¬¬IF(ISBLANK('DPW1'!AJ35),"",'DPW1'!AJ35) | ¬¬IF(ISBLANK('DPW1'!AK35),"",'DPW1'!AK35)
¬¬A1045 | ¬¬IF(ISBLANK('DPW1'!BX35),"",'DPW1'!BX35) | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL35),"",'DPW1'!AL35) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM35),"",'DPW1'!AM35)
¬¬A1046 | ¬¬IF(ISBLANK('DPW1'!CA35),"",'DPW1'!CA35) | ¬¬'DPW1'!F35 & "," & 'DPW1'!G35 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H35),"",'DPW1'!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO35),"",'DPW1'!AO35) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP35),"",'DPW1'!AP35)
¬¬A1047 | ¬¬IF(ISBLANK('DPW1'!AW36),"",'DPW1'!AW36) | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K36),"",'DPW1'!K36) | ¬¬IF(ISBLANK('DPW1'!L36),"",'DPW1'!L36) | ¬¬IF(ISBLANK('DPW1'!M36),"",'DPW1'!M36) | ¬¬IF(ISBLANK('DPW1'!N36),"",'DPW1'!N36) | ¬¬IF(ISBLANK('DPW1'!O36),"",'DPW1'!O36) | ¬¬IF(ISBLANK('DPW1'!P36),"",'DPW1'!P36) | ¬¬IF(ISBLANK('DPW1'!Q36),"",'DPW1'!Q36) | ¬¬IF(ISBLANK('DPW1'!R36),"",'DPW1'!R36) | ¬¬IF(ISBLANK('DPW1'!S36),"",'DPW1'!S36) | ¬¬IF(ISBLANK('DPW1'!T36),"",'DPW1'!T36) | ¬¬IF(ISBLANK('DPW1'!U36),"",'DPW1'!U36) | ¬¬IF(ISBLANK('DPW1'!V36),"",'DPW1'!V36)
¬¬A1048 | ¬¬IF(ISBLANK('DPW1'!BI36),"",'DPW1'!BI36) | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W36),"",'DPW1'!W36) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X36),"",'DPW1'!X36)
¬¬A1049 | ¬¬IF(ISBLANK('DPW1'!BL36),"",'DPW1'!BL36) | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z36),"",'DPW1'!Z36) | ¬¬IF(ISBLANK('DPW1'!AA36),"",'DPW1'!AA36) | ¬¬IF(ISBLANK('DPW1'!AB36),"",'DPW1'!AB36) | ¬¬IF(ISBLANK('DPW1'!AC36),"",'DPW1'!AC36) | ¬¬IF(ISBLANK('DPW1'!AD36),"",'DPW1'!AD36) | ¬¬IF(ISBLANK('DPW1'!AE36),"",'DPW1'!AE36) | ¬¬IF(ISBLANK('DPW1'!AF36),"",'DPW1'!AF36) | ¬¬IF(ISBLANK('DPW1'!AG36),"",'DPW1'!AG36) | ¬¬IF(ISBLANK('DPW1'!AH36),"",'DPW1'!AH36) | ¬¬IF(ISBLANK('DPW1'!AI36),"",'DPW1'!AI36) | ¬¬IF(ISBLANK('DPW1'!AJ36),"",'DPW1'!AJ36) | ¬¬IF(ISBLANK('DPW1'!AK36),"",'DPW1'!AK36)
¬¬A1050 | ¬¬IF(ISBLANK('DPW1'!BX36),"",'DPW1'!BX36) | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL36),"",'DPW1'!AL36) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM36),"",'DPW1'!AM36)
¬¬A1051 | ¬¬IF(ISBLANK('DPW1'!CA36),"",'DPW1'!CA36) | ¬¬'DPW1'!F36 & "," & 'DPW1'!G36 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H36),"",'DPW1'!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO36),"",'DPW1'!AO36) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP36),"",'DPW1'!AP36)
¬¬A1052 | ¬¬IF(ISBLANK('DPW1'!AW37),"",'DPW1'!AW37) | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K37),"",'DPW1'!K37) | ¬¬IF(ISBLANK('DPW1'!L37),"",'DPW1'!L37) | ¬¬IF(ISBLANK('DPW1'!M37),"",'DPW1'!M37) | ¬¬IF(ISBLANK('DPW1'!N37),"",'DPW1'!N37) | ¬¬IF(ISBLANK('DPW1'!O37),"",'DPW1'!O37) | ¬¬IF(ISBLANK('DPW1'!P37),"",'DPW1'!P37) | ¬¬IF(ISBLANK('DPW1'!Q37),"",'DPW1'!Q37) | ¬¬IF(ISBLANK('DPW1'!R37),"",'DPW1'!R37) | ¬¬IF(ISBLANK('DPW1'!S37),"",'DPW1'!S37) | ¬¬IF(ISBLANK('DPW1'!T37),"",'DPW1'!T37) | ¬¬IF(ISBLANK('DPW1'!U37),"",'DPW1'!U37) | ¬¬IF(ISBLANK('DPW1'!V37),"",'DPW1'!V37)
¬¬A1053 | ¬¬IF(ISBLANK('DPW1'!BI37),"",'DPW1'!BI37) | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W37),"",'DPW1'!W37) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X37),"",'DPW1'!X37)
¬¬A1054 | ¬¬IF(ISBLANK('DPW1'!BL37),"",'DPW1'!BL37) | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z37),"",'DPW1'!Z37) | ¬¬IF(ISBLANK('DPW1'!AA37),"",'DPW1'!AA37) | ¬¬IF(ISBLANK('DPW1'!AB37),"",'DPW1'!AB37) | ¬¬IF(ISBLANK('DPW1'!AC37),"",'DPW1'!AC37) | ¬¬IF(ISBLANK('DPW1'!AD37),"",'DPW1'!AD37) | ¬¬IF(ISBLANK('DPW1'!AE37),"",'DPW1'!AE37) | ¬¬IF(ISBLANK('DPW1'!AF37),"",'DPW1'!AF37) | ¬¬IF(ISBLANK('DPW1'!AG37),"",'DPW1'!AG37) | ¬¬IF(ISBLANK('DPW1'!AH37),"",'DPW1'!AH37) | ¬¬IF(ISBLANK('DPW1'!AI37),"",'DPW1'!AI37) | ¬¬IF(ISBLANK('DPW1'!AJ37),"",'DPW1'!AJ37) | ¬¬IF(ISBLANK('DPW1'!AK37),"",'DPW1'!AK37)
¬¬A1055 | ¬¬IF(ISBLANK('DPW1'!BX37),"",'DPW1'!BX37) | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL37),"",'DPW1'!AL37) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM37),"",'DPW1'!AM37)
¬¬A1056 | ¬¬IF(ISBLANK('DPW1'!CA37),"",'DPW1'!CA37) | ¬¬'DPW1'!F37 & "," & 'DPW1'!G37 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H37),"",'DPW1'!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO37),"",'DPW1'!AO37) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP37),"",'DPW1'!AP37)
¬¬A1057 | ¬¬IF(ISBLANK('DPW1'!AW38),"",'DPW1'!AW38) | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K38),"",'DPW1'!K38) | ¬¬IF(ISBLANK('DPW1'!L38),"",'DPW1'!L38) | ¬¬IF(ISBLANK('DPW1'!M38),"",'DPW1'!M38) | ¬¬IF(ISBLANK('DPW1'!N38),"",'DPW1'!N38) | ¬¬IF(ISBLANK('DPW1'!O38),"",'DPW1'!O38) | ¬¬IF(ISBLANK('DPW1'!P38),"",'DPW1'!P38) | ¬¬IF(ISBLANK('DPW1'!Q38),"",'DPW1'!Q38) | ¬¬IF(ISBLANK('DPW1'!R38),"",'DPW1'!R38) | ¬¬IF(ISBLANK('DPW1'!S38),"",'DPW1'!S38) | ¬¬IF(ISBLANK('DPW1'!T38),"",'DPW1'!T38) | ¬¬IF(ISBLANK('DPW1'!U38),"",'DPW1'!U38) | ¬¬IF(ISBLANK('DPW1'!V38),"",'DPW1'!V38)
¬¬A1058 | ¬¬IF(ISBLANK('DPW1'!BI38),"",'DPW1'!BI38) | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W38),"",'DPW1'!W38) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X38),"",'DPW1'!X38)
¬¬A1059 | ¬¬IF(ISBLANK('DPW1'!BL38),"",'DPW1'!BL38) | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z38),"",'DPW1'!Z38) | ¬¬IF(ISBLANK('DPW1'!AA38),"",'DPW1'!AA38) | ¬¬IF(ISBLANK('DPW1'!AB38),"",'DPW1'!AB38) | ¬¬IF(ISBLANK('DPW1'!AC38),"",'DPW1'!AC38) | ¬¬IF(ISBLANK('DPW1'!AD38),"",'DPW1'!AD38) | ¬¬IF(ISBLANK('DPW1'!AE38),"",'DPW1'!AE38) | ¬¬IF(ISBLANK('DPW1'!AF38),"",'DPW1'!AF38) | ¬¬IF(ISBLANK('DPW1'!AG38),"",'DPW1'!AG38) | ¬¬IF(ISBLANK('DPW1'!AH38),"",'DPW1'!AH38) | ¬¬IF(ISBLANK('DPW1'!AI38),"",'DPW1'!AI38) | ¬¬IF(ISBLANK('DPW1'!AJ38),"",'DPW1'!AJ38) | ¬¬IF(ISBLANK('DPW1'!AK38),"",'DPW1'!AK38)
¬¬A1060 | ¬¬IF(ISBLANK('DPW1'!BX38),"",'DPW1'!BX38) | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL38),"",'DPW1'!AL38) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM38),"",'DPW1'!AM38)
¬¬A1061 | ¬¬IF(ISBLANK('DPW1'!CA38),"",'DPW1'!CA38) | ¬¬'DPW1'!F38 & "," & 'DPW1'!G38 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H38),"",'DPW1'!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO38),"",'DPW1'!AO38) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP38),"",'DPW1'!AP38)
¬¬A1062 | ¬¬IF(ISBLANK('DPW1'!AW39),"",'DPW1'!AW39) | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K39),"",'DPW1'!K39) | ¬¬IF(ISBLANK('DPW1'!L39),"",'DPW1'!L39) | ¬¬IF(ISBLANK('DPW1'!M39),"",'DPW1'!M39) | ¬¬IF(ISBLANK('DPW1'!N39),"",'DPW1'!N39) | ¬¬IF(ISBLANK('DPW1'!O39),"",'DPW1'!O39) | ¬¬IF(ISBLANK('DPW1'!P39),"",'DPW1'!P39) | ¬¬IF(ISBLANK('DPW1'!Q39),"",'DPW1'!Q39) | ¬¬IF(ISBLANK('DPW1'!R39),"",'DPW1'!R39) | ¬¬IF(ISBLANK('DPW1'!S39),"",'DPW1'!S39) | ¬¬IF(ISBLANK('DPW1'!T39),"",'DPW1'!T39) | ¬¬IF(ISBLANK('DPW1'!U39),"",'DPW1'!U39) | ¬¬IF(ISBLANK('DPW1'!V39),"",'DPW1'!V39)
¬¬A1063 | ¬¬IF(ISBLANK('DPW1'!BI39),"",'DPW1'!BI39) | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W39),"",'DPW1'!W39) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X39),"",'DPW1'!X39)
¬¬A1064 | ¬¬IF(ISBLANK('DPW1'!BL39),"",'DPW1'!BL39) | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z39),"",'DPW1'!Z39) | ¬¬IF(ISBLANK('DPW1'!AA39),"",'DPW1'!AA39) | ¬¬IF(ISBLANK('DPW1'!AB39),"",'DPW1'!AB39) | ¬¬IF(ISBLANK('DPW1'!AC39),"",'DPW1'!AC39) | ¬¬IF(ISBLANK('DPW1'!AD39),"",'DPW1'!AD39) | ¬¬IF(ISBLANK('DPW1'!AE39),"",'DPW1'!AE39) | ¬¬IF(ISBLANK('DPW1'!AF39),"",'DPW1'!AF39) | ¬¬IF(ISBLANK('DPW1'!AG39),"",'DPW1'!AG39) | ¬¬IF(ISBLANK('DPW1'!AH39),"",'DPW1'!AH39) | ¬¬IF(ISBLANK('DPW1'!AI39),"",'DPW1'!AI39) | ¬¬IF(ISBLANK('DPW1'!AJ39),"",'DPW1'!AJ39) | ¬¬IF(ISBLANK('DPW1'!AK39),"",'DPW1'!AK39)
¬¬A1065 | ¬¬IF(ISBLANK('DPW1'!BX39),"",'DPW1'!BX39) | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL39),"",'DPW1'!AL39) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM39),"",'DPW1'!AM39)
¬¬A1066 | ¬¬IF(ISBLANK('DPW1'!CA39),"",'DPW1'!CA39) | ¬¬'DPW1'!F39 & "," & 'DPW1'!G39 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H39),"",'DPW1'!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO39),"",'DPW1'!AO39) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP39),"",'DPW1'!AP39)
¬¬A1067 | ¬¬IF(ISBLANK('DPW1'!AW40),"",'DPW1'!AW40) | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K40),"",'DPW1'!K40) | ¬¬IF(ISBLANK('DPW1'!L40),"",'DPW1'!L40) | ¬¬IF(ISBLANK('DPW1'!M40),"",'DPW1'!M40) | ¬¬IF(ISBLANK('DPW1'!N40),"",'DPW1'!N40) | ¬¬IF(ISBLANK('DPW1'!O40),"",'DPW1'!O40) | ¬¬IF(ISBLANK('DPW1'!P40),"",'DPW1'!P40) | ¬¬IF(ISBLANK('DPW1'!Q40),"",'DPW1'!Q40) | ¬¬IF(ISBLANK('DPW1'!R40),"",'DPW1'!R40) | ¬¬IF(ISBLANK('DPW1'!S40),"",'DPW1'!S40) | ¬¬IF(ISBLANK('DPW1'!T40),"",'DPW1'!T40) | ¬¬IF(ISBLANK('DPW1'!U40),"",'DPW1'!U40) | ¬¬IF(ISBLANK('DPW1'!V40),"",'DPW1'!V40)
¬¬A1068 | ¬¬IF(ISBLANK('DPW1'!BI40),"",'DPW1'!BI40) | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W40),"",'DPW1'!W40) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X40),"",'DPW1'!X40)
¬¬A1069 | ¬¬IF(ISBLANK('DPW1'!BL40),"",'DPW1'!BL40) | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z40),"",'DPW1'!Z40) | ¬¬IF(ISBLANK('DPW1'!AA40),"",'DPW1'!AA40) | ¬¬IF(ISBLANK('DPW1'!AB40),"",'DPW1'!AB40) | ¬¬IF(ISBLANK('DPW1'!AC40),"",'DPW1'!AC40) | ¬¬IF(ISBLANK('DPW1'!AD40),"",'DPW1'!AD40) | ¬¬IF(ISBLANK('DPW1'!AE40),"",'DPW1'!AE40) | ¬¬IF(ISBLANK('DPW1'!AF40),"",'DPW1'!AF40) | ¬¬IF(ISBLANK('DPW1'!AG40),"",'DPW1'!AG40) | ¬¬IF(ISBLANK('DPW1'!AH40),"",'DPW1'!AH40) | ¬¬IF(ISBLANK('DPW1'!AI40),"",'DPW1'!AI40) | ¬¬IF(ISBLANK('DPW1'!AJ40),"",'DPW1'!AJ40) | ¬¬IF(ISBLANK('DPW1'!AK40),"",'DPW1'!AK40)
¬¬A1070 | ¬¬IF(ISBLANK('DPW1'!BX40),"",'DPW1'!BX40) | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL40),"",'DPW1'!AL40) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM40),"",'DPW1'!AM40)
¬¬A1071 | ¬¬IF(ISBLANK('DPW1'!CA40),"",'DPW1'!CA40) | ¬¬'DPW1'!F40 & "," & 'DPW1'!G40 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H40),"",'DPW1'!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO40),"",'DPW1'!AO40) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP40),"",'DPW1'!AP40)
¬¬A1072 | ¬¬IF(ISBLANK('DPW1'!AW41),"",'DPW1'!AW41) | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K41),"",'DPW1'!K41) | ¬¬IF(ISBLANK('DPW1'!L41),"",'DPW1'!L41) | ¬¬IF(ISBLANK('DPW1'!M41),"",'DPW1'!M41) | ¬¬IF(ISBLANK('DPW1'!N41),"",'DPW1'!N41) | ¬¬IF(ISBLANK('DPW1'!O41),"",'DPW1'!O41) | ¬¬IF(ISBLANK('DPW1'!P41),"",'DPW1'!P41) | ¬¬IF(ISBLANK('DPW1'!Q41),"",'DPW1'!Q41) | ¬¬IF(ISBLANK('DPW1'!R41),"",'DPW1'!R41) | ¬¬IF(ISBLANK('DPW1'!S41),"",'DPW1'!S41) | ¬¬IF(ISBLANK('DPW1'!T41),"",'DPW1'!T41) | ¬¬IF(ISBLANK('DPW1'!U41),"",'DPW1'!U41) | ¬¬IF(ISBLANK('DPW1'!V41),"",'DPW1'!V41)
¬¬A1073 | ¬¬IF(ISBLANK('DPW1'!BI41),"",'DPW1'!BI41) | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W41),"",'DPW1'!W41) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X41),"",'DPW1'!X41)
¬¬A1074 | ¬¬IF(ISBLANK('DPW1'!BL41),"",'DPW1'!BL41) | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z41),"",'DPW1'!Z41) | ¬¬IF(ISBLANK('DPW1'!AA41),"",'DPW1'!AA41) | ¬¬IF(ISBLANK('DPW1'!AB41),"",'DPW1'!AB41) | ¬¬IF(ISBLANK('DPW1'!AC41),"",'DPW1'!AC41) | ¬¬IF(ISBLANK('DPW1'!AD41),"",'DPW1'!AD41) | ¬¬IF(ISBLANK('DPW1'!AE41),"",'DPW1'!AE41) | ¬¬IF(ISBLANK('DPW1'!AF41),"",'DPW1'!AF41) | ¬¬IF(ISBLANK('DPW1'!AG41),"",'DPW1'!AG41) | ¬¬IF(ISBLANK('DPW1'!AH41),"",'DPW1'!AH41) | ¬¬IF(ISBLANK('DPW1'!AI41),"",'DPW1'!AI41) | ¬¬IF(ISBLANK('DPW1'!AJ41),"",'DPW1'!AJ41) | ¬¬IF(ISBLANK('DPW1'!AK41),"",'DPW1'!AK41)
¬¬A1075 | ¬¬IF(ISBLANK('DPW1'!BX41),"",'DPW1'!BX41) | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL41),"",'DPW1'!AL41) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM41),"",'DPW1'!AM41)
¬¬A1076 | ¬¬IF(ISBLANK('DPW1'!CA41),"",'DPW1'!CA41) | ¬¬'DPW1'!F41 & "," & 'DPW1'!G41 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H41),"",'DPW1'!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO41),"",'DPW1'!AO41) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP41),"",'DPW1'!AP41)
¬¬A1077 | ¬¬IF(ISBLANK('DPW1'!AW42),"",'DPW1'!AW42) | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K42),"",'DPW1'!K42) | ¬¬IF(ISBLANK('DPW1'!L42),"",'DPW1'!L42) | ¬¬IF(ISBLANK('DPW1'!M42),"",'DPW1'!M42) | ¬¬IF(ISBLANK('DPW1'!N42),"",'DPW1'!N42) | ¬¬IF(ISBLANK('DPW1'!O42),"",'DPW1'!O42) | ¬¬IF(ISBLANK('DPW1'!P42),"",'DPW1'!P42) | ¬¬IF(ISBLANK('DPW1'!Q42),"",'DPW1'!Q42) | ¬¬IF(ISBLANK('DPW1'!R42),"",'DPW1'!R42) | ¬¬IF(ISBLANK('DPW1'!S42),"",'DPW1'!S42) | ¬¬IF(ISBLANK('DPW1'!T42),"",'DPW1'!T42) | ¬¬IF(ISBLANK('DPW1'!U42),"",'DPW1'!U42) | ¬¬IF(ISBLANK('DPW1'!V42),"",'DPW1'!V42)
¬¬A1078 | ¬¬IF(ISBLANK('DPW1'!BI42),"",'DPW1'!BI42) | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W42),"",'DPW1'!W42) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X42),"",'DPW1'!X42)
¬¬A1079 | ¬¬IF(ISBLANK('DPW1'!BL42),"",'DPW1'!BL42) | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z42),"",'DPW1'!Z42) | ¬¬IF(ISBLANK('DPW1'!AA42),"",'DPW1'!AA42) | ¬¬IF(ISBLANK('DPW1'!AB42),"",'DPW1'!AB42) | ¬¬IF(ISBLANK('DPW1'!AC42),"",'DPW1'!AC42) | ¬¬IF(ISBLANK('DPW1'!AD42),"",'DPW1'!AD42) | ¬¬IF(ISBLANK('DPW1'!AE42),"",'DPW1'!AE42) | ¬¬IF(ISBLANK('DPW1'!AF42),"",'DPW1'!AF42) | ¬¬IF(ISBLANK('DPW1'!AG42),"",'DPW1'!AG42) | ¬¬IF(ISBLANK('DPW1'!AH42),"",'DPW1'!AH42) | ¬¬IF(ISBLANK('DPW1'!AI42),"",'DPW1'!AI42) | ¬¬IF(ISBLANK('DPW1'!AJ42),"",'DPW1'!AJ42) | ¬¬IF(ISBLANK('DPW1'!AK42),"",'DPW1'!AK42)
¬¬A1080 | ¬¬IF(ISBLANK('DPW1'!BX42),"",'DPW1'!BX42) | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL42),"",'DPW1'!AL42) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM42),"",'DPW1'!AM42)
¬¬A1081 | ¬¬IF(ISBLANK('DPW1'!CA42),"",'DPW1'!CA42) | ¬¬'DPW1'!F42 & "," & 'DPW1'!G42 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H42),"",'DPW1'!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO42),"",'DPW1'!AO42) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP42),"",'DPW1'!AP42)
¬¬A1082 | ¬¬IF(ISBLANK('DPW1'!AW43),"",'DPW1'!AW43) | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K43),"",'DPW1'!K43) | ¬¬IF(ISBLANK('DPW1'!L43),"",'DPW1'!L43) | ¬¬IF(ISBLANK('DPW1'!M43),"",'DPW1'!M43) | ¬¬IF(ISBLANK('DPW1'!N43),"",'DPW1'!N43) | ¬¬IF(ISBLANK('DPW1'!O43),"",'DPW1'!O43) | ¬¬IF(ISBLANK('DPW1'!P43),"",'DPW1'!P43) | ¬¬IF(ISBLANK('DPW1'!Q43),"",'DPW1'!Q43) | ¬¬IF(ISBLANK('DPW1'!R43),"",'DPW1'!R43) | ¬¬IF(ISBLANK('DPW1'!S43),"",'DPW1'!S43) | ¬¬IF(ISBLANK('DPW1'!T43),"",'DPW1'!T43) | ¬¬IF(ISBLANK('DPW1'!U43),"",'DPW1'!U43) | ¬¬IF(ISBLANK('DPW1'!V43),"",'DPW1'!V43)
¬¬A1083 | ¬¬IF(ISBLANK('DPW1'!BI43),"",'DPW1'!BI43) | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W43),"",'DPW1'!W43) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X43),"",'DPW1'!X43)
¬¬A1084 | ¬¬IF(ISBLANK('DPW1'!BL43),"",'DPW1'!BL43) | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z43),"",'DPW1'!Z43) | ¬¬IF(ISBLANK('DPW1'!AA43),"",'DPW1'!AA43) | ¬¬IF(ISBLANK('DPW1'!AB43),"",'DPW1'!AB43) | ¬¬IF(ISBLANK('DPW1'!AC43),"",'DPW1'!AC43) | ¬¬IF(ISBLANK('DPW1'!AD43),"",'DPW1'!AD43) | ¬¬IF(ISBLANK('DPW1'!AE43),"",'DPW1'!AE43) | ¬¬IF(ISBLANK('DPW1'!AF43),"",'DPW1'!AF43) | ¬¬IF(ISBLANK('DPW1'!AG43),"",'DPW1'!AG43) | ¬¬IF(ISBLANK('DPW1'!AH43),"",'DPW1'!AH43) | ¬¬IF(ISBLANK('DPW1'!AI43),"",'DPW1'!AI43) | ¬¬IF(ISBLANK('DPW1'!AJ43),"",'DPW1'!AJ43) | ¬¬IF(ISBLANK('DPW1'!AK43),"",'DPW1'!AK43)
¬¬A1085 | ¬¬IF(ISBLANK('DPW1'!BX43),"",'DPW1'!BX43) | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL43),"",'DPW1'!AL43) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM43),"",'DPW1'!AM43)
¬¬A1086 | ¬¬IF(ISBLANK('DPW1'!CA43),"",'DPW1'!CA43) | ¬¬'DPW1'!F43 & "," & 'DPW1'!G43 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H43),"",'DPW1'!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO43),"",'DPW1'!AO43) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP43),"",'DPW1'!AP43)
¬¬A1087 | ¬¬IF(ISBLANK('DPW1'!AW44),"",'DPW1'!AW44) | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K45),"",'DPW1'!K45) | ¬¬IF(ISBLANK('DPW1'!L45),"",'DPW1'!L45) | ¬¬IF(ISBLANK('DPW1'!M45),"",'DPW1'!M45) | ¬¬IF(ISBLANK('DPW1'!N45),"",'DPW1'!N45) | ¬¬IF(ISBLANK('DPW1'!O45),"",'DPW1'!O45) | ¬¬IF(ISBLANK('DPW1'!P45),"",'DPW1'!P45) | ¬¬IF(ISBLANK('DPW1'!Q45),"",'DPW1'!Q45) | ¬¬IF(ISBLANK('DPW1'!R45),"",'DPW1'!R45) | ¬¬IF(ISBLANK('DPW1'!S45),"",'DPW1'!S45) | ¬¬IF(ISBLANK('DPW1'!T45),"",'DPW1'!T45) | ¬¬IF(ISBLANK('DPW1'!U45),"",'DPW1'!U45) | ¬¬IF(ISBLANK('DPW1'!V45),"",'DPW1'!V45)
¬¬A1088 | ¬¬IF(ISBLANK('DPW1'!BI44),"",'DPW1'!BI44) | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W45),"",'DPW1'!W45) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X45),"",'DPW1'!X45)
¬¬A1089 | ¬¬IF(ISBLANK('DPW1'!BL44),"",'DPW1'!BL44) | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z45),"",'DPW1'!Z45) | ¬¬IF(ISBLANK('DPW1'!AA45),"",'DPW1'!AA45) | ¬¬IF(ISBLANK('DPW1'!AB45),"",'DPW1'!AB45) | ¬¬IF(ISBLANK('DPW1'!AC45),"",'DPW1'!AC45) | ¬¬IF(ISBLANK('DPW1'!AD45),"",'DPW1'!AD45) | ¬¬IF(ISBLANK('DPW1'!AE45),"",'DPW1'!AE45) | ¬¬IF(ISBLANK('DPW1'!AF45),"",'DPW1'!AF45) | ¬¬IF(ISBLANK('DPW1'!AG45),"",'DPW1'!AG45) | ¬¬IF(ISBLANK('DPW1'!AH45),"",'DPW1'!AH45) | ¬¬IF(ISBLANK('DPW1'!AI45),"",'DPW1'!AI45) | ¬¬IF(ISBLANK('DPW1'!AJ45),"",'DPW1'!AJ45) | ¬¬IF(ISBLANK('DPW1'!AK45),"",'DPW1'!AK45)
¬¬A1090 | ¬¬IF(ISBLANK('DPW1'!BX44),"",'DPW1'!BX44) | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL45),"",'DPW1'!AL45) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM45),"",'DPW1'!AM45)
¬¬A1091 | ¬¬IF(ISBLANK('DPW1'!CA44),"",'DPW1'!CA44) | ¬¬'DPW1'!F44 & "," & 'DPW1'!G44 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H44),"",'DPW1'!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO45),"",'DPW1'!AO45) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP45),"",'DPW1'!AP45)
¬¬A1092 | ¬¬IF(ISBLANK('DPW1'!AW46),"",'DPW1'!AW46) | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K46),"",'DPW1'!K46) | ¬¬IF(ISBLANK('DPW1'!L46),"",'DPW1'!L46) | ¬¬IF(ISBLANK('DPW1'!M46),"",'DPW1'!M46) | ¬¬IF(ISBLANK('DPW1'!N46),"",'DPW1'!N46) | ¬¬IF(ISBLANK('DPW1'!O46),"",'DPW1'!O46) | ¬¬IF(ISBLANK('DPW1'!P46),"",'DPW1'!P46) | ¬¬IF(ISBLANK('DPW1'!Q46),"",'DPW1'!Q46) | ¬¬IF(ISBLANK('DPW1'!R46),"",'DPW1'!R46) | ¬¬IF(ISBLANK('DPW1'!S46),"",'DPW1'!S46) | ¬¬IF(ISBLANK('DPW1'!T46),"",'DPW1'!T46) | ¬¬IF(ISBLANK('DPW1'!U46),"",'DPW1'!U46) | ¬¬IF(ISBLANK('DPW1'!V46),"",'DPW1'!V46)
¬¬A1093 | ¬¬IF(ISBLANK('DPW1'!BI46),"",'DPW1'!BI46) | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W46),"",'DPW1'!W46) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X46),"",'DPW1'!X46)
¬¬A1094 | ¬¬IF(ISBLANK('DPW1'!BL46),"",'DPW1'!BL46) | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z46),"",'DPW1'!Z46) | ¬¬IF(ISBLANK('DPW1'!AA46),"",'DPW1'!AA46) | ¬¬IF(ISBLANK('DPW1'!AB46),"",'DPW1'!AB46) | ¬¬IF(ISBLANK('DPW1'!AC46),"",'DPW1'!AC46) | ¬¬IF(ISBLANK('DPW1'!AD46),"",'DPW1'!AD46) | ¬¬IF(ISBLANK('DPW1'!AE46),"",'DPW1'!AE46) | ¬¬IF(ISBLANK('DPW1'!AF46),"",'DPW1'!AF46) | ¬¬IF(ISBLANK('DPW1'!AG46),"",'DPW1'!AG46) | ¬¬IF(ISBLANK('DPW1'!AH46),"",'DPW1'!AH46) | ¬¬IF(ISBLANK('DPW1'!AI46),"",'DPW1'!AI46) | ¬¬IF(ISBLANK('DPW1'!AJ46),"",'DPW1'!AJ46) | ¬¬IF(ISBLANK('DPW1'!AK46),"",'DPW1'!AK46)
¬¬A1095 | ¬¬IF(ISBLANK('DPW1'!BX46),"",'DPW1'!BX46) | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL46),"",'DPW1'!AL46) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM46),"",'DPW1'!AM46)
¬¬A1096 | ¬¬IF(ISBLANK('DPW1'!CA46),"",'DPW1'!CA46) | ¬¬'DPW1'!F46 & "," & 'DPW1'!G46 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H46),"",'DPW1'!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO46),"",'DPW1'!AO46) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP46),"",'DPW1'!AP46)
¬¬A1097 | ¬¬IF(ISBLANK('DPW1'!AW47),"",'DPW1'!AW47) | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K47),"",'DPW1'!K47) | ¬¬IF(ISBLANK('DPW1'!L47),"",'DPW1'!L47) | ¬¬IF(ISBLANK('DPW1'!M47),"",'DPW1'!M47) | ¬¬IF(ISBLANK('DPW1'!N47),"",'DPW1'!N47) | ¬¬IF(ISBLANK('DPW1'!O47),"",'DPW1'!O47) | ¬¬IF(ISBLANK('DPW1'!P47),"",'DPW1'!P47) | ¬¬IF(ISBLANK('DPW1'!Q47),"",'DPW1'!Q47) | ¬¬IF(ISBLANK('DPW1'!R47),"",'DPW1'!R47) | ¬¬IF(ISBLANK('DPW1'!S47),"",'DPW1'!S47) | ¬¬IF(ISBLANK('DPW1'!T47),"",'DPW1'!T47) | ¬¬IF(ISBLANK('DPW1'!U47),"",'DPW1'!U47) | ¬¬IF(ISBLANK('DPW1'!V47),"",'DPW1'!V47)
¬¬A1098 | ¬¬IF(ISBLANK('DPW1'!BI47),"",'DPW1'!BI47) | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W47),"",'DPW1'!W47) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X47),"",'DPW1'!X47)
¬¬A1099 | ¬¬IF(ISBLANK('DPW1'!BL47),"",'DPW1'!BL47) | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z47),"",'DPW1'!Z47) | ¬¬IF(ISBLANK('DPW1'!AA47),"",'DPW1'!AA47) | ¬¬IF(ISBLANK('DPW1'!AB47),"",'DPW1'!AB47) | ¬¬IF(ISBLANK('DPW1'!AC47),"",'DPW1'!AC47) | ¬¬IF(ISBLANK('DPW1'!AD47),"",'DPW1'!AD47) | ¬¬IF(ISBLANK('DPW1'!AE47),"",'DPW1'!AE47) | ¬¬IF(ISBLANK('DPW1'!AF47),"",'DPW1'!AF47) | ¬¬IF(ISBLANK('DPW1'!AG47),"",'DPW1'!AG47) | ¬¬IF(ISBLANK('DPW1'!AH47),"",'DPW1'!AH47) | ¬¬IF(ISBLANK('DPW1'!AI47),"",'DPW1'!AI47) | ¬¬IF(ISBLANK('DPW1'!AJ47),"",'DPW1'!AJ47) | ¬¬IF(ISBLANK('DPW1'!AK47),"",'DPW1'!AK47)
¬¬A1100 | ¬¬IF(ISBLANK('DPW1'!BX47),"",'DPW1'!BX47) | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL47),"",'DPW1'!AL47) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM47),"",'DPW1'!AM47)
¬¬A1101 | ¬¬IF(ISBLANK('DPW1'!CA47),"",'DPW1'!CA47) | ¬¬'DPW1'!F47 & "," & 'DPW1'!G47 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H47),"",'DPW1'!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO47),"",'DPW1'!AO47) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP47),"",'DPW1'!AP47)
¬¬A1102 | ¬¬IF(ISBLANK('DPW1'!AW48),"",'DPW1'!AW48) | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K48),"",'DPW1'!K48) | ¬¬IF(ISBLANK('DPW1'!L48),"",'DPW1'!L48) | ¬¬IF(ISBLANK('DPW1'!M48),"",'DPW1'!M48) | ¬¬IF(ISBLANK('DPW1'!N48),"",'DPW1'!N48) | ¬¬IF(ISBLANK('DPW1'!O48),"",'DPW1'!O48) | ¬¬IF(ISBLANK('DPW1'!P48),"",'DPW1'!P48) | ¬¬IF(ISBLANK('DPW1'!Q48),"",'DPW1'!Q48) | ¬¬IF(ISBLANK('DPW1'!R48),"",'DPW1'!R48) | ¬¬IF(ISBLANK('DPW1'!S48),"",'DPW1'!S48) | ¬¬IF(ISBLANK('DPW1'!T48),"",'DPW1'!T48) | ¬¬IF(ISBLANK('DPW1'!U48),"",'DPW1'!U48) | ¬¬IF(ISBLANK('DPW1'!V48),"",'DPW1'!V48)
¬¬A1103 | ¬¬IF(ISBLANK('DPW1'!BI48),"",'DPW1'!BI48) | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W48),"",'DPW1'!W48) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X48),"",'DPW1'!X48)
¬¬A1104 | ¬¬IF(ISBLANK('DPW1'!BL48),"",'DPW1'!BL48) | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z48),"",'DPW1'!Z48) | ¬¬IF(ISBLANK('DPW1'!AA48),"",'DPW1'!AA48) | ¬¬IF(ISBLANK('DPW1'!AB48),"",'DPW1'!AB48) | ¬¬IF(ISBLANK('DPW1'!AC48),"",'DPW1'!AC48) | ¬¬IF(ISBLANK('DPW1'!AD48),"",'DPW1'!AD48) | ¬¬IF(ISBLANK('DPW1'!AE48),"",'DPW1'!AE48) | ¬¬IF(ISBLANK('DPW1'!AF48),"",'DPW1'!AF48) | ¬¬IF(ISBLANK('DPW1'!AG48),"",'DPW1'!AG48) | ¬¬IF(ISBLANK('DPW1'!AH48),"",'DPW1'!AH48) | ¬¬IF(ISBLANK('DPW1'!AI48),"",'DPW1'!AI48) | ¬¬IF(ISBLANK('DPW1'!AJ48),"",'DPW1'!AJ48) | ¬¬IF(ISBLANK('DPW1'!AK48),"",'DPW1'!AK48)
¬¬A1105 | ¬¬IF(ISBLANK('DPW1'!BX48),"",'DPW1'!BX48) | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL48),"",'DPW1'!AL48) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM48),"",'DPW1'!AM48)
¬¬A1106 | ¬¬IF(ISBLANK('DPW1'!CA48),"",'DPW1'!CA48) | ¬¬'DPW1'!F48 & "," & 'DPW1'!G48 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H48),"",'DPW1'!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO48),"",'DPW1'!AO48) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP48),"",'DPW1'!AP48)
¬¬A1107 | ¬¬IF(ISBLANK('DPW1'!AW49),"",'DPW1'!AW49) | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!AT5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) | Delta |  | ¬¬IF(ISBLANK('DPW1'!K49),"",'DPW1'!K49) | ¬¬IF(ISBLANK('DPW1'!L49),"",'DPW1'!L49) | ¬¬IF(ISBLANK('DPW1'!M49),"",'DPW1'!M49) | ¬¬IF(ISBLANK('DPW1'!N49),"",'DPW1'!N49) | ¬¬IF(ISBLANK('DPW1'!O49),"",'DPW1'!O49) | ¬¬IF(ISBLANK('DPW1'!P49),"",'DPW1'!P49) | ¬¬IF(ISBLANK('DPW1'!Q49),"",'DPW1'!Q49) | ¬¬IF(ISBLANK('DPW1'!R49),"",'DPW1'!R49) | ¬¬IF(ISBLANK('DPW1'!S49),"",'DPW1'!S49) | ¬¬IF(ISBLANK('DPW1'!T49),"",'DPW1'!T49) | ¬¬IF(ISBLANK('DPW1'!U49),"",'DPW1'!U49) | ¬¬IF(ISBLANK('DPW1'!V49),"",'DPW1'!V49)
¬¬A1108 | ¬¬IF(ISBLANK('DPW1'!BI49),"",'DPW1'!BI49) | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BI5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!W49),"",'DPW1'!W49) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!X49),"",'DPW1'!X49)
¬¬A1109 | ¬¬IF(ISBLANK('DPW1'!BL49),"",'DPW1'!BL49) | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BJ5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) | Delta |  | ¬¬IF(ISBLANK('DPW1'!Z49),"",'DPW1'!Z49) | ¬¬IF(ISBLANK('DPW1'!AA49),"",'DPW1'!AA49) | ¬¬IF(ISBLANK('DPW1'!AB49),"",'DPW1'!AB49) | ¬¬IF(ISBLANK('DPW1'!AC49),"",'DPW1'!AC49) | ¬¬IF(ISBLANK('DPW1'!AD49),"",'DPW1'!AD49) | ¬¬IF(ISBLANK('DPW1'!AE49),"",'DPW1'!AE49) | ¬¬IF(ISBLANK('DPW1'!AF49),"",'DPW1'!AF49) | ¬¬IF(ISBLANK('DPW1'!AG49),"",'DPW1'!AG49) | ¬¬IF(ISBLANK('DPW1'!AH49),"",'DPW1'!AH49) | ¬¬IF(ISBLANK('DPW1'!AI49),"",'DPW1'!AI49) | ¬¬IF(ISBLANK('DPW1'!AJ49),"",'DPW1'!AJ49) | ¬¬IF(ISBLANK('DPW1'!AK49),"",'DPW1'!AK49)
¬¬A1110 | ¬¬IF(ISBLANK('DPW1'!BX49),"",'DPW1'!BX49) | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!BX5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AL49),"",'DPW1'!AL49) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AM49),"",'DPW1'!AM49)
¬¬A1111 | ¬¬IF(ISBLANK('DPW1'!CA49),"",'DPW1'!CA49) | ¬¬'DPW1'!F49 & "," & 'DPW1'!G49 & "," & 'DPW1'!CA5 | ¬¬IF(ISBLANK('DPW1'!H49),"",'DPW1'!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW1'!AO49),"",'DPW1'!AO49) |  |  |  |  | ¬¬IF(ISBLANK('DPW1'!AP49),"",'DPW1'!AP49)
¬¬A1112 | ¬¬IF(ISBLANK('DPW2'!AV8),"",'DPW2'!AV8) | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J8),"",'DPW2'!J8)
¬¬A1113 | ¬¬IF(ISBLANK('DPW2'!AX8),"",'DPW2'!AX8) | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L8),"",'DPW2'!L8) | ¬¬IF(ISBLANK('DPW2'!M8),"",'DPW2'!M8) | ¬¬IF(ISBLANK('DPW2'!N8),"",'DPW2'!N8) | ¬¬IF(ISBLANK('DPW2'!O8),"",'DPW2'!O8) | ¬¬IF(ISBLANK('DPW2'!P8),"",'DPW2'!P8) | ¬¬IF(ISBLANK('DPW2'!Q8),"",'DPW2'!Q8) | ¬¬IF(ISBLANK('DPW2'!R8),"",'DPW2'!R8) | ¬¬IF(ISBLANK('DPW2'!S8),"",'DPW2'!S8) | ¬¬IF(ISBLANK('DPW2'!T8),"",'DPW2'!T8) | ¬¬IF(ISBLANK('DPW2'!U8),"",'DPW2'!U8) | ¬¬IF(ISBLANK('DPW2'!V8),"",'DPW2'!V8) | ¬¬IF(ISBLANK('DPW2'!W8),"",'DPW2'!W8)
¬¬A1114 | ¬¬IF(ISBLANK('DPW2'!BJ8),"",'DPW2'!BJ8) | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X8),"",'DPW2'!X8) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y8),"",'DPW2'!Y8)
¬¬A1115 | ¬¬IF(ISBLANK('DPW2'!BM8),"",'DPW2'!BM8) | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA8),"",'DPW2'!AA8) | ¬¬IF(ISBLANK('DPW2'!AB8),"",'DPW2'!AB8) | ¬¬IF(ISBLANK('DPW2'!AC8),"",'DPW2'!AC8) | ¬¬IF(ISBLANK('DPW2'!AD8),"",'DPW2'!AD8) | ¬¬IF(ISBLANK('DPW2'!AE8),"",'DPW2'!AE8) | ¬¬IF(ISBLANK('DPW2'!AF8),"",'DPW2'!AF8) | ¬¬IF(ISBLANK('DPW2'!AG8),"",'DPW2'!AG8) | ¬¬IF(ISBLANK('DPW2'!AH8),"",'DPW2'!AH8) | ¬¬IF(ISBLANK('DPW2'!AI8),"",'DPW2'!AI8) | ¬¬IF(ISBLANK('DPW2'!AJ8),"",'DPW2'!AJ8) | ¬¬IF(ISBLANK('DPW2'!AK8),"",'DPW2'!AK8) | ¬¬IF(ISBLANK('DPW2'!AL8),"",'DPW2'!AL8)
¬¬A1116 | ¬¬IF(ISBLANK('DPW2'!BY8),"",'DPW2'!BY8) | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM8),"",'DPW2'!AM8) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN8),"",'DPW2'!AN8)
¬¬A1117 | ¬¬IF(ISBLANK('DPW2'!CB8),"",'DPW2'!CB8) | ¬¬'DPW2'!F8 & "," & 'DPW2'!G8 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H8),"",'DPW2'!H8) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP8),"",'DPW2'!AP8) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ8),"",'DPW2'!AQ8)
¬¬A1118 | ¬¬IF(ISBLANK('DPW2'!AV9),"",'DPW2'!AV9) | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J9),"",'DPW2'!J9)
¬¬A1119 | ¬¬IF(ISBLANK('DPW2'!AX9),"",'DPW2'!AX9) | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L9),"",'DPW2'!L9) | ¬¬IF(ISBLANK('DPW2'!M9),"",'DPW2'!M9) | ¬¬IF(ISBLANK('DPW2'!N9),"",'DPW2'!N9) | ¬¬IF(ISBLANK('DPW2'!O9),"",'DPW2'!O9) | ¬¬IF(ISBLANK('DPW2'!P9),"",'DPW2'!P9) | ¬¬IF(ISBLANK('DPW2'!Q9),"",'DPW2'!Q9) | ¬¬IF(ISBLANK('DPW2'!R9),"",'DPW2'!R9) | ¬¬IF(ISBLANK('DPW2'!S9),"",'DPW2'!S9) | ¬¬IF(ISBLANK('DPW2'!T9),"",'DPW2'!T9) | ¬¬IF(ISBLANK('DPW2'!U9),"",'DPW2'!U9) | ¬¬IF(ISBLANK('DPW2'!V9),"",'DPW2'!V9) | ¬¬IF(ISBLANK('DPW2'!W9),"",'DPW2'!W9)
¬¬A1120 | ¬¬IF(ISBLANK('DPW2'!BJ9),"",'DPW2'!BJ9) | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X9),"",'DPW2'!X9) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y9),"",'DPW2'!Y9)
¬¬A1121 | ¬¬IF(ISBLANK('DPW2'!BM9),"",'DPW2'!BM9) | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA9),"",'DPW2'!AA9) | ¬¬IF(ISBLANK('DPW2'!AB9),"",'DPW2'!AB9) | ¬¬IF(ISBLANK('DPW2'!AC9),"",'DPW2'!AC9) | ¬¬IF(ISBLANK('DPW2'!AD9),"",'DPW2'!AD9) | ¬¬IF(ISBLANK('DPW2'!AE9),"",'DPW2'!AE9) | ¬¬IF(ISBLANK('DPW2'!AF9),"",'DPW2'!AF9) | ¬¬IF(ISBLANK('DPW2'!AG9),"",'DPW2'!AG9) | ¬¬IF(ISBLANK('DPW2'!AH9),"",'DPW2'!AH9) | ¬¬IF(ISBLANK('DPW2'!AI9),"",'DPW2'!AI9) | ¬¬IF(ISBLANK('DPW2'!AJ9),"",'DPW2'!AJ9) | ¬¬IF(ISBLANK('DPW2'!AK9),"",'DPW2'!AK9) | ¬¬IF(ISBLANK('DPW2'!AL9),"",'DPW2'!AL9)
¬¬A1122 | ¬¬IF(ISBLANK('DPW2'!BY9),"",'DPW2'!BY9) | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM9),"",'DPW2'!AM9) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN9),"",'DPW2'!AN9)
¬¬A1123 | ¬¬IF(ISBLANK('DPW2'!CB9),"",'DPW2'!CB9) | ¬¬'DPW2'!F9 & "," & 'DPW2'!G9 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H9),"",'DPW2'!H9) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP9),"",'DPW2'!AP9) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ9),"",'DPW2'!AQ9)
¬¬A1124 | ¬¬IF(ISBLANK('DPW2'!AV10),"",'DPW2'!AV10) | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J10),"",'DPW2'!J10)
¬¬A1125 | ¬¬IF(ISBLANK('DPW2'!AX10),"",'DPW2'!AX10) | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L10),"",'DPW2'!L10) | ¬¬IF(ISBLANK('DPW2'!M10),"",'DPW2'!M10) | ¬¬IF(ISBLANK('DPW2'!N10),"",'DPW2'!N10) | ¬¬IF(ISBLANK('DPW2'!O10),"",'DPW2'!O10) | ¬¬IF(ISBLANK('DPW2'!P10),"",'DPW2'!P10) | ¬¬IF(ISBLANK('DPW2'!Q10),"",'DPW2'!Q10) | ¬¬IF(ISBLANK('DPW2'!R10),"",'DPW2'!R10) | ¬¬IF(ISBLANK('DPW2'!S10),"",'DPW2'!S10) | ¬¬IF(ISBLANK('DPW2'!T10),"",'DPW2'!T10) | ¬¬IF(ISBLANK('DPW2'!U10),"",'DPW2'!U10) | ¬¬IF(ISBLANK('DPW2'!V10),"",'DPW2'!V10) | ¬¬IF(ISBLANK('DPW2'!W10),"",'DPW2'!W10)
¬¬A1126 | ¬¬IF(ISBLANK('DPW2'!BJ10),"",'DPW2'!BJ10) | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X10),"",'DPW2'!X10) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y10),"",'DPW2'!Y10)
¬¬A1127 | ¬¬IF(ISBLANK('DPW2'!BM10),"",'DPW2'!BM10) | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA10),"",'DPW2'!AA10) | ¬¬IF(ISBLANK('DPW2'!AB10),"",'DPW2'!AB10) | ¬¬IF(ISBLANK('DPW2'!AC10),"",'DPW2'!AC10) | ¬¬IF(ISBLANK('DPW2'!AD10),"",'DPW2'!AD10) | ¬¬IF(ISBLANK('DPW2'!AE10),"",'DPW2'!AE10) | ¬¬IF(ISBLANK('DPW2'!AF10),"",'DPW2'!AF10) | ¬¬IF(ISBLANK('DPW2'!AG10),"",'DPW2'!AG10) | ¬¬IF(ISBLANK('DPW2'!AH10),"",'DPW2'!AH10) | ¬¬IF(ISBLANK('DPW2'!AI10),"",'DPW2'!AI10) | ¬¬IF(ISBLANK('DPW2'!AJ10),"",'DPW2'!AJ10) | ¬¬IF(ISBLANK('DPW2'!AK10),"",'DPW2'!AK10) | ¬¬IF(ISBLANK('DPW2'!AL10),"",'DPW2'!AL10)
¬¬A1128 | ¬¬IF(ISBLANK('DPW2'!BY10),"",'DPW2'!BY10) | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM10),"",'DPW2'!AM10) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN10),"",'DPW2'!AN10)
¬¬A1129 | ¬¬IF(ISBLANK('DPW2'!CB10),"",'DPW2'!CB10) | ¬¬'DPW2'!F10 & "," & 'DPW2'!G10 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H10),"",'DPW2'!H10) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP10),"",'DPW2'!AP10) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ10),"",'DPW2'!AQ10)
¬¬A1130 | ¬¬IF(ISBLANK('DPW2'!AV11),"",'DPW2'!AV11) | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J11),"",'DPW2'!J11)
¬¬A1131 | ¬¬IF(ISBLANK('DPW2'!AX11),"",'DPW2'!AX11) | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L11),"",'DPW2'!L11) | ¬¬IF(ISBLANK('DPW2'!M11),"",'DPW2'!M11) | ¬¬IF(ISBLANK('DPW2'!N11),"",'DPW2'!N11) | ¬¬IF(ISBLANK('DPW2'!O11),"",'DPW2'!O11) | ¬¬IF(ISBLANK('DPW2'!P11),"",'DPW2'!P11) | ¬¬IF(ISBLANK('DPW2'!Q11),"",'DPW2'!Q11) | ¬¬IF(ISBLANK('DPW2'!R11),"",'DPW2'!R11) | ¬¬IF(ISBLANK('DPW2'!S11),"",'DPW2'!S11) | ¬¬IF(ISBLANK('DPW2'!T11),"",'DPW2'!T11) | ¬¬IF(ISBLANK('DPW2'!U11),"",'DPW2'!U11) | ¬¬IF(ISBLANK('DPW2'!V11),"",'DPW2'!V11) | ¬¬IF(ISBLANK('DPW2'!W11),"",'DPW2'!W11)
¬¬A1132 | ¬¬IF(ISBLANK('DPW2'!BJ11),"",'DPW2'!BJ11) | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X11),"",'DPW2'!X11) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y11),"",'DPW2'!Y11)
¬¬A1133 | ¬¬IF(ISBLANK('DPW2'!BM11),"",'DPW2'!BM11) | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA11),"",'DPW2'!AA11) | ¬¬IF(ISBLANK('DPW2'!AB11),"",'DPW2'!AB11) | ¬¬IF(ISBLANK('DPW2'!AC11),"",'DPW2'!AC11) | ¬¬IF(ISBLANK('DPW2'!AD11),"",'DPW2'!AD11) | ¬¬IF(ISBLANK('DPW2'!AE11),"",'DPW2'!AE11) | ¬¬IF(ISBLANK('DPW2'!AF11),"",'DPW2'!AF11) | ¬¬IF(ISBLANK('DPW2'!AG11),"",'DPW2'!AG11) | ¬¬IF(ISBLANK('DPW2'!AH11),"",'DPW2'!AH11) | ¬¬IF(ISBLANK('DPW2'!AI11),"",'DPW2'!AI11) | ¬¬IF(ISBLANK('DPW2'!AJ11),"",'DPW2'!AJ11) | ¬¬IF(ISBLANK('DPW2'!AK11),"",'DPW2'!AK11) | ¬¬IF(ISBLANK('DPW2'!AL11),"",'DPW2'!AL11)
¬¬A1134 | ¬¬IF(ISBLANK('DPW2'!BY11),"",'DPW2'!BY11) | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM11),"",'DPW2'!AM11) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN11),"",'DPW2'!AN11)
¬¬A1135 | ¬¬IF(ISBLANK('DPW2'!CB11),"",'DPW2'!CB11) | ¬¬'DPW2'!F11 & "," & 'DPW2'!G11 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H11),"",'DPW2'!H11) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP11),"",'DPW2'!AP11) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ11),"",'DPW2'!AQ11)
¬¬A1136 | ¬¬IF(ISBLANK('DPW2'!AV12),"",'DPW2'!AV12) | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J12),"",'DPW2'!J12)
¬¬A1137 | ¬¬IF(ISBLANK('DPW2'!AX12),"",'DPW2'!AX12) | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L12),"",'DPW2'!L12) | ¬¬IF(ISBLANK('DPW2'!M12),"",'DPW2'!M12) | ¬¬IF(ISBLANK('DPW2'!N12),"",'DPW2'!N12) | ¬¬IF(ISBLANK('DPW2'!O12),"",'DPW2'!O12) | ¬¬IF(ISBLANK('DPW2'!P12),"",'DPW2'!P12) | ¬¬IF(ISBLANK('DPW2'!Q12),"",'DPW2'!Q12) | ¬¬IF(ISBLANK('DPW2'!R12),"",'DPW2'!R12) | ¬¬IF(ISBLANK('DPW2'!S12),"",'DPW2'!S12) | ¬¬IF(ISBLANK('DPW2'!T12),"",'DPW2'!T12) | ¬¬IF(ISBLANK('DPW2'!U12),"",'DPW2'!U12) | ¬¬IF(ISBLANK('DPW2'!V12),"",'DPW2'!V12) | ¬¬IF(ISBLANK('DPW2'!W12),"",'DPW2'!W12)
¬¬A1138 | ¬¬IF(ISBLANK('DPW2'!BJ12),"",'DPW2'!BJ12) | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X12),"",'DPW2'!X12) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y12),"",'DPW2'!Y12)
¬¬A1139 | ¬¬IF(ISBLANK('DPW2'!BM12),"",'DPW2'!BM12) | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA12),"",'DPW2'!AA12) | ¬¬IF(ISBLANK('DPW2'!AB12),"",'DPW2'!AB12) | ¬¬IF(ISBLANK('DPW2'!AC12),"",'DPW2'!AC12) | ¬¬IF(ISBLANK('DPW2'!AD12),"",'DPW2'!AD12) | ¬¬IF(ISBLANK('DPW2'!AE12),"",'DPW2'!AE12) | ¬¬IF(ISBLANK('DPW2'!AF12),"",'DPW2'!AF12) | ¬¬IF(ISBLANK('DPW2'!AG12),"",'DPW2'!AG12) | ¬¬IF(ISBLANK('DPW2'!AH12),"",'DPW2'!AH12) | ¬¬IF(ISBLANK('DPW2'!AI12),"",'DPW2'!AI12) | ¬¬IF(ISBLANK('DPW2'!AJ12),"",'DPW2'!AJ12) | ¬¬IF(ISBLANK('DPW2'!AK12),"",'DPW2'!AK12) | ¬¬IF(ISBLANK('DPW2'!AL12),"",'DPW2'!AL12)
¬¬A1140 | ¬¬IF(ISBLANK('DPW2'!BY12),"",'DPW2'!BY12) | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM12),"",'DPW2'!AM12) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN12),"",'DPW2'!AN12)
¬¬A1141 | ¬¬IF(ISBLANK('DPW2'!CB12),"",'DPW2'!CB12) | ¬¬'DPW2'!F12 & "," & 'DPW2'!G12 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H12),"",'DPW2'!H12) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP12),"",'DPW2'!AP12) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ12),"",'DPW2'!AQ12)
¬¬A1142 | ¬¬IF(ISBLANK('DPW2'!AV13),"",'DPW2'!AV13) | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J13),"",'DPW2'!J13)
¬¬A1143 | ¬¬IF(ISBLANK('DPW2'!AX13),"",'DPW2'!AX13) | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L13),"",'DPW2'!L13) | ¬¬IF(ISBLANK('DPW2'!M13),"",'DPW2'!M13) | ¬¬IF(ISBLANK('DPW2'!N13),"",'DPW2'!N13) | ¬¬IF(ISBLANK('DPW2'!O13),"",'DPW2'!O13) | ¬¬IF(ISBLANK('DPW2'!P13),"",'DPW2'!P13) | ¬¬IF(ISBLANK('DPW2'!Q13),"",'DPW2'!Q13) | ¬¬IF(ISBLANK('DPW2'!R13),"",'DPW2'!R13) | ¬¬IF(ISBLANK('DPW2'!S13),"",'DPW2'!S13) | ¬¬IF(ISBLANK('DPW2'!T13),"",'DPW2'!T13) | ¬¬IF(ISBLANK('DPW2'!U13),"",'DPW2'!U13) | ¬¬IF(ISBLANK('DPW2'!V13),"",'DPW2'!V13) | ¬¬IF(ISBLANK('DPW2'!W13),"",'DPW2'!W13)
¬¬A1144 | ¬¬IF(ISBLANK('DPW2'!BJ13),"",'DPW2'!BJ13) | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X13),"",'DPW2'!X13) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y13),"",'DPW2'!Y13)
¬¬A1145 | ¬¬IF(ISBLANK('DPW2'!BM13),"",'DPW2'!BM13) | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA13),"",'DPW2'!AA13) | ¬¬IF(ISBLANK('DPW2'!AB13),"",'DPW2'!AB13) | ¬¬IF(ISBLANK('DPW2'!AC13),"",'DPW2'!AC13) | ¬¬IF(ISBLANK('DPW2'!AD13),"",'DPW2'!AD13) | ¬¬IF(ISBLANK('DPW2'!AE13),"",'DPW2'!AE13) | ¬¬IF(ISBLANK('DPW2'!AF13),"",'DPW2'!AF13) | ¬¬IF(ISBLANK('DPW2'!AG13),"",'DPW2'!AG13) | ¬¬IF(ISBLANK('DPW2'!AH13),"",'DPW2'!AH13) | ¬¬IF(ISBLANK('DPW2'!AI13),"",'DPW2'!AI13) | ¬¬IF(ISBLANK('DPW2'!AJ13),"",'DPW2'!AJ13) | ¬¬IF(ISBLANK('DPW2'!AK13),"",'DPW2'!AK13) | ¬¬IF(ISBLANK('DPW2'!AL13),"",'DPW2'!AL13)
¬¬A1146 | ¬¬IF(ISBLANK('DPW2'!BY13),"",'DPW2'!BY13) | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM13),"",'DPW2'!AM13) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN13),"",'DPW2'!AN13)
¬¬A1147 | ¬¬IF(ISBLANK('DPW2'!CB13),"",'DPW2'!CB13) | ¬¬'DPW2'!F13 & "," & 'DPW2'!G13 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H13),"",'DPW2'!H13) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP13),"",'DPW2'!AP13) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ13),"",'DPW2'!AQ13)
¬¬A1148 | ¬¬IF(ISBLANK('DPW2'!AV14),"",'DPW2'!AV14) | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J14),"",'DPW2'!J14)
¬¬A1149 | ¬¬IF(ISBLANK('DPW2'!AX14),"",'DPW2'!AX14) | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L14),"",'DPW2'!L14) | ¬¬IF(ISBLANK('DPW2'!M14),"",'DPW2'!M14) | ¬¬IF(ISBLANK('DPW2'!N14),"",'DPW2'!N14) | ¬¬IF(ISBLANK('DPW2'!O14),"",'DPW2'!O14) | ¬¬IF(ISBLANK('DPW2'!P14),"",'DPW2'!P14) | ¬¬IF(ISBLANK('DPW2'!Q14),"",'DPW2'!Q14) | ¬¬IF(ISBLANK('DPW2'!R14),"",'DPW2'!R14) | ¬¬IF(ISBLANK('DPW2'!S14),"",'DPW2'!S14) | ¬¬IF(ISBLANK('DPW2'!T14),"",'DPW2'!T14) | ¬¬IF(ISBLANK('DPW2'!U14),"",'DPW2'!U14) | ¬¬IF(ISBLANK('DPW2'!V14),"",'DPW2'!V14) | ¬¬IF(ISBLANK('DPW2'!W14),"",'DPW2'!W14)
¬¬A1150 | ¬¬IF(ISBLANK('DPW2'!BJ14),"",'DPW2'!BJ14) | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X14),"",'DPW2'!X14) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y14),"",'DPW2'!Y14)
¬¬A1151 | ¬¬IF(ISBLANK('DPW2'!BM14),"",'DPW2'!BM14) | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA14),"",'DPW2'!AA14) | ¬¬IF(ISBLANK('DPW2'!AB14),"",'DPW2'!AB14) | ¬¬IF(ISBLANK('DPW2'!AC14),"",'DPW2'!AC14) | ¬¬IF(ISBLANK('DPW2'!AD14),"",'DPW2'!AD14) | ¬¬IF(ISBLANK('DPW2'!AE14),"",'DPW2'!AE14) | ¬¬IF(ISBLANK('DPW2'!AF14),"",'DPW2'!AF14) | ¬¬IF(ISBLANK('DPW2'!AG14),"",'DPW2'!AG14) | ¬¬IF(ISBLANK('DPW2'!AH14),"",'DPW2'!AH14) | ¬¬IF(ISBLANK('DPW2'!AI14),"",'DPW2'!AI14) | ¬¬IF(ISBLANK('DPW2'!AJ14),"",'DPW2'!AJ14) | ¬¬IF(ISBLANK('DPW2'!AK14),"",'DPW2'!AK14) | ¬¬IF(ISBLANK('DPW2'!AL14),"",'DPW2'!AL14)
¬¬A1152 | ¬¬IF(ISBLANK('DPW2'!BY14),"",'DPW2'!BY14) | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM14),"",'DPW2'!AM14) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN14),"",'DPW2'!AN14)
¬¬A1153 | ¬¬IF(ISBLANK('DPW2'!CB14),"",'DPW2'!CB14) | ¬¬'DPW2'!F14 & "," & 'DPW2'!G14 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H14),"",'DPW2'!H14) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP14),"",'DPW2'!AP14) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ14),"",'DPW2'!AQ14)
¬¬A1154 | ¬¬IF(ISBLANK('DPW2'!AV15),"",'DPW2'!AV15) | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J15),"",'DPW2'!J15)
¬¬A1155 | ¬¬IF(ISBLANK('DPW2'!AX15),"",'DPW2'!AX15) | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L15),"",'DPW2'!L15) | ¬¬IF(ISBLANK('DPW2'!M15),"",'DPW2'!M15) | ¬¬IF(ISBLANK('DPW2'!N15),"",'DPW2'!N15) | ¬¬IF(ISBLANK('DPW2'!O15),"",'DPW2'!O15) | ¬¬IF(ISBLANK('DPW2'!P15),"",'DPW2'!P15) | ¬¬IF(ISBLANK('DPW2'!Q15),"",'DPW2'!Q15) | ¬¬IF(ISBLANK('DPW2'!R15),"",'DPW2'!R15) | ¬¬IF(ISBLANK('DPW2'!S15),"",'DPW2'!S15) | ¬¬IF(ISBLANK('DPW2'!T15),"",'DPW2'!T15) | ¬¬IF(ISBLANK('DPW2'!U15),"",'DPW2'!U15) | ¬¬IF(ISBLANK('DPW2'!V15),"",'DPW2'!V15) | ¬¬IF(ISBLANK('DPW2'!W15),"",'DPW2'!W15)
¬¬A1156 | ¬¬IF(ISBLANK('DPW2'!BJ15),"",'DPW2'!BJ15) | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X15),"",'DPW2'!X15) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y15),"",'DPW2'!Y15)
¬¬A1157 | ¬¬IF(ISBLANK('DPW2'!BM15),"",'DPW2'!BM15) | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA15),"",'DPW2'!AA15) | ¬¬IF(ISBLANK('DPW2'!AB15),"",'DPW2'!AB15) | ¬¬IF(ISBLANK('DPW2'!AC15),"",'DPW2'!AC15) | ¬¬IF(ISBLANK('DPW2'!AD15),"",'DPW2'!AD15) | ¬¬IF(ISBLANK('DPW2'!AE15),"",'DPW2'!AE15) | ¬¬IF(ISBLANK('DPW2'!AF15),"",'DPW2'!AF15) | ¬¬IF(ISBLANK('DPW2'!AG15),"",'DPW2'!AG15) | ¬¬IF(ISBLANK('DPW2'!AH15),"",'DPW2'!AH15) | ¬¬IF(ISBLANK('DPW2'!AI15),"",'DPW2'!AI15) | ¬¬IF(ISBLANK('DPW2'!AJ15),"",'DPW2'!AJ15) | ¬¬IF(ISBLANK('DPW2'!AK15),"",'DPW2'!AK15) | ¬¬IF(ISBLANK('DPW2'!AL15),"",'DPW2'!AL15)
¬¬A1158 | ¬¬IF(ISBLANK('DPW2'!BY15),"",'DPW2'!BY15) | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM15),"",'DPW2'!AM15) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN15),"",'DPW2'!AN15)
¬¬A1159 | ¬¬IF(ISBLANK('DPW2'!CB15),"",'DPW2'!CB15) | ¬¬'DPW2'!F15 & "," & 'DPW2'!G15 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H15),"",'DPW2'!H15) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP15),"",'DPW2'!AP15) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ15),"",'DPW2'!AQ15)
¬¬A1160 | ¬¬IF(ISBLANK('DPW2'!AV16),"",'DPW2'!AV16) | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J16),"",'DPW2'!J16)
¬¬A1161 | ¬¬IF(ISBLANK('DPW2'!AX16),"",'DPW2'!AX16) | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L16),"",'DPW2'!L16) | ¬¬IF(ISBLANK('DPW2'!M16),"",'DPW2'!M16) | ¬¬IF(ISBLANK('DPW2'!N16),"",'DPW2'!N16) | ¬¬IF(ISBLANK('DPW2'!O16),"",'DPW2'!O16) | ¬¬IF(ISBLANK('DPW2'!P16),"",'DPW2'!P16) | ¬¬IF(ISBLANK('DPW2'!Q16),"",'DPW2'!Q16) | ¬¬IF(ISBLANK('DPW2'!R16),"",'DPW2'!R16) | ¬¬IF(ISBLANK('DPW2'!S16),"",'DPW2'!S16) | ¬¬IF(ISBLANK('DPW2'!T16),"",'DPW2'!T16) | ¬¬IF(ISBLANK('DPW2'!U16),"",'DPW2'!U16) | ¬¬IF(ISBLANK('DPW2'!V16),"",'DPW2'!V16) | ¬¬IF(ISBLANK('DPW2'!W16),"",'DPW2'!W16)
¬¬A1162 | ¬¬IF(ISBLANK('DPW2'!BJ16),"",'DPW2'!BJ16) | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X16),"",'DPW2'!X16) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y16),"",'DPW2'!Y16)
¬¬A1163 | ¬¬IF(ISBLANK('DPW2'!BM16),"",'DPW2'!BM16) | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA16),"",'DPW2'!AA16) | ¬¬IF(ISBLANK('DPW2'!AB16),"",'DPW2'!AB16) | ¬¬IF(ISBLANK('DPW2'!AC16),"",'DPW2'!AC16) | ¬¬IF(ISBLANK('DPW2'!AD16),"",'DPW2'!AD16) | ¬¬IF(ISBLANK('DPW2'!AE16),"",'DPW2'!AE16) | ¬¬IF(ISBLANK('DPW2'!AF16),"",'DPW2'!AF16) | ¬¬IF(ISBLANK('DPW2'!AG16),"",'DPW2'!AG16) | ¬¬IF(ISBLANK('DPW2'!AH16),"",'DPW2'!AH16) | ¬¬IF(ISBLANK('DPW2'!AI16),"",'DPW2'!AI16) | ¬¬IF(ISBLANK('DPW2'!AJ16),"",'DPW2'!AJ16) | ¬¬IF(ISBLANK('DPW2'!AK16),"",'DPW2'!AK16) | ¬¬IF(ISBLANK('DPW2'!AL16),"",'DPW2'!AL16)
¬¬A1164 | ¬¬IF(ISBLANK('DPW2'!BY16),"",'DPW2'!BY16) | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM16),"",'DPW2'!AM16) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN16),"",'DPW2'!AN16)
¬¬A1165 | ¬¬IF(ISBLANK('DPW2'!CB16),"",'DPW2'!CB16) | ¬¬'DPW2'!F16 & "," & 'DPW2'!G16 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H16),"",'DPW2'!H16) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP16),"",'DPW2'!AP16) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ16),"",'DPW2'!AQ16)
¬¬A1166 | ¬¬IF(ISBLANK('DPW2'!AV17),"",'DPW2'!AV17) | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J17),"",'DPW2'!J17)
¬¬A1167 | ¬¬IF(ISBLANK('DPW2'!AX17),"",'DPW2'!AX17) | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L17),"",'DPW2'!L17) | ¬¬IF(ISBLANK('DPW2'!M17),"",'DPW2'!M17) | ¬¬IF(ISBLANK('DPW2'!N17),"",'DPW2'!N17) | ¬¬IF(ISBLANK('DPW2'!O17),"",'DPW2'!O17) | ¬¬IF(ISBLANK('DPW2'!P17),"",'DPW2'!P17) | ¬¬IF(ISBLANK('DPW2'!Q17),"",'DPW2'!Q17) | ¬¬IF(ISBLANK('DPW2'!R17),"",'DPW2'!R17) | ¬¬IF(ISBLANK('DPW2'!S17),"",'DPW2'!S17) | ¬¬IF(ISBLANK('DPW2'!T17),"",'DPW2'!T17) | ¬¬IF(ISBLANK('DPW2'!U17),"",'DPW2'!U17) | ¬¬IF(ISBLANK('DPW2'!V17),"",'DPW2'!V17) | ¬¬IF(ISBLANK('DPW2'!W17),"",'DPW2'!W17)
¬¬A1168 | ¬¬IF(ISBLANK('DPW2'!BJ17),"",'DPW2'!BJ17) | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X17),"",'DPW2'!X17) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y17),"",'DPW2'!Y17)
¬¬A1169 | ¬¬IF(ISBLANK('DPW2'!BM17),"",'DPW2'!BM17) | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA17),"",'DPW2'!AA17) | ¬¬IF(ISBLANK('DPW2'!AB17),"",'DPW2'!AB17) | ¬¬IF(ISBLANK('DPW2'!AC17),"",'DPW2'!AC17) | ¬¬IF(ISBLANK('DPW2'!AD17),"",'DPW2'!AD17) | ¬¬IF(ISBLANK('DPW2'!AE17),"",'DPW2'!AE17) | ¬¬IF(ISBLANK('DPW2'!AF17),"",'DPW2'!AF17) | ¬¬IF(ISBLANK('DPW2'!AG17),"",'DPW2'!AG17) | ¬¬IF(ISBLANK('DPW2'!AH17),"",'DPW2'!AH17) | ¬¬IF(ISBLANK('DPW2'!AI17),"",'DPW2'!AI17) | ¬¬IF(ISBLANK('DPW2'!AJ17),"",'DPW2'!AJ17) | ¬¬IF(ISBLANK('DPW2'!AK17),"",'DPW2'!AK17) | ¬¬IF(ISBLANK('DPW2'!AL17),"",'DPW2'!AL17)
¬¬A1170 | ¬¬IF(ISBLANK('DPW2'!BY17),"",'DPW2'!BY17) | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM17),"",'DPW2'!AM17) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN17),"",'DPW2'!AN17)
¬¬A1171 | ¬¬IF(ISBLANK('DPW2'!CB17),"",'DPW2'!CB17) | ¬¬'DPW2'!F17 & "," & 'DPW2'!G17 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H17),"",'DPW2'!H17) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP17),"",'DPW2'!AP17) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ17),"",'DPW2'!AQ17)
¬¬A1172 | ¬¬IF(ISBLANK('DPW2'!AV18),"",'DPW2'!AV18) | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J18),"",'DPW2'!J18)
¬¬A1173 | ¬¬IF(ISBLANK('DPW2'!AX18),"",'DPW2'!AX18) | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L18),"",'DPW2'!L18) | ¬¬IF(ISBLANK('DPW2'!M18),"",'DPW2'!M18) | ¬¬IF(ISBLANK('DPW2'!N18),"",'DPW2'!N18) | ¬¬IF(ISBLANK('DPW2'!O18),"",'DPW2'!O18) | ¬¬IF(ISBLANK('DPW2'!P18),"",'DPW2'!P18) | ¬¬IF(ISBLANK('DPW2'!Q18),"",'DPW2'!Q18) | ¬¬IF(ISBLANK('DPW2'!R18),"",'DPW2'!R18) | ¬¬IF(ISBLANK('DPW2'!S18),"",'DPW2'!S18) | ¬¬IF(ISBLANK('DPW2'!T18),"",'DPW2'!T18) | ¬¬IF(ISBLANK('DPW2'!U18),"",'DPW2'!U18) | ¬¬IF(ISBLANK('DPW2'!V18),"",'DPW2'!V18) | ¬¬IF(ISBLANK('DPW2'!W18),"",'DPW2'!W18)
¬¬A1174 | ¬¬IF(ISBLANK('DPW2'!BJ18),"",'DPW2'!BJ18) | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X18),"",'DPW2'!X18) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y18),"",'DPW2'!Y18)
¬¬A1175 | ¬¬IF(ISBLANK('DPW2'!BM18),"",'DPW2'!BM18) | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA18),"",'DPW2'!AA18) | ¬¬IF(ISBLANK('DPW2'!AB18),"",'DPW2'!AB18) | ¬¬IF(ISBLANK('DPW2'!AC18),"",'DPW2'!AC18) | ¬¬IF(ISBLANK('DPW2'!AD18),"",'DPW2'!AD18) | ¬¬IF(ISBLANK('DPW2'!AE18),"",'DPW2'!AE18) | ¬¬IF(ISBLANK('DPW2'!AF18),"",'DPW2'!AF18) | ¬¬IF(ISBLANK('DPW2'!AG18),"",'DPW2'!AG18) | ¬¬IF(ISBLANK('DPW2'!AH18),"",'DPW2'!AH18) | ¬¬IF(ISBLANK('DPW2'!AI18),"",'DPW2'!AI18) | ¬¬IF(ISBLANK('DPW2'!AJ18),"",'DPW2'!AJ18) | ¬¬IF(ISBLANK('DPW2'!AK18),"",'DPW2'!AK18) | ¬¬IF(ISBLANK('DPW2'!AL18),"",'DPW2'!AL18)
¬¬A1176 | ¬¬IF(ISBLANK('DPW2'!BY18),"",'DPW2'!BY18) | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM18),"",'DPW2'!AM18) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN18),"",'DPW2'!AN18)
¬¬A1177 | ¬¬IF(ISBLANK('DPW2'!CB18),"",'DPW2'!CB18) | ¬¬'DPW2'!F18 & "," & 'DPW2'!G18 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H18),"",'DPW2'!H18) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP18),"",'DPW2'!AP18) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ18),"",'DPW2'!AQ18)
¬¬A1178 | ¬¬IF(ISBLANK('DPW2'!AV19),"",'DPW2'!AV19) | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J19),"",'DPW2'!J19)
¬¬A1179 | ¬¬IF(ISBLANK('DPW2'!AX19),"",'DPW2'!AX19) | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L19),"",'DPW2'!L19) | ¬¬IF(ISBLANK('DPW2'!M19),"",'DPW2'!M19) | ¬¬IF(ISBLANK('DPW2'!N19),"",'DPW2'!N19) | ¬¬IF(ISBLANK('DPW2'!O19),"",'DPW2'!O19) | ¬¬IF(ISBLANK('DPW2'!P19),"",'DPW2'!P19) | ¬¬IF(ISBLANK('DPW2'!Q19),"",'DPW2'!Q19) | ¬¬IF(ISBLANK('DPW2'!R19),"",'DPW2'!R19) | ¬¬IF(ISBLANK('DPW2'!S19),"",'DPW2'!S19) | ¬¬IF(ISBLANK('DPW2'!T19),"",'DPW2'!T19) | ¬¬IF(ISBLANK('DPW2'!U19),"",'DPW2'!U19) | ¬¬IF(ISBLANK('DPW2'!V19),"",'DPW2'!V19) | ¬¬IF(ISBLANK('DPW2'!W19),"",'DPW2'!W19)
¬¬A1180 | ¬¬IF(ISBLANK('DPW2'!BJ19),"",'DPW2'!BJ19) | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X19),"",'DPW2'!X19) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y19),"",'DPW2'!Y19)
¬¬A1181 | ¬¬IF(ISBLANK('DPW2'!BM19),"",'DPW2'!BM19) | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA19),"",'DPW2'!AA19) | ¬¬IF(ISBLANK('DPW2'!AB19),"",'DPW2'!AB19) | ¬¬IF(ISBLANK('DPW2'!AC19),"",'DPW2'!AC19) | ¬¬IF(ISBLANK('DPW2'!AD19),"",'DPW2'!AD19) | ¬¬IF(ISBLANK('DPW2'!AE19),"",'DPW2'!AE19) | ¬¬IF(ISBLANK('DPW2'!AF19),"",'DPW2'!AF19) | ¬¬IF(ISBLANK('DPW2'!AG19),"",'DPW2'!AG19) | ¬¬IF(ISBLANK('DPW2'!AH19),"",'DPW2'!AH19) | ¬¬IF(ISBLANK('DPW2'!AI19),"",'DPW2'!AI19) | ¬¬IF(ISBLANK('DPW2'!AJ19),"",'DPW2'!AJ19) | ¬¬IF(ISBLANK('DPW2'!AK19),"",'DPW2'!AK19) | ¬¬IF(ISBLANK('DPW2'!AL19),"",'DPW2'!AL19)
¬¬A1182 | ¬¬IF(ISBLANK('DPW2'!BY19),"",'DPW2'!BY19) | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM19),"",'DPW2'!AM19) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN19),"",'DPW2'!AN19)
¬¬A1183 | ¬¬IF(ISBLANK('DPW2'!CB19),"",'DPW2'!CB19) | ¬¬'DPW2'!F19 & "," & 'DPW2'!G19 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H19),"",'DPW2'!H19) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP19),"",'DPW2'!AP19) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ19),"",'DPW2'!AQ19)
¬¬A1184 | ¬¬IF(ISBLANK('DPW2'!AV20),"",'DPW2'!AV20) | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J20),"",'DPW2'!J20)
¬¬A1185 | ¬¬IF(ISBLANK('DPW2'!AX20),"",'DPW2'!AX20) | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L20),"",'DPW2'!L20) | ¬¬IF(ISBLANK('DPW2'!M20),"",'DPW2'!M20) | ¬¬IF(ISBLANK('DPW2'!N20),"",'DPW2'!N20) | ¬¬IF(ISBLANK('DPW2'!O20),"",'DPW2'!O20) | ¬¬IF(ISBLANK('DPW2'!P20),"",'DPW2'!P20) | ¬¬IF(ISBLANK('DPW2'!Q20),"",'DPW2'!Q20) | ¬¬IF(ISBLANK('DPW2'!R20),"",'DPW2'!R20) | ¬¬IF(ISBLANK('DPW2'!S20),"",'DPW2'!S20) | ¬¬IF(ISBLANK('DPW2'!T20),"",'DPW2'!T20) | ¬¬IF(ISBLANK('DPW2'!U20),"",'DPW2'!U20) | ¬¬IF(ISBLANK('DPW2'!V20),"",'DPW2'!V20) | ¬¬IF(ISBLANK('DPW2'!W20),"",'DPW2'!W20)
¬¬A1186 | ¬¬IF(ISBLANK('DPW2'!BJ20),"",'DPW2'!BJ20) | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X20),"",'DPW2'!X20) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y20),"",'DPW2'!Y20)
¬¬A1187 | ¬¬IF(ISBLANK('DPW2'!BM20),"",'DPW2'!BM20) | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA20),"",'DPW2'!AA20) | ¬¬IF(ISBLANK('DPW2'!AB20),"",'DPW2'!AB20) | ¬¬IF(ISBLANK('DPW2'!AC20),"",'DPW2'!AC20) | ¬¬IF(ISBLANK('DPW2'!AD20),"",'DPW2'!AD20) | ¬¬IF(ISBLANK('DPW2'!AE20),"",'DPW2'!AE20) | ¬¬IF(ISBLANK('DPW2'!AF20),"",'DPW2'!AF20) | ¬¬IF(ISBLANK('DPW2'!AG20),"",'DPW2'!AG20) | ¬¬IF(ISBLANK('DPW2'!AH20),"",'DPW2'!AH20) | ¬¬IF(ISBLANK('DPW2'!AI20),"",'DPW2'!AI20) | ¬¬IF(ISBLANK('DPW2'!AJ20),"",'DPW2'!AJ20) | ¬¬IF(ISBLANK('DPW2'!AK20),"",'DPW2'!AK20) | ¬¬IF(ISBLANK('DPW2'!AL20),"",'DPW2'!AL20)
¬¬A1188 | ¬¬IF(ISBLANK('DPW2'!BY20),"",'DPW2'!BY20) | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM20),"",'DPW2'!AM20) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN20),"",'DPW2'!AN20)
¬¬A1189 | ¬¬IF(ISBLANK('DPW2'!CB20),"",'DPW2'!CB20) | ¬¬'DPW2'!F20 & "," & 'DPW2'!G20 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H20),"",'DPW2'!H20) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP20),"",'DPW2'!AP20) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ20),"",'DPW2'!AQ20)
¬¬A1190 | ¬¬IF(ISBLANK('DPW2'!AV21),"",'DPW2'!AV21) | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J21),"",'DPW2'!J21)
¬¬A1191 | ¬¬IF(ISBLANK('DPW2'!AX21),"",'DPW2'!AX21) | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L21),"",'DPW2'!L21) | ¬¬IF(ISBLANK('DPW2'!M21),"",'DPW2'!M21) | ¬¬IF(ISBLANK('DPW2'!N21),"",'DPW2'!N21) | ¬¬IF(ISBLANK('DPW2'!O21),"",'DPW2'!O21) | ¬¬IF(ISBLANK('DPW2'!P21),"",'DPW2'!P21) | ¬¬IF(ISBLANK('DPW2'!Q21),"",'DPW2'!Q21) | ¬¬IF(ISBLANK('DPW2'!R21),"",'DPW2'!R21) | ¬¬IF(ISBLANK('DPW2'!S21),"",'DPW2'!S21) | ¬¬IF(ISBLANK('DPW2'!T21),"",'DPW2'!T21) | ¬¬IF(ISBLANK('DPW2'!U21),"",'DPW2'!U21) | ¬¬IF(ISBLANK('DPW2'!V21),"",'DPW2'!V21) | ¬¬IF(ISBLANK('DPW2'!W21),"",'DPW2'!W21)
¬¬A1192 | ¬¬IF(ISBLANK('DPW2'!BJ21),"",'DPW2'!BJ21) | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X21),"",'DPW2'!X21) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y21),"",'DPW2'!Y21)
¬¬A1193 | ¬¬IF(ISBLANK('DPW2'!BM21),"",'DPW2'!BM21) | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA21),"",'DPW2'!AA21) | ¬¬IF(ISBLANK('DPW2'!AB21),"",'DPW2'!AB21) | ¬¬IF(ISBLANK('DPW2'!AC21),"",'DPW2'!AC21) | ¬¬IF(ISBLANK('DPW2'!AD21),"",'DPW2'!AD21) | ¬¬IF(ISBLANK('DPW2'!AE21),"",'DPW2'!AE21) | ¬¬IF(ISBLANK('DPW2'!AF21),"",'DPW2'!AF21) | ¬¬IF(ISBLANK('DPW2'!AG21),"",'DPW2'!AG21) | ¬¬IF(ISBLANK('DPW2'!AH21),"",'DPW2'!AH21) | ¬¬IF(ISBLANK('DPW2'!AI21),"",'DPW2'!AI21) | ¬¬IF(ISBLANK('DPW2'!AJ21),"",'DPW2'!AJ21) | ¬¬IF(ISBLANK('DPW2'!AK21),"",'DPW2'!AK21) | ¬¬IF(ISBLANK('DPW2'!AL21),"",'DPW2'!AL21)
¬¬A1194 | ¬¬IF(ISBLANK('DPW2'!BY21),"",'DPW2'!BY21) | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM21),"",'DPW2'!AM21) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN21),"",'DPW2'!AN21)
¬¬A1195 | ¬¬IF(ISBLANK('DPW2'!CB21),"",'DPW2'!CB21) | ¬¬'DPW2'!F21 & "," & 'DPW2'!G21 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H21),"",'DPW2'!H21) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP21),"",'DPW2'!AP21) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ21),"",'DPW2'!AQ21)
¬¬A1196 | ¬¬IF(ISBLANK('DPW2'!AV22),"",'DPW2'!AV22) | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J22),"",'DPW2'!J22)
¬¬A1197 | ¬¬IF(ISBLANK('DPW2'!AX22),"",'DPW2'!AX22) | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L22),"",'DPW2'!L22) | ¬¬IF(ISBLANK('DPW2'!M22),"",'DPW2'!M22) | ¬¬IF(ISBLANK('DPW2'!N22),"",'DPW2'!N22) | ¬¬IF(ISBLANK('DPW2'!O22),"",'DPW2'!O22) | ¬¬IF(ISBLANK('DPW2'!P22),"",'DPW2'!P22) | ¬¬IF(ISBLANK('DPW2'!Q22),"",'DPW2'!Q22) | ¬¬IF(ISBLANK('DPW2'!R22),"",'DPW2'!R22) | ¬¬IF(ISBLANK('DPW2'!S22),"",'DPW2'!S22) | ¬¬IF(ISBLANK('DPW2'!T22),"",'DPW2'!T22) | ¬¬IF(ISBLANK('DPW2'!U22),"",'DPW2'!U22) | ¬¬IF(ISBLANK('DPW2'!V22),"",'DPW2'!V22) | ¬¬IF(ISBLANK('DPW2'!W22),"",'DPW2'!W22)
¬¬A1198 | ¬¬IF(ISBLANK('DPW2'!BJ22),"",'DPW2'!BJ22) | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X22),"",'DPW2'!X22) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y22),"",'DPW2'!Y22)
¬¬A1199 | ¬¬IF(ISBLANK('DPW2'!BM22),"",'DPW2'!BM22) | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA22),"",'DPW2'!AA22) | ¬¬IF(ISBLANK('DPW2'!AB22),"",'DPW2'!AB22) | ¬¬IF(ISBLANK('DPW2'!AC22),"",'DPW2'!AC22) | ¬¬IF(ISBLANK('DPW2'!AD22),"",'DPW2'!AD22) | ¬¬IF(ISBLANK('DPW2'!AE22),"",'DPW2'!AE22) | ¬¬IF(ISBLANK('DPW2'!AF22),"",'DPW2'!AF22) | ¬¬IF(ISBLANK('DPW2'!AG22),"",'DPW2'!AG22) | ¬¬IF(ISBLANK('DPW2'!AH22),"",'DPW2'!AH22) | ¬¬IF(ISBLANK('DPW2'!AI22),"",'DPW2'!AI22) | ¬¬IF(ISBLANK('DPW2'!AJ22),"",'DPW2'!AJ22) | ¬¬IF(ISBLANK('DPW2'!AK22),"",'DPW2'!AK22) | ¬¬IF(ISBLANK('DPW2'!AL22),"",'DPW2'!AL22)
¬¬A1200 | ¬¬IF(ISBLANK('DPW2'!BY22),"",'DPW2'!BY22) | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM22),"",'DPW2'!AM22) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN22),"",'DPW2'!AN22)
¬¬A1201 | ¬¬IF(ISBLANK('DPW2'!CB22),"",'DPW2'!CB22) | ¬¬'DPW2'!F22 & "," & 'DPW2'!G22 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H22),"",'DPW2'!H22) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP22),"",'DPW2'!AP22) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ22),"",'DPW2'!AQ22)
¬¬A1202 | ¬¬IF(ISBLANK('DPW2'!AV23),"",'DPW2'!AV23) | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J23),"",'DPW2'!J23)
¬¬A1203 | ¬¬IF(ISBLANK('DPW2'!AX23),"",'DPW2'!AX23) | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L23),"",'DPW2'!L23) | ¬¬IF(ISBLANK('DPW2'!M23),"",'DPW2'!M23) | ¬¬IF(ISBLANK('DPW2'!N23),"",'DPW2'!N23) | ¬¬IF(ISBLANK('DPW2'!O23),"",'DPW2'!O23) | ¬¬IF(ISBLANK('DPW2'!P23),"",'DPW2'!P23) | ¬¬IF(ISBLANK('DPW2'!Q23),"",'DPW2'!Q23) | ¬¬IF(ISBLANK('DPW2'!R23),"",'DPW2'!R23) | ¬¬IF(ISBLANK('DPW2'!S23),"",'DPW2'!S23) | ¬¬IF(ISBLANK('DPW2'!T23),"",'DPW2'!T23) | ¬¬IF(ISBLANK('DPW2'!U23),"",'DPW2'!U23) | ¬¬IF(ISBLANK('DPW2'!V23),"",'DPW2'!V23) | ¬¬IF(ISBLANK('DPW2'!W23),"",'DPW2'!W23)
¬¬A1204 | ¬¬IF(ISBLANK('DPW2'!BJ23),"",'DPW2'!BJ23) | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X23),"",'DPW2'!X23) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y23),"",'DPW2'!Y23)
¬¬A1205 | ¬¬IF(ISBLANK('DPW2'!BM23),"",'DPW2'!BM23) | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA23),"",'DPW2'!AA23) | ¬¬IF(ISBLANK('DPW2'!AB23),"",'DPW2'!AB23) | ¬¬IF(ISBLANK('DPW2'!AC23),"",'DPW2'!AC23) | ¬¬IF(ISBLANK('DPW2'!AD23),"",'DPW2'!AD23) | ¬¬IF(ISBLANK('DPW2'!AE23),"",'DPW2'!AE23) | ¬¬IF(ISBLANK('DPW2'!AF23),"",'DPW2'!AF23) | ¬¬IF(ISBLANK('DPW2'!AG23),"",'DPW2'!AG23) | ¬¬IF(ISBLANK('DPW2'!AH23),"",'DPW2'!AH23) | ¬¬IF(ISBLANK('DPW2'!AI23),"",'DPW2'!AI23) | ¬¬IF(ISBLANK('DPW2'!AJ23),"",'DPW2'!AJ23) | ¬¬IF(ISBLANK('DPW2'!AK23),"",'DPW2'!AK23) | ¬¬IF(ISBLANK('DPW2'!AL23),"",'DPW2'!AL23)
¬¬A1206 | ¬¬IF(ISBLANK('DPW2'!BY23),"",'DPW2'!BY23) | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM23),"",'DPW2'!AM23) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN23),"",'DPW2'!AN23)
¬¬A1207 | ¬¬IF(ISBLANK('DPW2'!CB23),"",'DPW2'!CB23) | ¬¬'DPW2'!F23 & "," & 'DPW2'!G23 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H23),"",'DPW2'!H23) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP23),"",'DPW2'!AP23) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ23),"",'DPW2'!AQ23)
¬¬A1208 | ¬¬IF(ISBLANK('DPW2'!AV24),"",'DPW2'!AV24) | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J24),"",'DPW2'!J24)
¬¬A1209 | ¬¬IF(ISBLANK('DPW2'!AX24),"",'DPW2'!AX24) | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L24),"",'DPW2'!L24) | ¬¬IF(ISBLANK('DPW2'!M24),"",'DPW2'!M24) | ¬¬IF(ISBLANK('DPW2'!N24),"",'DPW2'!N24) | ¬¬IF(ISBLANK('DPW2'!O24),"",'DPW2'!O24) | ¬¬IF(ISBLANK('DPW2'!P24),"",'DPW2'!P24) | ¬¬IF(ISBLANK('DPW2'!Q24),"",'DPW2'!Q24) | ¬¬IF(ISBLANK('DPW2'!R24),"",'DPW2'!R24) | ¬¬IF(ISBLANK('DPW2'!S24),"",'DPW2'!S24) | ¬¬IF(ISBLANK('DPW2'!T24),"",'DPW2'!T24) | ¬¬IF(ISBLANK('DPW2'!U24),"",'DPW2'!U24) | ¬¬IF(ISBLANK('DPW2'!V24),"",'DPW2'!V24) | ¬¬IF(ISBLANK('DPW2'!W24),"",'DPW2'!W24)
¬¬A1210 | ¬¬IF(ISBLANK('DPW2'!BJ24),"",'DPW2'!BJ24) | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X24),"",'DPW2'!X24) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y24),"",'DPW2'!Y24)
¬¬A1211 | ¬¬IF(ISBLANK('DPW2'!BM24),"",'DPW2'!BM24) | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA24),"",'DPW2'!AA24) | ¬¬IF(ISBLANK('DPW2'!AB24),"",'DPW2'!AB24) | ¬¬IF(ISBLANK('DPW2'!AC24),"",'DPW2'!AC24) | ¬¬IF(ISBLANK('DPW2'!AD24),"",'DPW2'!AD24) | ¬¬IF(ISBLANK('DPW2'!AE24),"",'DPW2'!AE24) | ¬¬IF(ISBLANK('DPW2'!AF24),"",'DPW2'!AF24) | ¬¬IF(ISBLANK('DPW2'!AG24),"",'DPW2'!AG24) | ¬¬IF(ISBLANK('DPW2'!AH24),"",'DPW2'!AH24) | ¬¬IF(ISBLANK('DPW2'!AI24),"",'DPW2'!AI24) | ¬¬IF(ISBLANK('DPW2'!AJ24),"",'DPW2'!AJ24) | ¬¬IF(ISBLANK('DPW2'!AK24),"",'DPW2'!AK24) | ¬¬IF(ISBLANK('DPW2'!AL24),"",'DPW2'!AL24)
¬¬A1212 | ¬¬IF(ISBLANK('DPW2'!BY24),"",'DPW2'!BY24) | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM24),"",'DPW2'!AM24) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN24),"",'DPW2'!AN24)
¬¬A1213 | ¬¬IF(ISBLANK('DPW2'!CB24),"",'DPW2'!CB24) | ¬¬'DPW2'!F24 & "," & 'DPW2'!G24 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H24),"",'DPW2'!H24) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP24),"",'DPW2'!AP24) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ24),"",'DPW2'!AQ24)
¬¬A1214 | ¬¬IF(ISBLANK('DPW2'!AV25),"",'DPW2'!AV25) | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J25),"",'DPW2'!J25)
¬¬A1215 | ¬¬IF(ISBLANK('DPW2'!AX25),"",'DPW2'!AX25) | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L25),"",'DPW2'!L25) | ¬¬IF(ISBLANK('DPW2'!M25),"",'DPW2'!M25) | ¬¬IF(ISBLANK('DPW2'!N25),"",'DPW2'!N25) | ¬¬IF(ISBLANK('DPW2'!O25),"",'DPW2'!O25) | ¬¬IF(ISBLANK('DPW2'!P25),"",'DPW2'!P25) | ¬¬IF(ISBLANK('DPW2'!Q25),"",'DPW2'!Q25) | ¬¬IF(ISBLANK('DPW2'!R25),"",'DPW2'!R25) | ¬¬IF(ISBLANK('DPW2'!S25),"",'DPW2'!S25) | ¬¬IF(ISBLANK('DPW2'!T25),"",'DPW2'!T25) | ¬¬IF(ISBLANK('DPW2'!U25),"",'DPW2'!U25) | ¬¬IF(ISBLANK('DPW2'!V25),"",'DPW2'!V25) | ¬¬IF(ISBLANK('DPW2'!W25),"",'DPW2'!W25)
¬¬A1216 | ¬¬IF(ISBLANK('DPW2'!BJ25),"",'DPW2'!BJ25) | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X25),"",'DPW2'!X25) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y25),"",'DPW2'!Y25)
¬¬A1217 | ¬¬IF(ISBLANK('DPW2'!BM25),"",'DPW2'!BM25) | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA25),"",'DPW2'!AA25) | ¬¬IF(ISBLANK('DPW2'!AB25),"",'DPW2'!AB25) | ¬¬IF(ISBLANK('DPW2'!AC25),"",'DPW2'!AC25) | ¬¬IF(ISBLANK('DPW2'!AD25),"",'DPW2'!AD25) | ¬¬IF(ISBLANK('DPW2'!AE25),"",'DPW2'!AE25) | ¬¬IF(ISBLANK('DPW2'!AF25),"",'DPW2'!AF25) | ¬¬IF(ISBLANK('DPW2'!AG25),"",'DPW2'!AG25) | ¬¬IF(ISBLANK('DPW2'!AH25),"",'DPW2'!AH25) | ¬¬IF(ISBLANK('DPW2'!AI25),"",'DPW2'!AI25) | ¬¬IF(ISBLANK('DPW2'!AJ25),"",'DPW2'!AJ25) | ¬¬IF(ISBLANK('DPW2'!AK25),"",'DPW2'!AK25) | ¬¬IF(ISBLANK('DPW2'!AL25),"",'DPW2'!AL25)
¬¬A1218 | ¬¬IF(ISBLANK('DPW2'!BY25),"",'DPW2'!BY25) | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM25),"",'DPW2'!AM25) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN25),"",'DPW2'!AN25)
¬¬A1219 | ¬¬IF(ISBLANK('DPW2'!CB25),"",'DPW2'!CB25) | ¬¬'DPW2'!F25 & "," & 'DPW2'!G25 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H25),"",'DPW2'!H25) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP25),"",'DPW2'!AP25) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ25),"",'DPW2'!AQ25)
¬¬A1220 | ¬¬IF(ISBLANK('DPW2'!AV26),"",'DPW2'!AV26) | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J26),"",'DPW2'!J26)
¬¬A1221 | ¬¬IF(ISBLANK('DPW2'!AX26),"",'DPW2'!AX26) | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L26),"",'DPW2'!L26) | ¬¬IF(ISBLANK('DPW2'!M26),"",'DPW2'!M26) | ¬¬IF(ISBLANK('DPW2'!N26),"",'DPW2'!N26) | ¬¬IF(ISBLANK('DPW2'!O26),"",'DPW2'!O26) | ¬¬IF(ISBLANK('DPW2'!P26),"",'DPW2'!P26) | ¬¬IF(ISBLANK('DPW2'!Q26),"",'DPW2'!Q26) | ¬¬IF(ISBLANK('DPW2'!R26),"",'DPW2'!R26) | ¬¬IF(ISBLANK('DPW2'!S26),"",'DPW2'!S26) | ¬¬IF(ISBLANK('DPW2'!T26),"",'DPW2'!T26) | ¬¬IF(ISBLANK('DPW2'!U26),"",'DPW2'!U26) | ¬¬IF(ISBLANK('DPW2'!V26),"",'DPW2'!V26) | ¬¬IF(ISBLANK('DPW2'!W26),"",'DPW2'!W26)
¬¬A1222 | ¬¬IF(ISBLANK('DPW2'!BJ26),"",'DPW2'!BJ26) | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X26),"",'DPW2'!X26) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y26),"",'DPW2'!Y26)
¬¬A1223 | ¬¬IF(ISBLANK('DPW2'!BM26),"",'DPW2'!BM26) | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA26),"",'DPW2'!AA26) | ¬¬IF(ISBLANK('DPW2'!AB26),"",'DPW2'!AB26) | ¬¬IF(ISBLANK('DPW2'!AC26),"",'DPW2'!AC26) | ¬¬IF(ISBLANK('DPW2'!AD26),"",'DPW2'!AD26) | ¬¬IF(ISBLANK('DPW2'!AE26),"",'DPW2'!AE26) | ¬¬IF(ISBLANK('DPW2'!AF26),"",'DPW2'!AF26) | ¬¬IF(ISBLANK('DPW2'!AG26),"",'DPW2'!AG26) | ¬¬IF(ISBLANK('DPW2'!AH26),"",'DPW2'!AH26) | ¬¬IF(ISBLANK('DPW2'!AI26),"",'DPW2'!AI26) | ¬¬IF(ISBLANK('DPW2'!AJ26),"",'DPW2'!AJ26) | ¬¬IF(ISBLANK('DPW2'!AK26),"",'DPW2'!AK26) | ¬¬IF(ISBLANK('DPW2'!AL26),"",'DPW2'!AL26)
¬¬A1224 | ¬¬IF(ISBLANK('DPW2'!BY26),"",'DPW2'!BY26) | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM26),"",'DPW2'!AM26) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN26),"",'DPW2'!AN26)
¬¬A1225 | ¬¬IF(ISBLANK('DPW2'!CB26),"",'DPW2'!CB26) | ¬¬'DPW2'!F26 & "," & 'DPW2'!G26 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H26),"",'DPW2'!H26) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP26),"",'DPW2'!AP26) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ26),"",'DPW2'!AQ26)
¬¬A1226 | ¬¬IF(ISBLANK('DPW2'!AV27),"",'DPW2'!AV27) | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J27),"",'DPW2'!J27)
¬¬A1227 | ¬¬IF(ISBLANK('DPW2'!AX27),"",'DPW2'!AX27) | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L27),"",'DPW2'!L27) | ¬¬IF(ISBLANK('DPW2'!M27),"",'DPW2'!M27) | ¬¬IF(ISBLANK('DPW2'!N27),"",'DPW2'!N27) | ¬¬IF(ISBLANK('DPW2'!O27),"",'DPW2'!O27) | ¬¬IF(ISBLANK('DPW2'!P27),"",'DPW2'!P27) | ¬¬IF(ISBLANK('DPW2'!Q27),"",'DPW2'!Q27) | ¬¬IF(ISBLANK('DPW2'!R27),"",'DPW2'!R27) | ¬¬IF(ISBLANK('DPW2'!S27),"",'DPW2'!S27) | ¬¬IF(ISBLANK('DPW2'!T27),"",'DPW2'!T27) | ¬¬IF(ISBLANK('DPW2'!U27),"",'DPW2'!U27) | ¬¬IF(ISBLANK('DPW2'!V27),"",'DPW2'!V27) | ¬¬IF(ISBLANK('DPW2'!W27),"",'DPW2'!W27)
¬¬A1228 | ¬¬IF(ISBLANK('DPW2'!BJ27),"",'DPW2'!BJ27) | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X27),"",'DPW2'!X27) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y27),"",'DPW2'!Y27)
¬¬A1229 | ¬¬IF(ISBLANK('DPW2'!BM27),"",'DPW2'!BM27) | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA27),"",'DPW2'!AA27) | ¬¬IF(ISBLANK('DPW2'!AB27),"",'DPW2'!AB27) | ¬¬IF(ISBLANK('DPW2'!AC27),"",'DPW2'!AC27) | ¬¬IF(ISBLANK('DPW2'!AD27),"",'DPW2'!AD27) | ¬¬IF(ISBLANK('DPW2'!AE27),"",'DPW2'!AE27) | ¬¬IF(ISBLANK('DPW2'!AF27),"",'DPW2'!AF27) | ¬¬IF(ISBLANK('DPW2'!AG27),"",'DPW2'!AG27) | ¬¬IF(ISBLANK('DPW2'!AH27),"",'DPW2'!AH27) | ¬¬IF(ISBLANK('DPW2'!AI27),"",'DPW2'!AI27) | ¬¬IF(ISBLANK('DPW2'!AJ27),"",'DPW2'!AJ27) | ¬¬IF(ISBLANK('DPW2'!AK27),"",'DPW2'!AK27) | ¬¬IF(ISBLANK('DPW2'!AL27),"",'DPW2'!AL27)
¬¬A1230 | ¬¬IF(ISBLANK('DPW2'!BY27),"",'DPW2'!BY27) | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM27),"",'DPW2'!AM27) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN27),"",'DPW2'!AN27)
¬¬A1231 | ¬¬IF(ISBLANK('DPW2'!CB27),"",'DPW2'!CB27) | ¬¬'DPW2'!F27 & "," & 'DPW2'!G27 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H27),"",'DPW2'!H27) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP27),"",'DPW2'!AP27) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ27),"",'DPW2'!AQ27)
¬¬A1232 | ¬¬IF(ISBLANK('DPW2'!AV28),"",'DPW2'!AV28) | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J28),"",'DPW2'!J28)
¬¬A1233 | ¬¬IF(ISBLANK('DPW2'!AX28),"",'DPW2'!AX28) | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L28),"",'DPW2'!L28) | ¬¬IF(ISBLANK('DPW2'!M28),"",'DPW2'!M28) | ¬¬IF(ISBLANK('DPW2'!N28),"",'DPW2'!N28) | ¬¬IF(ISBLANK('DPW2'!O28),"",'DPW2'!O28) | ¬¬IF(ISBLANK('DPW2'!P28),"",'DPW2'!P28) | ¬¬IF(ISBLANK('DPW2'!Q28),"",'DPW2'!Q28) | ¬¬IF(ISBLANK('DPW2'!R28),"",'DPW2'!R28) | ¬¬IF(ISBLANK('DPW2'!S28),"",'DPW2'!S28) | ¬¬IF(ISBLANK('DPW2'!T28),"",'DPW2'!T28) | ¬¬IF(ISBLANK('DPW2'!U28),"",'DPW2'!U28) | ¬¬IF(ISBLANK('DPW2'!V28),"",'DPW2'!V28) | ¬¬IF(ISBLANK('DPW2'!W28),"",'DPW2'!W28)
¬¬A1234 | ¬¬IF(ISBLANK('DPW2'!BJ28),"",'DPW2'!BJ28) | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X28),"",'DPW2'!X28) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y28),"",'DPW2'!Y28)
¬¬A1235 | ¬¬IF(ISBLANK('DPW2'!BM28),"",'DPW2'!BM28) | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA28),"",'DPW2'!AA28) | ¬¬IF(ISBLANK('DPW2'!AB28),"",'DPW2'!AB28) | ¬¬IF(ISBLANK('DPW2'!AC28),"",'DPW2'!AC28) | ¬¬IF(ISBLANK('DPW2'!AD28),"",'DPW2'!AD28) | ¬¬IF(ISBLANK('DPW2'!AE28),"",'DPW2'!AE28) | ¬¬IF(ISBLANK('DPW2'!AF28),"",'DPW2'!AF28) | ¬¬IF(ISBLANK('DPW2'!AG28),"",'DPW2'!AG28) | ¬¬IF(ISBLANK('DPW2'!AH28),"",'DPW2'!AH28) | ¬¬IF(ISBLANK('DPW2'!AI28),"",'DPW2'!AI28) | ¬¬IF(ISBLANK('DPW2'!AJ28),"",'DPW2'!AJ28) | ¬¬IF(ISBLANK('DPW2'!AK28),"",'DPW2'!AK28) | ¬¬IF(ISBLANK('DPW2'!AL28),"",'DPW2'!AL28)
¬¬A1236 | ¬¬IF(ISBLANK('DPW2'!BY28),"",'DPW2'!BY28) | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM28),"",'DPW2'!AM28) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN28),"",'DPW2'!AN28)
¬¬A1237 | ¬¬IF(ISBLANK('DPW2'!CB28),"",'DPW2'!CB28) | ¬¬'DPW2'!F28 & "," & 'DPW2'!G28 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H28),"",'DPW2'!H28) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP28),"",'DPW2'!AP28) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ28),"",'DPW2'!AQ28)
¬¬A1238 | ¬¬IF(ISBLANK('DPW2'!AV29),"",'DPW2'!AV29) | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J29),"",'DPW2'!J29)
¬¬A1239 | ¬¬IF(ISBLANK('DPW2'!AX29),"",'DPW2'!AX29) | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L29),"",'DPW2'!L29) | ¬¬IF(ISBLANK('DPW2'!M29),"",'DPW2'!M29) | ¬¬IF(ISBLANK('DPW2'!N29),"",'DPW2'!N29) | ¬¬IF(ISBLANK('DPW2'!O29),"",'DPW2'!O29) | ¬¬IF(ISBLANK('DPW2'!P29),"",'DPW2'!P29) | ¬¬IF(ISBLANK('DPW2'!Q29),"",'DPW2'!Q29) | ¬¬IF(ISBLANK('DPW2'!R29),"",'DPW2'!R29) | ¬¬IF(ISBLANK('DPW2'!S29),"",'DPW2'!S29) | ¬¬IF(ISBLANK('DPW2'!T29),"",'DPW2'!T29) | ¬¬IF(ISBLANK('DPW2'!U29),"",'DPW2'!U29) | ¬¬IF(ISBLANK('DPW2'!V29),"",'DPW2'!V29) | ¬¬IF(ISBLANK('DPW2'!W29),"",'DPW2'!W29)
¬¬A1240 | ¬¬IF(ISBLANK('DPW2'!BJ29),"",'DPW2'!BJ29) | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X29),"",'DPW2'!X29) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y29),"",'DPW2'!Y29)
¬¬A1241 | ¬¬IF(ISBLANK('DPW2'!BM29),"",'DPW2'!BM29) | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA29),"",'DPW2'!AA29) | ¬¬IF(ISBLANK('DPW2'!AB29),"",'DPW2'!AB29) | ¬¬IF(ISBLANK('DPW2'!AC29),"",'DPW2'!AC29) | ¬¬IF(ISBLANK('DPW2'!AD29),"",'DPW2'!AD29) | ¬¬IF(ISBLANK('DPW2'!AE29),"",'DPW2'!AE29) | ¬¬IF(ISBLANK('DPW2'!AF29),"",'DPW2'!AF29) | ¬¬IF(ISBLANK('DPW2'!AG29),"",'DPW2'!AG29) | ¬¬IF(ISBLANK('DPW2'!AH29),"",'DPW2'!AH29) | ¬¬IF(ISBLANK('DPW2'!AI29),"",'DPW2'!AI29) | ¬¬IF(ISBLANK('DPW2'!AJ29),"",'DPW2'!AJ29) | ¬¬IF(ISBLANK('DPW2'!AK29),"",'DPW2'!AK29) | ¬¬IF(ISBLANK('DPW2'!AL29),"",'DPW2'!AL29)
¬¬A1242 | ¬¬IF(ISBLANK('DPW2'!BY29),"",'DPW2'!BY29) | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM29),"",'DPW2'!AM29) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN29),"",'DPW2'!AN29)
¬¬A1243 | ¬¬IF(ISBLANK('DPW2'!CB29),"",'DPW2'!CB29) | ¬¬'DPW2'!F29 & "," & 'DPW2'!G29 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H29),"",'DPW2'!H29) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP29),"",'DPW2'!AP29) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ29),"",'DPW2'!AQ29)
¬¬A1244 | ¬¬IF(ISBLANK('DPW2'!AV30),"",'DPW2'!AV30) | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J30),"",'DPW2'!J30)
¬¬A1245 | ¬¬IF(ISBLANK('DPW2'!AX30),"",'DPW2'!AX30) | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L30),"",'DPW2'!L30) | ¬¬IF(ISBLANK('DPW2'!M30),"",'DPW2'!M30) | ¬¬IF(ISBLANK('DPW2'!N30),"",'DPW2'!N30) | ¬¬IF(ISBLANK('DPW2'!O30),"",'DPW2'!O30) | ¬¬IF(ISBLANK('DPW2'!P30),"",'DPW2'!P30) | ¬¬IF(ISBLANK('DPW2'!Q30),"",'DPW2'!Q30) | ¬¬IF(ISBLANK('DPW2'!R30),"",'DPW2'!R30) | ¬¬IF(ISBLANK('DPW2'!S30),"",'DPW2'!S30) | ¬¬IF(ISBLANK('DPW2'!T30),"",'DPW2'!T30) | ¬¬IF(ISBLANK('DPW2'!U30),"",'DPW2'!U30) | ¬¬IF(ISBLANK('DPW2'!V30),"",'DPW2'!V30) | ¬¬IF(ISBLANK('DPW2'!W30),"",'DPW2'!W30)
¬¬A1246 | ¬¬IF(ISBLANK('DPW2'!BJ30),"",'DPW2'!BJ30) | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X30),"",'DPW2'!X30) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y30),"",'DPW2'!Y30)
¬¬A1247 | ¬¬IF(ISBLANK('DPW2'!BM30),"",'DPW2'!BM30) | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA30),"",'DPW2'!AA30) | ¬¬IF(ISBLANK('DPW2'!AB30),"",'DPW2'!AB30) | ¬¬IF(ISBLANK('DPW2'!AC30),"",'DPW2'!AC30) | ¬¬IF(ISBLANK('DPW2'!AD30),"",'DPW2'!AD30) | ¬¬IF(ISBLANK('DPW2'!AE30),"",'DPW2'!AE30) | ¬¬IF(ISBLANK('DPW2'!AF30),"",'DPW2'!AF30) | ¬¬IF(ISBLANK('DPW2'!AG30),"",'DPW2'!AG30) | ¬¬IF(ISBLANK('DPW2'!AH30),"",'DPW2'!AH30) | ¬¬IF(ISBLANK('DPW2'!AI30),"",'DPW2'!AI30) | ¬¬IF(ISBLANK('DPW2'!AJ30),"",'DPW2'!AJ30) | ¬¬IF(ISBLANK('DPW2'!AK30),"",'DPW2'!AK30) | ¬¬IF(ISBLANK('DPW2'!AL30),"",'DPW2'!AL30)
¬¬A1248 | ¬¬IF(ISBLANK('DPW2'!BY30),"",'DPW2'!BY30) | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM30),"",'DPW2'!AM30) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN30),"",'DPW2'!AN30)
¬¬A1249 | ¬¬IF(ISBLANK('DPW2'!CB30),"",'DPW2'!CB30) | ¬¬'DPW2'!F30 & "," & 'DPW2'!G30 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H30),"",'DPW2'!H30) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP30),"",'DPW2'!AP30) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ30),"",'DPW2'!AQ30)
¬¬A1250 | ¬¬IF(ISBLANK('DPW2'!AV31),"",'DPW2'!AV31) | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J31),"",'DPW2'!J31)
¬¬A1251 | ¬¬IF(ISBLANK('DPW2'!AX31),"",'DPW2'!AX31) | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L31),"",'DPW2'!L31) | ¬¬IF(ISBLANK('DPW2'!M31),"",'DPW2'!M31) | ¬¬IF(ISBLANK('DPW2'!N31),"",'DPW2'!N31) | ¬¬IF(ISBLANK('DPW2'!O31),"",'DPW2'!O31) | ¬¬IF(ISBLANK('DPW2'!P31),"",'DPW2'!P31) | ¬¬IF(ISBLANK('DPW2'!Q31),"",'DPW2'!Q31) | ¬¬IF(ISBLANK('DPW2'!R31),"",'DPW2'!R31) | ¬¬IF(ISBLANK('DPW2'!S31),"",'DPW2'!S31) | ¬¬IF(ISBLANK('DPW2'!T31),"",'DPW2'!T31) | ¬¬IF(ISBLANK('DPW2'!U31),"",'DPW2'!U31) | ¬¬IF(ISBLANK('DPW2'!V31),"",'DPW2'!V31) | ¬¬IF(ISBLANK('DPW2'!W31),"",'DPW2'!W31)
¬¬A1252 | ¬¬IF(ISBLANK('DPW2'!BJ31),"",'DPW2'!BJ31) | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X31),"",'DPW2'!X31) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y31),"",'DPW2'!Y31)
¬¬A1253 | ¬¬IF(ISBLANK('DPW2'!BM31),"",'DPW2'!BM31) | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA31),"",'DPW2'!AA31) | ¬¬IF(ISBLANK('DPW2'!AB31),"",'DPW2'!AB31) | ¬¬IF(ISBLANK('DPW2'!AC31),"",'DPW2'!AC31) | ¬¬IF(ISBLANK('DPW2'!AD31),"",'DPW2'!AD31) | ¬¬IF(ISBLANK('DPW2'!AE31),"",'DPW2'!AE31) | ¬¬IF(ISBLANK('DPW2'!AF31),"",'DPW2'!AF31) | ¬¬IF(ISBLANK('DPW2'!AG31),"",'DPW2'!AG31) | ¬¬IF(ISBLANK('DPW2'!AH31),"",'DPW2'!AH31) | ¬¬IF(ISBLANK('DPW2'!AI31),"",'DPW2'!AI31) | ¬¬IF(ISBLANK('DPW2'!AJ31),"",'DPW2'!AJ31) | ¬¬IF(ISBLANK('DPW2'!AK31),"",'DPW2'!AK31) | ¬¬IF(ISBLANK('DPW2'!AL31),"",'DPW2'!AL31)
¬¬A1254 | ¬¬IF(ISBLANK('DPW2'!BY31),"",'DPW2'!BY31) | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM31),"",'DPW2'!AM31) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN31),"",'DPW2'!AN31)
¬¬A1255 | ¬¬IF(ISBLANK('DPW2'!CB31),"",'DPW2'!CB31) | ¬¬'DPW2'!F31 & "," & 'DPW2'!G31 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H31),"",'DPW2'!H31) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP31),"",'DPW2'!AP31) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ31),"",'DPW2'!AQ31)
¬¬A1256 | ¬¬IF(ISBLANK('DPW2'!AV32),"",'DPW2'!AV32) | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J32),"",'DPW2'!J32)
¬¬A1257 | ¬¬IF(ISBLANK('DPW2'!AX32),"",'DPW2'!AX32) | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L32),"",'DPW2'!L32) | ¬¬IF(ISBLANK('DPW2'!M32),"",'DPW2'!M32) | ¬¬IF(ISBLANK('DPW2'!N32),"",'DPW2'!N32) | ¬¬IF(ISBLANK('DPW2'!O32),"",'DPW2'!O32) | ¬¬IF(ISBLANK('DPW2'!P32),"",'DPW2'!P32) | ¬¬IF(ISBLANK('DPW2'!Q32),"",'DPW2'!Q32) | ¬¬IF(ISBLANK('DPW2'!R32),"",'DPW2'!R32) | ¬¬IF(ISBLANK('DPW2'!S32),"",'DPW2'!S32) | ¬¬IF(ISBLANK('DPW2'!T32),"",'DPW2'!T32) | ¬¬IF(ISBLANK('DPW2'!U32),"",'DPW2'!U32) | ¬¬IF(ISBLANK('DPW2'!V32),"",'DPW2'!V32) | ¬¬IF(ISBLANK('DPW2'!W32),"",'DPW2'!W32)
¬¬A1258 | ¬¬IF(ISBLANK('DPW2'!BJ32),"",'DPW2'!BJ32) | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X32),"",'DPW2'!X32) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y32),"",'DPW2'!Y32)
¬¬A1259 | ¬¬IF(ISBLANK('DPW2'!BM32),"",'DPW2'!BM32) | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA32),"",'DPW2'!AA32) | ¬¬IF(ISBLANK('DPW2'!AB32),"",'DPW2'!AB32) | ¬¬IF(ISBLANK('DPW2'!AC32),"",'DPW2'!AC32) | ¬¬IF(ISBLANK('DPW2'!AD32),"",'DPW2'!AD32) | ¬¬IF(ISBLANK('DPW2'!AE32),"",'DPW2'!AE32) | ¬¬IF(ISBLANK('DPW2'!AF32),"",'DPW2'!AF32) | ¬¬IF(ISBLANK('DPW2'!AG32),"",'DPW2'!AG32) | ¬¬IF(ISBLANK('DPW2'!AH32),"",'DPW2'!AH32) | ¬¬IF(ISBLANK('DPW2'!AI32),"",'DPW2'!AI32) | ¬¬IF(ISBLANK('DPW2'!AJ32),"",'DPW2'!AJ32) | ¬¬IF(ISBLANK('DPW2'!AK32),"",'DPW2'!AK32) | ¬¬IF(ISBLANK('DPW2'!AL32),"",'DPW2'!AL32)
¬¬A1260 | ¬¬IF(ISBLANK('DPW2'!BY32),"",'DPW2'!BY32) | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM32),"",'DPW2'!AM32) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN32),"",'DPW2'!AN32)
¬¬A1261 | ¬¬IF(ISBLANK('DPW2'!CB32),"",'DPW2'!CB32) | ¬¬'DPW2'!F32 & "," & 'DPW2'!G32 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H32),"",'DPW2'!H32) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP32),"",'DPW2'!AP32) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ32),"",'DPW2'!AQ32)
¬¬A1262 | ¬¬IF(ISBLANK('DPW2'!AV33),"",'DPW2'!AV33) | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J33),"",'DPW2'!J33)
¬¬A1263 | ¬¬IF(ISBLANK('DPW2'!AX33),"",'DPW2'!AX33) | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L33),"",'DPW2'!L33) | ¬¬IF(ISBLANK('DPW2'!M33),"",'DPW2'!M33) | ¬¬IF(ISBLANK('DPW2'!N33),"",'DPW2'!N33) | ¬¬IF(ISBLANK('DPW2'!O33),"",'DPW2'!O33) | ¬¬IF(ISBLANK('DPW2'!P33),"",'DPW2'!P33) | ¬¬IF(ISBLANK('DPW2'!Q33),"",'DPW2'!Q33) | ¬¬IF(ISBLANK('DPW2'!R33),"",'DPW2'!R33) | ¬¬IF(ISBLANK('DPW2'!S33),"",'DPW2'!S33) | ¬¬IF(ISBLANK('DPW2'!T33),"",'DPW2'!T33) | ¬¬IF(ISBLANK('DPW2'!U33),"",'DPW2'!U33) | ¬¬IF(ISBLANK('DPW2'!V33),"",'DPW2'!V33) | ¬¬IF(ISBLANK('DPW2'!W33),"",'DPW2'!W33)
¬¬A1264 | ¬¬IF(ISBLANK('DPW2'!BJ33),"",'DPW2'!BJ33) | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X33),"",'DPW2'!X33) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y33),"",'DPW2'!Y33)
¬¬A1265 | ¬¬IF(ISBLANK('DPW2'!BM33),"",'DPW2'!BM33) | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA33),"",'DPW2'!AA33) | ¬¬IF(ISBLANK('DPW2'!AB33),"",'DPW2'!AB33) | ¬¬IF(ISBLANK('DPW2'!AC33),"",'DPW2'!AC33) | ¬¬IF(ISBLANK('DPW2'!AD33),"",'DPW2'!AD33) | ¬¬IF(ISBLANK('DPW2'!AE33),"",'DPW2'!AE33) | ¬¬IF(ISBLANK('DPW2'!AF33),"",'DPW2'!AF33) | ¬¬IF(ISBLANK('DPW2'!AG33),"",'DPW2'!AG33) | ¬¬IF(ISBLANK('DPW2'!AH33),"",'DPW2'!AH33) | ¬¬IF(ISBLANK('DPW2'!AI33),"",'DPW2'!AI33) | ¬¬IF(ISBLANK('DPW2'!AJ33),"",'DPW2'!AJ33) | ¬¬IF(ISBLANK('DPW2'!AK33),"",'DPW2'!AK33) | ¬¬IF(ISBLANK('DPW2'!AL33),"",'DPW2'!AL33)
¬¬A1266 | ¬¬IF(ISBLANK('DPW2'!BY33),"",'DPW2'!BY33) | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM33),"",'DPW2'!AM33) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN33),"",'DPW2'!AN33)
¬¬A1267 | ¬¬IF(ISBLANK('DPW2'!CB33),"",'DPW2'!CB33) | ¬¬'DPW2'!F33 & "," & 'DPW2'!G33 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H33),"",'DPW2'!H33) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP33),"",'DPW2'!AP33) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ33),"",'DPW2'!AQ33)
¬¬A1268 | ¬¬IF(ISBLANK('DPW2'!AV34),"",'DPW2'!AV34) | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J34),"",'DPW2'!J34)
¬¬A1269 | ¬¬IF(ISBLANK('DPW2'!AX34),"",'DPW2'!AX34) | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L34),"",'DPW2'!L34) | ¬¬IF(ISBLANK('DPW2'!M34),"",'DPW2'!M34) | ¬¬IF(ISBLANK('DPW2'!N34),"",'DPW2'!N34) | ¬¬IF(ISBLANK('DPW2'!O34),"",'DPW2'!O34) | ¬¬IF(ISBLANK('DPW2'!P34),"",'DPW2'!P34) | ¬¬IF(ISBLANK('DPW2'!Q34),"",'DPW2'!Q34) | ¬¬IF(ISBLANK('DPW2'!R34),"",'DPW2'!R34) | ¬¬IF(ISBLANK('DPW2'!S34),"",'DPW2'!S34) | ¬¬IF(ISBLANK('DPW2'!T34),"",'DPW2'!T34) | ¬¬IF(ISBLANK('DPW2'!U34),"",'DPW2'!U34) | ¬¬IF(ISBLANK('DPW2'!V34),"",'DPW2'!V34) | ¬¬IF(ISBLANK('DPW2'!W34),"",'DPW2'!W34)
¬¬A1270 | ¬¬IF(ISBLANK('DPW2'!BJ34),"",'DPW2'!BJ34) | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X34),"",'DPW2'!X34) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y34),"",'DPW2'!Y34)
¬¬A1271 | ¬¬IF(ISBLANK('DPW2'!BM34),"",'DPW2'!BM34) | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA34),"",'DPW2'!AA34) | ¬¬IF(ISBLANK('DPW2'!AB34),"",'DPW2'!AB34) | ¬¬IF(ISBLANK('DPW2'!AC34),"",'DPW2'!AC34) | ¬¬IF(ISBLANK('DPW2'!AD34),"",'DPW2'!AD34) | ¬¬IF(ISBLANK('DPW2'!AE34),"",'DPW2'!AE34) | ¬¬IF(ISBLANK('DPW2'!AF34),"",'DPW2'!AF34) | ¬¬IF(ISBLANK('DPW2'!AG34),"",'DPW2'!AG34) | ¬¬IF(ISBLANK('DPW2'!AH34),"",'DPW2'!AH34) | ¬¬IF(ISBLANK('DPW2'!AI34),"",'DPW2'!AI34) | ¬¬IF(ISBLANK('DPW2'!AJ34),"",'DPW2'!AJ34) | ¬¬IF(ISBLANK('DPW2'!AK34),"",'DPW2'!AK34) | ¬¬IF(ISBLANK('DPW2'!AL34),"",'DPW2'!AL34)
¬¬A1272 | ¬¬IF(ISBLANK('DPW2'!BY34),"",'DPW2'!BY34) | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM34),"",'DPW2'!AM34) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN34),"",'DPW2'!AN34)
¬¬A1273 | ¬¬IF(ISBLANK('DPW2'!CB34),"",'DPW2'!CB34) | ¬¬'DPW2'!F34 & "," & 'DPW2'!G34 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H34),"",'DPW2'!H34) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP34),"",'DPW2'!AP34) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ34),"",'DPW2'!AQ34)
¬¬A1274 | ¬¬IF(ISBLANK('DPW2'!AV35),"",'DPW2'!AV35) | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J35),"",'DPW2'!J35)
¬¬A1275 | ¬¬IF(ISBLANK('DPW2'!AX35),"",'DPW2'!AX35) | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L35),"",'DPW2'!L35) | ¬¬IF(ISBLANK('DPW2'!M35),"",'DPW2'!M35) | ¬¬IF(ISBLANK('DPW2'!N35),"",'DPW2'!N35) | ¬¬IF(ISBLANK('DPW2'!O35),"",'DPW2'!O35) | ¬¬IF(ISBLANK('DPW2'!P35),"",'DPW2'!P35) | ¬¬IF(ISBLANK('DPW2'!Q35),"",'DPW2'!Q35) | ¬¬IF(ISBLANK('DPW2'!R35),"",'DPW2'!R35) | ¬¬IF(ISBLANK('DPW2'!S35),"",'DPW2'!S35) | ¬¬IF(ISBLANK('DPW2'!T35),"",'DPW2'!T35) | ¬¬IF(ISBLANK('DPW2'!U35),"",'DPW2'!U35) | ¬¬IF(ISBLANK('DPW2'!V35),"",'DPW2'!V35) | ¬¬IF(ISBLANK('DPW2'!W35),"",'DPW2'!W35)
¬¬A1276 | ¬¬IF(ISBLANK('DPW2'!BJ35),"",'DPW2'!BJ35) | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X35),"",'DPW2'!X35) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y35),"",'DPW2'!Y35)
¬¬A1277 | ¬¬IF(ISBLANK('DPW2'!BM35),"",'DPW2'!BM35) | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA35),"",'DPW2'!AA35) | ¬¬IF(ISBLANK('DPW2'!AB35),"",'DPW2'!AB35) | ¬¬IF(ISBLANK('DPW2'!AC35),"",'DPW2'!AC35) | ¬¬IF(ISBLANK('DPW2'!AD35),"",'DPW2'!AD35) | ¬¬IF(ISBLANK('DPW2'!AE35),"",'DPW2'!AE35) | ¬¬IF(ISBLANK('DPW2'!AF35),"",'DPW2'!AF35) | ¬¬IF(ISBLANK('DPW2'!AG35),"",'DPW2'!AG35) | ¬¬IF(ISBLANK('DPW2'!AH35),"",'DPW2'!AH35) | ¬¬IF(ISBLANK('DPW2'!AI35),"",'DPW2'!AI35) | ¬¬IF(ISBLANK('DPW2'!AJ35),"",'DPW2'!AJ35) | ¬¬IF(ISBLANK('DPW2'!AK35),"",'DPW2'!AK35) | ¬¬IF(ISBLANK('DPW2'!AL35),"",'DPW2'!AL35)
¬¬A1278 | ¬¬IF(ISBLANK('DPW2'!BY35),"",'DPW2'!BY35) | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM35),"",'DPW2'!AM35) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN35),"",'DPW2'!AN35)
¬¬A1279 | ¬¬IF(ISBLANK('DPW2'!CB35),"",'DPW2'!CB35) | ¬¬'DPW2'!F35 & "," & 'DPW2'!G35 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H35),"",'DPW2'!H35) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP35),"",'DPW2'!AP35) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ35),"",'DPW2'!AQ35)
¬¬A1280 | ¬¬IF(ISBLANK('DPW2'!AV36),"",'DPW2'!AV36) | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J36),"",'DPW2'!J36)
¬¬A1281 | ¬¬IF(ISBLANK('DPW2'!AX36),"",'DPW2'!AX36) | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L36),"",'DPW2'!L36) | ¬¬IF(ISBLANK('DPW2'!M36),"",'DPW2'!M36) | ¬¬IF(ISBLANK('DPW2'!N36),"",'DPW2'!N36) | ¬¬IF(ISBLANK('DPW2'!O36),"",'DPW2'!O36) | ¬¬IF(ISBLANK('DPW2'!P36),"",'DPW2'!P36) | ¬¬IF(ISBLANK('DPW2'!Q36),"",'DPW2'!Q36) | ¬¬IF(ISBLANK('DPW2'!R36),"",'DPW2'!R36) | ¬¬IF(ISBLANK('DPW2'!S36),"",'DPW2'!S36) | ¬¬IF(ISBLANK('DPW2'!T36),"",'DPW2'!T36) | ¬¬IF(ISBLANK('DPW2'!U36),"",'DPW2'!U36) | ¬¬IF(ISBLANK('DPW2'!V36),"",'DPW2'!V36) | ¬¬IF(ISBLANK('DPW2'!W36),"",'DPW2'!W36)
¬¬A1282 | ¬¬IF(ISBLANK('DPW2'!BJ36),"",'DPW2'!BJ36) | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X36),"",'DPW2'!X36) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y36),"",'DPW2'!Y36)
¬¬A1283 | ¬¬IF(ISBLANK('DPW2'!BM36),"",'DPW2'!BM36) | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA36),"",'DPW2'!AA36) | ¬¬IF(ISBLANK('DPW2'!AB36),"",'DPW2'!AB36) | ¬¬IF(ISBLANK('DPW2'!AC36),"",'DPW2'!AC36) | ¬¬IF(ISBLANK('DPW2'!AD36),"",'DPW2'!AD36) | ¬¬IF(ISBLANK('DPW2'!AE36),"",'DPW2'!AE36) | ¬¬IF(ISBLANK('DPW2'!AF36),"",'DPW2'!AF36) | ¬¬IF(ISBLANK('DPW2'!AG36),"",'DPW2'!AG36) | ¬¬IF(ISBLANK('DPW2'!AH36),"",'DPW2'!AH36) | ¬¬IF(ISBLANK('DPW2'!AI36),"",'DPW2'!AI36) | ¬¬IF(ISBLANK('DPW2'!AJ36),"",'DPW2'!AJ36) | ¬¬IF(ISBLANK('DPW2'!AK36),"",'DPW2'!AK36) | ¬¬IF(ISBLANK('DPW2'!AL36),"",'DPW2'!AL36)
¬¬A1284 | ¬¬IF(ISBLANK('DPW2'!BY36),"",'DPW2'!BY36) | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM36),"",'DPW2'!AM36) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN36),"",'DPW2'!AN36)
¬¬A1285 | ¬¬IF(ISBLANK('DPW2'!CB36),"",'DPW2'!CB36) | ¬¬'DPW2'!F36 & "," & 'DPW2'!G36 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H36),"",'DPW2'!H36) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP36),"",'DPW2'!AP36) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ36),"",'DPW2'!AQ36)
¬¬A1286 | ¬¬IF(ISBLANK('DPW2'!AV37),"",'DPW2'!AV37) | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J37),"",'DPW2'!J37)
¬¬A1287 | ¬¬IF(ISBLANK('DPW2'!AX37),"",'DPW2'!AX37) | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L37),"",'DPW2'!L37) | ¬¬IF(ISBLANK('DPW2'!M37),"",'DPW2'!M37) | ¬¬IF(ISBLANK('DPW2'!N37),"",'DPW2'!N37) | ¬¬IF(ISBLANK('DPW2'!O37),"",'DPW2'!O37) | ¬¬IF(ISBLANK('DPW2'!P37),"",'DPW2'!P37) | ¬¬IF(ISBLANK('DPW2'!Q37),"",'DPW2'!Q37) | ¬¬IF(ISBLANK('DPW2'!R37),"",'DPW2'!R37) | ¬¬IF(ISBLANK('DPW2'!S37),"",'DPW2'!S37) | ¬¬IF(ISBLANK('DPW2'!T37),"",'DPW2'!T37) | ¬¬IF(ISBLANK('DPW2'!U37),"",'DPW2'!U37) | ¬¬IF(ISBLANK('DPW2'!V37),"",'DPW2'!V37) | ¬¬IF(ISBLANK('DPW2'!W37),"",'DPW2'!W37)
¬¬A1288 | ¬¬IF(ISBLANK('DPW2'!BJ37),"",'DPW2'!BJ37) | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X37),"",'DPW2'!X37) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y37),"",'DPW2'!Y37)
¬¬A1289 | ¬¬IF(ISBLANK('DPW2'!BM37),"",'DPW2'!BM37) | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA37),"",'DPW2'!AA37) | ¬¬IF(ISBLANK('DPW2'!AB37),"",'DPW2'!AB37) | ¬¬IF(ISBLANK('DPW2'!AC37),"",'DPW2'!AC37) | ¬¬IF(ISBLANK('DPW2'!AD37),"",'DPW2'!AD37) | ¬¬IF(ISBLANK('DPW2'!AE37),"",'DPW2'!AE37) | ¬¬IF(ISBLANK('DPW2'!AF37),"",'DPW2'!AF37) | ¬¬IF(ISBLANK('DPW2'!AG37),"",'DPW2'!AG37) | ¬¬IF(ISBLANK('DPW2'!AH37),"",'DPW2'!AH37) | ¬¬IF(ISBLANK('DPW2'!AI37),"",'DPW2'!AI37) | ¬¬IF(ISBLANK('DPW2'!AJ37),"",'DPW2'!AJ37) | ¬¬IF(ISBLANK('DPW2'!AK37),"",'DPW2'!AK37) | ¬¬IF(ISBLANK('DPW2'!AL37),"",'DPW2'!AL37)
¬¬A1290 | ¬¬IF(ISBLANK('DPW2'!BY37),"",'DPW2'!BY37) | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM37),"",'DPW2'!AM37) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN37),"",'DPW2'!AN37)
¬¬A1291 | ¬¬IF(ISBLANK('DPW2'!CB37),"",'DPW2'!CB37) | ¬¬'DPW2'!F37 & "," & 'DPW2'!G37 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H37),"",'DPW2'!H37) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP37),"",'DPW2'!AP37) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ37),"",'DPW2'!AQ37)
¬¬A1292 | ¬¬IF(ISBLANK('DPW2'!AV38),"",'DPW2'!AV38) | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J38),"",'DPW2'!J38)
¬¬A1293 | ¬¬IF(ISBLANK('DPW2'!AX38),"",'DPW2'!AX38) | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L38),"",'DPW2'!L38) | ¬¬IF(ISBLANK('DPW2'!M38),"",'DPW2'!M38) | ¬¬IF(ISBLANK('DPW2'!N38),"",'DPW2'!N38) | ¬¬IF(ISBLANK('DPW2'!O38),"",'DPW2'!O38) | ¬¬IF(ISBLANK('DPW2'!P38),"",'DPW2'!P38) | ¬¬IF(ISBLANK('DPW2'!Q38),"",'DPW2'!Q38) | ¬¬IF(ISBLANK('DPW2'!R38),"",'DPW2'!R38) | ¬¬IF(ISBLANK('DPW2'!S38),"",'DPW2'!S38) | ¬¬IF(ISBLANK('DPW2'!T38),"",'DPW2'!T38) | ¬¬IF(ISBLANK('DPW2'!U38),"",'DPW2'!U38) | ¬¬IF(ISBLANK('DPW2'!V38),"",'DPW2'!V38) | ¬¬IF(ISBLANK('DPW2'!W38),"",'DPW2'!W38)
¬¬A1294 | ¬¬IF(ISBLANK('DPW2'!BJ38),"",'DPW2'!BJ38) | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X38),"",'DPW2'!X38) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y38),"",'DPW2'!Y38)
¬¬A1295 | ¬¬IF(ISBLANK('DPW2'!BM38),"",'DPW2'!BM38) | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA38),"",'DPW2'!AA38) | ¬¬IF(ISBLANK('DPW2'!AB38),"",'DPW2'!AB38) | ¬¬IF(ISBLANK('DPW2'!AC38),"",'DPW2'!AC38) | ¬¬IF(ISBLANK('DPW2'!AD38),"",'DPW2'!AD38) | ¬¬IF(ISBLANK('DPW2'!AE38),"",'DPW2'!AE38) | ¬¬IF(ISBLANK('DPW2'!AF38),"",'DPW2'!AF38) | ¬¬IF(ISBLANK('DPW2'!AG38),"",'DPW2'!AG38) | ¬¬IF(ISBLANK('DPW2'!AH38),"",'DPW2'!AH38) | ¬¬IF(ISBLANK('DPW2'!AI38),"",'DPW2'!AI38) | ¬¬IF(ISBLANK('DPW2'!AJ38),"",'DPW2'!AJ38) | ¬¬IF(ISBLANK('DPW2'!AK38),"",'DPW2'!AK38) | ¬¬IF(ISBLANK('DPW2'!AL38),"",'DPW2'!AL38)
¬¬A1296 | ¬¬IF(ISBLANK('DPW2'!BY38),"",'DPW2'!BY38) | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM38),"",'DPW2'!AM38) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN38),"",'DPW2'!AN38)
¬¬A1297 | ¬¬IF(ISBLANK('DPW2'!CB38),"",'DPW2'!CB38) | ¬¬'DPW2'!F38 & "," & 'DPW2'!G38 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H38),"",'DPW2'!H38) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP38),"",'DPW2'!AP38) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ38),"",'DPW2'!AQ38)
¬¬A1298 | ¬¬IF(ISBLANK('DPW2'!AV39),"",'DPW2'!AV39) | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J39),"",'DPW2'!J39)
¬¬A1299 | ¬¬IF(ISBLANK('DPW2'!AX39),"",'DPW2'!AX39) | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L39),"",'DPW2'!L39) | ¬¬IF(ISBLANK('DPW2'!M39),"",'DPW2'!M39) | ¬¬IF(ISBLANK('DPW2'!N39),"",'DPW2'!N39) | ¬¬IF(ISBLANK('DPW2'!O39),"",'DPW2'!O39) | ¬¬IF(ISBLANK('DPW2'!P39),"",'DPW2'!P39) | ¬¬IF(ISBLANK('DPW2'!Q39),"",'DPW2'!Q39) | ¬¬IF(ISBLANK('DPW2'!R39),"",'DPW2'!R39) | ¬¬IF(ISBLANK('DPW2'!S39),"",'DPW2'!S39) | ¬¬IF(ISBLANK('DPW2'!T39),"",'DPW2'!T39) | ¬¬IF(ISBLANK('DPW2'!U39),"",'DPW2'!U39) | ¬¬IF(ISBLANK('DPW2'!V39),"",'DPW2'!V39) | ¬¬IF(ISBLANK('DPW2'!W39),"",'DPW2'!W39)
¬¬A1300 | ¬¬IF(ISBLANK('DPW2'!BJ39),"",'DPW2'!BJ39) | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X39),"",'DPW2'!X39) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y39),"",'DPW2'!Y39)
¬¬A1301 | ¬¬IF(ISBLANK('DPW2'!BM39),"",'DPW2'!BM39) | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA39),"",'DPW2'!AA39) | ¬¬IF(ISBLANK('DPW2'!AB39),"",'DPW2'!AB39) | ¬¬IF(ISBLANK('DPW2'!AC39),"",'DPW2'!AC39) | ¬¬IF(ISBLANK('DPW2'!AD39),"",'DPW2'!AD39) | ¬¬IF(ISBLANK('DPW2'!AE39),"",'DPW2'!AE39) | ¬¬IF(ISBLANK('DPW2'!AF39),"",'DPW2'!AF39) | ¬¬IF(ISBLANK('DPW2'!AG39),"",'DPW2'!AG39) | ¬¬IF(ISBLANK('DPW2'!AH39),"",'DPW2'!AH39) | ¬¬IF(ISBLANK('DPW2'!AI39),"",'DPW2'!AI39) | ¬¬IF(ISBLANK('DPW2'!AJ39),"",'DPW2'!AJ39) | ¬¬IF(ISBLANK('DPW2'!AK39),"",'DPW2'!AK39) | ¬¬IF(ISBLANK('DPW2'!AL39),"",'DPW2'!AL39)
¬¬A1302 | ¬¬IF(ISBLANK('DPW2'!BY39),"",'DPW2'!BY39) | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM39),"",'DPW2'!AM39) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN39),"",'DPW2'!AN39)
¬¬A1303 | ¬¬IF(ISBLANK('DPW2'!CB39),"",'DPW2'!CB39) | ¬¬'DPW2'!F39 & "," & 'DPW2'!G39 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H39),"",'DPW2'!H39) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP39),"",'DPW2'!AP39) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ39),"",'DPW2'!AQ39)
¬¬A1304 | ¬¬IF(ISBLANK('DPW2'!AV40),"",'DPW2'!AV40) | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J40),"",'DPW2'!J40)
¬¬A1305 | ¬¬IF(ISBLANK('DPW2'!AX40),"",'DPW2'!AX40) | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L40),"",'DPW2'!L40) | ¬¬IF(ISBLANK('DPW2'!M40),"",'DPW2'!M40) | ¬¬IF(ISBLANK('DPW2'!N40),"",'DPW2'!N40) | ¬¬IF(ISBLANK('DPW2'!O40),"",'DPW2'!O40) | ¬¬IF(ISBLANK('DPW2'!P40),"",'DPW2'!P40) | ¬¬IF(ISBLANK('DPW2'!Q40),"",'DPW2'!Q40) | ¬¬IF(ISBLANK('DPW2'!R40),"",'DPW2'!R40) | ¬¬IF(ISBLANK('DPW2'!S40),"",'DPW2'!S40) | ¬¬IF(ISBLANK('DPW2'!T40),"",'DPW2'!T40) | ¬¬IF(ISBLANK('DPW2'!U40),"",'DPW2'!U40) | ¬¬IF(ISBLANK('DPW2'!V40),"",'DPW2'!V40) | ¬¬IF(ISBLANK('DPW2'!W40),"",'DPW2'!W40)
¬¬A1306 | ¬¬IF(ISBLANK('DPW2'!BJ40),"",'DPW2'!BJ40) | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X40),"",'DPW2'!X40) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y40),"",'DPW2'!Y40)
¬¬A1307 | ¬¬IF(ISBLANK('DPW2'!BM40),"",'DPW2'!BM40) | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA40),"",'DPW2'!AA40) | ¬¬IF(ISBLANK('DPW2'!AB40),"",'DPW2'!AB40) | ¬¬IF(ISBLANK('DPW2'!AC40),"",'DPW2'!AC40) | ¬¬IF(ISBLANK('DPW2'!AD40),"",'DPW2'!AD40) | ¬¬IF(ISBLANK('DPW2'!AE40),"",'DPW2'!AE40) | ¬¬IF(ISBLANK('DPW2'!AF40),"",'DPW2'!AF40) | ¬¬IF(ISBLANK('DPW2'!AG40),"",'DPW2'!AG40) | ¬¬IF(ISBLANK('DPW2'!AH40),"",'DPW2'!AH40) | ¬¬IF(ISBLANK('DPW2'!AI40),"",'DPW2'!AI40) | ¬¬IF(ISBLANK('DPW2'!AJ40),"",'DPW2'!AJ40) | ¬¬IF(ISBLANK('DPW2'!AK40),"",'DPW2'!AK40) | ¬¬IF(ISBLANK('DPW2'!AL40),"",'DPW2'!AL40)
¬¬A1308 | ¬¬IF(ISBLANK('DPW2'!BY40),"",'DPW2'!BY40) | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM40),"",'DPW2'!AM40) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN40),"",'DPW2'!AN40)
¬¬A1309 | ¬¬IF(ISBLANK('DPW2'!CB40),"",'DPW2'!CB40) | ¬¬'DPW2'!F40 & "," & 'DPW2'!G40 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H40),"",'DPW2'!H40) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP40),"",'DPW2'!AP40) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ40),"",'DPW2'!AQ40)
¬¬A1310 | ¬¬IF(ISBLANK('DPW2'!AV41),"",'DPW2'!AV41) | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J41),"",'DPW2'!J41)
¬¬A1311 | ¬¬IF(ISBLANK('DPW2'!AX41),"",'DPW2'!AX41) | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L41),"",'DPW2'!L41) | ¬¬IF(ISBLANK('DPW2'!M41),"",'DPW2'!M41) | ¬¬IF(ISBLANK('DPW2'!N41),"",'DPW2'!N41) | ¬¬IF(ISBLANK('DPW2'!O41),"",'DPW2'!O41) | ¬¬IF(ISBLANK('DPW2'!P41),"",'DPW2'!P41) | ¬¬IF(ISBLANK('DPW2'!Q41),"",'DPW2'!Q41) | ¬¬IF(ISBLANK('DPW2'!R41),"",'DPW2'!R41) | ¬¬IF(ISBLANK('DPW2'!S41),"",'DPW2'!S41) | ¬¬IF(ISBLANK('DPW2'!T41),"",'DPW2'!T41) | ¬¬IF(ISBLANK('DPW2'!U41),"",'DPW2'!U41) | ¬¬IF(ISBLANK('DPW2'!V41),"",'DPW2'!V41) | ¬¬IF(ISBLANK('DPW2'!W41),"",'DPW2'!W41)
¬¬A1312 | ¬¬IF(ISBLANK('DPW2'!BJ41),"",'DPW2'!BJ41) | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X41),"",'DPW2'!X41) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y41),"",'DPW2'!Y41)
¬¬A1313 | ¬¬IF(ISBLANK('DPW2'!BM41),"",'DPW2'!BM41) | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA41),"",'DPW2'!AA41) | ¬¬IF(ISBLANK('DPW2'!AB41),"",'DPW2'!AB41) | ¬¬IF(ISBLANK('DPW2'!AC41),"",'DPW2'!AC41) | ¬¬IF(ISBLANK('DPW2'!AD41),"",'DPW2'!AD41) | ¬¬IF(ISBLANK('DPW2'!AE41),"",'DPW2'!AE41) | ¬¬IF(ISBLANK('DPW2'!AF41),"",'DPW2'!AF41) | ¬¬IF(ISBLANK('DPW2'!AG41),"",'DPW2'!AG41) | ¬¬IF(ISBLANK('DPW2'!AH41),"",'DPW2'!AH41) | ¬¬IF(ISBLANK('DPW2'!AI41),"",'DPW2'!AI41) | ¬¬IF(ISBLANK('DPW2'!AJ41),"",'DPW2'!AJ41) | ¬¬IF(ISBLANK('DPW2'!AK41),"",'DPW2'!AK41) | ¬¬IF(ISBLANK('DPW2'!AL41),"",'DPW2'!AL41)
¬¬A1314 | ¬¬IF(ISBLANK('DPW2'!BY41),"",'DPW2'!BY41) | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM41),"",'DPW2'!AM41) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN41),"",'DPW2'!AN41)
¬¬A1315 | ¬¬IF(ISBLANK('DPW2'!CB41),"",'DPW2'!CB41) | ¬¬'DPW2'!F41 & "," & 'DPW2'!G41 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H41),"",'DPW2'!H41) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP41),"",'DPW2'!AP41) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ41),"",'DPW2'!AQ41)
¬¬A1316 | ¬¬IF(ISBLANK('DPW2'!AV42),"",'DPW2'!AV42) | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J42),"",'DPW2'!J42)
¬¬A1317 | ¬¬IF(ISBLANK('DPW2'!AX42),"",'DPW2'!AX42) | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L42),"",'DPW2'!L42) | ¬¬IF(ISBLANK('DPW2'!M42),"",'DPW2'!M42) | ¬¬IF(ISBLANK('DPW2'!N42),"",'DPW2'!N42) | ¬¬IF(ISBLANK('DPW2'!O42),"",'DPW2'!O42) | ¬¬IF(ISBLANK('DPW2'!P42),"",'DPW2'!P42) | ¬¬IF(ISBLANK('DPW2'!Q42),"",'DPW2'!Q42) | ¬¬IF(ISBLANK('DPW2'!R42),"",'DPW2'!R42) | ¬¬IF(ISBLANK('DPW2'!S42),"",'DPW2'!S42) | ¬¬IF(ISBLANK('DPW2'!T42),"",'DPW2'!T42) | ¬¬IF(ISBLANK('DPW2'!U42),"",'DPW2'!U42) | ¬¬IF(ISBLANK('DPW2'!V42),"",'DPW2'!V42) | ¬¬IF(ISBLANK('DPW2'!W42),"",'DPW2'!W42)
¬¬A1318 | ¬¬IF(ISBLANK('DPW2'!BJ42),"",'DPW2'!BJ42) | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X42),"",'DPW2'!X42) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y42),"",'DPW2'!Y42)
¬¬A1319 | ¬¬IF(ISBLANK('DPW2'!BM42),"",'DPW2'!BM42) | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA42),"",'DPW2'!AA42) | ¬¬IF(ISBLANK('DPW2'!AB42),"",'DPW2'!AB42) | ¬¬IF(ISBLANK('DPW2'!AC42),"",'DPW2'!AC42) | ¬¬IF(ISBLANK('DPW2'!AD42),"",'DPW2'!AD42) | ¬¬IF(ISBLANK('DPW2'!AE42),"",'DPW2'!AE42) | ¬¬IF(ISBLANK('DPW2'!AF42),"",'DPW2'!AF42) | ¬¬IF(ISBLANK('DPW2'!AG42),"",'DPW2'!AG42) | ¬¬IF(ISBLANK('DPW2'!AH42),"",'DPW2'!AH42) | ¬¬IF(ISBLANK('DPW2'!AI42),"",'DPW2'!AI42) | ¬¬IF(ISBLANK('DPW2'!AJ42),"",'DPW2'!AJ42) | ¬¬IF(ISBLANK('DPW2'!AK42),"",'DPW2'!AK42) | ¬¬IF(ISBLANK('DPW2'!AL42),"",'DPW2'!AL42)
¬¬A1320 | ¬¬IF(ISBLANK('DPW2'!BY42),"",'DPW2'!BY42) | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM42),"",'DPW2'!AM42) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN42),"",'DPW2'!AN42)
¬¬A1321 | ¬¬IF(ISBLANK('DPW2'!CB42),"",'DPW2'!CB42) | ¬¬'DPW2'!F42 & "," & 'DPW2'!G42 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H42),"",'DPW2'!H42) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP42),"",'DPW2'!AP42) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ42),"",'DPW2'!AQ42)
¬¬A1322 | ¬¬IF(ISBLANK('DPW2'!AV43),"",'DPW2'!AV43) | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J43),"",'DPW2'!J43)
¬¬A1323 | ¬¬IF(ISBLANK('DPW2'!AX43),"",'DPW2'!AX43) | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L43),"",'DPW2'!L43) | ¬¬IF(ISBLANK('DPW2'!M43),"",'DPW2'!M43) | ¬¬IF(ISBLANK('DPW2'!N43),"",'DPW2'!N43) | ¬¬IF(ISBLANK('DPW2'!O43),"",'DPW2'!O43) | ¬¬IF(ISBLANK('DPW2'!P43),"",'DPW2'!P43) | ¬¬IF(ISBLANK('DPW2'!Q43),"",'DPW2'!Q43) | ¬¬IF(ISBLANK('DPW2'!R43),"",'DPW2'!R43) | ¬¬IF(ISBLANK('DPW2'!S43),"",'DPW2'!S43) | ¬¬IF(ISBLANK('DPW2'!T43),"",'DPW2'!T43) | ¬¬IF(ISBLANK('DPW2'!U43),"",'DPW2'!U43) | ¬¬IF(ISBLANK('DPW2'!V43),"",'DPW2'!V43) | ¬¬IF(ISBLANK('DPW2'!W43),"",'DPW2'!W43)
¬¬A1324 | ¬¬IF(ISBLANK('DPW2'!BJ43),"",'DPW2'!BJ43) | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X43),"",'DPW2'!X43) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y43),"",'DPW2'!Y43)
¬¬A1325 | ¬¬IF(ISBLANK('DPW2'!BM43),"",'DPW2'!BM43) | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA43),"",'DPW2'!AA43) | ¬¬IF(ISBLANK('DPW2'!AB43),"",'DPW2'!AB43) | ¬¬IF(ISBLANK('DPW2'!AC43),"",'DPW2'!AC43) | ¬¬IF(ISBLANK('DPW2'!AD43),"",'DPW2'!AD43) | ¬¬IF(ISBLANK('DPW2'!AE43),"",'DPW2'!AE43) | ¬¬IF(ISBLANK('DPW2'!AF43),"",'DPW2'!AF43) | ¬¬IF(ISBLANK('DPW2'!AG43),"",'DPW2'!AG43) | ¬¬IF(ISBLANK('DPW2'!AH43),"",'DPW2'!AH43) | ¬¬IF(ISBLANK('DPW2'!AI43),"",'DPW2'!AI43) | ¬¬IF(ISBLANK('DPW2'!AJ43),"",'DPW2'!AJ43) | ¬¬IF(ISBLANK('DPW2'!AK43),"",'DPW2'!AK43) | ¬¬IF(ISBLANK('DPW2'!AL43),"",'DPW2'!AL43)
¬¬A1326 | ¬¬IF(ISBLANK('DPW2'!BY43),"",'DPW2'!BY43) | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM43),"",'DPW2'!AM43) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN43),"",'DPW2'!AN43)
¬¬A1327 | ¬¬IF(ISBLANK('DPW2'!CB43),"",'DPW2'!CB43) | ¬¬'DPW2'!F43 & "," & 'DPW2'!G43 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H43),"",'DPW2'!H43) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP43),"",'DPW2'!AP43) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ43),"",'DPW2'!AQ43)
¬¬A1328 | ¬¬IF(ISBLANK('DPW2'!AV44),"",'DPW2'!AV44) | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J45),"",'DPW2'!J45)
¬¬A1329 | ¬¬IF(ISBLANK('DPW2'!AX44),"",'DPW2'!AX44) | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L45),"",'DPW2'!L45) | ¬¬IF(ISBLANK('DPW2'!M45),"",'DPW2'!M45) | ¬¬IF(ISBLANK('DPW2'!N45),"",'DPW2'!N45) | ¬¬IF(ISBLANK('DPW2'!O45),"",'DPW2'!O45) | ¬¬IF(ISBLANK('DPW2'!P45),"",'DPW2'!P45) | ¬¬IF(ISBLANK('DPW2'!Q45),"",'DPW2'!Q45) | ¬¬IF(ISBLANK('DPW2'!R45),"",'DPW2'!R45) | ¬¬IF(ISBLANK('DPW2'!S45),"",'DPW2'!S45) | ¬¬IF(ISBLANK('DPW2'!T45),"",'DPW2'!T45) | ¬¬IF(ISBLANK('DPW2'!U45),"",'DPW2'!U45) | ¬¬IF(ISBLANK('DPW2'!V45),"",'DPW2'!V45) | ¬¬IF(ISBLANK('DPW2'!W45),"",'DPW2'!W45)
¬¬A1330 | ¬¬IF(ISBLANK('DPW2'!BJ44),"",'DPW2'!BJ44) | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X45),"",'DPW2'!X45) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y45),"",'DPW2'!Y45)
¬¬A1331 | ¬¬IF(ISBLANK('DPW2'!BM44),"",'DPW2'!BM44) | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA45),"",'DPW2'!AA45) | ¬¬IF(ISBLANK('DPW2'!AB45),"",'DPW2'!AB45) | ¬¬IF(ISBLANK('DPW2'!AC45),"",'DPW2'!AC45) | ¬¬IF(ISBLANK('DPW2'!AD45),"",'DPW2'!AD45) | ¬¬IF(ISBLANK('DPW2'!AE45),"",'DPW2'!AE45) | ¬¬IF(ISBLANK('DPW2'!AF45),"",'DPW2'!AF45) | ¬¬IF(ISBLANK('DPW2'!AG45),"",'DPW2'!AG45) | ¬¬IF(ISBLANK('DPW2'!AH45),"",'DPW2'!AH45) | ¬¬IF(ISBLANK('DPW2'!AI45),"",'DPW2'!AI45) | ¬¬IF(ISBLANK('DPW2'!AJ45),"",'DPW2'!AJ45) | ¬¬IF(ISBLANK('DPW2'!AK45),"",'DPW2'!AK45) | ¬¬IF(ISBLANK('DPW2'!AL45),"",'DPW2'!AL45)
¬¬A1332 | ¬¬IF(ISBLANK('DPW2'!BY44),"",'DPW2'!BY44) | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM45),"",'DPW2'!AM45) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN45),"",'DPW2'!AN45)
¬¬A1333 | ¬¬IF(ISBLANK('DPW2'!CB44),"",'DPW2'!CB44) | ¬¬'DPW2'!F44 & "," & 'DPW2'!G44 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H44),"",'DPW2'!H44) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP45),"",'DPW2'!AP45) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ45),"",'DPW2'!AQ45)
¬¬A1334 | ¬¬IF(ISBLANK('DPW2'!AV46),"",'DPW2'!AV46) | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J46),"",'DPW2'!J46)
¬¬A1335 | ¬¬IF(ISBLANK('DPW2'!AX46),"",'DPW2'!AX46) | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L46),"",'DPW2'!L46) | ¬¬IF(ISBLANK('DPW2'!M46),"",'DPW2'!M46) | ¬¬IF(ISBLANK('DPW2'!N46),"",'DPW2'!N46) | ¬¬IF(ISBLANK('DPW2'!O46),"",'DPW2'!O46) | ¬¬IF(ISBLANK('DPW2'!P46),"",'DPW2'!P46) | ¬¬IF(ISBLANK('DPW2'!Q46),"",'DPW2'!Q46) | ¬¬IF(ISBLANK('DPW2'!R46),"",'DPW2'!R46) | ¬¬IF(ISBLANK('DPW2'!S46),"",'DPW2'!S46) | ¬¬IF(ISBLANK('DPW2'!T46),"",'DPW2'!T46) | ¬¬IF(ISBLANK('DPW2'!U46),"",'DPW2'!U46) | ¬¬IF(ISBLANK('DPW2'!V46),"",'DPW2'!V46) | ¬¬IF(ISBLANK('DPW2'!W46),"",'DPW2'!W46)
¬¬A1336 | ¬¬IF(ISBLANK('DPW2'!BJ46),"",'DPW2'!BJ46) | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X46),"",'DPW2'!X46) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y46),"",'DPW2'!Y46)
¬¬A1337 | ¬¬IF(ISBLANK('DPW2'!BM46),"",'DPW2'!BM46) | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA46),"",'DPW2'!AA46) | ¬¬IF(ISBLANK('DPW2'!AB46),"",'DPW2'!AB46) | ¬¬IF(ISBLANK('DPW2'!AC46),"",'DPW2'!AC46) | ¬¬IF(ISBLANK('DPW2'!AD46),"",'DPW2'!AD46) | ¬¬IF(ISBLANK('DPW2'!AE46),"",'DPW2'!AE46) | ¬¬IF(ISBLANK('DPW2'!AF46),"",'DPW2'!AF46) | ¬¬IF(ISBLANK('DPW2'!AG46),"",'DPW2'!AG46) | ¬¬IF(ISBLANK('DPW2'!AH46),"",'DPW2'!AH46) | ¬¬IF(ISBLANK('DPW2'!AI46),"",'DPW2'!AI46) | ¬¬IF(ISBLANK('DPW2'!AJ46),"",'DPW2'!AJ46) | ¬¬IF(ISBLANK('DPW2'!AK46),"",'DPW2'!AK46) | ¬¬IF(ISBLANK('DPW2'!AL46),"",'DPW2'!AL46)
¬¬A1338 | ¬¬IF(ISBLANK('DPW2'!BY46),"",'DPW2'!BY46) | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM46),"",'DPW2'!AM46) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN46),"",'DPW2'!AN46)
¬¬A1339 | ¬¬IF(ISBLANK('DPW2'!CB46),"",'DPW2'!CB46) | ¬¬'DPW2'!F46 & "," & 'DPW2'!G46 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H46),"",'DPW2'!H46) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP46),"",'DPW2'!AP46) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ46),"",'DPW2'!AQ46)
¬¬A1340 | ¬¬IF(ISBLANK('DPW2'!AV47),"",'DPW2'!AV47) | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J47),"",'DPW2'!J47)
¬¬A1341 | ¬¬IF(ISBLANK('DPW2'!AX47),"",'DPW2'!AX47) | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L47),"",'DPW2'!L47) | ¬¬IF(ISBLANK('DPW2'!M47),"",'DPW2'!M47) | ¬¬IF(ISBLANK('DPW2'!N47),"",'DPW2'!N47) | ¬¬IF(ISBLANK('DPW2'!O47),"",'DPW2'!O47) | ¬¬IF(ISBLANK('DPW2'!P47),"",'DPW2'!P47) | ¬¬IF(ISBLANK('DPW2'!Q47),"",'DPW2'!Q47) | ¬¬IF(ISBLANK('DPW2'!R47),"",'DPW2'!R47) | ¬¬IF(ISBLANK('DPW2'!S47),"",'DPW2'!S47) | ¬¬IF(ISBLANK('DPW2'!T47),"",'DPW2'!T47) | ¬¬IF(ISBLANK('DPW2'!U47),"",'DPW2'!U47) | ¬¬IF(ISBLANK('DPW2'!V47),"",'DPW2'!V47) | ¬¬IF(ISBLANK('DPW2'!W47),"",'DPW2'!W47)
¬¬A1342 | ¬¬IF(ISBLANK('DPW2'!BJ47),"",'DPW2'!BJ47) | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X47),"",'DPW2'!X47) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y47),"",'DPW2'!Y47)
¬¬A1343 | ¬¬IF(ISBLANK('DPW2'!BM47),"",'DPW2'!BM47) | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA47),"",'DPW2'!AA47) | ¬¬IF(ISBLANK('DPW2'!AB47),"",'DPW2'!AB47) | ¬¬IF(ISBLANK('DPW2'!AC47),"",'DPW2'!AC47) | ¬¬IF(ISBLANK('DPW2'!AD47),"",'DPW2'!AD47) | ¬¬IF(ISBLANK('DPW2'!AE47),"",'DPW2'!AE47) | ¬¬IF(ISBLANK('DPW2'!AF47),"",'DPW2'!AF47) | ¬¬IF(ISBLANK('DPW2'!AG47),"",'DPW2'!AG47) | ¬¬IF(ISBLANK('DPW2'!AH47),"",'DPW2'!AH47) | ¬¬IF(ISBLANK('DPW2'!AI47),"",'DPW2'!AI47) | ¬¬IF(ISBLANK('DPW2'!AJ47),"",'DPW2'!AJ47) | ¬¬IF(ISBLANK('DPW2'!AK47),"",'DPW2'!AK47) | ¬¬IF(ISBLANK('DPW2'!AL47),"",'DPW2'!AL47)
¬¬A1344 | ¬¬IF(ISBLANK('DPW2'!BY47),"",'DPW2'!BY47) | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM47),"",'DPW2'!AM47) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN47),"",'DPW2'!AN47)
¬¬A1345 | ¬¬IF(ISBLANK('DPW2'!CB47),"",'DPW2'!CB47) | ¬¬'DPW2'!F47 & "," & 'DPW2'!G47 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H47),"",'DPW2'!H47) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP47),"",'DPW2'!AP47) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ47),"",'DPW2'!AQ47)
¬¬A1346 | ¬¬IF(ISBLANK('DPW2'!AV48),"",'DPW2'!AV48) | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J48),"",'DPW2'!J48)
¬¬A1347 | ¬¬IF(ISBLANK('DPW2'!AX48),"",'DPW2'!AX48) | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L48),"",'DPW2'!L48) | ¬¬IF(ISBLANK('DPW2'!M48),"",'DPW2'!M48) | ¬¬IF(ISBLANK('DPW2'!N48),"",'DPW2'!N48) | ¬¬IF(ISBLANK('DPW2'!O48),"",'DPW2'!O48) | ¬¬IF(ISBLANK('DPW2'!P48),"",'DPW2'!P48) | ¬¬IF(ISBLANK('DPW2'!Q48),"",'DPW2'!Q48) | ¬¬IF(ISBLANK('DPW2'!R48),"",'DPW2'!R48) | ¬¬IF(ISBLANK('DPW2'!S48),"",'DPW2'!S48) | ¬¬IF(ISBLANK('DPW2'!T48),"",'DPW2'!T48) | ¬¬IF(ISBLANK('DPW2'!U48),"",'DPW2'!U48) | ¬¬IF(ISBLANK('DPW2'!V48),"",'DPW2'!V48) | ¬¬IF(ISBLANK('DPW2'!W48),"",'DPW2'!W48)
¬¬A1348 | ¬¬IF(ISBLANK('DPW2'!BJ48),"",'DPW2'!BJ48) | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X48),"",'DPW2'!X48) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y48),"",'DPW2'!Y48)
¬¬A1349 | ¬¬IF(ISBLANK('DPW2'!BM48),"",'DPW2'!BM48) | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA48),"",'DPW2'!AA48) | ¬¬IF(ISBLANK('DPW2'!AB48),"",'DPW2'!AB48) | ¬¬IF(ISBLANK('DPW2'!AC48),"",'DPW2'!AC48) | ¬¬IF(ISBLANK('DPW2'!AD48),"",'DPW2'!AD48) | ¬¬IF(ISBLANK('DPW2'!AE48),"",'DPW2'!AE48) | ¬¬IF(ISBLANK('DPW2'!AF48),"",'DPW2'!AF48) | ¬¬IF(ISBLANK('DPW2'!AG48),"",'DPW2'!AG48) | ¬¬IF(ISBLANK('DPW2'!AH48),"",'DPW2'!AH48) | ¬¬IF(ISBLANK('DPW2'!AI48),"",'DPW2'!AI48) | ¬¬IF(ISBLANK('DPW2'!AJ48),"",'DPW2'!AJ48) | ¬¬IF(ISBLANK('DPW2'!AK48),"",'DPW2'!AK48) | ¬¬IF(ISBLANK('DPW2'!AL48),"",'DPW2'!AL48)
¬¬A1350 | ¬¬IF(ISBLANK('DPW2'!BY48),"",'DPW2'!BY48) | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM48),"",'DPW2'!AM48) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN48),"",'DPW2'!AN48)
¬¬A1351 | ¬¬IF(ISBLANK('DPW2'!CB48),"",'DPW2'!CB48) | ¬¬'DPW2'!F48 & "," & 'DPW2'!G48 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H48),"",'DPW2'!H48) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP48),"",'DPW2'!AP48) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ48),"",'DPW2'!AQ48)
¬¬A1352 | ¬¬IF(ISBLANK('DPW2'!AV49),"",'DPW2'!AV49) | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J49),"",'DPW2'!J49)
¬¬A1353 | ¬¬IF(ISBLANK('DPW2'!AX49),"",'DPW2'!AX49) | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L49),"",'DPW2'!L49) | ¬¬IF(ISBLANK('DPW2'!M49),"",'DPW2'!M49) | ¬¬IF(ISBLANK('DPW2'!N49),"",'DPW2'!N49) | ¬¬IF(ISBLANK('DPW2'!O49),"",'DPW2'!O49) | ¬¬IF(ISBLANK('DPW2'!P49),"",'DPW2'!P49) | ¬¬IF(ISBLANK('DPW2'!Q49),"",'DPW2'!Q49) | ¬¬IF(ISBLANK('DPW2'!R49),"",'DPW2'!R49) | ¬¬IF(ISBLANK('DPW2'!S49),"",'DPW2'!S49) | ¬¬IF(ISBLANK('DPW2'!T49),"",'DPW2'!T49) | ¬¬IF(ISBLANK('DPW2'!U49),"",'DPW2'!U49) | ¬¬IF(ISBLANK('DPW2'!V49),"",'DPW2'!V49) | ¬¬IF(ISBLANK('DPW2'!W49),"",'DPW2'!W49)
¬¬A1354 | ¬¬IF(ISBLANK('DPW2'!BJ49),"",'DPW2'!BJ49) | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X49),"",'DPW2'!X49) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y49),"",'DPW2'!Y49)
¬¬A1355 | ¬¬IF(ISBLANK('DPW2'!BM49),"",'DPW2'!BM49) | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA49),"",'DPW2'!AA49) | ¬¬IF(ISBLANK('DPW2'!AB49),"",'DPW2'!AB49) | ¬¬IF(ISBLANK('DPW2'!AC49),"",'DPW2'!AC49) | ¬¬IF(ISBLANK('DPW2'!AD49),"",'DPW2'!AD49) | ¬¬IF(ISBLANK('DPW2'!AE49),"",'DPW2'!AE49) | ¬¬IF(ISBLANK('DPW2'!AF49),"",'DPW2'!AF49) | ¬¬IF(ISBLANK('DPW2'!AG49),"",'DPW2'!AG49) | ¬¬IF(ISBLANK('DPW2'!AH49),"",'DPW2'!AH49) | ¬¬IF(ISBLANK('DPW2'!AI49),"",'DPW2'!AI49) | ¬¬IF(ISBLANK('DPW2'!AJ49),"",'DPW2'!AJ49) | ¬¬IF(ISBLANK('DPW2'!AK49),"",'DPW2'!AK49) | ¬¬IF(ISBLANK('DPW2'!AL49),"",'DPW2'!AL49)
¬¬A1356 | ¬¬IF(ISBLANK('DPW2'!BY49),"",'DPW2'!BY49) | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM49),"",'DPW2'!AM49) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN49),"",'DPW2'!AN49)
¬¬A1357 | ¬¬IF(ISBLANK('DPW2'!CB49),"",'DPW2'!CB49) | ¬¬'DPW2'!F49 & "," & 'DPW2'!G49 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H49),"",'DPW2'!H49) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP49),"",'DPW2'!AP49) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ49),"",'DPW2'!AQ49)
¬¬A1358 | ¬¬IF(ISBLANK('DPW2'!AV50),"",'DPW2'!AV50) | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) | Delta | [13 empty] | ¬¬IF(ISBLANK('DPW2'!J50),"",'DPW2'!J50)
¬¬A1359 | ¬¬IF(ISBLANK('DPW2'!AX50),"",'DPW2'!AX50) | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!AV5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) | Delta |  | ¬¬IF(ISBLANK('DPW2'!L50),"",'DPW2'!L50) | ¬¬IF(ISBLANK('DPW2'!M50),"",'DPW2'!M50) | ¬¬IF(ISBLANK('DPW2'!N50),"",'DPW2'!N50) | ¬¬IF(ISBLANK('DPW2'!O50),"",'DPW2'!O50) | ¬¬IF(ISBLANK('DPW2'!P50),"",'DPW2'!P50) | ¬¬IF(ISBLANK('DPW2'!Q50),"",'DPW2'!Q50) | ¬¬IF(ISBLANK('DPW2'!R50),"",'DPW2'!R50) | ¬¬IF(ISBLANK('DPW2'!S50),"",'DPW2'!S50) | ¬¬IF(ISBLANK('DPW2'!T50),"",'DPW2'!T50) | ¬¬IF(ISBLANK('DPW2'!U50),"",'DPW2'!U50) | ¬¬IF(ISBLANK('DPW2'!V50),"",'DPW2'!V50) | ¬¬IF(ISBLANK('DPW2'!W50),"",'DPW2'!W50)
¬¬A1360 | ¬¬IF(ISBLANK('DPW2'!BJ50),"",'DPW2'!BJ50) | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BJ5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!X50),"",'DPW2'!X50) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!Y50),"",'DPW2'!Y50)
¬¬A1361 | ¬¬IF(ISBLANK('DPW2'!BM50),"",'DPW2'!BM50) | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BK5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) | Delta |  | ¬¬IF(ISBLANK('DPW2'!AA50),"",'DPW2'!AA50) | ¬¬IF(ISBLANK('DPW2'!AB50),"",'DPW2'!AB50) | ¬¬IF(ISBLANK('DPW2'!AC50),"",'DPW2'!AC50) | ¬¬IF(ISBLANK('DPW2'!AD50),"",'DPW2'!AD50) | ¬¬IF(ISBLANK('DPW2'!AE50),"",'DPW2'!AE50) | ¬¬IF(ISBLANK('DPW2'!AF50),"",'DPW2'!AF50) | ¬¬IF(ISBLANK('DPW2'!AG50),"",'DPW2'!AG50) | ¬¬IF(ISBLANK('DPW2'!AH50),"",'DPW2'!AH50) | ¬¬IF(ISBLANK('DPW2'!AI50),"",'DPW2'!AI50) | ¬¬IF(ISBLANK('DPW2'!AJ50),"",'DPW2'!AJ50) | ¬¬IF(ISBLANK('DPW2'!AK50),"",'DPW2'!AK50) | ¬¬IF(ISBLANK('DPW2'!AL50),"",'DPW2'!AL50)
¬¬A1362 | ¬¬IF(ISBLANK('DPW2'!BY50),"",'DPW2'!BY50) | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!BY5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AM50),"",'DPW2'!AM50) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AN50),"",'DPW2'!AN50)
¬¬A1363 | ¬¬IF(ISBLANK('DPW2'!CB50),"",'DPW2'!CB50) | ¬¬'DPW2'!F50 & "," & 'DPW2'!G50 & "," & 'DPW2'!CB5 | ¬¬IF(ISBLANK('DPW2'!H50),"",'DPW2'!H50) | Delta | [7 empty] | ¬¬IF(ISBLANK('DPW2'!AP50),"",'DPW2'!AP50) |  |  |  |  | ¬¬IF(ISBLANK('DPW2'!AQ50),"",'DPW2'!AQ50)
¬¬A1364 | ¬¬IF(ISBLANK('DPW3'!MT8),"",'DPW3'!MT8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!K8),"",'DPW3'!K8)
¬¬A1365 | ¬¬IF(ISBLANK('DPW3'!MV8),"",'DPW3'!MV8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M8),"",'DPW3'!M8) | ¬¬IF(ISBLANK('DPW3'!N8),"",'DPW3'!N8) | ¬¬IF(ISBLANK('DPW3'!O8),"",'DPW3'!O8) | ¬¬IF(ISBLANK('DPW3'!P8),"",'DPW3'!P8) | ¬¬IF(ISBLANK('DPW3'!Q8),"",'DPW3'!Q8) | ¬¬IF(ISBLANK('DPW3'!R8),"",'DPW3'!R8) | ¬¬IF(ISBLANK('DPW3'!S8),"",'DPW3'!S8) | ¬¬IF(ISBLANK('DPW3'!T8),"",'DPW3'!T8) | ¬¬IF(ISBLANK('DPW3'!U8),"",'DPW3'!U8) | ¬¬IF(ISBLANK('DPW3'!V8),"",'DPW3'!V8) | ¬¬IF(ISBLANK('DPW3'!W8),"",'DPW3'!W8) | ¬¬IF(ISBLANK('DPW3'!X8),"",'DPW3'!X8) | ¬¬IF(ISBLANK('DPW3'!Y8),"",'DPW3'!Y8) | ¬¬IF(ISBLANK('DPW3'!Z8),"",'DPW3'!Z8) | ¬¬IF(ISBLANK('DPW3'!AA8),"",'DPW3'!AA8) | ¬¬IF(ISBLANK('DPW3'!AB8),"",'DPW3'!AB8) | ¬¬IF(ISBLANK('DPW3'!AC8),"",'DPW3'!AC8) | ¬¬IF(ISBLANK('DPW3'!AD8),"",'DPW3'!AD8) | ¬¬IF(ISBLANK('DPW3'!AE8),"",'DPW3'!AE8) | ¬¬IF(ISBLANK('DPW3'!AF8),"",'DPW3'!AF8) | ¬¬IF(ISBLANK('DPW3'!AG8),"",'DPW3'!AG8) | ¬¬IF(ISBLANK('DPW3'!AH8),"",'DPW3'!AH8) | ¬¬IF(ISBLANK('DPW3'!AI8),"",'DPW3'!AI8) | ¬¬IF(ISBLANK('DPW3'!AJ8),"",'DPW3'!AJ8) | ¬¬IF(ISBLANK('DPW3'!AK8),"",'DPW3'!AK8) | ¬¬IF(ISBLANK('DPW3'!AL8),"",'DPW3'!AL8) | ¬¬IF(ISBLANK('DPW3'!AM8),"",'DPW3'!AM8) | ¬¬IF(ISBLANK('DPW3'!AN8),"",'DPW3'!AN8) | ¬¬IF(ISBLANK('DPW3'!AO8),"",'DPW3'!AO8) | ¬¬IF(ISBLANK('DPW3'!AP8),"",'DPW3'!AP8) | ¬¬IF(ISBLANK('DPW3'!AQ8),"",'DPW3'!AQ8) | ¬¬IF(ISBLANK('DPW3'!AR8),"",'DPW3'!AR8) | ¬¬IF(ISBLANK('DPW3'!AS8),"",'DPW3'!AS8) | ¬¬IF(ISBLANK('DPW3'!AT8),"",'DPW3'!AT8) | ¬¬IF(ISBLANK('DPW3'!AU8),"",'DPW3'!AU8) | ¬¬IF(ISBLANK('DPW3'!AV8),"",'DPW3'!AV8) | ¬¬IF(ISBLANK('DPW3'!AW8),"",'DPW3'!AW8) | ¬¬IF(ISBLANK('DPW3'!AX8),"",'DPW3'!AX8) | ¬¬IF(ISBLANK('DPW3'!AY8),"",'DPW3'!AY8) | ¬¬IF(ISBLANK('DPW3'!AZ8),"",'DPW3'!AZ8)
¬¬A1366 | ¬¬IF(ISBLANK('DPW3'!OK8),"",'DPW3'!OK8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB8),"",'DPW3'!BB8) | ¬¬IF(ISBLANK('DPW3'!BC8),"",'DPW3'!BC8) | ¬¬IF(ISBLANK('DPW3'!BD8),"",'DPW3'!BD8) | ¬¬IF(ISBLANK('DPW3'!BE8),"",'DPW3'!BE8) | ¬¬IF(ISBLANK('DPW3'!BF8),"",'DPW3'!BF8) | ¬¬IF(ISBLANK('DPW3'!BG8),"",'DPW3'!BG8) | ¬¬IF(ISBLANK('DPW3'!BH8),"",'DPW3'!BH8) | ¬¬IF(ISBLANK('DPW3'!BI8),"",'DPW3'!BI8) | ¬¬IF(ISBLANK('DPW3'!BJ8),"",'DPW3'!BJ8) | ¬¬IF(ISBLANK('DPW3'!BK8),"",'DPW3'!BK8) | ¬¬IF(ISBLANK('DPW3'!BL8),"",'DPW3'!BL8) | ¬¬IF(ISBLANK('DPW3'!BM8),"",'DPW3'!BM8) | ¬¬IF(ISBLANK('DPW3'!BN8),"",'DPW3'!BN8) | ¬¬IF(ISBLANK('DPW3'!BO8),"",'DPW3'!BO8) | ¬¬IF(ISBLANK('DPW3'!BP8),"",'DPW3'!BP8) | ¬¬IF(ISBLANK('DPW3'!BQ8),"",'DPW3'!BQ8) | ¬¬IF(ISBLANK('DPW3'!BR8),"",'DPW3'!BR8) | ¬¬IF(ISBLANK('DPW3'!BS8),"",'DPW3'!BS8) | ¬¬IF(ISBLANK('DPW3'!BT8),"",'DPW3'!BT8) | ¬¬IF(ISBLANK('DPW3'!BU8),"",'DPW3'!BU8) | ¬¬IF(ISBLANK('DPW3'!BV8),"",'DPW3'!BV8) | ¬¬IF(ISBLANK('DPW3'!BW8),"",'DPW3'!BW8) | ¬¬IF(ISBLANK('DPW3'!BX8),"",'DPW3'!BX8) | ¬¬IF(ISBLANK('DPW3'!BY8),"",'DPW3'!BY8) | ¬¬IF(ISBLANK('DPW3'!BZ8),"",'DPW3'!BZ8) | ¬¬IF(ISBLANK('DPW3'!CA8),"",'DPW3'!CA8) | ¬¬IF(ISBLANK('DPW3'!CB8),"",'DPW3'!CB8) | ¬¬IF(ISBLANK('DPW3'!CC8),"",'DPW3'!CC8) | ¬¬IF(ISBLANK('DPW3'!CD8),"",'DPW3'!CD8) | ¬¬IF(ISBLANK('DPW3'!CE8),"",'DPW3'!CE8) | ¬¬IF(ISBLANK('DPW3'!CF8),"",'DPW3'!CF8) | ¬¬IF(ISBLANK('DPW3'!CG8),"",'DPW3'!CG8) | ¬¬IF(ISBLANK('DPW3'!CH8),"",'DPW3'!CH8) | ¬¬IF(ISBLANK('DPW3'!CI8),"",'DPW3'!CI8) | ¬¬IF(ISBLANK('DPW3'!CJ8),"",'DPW3'!CJ8) | ¬¬IF(ISBLANK('DPW3'!CK8),"",'DPW3'!CK8) | ¬¬IF(ISBLANK('DPW3'!CL8),"",'DPW3'!CL8) | ¬¬IF(ISBLANK('DPW3'!CM8),"",'DPW3'!CM8) | ¬¬IF(ISBLANK('DPW3'!CN8),"",'DPW3'!CN8) | ¬¬IF(ISBLANK('DPW3'!CO8),"",'DPW3'!CO8)
¬¬A1367 | ¬¬IF(ISBLANK('DPW3'!PZ8),"",'DPW3'!PZ8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ8),"",'DPW3'!CQ8) | ¬¬IF(ISBLANK('DPW3'!CR8),"",'DPW3'!CR8) | ¬¬IF(ISBLANK('DPW3'!CS8),"",'DPW3'!CS8) | ¬¬IF(ISBLANK('DPW3'!CT8),"",'DPW3'!CT8) | ¬¬IF(ISBLANK('DPW3'!CU8),"",'DPW3'!CU8) | ¬¬IF(ISBLANK('DPW3'!CV8),"",'DPW3'!CV8) | ¬¬IF(ISBLANK('DPW3'!CW8),"",'DPW3'!CW8) | ¬¬IF(ISBLANK('DPW3'!CX8),"",'DPW3'!CX8) | ¬¬IF(ISBLANK('DPW3'!CY8),"",'DPW3'!CY8) | ¬¬IF(ISBLANK('DPW3'!CZ8),"",'DPW3'!CZ8) | ¬¬IF(ISBLANK('DPW3'!DA8),"",'DPW3'!DA8) | ¬¬IF(ISBLANK('DPW3'!DB8),"",'DPW3'!DB8) | ¬¬IF(ISBLANK('DPW3'!DC8),"",'DPW3'!DC8) | ¬¬IF(ISBLANK('DPW3'!DD8),"",'DPW3'!DD8) | ¬¬IF(ISBLANK('DPW3'!DE8),"",'DPW3'!DE8) | ¬¬IF(ISBLANK('DPW3'!DF8),"",'DPW3'!DF8) | ¬¬IF(ISBLANK('DPW3'!DG8),"",'DPW3'!DG8) | ¬¬IF(ISBLANK('DPW3'!DH8),"",'DPW3'!DH8) | ¬¬IF(ISBLANK('DPW3'!DI8),"",'DPW3'!DI8) | ¬¬IF(ISBLANK('DPW3'!DJ8),"",'DPW3'!DJ8) | ¬¬IF(ISBLANK('DPW3'!DK8),"",'DPW3'!DK8) | ¬¬IF(ISBLANK('DPW3'!DL8),"",'DPW3'!DL8) | ¬¬IF(ISBLANK('DPW3'!DM8),"",'DPW3'!DM8) | ¬¬IF(ISBLANK('DPW3'!DN8),"",'DPW3'!DN8) | ¬¬IF(ISBLANK('DPW3'!DO8),"",'DPW3'!DO8) | ¬¬IF(ISBLANK('DPW3'!DP8),"",'DPW3'!DP8) | ¬¬IF(ISBLANK('DPW3'!DQ8),"",'DPW3'!DQ8) | ¬¬IF(ISBLANK('DPW3'!DR8),"",'DPW3'!DR8) | ¬¬IF(ISBLANK('DPW3'!DS8),"",'DPW3'!DS8) | ¬¬IF(ISBLANK('DPW3'!DT8),"",'DPW3'!DT8) | ¬¬IF(ISBLANK('DPW3'!DU8),"",'DPW3'!DU8) | ¬¬IF(ISBLANK('DPW3'!DV8),"",'DPW3'!DV8) | ¬¬IF(ISBLANK('DPW3'!DW8),"",'DPW3'!DW8) | ¬¬IF(ISBLANK('DPW3'!DX8),"",'DPW3'!DX8) | ¬¬IF(ISBLANK('DPW3'!DY8),"",'DPW3'!DY8) | ¬¬IF(ISBLANK('DPW3'!DZ8),"",'DPW3'!DZ8) | ¬¬IF(ISBLANK('DPW3'!EA8),"",'DPW3'!EA8) | ¬¬IF(ISBLANK('DPW3'!EB8),"",'DPW3'!EB8) | ¬¬IF(ISBLANK('DPW3'!EC8),"",'DPW3'!EC8) | ¬¬IF(ISBLANK('DPW3'!ED8),"",'DPW3'!ED8)
¬¬A1368 | ¬¬IF(ISBLANK('DPW3'!RO8),"",'DPW3'!RO8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF8),"",'DPW3'!EF8) | ¬¬IF(ISBLANK('DPW3'!EG8),"",'DPW3'!EG8) | ¬¬IF(ISBLANK('DPW3'!EH8),"",'DPW3'!EH8) | ¬¬IF(ISBLANK('DPW3'!EI8),"",'DPW3'!EI8) | ¬¬IF(ISBLANK('DPW3'!EJ8),"",'DPW3'!EJ8) | ¬¬IF(ISBLANK('DPW3'!EK8),"",'DPW3'!EK8) | ¬¬IF(ISBLANK('DPW3'!EL8),"",'DPW3'!EL8) | ¬¬IF(ISBLANK('DPW3'!EM8),"",'DPW3'!EM8) | ¬¬IF(ISBLANK('DPW3'!EN8),"",'DPW3'!EN8) | ¬¬IF(ISBLANK('DPW3'!EO8),"",'DPW3'!EO8) | ¬¬IF(ISBLANK('DPW3'!EP8),"",'DPW3'!EP8) | ¬¬IF(ISBLANK('DPW3'!EQ8),"",'DPW3'!EQ8) | ¬¬IF(ISBLANK('DPW3'!ER8),"",'DPW3'!ER8) | ¬¬IF(ISBLANK('DPW3'!ES8),"",'DPW3'!ES8) | ¬¬IF(ISBLANK('DPW3'!ET8),"",'DPW3'!ET8) | ¬¬IF(ISBLANK('DPW3'!EU8),"",'DPW3'!EU8) | ¬¬IF(ISBLANK('DPW3'!EV8),"",'DPW3'!EV8) | ¬¬IF(ISBLANK('DPW3'!EW8),"",'DPW3'!EW8) | ¬¬IF(ISBLANK('DPW3'!EX8),"",'DPW3'!EX8) | ¬¬IF(ISBLANK('DPW3'!EY8),"",'DPW3'!EY8) | ¬¬IF(ISBLANK('DPW3'!EZ8),"",'DPW3'!EZ8) | ¬¬IF(ISBLANK('DPW3'!FA8),"",'DPW3'!FA8) | ¬¬IF(ISBLANK('DPW3'!FB8),"",'DPW3'!FB8) | ¬¬IF(ISBLANK('DPW3'!FC8),"",'DPW3'!FC8) | ¬¬IF(ISBLANK('DPW3'!FD8),"",'DPW3'!FD8) | ¬¬IF(ISBLANK('DPW3'!FE8),"",'DPW3'!FE8) | ¬¬IF(ISBLANK('DPW3'!FF8),"",'DPW3'!FF8) | ¬¬IF(ISBLANK('DPW3'!FG8),"",'DPW3'!FG8) | ¬¬IF(ISBLANK('DPW3'!FH8),"",'DPW3'!FH8) | ¬¬IF(ISBLANK('DPW3'!FI8),"",'DPW3'!FI8) | ¬¬IF(ISBLANK('DPW3'!FJ8),"",'DPW3'!FJ8) | ¬¬IF(ISBLANK('DPW3'!FK8),"",'DPW3'!FK8) | ¬¬IF(ISBLANK('DPW3'!FL8),"",'DPW3'!FL8) | ¬¬IF(ISBLANK('DPW3'!FM8),"",'DPW3'!FM8) | ¬¬IF(ISBLANK('DPW3'!FN8),"",'DPW3'!FN8) | ¬¬IF(ISBLANK('DPW3'!FO8),"",'DPW3'!FO8) | ¬¬IF(ISBLANK('DPW3'!FP8),"",'DPW3'!FP8) | ¬¬IF(ISBLANK('DPW3'!FQ8),"",'DPW3'!FQ8) | ¬¬IF(ISBLANK('DPW3'!FR8),"",'DPW3'!FR8) | ¬¬IF(ISBLANK('DPW3'!FS8),"",'DPW3'!FS8)
¬¬A1369 | ¬¬IF(ISBLANK('DPW3'!TD8),"",'DPW3'!TD8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU8),"",'DPW3'!FU8) | ¬¬IF(ISBLANK('DPW3'!FV8),"",'DPW3'!FV8) | ¬¬IF(ISBLANK('DPW3'!FW8),"",'DPW3'!FW8) | ¬¬IF(ISBLANK('DPW3'!FX8),"",'DPW3'!FX8) | ¬¬IF(ISBLANK('DPW3'!FY8),"",'DPW3'!FY8) | ¬¬IF(ISBLANK('DPW3'!FZ8),"",'DPW3'!FZ8) | ¬¬IF(ISBLANK('DPW3'!GA8),"",'DPW3'!GA8) | ¬¬IF(ISBLANK('DPW3'!GB8),"",'DPW3'!GB8) | ¬¬IF(ISBLANK('DPW3'!GC8),"",'DPW3'!GC8) | ¬¬IF(ISBLANK('DPW3'!GD8),"",'DPW3'!GD8) | ¬¬IF(ISBLANK('DPW3'!GE8),"",'DPW3'!GE8) | ¬¬IF(ISBLANK('DPW3'!GF8),"",'DPW3'!GF8) | ¬¬IF(ISBLANK('DPW3'!GG8),"",'DPW3'!GG8) | ¬¬IF(ISBLANK('DPW3'!GH8),"",'DPW3'!GH8) | ¬¬IF(ISBLANK('DPW3'!GI8),"",'DPW3'!GI8) | ¬¬IF(ISBLANK('DPW3'!GJ8),"",'DPW3'!GJ8) | ¬¬IF(ISBLANK('DPW3'!GK8),"",'DPW3'!GK8) | ¬¬IF(ISBLANK('DPW3'!GL8),"",'DPW3'!GL8) | ¬¬IF(ISBLANK('DPW3'!GM8),"",'DPW3'!GM8) | ¬¬IF(ISBLANK('DPW3'!GN8),"",'DPW3'!GN8) | ¬¬IF(ISBLANK('DPW3'!GO8),"",'DPW3'!GO8) | ¬¬IF(ISBLANK('DPW3'!GP8),"",'DPW3'!GP8) | ¬¬IF(ISBLANK('DPW3'!GQ8),"",'DPW3'!GQ8) | ¬¬IF(ISBLANK('DPW3'!GR8),"",'DPW3'!GR8) | ¬¬IF(ISBLANK('DPW3'!GS8),"",'DPW3'!GS8) | ¬¬IF(ISBLANK('DPW3'!GT8),"",'DPW3'!GT8) | ¬¬IF(ISBLANK('DPW3'!GU8),"",'DPW3'!GU8) | ¬¬IF(ISBLANK('DPW3'!GV8),"",'DPW3'!GV8) | ¬¬IF(ISBLANK('DPW3'!GW8),"",'DPW3'!GW8) | ¬¬IF(ISBLANK('DPW3'!GX8),"",'DPW3'!GX8) | ¬¬IF(ISBLANK('DPW3'!GY8),"",'DPW3'!GY8) | ¬¬IF(ISBLANK('DPW3'!GZ8),"",'DPW3'!GZ8) | ¬¬IF(ISBLANK('DPW3'!HA8),"",'DPW3'!HA8) | ¬¬IF(ISBLANK('DPW3'!HB8),"",'DPW3'!HB8) | ¬¬IF(ISBLANK('DPW3'!HC8),"",'DPW3'!HC8) | ¬¬IF(ISBLANK('DPW3'!HD8),"",'DPW3'!HD8) | ¬¬IF(ISBLANK('DPW3'!HE8),"",'DPW3'!HE8) | ¬¬IF(ISBLANK('DPW3'!HF8),"",'DPW3'!HF8) | ¬¬IF(ISBLANK('DPW3'!HG8),"",'DPW3'!HG8) | ¬¬IF(ISBLANK('DPW3'!HH8),"",'DPW3'!HH8)
¬¬A1370 | ¬¬IF(ISBLANK('DPW3'!US8),"",'DPW3'!US8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ8),"",'DPW3'!HJ8) | ¬¬IF(ISBLANK('DPW3'!HK8),"",'DPW3'!HK8) | ¬¬IF(ISBLANK('DPW3'!HL8),"",'DPW3'!HL8) | ¬¬IF(ISBLANK('DPW3'!HM8),"",'DPW3'!HM8) | ¬¬IF(ISBLANK('DPW3'!HN8),"",'DPW3'!HN8) | ¬¬IF(ISBLANK('DPW3'!HO8),"",'DPW3'!HO8) | ¬¬IF(ISBLANK('DPW3'!HP8),"",'DPW3'!HP8) | ¬¬IF(ISBLANK('DPW3'!HQ8),"",'DPW3'!HQ8) | ¬¬IF(ISBLANK('DPW3'!HR8),"",'DPW3'!HR8) | ¬¬IF(ISBLANK('DPW3'!HS8),"",'DPW3'!HS8) | ¬¬IF(ISBLANK('DPW3'!HT8),"",'DPW3'!HT8) | ¬¬IF(ISBLANK('DPW3'!HU8),"",'DPW3'!HU8) | ¬¬IF(ISBLANK('DPW3'!HV8),"",'DPW3'!HV8) | ¬¬IF(ISBLANK('DPW3'!HW8),"",'DPW3'!HW8) | ¬¬IF(ISBLANK('DPW3'!HX8),"",'DPW3'!HX8) | ¬¬IF(ISBLANK('DPW3'!HY8),"",'DPW3'!HY8) | ¬¬IF(ISBLANK('DPW3'!HZ8),"",'DPW3'!HZ8) | ¬¬IF(ISBLANK('DPW3'!IA8),"",'DPW3'!IA8) | ¬¬IF(ISBLANK('DPW3'!IB8),"",'DPW3'!IB8) | ¬¬IF(ISBLANK('DPW3'!IC8),"",'DPW3'!IC8) | ¬¬IF(ISBLANK('DPW3'!ID8),"",'DPW3'!ID8) | ¬¬IF(ISBLANK('DPW3'!IE8),"",'DPW3'!IE8) | ¬¬IF(ISBLANK('DPW3'!IF8),"",'DPW3'!IF8) | ¬¬IF(ISBLANK('DPW3'!IG8),"",'DPW3'!IG8) | ¬¬IF(ISBLANK('DPW3'!IH8),"",'DPW3'!IH8) | ¬¬IF(ISBLANK('DPW3'!II8),"",'DPW3'!II8) | ¬¬IF(ISBLANK('DPW3'!IJ8),"",'DPW3'!IJ8) | ¬¬IF(ISBLANK('DPW3'!IK8),"",'DPW3'!IK8) | ¬¬IF(ISBLANK('DPW3'!IL8),"",'DPW3'!IL8) | ¬¬IF(ISBLANK('DPW3'!IM8),"",'DPW3'!IM8) | ¬¬IF(ISBLANK('DPW3'!IN8),"",'DPW3'!IN8) | ¬¬IF(ISBLANK('DPW3'!IO8),"",'DPW3'!IO8) | ¬¬IF(ISBLANK('DPW3'!IP8),"",'DPW3'!IP8) | ¬¬IF(ISBLANK('DPW3'!IQ8),"",'DPW3'!IQ8) | ¬¬IF(ISBLANK('DPW3'!IR8),"",'DPW3'!IR8) | ¬¬IF(ISBLANK('DPW3'!IS8),"",'DPW3'!IS8) | ¬¬IF(ISBLANK('DPW3'!IT8),"",'DPW3'!IT8) | ¬¬IF(ISBLANK('DPW3'!IU8),"",'DPW3'!IU8) | ¬¬IF(ISBLANK('DPW3'!IV8),"",'DPW3'!IV8) | ¬¬IF(ISBLANK('DPW3'!IW8),"",'DPW3'!IW8)
¬¬A1371 | ¬¬IF(ISBLANK('DPW3'!WH8),"",'DPW3'!WH8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY8),"",'DPW3'!IY8) | ¬¬IF(ISBLANK('DPW3'!IZ8),"",'DPW3'!IZ8) | ¬¬IF(ISBLANK('DPW3'!JA8),"",'DPW3'!JA8) | ¬¬IF(ISBLANK('DPW3'!JB8),"",'DPW3'!JB8) | ¬¬IF(ISBLANK('DPW3'!JC8),"",'DPW3'!JC8) | ¬¬IF(ISBLANK('DPW3'!JD8),"",'DPW3'!JD8) | ¬¬IF(ISBLANK('DPW3'!JE8),"",'DPW3'!JE8) | ¬¬IF(ISBLANK('DPW3'!JF8),"",'DPW3'!JF8) | ¬¬IF(ISBLANK('DPW3'!JG8),"",'DPW3'!JG8) | ¬¬IF(ISBLANK('DPW3'!JH8),"",'DPW3'!JH8) | ¬¬IF(ISBLANK('DPW3'!JI8),"",'DPW3'!JI8) | ¬¬IF(ISBLANK('DPW3'!JJ8),"",'DPW3'!JJ8) | ¬¬IF(ISBLANK('DPW3'!JK8),"",'DPW3'!JK8) | ¬¬IF(ISBLANK('DPW3'!JL8),"",'DPW3'!JL8) | ¬¬IF(ISBLANK('DPW3'!JM8),"",'DPW3'!JM8) | ¬¬IF(ISBLANK('DPW3'!JN8),"",'DPW3'!JN8) | ¬¬IF(ISBLANK('DPW3'!JO8),"",'DPW3'!JO8) | ¬¬IF(ISBLANK('DPW3'!JP8),"",'DPW3'!JP8) | ¬¬IF(ISBLANK('DPW3'!JQ8),"",'DPW3'!JQ8) | ¬¬IF(ISBLANK('DPW3'!JR8),"",'DPW3'!JR8) | ¬¬IF(ISBLANK('DPW3'!JS8),"",'DPW3'!JS8) | ¬¬IF(ISBLANK('DPW3'!JT8),"",'DPW3'!JT8) | ¬¬IF(ISBLANK('DPW3'!JU8),"",'DPW3'!JU8) | ¬¬IF(ISBLANK('DPW3'!JV8),"",'DPW3'!JV8) | ¬¬IF(ISBLANK('DPW3'!JW8),"",'DPW3'!JW8) | ¬¬IF(ISBLANK('DPW3'!JX8),"",'DPW3'!JX8) | ¬¬IF(ISBLANK('DPW3'!JY8),"",'DPW3'!JY8) | ¬¬IF(ISBLANK('DPW3'!JZ8),"",'DPW3'!JZ8) | ¬¬IF(ISBLANK('DPW3'!KA8),"",'DPW3'!KA8) | ¬¬IF(ISBLANK('DPW3'!KB8),"",'DPW3'!KB8) | ¬¬IF(ISBLANK('DPW3'!KC8),"",'DPW3'!KC8) | ¬¬IF(ISBLANK('DPW3'!KD8),"",'DPW3'!KD8) | ¬¬IF(ISBLANK('DPW3'!KE8),"",'DPW3'!KE8) | ¬¬IF(ISBLANK('DPW3'!KF8),"",'DPW3'!KF8) | ¬¬IF(ISBLANK('DPW3'!KG8),"",'DPW3'!KG8) | ¬¬IF(ISBLANK('DPW3'!KH8),"",'DPW3'!KH8) | ¬¬IF(ISBLANK('DPW3'!KI8),"",'DPW3'!KI8) | ¬¬IF(ISBLANK('DPW3'!KJ8),"",'DPW3'!KJ8) | ¬¬IF(ISBLANK('DPW3'!KK8),"",'DPW3'!KK8) | ¬¬IF(ISBLANK('DPW3'!KL8),"",'DPW3'!KL8)
¬¬A1372 | ¬¬IF(ISBLANK('DPW3'!XW8),"",'DPW3'!XW8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN8),"",'DPW3'!KN8) | ¬¬IF(ISBLANK('DPW3'!KO8),"",'DPW3'!KO8) | ¬¬IF(ISBLANK('DPW3'!KP8),"",'DPW3'!KP8) | ¬¬IF(ISBLANK('DPW3'!KQ8),"",'DPW3'!KQ8) | ¬¬IF(ISBLANK('DPW3'!KR8),"",'DPW3'!KR8) | ¬¬IF(ISBLANK('DPW3'!KS8),"",'DPW3'!KS8) | ¬¬IF(ISBLANK('DPW3'!KT8),"",'DPW3'!KT8) | ¬¬IF(ISBLANK('DPW3'!KU8),"",'DPW3'!KU8) | ¬¬IF(ISBLANK('DPW3'!KV8),"",'DPW3'!KV8) | ¬¬IF(ISBLANK('DPW3'!KW8),"",'DPW3'!KW8) | ¬¬IF(ISBLANK('DPW3'!KX8),"",'DPW3'!KX8) | ¬¬IF(ISBLANK('DPW3'!KY8),"",'DPW3'!KY8) | ¬¬IF(ISBLANK('DPW3'!KZ8),"",'DPW3'!KZ8) | ¬¬IF(ISBLANK('DPW3'!LA8),"",'DPW3'!LA8) | ¬¬IF(ISBLANK('DPW3'!LB8),"",'DPW3'!LB8) | ¬¬IF(ISBLANK('DPW3'!LC8),"",'DPW3'!LC8) | ¬¬IF(ISBLANK('DPW3'!LD8),"",'DPW3'!LD8) | ¬¬IF(ISBLANK('DPW3'!LE8),"",'DPW3'!LE8) | ¬¬IF(ISBLANK('DPW3'!LF8),"",'DPW3'!LF8) | ¬¬IF(ISBLANK('DPW3'!LG8),"",'DPW3'!LG8) | ¬¬IF(ISBLANK('DPW3'!LH8),"",'DPW3'!LH8) | ¬¬IF(ISBLANK('DPW3'!LI8),"",'DPW3'!LI8) | ¬¬IF(ISBLANK('DPW3'!LJ8),"",'DPW3'!LJ8) | ¬¬IF(ISBLANK('DPW3'!LK8),"",'DPW3'!LK8) | ¬¬IF(ISBLANK('DPW3'!LL8),"",'DPW3'!LL8) | ¬¬IF(ISBLANK('DPW3'!LM8),"",'DPW3'!LM8) | ¬¬IF(ISBLANK('DPW3'!LN8),"",'DPW3'!LN8) | ¬¬IF(ISBLANK('DPW3'!LO8),"",'DPW3'!LO8) | ¬¬IF(ISBLANK('DPW3'!LP8),"",'DPW3'!LP8) | ¬¬IF(ISBLANK('DPW3'!LQ8),"",'DPW3'!LQ8) | ¬¬IF(ISBLANK('DPW3'!LR8),"",'DPW3'!LR8) | ¬¬IF(ISBLANK('DPW3'!LS8),"",'DPW3'!LS8) | ¬¬IF(ISBLANK('DPW3'!LT8),"",'DPW3'!LT8) | ¬¬IF(ISBLANK('DPW3'!LU8),"",'DPW3'!LU8) | ¬¬IF(ISBLANK('DPW3'!LV8),"",'DPW3'!LV8) | ¬¬IF(ISBLANK('DPW3'!LW8),"",'DPW3'!LW8) | ¬¬IF(ISBLANK('DPW3'!LX8),"",'DPW3'!LX8) | ¬¬IF(ISBLANK('DPW3'!LY8),"",'DPW3'!LY8) | ¬¬IF(ISBLANK('DPW3'!LZ8),"",'DPW3'!LZ8) | ¬¬IF(ISBLANK('DPW3'!MA8),"",'DPW3'!MA8)
¬¬A1373 | ¬¬IF(ISBLANK('DPW3'!ZL8),"",'DPW3'!ZL8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MC8),"",'DPW3'!MC8)
¬¬A1374 | ¬¬IF(ISBLANK('DPW3'!ZM8),"",'DPW3'!ZM8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MD8),"",'DPW3'!MD8)
¬¬A1375 | ¬¬IF(ISBLANK('DPW3'!ZN8),"",'DPW3'!ZN8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!ML8),"",'DPW3'!ML8)
¬¬A1376 | ¬¬IF(ISBLANK('DPW3'!ZO8),"",'DPW3'!ZO8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MF8),"",'DPW3'!MF8)
¬¬A1377 | ¬¬IF(ISBLANK('DPW3'!ZP8),"",'DPW3'!ZP8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MG8),"",'DPW3'!MG8)
¬¬A1378 | ¬¬IF(ISBLANK('DPW3'!ZQ8),"",'DPW3'!ZQ8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MH8),"",'DPW3'!MH8)
¬¬A1379 | ¬¬IF(ISBLANK('DPW3'!ZR8),"",'DPW3'!ZR8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MI8),"",'DPW3'!MI8)
¬¬A1380 | ¬¬IF(ISBLANK('DPW3'!ZS8),"",'DPW3'!ZS8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ8),"",'DPW3'!MJ8)
¬¬A1381 | ¬¬IF(ISBLANK('DPW3'!ZT8),"",'DPW3'!ZT8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MK8),"",'DPW3'!MK8)
¬¬A1382 | ¬¬IF(ISBLANK('DPW3'!ZV8),"",'DPW3'!ZV8) | ¬¬'DPW3'!F8 & "," & 'DPW3'!G8 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H8),"",'DPW3'!H8) | Delta | ¬¬IF(ISBLANK('DPW3'!MM8),"",'DPW3'!MM8)
¬¬A1383 | ¬¬IF(ISBLANK('DPW3'!MT9),"",'DPW3'!MT9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!K9),"",'DPW3'!K9)
¬¬A1384 | ¬¬IF(ISBLANK('DPW3'!MV9),"",'DPW3'!MV9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M9),"",'DPW3'!M9) | ¬¬IF(ISBLANK('DPW3'!N9),"",'DPW3'!N9) | ¬¬IF(ISBLANK('DPW3'!O9),"",'DPW3'!O9) | ¬¬IF(ISBLANK('DPW3'!P9),"",'DPW3'!P9) | ¬¬IF(ISBLANK('DPW3'!Q9),"",'DPW3'!Q9) | ¬¬IF(ISBLANK('DPW3'!R9),"",'DPW3'!R9) | ¬¬IF(ISBLANK('DPW3'!S9),"",'DPW3'!S9) | ¬¬IF(ISBLANK('DPW3'!T9),"",'DPW3'!T9) | ¬¬IF(ISBLANK('DPW3'!U9),"",'DPW3'!U9) | ¬¬IF(ISBLANK('DPW3'!V9),"",'DPW3'!V9) | ¬¬IF(ISBLANK('DPW3'!W9),"",'DPW3'!W9) | ¬¬IF(ISBLANK('DPW3'!X9),"",'DPW3'!X9) | ¬¬IF(ISBLANK('DPW3'!Y9),"",'DPW3'!Y9) | ¬¬IF(ISBLANK('DPW3'!Z9),"",'DPW3'!Z9) | ¬¬IF(ISBLANK('DPW3'!AA9),"",'DPW3'!AA9) | ¬¬IF(ISBLANK('DPW3'!AB9),"",'DPW3'!AB9) | ¬¬IF(ISBLANK('DPW3'!AC9),"",'DPW3'!AC9) | ¬¬IF(ISBLANK('DPW3'!AD9),"",'DPW3'!AD9) | ¬¬IF(ISBLANK('DPW3'!AE9),"",'DPW3'!AE9) | ¬¬IF(ISBLANK('DPW3'!AF9),"",'DPW3'!AF9) | ¬¬IF(ISBLANK('DPW3'!AG9),"",'DPW3'!AG9) | ¬¬IF(ISBLANK('DPW3'!AH9),"",'DPW3'!AH9) | ¬¬IF(ISBLANK('DPW3'!AI9),"",'DPW3'!AI9) | ¬¬IF(ISBLANK('DPW3'!AJ9),"",'DPW3'!AJ9) | ¬¬IF(ISBLANK('DPW3'!AK9),"",'DPW3'!AK9) | ¬¬IF(ISBLANK('DPW3'!AL9),"",'DPW3'!AL9) | ¬¬IF(ISBLANK('DPW3'!AM9),"",'DPW3'!AM9) | ¬¬IF(ISBLANK('DPW3'!AN9),"",'DPW3'!AN9) | ¬¬IF(ISBLANK('DPW3'!AO9),"",'DPW3'!AO9) | ¬¬IF(ISBLANK('DPW3'!AP9),"",'DPW3'!AP9) | ¬¬IF(ISBLANK('DPW3'!AQ9),"",'DPW3'!AQ9) | ¬¬IF(ISBLANK('DPW3'!AR9),"",'DPW3'!AR9) | ¬¬IF(ISBLANK('DPW3'!AS9),"",'DPW3'!AS9) | ¬¬IF(ISBLANK('DPW3'!AT9),"",'DPW3'!AT9) | ¬¬IF(ISBLANK('DPW3'!AU9),"",'DPW3'!AU9) | ¬¬IF(ISBLANK('DPW3'!AV9),"",'DPW3'!AV9) | ¬¬IF(ISBLANK('DPW3'!AW9),"",'DPW3'!AW9) | ¬¬IF(ISBLANK('DPW3'!AX9),"",'DPW3'!AX9) | ¬¬IF(ISBLANK('DPW3'!AY9),"",'DPW3'!AY9) | ¬¬IF(ISBLANK('DPW3'!AZ9),"",'DPW3'!AZ9)
¬¬A1385 | ¬¬IF(ISBLANK('DPW3'!OK9),"",'DPW3'!OK9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB9),"",'DPW3'!BB9) | ¬¬IF(ISBLANK('DPW3'!BC9),"",'DPW3'!BC9) | ¬¬IF(ISBLANK('DPW3'!BD9),"",'DPW3'!BD9) | ¬¬IF(ISBLANK('DPW3'!BE9),"",'DPW3'!BE9) | ¬¬IF(ISBLANK('DPW3'!BF9),"",'DPW3'!BF9) | ¬¬IF(ISBLANK('DPW3'!BG9),"",'DPW3'!BG9) | ¬¬IF(ISBLANK('DPW3'!BH9),"",'DPW3'!BH9) | ¬¬IF(ISBLANK('DPW3'!BI9),"",'DPW3'!BI9) | ¬¬IF(ISBLANK('DPW3'!BJ9),"",'DPW3'!BJ9) | ¬¬IF(ISBLANK('DPW3'!BK9),"",'DPW3'!BK9) | ¬¬IF(ISBLANK('DPW3'!BL9),"",'DPW3'!BL9) | ¬¬IF(ISBLANK('DPW3'!BM9),"",'DPW3'!BM9) | ¬¬IF(ISBLANK('DPW3'!BN9),"",'DPW3'!BN9) | ¬¬IF(ISBLANK('DPW3'!BO9),"",'DPW3'!BO9) | ¬¬IF(ISBLANK('DPW3'!BP9),"",'DPW3'!BP9) | ¬¬IF(ISBLANK('DPW3'!BQ9),"",'DPW3'!BQ9) | ¬¬IF(ISBLANK('DPW3'!BR9),"",'DPW3'!BR9) | ¬¬IF(ISBLANK('DPW3'!BS9),"",'DPW3'!BS9) | ¬¬IF(ISBLANK('DPW3'!BT9),"",'DPW3'!BT9) | ¬¬IF(ISBLANK('DPW3'!BU9),"",'DPW3'!BU9) | ¬¬IF(ISBLANK('DPW3'!BV9),"",'DPW3'!BV9) | ¬¬IF(ISBLANK('DPW3'!BW9),"",'DPW3'!BW9) | ¬¬IF(ISBLANK('DPW3'!BX9),"",'DPW3'!BX9) | ¬¬IF(ISBLANK('DPW3'!BY9),"",'DPW3'!BY9) | ¬¬IF(ISBLANK('DPW3'!BZ9),"",'DPW3'!BZ9) | ¬¬IF(ISBLANK('DPW3'!CA9),"",'DPW3'!CA9) | ¬¬IF(ISBLANK('DPW3'!CB9),"",'DPW3'!CB9) | ¬¬IF(ISBLANK('DPW3'!CC9),"",'DPW3'!CC9) | ¬¬IF(ISBLANK('DPW3'!CD9),"",'DPW3'!CD9) | ¬¬IF(ISBLANK('DPW3'!CE9),"",'DPW3'!CE9) | ¬¬IF(ISBLANK('DPW3'!CF9),"",'DPW3'!CF9) | ¬¬IF(ISBLANK('DPW3'!CG9),"",'DPW3'!CG9) | ¬¬IF(ISBLANK('DPW3'!CH9),"",'DPW3'!CH9) | ¬¬IF(ISBLANK('DPW3'!CI9),"",'DPW3'!CI9) | ¬¬IF(ISBLANK('DPW3'!CJ9),"",'DPW3'!CJ9) | ¬¬IF(ISBLANK('DPW3'!CK9),"",'DPW3'!CK9) | ¬¬IF(ISBLANK('DPW3'!CL9),"",'DPW3'!CL9) | ¬¬IF(ISBLANK('DPW3'!CM9),"",'DPW3'!CM9) | ¬¬IF(ISBLANK('DPW3'!CN9),"",'DPW3'!CN9) | ¬¬IF(ISBLANK('DPW3'!CO9),"",'DPW3'!CO9)
¬¬A1386 | ¬¬IF(ISBLANK('DPW3'!PZ9),"",'DPW3'!PZ9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ9),"",'DPW3'!CQ9) | ¬¬IF(ISBLANK('DPW3'!CR9),"",'DPW3'!CR9) | ¬¬IF(ISBLANK('DPW3'!CS9),"",'DPW3'!CS9) | ¬¬IF(ISBLANK('DPW3'!CT9),"",'DPW3'!CT9) | ¬¬IF(ISBLANK('DPW3'!CU9),"",'DPW3'!CU9) | ¬¬IF(ISBLANK('DPW3'!CV9),"",'DPW3'!CV9) | ¬¬IF(ISBLANK('DPW3'!CW9),"",'DPW3'!CW9) | ¬¬IF(ISBLANK('DPW3'!CX9),"",'DPW3'!CX9) | ¬¬IF(ISBLANK('DPW3'!CY9),"",'DPW3'!CY9) | ¬¬IF(ISBLANK('DPW3'!CZ9),"",'DPW3'!CZ9) | ¬¬IF(ISBLANK('DPW3'!DA9),"",'DPW3'!DA9) | ¬¬IF(ISBLANK('DPW3'!DB9),"",'DPW3'!DB9) | ¬¬IF(ISBLANK('DPW3'!DC9),"",'DPW3'!DC9) | ¬¬IF(ISBLANK('DPW3'!DD9),"",'DPW3'!DD9) | ¬¬IF(ISBLANK('DPW3'!DE9),"",'DPW3'!DE9) | ¬¬IF(ISBLANK('DPW3'!DF9),"",'DPW3'!DF9) | ¬¬IF(ISBLANK('DPW3'!DG9),"",'DPW3'!DG9) | ¬¬IF(ISBLANK('DPW3'!DH9),"",'DPW3'!DH9) | ¬¬IF(ISBLANK('DPW3'!DI9),"",'DPW3'!DI9) | ¬¬IF(ISBLANK('DPW3'!DJ9),"",'DPW3'!DJ9) | ¬¬IF(ISBLANK('DPW3'!DK9),"",'DPW3'!DK9) | ¬¬IF(ISBLANK('DPW3'!DL9),"",'DPW3'!DL9) | ¬¬IF(ISBLANK('DPW3'!DM9),"",'DPW3'!DM9) | ¬¬IF(ISBLANK('DPW3'!DN9),"",'DPW3'!DN9) | ¬¬IF(ISBLANK('DPW3'!DO9),"",'DPW3'!DO9) | ¬¬IF(ISBLANK('DPW3'!DP9),"",'DPW3'!DP9) | ¬¬IF(ISBLANK('DPW3'!DQ9),"",'DPW3'!DQ9) | ¬¬IF(ISBLANK('DPW3'!DR9),"",'DPW3'!DR9) | ¬¬IF(ISBLANK('DPW3'!DS9),"",'DPW3'!DS9) | ¬¬IF(ISBLANK('DPW3'!DT9),"",'DPW3'!DT9) | ¬¬IF(ISBLANK('DPW3'!DU9),"",'DPW3'!DU9) | ¬¬IF(ISBLANK('DPW3'!DV9),"",'DPW3'!DV9) | ¬¬IF(ISBLANK('DPW3'!DW9),"",'DPW3'!DW9) | ¬¬IF(ISBLANK('DPW3'!DX9),"",'DPW3'!DX9) | ¬¬IF(ISBLANK('DPW3'!DY9),"",'DPW3'!DY9) | ¬¬IF(ISBLANK('DPW3'!DZ9),"",'DPW3'!DZ9) | ¬¬IF(ISBLANK('DPW3'!EA9),"",'DPW3'!EA9) | ¬¬IF(ISBLANK('DPW3'!EB9),"",'DPW3'!EB9) | ¬¬IF(ISBLANK('DPW3'!EC9),"",'DPW3'!EC9) | ¬¬IF(ISBLANK('DPW3'!ED9),"",'DPW3'!ED9)
¬¬A1387 | ¬¬IF(ISBLANK('DPW3'!RO9),"",'DPW3'!RO9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF9),"",'DPW3'!EF9) | ¬¬IF(ISBLANK('DPW3'!EG9),"",'DPW3'!EG9) | ¬¬IF(ISBLANK('DPW3'!EH9),"",'DPW3'!EH9) | ¬¬IF(ISBLANK('DPW3'!EI9),"",'DPW3'!EI9) | ¬¬IF(ISBLANK('DPW3'!EJ9),"",'DPW3'!EJ9) | ¬¬IF(ISBLANK('DPW3'!EK9),"",'DPW3'!EK9) | ¬¬IF(ISBLANK('DPW3'!EL9),"",'DPW3'!EL9) | ¬¬IF(ISBLANK('DPW3'!EM9),"",'DPW3'!EM9) | ¬¬IF(ISBLANK('DPW3'!EN9),"",'DPW3'!EN9) | ¬¬IF(ISBLANK('DPW3'!EO9),"",'DPW3'!EO9) | ¬¬IF(ISBLANK('DPW3'!EP9),"",'DPW3'!EP9) | ¬¬IF(ISBLANK('DPW3'!EQ9),"",'DPW3'!EQ9) | ¬¬IF(ISBLANK('DPW3'!ER9),"",'DPW3'!ER9) | ¬¬IF(ISBLANK('DPW3'!ES9),"",'DPW3'!ES9) | ¬¬IF(ISBLANK('DPW3'!ET9),"",'DPW3'!ET9) | ¬¬IF(ISBLANK('DPW3'!EU9),"",'DPW3'!EU9) | ¬¬IF(ISBLANK('DPW3'!EV9),"",'DPW3'!EV9) | ¬¬IF(ISBLANK('DPW3'!EW9),"",'DPW3'!EW9) | ¬¬IF(ISBLANK('DPW3'!EX9),"",'DPW3'!EX9) | ¬¬IF(ISBLANK('DPW3'!EY9),"",'DPW3'!EY9) | ¬¬IF(ISBLANK('DPW3'!EZ9),"",'DPW3'!EZ9) | ¬¬IF(ISBLANK('DPW3'!FA9),"",'DPW3'!FA9) | ¬¬IF(ISBLANK('DPW3'!FB9),"",'DPW3'!FB9) | ¬¬IF(ISBLANK('DPW3'!FC9),"",'DPW3'!FC9) | ¬¬IF(ISBLANK('DPW3'!FD9),"",'DPW3'!FD9) | ¬¬IF(ISBLANK('DPW3'!FE9),"",'DPW3'!FE9) | ¬¬IF(ISBLANK('DPW3'!FF9),"",'DPW3'!FF9) | ¬¬IF(ISBLANK('DPW3'!FG9),"",'DPW3'!FG9) | ¬¬IF(ISBLANK('DPW3'!FH9),"",'DPW3'!FH9) | ¬¬IF(ISBLANK('DPW3'!FI9),"",'DPW3'!FI9) | ¬¬IF(ISBLANK('DPW3'!FJ9),"",'DPW3'!FJ9) | ¬¬IF(ISBLANK('DPW3'!FK9),"",'DPW3'!FK9) | ¬¬IF(ISBLANK('DPW3'!FL9),"",'DPW3'!FL9) | ¬¬IF(ISBLANK('DPW3'!FM9),"",'DPW3'!FM9) | ¬¬IF(ISBLANK('DPW3'!FN9),"",'DPW3'!FN9) | ¬¬IF(ISBLANK('DPW3'!FO9),"",'DPW3'!FO9) | ¬¬IF(ISBLANK('DPW3'!FP9),"",'DPW3'!FP9) | ¬¬IF(ISBLANK('DPW3'!FQ9),"",'DPW3'!FQ9) | ¬¬IF(ISBLANK('DPW3'!FR9),"",'DPW3'!FR9) | ¬¬IF(ISBLANK('DPW3'!FS9),"",'DPW3'!FS9)
¬¬A1388 | ¬¬IF(ISBLANK('DPW3'!TD9),"",'DPW3'!TD9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU9),"",'DPW3'!FU9) | ¬¬IF(ISBLANK('DPW3'!FV9),"",'DPW3'!FV9) | ¬¬IF(ISBLANK('DPW3'!FW9),"",'DPW3'!FW9) | ¬¬IF(ISBLANK('DPW3'!FX9),"",'DPW3'!FX9) | ¬¬IF(ISBLANK('DPW3'!FY9),"",'DPW3'!FY9) | ¬¬IF(ISBLANK('DPW3'!FZ9),"",'DPW3'!FZ9) | ¬¬IF(ISBLANK('DPW3'!GA9),"",'DPW3'!GA9) | ¬¬IF(ISBLANK('DPW3'!GB9),"",'DPW3'!GB9) | ¬¬IF(ISBLANK('DPW3'!GC9),"",'DPW3'!GC9) | ¬¬IF(ISBLANK('DPW3'!GD9),"",'DPW3'!GD9) | ¬¬IF(ISBLANK('DPW3'!GE9),"",'DPW3'!GE9) | ¬¬IF(ISBLANK('DPW3'!GF9),"",'DPW3'!GF9) | ¬¬IF(ISBLANK('DPW3'!GG9),"",'DPW3'!GG9) | ¬¬IF(ISBLANK('DPW3'!GH9),"",'DPW3'!GH9) | ¬¬IF(ISBLANK('DPW3'!GI9),"",'DPW3'!GI9) | ¬¬IF(ISBLANK('DPW3'!GJ9),"",'DPW3'!GJ9) | ¬¬IF(ISBLANK('DPW3'!GK9),"",'DPW3'!GK9) | ¬¬IF(ISBLANK('DPW3'!GL9),"",'DPW3'!GL9) | ¬¬IF(ISBLANK('DPW3'!GM9),"",'DPW3'!GM9) | ¬¬IF(ISBLANK('DPW3'!GN9),"",'DPW3'!GN9) | ¬¬IF(ISBLANK('DPW3'!GO9),"",'DPW3'!GO9) | ¬¬IF(ISBLANK('DPW3'!GP9),"",'DPW3'!GP9) | ¬¬IF(ISBLANK('DPW3'!GQ9),"",'DPW3'!GQ9) | ¬¬IF(ISBLANK('DPW3'!GR9),"",'DPW3'!GR9) | ¬¬IF(ISBLANK('DPW3'!GS9),"",'DPW3'!GS9) | ¬¬IF(ISBLANK('DPW3'!GT9),"",'DPW3'!GT9) | ¬¬IF(ISBLANK('DPW3'!GU9),"",'DPW3'!GU9) | ¬¬IF(ISBLANK('DPW3'!GV9),"",'DPW3'!GV9) | ¬¬IF(ISBLANK('DPW3'!GW9),"",'DPW3'!GW9) | ¬¬IF(ISBLANK('DPW3'!GX9),"",'DPW3'!GX9) | ¬¬IF(ISBLANK('DPW3'!GY9),"",'DPW3'!GY9) | ¬¬IF(ISBLANK('DPW3'!GZ9),"",'DPW3'!GZ9) | ¬¬IF(ISBLANK('DPW3'!HA9),"",'DPW3'!HA9) | ¬¬IF(ISBLANK('DPW3'!HB9),"",'DPW3'!HB9) | ¬¬IF(ISBLANK('DPW3'!HC9),"",'DPW3'!HC9) | ¬¬IF(ISBLANK('DPW3'!HD9),"",'DPW3'!HD9) | ¬¬IF(ISBLANK('DPW3'!HE9),"",'DPW3'!HE9) | ¬¬IF(ISBLANK('DPW3'!HF9),"",'DPW3'!HF9) | ¬¬IF(ISBLANK('DPW3'!HG9),"",'DPW3'!HG9) | ¬¬IF(ISBLANK('DPW3'!HH9),"",'DPW3'!HH9)
¬¬A1389 | ¬¬IF(ISBLANK('DPW3'!US9),"",'DPW3'!US9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ9),"",'DPW3'!HJ9) | ¬¬IF(ISBLANK('DPW3'!HK9),"",'DPW3'!HK9) | ¬¬IF(ISBLANK('DPW3'!HL9),"",'DPW3'!HL9) | ¬¬IF(ISBLANK('DPW3'!HM9),"",'DPW3'!HM9) | ¬¬IF(ISBLANK('DPW3'!HN9),"",'DPW3'!HN9) | ¬¬IF(ISBLANK('DPW3'!HO9),"",'DPW3'!HO9) | ¬¬IF(ISBLANK('DPW3'!HP9),"",'DPW3'!HP9) | ¬¬IF(ISBLANK('DPW3'!HQ9),"",'DPW3'!HQ9) | ¬¬IF(ISBLANK('DPW3'!HR9),"",'DPW3'!HR9) | ¬¬IF(ISBLANK('DPW3'!HS9),"",'DPW3'!HS9) | ¬¬IF(ISBLANK('DPW3'!HT9),"",'DPW3'!HT9) | ¬¬IF(ISBLANK('DPW3'!HU9),"",'DPW3'!HU9) | ¬¬IF(ISBLANK('DPW3'!HV9),"",'DPW3'!HV9) | ¬¬IF(ISBLANK('DPW3'!HW9),"",'DPW3'!HW9) | ¬¬IF(ISBLANK('DPW3'!HX9),"",'DPW3'!HX9) | ¬¬IF(ISBLANK('DPW3'!HY9),"",'DPW3'!HY9) | ¬¬IF(ISBLANK('DPW3'!HZ9),"",'DPW3'!HZ9) | ¬¬IF(ISBLANK('DPW3'!IA9),"",'DPW3'!IA9) | ¬¬IF(ISBLANK('DPW3'!IB9),"",'DPW3'!IB9) | ¬¬IF(ISBLANK('DPW3'!IC9),"",'DPW3'!IC9) | ¬¬IF(ISBLANK('DPW3'!ID9),"",'DPW3'!ID9) | ¬¬IF(ISBLANK('DPW3'!IE9),"",'DPW3'!IE9) | ¬¬IF(ISBLANK('DPW3'!IF9),"",'DPW3'!IF9) | ¬¬IF(ISBLANK('DPW3'!IG9),"",'DPW3'!IG9) | ¬¬IF(ISBLANK('DPW3'!IH9),"",'DPW3'!IH9) | ¬¬IF(ISBLANK('DPW3'!II9),"",'DPW3'!II9) | ¬¬IF(ISBLANK('DPW3'!IJ9),"",'DPW3'!IJ9) | ¬¬IF(ISBLANK('DPW3'!IK9),"",'DPW3'!IK9) | ¬¬IF(ISBLANK('DPW3'!IL9),"",'DPW3'!IL9) | ¬¬IF(ISBLANK('DPW3'!IM9),"",'DPW3'!IM9) | ¬¬IF(ISBLANK('DPW3'!IN9),"",'DPW3'!IN9) | ¬¬IF(ISBLANK('DPW3'!IO9),"",'DPW3'!IO9) | ¬¬IF(ISBLANK('DPW3'!IP9),"",'DPW3'!IP9) | ¬¬IF(ISBLANK('DPW3'!IQ9),"",'DPW3'!IQ9) | ¬¬IF(ISBLANK('DPW3'!IR9),"",'DPW3'!IR9) | ¬¬IF(ISBLANK('DPW3'!IS9),"",'DPW3'!IS9) | ¬¬IF(ISBLANK('DPW3'!IT9),"",'DPW3'!IT9) | ¬¬IF(ISBLANK('DPW3'!IU9),"",'DPW3'!IU9) | ¬¬IF(ISBLANK('DPW3'!IV9),"",'DPW3'!IV9) | ¬¬IF(ISBLANK('DPW3'!IW9),"",'DPW3'!IW9)
¬¬A1390 | ¬¬IF(ISBLANK('DPW3'!WH9),"",'DPW3'!WH9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY9),"",'DPW3'!IY9) | ¬¬IF(ISBLANK('DPW3'!IZ9),"",'DPW3'!IZ9) | ¬¬IF(ISBLANK('DPW3'!JA9),"",'DPW3'!JA9) | ¬¬IF(ISBLANK('DPW3'!JB9),"",'DPW3'!JB9) | ¬¬IF(ISBLANK('DPW3'!JC9),"",'DPW3'!JC9) | ¬¬IF(ISBLANK('DPW3'!JD9),"",'DPW3'!JD9) | ¬¬IF(ISBLANK('DPW3'!JE9),"",'DPW3'!JE9) | ¬¬IF(ISBLANK('DPW3'!JF9),"",'DPW3'!JF9) | ¬¬IF(ISBLANK('DPW3'!JG9),"",'DPW3'!JG9) | ¬¬IF(ISBLANK('DPW3'!JH9),"",'DPW3'!JH9) | ¬¬IF(ISBLANK('DPW3'!JI9),"",'DPW3'!JI9) | ¬¬IF(ISBLANK('DPW3'!JJ9),"",'DPW3'!JJ9) | ¬¬IF(ISBLANK('DPW3'!JK9),"",'DPW3'!JK9) | ¬¬IF(ISBLANK('DPW3'!JL9),"",'DPW3'!JL9) | ¬¬IF(ISBLANK('DPW3'!JM9),"",'DPW3'!JM9) | ¬¬IF(ISBLANK('DPW3'!JN9),"",'DPW3'!JN9) | ¬¬IF(ISBLANK('DPW3'!JO9),"",'DPW3'!JO9) | ¬¬IF(ISBLANK('DPW3'!JP9),"",'DPW3'!JP9) | ¬¬IF(ISBLANK('DPW3'!JQ9),"",'DPW3'!JQ9) | ¬¬IF(ISBLANK('DPW3'!JR9),"",'DPW3'!JR9) | ¬¬IF(ISBLANK('DPW3'!JS9),"",'DPW3'!JS9) | ¬¬IF(ISBLANK('DPW3'!JT9),"",'DPW3'!JT9) | ¬¬IF(ISBLANK('DPW3'!JU9),"",'DPW3'!JU9) | ¬¬IF(ISBLANK('DPW3'!JV9),"",'DPW3'!JV9) | ¬¬IF(ISBLANK('DPW3'!JW9),"",'DPW3'!JW9) | ¬¬IF(ISBLANK('DPW3'!JX9),"",'DPW3'!JX9) | ¬¬IF(ISBLANK('DPW3'!JY9),"",'DPW3'!JY9) | ¬¬IF(ISBLANK('DPW3'!JZ9),"",'DPW3'!JZ9) | ¬¬IF(ISBLANK('DPW3'!KA9),"",'DPW3'!KA9) | ¬¬IF(ISBLANK('DPW3'!KB9),"",'DPW3'!KB9) | ¬¬IF(ISBLANK('DPW3'!KC9),"",'DPW3'!KC9) | ¬¬IF(ISBLANK('DPW3'!KD9),"",'DPW3'!KD9) | ¬¬IF(ISBLANK('DPW3'!KE9),"",'DPW3'!KE9) | ¬¬IF(ISBLANK('DPW3'!KF9),"",'DPW3'!KF9) | ¬¬IF(ISBLANK('DPW3'!KG9),"",'DPW3'!KG9) | ¬¬IF(ISBLANK('DPW3'!KH9),"",'DPW3'!KH9) | ¬¬IF(ISBLANK('DPW3'!KI9),"",'DPW3'!KI9) | ¬¬IF(ISBLANK('DPW3'!KJ9),"",'DPW3'!KJ9) | ¬¬IF(ISBLANK('DPW3'!KK9),"",'DPW3'!KK9) | ¬¬IF(ISBLANK('DPW3'!KL9),"",'DPW3'!KL9)
¬¬A1391 | ¬¬IF(ISBLANK('DPW3'!XW9),"",'DPW3'!XW9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN9),"",'DPW3'!KN9) | ¬¬IF(ISBLANK('DPW3'!KO9),"",'DPW3'!KO9) | ¬¬IF(ISBLANK('DPW3'!KP9),"",'DPW3'!KP9) | ¬¬IF(ISBLANK('DPW3'!KQ9),"",'DPW3'!KQ9) | ¬¬IF(ISBLANK('DPW3'!KR9),"",'DPW3'!KR9) | ¬¬IF(ISBLANK('DPW3'!KS9),"",'DPW3'!KS9) | ¬¬IF(ISBLANK('DPW3'!KT9),"",'DPW3'!KT9) | ¬¬IF(ISBLANK('DPW3'!KU9),"",'DPW3'!KU9) | ¬¬IF(ISBLANK('DPW3'!KV9),"",'DPW3'!KV9) | ¬¬IF(ISBLANK('DPW3'!KW9),"",'DPW3'!KW9) | ¬¬IF(ISBLANK('DPW3'!KX9),"",'DPW3'!KX9) | ¬¬IF(ISBLANK('DPW3'!KY9),"",'DPW3'!KY9) | ¬¬IF(ISBLANK('DPW3'!KZ9),"",'DPW3'!KZ9) | ¬¬IF(ISBLANK('DPW3'!LA9),"",'DPW3'!LA9) | ¬¬IF(ISBLANK('DPW3'!LB9),"",'DPW3'!LB9) | ¬¬IF(ISBLANK('DPW3'!LC9),"",'DPW3'!LC9) | ¬¬IF(ISBLANK('DPW3'!LD9),"",'DPW3'!LD9) | ¬¬IF(ISBLANK('DPW3'!LE9),"",'DPW3'!LE9) | ¬¬IF(ISBLANK('DPW3'!LF9),"",'DPW3'!LF9) | ¬¬IF(ISBLANK('DPW3'!LG9),"",'DPW3'!LG9) | ¬¬IF(ISBLANK('DPW3'!LH9),"",'DPW3'!LH9) | ¬¬IF(ISBLANK('DPW3'!LI9),"",'DPW3'!LI9) | ¬¬IF(ISBLANK('DPW3'!LJ9),"",'DPW3'!LJ9) | ¬¬IF(ISBLANK('DPW3'!LK9),"",'DPW3'!LK9) | ¬¬IF(ISBLANK('DPW3'!LL9),"",'DPW3'!LL9) | ¬¬IF(ISBLANK('DPW3'!LM9),"",'DPW3'!LM9) | ¬¬IF(ISBLANK('DPW3'!LN9),"",'DPW3'!LN9) | ¬¬IF(ISBLANK('DPW3'!LO9),"",'DPW3'!LO9) | ¬¬IF(ISBLANK('DPW3'!LP9),"",'DPW3'!LP9) | ¬¬IF(ISBLANK('DPW3'!LQ9),"",'DPW3'!LQ9) | ¬¬IF(ISBLANK('DPW3'!LR9),"",'DPW3'!LR9) | ¬¬IF(ISBLANK('DPW3'!LS9),"",'DPW3'!LS9) | ¬¬IF(ISBLANK('DPW3'!LT9),"",'DPW3'!LT9) | ¬¬IF(ISBLANK('DPW3'!LU9),"",'DPW3'!LU9) | ¬¬IF(ISBLANK('DPW3'!LV9),"",'DPW3'!LV9) | ¬¬IF(ISBLANK('DPW3'!LW9),"",'DPW3'!LW9) | ¬¬IF(ISBLANK('DPW3'!LX9),"",'DPW3'!LX9) | ¬¬IF(ISBLANK('DPW3'!LY9),"",'DPW3'!LY9) | ¬¬IF(ISBLANK('DPW3'!LZ9),"",'DPW3'!LZ9) | ¬¬IF(ISBLANK('DPW3'!MA9),"",'DPW3'!MA9)
¬¬A1392 | ¬¬IF(ISBLANK('DPW3'!ZL9),"",'DPW3'!ZL9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MC9),"",'DPW3'!MC9)
¬¬A1393 | ¬¬IF(ISBLANK('DPW3'!ZM9),"",'DPW3'!ZM9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MD9),"",'DPW3'!MD9)
¬¬A1394 | ¬¬IF(ISBLANK('DPW3'!ZN9),"",'DPW3'!ZN9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!ML9),"",'DPW3'!ML9)
¬¬A1395 | ¬¬IF(ISBLANK('DPW3'!ZO9),"",'DPW3'!ZO9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MF9),"",'DPW3'!MF9)
¬¬A1396 | ¬¬IF(ISBLANK('DPW3'!ZP9),"",'DPW3'!ZP9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MG9),"",'DPW3'!MG9)
¬¬A1397 | ¬¬IF(ISBLANK('DPW3'!ZQ9),"",'DPW3'!ZQ9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MH9),"",'DPW3'!MH9)
¬¬A1398 | ¬¬IF(ISBLANK('DPW3'!ZR9),"",'DPW3'!ZR9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MI9),"",'DPW3'!MI9)
¬¬A1399 | ¬¬IF(ISBLANK('DPW3'!ZS9),"",'DPW3'!ZS9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ9),"",'DPW3'!MJ9)
¬¬A1400 | ¬¬IF(ISBLANK('DPW3'!ZT9),"",'DPW3'!ZT9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MK9),"",'DPW3'!MK9)
¬¬A1401 | ¬¬IF(ISBLANK('DPW3'!ZV9),"",'DPW3'!ZV9) | ¬¬'DPW3'!F9 & "," & 'DPW3'!G9 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H9),"",'DPW3'!H9) | Delta | ¬¬IF(ISBLANK('DPW3'!MM9),"",'DPW3'!MM9)
¬¬A1402 | ¬¬IF(ISBLANK('DPW3'!MT10),"",'DPW3'!MT10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!K10),"",'DPW3'!K10)
¬¬A1403 | ¬¬IF(ISBLANK('DPW3'!MV10),"",'DPW3'!MV10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M10),"",'DPW3'!M10) | ¬¬IF(ISBLANK('DPW3'!N10),"",'DPW3'!N10) | ¬¬IF(ISBLANK('DPW3'!O10),"",'DPW3'!O10) | ¬¬IF(ISBLANK('DPW3'!P10),"",'DPW3'!P10) | ¬¬IF(ISBLANK('DPW3'!Q10),"",'DPW3'!Q10) | ¬¬IF(ISBLANK('DPW3'!R10),"",'DPW3'!R10) | ¬¬IF(ISBLANK('DPW3'!S10),"",'DPW3'!S10) | ¬¬IF(ISBLANK('DPW3'!T10),"",'DPW3'!T10) | ¬¬IF(ISBLANK('DPW3'!U10),"",'DPW3'!U10) | ¬¬IF(ISBLANK('DPW3'!V10),"",'DPW3'!V10) | ¬¬IF(ISBLANK('DPW3'!W10),"",'DPW3'!W10) | ¬¬IF(ISBLANK('DPW3'!X10),"",'DPW3'!X10) | ¬¬IF(ISBLANK('DPW3'!Y10),"",'DPW3'!Y10) | ¬¬IF(ISBLANK('DPW3'!Z10),"",'DPW3'!Z10) | ¬¬IF(ISBLANK('DPW3'!AA10),"",'DPW3'!AA10) | ¬¬IF(ISBLANK('DPW3'!AB10),"",'DPW3'!AB10) | ¬¬IF(ISBLANK('DPW3'!AC10),"",'DPW3'!AC10) | ¬¬IF(ISBLANK('DPW3'!AD10),"",'DPW3'!AD10) | ¬¬IF(ISBLANK('DPW3'!AE10),"",'DPW3'!AE10) | ¬¬IF(ISBLANK('DPW3'!AF10),"",'DPW3'!AF10) | ¬¬IF(ISBLANK('DPW3'!AG10),"",'DPW3'!AG10) | ¬¬IF(ISBLANK('DPW3'!AH10),"",'DPW3'!AH10) | ¬¬IF(ISBLANK('DPW3'!AI10),"",'DPW3'!AI10) | ¬¬IF(ISBLANK('DPW3'!AJ10),"",'DPW3'!AJ10) | ¬¬IF(ISBLANK('DPW3'!AK10),"",'DPW3'!AK10) | ¬¬IF(ISBLANK('DPW3'!AL10),"",'DPW3'!AL10) | ¬¬IF(ISBLANK('DPW3'!AM10),"",'DPW3'!AM10) | ¬¬IF(ISBLANK('DPW3'!AN10),"",'DPW3'!AN10) | ¬¬IF(ISBLANK('DPW3'!AO10),"",'DPW3'!AO10) | ¬¬IF(ISBLANK('DPW3'!AP10),"",'DPW3'!AP10) | ¬¬IF(ISBLANK('DPW3'!AQ10),"",'DPW3'!AQ10) | ¬¬IF(ISBLANK('DPW3'!AR10),"",'DPW3'!AR10) | ¬¬IF(ISBLANK('DPW3'!AS10),"",'DPW3'!AS10) | ¬¬IF(ISBLANK('DPW3'!AT10),"",'DPW3'!AT10) | ¬¬IF(ISBLANK('DPW3'!AU10),"",'DPW3'!AU10) | ¬¬IF(ISBLANK('DPW3'!AV10),"",'DPW3'!AV10) | ¬¬IF(ISBLANK('DPW3'!AW10),"",'DPW3'!AW10) | ¬¬IF(ISBLANK('DPW3'!AX10),"",'DPW3'!AX10) | ¬¬IF(ISBLANK('DPW3'!AY10),"",'DPW3'!AY10) | ¬¬IF(ISBLANK('DPW3'!AZ10),"",'DPW3'!AZ10)
¬¬A1404 | ¬¬IF(ISBLANK('DPW3'!OK10),"",'DPW3'!OK10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB10),"",'DPW3'!BB10) | ¬¬IF(ISBLANK('DPW3'!BC10),"",'DPW3'!BC10) | ¬¬IF(ISBLANK('DPW3'!BD10),"",'DPW3'!BD10) | ¬¬IF(ISBLANK('DPW3'!BE10),"",'DPW3'!BE10) | ¬¬IF(ISBLANK('DPW3'!BF10),"",'DPW3'!BF10) | ¬¬IF(ISBLANK('DPW3'!BG10),"",'DPW3'!BG10) | ¬¬IF(ISBLANK('DPW3'!BH10),"",'DPW3'!BH10) | ¬¬IF(ISBLANK('DPW3'!BI10),"",'DPW3'!BI10) | ¬¬IF(ISBLANK('DPW3'!BJ10),"",'DPW3'!BJ10) | ¬¬IF(ISBLANK('DPW3'!BK10),"",'DPW3'!BK10) | ¬¬IF(ISBLANK('DPW3'!BL10),"",'DPW3'!BL10) | ¬¬IF(ISBLANK('DPW3'!BM10),"",'DPW3'!BM10) | ¬¬IF(ISBLANK('DPW3'!BN10),"",'DPW3'!BN10) | ¬¬IF(ISBLANK('DPW3'!BO10),"",'DPW3'!BO10) | ¬¬IF(ISBLANK('DPW3'!BP10),"",'DPW3'!BP10) | ¬¬IF(ISBLANK('DPW3'!BQ10),"",'DPW3'!BQ10) | ¬¬IF(ISBLANK('DPW3'!BR10),"",'DPW3'!BR10) | ¬¬IF(ISBLANK('DPW3'!BS10),"",'DPW3'!BS10) | ¬¬IF(ISBLANK('DPW3'!BT10),"",'DPW3'!BT10) | ¬¬IF(ISBLANK('DPW3'!BU10),"",'DPW3'!BU10) | ¬¬IF(ISBLANK('DPW3'!BV10),"",'DPW3'!BV10) | ¬¬IF(ISBLANK('DPW3'!BW10),"",'DPW3'!BW10) | ¬¬IF(ISBLANK('DPW3'!BX10),"",'DPW3'!BX10) | ¬¬IF(ISBLANK('DPW3'!BY10),"",'DPW3'!BY10) | ¬¬IF(ISBLANK('DPW3'!BZ10),"",'DPW3'!BZ10) | ¬¬IF(ISBLANK('DPW3'!CA10),"",'DPW3'!CA10) | ¬¬IF(ISBLANK('DPW3'!CB10),"",'DPW3'!CB10) | ¬¬IF(ISBLANK('DPW3'!CC10),"",'DPW3'!CC10) | ¬¬IF(ISBLANK('DPW3'!CD10),"",'DPW3'!CD10) | ¬¬IF(ISBLANK('DPW3'!CE10),"",'DPW3'!CE10) | ¬¬IF(ISBLANK('DPW3'!CF10),"",'DPW3'!CF10) | ¬¬IF(ISBLANK('DPW3'!CG10),"",'DPW3'!CG10) | ¬¬IF(ISBLANK('DPW3'!CH10),"",'DPW3'!CH10) | ¬¬IF(ISBLANK('DPW3'!CI10),"",'DPW3'!CI10) | ¬¬IF(ISBLANK('DPW3'!CJ10),"",'DPW3'!CJ10) | ¬¬IF(ISBLANK('DPW3'!CK10),"",'DPW3'!CK10) | ¬¬IF(ISBLANK('DPW3'!CL10),"",'DPW3'!CL10) | ¬¬IF(ISBLANK('DPW3'!CM10),"",'DPW3'!CM10) | ¬¬IF(ISBLANK('DPW3'!CN10),"",'DPW3'!CN10) | ¬¬IF(ISBLANK('DPW3'!CO10),"",'DPW3'!CO10)
¬¬A1405 | ¬¬IF(ISBLANK('DPW3'!PZ10),"",'DPW3'!PZ10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ10),"",'DPW3'!CQ10) | ¬¬IF(ISBLANK('DPW3'!CR10),"",'DPW3'!CR10) | ¬¬IF(ISBLANK('DPW3'!CS10),"",'DPW3'!CS10) | ¬¬IF(ISBLANK('DPW3'!CT10),"",'DPW3'!CT10) | ¬¬IF(ISBLANK('DPW3'!CU10),"",'DPW3'!CU10) | ¬¬IF(ISBLANK('DPW3'!CV10),"",'DPW3'!CV10) | ¬¬IF(ISBLANK('DPW3'!CW10),"",'DPW3'!CW10) | ¬¬IF(ISBLANK('DPW3'!CX10),"",'DPW3'!CX10) | ¬¬IF(ISBLANK('DPW3'!CY10),"",'DPW3'!CY10) | ¬¬IF(ISBLANK('DPW3'!CZ10),"",'DPW3'!CZ10) | ¬¬IF(ISBLANK('DPW3'!DA10),"",'DPW3'!DA10) | ¬¬IF(ISBLANK('DPW3'!DB10),"",'DPW3'!DB10) | ¬¬IF(ISBLANK('DPW3'!DC10),"",'DPW3'!DC10) | ¬¬IF(ISBLANK('DPW3'!DD10),"",'DPW3'!DD10) | ¬¬IF(ISBLANK('DPW3'!DE10),"",'DPW3'!DE10) | ¬¬IF(ISBLANK('DPW3'!DF10),"",'DPW3'!DF10) | ¬¬IF(ISBLANK('DPW3'!DG10),"",'DPW3'!DG10) | ¬¬IF(ISBLANK('DPW3'!DH10),"",'DPW3'!DH10) | ¬¬IF(ISBLANK('DPW3'!DI10),"",'DPW3'!DI10) | ¬¬IF(ISBLANK('DPW3'!DJ10),"",'DPW3'!DJ10) | ¬¬IF(ISBLANK('DPW3'!DK10),"",'DPW3'!DK10) | ¬¬IF(ISBLANK('DPW3'!DL10),"",'DPW3'!DL10) | ¬¬IF(ISBLANK('DPW3'!DM10),"",'DPW3'!DM10) | ¬¬IF(ISBLANK('DPW3'!DN10),"",'DPW3'!DN10) | ¬¬IF(ISBLANK('DPW3'!DO10),"",'DPW3'!DO10) | ¬¬IF(ISBLANK('DPW3'!DP10),"",'DPW3'!DP10) | ¬¬IF(ISBLANK('DPW3'!DQ10),"",'DPW3'!DQ10) | ¬¬IF(ISBLANK('DPW3'!DR10),"",'DPW3'!DR10) | ¬¬IF(ISBLANK('DPW3'!DS10),"",'DPW3'!DS10) | ¬¬IF(ISBLANK('DPW3'!DT10),"",'DPW3'!DT10) | ¬¬IF(ISBLANK('DPW3'!DU10),"",'DPW3'!DU10) | ¬¬IF(ISBLANK('DPW3'!DV10),"",'DPW3'!DV10) | ¬¬IF(ISBLANK('DPW3'!DW10),"",'DPW3'!DW10) | ¬¬IF(ISBLANK('DPW3'!DX10),"",'DPW3'!DX10) | ¬¬IF(ISBLANK('DPW3'!DY10),"",'DPW3'!DY10) | ¬¬IF(ISBLANK('DPW3'!DZ10),"",'DPW3'!DZ10) | ¬¬IF(ISBLANK('DPW3'!EA10),"",'DPW3'!EA10) | ¬¬IF(ISBLANK('DPW3'!EB10),"",'DPW3'!EB10) | ¬¬IF(ISBLANK('DPW3'!EC10),"",'DPW3'!EC10) | ¬¬IF(ISBLANK('DPW3'!ED10),"",'DPW3'!ED10)
¬¬A1406 | ¬¬IF(ISBLANK('DPW3'!RO10),"",'DPW3'!RO10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF10),"",'DPW3'!EF10) | ¬¬IF(ISBLANK('DPW3'!EG10),"",'DPW3'!EG10) | ¬¬IF(ISBLANK('DPW3'!EH10),"",'DPW3'!EH10) | ¬¬IF(ISBLANK('DPW3'!EI10),"",'DPW3'!EI10) | ¬¬IF(ISBLANK('DPW3'!EJ10),"",'DPW3'!EJ10) | ¬¬IF(ISBLANK('DPW3'!EK10),"",'DPW3'!EK10) | ¬¬IF(ISBLANK('DPW3'!EL10),"",'DPW3'!EL10) | ¬¬IF(ISBLANK('DPW3'!EM10),"",'DPW3'!EM10) | ¬¬IF(ISBLANK('DPW3'!EN10),"",'DPW3'!EN10) | ¬¬IF(ISBLANK('DPW3'!EO10),"",'DPW3'!EO10) | ¬¬IF(ISBLANK('DPW3'!EP10),"",'DPW3'!EP10) | ¬¬IF(ISBLANK('DPW3'!EQ10),"",'DPW3'!EQ10) | ¬¬IF(ISBLANK('DPW3'!ER10),"",'DPW3'!ER10) | ¬¬IF(ISBLANK('DPW3'!ES10),"",'DPW3'!ES10) | ¬¬IF(ISBLANK('DPW3'!ET10),"",'DPW3'!ET10) | ¬¬IF(ISBLANK('DPW3'!EU10),"",'DPW3'!EU10) | ¬¬IF(ISBLANK('DPW3'!EV10),"",'DPW3'!EV10) | ¬¬IF(ISBLANK('DPW3'!EW10),"",'DPW3'!EW10) | ¬¬IF(ISBLANK('DPW3'!EX10),"",'DPW3'!EX10) | ¬¬IF(ISBLANK('DPW3'!EY10),"",'DPW3'!EY10) | ¬¬IF(ISBLANK('DPW3'!EZ10),"",'DPW3'!EZ10) | ¬¬IF(ISBLANK('DPW3'!FA10),"",'DPW3'!FA10) | ¬¬IF(ISBLANK('DPW3'!FB10),"",'DPW3'!FB10) | ¬¬IF(ISBLANK('DPW3'!FC10),"",'DPW3'!FC10) | ¬¬IF(ISBLANK('DPW3'!FD10),"",'DPW3'!FD10) | ¬¬IF(ISBLANK('DPW3'!FE10),"",'DPW3'!FE10) | ¬¬IF(ISBLANK('DPW3'!FF10),"",'DPW3'!FF10) | ¬¬IF(ISBLANK('DPW3'!FG10),"",'DPW3'!FG10) | ¬¬IF(ISBLANK('DPW3'!FH10),"",'DPW3'!FH10) | ¬¬IF(ISBLANK('DPW3'!FI10),"",'DPW3'!FI10) | ¬¬IF(ISBLANK('DPW3'!FJ10),"",'DPW3'!FJ10) | ¬¬IF(ISBLANK('DPW3'!FK10),"",'DPW3'!FK10) | ¬¬IF(ISBLANK('DPW3'!FL10),"",'DPW3'!FL10) | ¬¬IF(ISBLANK('DPW3'!FM10),"",'DPW3'!FM10) | ¬¬IF(ISBLANK('DPW3'!FN10),"",'DPW3'!FN10) | ¬¬IF(ISBLANK('DPW3'!FO10),"",'DPW3'!FO10) | ¬¬IF(ISBLANK('DPW3'!FP10),"",'DPW3'!FP10) | ¬¬IF(ISBLANK('DPW3'!FQ10),"",'DPW3'!FQ10) | ¬¬IF(ISBLANK('DPW3'!FR10),"",'DPW3'!FR10) | ¬¬IF(ISBLANK('DPW3'!FS10),"",'DPW3'!FS10)
¬¬A1407 | ¬¬IF(ISBLANK('DPW3'!TD10),"",'DPW3'!TD10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU10),"",'DPW3'!FU10) | ¬¬IF(ISBLANK('DPW3'!FV10),"",'DPW3'!FV10) | ¬¬IF(ISBLANK('DPW3'!FW10),"",'DPW3'!FW10) | ¬¬IF(ISBLANK('DPW3'!FX10),"",'DPW3'!FX10) | ¬¬IF(ISBLANK('DPW3'!FY10),"",'DPW3'!FY10) | ¬¬IF(ISBLANK('DPW3'!FZ10),"",'DPW3'!FZ10) | ¬¬IF(ISBLANK('DPW3'!GA10),"",'DPW3'!GA10) | ¬¬IF(ISBLANK('DPW3'!GB10),"",'DPW3'!GB10) | ¬¬IF(ISBLANK('DPW3'!GC10),"",'DPW3'!GC10) | ¬¬IF(ISBLANK('DPW3'!GD10),"",'DPW3'!GD10) | ¬¬IF(ISBLANK('DPW3'!GE10),"",'DPW3'!GE10) | ¬¬IF(ISBLANK('DPW3'!GF10),"",'DPW3'!GF10) | ¬¬IF(ISBLANK('DPW3'!GG10),"",'DPW3'!GG10) | ¬¬IF(ISBLANK('DPW3'!GH10),"",'DPW3'!GH10) | ¬¬IF(ISBLANK('DPW3'!GI10),"",'DPW3'!GI10) | ¬¬IF(ISBLANK('DPW3'!GJ10),"",'DPW3'!GJ10) | ¬¬IF(ISBLANK('DPW3'!GK10),"",'DPW3'!GK10) | ¬¬IF(ISBLANK('DPW3'!GL10),"",'DPW3'!GL10) | ¬¬IF(ISBLANK('DPW3'!GM10),"",'DPW3'!GM10) | ¬¬IF(ISBLANK('DPW3'!GN10),"",'DPW3'!GN10) | ¬¬IF(ISBLANK('DPW3'!GO10),"",'DPW3'!GO10) | ¬¬IF(ISBLANK('DPW3'!GP10),"",'DPW3'!GP10) | ¬¬IF(ISBLANK('DPW3'!GQ10),"",'DPW3'!GQ10) | ¬¬IF(ISBLANK('DPW3'!GR10),"",'DPW3'!GR10) | ¬¬IF(ISBLANK('DPW3'!GS10),"",'DPW3'!GS10) | ¬¬IF(ISBLANK('DPW3'!GT10),"",'DPW3'!GT10) | ¬¬IF(ISBLANK('DPW3'!GU10),"",'DPW3'!GU10) | ¬¬IF(ISBLANK('DPW3'!GV10),"",'DPW3'!GV10) | ¬¬IF(ISBLANK('DPW3'!GW10),"",'DPW3'!GW10) | ¬¬IF(ISBLANK('DPW3'!GX10),"",'DPW3'!GX10) | ¬¬IF(ISBLANK('DPW3'!GY10),"",'DPW3'!GY10) | ¬¬IF(ISBLANK('DPW3'!GZ10),"",'DPW3'!GZ10) | ¬¬IF(ISBLANK('DPW3'!HA10),"",'DPW3'!HA10) | ¬¬IF(ISBLANK('DPW3'!HB10),"",'DPW3'!HB10) | ¬¬IF(ISBLANK('DPW3'!HC10),"",'DPW3'!HC10) | ¬¬IF(ISBLANK('DPW3'!HD10),"",'DPW3'!HD10) | ¬¬IF(ISBLANK('DPW3'!HE10),"",'DPW3'!HE10) | ¬¬IF(ISBLANK('DPW3'!HF10),"",'DPW3'!HF10) | ¬¬IF(ISBLANK('DPW3'!HG10),"",'DPW3'!HG10) | ¬¬IF(ISBLANK('DPW3'!HH10),"",'DPW3'!HH10)
¬¬A1408 | ¬¬IF(ISBLANK('DPW3'!US10),"",'DPW3'!US10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ10),"",'DPW3'!HJ10) | ¬¬IF(ISBLANK('DPW3'!HK10),"",'DPW3'!HK10) | ¬¬IF(ISBLANK('DPW3'!HL10),"",'DPW3'!HL10) | ¬¬IF(ISBLANK('DPW3'!HM10),"",'DPW3'!HM10) | ¬¬IF(ISBLANK('DPW3'!HN10),"",'DPW3'!HN10) | ¬¬IF(ISBLANK('DPW3'!HO10),"",'DPW3'!HO10) | ¬¬IF(ISBLANK('DPW3'!HP10),"",'DPW3'!HP10) | ¬¬IF(ISBLANK('DPW3'!HQ10),"",'DPW3'!HQ10) | ¬¬IF(ISBLANK('DPW3'!HR10),"",'DPW3'!HR10) | ¬¬IF(ISBLANK('DPW3'!HS10),"",'DPW3'!HS10) | ¬¬IF(ISBLANK('DPW3'!HT10),"",'DPW3'!HT10) | ¬¬IF(ISBLANK('DPW3'!HU10),"",'DPW3'!HU10) | ¬¬IF(ISBLANK('DPW3'!HV10),"",'DPW3'!HV10) | ¬¬IF(ISBLANK('DPW3'!HW10),"",'DPW3'!HW10) | ¬¬IF(ISBLANK('DPW3'!HX10),"",'DPW3'!HX10) | ¬¬IF(ISBLANK('DPW3'!HY10),"",'DPW3'!HY10) | ¬¬IF(ISBLANK('DPW3'!HZ10),"",'DPW3'!HZ10) | ¬¬IF(ISBLANK('DPW3'!IA10),"",'DPW3'!IA10) | ¬¬IF(ISBLANK('DPW3'!IB10),"",'DPW3'!IB10) | ¬¬IF(ISBLANK('DPW3'!IC10),"",'DPW3'!IC10) | ¬¬IF(ISBLANK('DPW3'!ID10),"",'DPW3'!ID10) | ¬¬IF(ISBLANK('DPW3'!IE10),"",'DPW3'!IE10) | ¬¬IF(ISBLANK('DPW3'!IF10),"",'DPW3'!IF10) | ¬¬IF(ISBLANK('DPW3'!IG10),"",'DPW3'!IG10) | ¬¬IF(ISBLANK('DPW3'!IH10),"",'DPW3'!IH10) | ¬¬IF(ISBLANK('DPW3'!II10),"",'DPW3'!II10) | ¬¬IF(ISBLANK('DPW3'!IJ10),"",'DPW3'!IJ10) | ¬¬IF(ISBLANK('DPW3'!IK10),"",'DPW3'!IK10) | ¬¬IF(ISBLANK('DPW3'!IL10),"",'DPW3'!IL10) | ¬¬IF(ISBLANK('DPW3'!IM10),"",'DPW3'!IM10) | ¬¬IF(ISBLANK('DPW3'!IN10),"",'DPW3'!IN10) | ¬¬IF(ISBLANK('DPW3'!IO10),"",'DPW3'!IO10) | ¬¬IF(ISBLANK('DPW3'!IP10),"",'DPW3'!IP10) | ¬¬IF(ISBLANK('DPW3'!IQ10),"",'DPW3'!IQ10) | ¬¬IF(ISBLANK('DPW3'!IR10),"",'DPW3'!IR10) | ¬¬IF(ISBLANK('DPW3'!IS10),"",'DPW3'!IS10) | ¬¬IF(ISBLANK('DPW3'!IT10),"",'DPW3'!IT10) | ¬¬IF(ISBLANK('DPW3'!IU10),"",'DPW3'!IU10) | ¬¬IF(ISBLANK('DPW3'!IV10),"",'DPW3'!IV10) | ¬¬IF(ISBLANK('DPW3'!IW10),"",'DPW3'!IW10)
¬¬A1409 | ¬¬IF(ISBLANK('DPW3'!WH10),"",'DPW3'!WH10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY10),"",'DPW3'!IY10) | ¬¬IF(ISBLANK('DPW3'!IZ10),"",'DPW3'!IZ10) | ¬¬IF(ISBLANK('DPW3'!JA10),"",'DPW3'!JA10) | ¬¬IF(ISBLANK('DPW3'!JB10),"",'DPW3'!JB10) | ¬¬IF(ISBLANK('DPW3'!JC10),"",'DPW3'!JC10) | ¬¬IF(ISBLANK('DPW3'!JD10),"",'DPW3'!JD10) | ¬¬IF(ISBLANK('DPW3'!JE10),"",'DPW3'!JE10) | ¬¬IF(ISBLANK('DPW3'!JF10),"",'DPW3'!JF10) | ¬¬IF(ISBLANK('DPW3'!JG10),"",'DPW3'!JG10) | ¬¬IF(ISBLANK('DPW3'!JH10),"",'DPW3'!JH10) | ¬¬IF(ISBLANK('DPW3'!JI10),"",'DPW3'!JI10) | ¬¬IF(ISBLANK('DPW3'!JJ10),"",'DPW3'!JJ10) | ¬¬IF(ISBLANK('DPW3'!JK10),"",'DPW3'!JK10) | ¬¬IF(ISBLANK('DPW3'!JL10),"",'DPW3'!JL10) | ¬¬IF(ISBLANK('DPW3'!JM10),"",'DPW3'!JM10) | ¬¬IF(ISBLANK('DPW3'!JN10),"",'DPW3'!JN10) | ¬¬IF(ISBLANK('DPW3'!JO10),"",'DPW3'!JO10) | ¬¬IF(ISBLANK('DPW3'!JP10),"",'DPW3'!JP10) | ¬¬IF(ISBLANK('DPW3'!JQ10),"",'DPW3'!JQ10) | ¬¬IF(ISBLANK('DPW3'!JR10),"",'DPW3'!JR10) | ¬¬IF(ISBLANK('DPW3'!JS10),"",'DPW3'!JS10) | ¬¬IF(ISBLANK('DPW3'!JT10),"",'DPW3'!JT10) | ¬¬IF(ISBLANK('DPW3'!JU10),"",'DPW3'!JU10) | ¬¬IF(ISBLANK('DPW3'!JV10),"",'DPW3'!JV10) | ¬¬IF(ISBLANK('DPW3'!JW10),"",'DPW3'!JW10) | ¬¬IF(ISBLANK('DPW3'!JX10),"",'DPW3'!JX10) | ¬¬IF(ISBLANK('DPW3'!JY10),"",'DPW3'!JY10) | ¬¬IF(ISBLANK('DPW3'!JZ10),"",'DPW3'!JZ10) | ¬¬IF(ISBLANK('DPW3'!KA10),"",'DPW3'!KA10) | ¬¬IF(ISBLANK('DPW3'!KB10),"",'DPW3'!KB10) | ¬¬IF(ISBLANK('DPW3'!KC10),"",'DPW3'!KC10) | ¬¬IF(ISBLANK('DPW3'!KD10),"",'DPW3'!KD10) | ¬¬IF(ISBLANK('DPW3'!KE10),"",'DPW3'!KE10) | ¬¬IF(ISBLANK('DPW3'!KF10),"",'DPW3'!KF10) | ¬¬IF(ISBLANK('DPW3'!KG10),"",'DPW3'!KG10) | ¬¬IF(ISBLANK('DPW3'!KH10),"",'DPW3'!KH10) | ¬¬IF(ISBLANK('DPW3'!KI10),"",'DPW3'!KI10) | ¬¬IF(ISBLANK('DPW3'!KJ10),"",'DPW3'!KJ10) | ¬¬IF(ISBLANK('DPW3'!KK10),"",'DPW3'!KK10) | ¬¬IF(ISBLANK('DPW3'!KL10),"",'DPW3'!KL10)
¬¬A1410 | ¬¬IF(ISBLANK('DPW3'!XW10),"",'DPW3'!XW10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN10),"",'DPW3'!KN10) | ¬¬IF(ISBLANK('DPW3'!KO10),"",'DPW3'!KO10) | ¬¬IF(ISBLANK('DPW3'!KP10),"",'DPW3'!KP10) | ¬¬IF(ISBLANK('DPW3'!KQ10),"",'DPW3'!KQ10) | ¬¬IF(ISBLANK('DPW3'!KR10),"",'DPW3'!KR10) | ¬¬IF(ISBLANK('DPW3'!KS10),"",'DPW3'!KS10) | ¬¬IF(ISBLANK('DPW3'!KT10),"",'DPW3'!KT10) | ¬¬IF(ISBLANK('DPW3'!KU10),"",'DPW3'!KU10) | ¬¬IF(ISBLANK('DPW3'!KV10),"",'DPW3'!KV10) | ¬¬IF(ISBLANK('DPW3'!KW10),"",'DPW3'!KW10) | ¬¬IF(ISBLANK('DPW3'!KX10),"",'DPW3'!KX10) | ¬¬IF(ISBLANK('DPW3'!KY10),"",'DPW3'!KY10) | ¬¬IF(ISBLANK('DPW3'!KZ10),"",'DPW3'!KZ10) | ¬¬IF(ISBLANK('DPW3'!LA10),"",'DPW3'!LA10) | ¬¬IF(ISBLANK('DPW3'!LB10),"",'DPW3'!LB10) | ¬¬IF(ISBLANK('DPW3'!LC10),"",'DPW3'!LC10) | ¬¬IF(ISBLANK('DPW3'!LD10),"",'DPW3'!LD10) | ¬¬IF(ISBLANK('DPW3'!LE10),"",'DPW3'!LE10) | ¬¬IF(ISBLANK('DPW3'!LF10),"",'DPW3'!LF10) | ¬¬IF(ISBLANK('DPW3'!LG10),"",'DPW3'!LG10) | ¬¬IF(ISBLANK('DPW3'!LH10),"",'DPW3'!LH10) | ¬¬IF(ISBLANK('DPW3'!LI10),"",'DPW3'!LI10) | ¬¬IF(ISBLANK('DPW3'!LJ10),"",'DPW3'!LJ10) | ¬¬IF(ISBLANK('DPW3'!LK10),"",'DPW3'!LK10) | ¬¬IF(ISBLANK('DPW3'!LL10),"",'DPW3'!LL10) | ¬¬IF(ISBLANK('DPW3'!LM10),"",'DPW3'!LM10) | ¬¬IF(ISBLANK('DPW3'!LN10),"",'DPW3'!LN10) | ¬¬IF(ISBLANK('DPW3'!LO10),"",'DPW3'!LO10) | ¬¬IF(ISBLANK('DPW3'!LP10),"",'DPW3'!LP10) | ¬¬IF(ISBLANK('DPW3'!LQ10),"",'DPW3'!LQ10) | ¬¬IF(ISBLANK('DPW3'!LR10),"",'DPW3'!LR10) | ¬¬IF(ISBLANK('DPW3'!LS10),"",'DPW3'!LS10) | ¬¬IF(ISBLANK('DPW3'!LT10),"",'DPW3'!LT10) | ¬¬IF(ISBLANK('DPW3'!LU10),"",'DPW3'!LU10) | ¬¬IF(ISBLANK('DPW3'!LV10),"",'DPW3'!LV10) | ¬¬IF(ISBLANK('DPW3'!LW10),"",'DPW3'!LW10) | ¬¬IF(ISBLANK('DPW3'!LX10),"",'DPW3'!LX10) | ¬¬IF(ISBLANK('DPW3'!LY10),"",'DPW3'!LY10) | ¬¬IF(ISBLANK('DPW3'!LZ10),"",'DPW3'!LZ10) | ¬¬IF(ISBLANK('DPW3'!MA10),"",'DPW3'!MA10)
¬¬A1411 | ¬¬IF(ISBLANK('DPW3'!ZL10),"",'DPW3'!ZL10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MC10),"",'DPW3'!MC10)
¬¬A1412 | ¬¬IF(ISBLANK('DPW3'!ZM10),"",'DPW3'!ZM10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MD10),"",'DPW3'!MD10)
¬¬A1413 | ¬¬IF(ISBLANK('DPW3'!ZN10),"",'DPW3'!ZN10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!ML10),"",'DPW3'!ML10)
¬¬A1414 | ¬¬IF(ISBLANK('DPW3'!ZO10),"",'DPW3'!ZO10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MF10),"",'DPW3'!MF10)
¬¬A1415 | ¬¬IF(ISBLANK('DPW3'!ZP10),"",'DPW3'!ZP10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MG10),"",'DPW3'!MG10)
¬¬A1416 | ¬¬IF(ISBLANK('DPW3'!ZQ10),"",'DPW3'!ZQ10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MH10),"",'DPW3'!MH10)
¬¬A1417 | ¬¬IF(ISBLANK('DPW3'!ZR10),"",'DPW3'!ZR10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MI10),"",'DPW3'!MI10)
¬¬A1418 | ¬¬IF(ISBLANK('DPW3'!ZS10),"",'DPW3'!ZS10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ10),"",'DPW3'!MJ10)
¬¬A1419 | ¬¬IF(ISBLANK('DPW3'!ZT10),"",'DPW3'!ZT10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MK10),"",'DPW3'!MK10)
¬¬A1420 | ¬¬IF(ISBLANK('DPW3'!ZV10),"",'DPW3'!ZV10) | ¬¬'DPW3'!F10 & "," & 'DPW3'!G10 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H10),"",'DPW3'!H10) | Delta | ¬¬IF(ISBLANK('DPW3'!MM10),"",'DPW3'!MM10)
¬¬A1421 | ¬¬IF(ISBLANK('DPW3'!MT11),"",'DPW3'!MT11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!K11),"",'DPW3'!K11)
¬¬A1422 | ¬¬IF(ISBLANK('DPW3'!MV11),"",'DPW3'!MV11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M11),"",'DPW3'!M11) | ¬¬IF(ISBLANK('DPW3'!N11),"",'DPW3'!N11) | ¬¬IF(ISBLANK('DPW3'!O11),"",'DPW3'!O11) | ¬¬IF(ISBLANK('DPW3'!P11),"",'DPW3'!P11) | ¬¬IF(ISBLANK('DPW3'!Q11),"",'DPW3'!Q11) | ¬¬IF(ISBLANK('DPW3'!R11),"",'DPW3'!R11) | ¬¬IF(ISBLANK('DPW3'!S11),"",'DPW3'!S11) | ¬¬IF(ISBLANK('DPW3'!T11),"",'DPW3'!T11) | ¬¬IF(ISBLANK('DPW3'!U11),"",'DPW3'!U11) | ¬¬IF(ISBLANK('DPW3'!V11),"",'DPW3'!V11) | ¬¬IF(ISBLANK('DPW3'!W11),"",'DPW3'!W11) | ¬¬IF(ISBLANK('DPW3'!X11),"",'DPW3'!X11) | ¬¬IF(ISBLANK('DPW3'!Y11),"",'DPW3'!Y11) | ¬¬IF(ISBLANK('DPW3'!Z11),"",'DPW3'!Z11) | ¬¬IF(ISBLANK('DPW3'!AA11),"",'DPW3'!AA11) | ¬¬IF(ISBLANK('DPW3'!AB11),"",'DPW3'!AB11) | ¬¬IF(ISBLANK('DPW3'!AC11),"",'DPW3'!AC11) | ¬¬IF(ISBLANK('DPW3'!AD11),"",'DPW3'!AD11) | ¬¬IF(ISBLANK('DPW3'!AE11),"",'DPW3'!AE11) | ¬¬IF(ISBLANK('DPW3'!AF11),"",'DPW3'!AF11) | ¬¬IF(ISBLANK('DPW3'!AG11),"",'DPW3'!AG11) | ¬¬IF(ISBLANK('DPW3'!AH11),"",'DPW3'!AH11) | ¬¬IF(ISBLANK('DPW3'!AI11),"",'DPW3'!AI11) | ¬¬IF(ISBLANK('DPW3'!AJ11),"",'DPW3'!AJ11) | ¬¬IF(ISBLANK('DPW3'!AK11),"",'DPW3'!AK11) | ¬¬IF(ISBLANK('DPW3'!AL11),"",'DPW3'!AL11) | ¬¬IF(ISBLANK('DPW3'!AM11),"",'DPW3'!AM11) | ¬¬IF(ISBLANK('DPW3'!AN11),"",'DPW3'!AN11) | ¬¬IF(ISBLANK('DPW3'!AO11),"",'DPW3'!AO11) | ¬¬IF(ISBLANK('DPW3'!AP11),"",'DPW3'!AP11) | ¬¬IF(ISBLANK('DPW3'!AQ11),"",'DPW3'!AQ11) | ¬¬IF(ISBLANK('DPW3'!AR11),"",'DPW3'!AR11) | ¬¬IF(ISBLANK('DPW3'!AS11),"",'DPW3'!AS11) | ¬¬IF(ISBLANK('DPW3'!AT11),"",'DPW3'!AT11) | ¬¬IF(ISBLANK('DPW3'!AU11),"",'DPW3'!AU11) | ¬¬IF(ISBLANK('DPW3'!AV11),"",'DPW3'!AV11) | ¬¬IF(ISBLANK('DPW3'!AW11),"",'DPW3'!AW11) | ¬¬IF(ISBLANK('DPW3'!AX11),"",'DPW3'!AX11) | ¬¬IF(ISBLANK('DPW3'!AY11),"",'DPW3'!AY11) | ¬¬IF(ISBLANK('DPW3'!AZ11),"",'DPW3'!AZ11)
¬¬A1423 | ¬¬IF(ISBLANK('DPW3'!OK11),"",'DPW3'!OK11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB11),"",'DPW3'!BB11) | ¬¬IF(ISBLANK('DPW3'!BC11),"",'DPW3'!BC11) | ¬¬IF(ISBLANK('DPW3'!BD11),"",'DPW3'!BD11) | ¬¬IF(ISBLANK('DPW3'!BE11),"",'DPW3'!BE11) | ¬¬IF(ISBLANK('DPW3'!BF11),"",'DPW3'!BF11) | ¬¬IF(ISBLANK('DPW3'!BG11),"",'DPW3'!BG11) | ¬¬IF(ISBLANK('DPW3'!BH11),"",'DPW3'!BH11) | ¬¬IF(ISBLANK('DPW3'!BI11),"",'DPW3'!BI11) | ¬¬IF(ISBLANK('DPW3'!BJ11),"",'DPW3'!BJ11) | ¬¬IF(ISBLANK('DPW3'!BK11),"",'DPW3'!BK11) | ¬¬IF(ISBLANK('DPW3'!BL11),"",'DPW3'!BL11) | ¬¬IF(ISBLANK('DPW3'!BM11),"",'DPW3'!BM11) | ¬¬IF(ISBLANK('DPW3'!BN11),"",'DPW3'!BN11) | ¬¬IF(ISBLANK('DPW3'!BO11),"",'DPW3'!BO11) | ¬¬IF(ISBLANK('DPW3'!BP11),"",'DPW3'!BP11) | ¬¬IF(ISBLANK('DPW3'!BQ11),"",'DPW3'!BQ11) | ¬¬IF(ISBLANK('DPW3'!BR11),"",'DPW3'!BR11) | ¬¬IF(ISBLANK('DPW3'!BS11),"",'DPW3'!BS11) | ¬¬IF(ISBLANK('DPW3'!BT11),"",'DPW3'!BT11) | ¬¬IF(ISBLANK('DPW3'!BU11),"",'DPW3'!BU11) | ¬¬IF(ISBLANK('DPW3'!BV11),"",'DPW3'!BV11) | ¬¬IF(ISBLANK('DPW3'!BW11),"",'DPW3'!BW11) | ¬¬IF(ISBLANK('DPW3'!BX11),"",'DPW3'!BX11) | ¬¬IF(ISBLANK('DPW3'!BY11),"",'DPW3'!BY11) | ¬¬IF(ISBLANK('DPW3'!BZ11),"",'DPW3'!BZ11) | ¬¬IF(ISBLANK('DPW3'!CA11),"",'DPW3'!CA11) | ¬¬IF(ISBLANK('DPW3'!CB11),"",'DPW3'!CB11) | ¬¬IF(ISBLANK('DPW3'!CC11),"",'DPW3'!CC11) | ¬¬IF(ISBLANK('DPW3'!CD11),"",'DPW3'!CD11) | ¬¬IF(ISBLANK('DPW3'!CE11),"",'DPW3'!CE11) | ¬¬IF(ISBLANK('DPW3'!CF11),"",'DPW3'!CF11) | ¬¬IF(ISBLANK('DPW3'!CG11),"",'DPW3'!CG11) | ¬¬IF(ISBLANK('DPW3'!CH11),"",'DPW3'!CH11) | ¬¬IF(ISBLANK('DPW3'!CI11),"",'DPW3'!CI11) | ¬¬IF(ISBLANK('DPW3'!CJ11),"",'DPW3'!CJ11) | ¬¬IF(ISBLANK('DPW3'!CK11),"",'DPW3'!CK11) | ¬¬IF(ISBLANK('DPW3'!CL11),"",'DPW3'!CL11) | ¬¬IF(ISBLANK('DPW3'!CM11),"",'DPW3'!CM11) | ¬¬IF(ISBLANK('DPW3'!CN11),"",'DPW3'!CN11) | ¬¬IF(ISBLANK('DPW3'!CO11),"",'DPW3'!CO11)
¬¬A1424 | ¬¬IF(ISBLANK('DPW3'!PZ11),"",'DPW3'!PZ11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ11),"",'DPW3'!CQ11) | ¬¬IF(ISBLANK('DPW3'!CR11),"",'DPW3'!CR11) | ¬¬IF(ISBLANK('DPW3'!CS11),"",'DPW3'!CS11) | ¬¬IF(ISBLANK('DPW3'!CT11),"",'DPW3'!CT11) | ¬¬IF(ISBLANK('DPW3'!CU11),"",'DPW3'!CU11) | ¬¬IF(ISBLANK('DPW3'!CV11),"",'DPW3'!CV11) | ¬¬IF(ISBLANK('DPW3'!CW11),"",'DPW3'!CW11) | ¬¬IF(ISBLANK('DPW3'!CX11),"",'DPW3'!CX11) | ¬¬IF(ISBLANK('DPW3'!CY11),"",'DPW3'!CY11) | ¬¬IF(ISBLANK('DPW3'!CZ11),"",'DPW3'!CZ11) | ¬¬IF(ISBLANK('DPW3'!DA11),"",'DPW3'!DA11) | ¬¬IF(ISBLANK('DPW3'!DB11),"",'DPW3'!DB11) | ¬¬IF(ISBLANK('DPW3'!DC11),"",'DPW3'!DC11) | ¬¬IF(ISBLANK('DPW3'!DD11),"",'DPW3'!DD11) | ¬¬IF(ISBLANK('DPW3'!DE11),"",'DPW3'!DE11) | ¬¬IF(ISBLANK('DPW3'!DF11),"",'DPW3'!DF11) | ¬¬IF(ISBLANK('DPW3'!DG11),"",'DPW3'!DG11) | ¬¬IF(ISBLANK('DPW3'!DH11),"",'DPW3'!DH11) | ¬¬IF(ISBLANK('DPW3'!DI11),"",'DPW3'!DI11) | ¬¬IF(ISBLANK('DPW3'!DJ11),"",'DPW3'!DJ11) | ¬¬IF(ISBLANK('DPW3'!DK11),"",'DPW3'!DK11) | ¬¬IF(ISBLANK('DPW3'!DL11),"",'DPW3'!DL11) | ¬¬IF(ISBLANK('DPW3'!DM11),"",'DPW3'!DM11) | ¬¬IF(ISBLANK('DPW3'!DN11),"",'DPW3'!DN11) | ¬¬IF(ISBLANK('DPW3'!DO11),"",'DPW3'!DO11) | ¬¬IF(ISBLANK('DPW3'!DP11),"",'DPW3'!DP11) | ¬¬IF(ISBLANK('DPW3'!DQ11),"",'DPW3'!DQ11) | ¬¬IF(ISBLANK('DPW3'!DR11),"",'DPW3'!DR11) | ¬¬IF(ISBLANK('DPW3'!DS11),"",'DPW3'!DS11) | ¬¬IF(ISBLANK('DPW3'!DT11),"",'DPW3'!DT11) | ¬¬IF(ISBLANK('DPW3'!DU11),"",'DPW3'!DU11) | ¬¬IF(ISBLANK('DPW3'!DV11),"",'DPW3'!DV11) | ¬¬IF(ISBLANK('DPW3'!DW11),"",'DPW3'!DW11) | ¬¬IF(ISBLANK('DPW3'!DX11),"",'DPW3'!DX11) | ¬¬IF(ISBLANK('DPW3'!DY11),"",'DPW3'!DY11) | ¬¬IF(ISBLANK('DPW3'!DZ11),"",'DPW3'!DZ11) | ¬¬IF(ISBLANK('DPW3'!EA11),"",'DPW3'!EA11) | ¬¬IF(ISBLANK('DPW3'!EB11),"",'DPW3'!EB11) | ¬¬IF(ISBLANK('DPW3'!EC11),"",'DPW3'!EC11) | ¬¬IF(ISBLANK('DPW3'!ED11),"",'DPW3'!ED11)
¬¬A1425 | ¬¬IF(ISBLANK('DPW3'!RO11),"",'DPW3'!RO11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF11),"",'DPW3'!EF11) | ¬¬IF(ISBLANK('DPW3'!EG11),"",'DPW3'!EG11) | ¬¬IF(ISBLANK('DPW3'!EH11),"",'DPW3'!EH11) | ¬¬IF(ISBLANK('DPW3'!EI11),"",'DPW3'!EI11) | ¬¬IF(ISBLANK('DPW3'!EJ11),"",'DPW3'!EJ11) | ¬¬IF(ISBLANK('DPW3'!EK11),"",'DPW3'!EK11) | ¬¬IF(ISBLANK('DPW3'!EL11),"",'DPW3'!EL11) | ¬¬IF(ISBLANK('DPW3'!EM11),"",'DPW3'!EM11) | ¬¬IF(ISBLANK('DPW3'!EN11),"",'DPW3'!EN11) | ¬¬IF(ISBLANK('DPW3'!EO11),"",'DPW3'!EO11) | ¬¬IF(ISBLANK('DPW3'!EP11),"",'DPW3'!EP11) | ¬¬IF(ISBLANK('DPW3'!EQ11),"",'DPW3'!EQ11) | ¬¬IF(ISBLANK('DPW3'!ER11),"",'DPW3'!ER11) | ¬¬IF(ISBLANK('DPW3'!ES11),"",'DPW3'!ES11) | ¬¬IF(ISBLANK('DPW3'!ET11),"",'DPW3'!ET11) | ¬¬IF(ISBLANK('DPW3'!EU11),"",'DPW3'!EU11) | ¬¬IF(ISBLANK('DPW3'!EV11),"",'DPW3'!EV11) | ¬¬IF(ISBLANK('DPW3'!EW11),"",'DPW3'!EW11) | ¬¬IF(ISBLANK('DPW3'!EX11),"",'DPW3'!EX11) | ¬¬IF(ISBLANK('DPW3'!EY11),"",'DPW3'!EY11) | ¬¬IF(ISBLANK('DPW3'!EZ11),"",'DPW3'!EZ11) | ¬¬IF(ISBLANK('DPW3'!FA11),"",'DPW3'!FA11) | ¬¬IF(ISBLANK('DPW3'!FB11),"",'DPW3'!FB11) | ¬¬IF(ISBLANK('DPW3'!FC11),"",'DPW3'!FC11) | ¬¬IF(ISBLANK('DPW3'!FD11),"",'DPW3'!FD11) | ¬¬IF(ISBLANK('DPW3'!FE11),"",'DPW3'!FE11) | ¬¬IF(ISBLANK('DPW3'!FF11),"",'DPW3'!FF11) | ¬¬IF(ISBLANK('DPW3'!FG11),"",'DPW3'!FG11) | ¬¬IF(ISBLANK('DPW3'!FH11),"",'DPW3'!FH11) | ¬¬IF(ISBLANK('DPW3'!FI11),"",'DPW3'!FI11) | ¬¬IF(ISBLANK('DPW3'!FJ11),"",'DPW3'!FJ11) | ¬¬IF(ISBLANK('DPW3'!FK11),"",'DPW3'!FK11) | ¬¬IF(ISBLANK('DPW3'!FL11),"",'DPW3'!FL11) | ¬¬IF(ISBLANK('DPW3'!FM11),"",'DPW3'!FM11) | ¬¬IF(ISBLANK('DPW3'!FN11),"",'DPW3'!FN11) | ¬¬IF(ISBLANK('DPW3'!FO11),"",'DPW3'!FO11) | ¬¬IF(ISBLANK('DPW3'!FP11),"",'DPW3'!FP11) | ¬¬IF(ISBLANK('DPW3'!FQ11),"",'DPW3'!FQ11) | ¬¬IF(ISBLANK('DPW3'!FR11),"",'DPW3'!FR11) | ¬¬IF(ISBLANK('DPW3'!FS11),"",'DPW3'!FS11)
¬¬A1426 | ¬¬IF(ISBLANK('DPW3'!TD11),"",'DPW3'!TD11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU11),"",'DPW3'!FU11) | ¬¬IF(ISBLANK('DPW3'!FV11),"",'DPW3'!FV11) | ¬¬IF(ISBLANK('DPW3'!FW11),"",'DPW3'!FW11) | ¬¬IF(ISBLANK('DPW3'!FX11),"",'DPW3'!FX11) | ¬¬IF(ISBLANK('DPW3'!FY11),"",'DPW3'!FY11) | ¬¬IF(ISBLANK('DPW3'!FZ11),"",'DPW3'!FZ11) | ¬¬IF(ISBLANK('DPW3'!GA11),"",'DPW3'!GA11) | ¬¬IF(ISBLANK('DPW3'!GB11),"",'DPW3'!GB11) | ¬¬IF(ISBLANK('DPW3'!GC11),"",'DPW3'!GC11) | ¬¬IF(ISBLANK('DPW3'!GD11),"",'DPW3'!GD11) | ¬¬IF(ISBLANK('DPW3'!GE11),"",'DPW3'!GE11) | ¬¬IF(ISBLANK('DPW3'!GF11),"",'DPW3'!GF11) | ¬¬IF(ISBLANK('DPW3'!GG11),"",'DPW3'!GG11) | ¬¬IF(ISBLANK('DPW3'!GH11),"",'DPW3'!GH11) | ¬¬IF(ISBLANK('DPW3'!GI11),"",'DPW3'!GI11) | ¬¬IF(ISBLANK('DPW3'!GJ11),"",'DPW3'!GJ11) | ¬¬IF(ISBLANK('DPW3'!GK11),"",'DPW3'!GK11) | ¬¬IF(ISBLANK('DPW3'!GL11),"",'DPW3'!GL11) | ¬¬IF(ISBLANK('DPW3'!GM11),"",'DPW3'!GM11) | ¬¬IF(ISBLANK('DPW3'!GN11),"",'DPW3'!GN11) | ¬¬IF(ISBLANK('DPW3'!GO11),"",'DPW3'!GO11) | ¬¬IF(ISBLANK('DPW3'!GP11),"",'DPW3'!GP11) | ¬¬IF(ISBLANK('DPW3'!GQ11),"",'DPW3'!GQ11) | ¬¬IF(ISBLANK('DPW3'!GR11),"",'DPW3'!GR11) | ¬¬IF(ISBLANK('DPW3'!GS11),"",'DPW3'!GS11) | ¬¬IF(ISBLANK('DPW3'!GT11),"",'DPW3'!GT11) | ¬¬IF(ISBLANK('DPW3'!GU11),"",'DPW3'!GU11) | ¬¬IF(ISBLANK('DPW3'!GV11),"",'DPW3'!GV11) | ¬¬IF(ISBLANK('DPW3'!GW11),"",'DPW3'!GW11) | ¬¬IF(ISBLANK('DPW3'!GX11),"",'DPW3'!GX11) | ¬¬IF(ISBLANK('DPW3'!GY11),"",'DPW3'!GY11) | ¬¬IF(ISBLANK('DPW3'!GZ11),"",'DPW3'!GZ11) | ¬¬IF(ISBLANK('DPW3'!HA11),"",'DPW3'!HA11) | ¬¬IF(ISBLANK('DPW3'!HB11),"",'DPW3'!HB11) | ¬¬IF(ISBLANK('DPW3'!HC11),"",'DPW3'!HC11) | ¬¬IF(ISBLANK('DPW3'!HD11),"",'DPW3'!HD11) | ¬¬IF(ISBLANK('DPW3'!HE11),"",'DPW3'!HE11) | ¬¬IF(ISBLANK('DPW3'!HF11),"",'DPW3'!HF11) | ¬¬IF(ISBLANK('DPW3'!HG11),"",'DPW3'!HG11) | ¬¬IF(ISBLANK('DPW3'!HH11),"",'DPW3'!HH11)
¬¬A1427 | ¬¬IF(ISBLANK('DPW3'!US11),"",'DPW3'!US11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ11),"",'DPW3'!HJ11) | ¬¬IF(ISBLANK('DPW3'!HK11),"",'DPW3'!HK11) | ¬¬IF(ISBLANK('DPW3'!HL11),"",'DPW3'!HL11) | ¬¬IF(ISBLANK('DPW3'!HM11),"",'DPW3'!HM11) | ¬¬IF(ISBLANK('DPW3'!HN11),"",'DPW3'!HN11) | ¬¬IF(ISBLANK('DPW3'!HO11),"",'DPW3'!HO11) | ¬¬IF(ISBLANK('DPW3'!HP11),"",'DPW3'!HP11) | ¬¬IF(ISBLANK('DPW3'!HQ11),"",'DPW3'!HQ11) | ¬¬IF(ISBLANK('DPW3'!HR11),"",'DPW3'!HR11) | ¬¬IF(ISBLANK('DPW3'!HS11),"",'DPW3'!HS11) | ¬¬IF(ISBLANK('DPW3'!HT11),"",'DPW3'!HT11) | ¬¬IF(ISBLANK('DPW3'!HU11),"",'DPW3'!HU11) | ¬¬IF(ISBLANK('DPW3'!HV11),"",'DPW3'!HV11) | ¬¬IF(ISBLANK('DPW3'!HW11),"",'DPW3'!HW11) | ¬¬IF(ISBLANK('DPW3'!HX11),"",'DPW3'!HX11) | ¬¬IF(ISBLANK('DPW3'!HY11),"",'DPW3'!HY11) | ¬¬IF(ISBLANK('DPW3'!HZ11),"",'DPW3'!HZ11) | ¬¬IF(ISBLANK('DPW3'!IA11),"",'DPW3'!IA11) | ¬¬IF(ISBLANK('DPW3'!IB11),"",'DPW3'!IB11) | ¬¬IF(ISBLANK('DPW3'!IC11),"",'DPW3'!IC11) | ¬¬IF(ISBLANK('DPW3'!ID11),"",'DPW3'!ID11) | ¬¬IF(ISBLANK('DPW3'!IE11),"",'DPW3'!IE11) | ¬¬IF(ISBLANK('DPW3'!IF11),"",'DPW3'!IF11) | ¬¬IF(ISBLANK('DPW3'!IG11),"",'DPW3'!IG11) | ¬¬IF(ISBLANK('DPW3'!IH11),"",'DPW3'!IH11) | ¬¬IF(ISBLANK('DPW3'!II11),"",'DPW3'!II11) | ¬¬IF(ISBLANK('DPW3'!IJ11),"",'DPW3'!IJ11) | ¬¬IF(ISBLANK('DPW3'!IK11),"",'DPW3'!IK11) | ¬¬IF(ISBLANK('DPW3'!IL11),"",'DPW3'!IL11) | ¬¬IF(ISBLANK('DPW3'!IM11),"",'DPW3'!IM11) | ¬¬IF(ISBLANK('DPW3'!IN11),"",'DPW3'!IN11) | ¬¬IF(ISBLANK('DPW3'!IO11),"",'DPW3'!IO11) | ¬¬IF(ISBLANK('DPW3'!IP11),"",'DPW3'!IP11) | ¬¬IF(ISBLANK('DPW3'!IQ11),"",'DPW3'!IQ11) | ¬¬IF(ISBLANK('DPW3'!IR11),"",'DPW3'!IR11) | ¬¬IF(ISBLANK('DPW3'!IS11),"",'DPW3'!IS11) | ¬¬IF(ISBLANK('DPW3'!IT11),"",'DPW3'!IT11) | ¬¬IF(ISBLANK('DPW3'!IU11),"",'DPW3'!IU11) | ¬¬IF(ISBLANK('DPW3'!IV11),"",'DPW3'!IV11) | ¬¬IF(ISBLANK('DPW3'!IW11),"",'DPW3'!IW11)
¬¬A1428 | ¬¬IF(ISBLANK('DPW3'!WH11),"",'DPW3'!WH11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY11),"",'DPW3'!IY11) | ¬¬IF(ISBLANK('DPW3'!IZ11),"",'DPW3'!IZ11) | ¬¬IF(ISBLANK('DPW3'!JA11),"",'DPW3'!JA11) | ¬¬IF(ISBLANK('DPW3'!JB11),"",'DPW3'!JB11) | ¬¬IF(ISBLANK('DPW3'!JC11),"",'DPW3'!JC11) | ¬¬IF(ISBLANK('DPW3'!JD11),"",'DPW3'!JD11) | ¬¬IF(ISBLANK('DPW3'!JE11),"",'DPW3'!JE11) | ¬¬IF(ISBLANK('DPW3'!JF11),"",'DPW3'!JF11) | ¬¬IF(ISBLANK('DPW3'!JG11),"",'DPW3'!JG11) | ¬¬IF(ISBLANK('DPW3'!JH11),"",'DPW3'!JH11) | ¬¬IF(ISBLANK('DPW3'!JI11),"",'DPW3'!JI11) | ¬¬IF(ISBLANK('DPW3'!JJ11),"",'DPW3'!JJ11) | ¬¬IF(ISBLANK('DPW3'!JK11),"",'DPW3'!JK11) | ¬¬IF(ISBLANK('DPW3'!JL11),"",'DPW3'!JL11) | ¬¬IF(ISBLANK('DPW3'!JM11),"",'DPW3'!JM11) | ¬¬IF(ISBLANK('DPW3'!JN11),"",'DPW3'!JN11) | ¬¬IF(ISBLANK('DPW3'!JO11),"",'DPW3'!JO11) | ¬¬IF(ISBLANK('DPW3'!JP11),"",'DPW3'!JP11) | ¬¬IF(ISBLANK('DPW3'!JQ11),"",'DPW3'!JQ11) | ¬¬IF(ISBLANK('DPW3'!JR11),"",'DPW3'!JR11) | ¬¬IF(ISBLANK('DPW3'!JS11),"",'DPW3'!JS11) | ¬¬IF(ISBLANK('DPW3'!JT11),"",'DPW3'!JT11) | ¬¬IF(ISBLANK('DPW3'!JU11),"",'DPW3'!JU11) | ¬¬IF(ISBLANK('DPW3'!JV11),"",'DPW3'!JV11) | ¬¬IF(ISBLANK('DPW3'!JW11),"",'DPW3'!JW11) | ¬¬IF(ISBLANK('DPW3'!JX11),"",'DPW3'!JX11) | ¬¬IF(ISBLANK('DPW3'!JY11),"",'DPW3'!JY11) | ¬¬IF(ISBLANK('DPW3'!JZ11),"",'DPW3'!JZ11) | ¬¬IF(ISBLANK('DPW3'!KA11),"",'DPW3'!KA11) | ¬¬IF(ISBLANK('DPW3'!KB11),"",'DPW3'!KB11) | ¬¬IF(ISBLANK('DPW3'!KC11),"",'DPW3'!KC11) | ¬¬IF(ISBLANK('DPW3'!KD11),"",'DPW3'!KD11) | ¬¬IF(ISBLANK('DPW3'!KE11),"",'DPW3'!KE11) | ¬¬IF(ISBLANK('DPW3'!KF11),"",'DPW3'!KF11) | ¬¬IF(ISBLANK('DPW3'!KG11),"",'DPW3'!KG11) | ¬¬IF(ISBLANK('DPW3'!KH11),"",'DPW3'!KH11) | ¬¬IF(ISBLANK('DPW3'!KI11),"",'DPW3'!KI11) | ¬¬IF(ISBLANK('DPW3'!KJ11),"",'DPW3'!KJ11) | ¬¬IF(ISBLANK('DPW3'!KK11),"",'DPW3'!KK11) | ¬¬IF(ISBLANK('DPW3'!KL11),"",'DPW3'!KL11)
¬¬A1429 | ¬¬IF(ISBLANK('DPW3'!XW11),"",'DPW3'!XW11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN11),"",'DPW3'!KN11) | ¬¬IF(ISBLANK('DPW3'!KO11),"",'DPW3'!KO11) | ¬¬IF(ISBLANK('DPW3'!KP11),"",'DPW3'!KP11) | ¬¬IF(ISBLANK('DPW3'!KQ11),"",'DPW3'!KQ11) | ¬¬IF(ISBLANK('DPW3'!KR11),"",'DPW3'!KR11) | ¬¬IF(ISBLANK('DPW3'!KS11),"",'DPW3'!KS11) | ¬¬IF(ISBLANK('DPW3'!KT11),"",'DPW3'!KT11) | ¬¬IF(ISBLANK('DPW3'!KU11),"",'DPW3'!KU11) | ¬¬IF(ISBLANK('DPW3'!KV11),"",'DPW3'!KV11) | ¬¬IF(ISBLANK('DPW3'!KW11),"",'DPW3'!KW11) | ¬¬IF(ISBLANK('DPW3'!KX11),"",'DPW3'!KX11) | ¬¬IF(ISBLANK('DPW3'!KY11),"",'DPW3'!KY11) | ¬¬IF(ISBLANK('DPW3'!KZ11),"",'DPW3'!KZ11) | ¬¬IF(ISBLANK('DPW3'!LA11),"",'DPW3'!LA11) | ¬¬IF(ISBLANK('DPW3'!LB11),"",'DPW3'!LB11) | ¬¬IF(ISBLANK('DPW3'!LC11),"",'DPW3'!LC11) | ¬¬IF(ISBLANK('DPW3'!LD11),"",'DPW3'!LD11) | ¬¬IF(ISBLANK('DPW3'!LE11),"",'DPW3'!LE11) | ¬¬IF(ISBLANK('DPW3'!LF11),"",'DPW3'!LF11) | ¬¬IF(ISBLANK('DPW3'!LG11),"",'DPW3'!LG11) | ¬¬IF(ISBLANK('DPW3'!LH11),"",'DPW3'!LH11) | ¬¬IF(ISBLANK('DPW3'!LI11),"",'DPW3'!LI11) | ¬¬IF(ISBLANK('DPW3'!LJ11),"",'DPW3'!LJ11) | ¬¬IF(ISBLANK('DPW3'!LK11),"",'DPW3'!LK11) | ¬¬IF(ISBLANK('DPW3'!LL11),"",'DPW3'!LL11) | ¬¬IF(ISBLANK('DPW3'!LM11),"",'DPW3'!LM11) | ¬¬IF(ISBLANK('DPW3'!LN11),"",'DPW3'!LN11) | ¬¬IF(ISBLANK('DPW3'!LO11),"",'DPW3'!LO11) | ¬¬IF(ISBLANK('DPW3'!LP11),"",'DPW3'!LP11) | ¬¬IF(ISBLANK('DPW3'!LQ11),"",'DPW3'!LQ11) | ¬¬IF(ISBLANK('DPW3'!LR11),"",'DPW3'!LR11) | ¬¬IF(ISBLANK('DPW3'!LS11),"",'DPW3'!LS11) | ¬¬IF(ISBLANK('DPW3'!LT11),"",'DPW3'!LT11) | ¬¬IF(ISBLANK('DPW3'!LU11),"",'DPW3'!LU11) | ¬¬IF(ISBLANK('DPW3'!LV11),"",'DPW3'!LV11) | ¬¬IF(ISBLANK('DPW3'!LW11),"",'DPW3'!LW11) | ¬¬IF(ISBLANK('DPW3'!LX11),"",'DPW3'!LX11) | ¬¬IF(ISBLANK('DPW3'!LY11),"",'DPW3'!LY11) | ¬¬IF(ISBLANK('DPW3'!LZ11),"",'DPW3'!LZ11) | ¬¬IF(ISBLANK('DPW3'!MA11),"",'DPW3'!MA11)
¬¬A1430 | ¬¬IF(ISBLANK('DPW3'!ZL11),"",'DPW3'!ZL11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MC11),"",'DPW3'!MC11)
¬¬A1431 | ¬¬IF(ISBLANK('DPW3'!ZM11),"",'DPW3'!ZM11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MD11),"",'DPW3'!MD11)
¬¬A1432 | ¬¬IF(ISBLANK('DPW3'!ZN11),"",'DPW3'!ZN11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!ML11),"",'DPW3'!ML11)
¬¬A1433 | ¬¬IF(ISBLANK('DPW3'!ZO11),"",'DPW3'!ZO11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MF11),"",'DPW3'!MF11)
¬¬A1434 | ¬¬IF(ISBLANK('DPW3'!ZP11),"",'DPW3'!ZP11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MG11),"",'DPW3'!MG11)
¬¬A1435 | ¬¬IF(ISBLANK('DPW3'!ZQ11),"",'DPW3'!ZQ11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MH11),"",'DPW3'!MH11)
¬¬A1436 | ¬¬IF(ISBLANK('DPW3'!ZR11),"",'DPW3'!ZR11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MI11),"",'DPW3'!MI11)
¬¬A1437 | ¬¬IF(ISBLANK('DPW3'!ZS11),"",'DPW3'!ZS11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ11),"",'DPW3'!MJ11)
¬¬A1438 | ¬¬IF(ISBLANK('DPW3'!ZT11),"",'DPW3'!ZT11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MK11),"",'DPW3'!MK11)
¬¬A1439 | ¬¬IF(ISBLANK('DPW3'!ZV11),"",'DPW3'!ZV11) | ¬¬'DPW3'!F11 & "," & 'DPW3'!G11 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H11),"",'DPW3'!H11) | Delta | ¬¬IF(ISBLANK('DPW3'!MM11),"",'DPW3'!MM11)
¬¬A1440 | ¬¬IF(ISBLANK('DPW3'!MT12),"",'DPW3'!MT12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!K12),"",'DPW3'!K12)
¬¬A1441 | ¬¬IF(ISBLANK('DPW3'!MV12),"",'DPW3'!MV12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M12),"",'DPW3'!M12) | ¬¬IF(ISBLANK('DPW3'!N12),"",'DPW3'!N12) | ¬¬IF(ISBLANK('DPW3'!O12),"",'DPW3'!O12) | ¬¬IF(ISBLANK('DPW3'!P12),"",'DPW3'!P12) | ¬¬IF(ISBLANK('DPW3'!Q12),"",'DPW3'!Q12) | ¬¬IF(ISBLANK('DPW3'!R12),"",'DPW3'!R12) | ¬¬IF(ISBLANK('DPW3'!S12),"",'DPW3'!S12) | ¬¬IF(ISBLANK('DPW3'!T12),"",'DPW3'!T12) | ¬¬IF(ISBLANK('DPW3'!U12),"",'DPW3'!U12) | ¬¬IF(ISBLANK('DPW3'!V12),"",'DPW3'!V12) | ¬¬IF(ISBLANK('DPW3'!W12),"",'DPW3'!W12) | ¬¬IF(ISBLANK('DPW3'!X12),"",'DPW3'!X12) | ¬¬IF(ISBLANK('DPW3'!Y12),"",'DPW3'!Y12) | ¬¬IF(ISBLANK('DPW3'!Z12),"",'DPW3'!Z12) | ¬¬IF(ISBLANK('DPW3'!AA12),"",'DPW3'!AA12) | ¬¬IF(ISBLANK('DPW3'!AB12),"",'DPW3'!AB12) | ¬¬IF(ISBLANK('DPW3'!AC12),"",'DPW3'!AC12) | ¬¬IF(ISBLANK('DPW3'!AD12),"",'DPW3'!AD12) | ¬¬IF(ISBLANK('DPW3'!AE12),"",'DPW3'!AE12) | ¬¬IF(ISBLANK('DPW3'!AF12),"",'DPW3'!AF12) | ¬¬IF(ISBLANK('DPW3'!AG12),"",'DPW3'!AG12) | ¬¬IF(ISBLANK('DPW3'!AH12),"",'DPW3'!AH12) | ¬¬IF(ISBLANK('DPW3'!AI12),"",'DPW3'!AI12) | ¬¬IF(ISBLANK('DPW3'!AJ12),"",'DPW3'!AJ12) | ¬¬IF(ISBLANK('DPW3'!AK12),"",'DPW3'!AK12) | ¬¬IF(ISBLANK('DPW3'!AL12),"",'DPW3'!AL12) | ¬¬IF(ISBLANK('DPW3'!AM12),"",'DPW3'!AM12) | ¬¬IF(ISBLANK('DPW3'!AN12),"",'DPW3'!AN12) | ¬¬IF(ISBLANK('DPW3'!AO12),"",'DPW3'!AO12) | ¬¬IF(ISBLANK('DPW3'!AP12),"",'DPW3'!AP12) | ¬¬IF(ISBLANK('DPW3'!AQ12),"",'DPW3'!AQ12) | ¬¬IF(ISBLANK('DPW3'!AR12),"",'DPW3'!AR12) | ¬¬IF(ISBLANK('DPW3'!AS12),"",'DPW3'!AS12) | ¬¬IF(ISBLANK('DPW3'!AT12),"",'DPW3'!AT12) | ¬¬IF(ISBLANK('DPW3'!AU12),"",'DPW3'!AU12) | ¬¬IF(ISBLANK('DPW3'!AV12),"",'DPW3'!AV12) | ¬¬IF(ISBLANK('DPW3'!AW12),"",'DPW3'!AW12) | ¬¬IF(ISBLANK('DPW3'!AX12),"",'DPW3'!AX12) | ¬¬IF(ISBLANK('DPW3'!AY12),"",'DPW3'!AY12) | ¬¬IF(ISBLANK('DPW3'!AZ12),"",'DPW3'!AZ12)
¬¬A1442 | ¬¬IF(ISBLANK('DPW3'!OK12),"",'DPW3'!OK12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB12),"",'DPW3'!BB12) | ¬¬IF(ISBLANK('DPW3'!BC12),"",'DPW3'!BC12) | ¬¬IF(ISBLANK('DPW3'!BD12),"",'DPW3'!BD12) | ¬¬IF(ISBLANK('DPW3'!BE12),"",'DPW3'!BE12) | ¬¬IF(ISBLANK('DPW3'!BF12),"",'DPW3'!BF12) | ¬¬IF(ISBLANK('DPW3'!BG12),"",'DPW3'!BG12) | ¬¬IF(ISBLANK('DPW3'!BH12),"",'DPW3'!BH12) | ¬¬IF(ISBLANK('DPW3'!BI12),"",'DPW3'!BI12) | ¬¬IF(ISBLANK('DPW3'!BJ12),"",'DPW3'!BJ12) | ¬¬IF(ISBLANK('DPW3'!BK12),"",'DPW3'!BK12) | ¬¬IF(ISBLANK('DPW3'!BL12),"",'DPW3'!BL12) | ¬¬IF(ISBLANK('DPW3'!BM12),"",'DPW3'!BM12) | ¬¬IF(ISBLANK('DPW3'!BN12),"",'DPW3'!BN12) | ¬¬IF(ISBLANK('DPW3'!BO12),"",'DPW3'!BO12) | ¬¬IF(ISBLANK('DPW3'!BP12),"",'DPW3'!BP12) | ¬¬IF(ISBLANK('DPW3'!BQ12),"",'DPW3'!BQ12) | ¬¬IF(ISBLANK('DPW3'!BR12),"",'DPW3'!BR12) | ¬¬IF(ISBLANK('DPW3'!BS12),"",'DPW3'!BS12) | ¬¬IF(ISBLANK('DPW3'!BT12),"",'DPW3'!BT12) | ¬¬IF(ISBLANK('DPW3'!BU12),"",'DPW3'!BU12) | ¬¬IF(ISBLANK('DPW3'!BV12),"",'DPW3'!BV12) | ¬¬IF(ISBLANK('DPW3'!BW12),"",'DPW3'!BW12) | ¬¬IF(ISBLANK('DPW3'!BX12),"",'DPW3'!BX12) | ¬¬IF(ISBLANK('DPW3'!BY12),"",'DPW3'!BY12) | ¬¬IF(ISBLANK('DPW3'!BZ12),"",'DPW3'!BZ12) | ¬¬IF(ISBLANK('DPW3'!CA12),"",'DPW3'!CA12) | ¬¬IF(ISBLANK('DPW3'!CB12),"",'DPW3'!CB12) | ¬¬IF(ISBLANK('DPW3'!CC12),"",'DPW3'!CC12) | ¬¬IF(ISBLANK('DPW3'!CD12),"",'DPW3'!CD12) | ¬¬IF(ISBLANK('DPW3'!CE12),"",'DPW3'!CE12) | ¬¬IF(ISBLANK('DPW3'!CF12),"",'DPW3'!CF12) | ¬¬IF(ISBLANK('DPW3'!CG12),"",'DPW3'!CG12) | ¬¬IF(ISBLANK('DPW3'!CH12),"",'DPW3'!CH12) | ¬¬IF(ISBLANK('DPW3'!CI12),"",'DPW3'!CI12) | ¬¬IF(ISBLANK('DPW3'!CJ12),"",'DPW3'!CJ12) | ¬¬IF(ISBLANK('DPW3'!CK12),"",'DPW3'!CK12) | ¬¬IF(ISBLANK('DPW3'!CL12),"",'DPW3'!CL12) | ¬¬IF(ISBLANK('DPW3'!CM12),"",'DPW3'!CM12) | ¬¬IF(ISBLANK('DPW3'!CN12),"",'DPW3'!CN12) | ¬¬IF(ISBLANK('DPW3'!CO12),"",'DPW3'!CO12)
¬¬A1443 | ¬¬IF(ISBLANK('DPW3'!PZ12),"",'DPW3'!PZ12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ12),"",'DPW3'!CQ12) | ¬¬IF(ISBLANK('DPW3'!CR12),"",'DPW3'!CR12) | ¬¬IF(ISBLANK('DPW3'!CS12),"",'DPW3'!CS12) | ¬¬IF(ISBLANK('DPW3'!CT12),"",'DPW3'!CT12) | ¬¬IF(ISBLANK('DPW3'!CU12),"",'DPW3'!CU12) | ¬¬IF(ISBLANK('DPW3'!CV12),"",'DPW3'!CV12) | ¬¬IF(ISBLANK('DPW3'!CW12),"",'DPW3'!CW12) | ¬¬IF(ISBLANK('DPW3'!CX12),"",'DPW3'!CX12) | ¬¬IF(ISBLANK('DPW3'!CY12),"",'DPW3'!CY12) | ¬¬IF(ISBLANK('DPW3'!CZ12),"",'DPW3'!CZ12) | ¬¬IF(ISBLANK('DPW3'!DA12),"",'DPW3'!DA12) | ¬¬IF(ISBLANK('DPW3'!DB12),"",'DPW3'!DB12) | ¬¬IF(ISBLANK('DPW3'!DC12),"",'DPW3'!DC12) | ¬¬IF(ISBLANK('DPW3'!DD12),"",'DPW3'!DD12) | ¬¬IF(ISBLANK('DPW3'!DE12),"",'DPW3'!DE12) | ¬¬IF(ISBLANK('DPW3'!DF12),"",'DPW3'!DF12) | ¬¬IF(ISBLANK('DPW3'!DG12),"",'DPW3'!DG12) | ¬¬IF(ISBLANK('DPW3'!DH12),"",'DPW3'!DH12) | ¬¬IF(ISBLANK('DPW3'!DI12),"",'DPW3'!DI12) | ¬¬IF(ISBLANK('DPW3'!DJ12),"",'DPW3'!DJ12) | ¬¬IF(ISBLANK('DPW3'!DK12),"",'DPW3'!DK12) | ¬¬IF(ISBLANK('DPW3'!DL12),"",'DPW3'!DL12) | ¬¬IF(ISBLANK('DPW3'!DM12),"",'DPW3'!DM12) | ¬¬IF(ISBLANK('DPW3'!DN12),"",'DPW3'!DN12) | ¬¬IF(ISBLANK('DPW3'!DO12),"",'DPW3'!DO12) | ¬¬IF(ISBLANK('DPW3'!DP12),"",'DPW3'!DP12) | ¬¬IF(ISBLANK('DPW3'!DQ12),"",'DPW3'!DQ12) | ¬¬IF(ISBLANK('DPW3'!DR12),"",'DPW3'!DR12) | ¬¬IF(ISBLANK('DPW3'!DS12),"",'DPW3'!DS12) | ¬¬IF(ISBLANK('DPW3'!DT12),"",'DPW3'!DT12) | ¬¬IF(ISBLANK('DPW3'!DU12),"",'DPW3'!DU12) | ¬¬IF(ISBLANK('DPW3'!DV12),"",'DPW3'!DV12) | ¬¬IF(ISBLANK('DPW3'!DW12),"",'DPW3'!DW12) | ¬¬IF(ISBLANK('DPW3'!DX12),"",'DPW3'!DX12) | ¬¬IF(ISBLANK('DPW3'!DY12),"",'DPW3'!DY12) | ¬¬IF(ISBLANK('DPW3'!DZ12),"",'DPW3'!DZ12) | ¬¬IF(ISBLANK('DPW3'!EA12),"",'DPW3'!EA12) | ¬¬IF(ISBLANK('DPW3'!EB12),"",'DPW3'!EB12) | ¬¬IF(ISBLANK('DPW3'!EC12),"",'DPW3'!EC12) | ¬¬IF(ISBLANK('DPW3'!ED12),"",'DPW3'!ED12)
¬¬A1444 | ¬¬IF(ISBLANK('DPW3'!RO12),"",'DPW3'!RO12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF12),"",'DPW3'!EF12) | ¬¬IF(ISBLANK('DPW3'!EG12),"",'DPW3'!EG12) | ¬¬IF(ISBLANK('DPW3'!EH12),"",'DPW3'!EH12) | ¬¬IF(ISBLANK('DPW3'!EI12),"",'DPW3'!EI12) | ¬¬IF(ISBLANK('DPW3'!EJ12),"",'DPW3'!EJ12) | ¬¬IF(ISBLANK('DPW3'!EK12),"",'DPW3'!EK12) | ¬¬IF(ISBLANK('DPW3'!EL12),"",'DPW3'!EL12) | ¬¬IF(ISBLANK('DPW3'!EM12),"",'DPW3'!EM12) | ¬¬IF(ISBLANK('DPW3'!EN12),"",'DPW3'!EN12) | ¬¬IF(ISBLANK('DPW3'!EO12),"",'DPW3'!EO12) | ¬¬IF(ISBLANK('DPW3'!EP12),"",'DPW3'!EP12) | ¬¬IF(ISBLANK('DPW3'!EQ12),"",'DPW3'!EQ12) | ¬¬IF(ISBLANK('DPW3'!ER12),"",'DPW3'!ER12) | ¬¬IF(ISBLANK('DPW3'!ES12),"",'DPW3'!ES12) | ¬¬IF(ISBLANK('DPW3'!ET12),"",'DPW3'!ET12) | ¬¬IF(ISBLANK('DPW3'!EU12),"",'DPW3'!EU12) | ¬¬IF(ISBLANK('DPW3'!EV12),"",'DPW3'!EV12) | ¬¬IF(ISBLANK('DPW3'!EW12),"",'DPW3'!EW12) | ¬¬IF(ISBLANK('DPW3'!EX12),"",'DPW3'!EX12) | ¬¬IF(ISBLANK('DPW3'!EY12),"",'DPW3'!EY12) | ¬¬IF(ISBLANK('DPW3'!EZ12),"",'DPW3'!EZ12) | ¬¬IF(ISBLANK('DPW3'!FA12),"",'DPW3'!FA12) | ¬¬IF(ISBLANK('DPW3'!FB12),"",'DPW3'!FB12) | ¬¬IF(ISBLANK('DPW3'!FC12),"",'DPW3'!FC12) | ¬¬IF(ISBLANK('DPW3'!FD12),"",'DPW3'!FD12) | ¬¬IF(ISBLANK('DPW3'!FE12),"",'DPW3'!FE12) | ¬¬IF(ISBLANK('DPW3'!FF12),"",'DPW3'!FF12) | ¬¬IF(ISBLANK('DPW3'!FG12),"",'DPW3'!FG12) | ¬¬IF(ISBLANK('DPW3'!FH12),"",'DPW3'!FH12) | ¬¬IF(ISBLANK('DPW3'!FI12),"",'DPW3'!FI12) | ¬¬IF(ISBLANK('DPW3'!FJ12),"",'DPW3'!FJ12) | ¬¬IF(ISBLANK('DPW3'!FK12),"",'DPW3'!FK12) | ¬¬IF(ISBLANK('DPW3'!FL12),"",'DPW3'!FL12) | ¬¬IF(ISBLANK('DPW3'!FM12),"",'DPW3'!FM12) | ¬¬IF(ISBLANK('DPW3'!FN12),"",'DPW3'!FN12) | ¬¬IF(ISBLANK('DPW3'!FO12),"",'DPW3'!FO12) | ¬¬IF(ISBLANK('DPW3'!FP12),"",'DPW3'!FP12) | ¬¬IF(ISBLANK('DPW3'!FQ12),"",'DPW3'!FQ12) | ¬¬IF(ISBLANK('DPW3'!FR12),"",'DPW3'!FR12) | ¬¬IF(ISBLANK('DPW3'!FS12),"",'DPW3'!FS12)
¬¬A1445 | ¬¬IF(ISBLANK('DPW3'!TD12),"",'DPW3'!TD12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU12),"",'DPW3'!FU12) | ¬¬IF(ISBLANK('DPW3'!FV12),"",'DPW3'!FV12) | ¬¬IF(ISBLANK('DPW3'!FW12),"",'DPW3'!FW12) | ¬¬IF(ISBLANK('DPW3'!FX12),"",'DPW3'!FX12) | ¬¬IF(ISBLANK('DPW3'!FY12),"",'DPW3'!FY12) | ¬¬IF(ISBLANK('DPW3'!FZ12),"",'DPW3'!FZ12) | ¬¬IF(ISBLANK('DPW3'!GA12),"",'DPW3'!GA12) | ¬¬IF(ISBLANK('DPW3'!GB12),"",'DPW3'!GB12) | ¬¬IF(ISBLANK('DPW3'!GC12),"",'DPW3'!GC12) | ¬¬IF(ISBLANK('DPW3'!GD12),"",'DPW3'!GD12) | ¬¬IF(ISBLANK('DPW3'!GE12),"",'DPW3'!GE12) | ¬¬IF(ISBLANK('DPW3'!GF12),"",'DPW3'!GF12) | ¬¬IF(ISBLANK('DPW3'!GG12),"",'DPW3'!GG12) | ¬¬IF(ISBLANK('DPW3'!GH12),"",'DPW3'!GH12) | ¬¬IF(ISBLANK('DPW3'!GI12),"",'DPW3'!GI12) | ¬¬IF(ISBLANK('DPW3'!GJ12),"",'DPW3'!GJ12) | ¬¬IF(ISBLANK('DPW3'!GK12),"",'DPW3'!GK12) | ¬¬IF(ISBLANK('DPW3'!GL12),"",'DPW3'!GL12) | ¬¬IF(ISBLANK('DPW3'!GM12),"",'DPW3'!GM12) | ¬¬IF(ISBLANK('DPW3'!GN12),"",'DPW3'!GN12) | ¬¬IF(ISBLANK('DPW3'!GO12),"",'DPW3'!GO12) | ¬¬IF(ISBLANK('DPW3'!GP12),"",'DPW3'!GP12) | ¬¬IF(ISBLANK('DPW3'!GQ12),"",'DPW3'!GQ12) | ¬¬IF(ISBLANK('DPW3'!GR12),"",'DPW3'!GR12) | ¬¬IF(ISBLANK('DPW3'!GS12),"",'DPW3'!GS12) | ¬¬IF(ISBLANK('DPW3'!GT12),"",'DPW3'!GT12) | ¬¬IF(ISBLANK('DPW3'!GU12),"",'DPW3'!GU12) | ¬¬IF(ISBLANK('DPW3'!GV12),"",'DPW3'!GV12) | ¬¬IF(ISBLANK('DPW3'!GW12),"",'DPW3'!GW12) | ¬¬IF(ISBLANK('DPW3'!GX12),"",'DPW3'!GX12) | ¬¬IF(ISBLANK('DPW3'!GY12),"",'DPW3'!GY12) | ¬¬IF(ISBLANK('DPW3'!GZ12),"",'DPW3'!GZ12) | ¬¬IF(ISBLANK('DPW3'!HA12),"",'DPW3'!HA12) | ¬¬IF(ISBLANK('DPW3'!HB12),"",'DPW3'!HB12) | ¬¬IF(ISBLANK('DPW3'!HC12),"",'DPW3'!HC12) | ¬¬IF(ISBLANK('DPW3'!HD12),"",'DPW3'!HD12) | ¬¬IF(ISBLANK('DPW3'!HE12),"",'DPW3'!HE12) | ¬¬IF(ISBLANK('DPW3'!HF12),"",'DPW3'!HF12) | ¬¬IF(ISBLANK('DPW3'!HG12),"",'DPW3'!HG12) | ¬¬IF(ISBLANK('DPW3'!HH12),"",'DPW3'!HH12)
¬¬A1446 | ¬¬IF(ISBLANK('DPW3'!US12),"",'DPW3'!US12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ12),"",'DPW3'!HJ12) | ¬¬IF(ISBLANK('DPW3'!HK12),"",'DPW3'!HK12) | ¬¬IF(ISBLANK('DPW3'!HL12),"",'DPW3'!HL12) | ¬¬IF(ISBLANK('DPW3'!HM12),"",'DPW3'!HM12) | ¬¬IF(ISBLANK('DPW3'!HN12),"",'DPW3'!HN12) | ¬¬IF(ISBLANK('DPW3'!HO12),"",'DPW3'!HO12) | ¬¬IF(ISBLANK('DPW3'!HP12),"",'DPW3'!HP12) | ¬¬IF(ISBLANK('DPW3'!HQ12),"",'DPW3'!HQ12) | ¬¬IF(ISBLANK('DPW3'!HR12),"",'DPW3'!HR12) | ¬¬IF(ISBLANK('DPW3'!HS12),"",'DPW3'!HS12) | ¬¬IF(ISBLANK('DPW3'!HT12),"",'DPW3'!HT12) | ¬¬IF(ISBLANK('DPW3'!HU12),"",'DPW3'!HU12) | ¬¬IF(ISBLANK('DPW3'!HV12),"",'DPW3'!HV12) | ¬¬IF(ISBLANK('DPW3'!HW12),"",'DPW3'!HW12) | ¬¬IF(ISBLANK('DPW3'!HX12),"",'DPW3'!HX12) | ¬¬IF(ISBLANK('DPW3'!HY12),"",'DPW3'!HY12) | ¬¬IF(ISBLANK('DPW3'!HZ12),"",'DPW3'!HZ12) | ¬¬IF(ISBLANK('DPW3'!IA12),"",'DPW3'!IA12) | ¬¬IF(ISBLANK('DPW3'!IB12),"",'DPW3'!IB12) | ¬¬IF(ISBLANK('DPW3'!IC12),"",'DPW3'!IC12) | ¬¬IF(ISBLANK('DPW3'!ID12),"",'DPW3'!ID12) | ¬¬IF(ISBLANK('DPW3'!IE12),"",'DPW3'!IE12) | ¬¬IF(ISBLANK('DPW3'!IF12),"",'DPW3'!IF12) | ¬¬IF(ISBLANK('DPW3'!IG12),"",'DPW3'!IG12) | ¬¬IF(ISBLANK('DPW3'!IH12),"",'DPW3'!IH12) | ¬¬IF(ISBLANK('DPW3'!II12),"",'DPW3'!II12) | ¬¬IF(ISBLANK('DPW3'!IJ12),"",'DPW3'!IJ12) | ¬¬IF(ISBLANK('DPW3'!IK12),"",'DPW3'!IK12) | ¬¬IF(ISBLANK('DPW3'!IL12),"",'DPW3'!IL12) | ¬¬IF(ISBLANK('DPW3'!IM12),"",'DPW3'!IM12) | ¬¬IF(ISBLANK('DPW3'!IN12),"",'DPW3'!IN12) | ¬¬IF(ISBLANK('DPW3'!IO12),"",'DPW3'!IO12) | ¬¬IF(ISBLANK('DPW3'!IP12),"",'DPW3'!IP12) | ¬¬IF(ISBLANK('DPW3'!IQ12),"",'DPW3'!IQ12) | ¬¬IF(ISBLANK('DPW3'!IR12),"",'DPW3'!IR12) | ¬¬IF(ISBLANK('DPW3'!IS12),"",'DPW3'!IS12) | ¬¬IF(ISBLANK('DPW3'!IT12),"",'DPW3'!IT12) | ¬¬IF(ISBLANK('DPW3'!IU12),"",'DPW3'!IU12) | ¬¬IF(ISBLANK('DPW3'!IV12),"",'DPW3'!IV12) | ¬¬IF(ISBLANK('DPW3'!IW12),"",'DPW3'!IW12)
¬¬A1447 | ¬¬IF(ISBLANK('DPW3'!WH12),"",'DPW3'!WH12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY12),"",'DPW3'!IY12) | ¬¬IF(ISBLANK('DPW3'!IZ12),"",'DPW3'!IZ12) | ¬¬IF(ISBLANK('DPW3'!JA12),"",'DPW3'!JA12) | ¬¬IF(ISBLANK('DPW3'!JB12),"",'DPW3'!JB12) | ¬¬IF(ISBLANK('DPW3'!JC12),"",'DPW3'!JC12) | ¬¬IF(ISBLANK('DPW3'!JD12),"",'DPW3'!JD12) | ¬¬IF(ISBLANK('DPW3'!JE12),"",'DPW3'!JE12) | ¬¬IF(ISBLANK('DPW3'!JF12),"",'DPW3'!JF12) | ¬¬IF(ISBLANK('DPW3'!JG12),"",'DPW3'!JG12) | ¬¬IF(ISBLANK('DPW3'!JH12),"",'DPW3'!JH12) | ¬¬IF(ISBLANK('DPW3'!JI12),"",'DPW3'!JI12) | ¬¬IF(ISBLANK('DPW3'!JJ12),"",'DPW3'!JJ12) | ¬¬IF(ISBLANK('DPW3'!JK12),"",'DPW3'!JK12) | ¬¬IF(ISBLANK('DPW3'!JL12),"",'DPW3'!JL12) | ¬¬IF(ISBLANK('DPW3'!JM12),"",'DPW3'!JM12) | ¬¬IF(ISBLANK('DPW3'!JN12),"",'DPW3'!JN12) | ¬¬IF(ISBLANK('DPW3'!JO12),"",'DPW3'!JO12) | ¬¬IF(ISBLANK('DPW3'!JP12),"",'DPW3'!JP12) | ¬¬IF(ISBLANK('DPW3'!JQ12),"",'DPW3'!JQ12) | ¬¬IF(ISBLANK('DPW3'!JR12),"",'DPW3'!JR12) | ¬¬IF(ISBLANK('DPW3'!JS12),"",'DPW3'!JS12) | ¬¬IF(ISBLANK('DPW3'!JT12),"",'DPW3'!JT12) | ¬¬IF(ISBLANK('DPW3'!JU12),"",'DPW3'!JU12) | ¬¬IF(ISBLANK('DPW3'!JV12),"",'DPW3'!JV12) | ¬¬IF(ISBLANK('DPW3'!JW12),"",'DPW3'!JW12) | ¬¬IF(ISBLANK('DPW3'!JX12),"",'DPW3'!JX12) | ¬¬IF(ISBLANK('DPW3'!JY12),"",'DPW3'!JY12) | ¬¬IF(ISBLANK('DPW3'!JZ12),"",'DPW3'!JZ12) | ¬¬IF(ISBLANK('DPW3'!KA12),"",'DPW3'!KA12) | ¬¬IF(ISBLANK('DPW3'!KB12),"",'DPW3'!KB12) | ¬¬IF(ISBLANK('DPW3'!KC12),"",'DPW3'!KC12) | ¬¬IF(ISBLANK('DPW3'!KD12),"",'DPW3'!KD12) | ¬¬IF(ISBLANK('DPW3'!KE12),"",'DPW3'!KE12) | ¬¬IF(ISBLANK('DPW3'!KF12),"",'DPW3'!KF12) | ¬¬IF(ISBLANK('DPW3'!KG12),"",'DPW3'!KG12) | ¬¬IF(ISBLANK('DPW3'!KH12),"",'DPW3'!KH12) | ¬¬IF(ISBLANK('DPW3'!KI12),"",'DPW3'!KI12) | ¬¬IF(ISBLANK('DPW3'!KJ12),"",'DPW3'!KJ12) | ¬¬IF(ISBLANK('DPW3'!KK12),"",'DPW3'!KK12) | ¬¬IF(ISBLANK('DPW3'!KL12),"",'DPW3'!KL12)
¬¬A1448 | ¬¬IF(ISBLANK('DPW3'!XW12),"",'DPW3'!XW12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN12),"",'DPW3'!KN12) | ¬¬IF(ISBLANK('DPW3'!KO12),"",'DPW3'!KO12) | ¬¬IF(ISBLANK('DPW3'!KP12),"",'DPW3'!KP12) | ¬¬IF(ISBLANK('DPW3'!KQ12),"",'DPW3'!KQ12) | ¬¬IF(ISBLANK('DPW3'!KR12),"",'DPW3'!KR12) | ¬¬IF(ISBLANK('DPW3'!KS12),"",'DPW3'!KS12) | ¬¬IF(ISBLANK('DPW3'!KT12),"",'DPW3'!KT12) | ¬¬IF(ISBLANK('DPW3'!KU12),"",'DPW3'!KU12) | ¬¬IF(ISBLANK('DPW3'!KV12),"",'DPW3'!KV12) | ¬¬IF(ISBLANK('DPW3'!KW12),"",'DPW3'!KW12) | ¬¬IF(ISBLANK('DPW3'!KX12),"",'DPW3'!KX12) | ¬¬IF(ISBLANK('DPW3'!KY12),"",'DPW3'!KY12) | ¬¬IF(ISBLANK('DPW3'!KZ12),"",'DPW3'!KZ12) | ¬¬IF(ISBLANK('DPW3'!LA12),"",'DPW3'!LA12) | ¬¬IF(ISBLANK('DPW3'!LB12),"",'DPW3'!LB12) | ¬¬IF(ISBLANK('DPW3'!LC12),"",'DPW3'!LC12) | ¬¬IF(ISBLANK('DPW3'!LD12),"",'DPW3'!LD12) | ¬¬IF(ISBLANK('DPW3'!LE12),"",'DPW3'!LE12) | ¬¬IF(ISBLANK('DPW3'!LF12),"",'DPW3'!LF12) | ¬¬IF(ISBLANK('DPW3'!LG12),"",'DPW3'!LG12) | ¬¬IF(ISBLANK('DPW3'!LH12),"",'DPW3'!LH12) | ¬¬IF(ISBLANK('DPW3'!LI12),"",'DPW3'!LI12) | ¬¬IF(ISBLANK('DPW3'!LJ12),"",'DPW3'!LJ12) | ¬¬IF(ISBLANK('DPW3'!LK12),"",'DPW3'!LK12) | ¬¬IF(ISBLANK('DPW3'!LL12),"",'DPW3'!LL12) | ¬¬IF(ISBLANK('DPW3'!LM12),"",'DPW3'!LM12) | ¬¬IF(ISBLANK('DPW3'!LN12),"",'DPW3'!LN12) | ¬¬IF(ISBLANK('DPW3'!LO12),"",'DPW3'!LO12) | ¬¬IF(ISBLANK('DPW3'!LP12),"",'DPW3'!LP12) | ¬¬IF(ISBLANK('DPW3'!LQ12),"",'DPW3'!LQ12) | ¬¬IF(ISBLANK('DPW3'!LR12),"",'DPW3'!LR12) | ¬¬IF(ISBLANK('DPW3'!LS12),"",'DPW3'!LS12) | ¬¬IF(ISBLANK('DPW3'!LT12),"",'DPW3'!LT12) | ¬¬IF(ISBLANK('DPW3'!LU12),"",'DPW3'!LU12) | ¬¬IF(ISBLANK('DPW3'!LV12),"",'DPW3'!LV12) | ¬¬IF(ISBLANK('DPW3'!LW12),"",'DPW3'!LW12) | ¬¬IF(ISBLANK('DPW3'!LX12),"",'DPW3'!LX12) | ¬¬IF(ISBLANK('DPW3'!LY12),"",'DPW3'!LY12) | ¬¬IF(ISBLANK('DPW3'!LZ12),"",'DPW3'!LZ12) | ¬¬IF(ISBLANK('DPW3'!MA12),"",'DPW3'!MA12)
¬¬A1449 | ¬¬IF(ISBLANK('DPW3'!ZL12),"",'DPW3'!ZL12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MC12),"",'DPW3'!MC12)
¬¬A1450 | ¬¬IF(ISBLANK('DPW3'!ZM12),"",'DPW3'!ZM12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MD12),"",'DPW3'!MD12)
¬¬A1451 | ¬¬IF(ISBLANK('DPW3'!ZN12),"",'DPW3'!ZN12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!ML12),"",'DPW3'!ML12)
¬¬A1452 | ¬¬IF(ISBLANK('DPW3'!ZO12),"",'DPW3'!ZO12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MF12),"",'DPW3'!MF12)
¬¬A1453 | ¬¬IF(ISBLANK('DPW3'!ZP12),"",'DPW3'!ZP12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MG12),"",'DPW3'!MG12)
¬¬A1454 | ¬¬IF(ISBLANK('DPW3'!ZQ12),"",'DPW3'!ZQ12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MH12),"",'DPW3'!MH12)
¬¬A1455 | ¬¬IF(ISBLANK('DPW3'!ZR12),"",'DPW3'!ZR12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MI12),"",'DPW3'!MI12)
¬¬A1456 | ¬¬IF(ISBLANK('DPW3'!ZS12),"",'DPW3'!ZS12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ12),"",'DPW3'!MJ12)
¬¬A1457 | ¬¬IF(ISBLANK('DPW3'!ZT12),"",'DPW3'!ZT12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MK12),"",'DPW3'!MK12)
¬¬A1458 | ¬¬IF(ISBLANK('DPW3'!ZV12),"",'DPW3'!ZV12) | ¬¬'DPW3'!F12 & "," & 'DPW3'!G12 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H12),"",'DPW3'!H12) | Delta | ¬¬IF(ISBLANK('DPW3'!MM12),"",'DPW3'!MM12)
¬¬A1459 | ¬¬IF(ISBLANK('DPW3'!MT13),"",'DPW3'!MT13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!K13),"",'DPW3'!K13)
¬¬A1460 | ¬¬IF(ISBLANK('DPW3'!MV13),"",'DPW3'!MV13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M13),"",'DPW3'!M13) | ¬¬IF(ISBLANK('DPW3'!N13),"",'DPW3'!N13) | ¬¬IF(ISBLANK('DPW3'!O13),"",'DPW3'!O13) | ¬¬IF(ISBLANK('DPW3'!P13),"",'DPW3'!P13) | ¬¬IF(ISBLANK('DPW3'!Q13),"",'DPW3'!Q13) | ¬¬IF(ISBLANK('DPW3'!R13),"",'DPW3'!R13) | ¬¬IF(ISBLANK('DPW3'!S13),"",'DPW3'!S13) | ¬¬IF(ISBLANK('DPW3'!T13),"",'DPW3'!T13) | ¬¬IF(ISBLANK('DPW3'!U13),"",'DPW3'!U13) | ¬¬IF(ISBLANK('DPW3'!V13),"",'DPW3'!V13) | ¬¬IF(ISBLANK('DPW3'!W13),"",'DPW3'!W13) | ¬¬IF(ISBLANK('DPW3'!X13),"",'DPW3'!X13) | ¬¬IF(ISBLANK('DPW3'!Y13),"",'DPW3'!Y13) | ¬¬IF(ISBLANK('DPW3'!Z13),"",'DPW3'!Z13) | ¬¬IF(ISBLANK('DPW3'!AA13),"",'DPW3'!AA13) | ¬¬IF(ISBLANK('DPW3'!AB13),"",'DPW3'!AB13) | ¬¬IF(ISBLANK('DPW3'!AC13),"",'DPW3'!AC13) | ¬¬IF(ISBLANK('DPW3'!AD13),"",'DPW3'!AD13) | ¬¬IF(ISBLANK('DPW3'!AE13),"",'DPW3'!AE13) | ¬¬IF(ISBLANK('DPW3'!AF13),"",'DPW3'!AF13) | ¬¬IF(ISBLANK('DPW3'!AG13),"",'DPW3'!AG13) | ¬¬IF(ISBLANK('DPW3'!AH13),"",'DPW3'!AH13) | ¬¬IF(ISBLANK('DPW3'!AI13),"",'DPW3'!AI13) | ¬¬IF(ISBLANK('DPW3'!AJ13),"",'DPW3'!AJ13) | ¬¬IF(ISBLANK('DPW3'!AK13),"",'DPW3'!AK13) | ¬¬IF(ISBLANK('DPW3'!AL13),"",'DPW3'!AL13) | ¬¬IF(ISBLANK('DPW3'!AM13),"",'DPW3'!AM13) | ¬¬IF(ISBLANK('DPW3'!AN13),"",'DPW3'!AN13) | ¬¬IF(ISBLANK('DPW3'!AO13),"",'DPW3'!AO13) | ¬¬IF(ISBLANK('DPW3'!AP13),"",'DPW3'!AP13) | ¬¬IF(ISBLANK('DPW3'!AQ13),"",'DPW3'!AQ13) | ¬¬IF(ISBLANK('DPW3'!AR13),"",'DPW3'!AR13) | ¬¬IF(ISBLANK('DPW3'!AS13),"",'DPW3'!AS13) | ¬¬IF(ISBLANK('DPW3'!AT13),"",'DPW3'!AT13) | ¬¬IF(ISBLANK('DPW3'!AU13),"",'DPW3'!AU13) | ¬¬IF(ISBLANK('DPW3'!AV13),"",'DPW3'!AV13) | ¬¬IF(ISBLANK('DPW3'!AW13),"",'DPW3'!AW13) | ¬¬IF(ISBLANK('DPW3'!AX13),"",'DPW3'!AX13) | ¬¬IF(ISBLANK('DPW3'!AY13),"",'DPW3'!AY13) | ¬¬IF(ISBLANK('DPW3'!AZ13),"",'DPW3'!AZ13)
¬¬A1461 | ¬¬IF(ISBLANK('DPW3'!OK13),"",'DPW3'!OK13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB13),"",'DPW3'!BB13) | ¬¬IF(ISBLANK('DPW3'!BC13),"",'DPW3'!BC13) | ¬¬IF(ISBLANK('DPW3'!BD13),"",'DPW3'!BD13) | ¬¬IF(ISBLANK('DPW3'!BE13),"",'DPW3'!BE13) | ¬¬IF(ISBLANK('DPW3'!BF13),"",'DPW3'!BF13) | ¬¬IF(ISBLANK('DPW3'!BG13),"",'DPW3'!BG13) | ¬¬IF(ISBLANK('DPW3'!BH13),"",'DPW3'!BH13) | ¬¬IF(ISBLANK('DPW3'!BI13),"",'DPW3'!BI13) | ¬¬IF(ISBLANK('DPW3'!BJ13),"",'DPW3'!BJ13) | ¬¬IF(ISBLANK('DPW3'!BK13),"",'DPW3'!BK13) | ¬¬IF(ISBLANK('DPW3'!BL13),"",'DPW3'!BL13) | ¬¬IF(ISBLANK('DPW3'!BM13),"",'DPW3'!BM13) | ¬¬IF(ISBLANK('DPW3'!BN13),"",'DPW3'!BN13) | ¬¬IF(ISBLANK('DPW3'!BO13),"",'DPW3'!BO13) | ¬¬IF(ISBLANK('DPW3'!BP13),"",'DPW3'!BP13) | ¬¬IF(ISBLANK('DPW3'!BQ13),"",'DPW3'!BQ13) | ¬¬IF(ISBLANK('DPW3'!BR13),"",'DPW3'!BR13) | ¬¬IF(ISBLANK('DPW3'!BS13),"",'DPW3'!BS13) | ¬¬IF(ISBLANK('DPW3'!BT13),"",'DPW3'!BT13) | ¬¬IF(ISBLANK('DPW3'!BU13),"",'DPW3'!BU13) | ¬¬IF(ISBLANK('DPW3'!BV13),"",'DPW3'!BV13) | ¬¬IF(ISBLANK('DPW3'!BW13),"",'DPW3'!BW13) | ¬¬IF(ISBLANK('DPW3'!BX13),"",'DPW3'!BX13) | ¬¬IF(ISBLANK('DPW3'!BY13),"",'DPW3'!BY13) | ¬¬IF(ISBLANK('DPW3'!BZ13),"",'DPW3'!BZ13) | ¬¬IF(ISBLANK('DPW3'!CA13),"",'DPW3'!CA13) | ¬¬IF(ISBLANK('DPW3'!CB13),"",'DPW3'!CB13) | ¬¬IF(ISBLANK('DPW3'!CC13),"",'DPW3'!CC13) | ¬¬IF(ISBLANK('DPW3'!CD13),"",'DPW3'!CD13) | ¬¬IF(ISBLANK('DPW3'!CE13),"",'DPW3'!CE13) | ¬¬IF(ISBLANK('DPW3'!CF13),"",'DPW3'!CF13) | ¬¬IF(ISBLANK('DPW3'!CG13),"",'DPW3'!CG13) | ¬¬IF(ISBLANK('DPW3'!CH13),"",'DPW3'!CH13) | ¬¬IF(ISBLANK('DPW3'!CI13),"",'DPW3'!CI13) | ¬¬IF(ISBLANK('DPW3'!CJ13),"",'DPW3'!CJ13) | ¬¬IF(ISBLANK('DPW3'!CK13),"",'DPW3'!CK13) | ¬¬IF(ISBLANK('DPW3'!CL13),"",'DPW3'!CL13) | ¬¬IF(ISBLANK('DPW3'!CM13),"",'DPW3'!CM13) | ¬¬IF(ISBLANK('DPW3'!CN13),"",'DPW3'!CN13) | ¬¬IF(ISBLANK('DPW3'!CO13),"",'DPW3'!CO13)
¬¬A1462 | ¬¬IF(ISBLANK('DPW3'!PZ13),"",'DPW3'!PZ13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ13),"",'DPW3'!CQ13) | ¬¬IF(ISBLANK('DPW3'!CR13),"",'DPW3'!CR13) | ¬¬IF(ISBLANK('DPW3'!CS13),"",'DPW3'!CS13) | ¬¬IF(ISBLANK('DPW3'!CT13),"",'DPW3'!CT13) | ¬¬IF(ISBLANK('DPW3'!CU13),"",'DPW3'!CU13) | ¬¬IF(ISBLANK('DPW3'!CV13),"",'DPW3'!CV13) | ¬¬IF(ISBLANK('DPW3'!CW13),"",'DPW3'!CW13) | ¬¬IF(ISBLANK('DPW3'!CX13),"",'DPW3'!CX13) | ¬¬IF(ISBLANK('DPW3'!CY13),"",'DPW3'!CY13) | ¬¬IF(ISBLANK('DPW3'!CZ13),"",'DPW3'!CZ13) | ¬¬IF(ISBLANK('DPW3'!DA13),"",'DPW3'!DA13) | ¬¬IF(ISBLANK('DPW3'!DB13),"",'DPW3'!DB13) | ¬¬IF(ISBLANK('DPW3'!DC13),"",'DPW3'!DC13) | ¬¬IF(ISBLANK('DPW3'!DD13),"",'DPW3'!DD13) | ¬¬IF(ISBLANK('DPW3'!DE13),"",'DPW3'!DE13) | ¬¬IF(ISBLANK('DPW3'!DF13),"",'DPW3'!DF13) | ¬¬IF(ISBLANK('DPW3'!DG13),"",'DPW3'!DG13) | ¬¬IF(ISBLANK('DPW3'!DH13),"",'DPW3'!DH13) | ¬¬IF(ISBLANK('DPW3'!DI13),"",'DPW3'!DI13) | ¬¬IF(ISBLANK('DPW3'!DJ13),"",'DPW3'!DJ13) | ¬¬IF(ISBLANK('DPW3'!DK13),"",'DPW3'!DK13) | ¬¬IF(ISBLANK('DPW3'!DL13),"",'DPW3'!DL13) | ¬¬IF(ISBLANK('DPW3'!DM13),"",'DPW3'!DM13) | ¬¬IF(ISBLANK('DPW3'!DN13),"",'DPW3'!DN13) | ¬¬IF(ISBLANK('DPW3'!DO13),"",'DPW3'!DO13) | ¬¬IF(ISBLANK('DPW3'!DP13),"",'DPW3'!DP13) | ¬¬IF(ISBLANK('DPW3'!DQ13),"",'DPW3'!DQ13) | ¬¬IF(ISBLANK('DPW3'!DR13),"",'DPW3'!DR13) | ¬¬IF(ISBLANK('DPW3'!DS13),"",'DPW3'!DS13) | ¬¬IF(ISBLANK('DPW3'!DT13),"",'DPW3'!DT13) | ¬¬IF(ISBLANK('DPW3'!DU13),"",'DPW3'!DU13) | ¬¬IF(ISBLANK('DPW3'!DV13),"",'DPW3'!DV13) | ¬¬IF(ISBLANK('DPW3'!DW13),"",'DPW3'!DW13) | ¬¬IF(ISBLANK('DPW3'!DX13),"",'DPW3'!DX13) | ¬¬IF(ISBLANK('DPW3'!DY13),"",'DPW3'!DY13) | ¬¬IF(ISBLANK('DPW3'!DZ13),"",'DPW3'!DZ13) | ¬¬IF(ISBLANK('DPW3'!EA13),"",'DPW3'!EA13) | ¬¬IF(ISBLANK('DPW3'!EB13),"",'DPW3'!EB13) | ¬¬IF(ISBLANK('DPW3'!EC13),"",'DPW3'!EC13) | ¬¬IF(ISBLANK('DPW3'!ED13),"",'DPW3'!ED13)
¬¬A1463 | ¬¬IF(ISBLANK('DPW3'!RO13),"",'DPW3'!RO13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF13),"",'DPW3'!EF13) | ¬¬IF(ISBLANK('DPW3'!EG13),"",'DPW3'!EG13) | ¬¬IF(ISBLANK('DPW3'!EH13),"",'DPW3'!EH13) | ¬¬IF(ISBLANK('DPW3'!EI13),"",'DPW3'!EI13) | ¬¬IF(ISBLANK('DPW3'!EJ13),"",'DPW3'!EJ13) | ¬¬IF(ISBLANK('DPW3'!EK13),"",'DPW3'!EK13) | ¬¬IF(ISBLANK('DPW3'!EL13),"",'DPW3'!EL13) | ¬¬IF(ISBLANK('DPW3'!EM13),"",'DPW3'!EM13) | ¬¬IF(ISBLANK('DPW3'!EN13),"",'DPW3'!EN13) | ¬¬IF(ISBLANK('DPW3'!EO13),"",'DPW3'!EO13) | ¬¬IF(ISBLANK('DPW3'!EP13),"",'DPW3'!EP13) | ¬¬IF(ISBLANK('DPW3'!EQ13),"",'DPW3'!EQ13) | ¬¬IF(ISBLANK('DPW3'!ER13),"",'DPW3'!ER13) | ¬¬IF(ISBLANK('DPW3'!ES13),"",'DPW3'!ES13) | ¬¬IF(ISBLANK('DPW3'!ET13),"",'DPW3'!ET13) | ¬¬IF(ISBLANK('DPW3'!EU13),"",'DPW3'!EU13) | ¬¬IF(ISBLANK('DPW3'!EV13),"",'DPW3'!EV13) | ¬¬IF(ISBLANK('DPW3'!EW13),"",'DPW3'!EW13) | ¬¬IF(ISBLANK('DPW3'!EX13),"",'DPW3'!EX13) | ¬¬IF(ISBLANK('DPW3'!EY13),"",'DPW3'!EY13) | ¬¬IF(ISBLANK('DPW3'!EZ13),"",'DPW3'!EZ13) | ¬¬IF(ISBLANK('DPW3'!FA13),"",'DPW3'!FA13) | ¬¬IF(ISBLANK('DPW3'!FB13),"",'DPW3'!FB13) | ¬¬IF(ISBLANK('DPW3'!FC13),"",'DPW3'!FC13) | ¬¬IF(ISBLANK('DPW3'!FD13),"",'DPW3'!FD13) | ¬¬IF(ISBLANK('DPW3'!FE13),"",'DPW3'!FE13) | ¬¬IF(ISBLANK('DPW3'!FF13),"",'DPW3'!FF13) | ¬¬IF(ISBLANK('DPW3'!FG13),"",'DPW3'!FG13) | ¬¬IF(ISBLANK('DPW3'!FH13),"",'DPW3'!FH13) | ¬¬IF(ISBLANK('DPW3'!FI13),"",'DPW3'!FI13) | ¬¬IF(ISBLANK('DPW3'!FJ13),"",'DPW3'!FJ13) | ¬¬IF(ISBLANK('DPW3'!FK13),"",'DPW3'!FK13) | ¬¬IF(ISBLANK('DPW3'!FL13),"",'DPW3'!FL13) | ¬¬IF(ISBLANK('DPW3'!FM13),"",'DPW3'!FM13) | ¬¬IF(ISBLANK('DPW3'!FN13),"",'DPW3'!FN13) | ¬¬IF(ISBLANK('DPW3'!FO13),"",'DPW3'!FO13) | ¬¬IF(ISBLANK('DPW3'!FP13),"",'DPW3'!FP13) | ¬¬IF(ISBLANK('DPW3'!FQ13),"",'DPW3'!FQ13) | ¬¬IF(ISBLANK('DPW3'!FR13),"",'DPW3'!FR13) | ¬¬IF(ISBLANK('DPW3'!FS13),"",'DPW3'!FS13)
¬¬A1464 | ¬¬IF(ISBLANK('DPW3'!TD13),"",'DPW3'!TD13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU13),"",'DPW3'!FU13) | ¬¬IF(ISBLANK('DPW3'!FV13),"",'DPW3'!FV13) | ¬¬IF(ISBLANK('DPW3'!FW13),"",'DPW3'!FW13) | ¬¬IF(ISBLANK('DPW3'!FX13),"",'DPW3'!FX13) | ¬¬IF(ISBLANK('DPW3'!FY13),"",'DPW3'!FY13) | ¬¬IF(ISBLANK('DPW3'!FZ13),"",'DPW3'!FZ13) | ¬¬IF(ISBLANK('DPW3'!GA13),"",'DPW3'!GA13) | ¬¬IF(ISBLANK('DPW3'!GB13),"",'DPW3'!GB13) | ¬¬IF(ISBLANK('DPW3'!GC13),"",'DPW3'!GC13) | ¬¬IF(ISBLANK('DPW3'!GD13),"",'DPW3'!GD13) | ¬¬IF(ISBLANK('DPW3'!GE13),"",'DPW3'!GE13) | ¬¬IF(ISBLANK('DPW3'!GF13),"",'DPW3'!GF13) | ¬¬IF(ISBLANK('DPW3'!GG13),"",'DPW3'!GG13) | ¬¬IF(ISBLANK('DPW3'!GH13),"",'DPW3'!GH13) | ¬¬IF(ISBLANK('DPW3'!GI13),"",'DPW3'!GI13) | ¬¬IF(ISBLANK('DPW3'!GJ13),"",'DPW3'!GJ13) | ¬¬IF(ISBLANK('DPW3'!GK13),"",'DPW3'!GK13) | ¬¬IF(ISBLANK('DPW3'!GL13),"",'DPW3'!GL13) | ¬¬IF(ISBLANK('DPW3'!GM13),"",'DPW3'!GM13) | ¬¬IF(ISBLANK('DPW3'!GN13),"",'DPW3'!GN13) | ¬¬IF(ISBLANK('DPW3'!GO13),"",'DPW3'!GO13) | ¬¬IF(ISBLANK('DPW3'!GP13),"",'DPW3'!GP13) | ¬¬IF(ISBLANK('DPW3'!GQ13),"",'DPW3'!GQ13) | ¬¬IF(ISBLANK('DPW3'!GR13),"",'DPW3'!GR13) | ¬¬IF(ISBLANK('DPW3'!GS13),"",'DPW3'!GS13) | ¬¬IF(ISBLANK('DPW3'!GT13),"",'DPW3'!GT13) | ¬¬IF(ISBLANK('DPW3'!GU13),"",'DPW3'!GU13) | ¬¬IF(ISBLANK('DPW3'!GV13),"",'DPW3'!GV13) | ¬¬IF(ISBLANK('DPW3'!GW13),"",'DPW3'!GW13) | ¬¬IF(ISBLANK('DPW3'!GX13),"",'DPW3'!GX13) | ¬¬IF(ISBLANK('DPW3'!GY13),"",'DPW3'!GY13) | ¬¬IF(ISBLANK('DPW3'!GZ13),"",'DPW3'!GZ13) | ¬¬IF(ISBLANK('DPW3'!HA13),"",'DPW3'!HA13) | ¬¬IF(ISBLANK('DPW3'!HB13),"",'DPW3'!HB13) | ¬¬IF(ISBLANK('DPW3'!HC13),"",'DPW3'!HC13) | ¬¬IF(ISBLANK('DPW3'!HD13),"",'DPW3'!HD13) | ¬¬IF(ISBLANK('DPW3'!HE13),"",'DPW3'!HE13) | ¬¬IF(ISBLANK('DPW3'!HF13),"",'DPW3'!HF13) | ¬¬IF(ISBLANK('DPW3'!HG13),"",'DPW3'!HG13) | ¬¬IF(ISBLANK('DPW3'!HH13),"",'DPW3'!HH13)
¬¬A1465 | ¬¬IF(ISBLANK('DPW3'!US13),"",'DPW3'!US13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ13),"",'DPW3'!HJ13) | ¬¬IF(ISBLANK('DPW3'!HK13),"",'DPW3'!HK13) | ¬¬IF(ISBLANK('DPW3'!HL13),"",'DPW3'!HL13) | ¬¬IF(ISBLANK('DPW3'!HM13),"",'DPW3'!HM13) | ¬¬IF(ISBLANK('DPW3'!HN13),"",'DPW3'!HN13) | ¬¬IF(ISBLANK('DPW3'!HO13),"",'DPW3'!HO13) | ¬¬IF(ISBLANK('DPW3'!HP13),"",'DPW3'!HP13) | ¬¬IF(ISBLANK('DPW3'!HQ13),"",'DPW3'!HQ13) | ¬¬IF(ISBLANK('DPW3'!HR13),"",'DPW3'!HR13) | ¬¬IF(ISBLANK('DPW3'!HS13),"",'DPW3'!HS13) | ¬¬IF(ISBLANK('DPW3'!HT13),"",'DPW3'!HT13) | ¬¬IF(ISBLANK('DPW3'!HU13),"",'DPW3'!HU13) | ¬¬IF(ISBLANK('DPW3'!HV13),"",'DPW3'!HV13) | ¬¬IF(ISBLANK('DPW3'!HW13),"",'DPW3'!HW13) | ¬¬IF(ISBLANK('DPW3'!HX13),"",'DPW3'!HX13) | ¬¬IF(ISBLANK('DPW3'!HY13),"",'DPW3'!HY13) | ¬¬IF(ISBLANK('DPW3'!HZ13),"",'DPW3'!HZ13) | ¬¬IF(ISBLANK('DPW3'!IA13),"",'DPW3'!IA13) | ¬¬IF(ISBLANK('DPW3'!IB13),"",'DPW3'!IB13) | ¬¬IF(ISBLANK('DPW3'!IC13),"",'DPW3'!IC13) | ¬¬IF(ISBLANK('DPW3'!ID13),"",'DPW3'!ID13) | ¬¬IF(ISBLANK('DPW3'!IE13),"",'DPW3'!IE13) | ¬¬IF(ISBLANK('DPW3'!IF13),"",'DPW3'!IF13) | ¬¬IF(ISBLANK('DPW3'!IG13),"",'DPW3'!IG13) | ¬¬IF(ISBLANK('DPW3'!IH13),"",'DPW3'!IH13) | ¬¬IF(ISBLANK('DPW3'!II13),"",'DPW3'!II13) | ¬¬IF(ISBLANK('DPW3'!IJ13),"",'DPW3'!IJ13) | ¬¬IF(ISBLANK('DPW3'!IK13),"",'DPW3'!IK13) | ¬¬IF(ISBLANK('DPW3'!IL13),"",'DPW3'!IL13) | ¬¬IF(ISBLANK('DPW3'!IM13),"",'DPW3'!IM13) | ¬¬IF(ISBLANK('DPW3'!IN13),"",'DPW3'!IN13) | ¬¬IF(ISBLANK('DPW3'!IO13),"",'DPW3'!IO13) | ¬¬IF(ISBLANK('DPW3'!IP13),"",'DPW3'!IP13) | ¬¬IF(ISBLANK('DPW3'!IQ13),"",'DPW3'!IQ13) | ¬¬IF(ISBLANK('DPW3'!IR13),"",'DPW3'!IR13) | ¬¬IF(ISBLANK('DPW3'!IS13),"",'DPW3'!IS13) | ¬¬IF(ISBLANK('DPW3'!IT13),"",'DPW3'!IT13) | ¬¬IF(ISBLANK('DPW3'!IU13),"",'DPW3'!IU13) | ¬¬IF(ISBLANK('DPW3'!IV13),"",'DPW3'!IV13) | ¬¬IF(ISBLANK('DPW3'!IW13),"",'DPW3'!IW13)
¬¬A1466 | ¬¬IF(ISBLANK('DPW3'!WH13),"",'DPW3'!WH13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY13),"",'DPW3'!IY13) | ¬¬IF(ISBLANK('DPW3'!IZ13),"",'DPW3'!IZ13) | ¬¬IF(ISBLANK('DPW3'!JA13),"",'DPW3'!JA13) | ¬¬IF(ISBLANK('DPW3'!JB13),"",'DPW3'!JB13) | ¬¬IF(ISBLANK('DPW3'!JC13),"",'DPW3'!JC13) | ¬¬IF(ISBLANK('DPW3'!JD13),"",'DPW3'!JD13) | ¬¬IF(ISBLANK('DPW3'!JE13),"",'DPW3'!JE13) | ¬¬IF(ISBLANK('DPW3'!JF13),"",'DPW3'!JF13) | ¬¬IF(ISBLANK('DPW3'!JG13),"",'DPW3'!JG13) | ¬¬IF(ISBLANK('DPW3'!JH13),"",'DPW3'!JH13) | ¬¬IF(ISBLANK('DPW3'!JI13),"",'DPW3'!JI13) | ¬¬IF(ISBLANK('DPW3'!JJ13),"",'DPW3'!JJ13) | ¬¬IF(ISBLANK('DPW3'!JK13),"",'DPW3'!JK13) | ¬¬IF(ISBLANK('DPW3'!JL13),"",'DPW3'!JL13) | ¬¬IF(ISBLANK('DPW3'!JM13),"",'DPW3'!JM13) | ¬¬IF(ISBLANK('DPW3'!JN13),"",'DPW3'!JN13) | ¬¬IF(ISBLANK('DPW3'!JO13),"",'DPW3'!JO13) | ¬¬IF(ISBLANK('DPW3'!JP13),"",'DPW3'!JP13) | ¬¬IF(ISBLANK('DPW3'!JQ13),"",'DPW3'!JQ13) | ¬¬IF(ISBLANK('DPW3'!JR13),"",'DPW3'!JR13) | ¬¬IF(ISBLANK('DPW3'!JS13),"",'DPW3'!JS13) | ¬¬IF(ISBLANK('DPW3'!JT13),"",'DPW3'!JT13) | ¬¬IF(ISBLANK('DPW3'!JU13),"",'DPW3'!JU13) | ¬¬IF(ISBLANK('DPW3'!JV13),"",'DPW3'!JV13) | ¬¬IF(ISBLANK('DPW3'!JW13),"",'DPW3'!JW13) | ¬¬IF(ISBLANK('DPW3'!JX13),"",'DPW3'!JX13) | ¬¬IF(ISBLANK('DPW3'!JY13),"",'DPW3'!JY13) | ¬¬IF(ISBLANK('DPW3'!JZ13),"",'DPW3'!JZ13) | ¬¬IF(ISBLANK('DPW3'!KA13),"",'DPW3'!KA13) | ¬¬IF(ISBLANK('DPW3'!KB13),"",'DPW3'!KB13) | ¬¬IF(ISBLANK('DPW3'!KC13),"",'DPW3'!KC13) | ¬¬IF(ISBLANK('DPW3'!KD13),"",'DPW3'!KD13) | ¬¬IF(ISBLANK('DPW3'!KE13),"",'DPW3'!KE13) | ¬¬IF(ISBLANK('DPW3'!KF13),"",'DPW3'!KF13) | ¬¬IF(ISBLANK('DPW3'!KG13),"",'DPW3'!KG13) | ¬¬IF(ISBLANK('DPW3'!KH13),"",'DPW3'!KH13) | ¬¬IF(ISBLANK('DPW3'!KI13),"",'DPW3'!KI13) | ¬¬IF(ISBLANK('DPW3'!KJ13),"",'DPW3'!KJ13) | ¬¬IF(ISBLANK('DPW3'!KK13),"",'DPW3'!KK13) | ¬¬IF(ISBLANK('DPW3'!KL13),"",'DPW3'!KL13)
¬¬A1467 | ¬¬IF(ISBLANK('DPW3'!XW13),"",'DPW3'!XW13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN13),"",'DPW3'!KN13) | ¬¬IF(ISBLANK('DPW3'!KO13),"",'DPW3'!KO13) | ¬¬IF(ISBLANK('DPW3'!KP13),"",'DPW3'!KP13) | ¬¬IF(ISBLANK('DPW3'!KQ13),"",'DPW3'!KQ13) | ¬¬IF(ISBLANK('DPW3'!KR13),"",'DPW3'!KR13) | ¬¬IF(ISBLANK('DPW3'!KS13),"",'DPW3'!KS13) | ¬¬IF(ISBLANK('DPW3'!KT13),"",'DPW3'!KT13) | ¬¬IF(ISBLANK('DPW3'!KU13),"",'DPW3'!KU13) | ¬¬IF(ISBLANK('DPW3'!KV13),"",'DPW3'!KV13) | ¬¬IF(ISBLANK('DPW3'!KW13),"",'DPW3'!KW13) | ¬¬IF(ISBLANK('DPW3'!KX13),"",'DPW3'!KX13) | ¬¬IF(ISBLANK('DPW3'!KY13),"",'DPW3'!KY13) | ¬¬IF(ISBLANK('DPW3'!KZ13),"",'DPW3'!KZ13) | ¬¬IF(ISBLANK('DPW3'!LA13),"",'DPW3'!LA13) | ¬¬IF(ISBLANK('DPW3'!LB13),"",'DPW3'!LB13) | ¬¬IF(ISBLANK('DPW3'!LC13),"",'DPW3'!LC13) | ¬¬IF(ISBLANK('DPW3'!LD13),"",'DPW3'!LD13) | ¬¬IF(ISBLANK('DPW3'!LE13),"",'DPW3'!LE13) | ¬¬IF(ISBLANK('DPW3'!LF13),"",'DPW3'!LF13) | ¬¬IF(ISBLANK('DPW3'!LG13),"",'DPW3'!LG13) | ¬¬IF(ISBLANK('DPW3'!LH13),"",'DPW3'!LH13) | ¬¬IF(ISBLANK('DPW3'!LI13),"",'DPW3'!LI13) | ¬¬IF(ISBLANK('DPW3'!LJ13),"",'DPW3'!LJ13) | ¬¬IF(ISBLANK('DPW3'!LK13),"",'DPW3'!LK13) | ¬¬IF(ISBLANK('DPW3'!LL13),"",'DPW3'!LL13) | ¬¬IF(ISBLANK('DPW3'!LM13),"",'DPW3'!LM13) | ¬¬IF(ISBLANK('DPW3'!LN13),"",'DPW3'!LN13) | ¬¬IF(ISBLANK('DPW3'!LO13),"",'DPW3'!LO13) | ¬¬IF(ISBLANK('DPW3'!LP13),"",'DPW3'!LP13) | ¬¬IF(ISBLANK('DPW3'!LQ13),"",'DPW3'!LQ13) | ¬¬IF(ISBLANK('DPW3'!LR13),"",'DPW3'!LR13) | ¬¬IF(ISBLANK('DPW3'!LS13),"",'DPW3'!LS13) | ¬¬IF(ISBLANK('DPW3'!LT13),"",'DPW3'!LT13) | ¬¬IF(ISBLANK('DPW3'!LU13),"",'DPW3'!LU13) | ¬¬IF(ISBLANK('DPW3'!LV13),"",'DPW3'!LV13) | ¬¬IF(ISBLANK('DPW3'!LW13),"",'DPW3'!LW13) | ¬¬IF(ISBLANK('DPW3'!LX13),"",'DPW3'!LX13) | ¬¬IF(ISBLANK('DPW3'!LY13),"",'DPW3'!LY13) | ¬¬IF(ISBLANK('DPW3'!LZ13),"",'DPW3'!LZ13) | ¬¬IF(ISBLANK('DPW3'!MA13),"",'DPW3'!MA13)
¬¬A1468 | ¬¬IF(ISBLANK('DPW3'!ZL13),"",'DPW3'!ZL13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MC13),"",'DPW3'!MC13)
¬¬A1469 | ¬¬IF(ISBLANK('DPW3'!ZM13),"",'DPW3'!ZM13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MD13),"",'DPW3'!MD13)
¬¬A1470 | ¬¬IF(ISBLANK('DPW3'!ZN13),"",'DPW3'!ZN13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!ML13),"",'DPW3'!ML13)
¬¬A1471 | ¬¬IF(ISBLANK('DPW3'!ZO13),"",'DPW3'!ZO13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MF13),"",'DPW3'!MF13)
¬¬A1472 | ¬¬IF(ISBLANK('DPW3'!ZP13),"",'DPW3'!ZP13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MG13),"",'DPW3'!MG13)
¬¬A1473 | ¬¬IF(ISBLANK('DPW3'!ZQ13),"",'DPW3'!ZQ13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MH13),"",'DPW3'!MH13)
¬¬A1474 | ¬¬IF(ISBLANK('DPW3'!ZR13),"",'DPW3'!ZR13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MI13),"",'DPW3'!MI13)
¬¬A1475 | ¬¬IF(ISBLANK('DPW3'!ZS13),"",'DPW3'!ZS13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ13),"",'DPW3'!MJ13)
¬¬A1476 | ¬¬IF(ISBLANK('DPW3'!ZT13),"",'DPW3'!ZT13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MK13),"",'DPW3'!MK13)
¬¬A1477 | ¬¬IF(ISBLANK('DPW3'!ZV13),"",'DPW3'!ZV13) | ¬¬'DPW3'!F13 & "," & 'DPW3'!G13 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H13),"",'DPW3'!H13) | Delta | ¬¬IF(ISBLANK('DPW3'!MM13),"",'DPW3'!MM13)
¬¬A1478 | ¬¬IF(ISBLANK('DPW3'!MT14),"",'DPW3'!MT14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!K14),"",'DPW3'!K14)
¬¬A1479 | ¬¬IF(ISBLANK('DPW3'!MV14),"",'DPW3'!MV14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M14),"",'DPW3'!M14) | ¬¬IF(ISBLANK('DPW3'!N14),"",'DPW3'!N14) | ¬¬IF(ISBLANK('DPW3'!O14),"",'DPW3'!O14) | ¬¬IF(ISBLANK('DPW3'!P14),"",'DPW3'!P14) | ¬¬IF(ISBLANK('DPW3'!Q14),"",'DPW3'!Q14) | ¬¬IF(ISBLANK('DPW3'!R14),"",'DPW3'!R14) | ¬¬IF(ISBLANK('DPW3'!S14),"",'DPW3'!S14) | ¬¬IF(ISBLANK('DPW3'!T14),"",'DPW3'!T14) | ¬¬IF(ISBLANK('DPW3'!U14),"",'DPW3'!U14) | ¬¬IF(ISBLANK('DPW3'!V14),"",'DPW3'!V14) | ¬¬IF(ISBLANK('DPW3'!W14),"",'DPW3'!W14) | ¬¬IF(ISBLANK('DPW3'!X14),"",'DPW3'!X14) | ¬¬IF(ISBLANK('DPW3'!Y14),"",'DPW3'!Y14) | ¬¬IF(ISBLANK('DPW3'!Z14),"",'DPW3'!Z14) | ¬¬IF(ISBLANK('DPW3'!AA14),"",'DPW3'!AA14) | ¬¬IF(ISBLANK('DPW3'!AB14),"",'DPW3'!AB14) | ¬¬IF(ISBLANK('DPW3'!AC14),"",'DPW3'!AC14) | ¬¬IF(ISBLANK('DPW3'!AD14),"",'DPW3'!AD14) | ¬¬IF(ISBLANK('DPW3'!AE14),"",'DPW3'!AE14) | ¬¬IF(ISBLANK('DPW3'!AF14),"",'DPW3'!AF14) | ¬¬IF(ISBLANK('DPW3'!AG14),"",'DPW3'!AG14) | ¬¬IF(ISBLANK('DPW3'!AH14),"",'DPW3'!AH14) | ¬¬IF(ISBLANK('DPW3'!AI14),"",'DPW3'!AI14) | ¬¬IF(ISBLANK('DPW3'!AJ14),"",'DPW3'!AJ14) | ¬¬IF(ISBLANK('DPW3'!AK14),"",'DPW3'!AK14) | ¬¬IF(ISBLANK('DPW3'!AL14),"",'DPW3'!AL14) | ¬¬IF(ISBLANK('DPW3'!AM14),"",'DPW3'!AM14) | ¬¬IF(ISBLANK('DPW3'!AN14),"",'DPW3'!AN14) | ¬¬IF(ISBLANK('DPW3'!AO14),"",'DPW3'!AO14) | ¬¬IF(ISBLANK('DPW3'!AP14),"",'DPW3'!AP14) | ¬¬IF(ISBLANK('DPW3'!AQ14),"",'DPW3'!AQ14) | ¬¬IF(ISBLANK('DPW3'!AR14),"",'DPW3'!AR14) | ¬¬IF(ISBLANK('DPW3'!AS14),"",'DPW3'!AS14) | ¬¬IF(ISBLANK('DPW3'!AT14),"",'DPW3'!AT14) | ¬¬IF(ISBLANK('DPW3'!AU14),"",'DPW3'!AU14) | ¬¬IF(ISBLANK('DPW3'!AV14),"",'DPW3'!AV14) | ¬¬IF(ISBLANK('DPW3'!AW14),"",'DPW3'!AW14) | ¬¬IF(ISBLANK('DPW3'!AX14),"",'DPW3'!AX14) | ¬¬IF(ISBLANK('DPW3'!AY14),"",'DPW3'!AY14) | ¬¬IF(ISBLANK('DPW3'!AZ14),"",'DPW3'!AZ14)
¬¬A1480 | ¬¬IF(ISBLANK('DPW3'!OK14),"",'DPW3'!OK14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB14),"",'DPW3'!BB14) | ¬¬IF(ISBLANK('DPW3'!BC14),"",'DPW3'!BC14) | ¬¬IF(ISBLANK('DPW3'!BD14),"",'DPW3'!BD14) | ¬¬IF(ISBLANK('DPW3'!BE14),"",'DPW3'!BE14) | ¬¬IF(ISBLANK('DPW3'!BF14),"",'DPW3'!BF14) | ¬¬IF(ISBLANK('DPW3'!BG14),"",'DPW3'!BG14) | ¬¬IF(ISBLANK('DPW3'!BH14),"",'DPW3'!BH14) | ¬¬IF(ISBLANK('DPW3'!BI14),"",'DPW3'!BI14) | ¬¬IF(ISBLANK('DPW3'!BJ14),"",'DPW3'!BJ14) | ¬¬IF(ISBLANK('DPW3'!BK14),"",'DPW3'!BK14) | ¬¬IF(ISBLANK('DPW3'!BL14),"",'DPW3'!BL14) | ¬¬IF(ISBLANK('DPW3'!BM14),"",'DPW3'!BM14) | ¬¬IF(ISBLANK('DPW3'!BN14),"",'DPW3'!BN14) | ¬¬IF(ISBLANK('DPW3'!BO14),"",'DPW3'!BO14) | ¬¬IF(ISBLANK('DPW3'!BP14),"",'DPW3'!BP14) | ¬¬IF(ISBLANK('DPW3'!BQ14),"",'DPW3'!BQ14) | ¬¬IF(ISBLANK('DPW3'!BR14),"",'DPW3'!BR14) | ¬¬IF(ISBLANK('DPW3'!BS14),"",'DPW3'!BS14) | ¬¬IF(ISBLANK('DPW3'!BT14),"",'DPW3'!BT14) | ¬¬IF(ISBLANK('DPW3'!BU14),"",'DPW3'!BU14) | ¬¬IF(ISBLANK('DPW3'!BV14),"",'DPW3'!BV14) | ¬¬IF(ISBLANK('DPW3'!BW14),"",'DPW3'!BW14) | ¬¬IF(ISBLANK('DPW3'!BX14),"",'DPW3'!BX14) | ¬¬IF(ISBLANK('DPW3'!BY14),"",'DPW3'!BY14) | ¬¬IF(ISBLANK('DPW3'!BZ14),"",'DPW3'!BZ14) | ¬¬IF(ISBLANK('DPW3'!CA14),"",'DPW3'!CA14) | ¬¬IF(ISBLANK('DPW3'!CB14),"",'DPW3'!CB14) | ¬¬IF(ISBLANK('DPW3'!CC14),"",'DPW3'!CC14) | ¬¬IF(ISBLANK('DPW3'!CD14),"",'DPW3'!CD14) | ¬¬IF(ISBLANK('DPW3'!CE14),"",'DPW3'!CE14) | ¬¬IF(ISBLANK('DPW3'!CF14),"",'DPW3'!CF14) | ¬¬IF(ISBLANK('DPW3'!CG14),"",'DPW3'!CG14) | ¬¬IF(ISBLANK('DPW3'!CH14),"",'DPW3'!CH14) | ¬¬IF(ISBLANK('DPW3'!CI14),"",'DPW3'!CI14) | ¬¬IF(ISBLANK('DPW3'!CJ14),"",'DPW3'!CJ14) | ¬¬IF(ISBLANK('DPW3'!CK14),"",'DPW3'!CK14) | ¬¬IF(ISBLANK('DPW3'!CL14),"",'DPW3'!CL14) | ¬¬IF(ISBLANK('DPW3'!CM14),"",'DPW3'!CM14) | ¬¬IF(ISBLANK('DPW3'!CN14),"",'DPW3'!CN14) | ¬¬IF(ISBLANK('DPW3'!CO14),"",'DPW3'!CO14)
¬¬A1481 | ¬¬IF(ISBLANK('DPW3'!PZ14),"",'DPW3'!PZ14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ14),"",'DPW3'!CQ14) | ¬¬IF(ISBLANK('DPW3'!CR14),"",'DPW3'!CR14) | ¬¬IF(ISBLANK('DPW3'!CS14),"",'DPW3'!CS14) | ¬¬IF(ISBLANK('DPW3'!CT14),"",'DPW3'!CT14) | ¬¬IF(ISBLANK('DPW3'!CU14),"",'DPW3'!CU14) | ¬¬IF(ISBLANK('DPW3'!CV14),"",'DPW3'!CV14) | ¬¬IF(ISBLANK('DPW3'!CW14),"",'DPW3'!CW14) | ¬¬IF(ISBLANK('DPW3'!CX14),"",'DPW3'!CX14) | ¬¬IF(ISBLANK('DPW3'!CY14),"",'DPW3'!CY14) | ¬¬IF(ISBLANK('DPW3'!CZ14),"",'DPW3'!CZ14) | ¬¬IF(ISBLANK('DPW3'!DA14),"",'DPW3'!DA14) | ¬¬IF(ISBLANK('DPW3'!DB14),"",'DPW3'!DB14) | ¬¬IF(ISBLANK('DPW3'!DC14),"",'DPW3'!DC14) | ¬¬IF(ISBLANK('DPW3'!DD14),"",'DPW3'!DD14) | ¬¬IF(ISBLANK('DPW3'!DE14),"",'DPW3'!DE14) | ¬¬IF(ISBLANK('DPW3'!DF14),"",'DPW3'!DF14) | ¬¬IF(ISBLANK('DPW3'!DG14),"",'DPW3'!DG14) | ¬¬IF(ISBLANK('DPW3'!DH14),"",'DPW3'!DH14) | ¬¬IF(ISBLANK('DPW3'!DI14),"",'DPW3'!DI14) | ¬¬IF(ISBLANK('DPW3'!DJ14),"",'DPW3'!DJ14) | ¬¬IF(ISBLANK('DPW3'!DK14),"",'DPW3'!DK14) | ¬¬IF(ISBLANK('DPW3'!DL14),"",'DPW3'!DL14) | ¬¬IF(ISBLANK('DPW3'!DM14),"",'DPW3'!DM14) | ¬¬IF(ISBLANK('DPW3'!DN14),"",'DPW3'!DN14) | ¬¬IF(ISBLANK('DPW3'!DO14),"",'DPW3'!DO14) | ¬¬IF(ISBLANK('DPW3'!DP14),"",'DPW3'!DP14) | ¬¬IF(ISBLANK('DPW3'!DQ14),"",'DPW3'!DQ14) | ¬¬IF(ISBLANK('DPW3'!DR14),"",'DPW3'!DR14) | ¬¬IF(ISBLANK('DPW3'!DS14),"",'DPW3'!DS14) | ¬¬IF(ISBLANK('DPW3'!DT14),"",'DPW3'!DT14) | ¬¬IF(ISBLANK('DPW3'!DU14),"",'DPW3'!DU14) | ¬¬IF(ISBLANK('DPW3'!DV14),"",'DPW3'!DV14) | ¬¬IF(ISBLANK('DPW3'!DW14),"",'DPW3'!DW14) | ¬¬IF(ISBLANK('DPW3'!DX14),"",'DPW3'!DX14) | ¬¬IF(ISBLANK('DPW3'!DY14),"",'DPW3'!DY14) | ¬¬IF(ISBLANK('DPW3'!DZ14),"",'DPW3'!DZ14) | ¬¬IF(ISBLANK('DPW3'!EA14),"",'DPW3'!EA14) | ¬¬IF(ISBLANK('DPW3'!EB14),"",'DPW3'!EB14) | ¬¬IF(ISBLANK('DPW3'!EC14),"",'DPW3'!EC14) | ¬¬IF(ISBLANK('DPW3'!ED14),"",'DPW3'!ED14)
¬¬A1482 | ¬¬IF(ISBLANK('DPW3'!RO14),"",'DPW3'!RO14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF14),"",'DPW3'!EF14) | ¬¬IF(ISBLANK('DPW3'!EG14),"",'DPW3'!EG14) | ¬¬IF(ISBLANK('DPW3'!EH14),"",'DPW3'!EH14) | ¬¬IF(ISBLANK('DPW3'!EI14),"",'DPW3'!EI14) | ¬¬IF(ISBLANK('DPW3'!EJ14),"",'DPW3'!EJ14) | ¬¬IF(ISBLANK('DPW3'!EK14),"",'DPW3'!EK14) | ¬¬IF(ISBLANK('DPW3'!EL14),"",'DPW3'!EL14) | ¬¬IF(ISBLANK('DPW3'!EM14),"",'DPW3'!EM14) | ¬¬IF(ISBLANK('DPW3'!EN14),"",'DPW3'!EN14) | ¬¬IF(ISBLANK('DPW3'!EO14),"",'DPW3'!EO14) | ¬¬IF(ISBLANK('DPW3'!EP14),"",'DPW3'!EP14) | ¬¬IF(ISBLANK('DPW3'!EQ14),"",'DPW3'!EQ14) | ¬¬IF(ISBLANK('DPW3'!ER14),"",'DPW3'!ER14) | ¬¬IF(ISBLANK('DPW3'!ES14),"",'DPW3'!ES14) | ¬¬IF(ISBLANK('DPW3'!ET14),"",'DPW3'!ET14) | ¬¬IF(ISBLANK('DPW3'!EU14),"",'DPW3'!EU14) | ¬¬IF(ISBLANK('DPW3'!EV14),"",'DPW3'!EV14) | ¬¬IF(ISBLANK('DPW3'!EW14),"",'DPW3'!EW14) | ¬¬IF(ISBLANK('DPW3'!EX14),"",'DPW3'!EX14) | ¬¬IF(ISBLANK('DPW3'!EY14),"",'DPW3'!EY14) | ¬¬IF(ISBLANK('DPW3'!EZ14),"",'DPW3'!EZ14) | ¬¬IF(ISBLANK('DPW3'!FA14),"",'DPW3'!FA14) | ¬¬IF(ISBLANK('DPW3'!FB14),"",'DPW3'!FB14) | ¬¬IF(ISBLANK('DPW3'!FC14),"",'DPW3'!FC14) | ¬¬IF(ISBLANK('DPW3'!FD14),"",'DPW3'!FD14) | ¬¬IF(ISBLANK('DPW3'!FE14),"",'DPW3'!FE14) | ¬¬IF(ISBLANK('DPW3'!FF14),"",'DPW3'!FF14) | ¬¬IF(ISBLANK('DPW3'!FG14),"",'DPW3'!FG14) | ¬¬IF(ISBLANK('DPW3'!FH14),"",'DPW3'!FH14) | ¬¬IF(ISBLANK('DPW3'!FI14),"",'DPW3'!FI14) | ¬¬IF(ISBLANK('DPW3'!FJ14),"",'DPW3'!FJ14) | ¬¬IF(ISBLANK('DPW3'!FK14),"",'DPW3'!FK14) | ¬¬IF(ISBLANK('DPW3'!FL14),"",'DPW3'!FL14) | ¬¬IF(ISBLANK('DPW3'!FM14),"",'DPW3'!FM14) | ¬¬IF(ISBLANK('DPW3'!FN14),"",'DPW3'!FN14) | ¬¬IF(ISBLANK('DPW3'!FO14),"",'DPW3'!FO14) | ¬¬IF(ISBLANK('DPW3'!FP14),"",'DPW3'!FP14) | ¬¬IF(ISBLANK('DPW3'!FQ14),"",'DPW3'!FQ14) | ¬¬IF(ISBLANK('DPW3'!FR14),"",'DPW3'!FR14) | ¬¬IF(ISBLANK('DPW3'!FS14),"",'DPW3'!FS14)
¬¬A1483 | ¬¬IF(ISBLANK('DPW3'!TD14),"",'DPW3'!TD14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU14),"",'DPW3'!FU14) | ¬¬IF(ISBLANK('DPW3'!FV14),"",'DPW3'!FV14) | ¬¬IF(ISBLANK('DPW3'!FW14),"",'DPW3'!FW14) | ¬¬IF(ISBLANK('DPW3'!FX14),"",'DPW3'!FX14) | ¬¬IF(ISBLANK('DPW3'!FY14),"",'DPW3'!FY14) | ¬¬IF(ISBLANK('DPW3'!FZ14),"",'DPW3'!FZ14) | ¬¬IF(ISBLANK('DPW3'!GA14),"",'DPW3'!GA14) | ¬¬IF(ISBLANK('DPW3'!GB14),"",'DPW3'!GB14) | ¬¬IF(ISBLANK('DPW3'!GC14),"",'DPW3'!GC14) | ¬¬IF(ISBLANK('DPW3'!GD14),"",'DPW3'!GD14) | ¬¬IF(ISBLANK('DPW3'!GE14),"",'DPW3'!GE14) | ¬¬IF(ISBLANK('DPW3'!GF14),"",'DPW3'!GF14) | ¬¬IF(ISBLANK('DPW3'!GG14),"",'DPW3'!GG14) | ¬¬IF(ISBLANK('DPW3'!GH14),"",'DPW3'!GH14) | ¬¬IF(ISBLANK('DPW3'!GI14),"",'DPW3'!GI14) | ¬¬IF(ISBLANK('DPW3'!GJ14),"",'DPW3'!GJ14) | ¬¬IF(ISBLANK('DPW3'!GK14),"",'DPW3'!GK14) | ¬¬IF(ISBLANK('DPW3'!GL14),"",'DPW3'!GL14) | ¬¬IF(ISBLANK('DPW3'!GM14),"",'DPW3'!GM14) | ¬¬IF(ISBLANK('DPW3'!GN14),"",'DPW3'!GN14) | ¬¬IF(ISBLANK('DPW3'!GO14),"",'DPW3'!GO14) | ¬¬IF(ISBLANK('DPW3'!GP14),"",'DPW3'!GP14) | ¬¬IF(ISBLANK('DPW3'!GQ14),"",'DPW3'!GQ14) | ¬¬IF(ISBLANK('DPW3'!GR14),"",'DPW3'!GR14) | ¬¬IF(ISBLANK('DPW3'!GS14),"",'DPW3'!GS14) | ¬¬IF(ISBLANK('DPW3'!GT14),"",'DPW3'!GT14) | ¬¬IF(ISBLANK('DPW3'!GU14),"",'DPW3'!GU14) | ¬¬IF(ISBLANK('DPW3'!GV14),"",'DPW3'!GV14) | ¬¬IF(ISBLANK('DPW3'!GW14),"",'DPW3'!GW14) | ¬¬IF(ISBLANK('DPW3'!GX14),"",'DPW3'!GX14) | ¬¬IF(ISBLANK('DPW3'!GY14),"",'DPW3'!GY14) | ¬¬IF(ISBLANK('DPW3'!GZ14),"",'DPW3'!GZ14) | ¬¬IF(ISBLANK('DPW3'!HA14),"",'DPW3'!HA14) | ¬¬IF(ISBLANK('DPW3'!HB14),"",'DPW3'!HB14) | ¬¬IF(ISBLANK('DPW3'!HC14),"",'DPW3'!HC14) | ¬¬IF(ISBLANK('DPW3'!HD14),"",'DPW3'!HD14) | ¬¬IF(ISBLANK('DPW3'!HE14),"",'DPW3'!HE14) | ¬¬IF(ISBLANK('DPW3'!HF14),"",'DPW3'!HF14) | ¬¬IF(ISBLANK('DPW3'!HG14),"",'DPW3'!HG14) | ¬¬IF(ISBLANK('DPW3'!HH14),"",'DPW3'!HH14)
¬¬A1484 | ¬¬IF(ISBLANK('DPW3'!US14),"",'DPW3'!US14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ14),"",'DPW3'!HJ14) | ¬¬IF(ISBLANK('DPW3'!HK14),"",'DPW3'!HK14) | ¬¬IF(ISBLANK('DPW3'!HL14),"",'DPW3'!HL14) | ¬¬IF(ISBLANK('DPW3'!HM14),"",'DPW3'!HM14) | ¬¬IF(ISBLANK('DPW3'!HN14),"",'DPW3'!HN14) | ¬¬IF(ISBLANK('DPW3'!HO14),"",'DPW3'!HO14) | ¬¬IF(ISBLANK('DPW3'!HP14),"",'DPW3'!HP14) | ¬¬IF(ISBLANK('DPW3'!HQ14),"",'DPW3'!HQ14) | ¬¬IF(ISBLANK('DPW3'!HR14),"",'DPW3'!HR14) | ¬¬IF(ISBLANK('DPW3'!HS14),"",'DPW3'!HS14) | ¬¬IF(ISBLANK('DPW3'!HT14),"",'DPW3'!HT14) | ¬¬IF(ISBLANK('DPW3'!HU14),"",'DPW3'!HU14) | ¬¬IF(ISBLANK('DPW3'!HV14),"",'DPW3'!HV14) | ¬¬IF(ISBLANK('DPW3'!HW14),"",'DPW3'!HW14) | ¬¬IF(ISBLANK('DPW3'!HX14),"",'DPW3'!HX14) | ¬¬IF(ISBLANK('DPW3'!HY14),"",'DPW3'!HY14) | ¬¬IF(ISBLANK('DPW3'!HZ14),"",'DPW3'!HZ14) | ¬¬IF(ISBLANK('DPW3'!IA14),"",'DPW3'!IA14) | ¬¬IF(ISBLANK('DPW3'!IB14),"",'DPW3'!IB14) | ¬¬IF(ISBLANK('DPW3'!IC14),"",'DPW3'!IC14) | ¬¬IF(ISBLANK('DPW3'!ID14),"",'DPW3'!ID14) | ¬¬IF(ISBLANK('DPW3'!IE14),"",'DPW3'!IE14) | ¬¬IF(ISBLANK('DPW3'!IF14),"",'DPW3'!IF14) | ¬¬IF(ISBLANK('DPW3'!IG14),"",'DPW3'!IG14) | ¬¬IF(ISBLANK('DPW3'!IH14),"",'DPW3'!IH14) | ¬¬IF(ISBLANK('DPW3'!II14),"",'DPW3'!II14) | ¬¬IF(ISBLANK('DPW3'!IJ14),"",'DPW3'!IJ14) | ¬¬IF(ISBLANK('DPW3'!IK14),"",'DPW3'!IK14) | ¬¬IF(ISBLANK('DPW3'!IL14),"",'DPW3'!IL14) | ¬¬IF(ISBLANK('DPW3'!IM14),"",'DPW3'!IM14) | ¬¬IF(ISBLANK('DPW3'!IN14),"",'DPW3'!IN14) | ¬¬IF(ISBLANK('DPW3'!IO14),"",'DPW3'!IO14) | ¬¬IF(ISBLANK('DPW3'!IP14),"",'DPW3'!IP14) | ¬¬IF(ISBLANK('DPW3'!IQ14),"",'DPW3'!IQ14) | ¬¬IF(ISBLANK('DPW3'!IR14),"",'DPW3'!IR14) | ¬¬IF(ISBLANK('DPW3'!IS14),"",'DPW3'!IS14) | ¬¬IF(ISBLANK('DPW3'!IT14),"",'DPW3'!IT14) | ¬¬IF(ISBLANK('DPW3'!IU14),"",'DPW3'!IU14) | ¬¬IF(ISBLANK('DPW3'!IV14),"",'DPW3'!IV14) | ¬¬IF(ISBLANK('DPW3'!IW14),"",'DPW3'!IW14)
¬¬A1485 | ¬¬IF(ISBLANK('DPW3'!WH14),"",'DPW3'!WH14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY14),"",'DPW3'!IY14) | ¬¬IF(ISBLANK('DPW3'!IZ14),"",'DPW3'!IZ14) | ¬¬IF(ISBLANK('DPW3'!JA14),"",'DPW3'!JA14) | ¬¬IF(ISBLANK('DPW3'!JB14),"",'DPW3'!JB14) | ¬¬IF(ISBLANK('DPW3'!JC14),"",'DPW3'!JC14) | ¬¬IF(ISBLANK('DPW3'!JD14),"",'DPW3'!JD14) | ¬¬IF(ISBLANK('DPW3'!JE14),"",'DPW3'!JE14) | ¬¬IF(ISBLANK('DPW3'!JF14),"",'DPW3'!JF14) | ¬¬IF(ISBLANK('DPW3'!JG14),"",'DPW3'!JG14) | ¬¬IF(ISBLANK('DPW3'!JH14),"",'DPW3'!JH14) | ¬¬IF(ISBLANK('DPW3'!JI14),"",'DPW3'!JI14) | ¬¬IF(ISBLANK('DPW3'!JJ14),"",'DPW3'!JJ14) | ¬¬IF(ISBLANK('DPW3'!JK14),"",'DPW3'!JK14) | ¬¬IF(ISBLANK('DPW3'!JL14),"",'DPW3'!JL14) | ¬¬IF(ISBLANK('DPW3'!JM14),"",'DPW3'!JM14) | ¬¬IF(ISBLANK('DPW3'!JN14),"",'DPW3'!JN14) | ¬¬IF(ISBLANK('DPW3'!JO14),"",'DPW3'!JO14) | ¬¬IF(ISBLANK('DPW3'!JP14),"",'DPW3'!JP14) | ¬¬IF(ISBLANK('DPW3'!JQ14),"",'DPW3'!JQ14) | ¬¬IF(ISBLANK('DPW3'!JR14),"",'DPW3'!JR14) | ¬¬IF(ISBLANK('DPW3'!JS14),"",'DPW3'!JS14) | ¬¬IF(ISBLANK('DPW3'!JT14),"",'DPW3'!JT14) | ¬¬IF(ISBLANK('DPW3'!JU14),"",'DPW3'!JU14) | ¬¬IF(ISBLANK('DPW3'!JV14),"",'DPW3'!JV14) | ¬¬IF(ISBLANK('DPW3'!JW14),"",'DPW3'!JW14) | ¬¬IF(ISBLANK('DPW3'!JX14),"",'DPW3'!JX14) | ¬¬IF(ISBLANK('DPW3'!JY14),"",'DPW3'!JY14) | ¬¬IF(ISBLANK('DPW3'!JZ14),"",'DPW3'!JZ14) | ¬¬IF(ISBLANK('DPW3'!KA14),"",'DPW3'!KA14) | ¬¬IF(ISBLANK('DPW3'!KB14),"",'DPW3'!KB14) | ¬¬IF(ISBLANK('DPW3'!KC14),"",'DPW3'!KC14) | ¬¬IF(ISBLANK('DPW3'!KD14),"",'DPW3'!KD14) | ¬¬IF(ISBLANK('DPW3'!KE14),"",'DPW3'!KE14) | ¬¬IF(ISBLANK('DPW3'!KF14),"",'DPW3'!KF14) | ¬¬IF(ISBLANK('DPW3'!KG14),"",'DPW3'!KG14) | ¬¬IF(ISBLANK('DPW3'!KH14),"",'DPW3'!KH14) | ¬¬IF(ISBLANK('DPW3'!KI14),"",'DPW3'!KI14) | ¬¬IF(ISBLANK('DPW3'!KJ14),"",'DPW3'!KJ14) | ¬¬IF(ISBLANK('DPW3'!KK14),"",'DPW3'!KK14) | ¬¬IF(ISBLANK('DPW3'!KL14),"",'DPW3'!KL14)
¬¬A1486 | ¬¬IF(ISBLANK('DPW3'!XW14),"",'DPW3'!XW14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN14),"",'DPW3'!KN14) | ¬¬IF(ISBLANK('DPW3'!KO14),"",'DPW3'!KO14) | ¬¬IF(ISBLANK('DPW3'!KP14),"",'DPW3'!KP14) | ¬¬IF(ISBLANK('DPW3'!KQ14),"",'DPW3'!KQ14) | ¬¬IF(ISBLANK('DPW3'!KR14),"",'DPW3'!KR14) | ¬¬IF(ISBLANK('DPW3'!KS14),"",'DPW3'!KS14) | ¬¬IF(ISBLANK('DPW3'!KT14),"",'DPW3'!KT14) | ¬¬IF(ISBLANK('DPW3'!KU14),"",'DPW3'!KU14) | ¬¬IF(ISBLANK('DPW3'!KV14),"",'DPW3'!KV14) | ¬¬IF(ISBLANK('DPW3'!KW14),"",'DPW3'!KW14) | ¬¬IF(ISBLANK('DPW3'!KX14),"",'DPW3'!KX14) | ¬¬IF(ISBLANK('DPW3'!KY14),"",'DPW3'!KY14) | ¬¬IF(ISBLANK('DPW3'!KZ14),"",'DPW3'!KZ14) | ¬¬IF(ISBLANK('DPW3'!LA14),"",'DPW3'!LA14) | ¬¬IF(ISBLANK('DPW3'!LB14),"",'DPW3'!LB14) | ¬¬IF(ISBLANK('DPW3'!LC14),"",'DPW3'!LC14) | ¬¬IF(ISBLANK('DPW3'!LD14),"",'DPW3'!LD14) | ¬¬IF(ISBLANK('DPW3'!LE14),"",'DPW3'!LE14) | ¬¬IF(ISBLANK('DPW3'!LF14),"",'DPW3'!LF14) | ¬¬IF(ISBLANK('DPW3'!LG14),"",'DPW3'!LG14) | ¬¬IF(ISBLANK('DPW3'!LH14),"",'DPW3'!LH14) | ¬¬IF(ISBLANK('DPW3'!LI14),"",'DPW3'!LI14) | ¬¬IF(ISBLANK('DPW3'!LJ14),"",'DPW3'!LJ14) | ¬¬IF(ISBLANK('DPW3'!LK14),"",'DPW3'!LK14) | ¬¬IF(ISBLANK('DPW3'!LL14),"",'DPW3'!LL14) | ¬¬IF(ISBLANK('DPW3'!LM14),"",'DPW3'!LM14) | ¬¬IF(ISBLANK('DPW3'!LN14),"",'DPW3'!LN14) | ¬¬IF(ISBLANK('DPW3'!LO14),"",'DPW3'!LO14) | ¬¬IF(ISBLANK('DPW3'!LP14),"",'DPW3'!LP14) | ¬¬IF(ISBLANK('DPW3'!LQ14),"",'DPW3'!LQ14) | ¬¬IF(ISBLANK('DPW3'!LR14),"",'DPW3'!LR14) | ¬¬IF(ISBLANK('DPW3'!LS14),"",'DPW3'!LS14) | ¬¬IF(ISBLANK('DPW3'!LT14),"",'DPW3'!LT14) | ¬¬IF(ISBLANK('DPW3'!LU14),"",'DPW3'!LU14) | ¬¬IF(ISBLANK('DPW3'!LV14),"",'DPW3'!LV14) | ¬¬IF(ISBLANK('DPW3'!LW14),"",'DPW3'!LW14) | ¬¬IF(ISBLANK('DPW3'!LX14),"",'DPW3'!LX14) | ¬¬IF(ISBLANK('DPW3'!LY14),"",'DPW3'!LY14) | ¬¬IF(ISBLANK('DPW3'!LZ14),"",'DPW3'!LZ14) | ¬¬IF(ISBLANK('DPW3'!MA14),"",'DPW3'!MA14)
¬¬A1487 | ¬¬IF(ISBLANK('DPW3'!ZL14),"",'DPW3'!ZL14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MC14),"",'DPW3'!MC14)
¬¬A1488 | ¬¬IF(ISBLANK('DPW3'!ZM14),"",'DPW3'!ZM14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MD14),"",'DPW3'!MD14)
¬¬A1489 | ¬¬IF(ISBLANK('DPW3'!ZN14),"",'DPW3'!ZN14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!ML14),"",'DPW3'!ML14)
¬¬A1490 | ¬¬IF(ISBLANK('DPW3'!ZO14),"",'DPW3'!ZO14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MF14),"",'DPW3'!MF14)
¬¬A1491 | ¬¬IF(ISBLANK('DPW3'!ZP14),"",'DPW3'!ZP14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MG14),"",'DPW3'!MG14)
¬¬A1492 | ¬¬IF(ISBLANK('DPW3'!ZQ14),"",'DPW3'!ZQ14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MH14),"",'DPW3'!MH14)
¬¬A1493 | ¬¬IF(ISBLANK('DPW3'!ZR14),"",'DPW3'!ZR14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MI14),"",'DPW3'!MI14)
¬¬A1494 | ¬¬IF(ISBLANK('DPW3'!ZS14),"",'DPW3'!ZS14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ14),"",'DPW3'!MJ14)
¬¬A1495 | ¬¬IF(ISBLANK('DPW3'!ZT14),"",'DPW3'!ZT14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MK14),"",'DPW3'!MK14)
¬¬A1496 | ¬¬IF(ISBLANK('DPW3'!ZV14),"",'DPW3'!ZV14) | ¬¬'DPW3'!F14 & "," & 'DPW3'!G14 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H14),"",'DPW3'!H14) | Delta | ¬¬IF(ISBLANK('DPW3'!MM14),"",'DPW3'!MM14)
¬¬A1497 | ¬¬IF(ISBLANK('DPW3'!MT15),"",'DPW3'!MT15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!K15),"",'DPW3'!K15)
¬¬A1498 | ¬¬IF(ISBLANK('DPW3'!MV15),"",'DPW3'!MV15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M15),"",'DPW3'!M15) | ¬¬IF(ISBLANK('DPW3'!N15),"",'DPW3'!N15) | ¬¬IF(ISBLANK('DPW3'!O15),"",'DPW3'!O15) | ¬¬IF(ISBLANK('DPW3'!P15),"",'DPW3'!P15) | ¬¬IF(ISBLANK('DPW3'!Q15),"",'DPW3'!Q15) | ¬¬IF(ISBLANK('DPW3'!R15),"",'DPW3'!R15) | ¬¬IF(ISBLANK('DPW3'!S15),"",'DPW3'!S15) | ¬¬IF(ISBLANK('DPW3'!T15),"",'DPW3'!T15) | ¬¬IF(ISBLANK('DPW3'!U15),"",'DPW3'!U15) | ¬¬IF(ISBLANK('DPW3'!V15),"",'DPW3'!V15) | ¬¬IF(ISBLANK('DPW3'!W15),"",'DPW3'!W15) | ¬¬IF(ISBLANK('DPW3'!X15),"",'DPW3'!X15) | ¬¬IF(ISBLANK('DPW3'!Y15),"",'DPW3'!Y15) | ¬¬IF(ISBLANK('DPW3'!Z15),"",'DPW3'!Z15) | ¬¬IF(ISBLANK('DPW3'!AA15),"",'DPW3'!AA15) | ¬¬IF(ISBLANK('DPW3'!AB15),"",'DPW3'!AB15) | ¬¬IF(ISBLANK('DPW3'!AC15),"",'DPW3'!AC15) | ¬¬IF(ISBLANK('DPW3'!AD15),"",'DPW3'!AD15) | ¬¬IF(ISBLANK('DPW3'!AE15),"",'DPW3'!AE15) | ¬¬IF(ISBLANK('DPW3'!AF15),"",'DPW3'!AF15) | ¬¬IF(ISBLANK('DPW3'!AG15),"",'DPW3'!AG15) | ¬¬IF(ISBLANK('DPW3'!AH15),"",'DPW3'!AH15) | ¬¬IF(ISBLANK('DPW3'!AI15),"",'DPW3'!AI15) | ¬¬IF(ISBLANK('DPW3'!AJ15),"",'DPW3'!AJ15) | ¬¬IF(ISBLANK('DPW3'!AK15),"",'DPW3'!AK15) | ¬¬IF(ISBLANK('DPW3'!AL15),"",'DPW3'!AL15) | ¬¬IF(ISBLANK('DPW3'!AM15),"",'DPW3'!AM15) | ¬¬IF(ISBLANK('DPW3'!AN15),"",'DPW3'!AN15) | ¬¬IF(ISBLANK('DPW3'!AO15),"",'DPW3'!AO15) | ¬¬IF(ISBLANK('DPW3'!AP15),"",'DPW3'!AP15) | ¬¬IF(ISBLANK('DPW3'!AQ15),"",'DPW3'!AQ15) | ¬¬IF(ISBLANK('DPW3'!AR15),"",'DPW3'!AR15) | ¬¬IF(ISBLANK('DPW3'!AS15),"",'DPW3'!AS15) | ¬¬IF(ISBLANK('DPW3'!AT15),"",'DPW3'!AT15) | ¬¬IF(ISBLANK('DPW3'!AU15),"",'DPW3'!AU15) | ¬¬IF(ISBLANK('DPW3'!AV15),"",'DPW3'!AV15) | ¬¬IF(ISBLANK('DPW3'!AW15),"",'DPW3'!AW15) | ¬¬IF(ISBLANK('DPW3'!AX15),"",'DPW3'!AX15) | ¬¬IF(ISBLANK('DPW3'!AY15),"",'DPW3'!AY15) | ¬¬IF(ISBLANK('DPW3'!AZ15),"",'DPW3'!AZ15)
¬¬A1499 | ¬¬IF(ISBLANK('DPW3'!OK15),"",'DPW3'!OK15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB15),"",'DPW3'!BB15) | ¬¬IF(ISBLANK('DPW3'!BC15),"",'DPW3'!BC15) | ¬¬IF(ISBLANK('DPW3'!BD15),"",'DPW3'!BD15) | ¬¬IF(ISBLANK('DPW3'!BE15),"",'DPW3'!BE15) | ¬¬IF(ISBLANK('DPW3'!BF15),"",'DPW3'!BF15) | ¬¬IF(ISBLANK('DPW3'!BG15),"",'DPW3'!BG15) | ¬¬IF(ISBLANK('DPW3'!BH15),"",'DPW3'!BH15) | ¬¬IF(ISBLANK('DPW3'!BI15),"",'DPW3'!BI15) | ¬¬IF(ISBLANK('DPW3'!BJ15),"",'DPW3'!BJ15) | ¬¬IF(ISBLANK('DPW3'!BK15),"",'DPW3'!BK15) | ¬¬IF(ISBLANK('DPW3'!BL15),"",'DPW3'!BL15) | ¬¬IF(ISBLANK('DPW3'!BM15),"",'DPW3'!BM15) | ¬¬IF(ISBLANK('DPW3'!BN15),"",'DPW3'!BN15) | ¬¬IF(ISBLANK('DPW3'!BO15),"",'DPW3'!BO15) | ¬¬IF(ISBLANK('DPW3'!BP15),"",'DPW3'!BP15) | ¬¬IF(ISBLANK('DPW3'!BQ15),"",'DPW3'!BQ15) | ¬¬IF(ISBLANK('DPW3'!BR15),"",'DPW3'!BR15) | ¬¬IF(ISBLANK('DPW3'!BS15),"",'DPW3'!BS15) | ¬¬IF(ISBLANK('DPW3'!BT15),"",'DPW3'!BT15) | ¬¬IF(ISBLANK('DPW3'!BU15),"",'DPW3'!BU15) | ¬¬IF(ISBLANK('DPW3'!BV15),"",'DPW3'!BV15) | ¬¬IF(ISBLANK('DPW3'!BW15),"",'DPW3'!BW15) | ¬¬IF(ISBLANK('DPW3'!BX15),"",'DPW3'!BX15) | ¬¬IF(ISBLANK('DPW3'!BY15),"",'DPW3'!BY15) | ¬¬IF(ISBLANK('DPW3'!BZ15),"",'DPW3'!BZ15) | ¬¬IF(ISBLANK('DPW3'!CA15),"",'DPW3'!CA15) | ¬¬IF(ISBLANK('DPW3'!CB15),"",'DPW3'!CB15) | ¬¬IF(ISBLANK('DPW3'!CC15),"",'DPW3'!CC15) | ¬¬IF(ISBLANK('DPW3'!CD15),"",'DPW3'!CD15) | ¬¬IF(ISBLANK('DPW3'!CE15),"",'DPW3'!CE15) | ¬¬IF(ISBLANK('DPW3'!CF15),"",'DPW3'!CF15) | ¬¬IF(ISBLANK('DPW3'!CG15),"",'DPW3'!CG15) | ¬¬IF(ISBLANK('DPW3'!CH15),"",'DPW3'!CH15) | ¬¬IF(ISBLANK('DPW3'!CI15),"",'DPW3'!CI15) | ¬¬IF(ISBLANK('DPW3'!CJ15),"",'DPW3'!CJ15) | ¬¬IF(ISBLANK('DPW3'!CK15),"",'DPW3'!CK15) | ¬¬IF(ISBLANK('DPW3'!CL15),"",'DPW3'!CL15) | ¬¬IF(ISBLANK('DPW3'!CM15),"",'DPW3'!CM15) | ¬¬IF(ISBLANK('DPW3'!CN15),"",'DPW3'!CN15) | ¬¬IF(ISBLANK('DPW3'!CO15),"",'DPW3'!CO15)
¬¬A1500 | ¬¬IF(ISBLANK('DPW3'!PZ15),"",'DPW3'!PZ15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ15),"",'DPW3'!CQ15) | ¬¬IF(ISBLANK('DPW3'!CR15),"",'DPW3'!CR15) | ¬¬IF(ISBLANK('DPW3'!CS15),"",'DPW3'!CS15) | ¬¬IF(ISBLANK('DPW3'!CT15),"",'DPW3'!CT15) | ¬¬IF(ISBLANK('DPW3'!CU15),"",'DPW3'!CU15) | ¬¬IF(ISBLANK('DPW3'!CV15),"",'DPW3'!CV15) | ¬¬IF(ISBLANK('DPW3'!CW15),"",'DPW3'!CW15) | ¬¬IF(ISBLANK('DPW3'!CX15),"",'DPW3'!CX15) | ¬¬IF(ISBLANK('DPW3'!CY15),"",'DPW3'!CY15) | ¬¬IF(ISBLANK('DPW3'!CZ15),"",'DPW3'!CZ15) | ¬¬IF(ISBLANK('DPW3'!DA15),"",'DPW3'!DA15) | ¬¬IF(ISBLANK('DPW3'!DB15),"",'DPW3'!DB15) | ¬¬IF(ISBLANK('DPW3'!DC15),"",'DPW3'!DC15) | ¬¬IF(ISBLANK('DPW3'!DD15),"",'DPW3'!DD15) | ¬¬IF(ISBLANK('DPW3'!DE15),"",'DPW3'!DE15) | ¬¬IF(ISBLANK('DPW3'!DF15),"",'DPW3'!DF15) | ¬¬IF(ISBLANK('DPW3'!DG15),"",'DPW3'!DG15) | ¬¬IF(ISBLANK('DPW3'!DH15),"",'DPW3'!DH15) | ¬¬IF(ISBLANK('DPW3'!DI15),"",'DPW3'!DI15) | ¬¬IF(ISBLANK('DPW3'!DJ15),"",'DPW3'!DJ15) | ¬¬IF(ISBLANK('DPW3'!DK15),"",'DPW3'!DK15) | ¬¬IF(ISBLANK('DPW3'!DL15),"",'DPW3'!DL15) | ¬¬IF(ISBLANK('DPW3'!DM15),"",'DPW3'!DM15) | ¬¬IF(ISBLANK('DPW3'!DN15),"",'DPW3'!DN15) | ¬¬IF(ISBLANK('DPW3'!DO15),"",'DPW3'!DO15) | ¬¬IF(ISBLANK('DPW3'!DP15),"",'DPW3'!DP15) | ¬¬IF(ISBLANK('DPW3'!DQ15),"",'DPW3'!DQ15) | ¬¬IF(ISBLANK('DPW3'!DR15),"",'DPW3'!DR15) | ¬¬IF(ISBLANK('DPW3'!DS15),"",'DPW3'!DS15) | ¬¬IF(ISBLANK('DPW3'!DT15),"",'DPW3'!DT15) | ¬¬IF(ISBLANK('DPW3'!DU15),"",'DPW3'!DU15) | ¬¬IF(ISBLANK('DPW3'!DV15),"",'DPW3'!DV15) | ¬¬IF(ISBLANK('DPW3'!DW15),"",'DPW3'!DW15) | ¬¬IF(ISBLANK('DPW3'!DX15),"",'DPW3'!DX15) | ¬¬IF(ISBLANK('DPW3'!DY15),"",'DPW3'!DY15) | ¬¬IF(ISBLANK('DPW3'!DZ15),"",'DPW3'!DZ15) | ¬¬IF(ISBLANK('DPW3'!EA15),"",'DPW3'!EA15) | ¬¬IF(ISBLANK('DPW3'!EB15),"",'DPW3'!EB15) | ¬¬IF(ISBLANK('DPW3'!EC15),"",'DPW3'!EC15) | ¬¬IF(ISBLANK('DPW3'!ED15),"",'DPW3'!ED15)
¬¬A1501 | ¬¬IF(ISBLANK('DPW3'!RO15),"",'DPW3'!RO15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF15),"",'DPW3'!EF15) | ¬¬IF(ISBLANK('DPW3'!EG15),"",'DPW3'!EG15) | ¬¬IF(ISBLANK('DPW3'!EH15),"",'DPW3'!EH15) | ¬¬IF(ISBLANK('DPW3'!EI15),"",'DPW3'!EI15) | ¬¬IF(ISBLANK('DPW3'!EJ15),"",'DPW3'!EJ15) | ¬¬IF(ISBLANK('DPW3'!EK15),"",'DPW3'!EK15) | ¬¬IF(ISBLANK('DPW3'!EL15),"",'DPW3'!EL15) | ¬¬IF(ISBLANK('DPW3'!EM15),"",'DPW3'!EM15) | ¬¬IF(ISBLANK('DPW3'!EN15),"",'DPW3'!EN15) | ¬¬IF(ISBLANK('DPW3'!EO15),"",'DPW3'!EO15) | ¬¬IF(ISBLANK('DPW3'!EP15),"",'DPW3'!EP15) | ¬¬IF(ISBLANK('DPW3'!EQ15),"",'DPW3'!EQ15) | ¬¬IF(ISBLANK('DPW3'!ER15),"",'DPW3'!ER15) | ¬¬IF(ISBLANK('DPW3'!ES15),"",'DPW3'!ES15) | ¬¬IF(ISBLANK('DPW3'!ET15),"",'DPW3'!ET15) | ¬¬IF(ISBLANK('DPW3'!EU15),"",'DPW3'!EU15) | ¬¬IF(ISBLANK('DPW3'!EV15),"",'DPW3'!EV15) | ¬¬IF(ISBLANK('DPW3'!EW15),"",'DPW3'!EW15) | ¬¬IF(ISBLANK('DPW3'!EX15),"",'DPW3'!EX15) | ¬¬IF(ISBLANK('DPW3'!EY15),"",'DPW3'!EY15) | ¬¬IF(ISBLANK('DPW3'!EZ15),"",'DPW3'!EZ15) | ¬¬IF(ISBLANK('DPW3'!FA15),"",'DPW3'!FA15) | ¬¬IF(ISBLANK('DPW3'!FB15),"",'DPW3'!FB15) | ¬¬IF(ISBLANK('DPW3'!FC15),"",'DPW3'!FC15) | ¬¬IF(ISBLANK('DPW3'!FD15),"",'DPW3'!FD15) | ¬¬IF(ISBLANK('DPW3'!FE15),"",'DPW3'!FE15) | ¬¬IF(ISBLANK('DPW3'!FF15),"",'DPW3'!FF15) | ¬¬IF(ISBLANK('DPW3'!FG15),"",'DPW3'!FG15) | ¬¬IF(ISBLANK('DPW3'!FH15),"",'DPW3'!FH15) | ¬¬IF(ISBLANK('DPW3'!FI15),"",'DPW3'!FI15) | ¬¬IF(ISBLANK('DPW3'!FJ15),"",'DPW3'!FJ15) | ¬¬IF(ISBLANK('DPW3'!FK15),"",'DPW3'!FK15) | ¬¬IF(ISBLANK('DPW3'!FL15),"",'DPW3'!FL15) | ¬¬IF(ISBLANK('DPW3'!FM15),"",'DPW3'!FM15) | ¬¬IF(ISBLANK('DPW3'!FN15),"",'DPW3'!FN15) | ¬¬IF(ISBLANK('DPW3'!FO15),"",'DPW3'!FO15) | ¬¬IF(ISBLANK('DPW3'!FP15),"",'DPW3'!FP15) | ¬¬IF(ISBLANK('DPW3'!FQ15),"",'DPW3'!FQ15) | ¬¬IF(ISBLANK('DPW3'!FR15),"",'DPW3'!FR15) | ¬¬IF(ISBLANK('DPW3'!FS15),"",'DPW3'!FS15)
¬¬A1502 | ¬¬IF(ISBLANK('DPW3'!TD15),"",'DPW3'!TD15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU15),"",'DPW3'!FU15) | ¬¬IF(ISBLANK('DPW3'!FV15),"",'DPW3'!FV15) | ¬¬IF(ISBLANK('DPW3'!FW15),"",'DPW3'!FW15) | ¬¬IF(ISBLANK('DPW3'!FX15),"",'DPW3'!FX15) | ¬¬IF(ISBLANK('DPW3'!FY15),"",'DPW3'!FY15) | ¬¬IF(ISBLANK('DPW3'!FZ15),"",'DPW3'!FZ15) | ¬¬IF(ISBLANK('DPW3'!GA15),"",'DPW3'!GA15) | ¬¬IF(ISBLANK('DPW3'!GB15),"",'DPW3'!GB15) | ¬¬IF(ISBLANK('DPW3'!GC15),"",'DPW3'!GC15) | ¬¬IF(ISBLANK('DPW3'!GD15),"",'DPW3'!GD15) | ¬¬IF(ISBLANK('DPW3'!GE15),"",'DPW3'!GE15) | ¬¬IF(ISBLANK('DPW3'!GF15),"",'DPW3'!GF15) | ¬¬IF(ISBLANK('DPW3'!GG15),"",'DPW3'!GG15) | ¬¬IF(ISBLANK('DPW3'!GH15),"",'DPW3'!GH15) | ¬¬IF(ISBLANK('DPW3'!GI15),"",'DPW3'!GI15) | ¬¬IF(ISBLANK('DPW3'!GJ15),"",'DPW3'!GJ15) | ¬¬IF(ISBLANK('DPW3'!GK15),"",'DPW3'!GK15) | ¬¬IF(ISBLANK('DPW3'!GL15),"",'DPW3'!GL15) | ¬¬IF(ISBLANK('DPW3'!GM15),"",'DPW3'!GM15) | ¬¬IF(ISBLANK('DPW3'!GN15),"",'DPW3'!GN15) | ¬¬IF(ISBLANK('DPW3'!GO15),"",'DPW3'!GO15) | ¬¬IF(ISBLANK('DPW3'!GP15),"",'DPW3'!GP15) | ¬¬IF(ISBLANK('DPW3'!GQ15),"",'DPW3'!GQ15) | ¬¬IF(ISBLANK('DPW3'!GR15),"",'DPW3'!GR15) | ¬¬IF(ISBLANK('DPW3'!GS15),"",'DPW3'!GS15) | ¬¬IF(ISBLANK('DPW3'!GT15),"",'DPW3'!GT15) | ¬¬IF(ISBLANK('DPW3'!GU15),"",'DPW3'!GU15) | ¬¬IF(ISBLANK('DPW3'!GV15),"",'DPW3'!GV15) | ¬¬IF(ISBLANK('DPW3'!GW15),"",'DPW3'!GW15) | ¬¬IF(ISBLANK('DPW3'!GX15),"",'DPW3'!GX15) | ¬¬IF(ISBLANK('DPW3'!GY15),"",'DPW3'!GY15) | ¬¬IF(ISBLANK('DPW3'!GZ15),"",'DPW3'!GZ15) | ¬¬IF(ISBLANK('DPW3'!HA15),"",'DPW3'!HA15) | ¬¬IF(ISBLANK('DPW3'!HB15),"",'DPW3'!HB15) | ¬¬IF(ISBLANK('DPW3'!HC15),"",'DPW3'!HC15) | ¬¬IF(ISBLANK('DPW3'!HD15),"",'DPW3'!HD15) | ¬¬IF(ISBLANK('DPW3'!HE15),"",'DPW3'!HE15) | ¬¬IF(ISBLANK('DPW3'!HF15),"",'DPW3'!HF15) | ¬¬IF(ISBLANK('DPW3'!HG15),"",'DPW3'!HG15) | ¬¬IF(ISBLANK('DPW3'!HH15),"",'DPW3'!HH15)
¬¬A1503 | ¬¬IF(ISBLANK('DPW3'!US15),"",'DPW3'!US15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ15),"",'DPW3'!HJ15) | ¬¬IF(ISBLANK('DPW3'!HK15),"",'DPW3'!HK15) | ¬¬IF(ISBLANK('DPW3'!HL15),"",'DPW3'!HL15) | ¬¬IF(ISBLANK('DPW3'!HM15),"",'DPW3'!HM15) | ¬¬IF(ISBLANK('DPW3'!HN15),"",'DPW3'!HN15) | ¬¬IF(ISBLANK('DPW3'!HO15),"",'DPW3'!HO15) | ¬¬IF(ISBLANK('DPW3'!HP15),"",'DPW3'!HP15) | ¬¬IF(ISBLANK('DPW3'!HQ15),"",'DPW3'!HQ15) | ¬¬IF(ISBLANK('DPW3'!HR15),"",'DPW3'!HR15) | ¬¬IF(ISBLANK('DPW3'!HS15),"",'DPW3'!HS15) | ¬¬IF(ISBLANK('DPW3'!HT15),"",'DPW3'!HT15) | ¬¬IF(ISBLANK('DPW3'!HU15),"",'DPW3'!HU15) | ¬¬IF(ISBLANK('DPW3'!HV15),"",'DPW3'!HV15) | ¬¬IF(ISBLANK('DPW3'!HW15),"",'DPW3'!HW15) | ¬¬IF(ISBLANK('DPW3'!HX15),"",'DPW3'!HX15) | ¬¬IF(ISBLANK('DPW3'!HY15),"",'DPW3'!HY15) | ¬¬IF(ISBLANK('DPW3'!HZ15),"",'DPW3'!HZ15) | ¬¬IF(ISBLANK('DPW3'!IA15),"",'DPW3'!IA15) | ¬¬IF(ISBLANK('DPW3'!IB15),"",'DPW3'!IB15) | ¬¬IF(ISBLANK('DPW3'!IC15),"",'DPW3'!IC15) | ¬¬IF(ISBLANK('DPW3'!ID15),"",'DPW3'!ID15) | ¬¬IF(ISBLANK('DPW3'!IE15),"",'DPW3'!IE15) | ¬¬IF(ISBLANK('DPW3'!IF15),"",'DPW3'!IF15) | ¬¬IF(ISBLANK('DPW3'!IG15),"",'DPW3'!IG15) | ¬¬IF(ISBLANK('DPW3'!IH15),"",'DPW3'!IH15) | ¬¬IF(ISBLANK('DPW3'!II15),"",'DPW3'!II15) | ¬¬IF(ISBLANK('DPW3'!IJ15),"",'DPW3'!IJ15) | ¬¬IF(ISBLANK('DPW3'!IK15),"",'DPW3'!IK15) | ¬¬IF(ISBLANK('DPW3'!IL15),"",'DPW3'!IL15) | ¬¬IF(ISBLANK('DPW3'!IM15),"",'DPW3'!IM15) | ¬¬IF(ISBLANK('DPW3'!IN15),"",'DPW3'!IN15) | ¬¬IF(ISBLANK('DPW3'!IO15),"",'DPW3'!IO15) | ¬¬IF(ISBLANK('DPW3'!IP15),"",'DPW3'!IP15) | ¬¬IF(ISBLANK('DPW3'!IQ15),"",'DPW3'!IQ15) | ¬¬IF(ISBLANK('DPW3'!IR15),"",'DPW3'!IR15) | ¬¬IF(ISBLANK('DPW3'!IS15),"",'DPW3'!IS15) | ¬¬IF(ISBLANK('DPW3'!IT15),"",'DPW3'!IT15) | ¬¬IF(ISBLANK('DPW3'!IU15),"",'DPW3'!IU15) | ¬¬IF(ISBLANK('DPW3'!IV15),"",'DPW3'!IV15) | ¬¬IF(ISBLANK('DPW3'!IW15),"",'DPW3'!IW15)
¬¬A1504 | ¬¬IF(ISBLANK('DPW3'!WH15),"",'DPW3'!WH15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY15),"",'DPW3'!IY15) | ¬¬IF(ISBLANK('DPW3'!IZ15),"",'DPW3'!IZ15) | ¬¬IF(ISBLANK('DPW3'!JA15),"",'DPW3'!JA15) | ¬¬IF(ISBLANK('DPW3'!JB15),"",'DPW3'!JB15) | ¬¬IF(ISBLANK('DPW3'!JC15),"",'DPW3'!JC15) | ¬¬IF(ISBLANK('DPW3'!JD15),"",'DPW3'!JD15) | ¬¬IF(ISBLANK('DPW3'!JE15),"",'DPW3'!JE15) | ¬¬IF(ISBLANK('DPW3'!JF15),"",'DPW3'!JF15) | ¬¬IF(ISBLANK('DPW3'!JG15),"",'DPW3'!JG15) | ¬¬IF(ISBLANK('DPW3'!JH15),"",'DPW3'!JH15) | ¬¬IF(ISBLANK('DPW3'!JI15),"",'DPW3'!JI15) | ¬¬IF(ISBLANK('DPW3'!JJ15),"",'DPW3'!JJ15) | ¬¬IF(ISBLANK('DPW3'!JK15),"",'DPW3'!JK15) | ¬¬IF(ISBLANK('DPW3'!JL15),"",'DPW3'!JL15) | ¬¬IF(ISBLANK('DPW3'!JM15),"",'DPW3'!JM15) | ¬¬IF(ISBLANK('DPW3'!JN15),"",'DPW3'!JN15) | ¬¬IF(ISBLANK('DPW3'!JO15),"",'DPW3'!JO15) | ¬¬IF(ISBLANK('DPW3'!JP15),"",'DPW3'!JP15) | ¬¬IF(ISBLANK('DPW3'!JQ15),"",'DPW3'!JQ15) | ¬¬IF(ISBLANK('DPW3'!JR15),"",'DPW3'!JR15) | ¬¬IF(ISBLANK('DPW3'!JS15),"",'DPW3'!JS15) | ¬¬IF(ISBLANK('DPW3'!JT15),"",'DPW3'!JT15) | ¬¬IF(ISBLANK('DPW3'!JU15),"",'DPW3'!JU15) | ¬¬IF(ISBLANK('DPW3'!JV15),"",'DPW3'!JV15) | ¬¬IF(ISBLANK('DPW3'!JW15),"",'DPW3'!JW15) | ¬¬IF(ISBLANK('DPW3'!JX15),"",'DPW3'!JX15) | ¬¬IF(ISBLANK('DPW3'!JY15),"",'DPW3'!JY15) | ¬¬IF(ISBLANK('DPW3'!JZ15),"",'DPW3'!JZ15) | ¬¬IF(ISBLANK('DPW3'!KA15),"",'DPW3'!KA15) | ¬¬IF(ISBLANK('DPW3'!KB15),"",'DPW3'!KB15) | ¬¬IF(ISBLANK('DPW3'!KC15),"",'DPW3'!KC15) | ¬¬IF(ISBLANK('DPW3'!KD15),"",'DPW3'!KD15) | ¬¬IF(ISBLANK('DPW3'!KE15),"",'DPW3'!KE15) | ¬¬IF(ISBLANK('DPW3'!KF15),"",'DPW3'!KF15) | ¬¬IF(ISBLANK('DPW3'!KG15),"",'DPW3'!KG15) | ¬¬IF(ISBLANK('DPW3'!KH15),"",'DPW3'!KH15) | ¬¬IF(ISBLANK('DPW3'!KI15),"",'DPW3'!KI15) | ¬¬IF(ISBLANK('DPW3'!KJ15),"",'DPW3'!KJ15) | ¬¬IF(ISBLANK('DPW3'!KK15),"",'DPW3'!KK15) | ¬¬IF(ISBLANK('DPW3'!KL15),"",'DPW3'!KL15)
¬¬A1505 | ¬¬IF(ISBLANK('DPW3'!XW15),"",'DPW3'!XW15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN15),"",'DPW3'!KN15) | ¬¬IF(ISBLANK('DPW3'!KO15),"",'DPW3'!KO15) | ¬¬IF(ISBLANK('DPW3'!KP15),"",'DPW3'!KP15) | ¬¬IF(ISBLANK('DPW3'!KQ15),"",'DPW3'!KQ15) | ¬¬IF(ISBLANK('DPW3'!KR15),"",'DPW3'!KR15) | ¬¬IF(ISBLANK('DPW3'!KS15),"",'DPW3'!KS15) | ¬¬IF(ISBLANK('DPW3'!KT15),"",'DPW3'!KT15) | ¬¬IF(ISBLANK('DPW3'!KU15),"",'DPW3'!KU15) | ¬¬IF(ISBLANK('DPW3'!KV15),"",'DPW3'!KV15) | ¬¬IF(ISBLANK('DPW3'!KW15),"",'DPW3'!KW15) | ¬¬IF(ISBLANK('DPW3'!KX15),"",'DPW3'!KX15) | ¬¬IF(ISBLANK('DPW3'!KY15),"",'DPW3'!KY15) | ¬¬IF(ISBLANK('DPW3'!KZ15),"",'DPW3'!KZ15) | ¬¬IF(ISBLANK('DPW3'!LA15),"",'DPW3'!LA15) | ¬¬IF(ISBLANK('DPW3'!LB15),"",'DPW3'!LB15) | ¬¬IF(ISBLANK('DPW3'!LC15),"",'DPW3'!LC15) | ¬¬IF(ISBLANK('DPW3'!LD15),"",'DPW3'!LD15) | ¬¬IF(ISBLANK('DPW3'!LE15),"",'DPW3'!LE15) | ¬¬IF(ISBLANK('DPW3'!LF15),"",'DPW3'!LF15) | ¬¬IF(ISBLANK('DPW3'!LG15),"",'DPW3'!LG15) | ¬¬IF(ISBLANK('DPW3'!LH15),"",'DPW3'!LH15) | ¬¬IF(ISBLANK('DPW3'!LI15),"",'DPW3'!LI15) | ¬¬IF(ISBLANK('DPW3'!LJ15),"",'DPW3'!LJ15) | ¬¬IF(ISBLANK('DPW3'!LK15),"",'DPW3'!LK15) | ¬¬IF(ISBLANK('DPW3'!LL15),"",'DPW3'!LL15) | ¬¬IF(ISBLANK('DPW3'!LM15),"",'DPW3'!LM15) | ¬¬IF(ISBLANK('DPW3'!LN15),"",'DPW3'!LN15) | ¬¬IF(ISBLANK('DPW3'!LO15),"",'DPW3'!LO15) | ¬¬IF(ISBLANK('DPW3'!LP15),"",'DPW3'!LP15) | ¬¬IF(ISBLANK('DPW3'!LQ15),"",'DPW3'!LQ15) | ¬¬IF(ISBLANK('DPW3'!LR15),"",'DPW3'!LR15) | ¬¬IF(ISBLANK('DPW3'!LS15),"",'DPW3'!LS15) | ¬¬IF(ISBLANK('DPW3'!LT15),"",'DPW3'!LT15) | ¬¬IF(ISBLANK('DPW3'!LU15),"",'DPW3'!LU15) | ¬¬IF(ISBLANK('DPW3'!LV15),"",'DPW3'!LV15) | ¬¬IF(ISBLANK('DPW3'!LW15),"",'DPW3'!LW15) | ¬¬IF(ISBLANK('DPW3'!LX15),"",'DPW3'!LX15) | ¬¬IF(ISBLANK('DPW3'!LY15),"",'DPW3'!LY15) | ¬¬IF(ISBLANK('DPW3'!LZ15),"",'DPW3'!LZ15) | ¬¬IF(ISBLANK('DPW3'!MA15),"",'DPW3'!MA15)
¬¬A1506 | ¬¬IF(ISBLANK('DPW3'!ZL15),"",'DPW3'!ZL15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MC15),"",'DPW3'!MC15)
¬¬A1507 | ¬¬IF(ISBLANK('DPW3'!ZM15),"",'DPW3'!ZM15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MD15),"",'DPW3'!MD15)
¬¬A1508 | ¬¬IF(ISBLANK('DPW3'!ZN15),"",'DPW3'!ZN15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!ML15),"",'DPW3'!ML15)
¬¬A1509 | ¬¬IF(ISBLANK('DPW3'!ZO15),"",'DPW3'!ZO15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MF15),"",'DPW3'!MF15)
¬¬A1510 | ¬¬IF(ISBLANK('DPW3'!ZP15),"",'DPW3'!ZP15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MG15),"",'DPW3'!MG15)
¬¬A1511 | ¬¬IF(ISBLANK('DPW3'!ZQ15),"",'DPW3'!ZQ15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MH15),"",'DPW3'!MH15)
¬¬A1512 | ¬¬IF(ISBLANK('DPW3'!ZR15),"",'DPW3'!ZR15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MI15),"",'DPW3'!MI15)
¬¬A1513 | ¬¬IF(ISBLANK('DPW3'!ZS15),"",'DPW3'!ZS15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ15),"",'DPW3'!MJ15)
¬¬A1514 | ¬¬IF(ISBLANK('DPW3'!ZT15),"",'DPW3'!ZT15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MK15),"",'DPW3'!MK15)
¬¬A1515 | ¬¬IF(ISBLANK('DPW3'!ZV15),"",'DPW3'!ZV15) | ¬¬'DPW3'!F15 & "," & 'DPW3'!G15 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H15),"",'DPW3'!H15) | Delta | ¬¬IF(ISBLANK('DPW3'!MM15),"",'DPW3'!MM15)
¬¬A1516 | ¬¬IF(ISBLANK('DPW3'!MT16),"",'DPW3'!MT16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!K16),"",'DPW3'!K16)
¬¬A1517 | ¬¬IF(ISBLANK('DPW3'!MV16),"",'DPW3'!MV16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M16),"",'DPW3'!M16) | ¬¬IF(ISBLANK('DPW3'!N16),"",'DPW3'!N16) | ¬¬IF(ISBLANK('DPW3'!O16),"",'DPW3'!O16) | ¬¬IF(ISBLANK('DPW3'!P16),"",'DPW3'!P16) | ¬¬IF(ISBLANK('DPW3'!Q16),"",'DPW3'!Q16) | ¬¬IF(ISBLANK('DPW3'!R16),"",'DPW3'!R16) | ¬¬IF(ISBLANK('DPW3'!S16),"",'DPW3'!S16) | ¬¬IF(ISBLANK('DPW3'!T16),"",'DPW3'!T16) | ¬¬IF(ISBLANK('DPW3'!U16),"",'DPW3'!U16) | ¬¬IF(ISBLANK('DPW3'!V16),"",'DPW3'!V16) | ¬¬IF(ISBLANK('DPW3'!W16),"",'DPW3'!W16) | ¬¬IF(ISBLANK('DPW3'!X16),"",'DPW3'!X16) | ¬¬IF(ISBLANK('DPW3'!Y16),"",'DPW3'!Y16) | ¬¬IF(ISBLANK('DPW3'!Z16),"",'DPW3'!Z16) | ¬¬IF(ISBLANK('DPW3'!AA16),"",'DPW3'!AA16) | ¬¬IF(ISBLANK('DPW3'!AB16),"",'DPW3'!AB16) | ¬¬IF(ISBLANK('DPW3'!AC16),"",'DPW3'!AC16) | ¬¬IF(ISBLANK('DPW3'!AD16),"",'DPW3'!AD16) | ¬¬IF(ISBLANK('DPW3'!AE16),"",'DPW3'!AE16) | ¬¬IF(ISBLANK('DPW3'!AF16),"",'DPW3'!AF16) | ¬¬IF(ISBLANK('DPW3'!AG16),"",'DPW3'!AG16) | ¬¬IF(ISBLANK('DPW3'!AH16),"",'DPW3'!AH16) | ¬¬IF(ISBLANK('DPW3'!AI16),"",'DPW3'!AI16) | ¬¬IF(ISBLANK('DPW3'!AJ16),"",'DPW3'!AJ16) | ¬¬IF(ISBLANK('DPW3'!AK16),"",'DPW3'!AK16) | ¬¬IF(ISBLANK('DPW3'!AL16),"",'DPW3'!AL16) | ¬¬IF(ISBLANK('DPW3'!AM16),"",'DPW3'!AM16) | ¬¬IF(ISBLANK('DPW3'!AN16),"",'DPW3'!AN16) | ¬¬IF(ISBLANK('DPW3'!AO16),"",'DPW3'!AO16) | ¬¬IF(ISBLANK('DPW3'!AP16),"",'DPW3'!AP16) | ¬¬IF(ISBLANK('DPW3'!AQ16),"",'DPW3'!AQ16) | ¬¬IF(ISBLANK('DPW3'!AR16),"",'DPW3'!AR16) | ¬¬IF(ISBLANK('DPW3'!AS16),"",'DPW3'!AS16) | ¬¬IF(ISBLANK('DPW3'!AT16),"",'DPW3'!AT16) | ¬¬IF(ISBLANK('DPW3'!AU16),"",'DPW3'!AU16) | ¬¬IF(ISBLANK('DPW3'!AV16),"",'DPW3'!AV16) | ¬¬IF(ISBLANK('DPW3'!AW16),"",'DPW3'!AW16) | ¬¬IF(ISBLANK('DPW3'!AX16),"",'DPW3'!AX16) | ¬¬IF(ISBLANK('DPW3'!AY16),"",'DPW3'!AY16) | ¬¬IF(ISBLANK('DPW3'!AZ16),"",'DPW3'!AZ16)
¬¬A1518 | ¬¬IF(ISBLANK('DPW3'!OK16),"",'DPW3'!OK16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB16),"",'DPW3'!BB16) | ¬¬IF(ISBLANK('DPW3'!BC16),"",'DPW3'!BC16) | ¬¬IF(ISBLANK('DPW3'!BD16),"",'DPW3'!BD16) | ¬¬IF(ISBLANK('DPW3'!BE16),"",'DPW3'!BE16) | ¬¬IF(ISBLANK('DPW3'!BF16),"",'DPW3'!BF16) | ¬¬IF(ISBLANK('DPW3'!BG16),"",'DPW3'!BG16) | ¬¬IF(ISBLANK('DPW3'!BH16),"",'DPW3'!BH16) | ¬¬IF(ISBLANK('DPW3'!BI16),"",'DPW3'!BI16) | ¬¬IF(ISBLANK('DPW3'!BJ16),"",'DPW3'!BJ16) | ¬¬IF(ISBLANK('DPW3'!BK16),"",'DPW3'!BK16) | ¬¬IF(ISBLANK('DPW3'!BL16),"",'DPW3'!BL16) | ¬¬IF(ISBLANK('DPW3'!BM16),"",'DPW3'!BM16) | ¬¬IF(ISBLANK('DPW3'!BN16),"",'DPW3'!BN16) | ¬¬IF(ISBLANK('DPW3'!BO16),"",'DPW3'!BO16) | ¬¬IF(ISBLANK('DPW3'!BP16),"",'DPW3'!BP16) | ¬¬IF(ISBLANK('DPW3'!BQ16),"",'DPW3'!BQ16) | ¬¬IF(ISBLANK('DPW3'!BR16),"",'DPW3'!BR16) | ¬¬IF(ISBLANK('DPW3'!BS16),"",'DPW3'!BS16) | ¬¬IF(ISBLANK('DPW3'!BT16),"",'DPW3'!BT16) | ¬¬IF(ISBLANK('DPW3'!BU16),"",'DPW3'!BU16) | ¬¬IF(ISBLANK('DPW3'!BV16),"",'DPW3'!BV16) | ¬¬IF(ISBLANK('DPW3'!BW16),"",'DPW3'!BW16) | ¬¬IF(ISBLANK('DPW3'!BX16),"",'DPW3'!BX16) | ¬¬IF(ISBLANK('DPW3'!BY16),"",'DPW3'!BY16) | ¬¬IF(ISBLANK('DPW3'!BZ16),"",'DPW3'!BZ16) | ¬¬IF(ISBLANK('DPW3'!CA16),"",'DPW3'!CA16) | ¬¬IF(ISBLANK('DPW3'!CB16),"",'DPW3'!CB16) | ¬¬IF(ISBLANK('DPW3'!CC16),"",'DPW3'!CC16) | ¬¬IF(ISBLANK('DPW3'!CD16),"",'DPW3'!CD16) | ¬¬IF(ISBLANK('DPW3'!CE16),"",'DPW3'!CE16) | ¬¬IF(ISBLANK('DPW3'!CF16),"",'DPW3'!CF16) | ¬¬IF(ISBLANK('DPW3'!CG16),"",'DPW3'!CG16) | ¬¬IF(ISBLANK('DPW3'!CH16),"",'DPW3'!CH16) | ¬¬IF(ISBLANK('DPW3'!CI16),"",'DPW3'!CI16) | ¬¬IF(ISBLANK('DPW3'!CJ16),"",'DPW3'!CJ16) | ¬¬IF(ISBLANK('DPW3'!CK16),"",'DPW3'!CK16) | ¬¬IF(ISBLANK('DPW3'!CL16),"",'DPW3'!CL16) | ¬¬IF(ISBLANK('DPW3'!CM16),"",'DPW3'!CM16) | ¬¬IF(ISBLANK('DPW3'!CN16),"",'DPW3'!CN16) | ¬¬IF(ISBLANK('DPW3'!CO16),"",'DPW3'!CO16)
¬¬A1519 | ¬¬IF(ISBLANK('DPW3'!PZ16),"",'DPW3'!PZ16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ16),"",'DPW3'!CQ16) | ¬¬IF(ISBLANK('DPW3'!CR16),"",'DPW3'!CR16) | ¬¬IF(ISBLANK('DPW3'!CS16),"",'DPW3'!CS16) | ¬¬IF(ISBLANK('DPW3'!CT16),"",'DPW3'!CT16) | ¬¬IF(ISBLANK('DPW3'!CU16),"",'DPW3'!CU16) | ¬¬IF(ISBLANK('DPW3'!CV16),"",'DPW3'!CV16) | ¬¬IF(ISBLANK('DPW3'!CW16),"",'DPW3'!CW16) | ¬¬IF(ISBLANK('DPW3'!CX16),"",'DPW3'!CX16) | ¬¬IF(ISBLANK('DPW3'!CY16),"",'DPW3'!CY16) | ¬¬IF(ISBLANK('DPW3'!CZ16),"",'DPW3'!CZ16) | ¬¬IF(ISBLANK('DPW3'!DA16),"",'DPW3'!DA16) | ¬¬IF(ISBLANK('DPW3'!DB16),"",'DPW3'!DB16) | ¬¬IF(ISBLANK('DPW3'!DC16),"",'DPW3'!DC16) | ¬¬IF(ISBLANK('DPW3'!DD16),"",'DPW3'!DD16) | ¬¬IF(ISBLANK('DPW3'!DE16),"",'DPW3'!DE16) | ¬¬IF(ISBLANK('DPW3'!DF16),"",'DPW3'!DF16) | ¬¬IF(ISBLANK('DPW3'!DG16),"",'DPW3'!DG16) | ¬¬IF(ISBLANK('DPW3'!DH16),"",'DPW3'!DH16) | ¬¬IF(ISBLANK('DPW3'!DI16),"",'DPW3'!DI16) | ¬¬IF(ISBLANK('DPW3'!DJ16),"",'DPW3'!DJ16) | ¬¬IF(ISBLANK('DPW3'!DK16),"",'DPW3'!DK16) | ¬¬IF(ISBLANK('DPW3'!DL16),"",'DPW3'!DL16) | ¬¬IF(ISBLANK('DPW3'!DM16),"",'DPW3'!DM16) | ¬¬IF(ISBLANK('DPW3'!DN16),"",'DPW3'!DN16) | ¬¬IF(ISBLANK('DPW3'!DO16),"",'DPW3'!DO16) | ¬¬IF(ISBLANK('DPW3'!DP16),"",'DPW3'!DP16) | ¬¬IF(ISBLANK('DPW3'!DQ16),"",'DPW3'!DQ16) | ¬¬IF(ISBLANK('DPW3'!DR16),"",'DPW3'!DR16) | ¬¬IF(ISBLANK('DPW3'!DS16),"",'DPW3'!DS16) | ¬¬IF(ISBLANK('DPW3'!DT16),"",'DPW3'!DT16) | ¬¬IF(ISBLANK('DPW3'!DU16),"",'DPW3'!DU16) | ¬¬IF(ISBLANK('DPW3'!DV16),"",'DPW3'!DV16) | ¬¬IF(ISBLANK('DPW3'!DW16),"",'DPW3'!DW16) | ¬¬IF(ISBLANK('DPW3'!DX16),"",'DPW3'!DX16) | ¬¬IF(ISBLANK('DPW3'!DY16),"",'DPW3'!DY16) | ¬¬IF(ISBLANK('DPW3'!DZ16),"",'DPW3'!DZ16) | ¬¬IF(ISBLANK('DPW3'!EA16),"",'DPW3'!EA16) | ¬¬IF(ISBLANK('DPW3'!EB16),"",'DPW3'!EB16) | ¬¬IF(ISBLANK('DPW3'!EC16),"",'DPW3'!EC16) | ¬¬IF(ISBLANK('DPW3'!ED16),"",'DPW3'!ED16)
¬¬A1520 | ¬¬IF(ISBLANK('DPW3'!RO16),"",'DPW3'!RO16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF16),"",'DPW3'!EF16) | ¬¬IF(ISBLANK('DPW3'!EG16),"",'DPW3'!EG16) | ¬¬IF(ISBLANK('DPW3'!EH16),"",'DPW3'!EH16) | ¬¬IF(ISBLANK('DPW3'!EI16),"",'DPW3'!EI16) | ¬¬IF(ISBLANK('DPW3'!EJ16),"",'DPW3'!EJ16) | ¬¬IF(ISBLANK('DPW3'!EK16),"",'DPW3'!EK16) | ¬¬IF(ISBLANK('DPW3'!EL16),"",'DPW3'!EL16) | ¬¬IF(ISBLANK('DPW3'!EM16),"",'DPW3'!EM16) | ¬¬IF(ISBLANK('DPW3'!EN16),"",'DPW3'!EN16) | ¬¬IF(ISBLANK('DPW3'!EO16),"",'DPW3'!EO16) | ¬¬IF(ISBLANK('DPW3'!EP16),"",'DPW3'!EP16) | ¬¬IF(ISBLANK('DPW3'!EQ16),"",'DPW3'!EQ16) | ¬¬IF(ISBLANK('DPW3'!ER16),"",'DPW3'!ER16) | ¬¬IF(ISBLANK('DPW3'!ES16),"",'DPW3'!ES16) | ¬¬IF(ISBLANK('DPW3'!ET16),"",'DPW3'!ET16) | ¬¬IF(ISBLANK('DPW3'!EU16),"",'DPW3'!EU16) | ¬¬IF(ISBLANK('DPW3'!EV16),"",'DPW3'!EV16) | ¬¬IF(ISBLANK('DPW3'!EW16),"",'DPW3'!EW16) | ¬¬IF(ISBLANK('DPW3'!EX16),"",'DPW3'!EX16) | ¬¬IF(ISBLANK('DPW3'!EY16),"",'DPW3'!EY16) | ¬¬IF(ISBLANK('DPW3'!EZ16),"",'DPW3'!EZ16) | ¬¬IF(ISBLANK('DPW3'!FA16),"",'DPW3'!FA16) | ¬¬IF(ISBLANK('DPW3'!FB16),"",'DPW3'!FB16) | ¬¬IF(ISBLANK('DPW3'!FC16),"",'DPW3'!FC16) | ¬¬IF(ISBLANK('DPW3'!FD16),"",'DPW3'!FD16) | ¬¬IF(ISBLANK('DPW3'!FE16),"",'DPW3'!FE16) | ¬¬IF(ISBLANK('DPW3'!FF16),"",'DPW3'!FF16) | ¬¬IF(ISBLANK('DPW3'!FG16),"",'DPW3'!FG16) | ¬¬IF(ISBLANK('DPW3'!FH16),"",'DPW3'!FH16) | ¬¬IF(ISBLANK('DPW3'!FI16),"",'DPW3'!FI16) | ¬¬IF(ISBLANK('DPW3'!FJ16),"",'DPW3'!FJ16) | ¬¬IF(ISBLANK('DPW3'!FK16),"",'DPW3'!FK16) | ¬¬IF(ISBLANK('DPW3'!FL16),"",'DPW3'!FL16) | ¬¬IF(ISBLANK('DPW3'!FM16),"",'DPW3'!FM16) | ¬¬IF(ISBLANK('DPW3'!FN16),"",'DPW3'!FN16) | ¬¬IF(ISBLANK('DPW3'!FO16),"",'DPW3'!FO16) | ¬¬IF(ISBLANK('DPW3'!FP16),"",'DPW3'!FP16) | ¬¬IF(ISBLANK('DPW3'!FQ16),"",'DPW3'!FQ16) | ¬¬IF(ISBLANK('DPW3'!FR16),"",'DPW3'!FR16) | ¬¬IF(ISBLANK('DPW3'!FS16),"",'DPW3'!FS16)
¬¬A1521 | ¬¬IF(ISBLANK('DPW3'!TD16),"",'DPW3'!TD16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU16),"",'DPW3'!FU16) | ¬¬IF(ISBLANK('DPW3'!FV16),"",'DPW3'!FV16) | ¬¬IF(ISBLANK('DPW3'!FW16),"",'DPW3'!FW16) | ¬¬IF(ISBLANK('DPW3'!FX16),"",'DPW3'!FX16) | ¬¬IF(ISBLANK('DPW3'!FY16),"",'DPW3'!FY16) | ¬¬IF(ISBLANK('DPW3'!FZ16),"",'DPW3'!FZ16) | ¬¬IF(ISBLANK('DPW3'!GA16),"",'DPW3'!GA16) | ¬¬IF(ISBLANK('DPW3'!GB16),"",'DPW3'!GB16) | ¬¬IF(ISBLANK('DPW3'!GC16),"",'DPW3'!GC16) | ¬¬IF(ISBLANK('DPW3'!GD16),"",'DPW3'!GD16) | ¬¬IF(ISBLANK('DPW3'!GE16),"",'DPW3'!GE16) | ¬¬IF(ISBLANK('DPW3'!GF16),"",'DPW3'!GF16) | ¬¬IF(ISBLANK('DPW3'!GG16),"",'DPW3'!GG16) | ¬¬IF(ISBLANK('DPW3'!GH16),"",'DPW3'!GH16) | ¬¬IF(ISBLANK('DPW3'!GI16),"",'DPW3'!GI16) | ¬¬IF(ISBLANK('DPW3'!GJ16),"",'DPW3'!GJ16) | ¬¬IF(ISBLANK('DPW3'!GK16),"",'DPW3'!GK16) | ¬¬IF(ISBLANK('DPW3'!GL16),"",'DPW3'!GL16) | ¬¬IF(ISBLANK('DPW3'!GM16),"",'DPW3'!GM16) | ¬¬IF(ISBLANK('DPW3'!GN16),"",'DPW3'!GN16) | ¬¬IF(ISBLANK('DPW3'!GO16),"",'DPW3'!GO16) | ¬¬IF(ISBLANK('DPW3'!GP16),"",'DPW3'!GP16) | ¬¬IF(ISBLANK('DPW3'!GQ16),"",'DPW3'!GQ16) | ¬¬IF(ISBLANK('DPW3'!GR16),"",'DPW3'!GR16) | ¬¬IF(ISBLANK('DPW3'!GS16),"",'DPW3'!GS16) | ¬¬IF(ISBLANK('DPW3'!GT16),"",'DPW3'!GT16) | ¬¬IF(ISBLANK('DPW3'!GU16),"",'DPW3'!GU16) | ¬¬IF(ISBLANK('DPW3'!GV16),"",'DPW3'!GV16) | ¬¬IF(ISBLANK('DPW3'!GW16),"",'DPW3'!GW16) | ¬¬IF(ISBLANK('DPW3'!GX16),"",'DPW3'!GX16) | ¬¬IF(ISBLANK('DPW3'!GY16),"",'DPW3'!GY16) | ¬¬IF(ISBLANK('DPW3'!GZ16),"",'DPW3'!GZ16) | ¬¬IF(ISBLANK('DPW3'!HA16),"",'DPW3'!HA16) | ¬¬IF(ISBLANK('DPW3'!HB16),"",'DPW3'!HB16) | ¬¬IF(ISBLANK('DPW3'!HC16),"",'DPW3'!HC16) | ¬¬IF(ISBLANK('DPW3'!HD16),"",'DPW3'!HD16) | ¬¬IF(ISBLANK('DPW3'!HE16),"",'DPW3'!HE16) | ¬¬IF(ISBLANK('DPW3'!HF16),"",'DPW3'!HF16) | ¬¬IF(ISBLANK('DPW3'!HG16),"",'DPW3'!HG16) | ¬¬IF(ISBLANK('DPW3'!HH16),"",'DPW3'!HH16)
¬¬A1522 | ¬¬IF(ISBLANK('DPW3'!US16),"",'DPW3'!US16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ16),"",'DPW3'!HJ16) | ¬¬IF(ISBLANK('DPW3'!HK16),"",'DPW3'!HK16) | ¬¬IF(ISBLANK('DPW3'!HL16),"",'DPW3'!HL16) | ¬¬IF(ISBLANK('DPW3'!HM16),"",'DPW3'!HM16) | ¬¬IF(ISBLANK('DPW3'!HN16),"",'DPW3'!HN16) | ¬¬IF(ISBLANK('DPW3'!HO16),"",'DPW3'!HO16) | ¬¬IF(ISBLANK('DPW3'!HP16),"",'DPW3'!HP16) | ¬¬IF(ISBLANK('DPW3'!HQ16),"",'DPW3'!HQ16) | ¬¬IF(ISBLANK('DPW3'!HR16),"",'DPW3'!HR16) | ¬¬IF(ISBLANK('DPW3'!HS16),"",'DPW3'!HS16) | ¬¬IF(ISBLANK('DPW3'!HT16),"",'DPW3'!HT16) | ¬¬IF(ISBLANK('DPW3'!HU16),"",'DPW3'!HU16) | ¬¬IF(ISBLANK('DPW3'!HV16),"",'DPW3'!HV16) | ¬¬IF(ISBLANK('DPW3'!HW16),"",'DPW3'!HW16) | ¬¬IF(ISBLANK('DPW3'!HX16),"",'DPW3'!HX16) | ¬¬IF(ISBLANK('DPW3'!HY16),"",'DPW3'!HY16) | ¬¬IF(ISBLANK('DPW3'!HZ16),"",'DPW3'!HZ16) | ¬¬IF(ISBLANK('DPW3'!IA16),"",'DPW3'!IA16) | ¬¬IF(ISBLANK('DPW3'!IB16),"",'DPW3'!IB16) | ¬¬IF(ISBLANK('DPW3'!IC16),"",'DPW3'!IC16) | ¬¬IF(ISBLANK('DPW3'!ID16),"",'DPW3'!ID16) | ¬¬IF(ISBLANK('DPW3'!IE16),"",'DPW3'!IE16) | ¬¬IF(ISBLANK('DPW3'!IF16),"",'DPW3'!IF16) | ¬¬IF(ISBLANK('DPW3'!IG16),"",'DPW3'!IG16) | ¬¬IF(ISBLANK('DPW3'!IH16),"",'DPW3'!IH16) | ¬¬IF(ISBLANK('DPW3'!II16),"",'DPW3'!II16) | ¬¬IF(ISBLANK('DPW3'!IJ16),"",'DPW3'!IJ16) | ¬¬IF(ISBLANK('DPW3'!IK16),"",'DPW3'!IK16) | ¬¬IF(ISBLANK('DPW3'!IL16),"",'DPW3'!IL16) | ¬¬IF(ISBLANK('DPW3'!IM16),"",'DPW3'!IM16) | ¬¬IF(ISBLANK('DPW3'!IN16),"",'DPW3'!IN16) | ¬¬IF(ISBLANK('DPW3'!IO16),"",'DPW3'!IO16) | ¬¬IF(ISBLANK('DPW3'!IP16),"",'DPW3'!IP16) | ¬¬IF(ISBLANK('DPW3'!IQ16),"",'DPW3'!IQ16) | ¬¬IF(ISBLANK('DPW3'!IR16),"",'DPW3'!IR16) | ¬¬IF(ISBLANK('DPW3'!IS16),"",'DPW3'!IS16) | ¬¬IF(ISBLANK('DPW3'!IT16),"",'DPW3'!IT16) | ¬¬IF(ISBLANK('DPW3'!IU16),"",'DPW3'!IU16) | ¬¬IF(ISBLANK('DPW3'!IV16),"",'DPW3'!IV16) | ¬¬IF(ISBLANK('DPW3'!IW16),"",'DPW3'!IW16)
¬¬A1523 | ¬¬IF(ISBLANK('DPW3'!WH16),"",'DPW3'!WH16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY16),"",'DPW3'!IY16) | ¬¬IF(ISBLANK('DPW3'!IZ16),"",'DPW3'!IZ16) | ¬¬IF(ISBLANK('DPW3'!JA16),"",'DPW3'!JA16) | ¬¬IF(ISBLANK('DPW3'!JB16),"",'DPW3'!JB16) | ¬¬IF(ISBLANK('DPW3'!JC16),"",'DPW3'!JC16) | ¬¬IF(ISBLANK('DPW3'!JD16),"",'DPW3'!JD16) | ¬¬IF(ISBLANK('DPW3'!JE16),"",'DPW3'!JE16) | ¬¬IF(ISBLANK('DPW3'!JF16),"",'DPW3'!JF16) | ¬¬IF(ISBLANK('DPW3'!JG16),"",'DPW3'!JG16) | ¬¬IF(ISBLANK('DPW3'!JH16),"",'DPW3'!JH16) | ¬¬IF(ISBLANK('DPW3'!JI16),"",'DPW3'!JI16) | ¬¬IF(ISBLANK('DPW3'!JJ16),"",'DPW3'!JJ16) | ¬¬IF(ISBLANK('DPW3'!JK16),"",'DPW3'!JK16) | ¬¬IF(ISBLANK('DPW3'!JL16),"",'DPW3'!JL16) | ¬¬IF(ISBLANK('DPW3'!JM16),"",'DPW3'!JM16) | ¬¬IF(ISBLANK('DPW3'!JN16),"",'DPW3'!JN16) | ¬¬IF(ISBLANK('DPW3'!JO16),"",'DPW3'!JO16) | ¬¬IF(ISBLANK('DPW3'!JP16),"",'DPW3'!JP16) | ¬¬IF(ISBLANK('DPW3'!JQ16),"",'DPW3'!JQ16) | ¬¬IF(ISBLANK('DPW3'!JR16),"",'DPW3'!JR16) | ¬¬IF(ISBLANK('DPW3'!JS16),"",'DPW3'!JS16) | ¬¬IF(ISBLANK('DPW3'!JT16),"",'DPW3'!JT16) | ¬¬IF(ISBLANK('DPW3'!JU16),"",'DPW3'!JU16) | ¬¬IF(ISBLANK('DPW3'!JV16),"",'DPW3'!JV16) | ¬¬IF(ISBLANK('DPW3'!JW16),"",'DPW3'!JW16) | ¬¬IF(ISBLANK('DPW3'!JX16),"",'DPW3'!JX16) | ¬¬IF(ISBLANK('DPW3'!JY16),"",'DPW3'!JY16) | ¬¬IF(ISBLANK('DPW3'!JZ16),"",'DPW3'!JZ16) | ¬¬IF(ISBLANK('DPW3'!KA16),"",'DPW3'!KA16) | ¬¬IF(ISBLANK('DPW3'!KB16),"",'DPW3'!KB16) | ¬¬IF(ISBLANK('DPW3'!KC16),"",'DPW3'!KC16) | ¬¬IF(ISBLANK('DPW3'!KD16),"",'DPW3'!KD16) | ¬¬IF(ISBLANK('DPW3'!KE16),"",'DPW3'!KE16) | ¬¬IF(ISBLANK('DPW3'!KF16),"",'DPW3'!KF16) | ¬¬IF(ISBLANK('DPW3'!KG16),"",'DPW3'!KG16) | ¬¬IF(ISBLANK('DPW3'!KH16),"",'DPW3'!KH16) | ¬¬IF(ISBLANK('DPW3'!KI16),"",'DPW3'!KI16) | ¬¬IF(ISBLANK('DPW3'!KJ16),"",'DPW3'!KJ16) | ¬¬IF(ISBLANK('DPW3'!KK16),"",'DPW3'!KK16) | ¬¬IF(ISBLANK('DPW3'!KL16),"",'DPW3'!KL16)
¬¬A1524 | ¬¬IF(ISBLANK('DPW3'!XW16),"",'DPW3'!XW16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN16),"",'DPW3'!KN16) | ¬¬IF(ISBLANK('DPW3'!KO16),"",'DPW3'!KO16) | ¬¬IF(ISBLANK('DPW3'!KP16),"",'DPW3'!KP16) | ¬¬IF(ISBLANK('DPW3'!KQ16),"",'DPW3'!KQ16) | ¬¬IF(ISBLANK('DPW3'!KR16),"",'DPW3'!KR16) | ¬¬IF(ISBLANK('DPW3'!KS16),"",'DPW3'!KS16) | ¬¬IF(ISBLANK('DPW3'!KT16),"",'DPW3'!KT16) | ¬¬IF(ISBLANK('DPW3'!KU16),"",'DPW3'!KU16) | ¬¬IF(ISBLANK('DPW3'!KV16),"",'DPW3'!KV16) | ¬¬IF(ISBLANK('DPW3'!KW16),"",'DPW3'!KW16) | ¬¬IF(ISBLANK('DPW3'!KX16),"",'DPW3'!KX16) | ¬¬IF(ISBLANK('DPW3'!KY16),"",'DPW3'!KY16) | ¬¬IF(ISBLANK('DPW3'!KZ16),"",'DPW3'!KZ16) | ¬¬IF(ISBLANK('DPW3'!LA16),"",'DPW3'!LA16) | ¬¬IF(ISBLANK('DPW3'!LB16),"",'DPW3'!LB16) | ¬¬IF(ISBLANK('DPW3'!LC16),"",'DPW3'!LC16) | ¬¬IF(ISBLANK('DPW3'!LD16),"",'DPW3'!LD16) | ¬¬IF(ISBLANK('DPW3'!LE16),"",'DPW3'!LE16) | ¬¬IF(ISBLANK('DPW3'!LF16),"",'DPW3'!LF16) | ¬¬IF(ISBLANK('DPW3'!LG16),"",'DPW3'!LG16) | ¬¬IF(ISBLANK('DPW3'!LH16),"",'DPW3'!LH16) | ¬¬IF(ISBLANK('DPW3'!LI16),"",'DPW3'!LI16) | ¬¬IF(ISBLANK('DPW3'!LJ16),"",'DPW3'!LJ16) | ¬¬IF(ISBLANK('DPW3'!LK16),"",'DPW3'!LK16) | ¬¬IF(ISBLANK('DPW3'!LL16),"",'DPW3'!LL16) | ¬¬IF(ISBLANK('DPW3'!LM16),"",'DPW3'!LM16) | ¬¬IF(ISBLANK('DPW3'!LN16),"",'DPW3'!LN16) | ¬¬IF(ISBLANK('DPW3'!LO16),"",'DPW3'!LO16) | ¬¬IF(ISBLANK('DPW3'!LP16),"",'DPW3'!LP16) | ¬¬IF(ISBLANK('DPW3'!LQ16),"",'DPW3'!LQ16) | ¬¬IF(ISBLANK('DPW3'!LR16),"",'DPW3'!LR16) | ¬¬IF(ISBLANK('DPW3'!LS16),"",'DPW3'!LS16) | ¬¬IF(ISBLANK('DPW3'!LT16),"",'DPW3'!LT16) | ¬¬IF(ISBLANK('DPW3'!LU16),"",'DPW3'!LU16) | ¬¬IF(ISBLANK('DPW3'!LV16),"",'DPW3'!LV16) | ¬¬IF(ISBLANK('DPW3'!LW16),"",'DPW3'!LW16) | ¬¬IF(ISBLANK('DPW3'!LX16),"",'DPW3'!LX16) | ¬¬IF(ISBLANK('DPW3'!LY16),"",'DPW3'!LY16) | ¬¬IF(ISBLANK('DPW3'!LZ16),"",'DPW3'!LZ16) | ¬¬IF(ISBLANK('DPW3'!MA16),"",'DPW3'!MA16)
¬¬A1525 | ¬¬IF(ISBLANK('DPW3'!ZL16),"",'DPW3'!ZL16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MC16),"",'DPW3'!MC16)
¬¬A1526 | ¬¬IF(ISBLANK('DPW3'!ZM16),"",'DPW3'!ZM16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MD16),"",'DPW3'!MD16)
¬¬A1527 | ¬¬IF(ISBLANK('DPW3'!ZN16),"",'DPW3'!ZN16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!ML16),"",'DPW3'!ML16)
¬¬A1528 | ¬¬IF(ISBLANK('DPW3'!ZO16),"",'DPW3'!ZO16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MF16),"",'DPW3'!MF16)
¬¬A1529 | ¬¬IF(ISBLANK('DPW3'!ZP16),"",'DPW3'!ZP16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MG16),"",'DPW3'!MG16)
¬¬A1530 | ¬¬IF(ISBLANK('DPW3'!ZQ16),"",'DPW3'!ZQ16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MH16),"",'DPW3'!MH16)
¬¬A1531 | ¬¬IF(ISBLANK('DPW3'!ZR16),"",'DPW3'!ZR16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MI16),"",'DPW3'!MI16)
¬¬A1532 | ¬¬IF(ISBLANK('DPW3'!ZS16),"",'DPW3'!ZS16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ16),"",'DPW3'!MJ16)
¬¬A1533 | ¬¬IF(ISBLANK('DPW3'!ZT16),"",'DPW3'!ZT16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MK16),"",'DPW3'!MK16)
¬¬A1534 | ¬¬IF(ISBLANK('DPW3'!ZV16),"",'DPW3'!ZV16) | ¬¬'DPW3'!F16 & "," & 'DPW3'!G16 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H16),"",'DPW3'!H16) | Delta | ¬¬IF(ISBLANK('DPW3'!MM16),"",'DPW3'!MM16)
¬¬A1535 | ¬¬IF(ISBLANK('DPW3'!MT17),"",'DPW3'!MT17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!K17),"",'DPW3'!K17)
¬¬A1536 | ¬¬IF(ISBLANK('DPW3'!MV17),"",'DPW3'!MV17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M17),"",'DPW3'!M17) | ¬¬IF(ISBLANK('DPW3'!N17),"",'DPW3'!N17) | ¬¬IF(ISBLANK('DPW3'!O17),"",'DPW3'!O17) | ¬¬IF(ISBLANK('DPW3'!P17),"",'DPW3'!P17) | ¬¬IF(ISBLANK('DPW3'!Q17),"",'DPW3'!Q17) | ¬¬IF(ISBLANK('DPW3'!R17),"",'DPW3'!R17) | ¬¬IF(ISBLANK('DPW3'!S17),"",'DPW3'!S17) | ¬¬IF(ISBLANK('DPW3'!T17),"",'DPW3'!T17) | ¬¬IF(ISBLANK('DPW3'!U17),"",'DPW3'!U17) | ¬¬IF(ISBLANK('DPW3'!V17),"",'DPW3'!V17) | ¬¬IF(ISBLANK('DPW3'!W17),"",'DPW3'!W17) | ¬¬IF(ISBLANK('DPW3'!X17),"",'DPW3'!X17) | ¬¬IF(ISBLANK('DPW3'!Y17),"",'DPW3'!Y17) | ¬¬IF(ISBLANK('DPW3'!Z17),"",'DPW3'!Z17) | ¬¬IF(ISBLANK('DPW3'!AA17),"",'DPW3'!AA17) | ¬¬IF(ISBLANK('DPW3'!AB17),"",'DPW3'!AB17) | ¬¬IF(ISBLANK('DPW3'!AC17),"",'DPW3'!AC17) | ¬¬IF(ISBLANK('DPW3'!AD17),"",'DPW3'!AD17) | ¬¬IF(ISBLANK('DPW3'!AE17),"",'DPW3'!AE17) | ¬¬IF(ISBLANK('DPW3'!AF17),"",'DPW3'!AF17) | ¬¬IF(ISBLANK('DPW3'!AG17),"",'DPW3'!AG17) | ¬¬IF(ISBLANK('DPW3'!AH17),"",'DPW3'!AH17) | ¬¬IF(ISBLANK('DPW3'!AI17),"",'DPW3'!AI17) | ¬¬IF(ISBLANK('DPW3'!AJ17),"",'DPW3'!AJ17) | ¬¬IF(ISBLANK('DPW3'!AK17),"",'DPW3'!AK17) | ¬¬IF(ISBLANK('DPW3'!AL17),"",'DPW3'!AL17) | ¬¬IF(ISBLANK('DPW3'!AM17),"",'DPW3'!AM17) | ¬¬IF(ISBLANK('DPW3'!AN17),"",'DPW3'!AN17) | ¬¬IF(ISBLANK('DPW3'!AO17),"",'DPW3'!AO17) | ¬¬IF(ISBLANK('DPW3'!AP17),"",'DPW3'!AP17) | ¬¬IF(ISBLANK('DPW3'!AQ17),"",'DPW3'!AQ17) | ¬¬IF(ISBLANK('DPW3'!AR17),"",'DPW3'!AR17) | ¬¬IF(ISBLANK('DPW3'!AS17),"",'DPW3'!AS17) | ¬¬IF(ISBLANK('DPW3'!AT17),"",'DPW3'!AT17) | ¬¬IF(ISBLANK('DPW3'!AU17),"",'DPW3'!AU17) | ¬¬IF(ISBLANK('DPW3'!AV17),"",'DPW3'!AV17) | ¬¬IF(ISBLANK('DPW3'!AW17),"",'DPW3'!AW17) | ¬¬IF(ISBLANK('DPW3'!AX17),"",'DPW3'!AX17) | ¬¬IF(ISBLANK('DPW3'!AY17),"",'DPW3'!AY17) | ¬¬IF(ISBLANK('DPW3'!AZ17),"",'DPW3'!AZ17)
¬¬A1537 | ¬¬IF(ISBLANK('DPW3'!OK17),"",'DPW3'!OK17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB17),"",'DPW3'!BB17) | ¬¬IF(ISBLANK('DPW3'!BC17),"",'DPW3'!BC17) | ¬¬IF(ISBLANK('DPW3'!BD17),"",'DPW3'!BD17) | ¬¬IF(ISBLANK('DPW3'!BE17),"",'DPW3'!BE17) | ¬¬IF(ISBLANK('DPW3'!BF17),"",'DPW3'!BF17) | ¬¬IF(ISBLANK('DPW3'!BG17),"",'DPW3'!BG17) | ¬¬IF(ISBLANK('DPW3'!BH17),"",'DPW3'!BH17) | ¬¬IF(ISBLANK('DPW3'!BI17),"",'DPW3'!BI17) | ¬¬IF(ISBLANK('DPW3'!BJ17),"",'DPW3'!BJ17) | ¬¬IF(ISBLANK('DPW3'!BK17),"",'DPW3'!BK17) | ¬¬IF(ISBLANK('DPW3'!BL17),"",'DPW3'!BL17) | ¬¬IF(ISBLANK('DPW3'!BM17),"",'DPW3'!BM17) | ¬¬IF(ISBLANK('DPW3'!BN17),"",'DPW3'!BN17) | ¬¬IF(ISBLANK('DPW3'!BO17),"",'DPW3'!BO17) | ¬¬IF(ISBLANK('DPW3'!BP17),"",'DPW3'!BP17) | ¬¬IF(ISBLANK('DPW3'!BQ17),"",'DPW3'!BQ17) | ¬¬IF(ISBLANK('DPW3'!BR17),"",'DPW3'!BR17) | ¬¬IF(ISBLANK('DPW3'!BS17),"",'DPW3'!BS17) | ¬¬IF(ISBLANK('DPW3'!BT17),"",'DPW3'!BT17) | ¬¬IF(ISBLANK('DPW3'!BU17),"",'DPW3'!BU17) | ¬¬IF(ISBLANK('DPW3'!BV17),"",'DPW3'!BV17) | ¬¬IF(ISBLANK('DPW3'!BW17),"",'DPW3'!BW17) | ¬¬IF(ISBLANK('DPW3'!BX17),"",'DPW3'!BX17) | ¬¬IF(ISBLANK('DPW3'!BY17),"",'DPW3'!BY17) | ¬¬IF(ISBLANK('DPW3'!BZ17),"",'DPW3'!BZ17) | ¬¬IF(ISBLANK('DPW3'!CA17),"",'DPW3'!CA17) | ¬¬IF(ISBLANK('DPW3'!CB17),"",'DPW3'!CB17) | ¬¬IF(ISBLANK('DPW3'!CC17),"",'DPW3'!CC17) | ¬¬IF(ISBLANK('DPW3'!CD17),"",'DPW3'!CD17) | ¬¬IF(ISBLANK('DPW3'!CE17),"",'DPW3'!CE17) | ¬¬IF(ISBLANK('DPW3'!CF17),"",'DPW3'!CF17) | ¬¬IF(ISBLANK('DPW3'!CG17),"",'DPW3'!CG17) | ¬¬IF(ISBLANK('DPW3'!CH17),"",'DPW3'!CH17) | ¬¬IF(ISBLANK('DPW3'!CI17),"",'DPW3'!CI17) | ¬¬IF(ISBLANK('DPW3'!CJ17),"",'DPW3'!CJ17) | ¬¬IF(ISBLANK('DPW3'!CK17),"",'DPW3'!CK17) | ¬¬IF(ISBLANK('DPW3'!CL17),"",'DPW3'!CL17) | ¬¬IF(ISBLANK('DPW3'!CM17),"",'DPW3'!CM17) | ¬¬IF(ISBLANK('DPW3'!CN17),"",'DPW3'!CN17) | ¬¬IF(ISBLANK('DPW3'!CO17),"",'DPW3'!CO17)
¬¬A1538 | ¬¬IF(ISBLANK('DPW3'!PZ17),"",'DPW3'!PZ17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ17),"",'DPW3'!CQ17) | ¬¬IF(ISBLANK('DPW3'!CR17),"",'DPW3'!CR17) | ¬¬IF(ISBLANK('DPW3'!CS17),"",'DPW3'!CS17) | ¬¬IF(ISBLANK('DPW3'!CT17),"",'DPW3'!CT17) | ¬¬IF(ISBLANK('DPW3'!CU17),"",'DPW3'!CU17) | ¬¬IF(ISBLANK('DPW3'!CV17),"",'DPW3'!CV17) | ¬¬IF(ISBLANK('DPW3'!CW17),"",'DPW3'!CW17) | ¬¬IF(ISBLANK('DPW3'!CX17),"",'DPW3'!CX17) | ¬¬IF(ISBLANK('DPW3'!CY17),"",'DPW3'!CY17) | ¬¬IF(ISBLANK('DPW3'!CZ17),"",'DPW3'!CZ17) | ¬¬IF(ISBLANK('DPW3'!DA17),"",'DPW3'!DA17) | ¬¬IF(ISBLANK('DPW3'!DB17),"",'DPW3'!DB17) | ¬¬IF(ISBLANK('DPW3'!DC17),"",'DPW3'!DC17) | ¬¬IF(ISBLANK('DPW3'!DD17),"",'DPW3'!DD17) | ¬¬IF(ISBLANK('DPW3'!DE17),"",'DPW3'!DE17) | ¬¬IF(ISBLANK('DPW3'!DF17),"",'DPW3'!DF17) | ¬¬IF(ISBLANK('DPW3'!DG17),"",'DPW3'!DG17) | ¬¬IF(ISBLANK('DPW3'!DH17),"",'DPW3'!DH17) | ¬¬IF(ISBLANK('DPW3'!DI17),"",'DPW3'!DI17) | ¬¬IF(ISBLANK('DPW3'!DJ17),"",'DPW3'!DJ17) | ¬¬IF(ISBLANK('DPW3'!DK17),"",'DPW3'!DK17) | ¬¬IF(ISBLANK('DPW3'!DL17),"",'DPW3'!DL17) | ¬¬IF(ISBLANK('DPW3'!DM17),"",'DPW3'!DM17) | ¬¬IF(ISBLANK('DPW3'!DN17),"",'DPW3'!DN17) | ¬¬IF(ISBLANK('DPW3'!DO17),"",'DPW3'!DO17) | ¬¬IF(ISBLANK('DPW3'!DP17),"",'DPW3'!DP17) | ¬¬IF(ISBLANK('DPW3'!DQ17),"",'DPW3'!DQ17) | ¬¬IF(ISBLANK('DPW3'!DR17),"",'DPW3'!DR17) | ¬¬IF(ISBLANK('DPW3'!DS17),"",'DPW3'!DS17) | ¬¬IF(ISBLANK('DPW3'!DT17),"",'DPW3'!DT17) | ¬¬IF(ISBLANK('DPW3'!DU17),"",'DPW3'!DU17) | ¬¬IF(ISBLANK('DPW3'!DV17),"",'DPW3'!DV17) | ¬¬IF(ISBLANK('DPW3'!DW17),"",'DPW3'!DW17) | ¬¬IF(ISBLANK('DPW3'!DX17),"",'DPW3'!DX17) | ¬¬IF(ISBLANK('DPW3'!DY17),"",'DPW3'!DY17) | ¬¬IF(ISBLANK('DPW3'!DZ17),"",'DPW3'!DZ17) | ¬¬IF(ISBLANK('DPW3'!EA17),"",'DPW3'!EA17) | ¬¬IF(ISBLANK('DPW3'!EB17),"",'DPW3'!EB17) | ¬¬IF(ISBLANK('DPW3'!EC17),"",'DPW3'!EC17) | ¬¬IF(ISBLANK('DPW3'!ED17),"",'DPW3'!ED17)
¬¬A1539 | ¬¬IF(ISBLANK('DPW3'!RO17),"",'DPW3'!RO17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF17),"",'DPW3'!EF17) | ¬¬IF(ISBLANK('DPW3'!EG17),"",'DPW3'!EG17) | ¬¬IF(ISBLANK('DPW3'!EH17),"",'DPW3'!EH17) | ¬¬IF(ISBLANK('DPW3'!EI17),"",'DPW3'!EI17) | ¬¬IF(ISBLANK('DPW3'!EJ17),"",'DPW3'!EJ17) | ¬¬IF(ISBLANK('DPW3'!EK17),"",'DPW3'!EK17) | ¬¬IF(ISBLANK('DPW3'!EL17),"",'DPW3'!EL17) | ¬¬IF(ISBLANK('DPW3'!EM17),"",'DPW3'!EM17) | ¬¬IF(ISBLANK('DPW3'!EN17),"",'DPW3'!EN17) | ¬¬IF(ISBLANK('DPW3'!EO17),"",'DPW3'!EO17) | ¬¬IF(ISBLANK('DPW3'!EP17),"",'DPW3'!EP17) | ¬¬IF(ISBLANK('DPW3'!EQ17),"",'DPW3'!EQ17) | ¬¬IF(ISBLANK('DPW3'!ER17),"",'DPW3'!ER17) | ¬¬IF(ISBLANK('DPW3'!ES17),"",'DPW3'!ES17) | ¬¬IF(ISBLANK('DPW3'!ET17),"",'DPW3'!ET17) | ¬¬IF(ISBLANK('DPW3'!EU17),"",'DPW3'!EU17) | ¬¬IF(ISBLANK('DPW3'!EV17),"",'DPW3'!EV17) | ¬¬IF(ISBLANK('DPW3'!EW17),"",'DPW3'!EW17) | ¬¬IF(ISBLANK('DPW3'!EX17),"",'DPW3'!EX17) | ¬¬IF(ISBLANK('DPW3'!EY17),"",'DPW3'!EY17) | ¬¬IF(ISBLANK('DPW3'!EZ17),"",'DPW3'!EZ17) | ¬¬IF(ISBLANK('DPW3'!FA17),"",'DPW3'!FA17) | ¬¬IF(ISBLANK('DPW3'!FB17),"",'DPW3'!FB17) | ¬¬IF(ISBLANK('DPW3'!FC17),"",'DPW3'!FC17) | ¬¬IF(ISBLANK('DPW3'!FD17),"",'DPW3'!FD17) | ¬¬IF(ISBLANK('DPW3'!FE17),"",'DPW3'!FE17) | ¬¬IF(ISBLANK('DPW3'!FF17),"",'DPW3'!FF17) | ¬¬IF(ISBLANK('DPW3'!FG17),"",'DPW3'!FG17) | ¬¬IF(ISBLANK('DPW3'!FH17),"",'DPW3'!FH17) | ¬¬IF(ISBLANK('DPW3'!FI17),"",'DPW3'!FI17) | ¬¬IF(ISBLANK('DPW3'!FJ17),"",'DPW3'!FJ17) | ¬¬IF(ISBLANK('DPW3'!FK17),"",'DPW3'!FK17) | ¬¬IF(ISBLANK('DPW3'!FL17),"",'DPW3'!FL17) | ¬¬IF(ISBLANK('DPW3'!FM17),"",'DPW3'!FM17) | ¬¬IF(ISBLANK('DPW3'!FN17),"",'DPW3'!FN17) | ¬¬IF(ISBLANK('DPW3'!FO17),"",'DPW3'!FO17) | ¬¬IF(ISBLANK('DPW3'!FP17),"",'DPW3'!FP17) | ¬¬IF(ISBLANK('DPW3'!FQ17),"",'DPW3'!FQ17) | ¬¬IF(ISBLANK('DPW3'!FR17),"",'DPW3'!FR17) | ¬¬IF(ISBLANK('DPW3'!FS17),"",'DPW3'!FS17)
¬¬A1540 | ¬¬IF(ISBLANK('DPW3'!TD17),"",'DPW3'!TD17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU17),"",'DPW3'!FU17) | ¬¬IF(ISBLANK('DPW3'!FV17),"",'DPW3'!FV17) | ¬¬IF(ISBLANK('DPW3'!FW17),"",'DPW3'!FW17) | ¬¬IF(ISBLANK('DPW3'!FX17),"",'DPW3'!FX17) | ¬¬IF(ISBLANK('DPW3'!FY17),"",'DPW3'!FY17) | ¬¬IF(ISBLANK('DPW3'!FZ17),"",'DPW3'!FZ17) | ¬¬IF(ISBLANK('DPW3'!GA17),"",'DPW3'!GA17) | ¬¬IF(ISBLANK('DPW3'!GB17),"",'DPW3'!GB17) | ¬¬IF(ISBLANK('DPW3'!GC17),"",'DPW3'!GC17) | ¬¬IF(ISBLANK('DPW3'!GD17),"",'DPW3'!GD17) | ¬¬IF(ISBLANK('DPW3'!GE17),"",'DPW3'!GE17) | ¬¬IF(ISBLANK('DPW3'!GF17),"",'DPW3'!GF17) | ¬¬IF(ISBLANK('DPW3'!GG17),"",'DPW3'!GG17) | ¬¬IF(ISBLANK('DPW3'!GH17),"",'DPW3'!GH17) | ¬¬IF(ISBLANK('DPW3'!GI17),"",'DPW3'!GI17) | ¬¬IF(ISBLANK('DPW3'!GJ17),"",'DPW3'!GJ17) | ¬¬IF(ISBLANK('DPW3'!GK17),"",'DPW3'!GK17) | ¬¬IF(ISBLANK('DPW3'!GL17),"",'DPW3'!GL17) | ¬¬IF(ISBLANK('DPW3'!GM17),"",'DPW3'!GM17) | ¬¬IF(ISBLANK('DPW3'!GN17),"",'DPW3'!GN17) | ¬¬IF(ISBLANK('DPW3'!GO17),"",'DPW3'!GO17) | ¬¬IF(ISBLANK('DPW3'!GP17),"",'DPW3'!GP17) | ¬¬IF(ISBLANK('DPW3'!GQ17),"",'DPW3'!GQ17) | ¬¬IF(ISBLANK('DPW3'!GR17),"",'DPW3'!GR17) | ¬¬IF(ISBLANK('DPW3'!GS17),"",'DPW3'!GS17) | ¬¬IF(ISBLANK('DPW3'!GT17),"",'DPW3'!GT17) | ¬¬IF(ISBLANK('DPW3'!GU17),"",'DPW3'!GU17) | ¬¬IF(ISBLANK('DPW3'!GV17),"",'DPW3'!GV17) | ¬¬IF(ISBLANK('DPW3'!GW17),"",'DPW3'!GW17) | ¬¬IF(ISBLANK('DPW3'!GX17),"",'DPW3'!GX17) | ¬¬IF(ISBLANK('DPW3'!GY17),"",'DPW3'!GY17) | ¬¬IF(ISBLANK('DPW3'!GZ17),"",'DPW3'!GZ17) | ¬¬IF(ISBLANK('DPW3'!HA17),"",'DPW3'!HA17) | ¬¬IF(ISBLANK('DPW3'!HB17),"",'DPW3'!HB17) | ¬¬IF(ISBLANK('DPW3'!HC17),"",'DPW3'!HC17) | ¬¬IF(ISBLANK('DPW3'!HD17),"",'DPW3'!HD17) | ¬¬IF(ISBLANK('DPW3'!HE17),"",'DPW3'!HE17) | ¬¬IF(ISBLANK('DPW3'!HF17),"",'DPW3'!HF17) | ¬¬IF(ISBLANK('DPW3'!HG17),"",'DPW3'!HG17) | ¬¬IF(ISBLANK('DPW3'!HH17),"",'DPW3'!HH17)
¬¬A1541 | ¬¬IF(ISBLANK('DPW3'!US17),"",'DPW3'!US17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ17),"",'DPW3'!HJ17) | ¬¬IF(ISBLANK('DPW3'!HK17),"",'DPW3'!HK17) | ¬¬IF(ISBLANK('DPW3'!HL17),"",'DPW3'!HL17) | ¬¬IF(ISBLANK('DPW3'!HM17),"",'DPW3'!HM17) | ¬¬IF(ISBLANK('DPW3'!HN17),"",'DPW3'!HN17) | ¬¬IF(ISBLANK('DPW3'!HO17),"",'DPW3'!HO17) | ¬¬IF(ISBLANK('DPW3'!HP17),"",'DPW3'!HP17) | ¬¬IF(ISBLANK('DPW3'!HQ17),"",'DPW3'!HQ17) | ¬¬IF(ISBLANK('DPW3'!HR17),"",'DPW3'!HR17) | ¬¬IF(ISBLANK('DPW3'!HS17),"",'DPW3'!HS17) | ¬¬IF(ISBLANK('DPW3'!HT17),"",'DPW3'!HT17) | ¬¬IF(ISBLANK('DPW3'!HU17),"",'DPW3'!HU17) | ¬¬IF(ISBLANK('DPW3'!HV17),"",'DPW3'!HV17) | ¬¬IF(ISBLANK('DPW3'!HW17),"",'DPW3'!HW17) | ¬¬IF(ISBLANK('DPW3'!HX17),"",'DPW3'!HX17) | ¬¬IF(ISBLANK('DPW3'!HY17),"",'DPW3'!HY17) | ¬¬IF(ISBLANK('DPW3'!HZ17),"",'DPW3'!HZ17) | ¬¬IF(ISBLANK('DPW3'!IA17),"",'DPW3'!IA17) | ¬¬IF(ISBLANK('DPW3'!IB17),"",'DPW3'!IB17) | ¬¬IF(ISBLANK('DPW3'!IC17),"",'DPW3'!IC17) | ¬¬IF(ISBLANK('DPW3'!ID17),"",'DPW3'!ID17) | ¬¬IF(ISBLANK('DPW3'!IE17),"",'DPW3'!IE17) | ¬¬IF(ISBLANK('DPW3'!IF17),"",'DPW3'!IF17) | ¬¬IF(ISBLANK('DPW3'!IG17),"",'DPW3'!IG17) | ¬¬IF(ISBLANK('DPW3'!IH17),"",'DPW3'!IH17) | ¬¬IF(ISBLANK('DPW3'!II17),"",'DPW3'!II17) | ¬¬IF(ISBLANK('DPW3'!IJ17),"",'DPW3'!IJ17) | ¬¬IF(ISBLANK('DPW3'!IK17),"",'DPW3'!IK17) | ¬¬IF(ISBLANK('DPW3'!IL17),"",'DPW3'!IL17) | ¬¬IF(ISBLANK('DPW3'!IM17),"",'DPW3'!IM17) | ¬¬IF(ISBLANK('DPW3'!IN17),"",'DPW3'!IN17) | ¬¬IF(ISBLANK('DPW3'!IO17),"",'DPW3'!IO17) | ¬¬IF(ISBLANK('DPW3'!IP17),"",'DPW3'!IP17) | ¬¬IF(ISBLANK('DPW3'!IQ17),"",'DPW3'!IQ17) | ¬¬IF(ISBLANK('DPW3'!IR17),"",'DPW3'!IR17) | ¬¬IF(ISBLANK('DPW3'!IS17),"",'DPW3'!IS17) | ¬¬IF(ISBLANK('DPW3'!IT17),"",'DPW3'!IT17) | ¬¬IF(ISBLANK('DPW3'!IU17),"",'DPW3'!IU17) | ¬¬IF(ISBLANK('DPW3'!IV17),"",'DPW3'!IV17) | ¬¬IF(ISBLANK('DPW3'!IW17),"",'DPW3'!IW17)
¬¬A1542 | ¬¬IF(ISBLANK('DPW3'!WH17),"",'DPW3'!WH17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY17),"",'DPW3'!IY17) | ¬¬IF(ISBLANK('DPW3'!IZ17),"",'DPW3'!IZ17) | ¬¬IF(ISBLANK('DPW3'!JA17),"",'DPW3'!JA17) | ¬¬IF(ISBLANK('DPW3'!JB17),"",'DPW3'!JB17) | ¬¬IF(ISBLANK('DPW3'!JC17),"",'DPW3'!JC17) | ¬¬IF(ISBLANK('DPW3'!JD17),"",'DPW3'!JD17) | ¬¬IF(ISBLANK('DPW3'!JE17),"",'DPW3'!JE17) | ¬¬IF(ISBLANK('DPW3'!JF17),"",'DPW3'!JF17) | ¬¬IF(ISBLANK('DPW3'!JG17),"",'DPW3'!JG17) | ¬¬IF(ISBLANK('DPW3'!JH17),"",'DPW3'!JH17) | ¬¬IF(ISBLANK('DPW3'!JI17),"",'DPW3'!JI17) | ¬¬IF(ISBLANK('DPW3'!JJ17),"",'DPW3'!JJ17) | ¬¬IF(ISBLANK('DPW3'!JK17),"",'DPW3'!JK17) | ¬¬IF(ISBLANK('DPW3'!JL17),"",'DPW3'!JL17) | ¬¬IF(ISBLANK('DPW3'!JM17),"",'DPW3'!JM17) | ¬¬IF(ISBLANK('DPW3'!JN17),"",'DPW3'!JN17) | ¬¬IF(ISBLANK('DPW3'!JO17),"",'DPW3'!JO17) | ¬¬IF(ISBLANK('DPW3'!JP17),"",'DPW3'!JP17) | ¬¬IF(ISBLANK('DPW3'!JQ17),"",'DPW3'!JQ17) | ¬¬IF(ISBLANK('DPW3'!JR17),"",'DPW3'!JR17) | ¬¬IF(ISBLANK('DPW3'!JS17),"",'DPW3'!JS17) | ¬¬IF(ISBLANK('DPW3'!JT17),"",'DPW3'!JT17) | ¬¬IF(ISBLANK('DPW3'!JU17),"",'DPW3'!JU17) | ¬¬IF(ISBLANK('DPW3'!JV17),"",'DPW3'!JV17) | ¬¬IF(ISBLANK('DPW3'!JW17),"",'DPW3'!JW17) | ¬¬IF(ISBLANK('DPW3'!JX17),"",'DPW3'!JX17) | ¬¬IF(ISBLANK('DPW3'!JY17),"",'DPW3'!JY17) | ¬¬IF(ISBLANK('DPW3'!JZ17),"",'DPW3'!JZ17) | ¬¬IF(ISBLANK('DPW3'!KA17),"",'DPW3'!KA17) | ¬¬IF(ISBLANK('DPW3'!KB17),"",'DPW3'!KB17) | ¬¬IF(ISBLANK('DPW3'!KC17),"",'DPW3'!KC17) | ¬¬IF(ISBLANK('DPW3'!KD17),"",'DPW3'!KD17) | ¬¬IF(ISBLANK('DPW3'!KE17),"",'DPW3'!KE17) | ¬¬IF(ISBLANK('DPW3'!KF17),"",'DPW3'!KF17) | ¬¬IF(ISBLANK('DPW3'!KG17),"",'DPW3'!KG17) | ¬¬IF(ISBLANK('DPW3'!KH17),"",'DPW3'!KH17) | ¬¬IF(ISBLANK('DPW3'!KI17),"",'DPW3'!KI17) | ¬¬IF(ISBLANK('DPW3'!KJ17),"",'DPW3'!KJ17) | ¬¬IF(ISBLANK('DPW3'!KK17),"",'DPW3'!KK17) | ¬¬IF(ISBLANK('DPW3'!KL17),"",'DPW3'!KL17)
¬¬A1543 | ¬¬IF(ISBLANK('DPW3'!XW17),"",'DPW3'!XW17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN17),"",'DPW3'!KN17) | ¬¬IF(ISBLANK('DPW3'!KO17),"",'DPW3'!KO17) | ¬¬IF(ISBLANK('DPW3'!KP17),"",'DPW3'!KP17) | ¬¬IF(ISBLANK('DPW3'!KQ17),"",'DPW3'!KQ17) | ¬¬IF(ISBLANK('DPW3'!KR17),"",'DPW3'!KR17) | ¬¬IF(ISBLANK('DPW3'!KS17),"",'DPW3'!KS17) | ¬¬IF(ISBLANK('DPW3'!KT17),"",'DPW3'!KT17) | ¬¬IF(ISBLANK('DPW3'!KU17),"",'DPW3'!KU17) | ¬¬IF(ISBLANK('DPW3'!KV17),"",'DPW3'!KV17) | ¬¬IF(ISBLANK('DPW3'!KW17),"",'DPW3'!KW17) | ¬¬IF(ISBLANK('DPW3'!KX17),"",'DPW3'!KX17) | ¬¬IF(ISBLANK('DPW3'!KY17),"",'DPW3'!KY17) | ¬¬IF(ISBLANK('DPW3'!KZ17),"",'DPW3'!KZ17) | ¬¬IF(ISBLANK('DPW3'!LA17),"",'DPW3'!LA17) | ¬¬IF(ISBLANK('DPW3'!LB17),"",'DPW3'!LB17) | ¬¬IF(ISBLANK('DPW3'!LC17),"",'DPW3'!LC17) | ¬¬IF(ISBLANK('DPW3'!LD17),"",'DPW3'!LD17) | ¬¬IF(ISBLANK('DPW3'!LE17),"",'DPW3'!LE17) | ¬¬IF(ISBLANK('DPW3'!LF17),"",'DPW3'!LF17) | ¬¬IF(ISBLANK('DPW3'!LG17),"",'DPW3'!LG17) | ¬¬IF(ISBLANK('DPW3'!LH17),"",'DPW3'!LH17) | ¬¬IF(ISBLANK('DPW3'!LI17),"",'DPW3'!LI17) | ¬¬IF(ISBLANK('DPW3'!LJ17),"",'DPW3'!LJ17) | ¬¬IF(ISBLANK('DPW3'!LK17),"",'DPW3'!LK17) | ¬¬IF(ISBLANK('DPW3'!LL17),"",'DPW3'!LL17) | ¬¬IF(ISBLANK('DPW3'!LM17),"",'DPW3'!LM17) | ¬¬IF(ISBLANK('DPW3'!LN17),"",'DPW3'!LN17) | ¬¬IF(ISBLANK('DPW3'!LO17),"",'DPW3'!LO17) | ¬¬IF(ISBLANK('DPW3'!LP17),"",'DPW3'!LP17) | ¬¬IF(ISBLANK('DPW3'!LQ17),"",'DPW3'!LQ17) | ¬¬IF(ISBLANK('DPW3'!LR17),"",'DPW3'!LR17) | ¬¬IF(ISBLANK('DPW3'!LS17),"",'DPW3'!LS17) | ¬¬IF(ISBLANK('DPW3'!LT17),"",'DPW3'!LT17) | ¬¬IF(ISBLANK('DPW3'!LU17),"",'DPW3'!LU17) | ¬¬IF(ISBLANK('DPW3'!LV17),"",'DPW3'!LV17) | ¬¬IF(ISBLANK('DPW3'!LW17),"",'DPW3'!LW17) | ¬¬IF(ISBLANK('DPW3'!LX17),"",'DPW3'!LX17) | ¬¬IF(ISBLANK('DPW3'!LY17),"",'DPW3'!LY17) | ¬¬IF(ISBLANK('DPW3'!LZ17),"",'DPW3'!LZ17) | ¬¬IF(ISBLANK('DPW3'!MA17),"",'DPW3'!MA17)
¬¬A1544 | ¬¬IF(ISBLANK('DPW3'!ZL17),"",'DPW3'!ZL17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MC17),"",'DPW3'!MC17)
¬¬A1545 | ¬¬IF(ISBLANK('DPW3'!ZM17),"",'DPW3'!ZM17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MD17),"",'DPW3'!MD17)
¬¬A1546 | ¬¬IF(ISBLANK('DPW3'!ZN17),"",'DPW3'!ZN17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!ML17),"",'DPW3'!ML17)
¬¬A1547 | ¬¬IF(ISBLANK('DPW3'!ZO17),"",'DPW3'!ZO17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MF17),"",'DPW3'!MF17)
¬¬A1548 | ¬¬IF(ISBLANK('DPW3'!ZP17),"",'DPW3'!ZP17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MG17),"",'DPW3'!MG17)
¬¬A1549 | ¬¬IF(ISBLANK('DPW3'!ZQ17),"",'DPW3'!ZQ17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MH17),"",'DPW3'!MH17)
¬¬A1550 | ¬¬IF(ISBLANK('DPW3'!ZR17),"",'DPW3'!ZR17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MI17),"",'DPW3'!MI17)
¬¬A1551 | ¬¬IF(ISBLANK('DPW3'!ZS17),"",'DPW3'!ZS17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ17),"",'DPW3'!MJ17)
¬¬A1552 | ¬¬IF(ISBLANK('DPW3'!ZT17),"",'DPW3'!ZT17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MK17),"",'DPW3'!MK17)
¬¬A1553 | ¬¬IF(ISBLANK('DPW3'!ZV17),"",'DPW3'!ZV17) | ¬¬'DPW3'!F17 & "," & 'DPW3'!G17 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H17),"",'DPW3'!H17) | Delta | ¬¬IF(ISBLANK('DPW3'!MM17),"",'DPW3'!MM17)
¬¬A1554 | ¬¬IF(ISBLANK('DPW3'!MT18),"",'DPW3'!MT18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!K19),"",'DPW3'!K19)
¬¬A1555 | ¬¬IF(ISBLANK('DPW3'!MV18),"",'DPW3'!MV18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M19),"",'DPW3'!M19) | ¬¬IF(ISBLANK('DPW3'!N19),"",'DPW3'!N19) | ¬¬IF(ISBLANK('DPW3'!O19),"",'DPW3'!O19) | ¬¬IF(ISBLANK('DPW3'!P19),"",'DPW3'!P19) | ¬¬IF(ISBLANK('DPW3'!Q19),"",'DPW3'!Q19) | ¬¬IF(ISBLANK('DPW3'!R19),"",'DPW3'!R19) | ¬¬IF(ISBLANK('DPW3'!S19),"",'DPW3'!S19) | ¬¬IF(ISBLANK('DPW3'!T19),"",'DPW3'!T19) | ¬¬IF(ISBLANK('DPW3'!U19),"",'DPW3'!U19) | ¬¬IF(ISBLANK('DPW3'!V19),"",'DPW3'!V19) | ¬¬IF(ISBLANK('DPW3'!W19),"",'DPW3'!W19) | ¬¬IF(ISBLANK('DPW3'!X19),"",'DPW3'!X19) | ¬¬IF(ISBLANK('DPW3'!Y19),"",'DPW3'!Y19) | ¬¬IF(ISBLANK('DPW3'!Z19),"",'DPW3'!Z19) | ¬¬IF(ISBLANK('DPW3'!AA19),"",'DPW3'!AA19) | ¬¬IF(ISBLANK('DPW3'!AB19),"",'DPW3'!AB19) | ¬¬IF(ISBLANK('DPW3'!AC19),"",'DPW3'!AC19) | ¬¬IF(ISBLANK('DPW3'!AD19),"",'DPW3'!AD19) | ¬¬IF(ISBLANK('DPW3'!AE19),"",'DPW3'!AE19) | ¬¬IF(ISBLANK('DPW3'!AF19),"",'DPW3'!AF19) | ¬¬IF(ISBLANK('DPW3'!AG19),"",'DPW3'!AG19) | ¬¬IF(ISBLANK('DPW3'!AH19),"",'DPW3'!AH19) | ¬¬IF(ISBLANK('DPW3'!AI19),"",'DPW3'!AI19) | ¬¬IF(ISBLANK('DPW3'!AJ19),"",'DPW3'!AJ19) | ¬¬IF(ISBLANK('DPW3'!AK19),"",'DPW3'!AK19) | ¬¬IF(ISBLANK('DPW3'!AL19),"",'DPW3'!AL19) | ¬¬IF(ISBLANK('DPW3'!AM19),"",'DPW3'!AM19) | ¬¬IF(ISBLANK('DPW3'!AN19),"",'DPW3'!AN19) | ¬¬IF(ISBLANK('DPW3'!AO19),"",'DPW3'!AO19) | ¬¬IF(ISBLANK('DPW3'!AP19),"",'DPW3'!AP19) | ¬¬IF(ISBLANK('DPW3'!AQ19),"",'DPW3'!AQ19) | ¬¬IF(ISBLANK('DPW3'!AR19),"",'DPW3'!AR19) | ¬¬IF(ISBLANK('DPW3'!AS19),"",'DPW3'!AS19) | ¬¬IF(ISBLANK('DPW3'!AT19),"",'DPW3'!AT19) | ¬¬IF(ISBLANK('DPW3'!AU19),"",'DPW3'!AU19) | ¬¬IF(ISBLANK('DPW3'!AV19),"",'DPW3'!AV19) | ¬¬IF(ISBLANK('DPW3'!AW19),"",'DPW3'!AW19) | ¬¬IF(ISBLANK('DPW3'!AX19),"",'DPW3'!AX19) | ¬¬IF(ISBLANK('DPW3'!AY19),"",'DPW3'!AY19) | ¬¬IF(ISBLANK('DPW3'!AZ19),"",'DPW3'!AZ19)
¬¬A1556 | ¬¬IF(ISBLANK('DPW3'!OK18),"",'DPW3'!OK18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB19),"",'DPW3'!BB19) | ¬¬IF(ISBLANK('DPW3'!BC19),"",'DPW3'!BC19) | ¬¬IF(ISBLANK('DPW3'!BD19),"",'DPW3'!BD19) | ¬¬IF(ISBLANK('DPW3'!BE19),"",'DPW3'!BE19) | ¬¬IF(ISBLANK('DPW3'!BF19),"",'DPW3'!BF19) | ¬¬IF(ISBLANK('DPW3'!BG19),"",'DPW3'!BG19) | ¬¬IF(ISBLANK('DPW3'!BH19),"",'DPW3'!BH19) | ¬¬IF(ISBLANK('DPW3'!BI19),"",'DPW3'!BI19) | ¬¬IF(ISBLANK('DPW3'!BJ19),"",'DPW3'!BJ19) | ¬¬IF(ISBLANK('DPW3'!BK19),"",'DPW3'!BK19) | ¬¬IF(ISBLANK('DPW3'!BL19),"",'DPW3'!BL19) | ¬¬IF(ISBLANK('DPW3'!BM19),"",'DPW3'!BM19) | ¬¬IF(ISBLANK('DPW3'!BN19),"",'DPW3'!BN19) | ¬¬IF(ISBLANK('DPW3'!BO19),"",'DPW3'!BO19) | ¬¬IF(ISBLANK('DPW3'!BP19),"",'DPW3'!BP19) | ¬¬IF(ISBLANK('DPW3'!BQ19),"",'DPW3'!BQ19) | ¬¬IF(ISBLANK('DPW3'!BR19),"",'DPW3'!BR19) | ¬¬IF(ISBLANK('DPW3'!BS19),"",'DPW3'!BS19) | ¬¬IF(ISBLANK('DPW3'!BT19),"",'DPW3'!BT19) | ¬¬IF(ISBLANK('DPW3'!BU19),"",'DPW3'!BU19) | ¬¬IF(ISBLANK('DPW3'!BV19),"",'DPW3'!BV19) | ¬¬IF(ISBLANK('DPW3'!BW19),"",'DPW3'!BW19) | ¬¬IF(ISBLANK('DPW3'!BX19),"",'DPW3'!BX19) | ¬¬IF(ISBLANK('DPW3'!BY19),"",'DPW3'!BY19) | ¬¬IF(ISBLANK('DPW3'!BZ19),"",'DPW3'!BZ19) | ¬¬IF(ISBLANK('DPW3'!CA19),"",'DPW3'!CA19) | ¬¬IF(ISBLANK('DPW3'!CB19),"",'DPW3'!CB19) | ¬¬IF(ISBLANK('DPW3'!CC19),"",'DPW3'!CC19) | ¬¬IF(ISBLANK('DPW3'!CD19),"",'DPW3'!CD19) | ¬¬IF(ISBLANK('DPW3'!CE19),"",'DPW3'!CE19) | ¬¬IF(ISBLANK('DPW3'!CF19),"",'DPW3'!CF19) | ¬¬IF(ISBLANK('DPW3'!CG19),"",'DPW3'!CG19) | ¬¬IF(ISBLANK('DPW3'!CH19),"",'DPW3'!CH19) | ¬¬IF(ISBLANK('DPW3'!CI19),"",'DPW3'!CI19) | ¬¬IF(ISBLANK('DPW3'!CJ19),"",'DPW3'!CJ19) | ¬¬IF(ISBLANK('DPW3'!CK19),"",'DPW3'!CK19) | ¬¬IF(ISBLANK('DPW3'!CL19),"",'DPW3'!CL19) | ¬¬IF(ISBLANK('DPW3'!CM19),"",'DPW3'!CM19) | ¬¬IF(ISBLANK('DPW3'!CN19),"",'DPW3'!CN19) | ¬¬IF(ISBLANK('DPW3'!CO19),"",'DPW3'!CO19)
¬¬A1557 | ¬¬IF(ISBLANK('DPW3'!PZ18),"",'DPW3'!PZ18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ19),"",'DPW3'!CQ19) | ¬¬IF(ISBLANK('DPW3'!CR19),"",'DPW3'!CR19) | ¬¬IF(ISBLANK('DPW3'!CS19),"",'DPW3'!CS19) | ¬¬IF(ISBLANK('DPW3'!CT19),"",'DPW3'!CT19) | ¬¬IF(ISBLANK('DPW3'!CU19),"",'DPW3'!CU19) | ¬¬IF(ISBLANK('DPW3'!CV19),"",'DPW3'!CV19) | ¬¬IF(ISBLANK('DPW3'!CW19),"",'DPW3'!CW19) | ¬¬IF(ISBLANK('DPW3'!CX19),"",'DPW3'!CX19) | ¬¬IF(ISBLANK('DPW3'!CY19),"",'DPW3'!CY19) | ¬¬IF(ISBLANK('DPW3'!CZ19),"",'DPW3'!CZ19) | ¬¬IF(ISBLANK('DPW3'!DA19),"",'DPW3'!DA19) | ¬¬IF(ISBLANK('DPW3'!DB19),"",'DPW3'!DB19) | ¬¬IF(ISBLANK('DPW3'!DC19),"",'DPW3'!DC19) | ¬¬IF(ISBLANK('DPW3'!DD19),"",'DPW3'!DD19) | ¬¬IF(ISBLANK('DPW3'!DE19),"",'DPW3'!DE19) | ¬¬IF(ISBLANK('DPW3'!DF19),"",'DPW3'!DF19) | ¬¬IF(ISBLANK('DPW3'!DG19),"",'DPW3'!DG19) | ¬¬IF(ISBLANK('DPW3'!DH19),"",'DPW3'!DH19) | ¬¬IF(ISBLANK('DPW3'!DI19),"",'DPW3'!DI19) | ¬¬IF(ISBLANK('DPW3'!DJ19),"",'DPW3'!DJ19) | ¬¬IF(ISBLANK('DPW3'!DK19),"",'DPW3'!DK19) | ¬¬IF(ISBLANK('DPW3'!DL19),"",'DPW3'!DL19) | ¬¬IF(ISBLANK('DPW3'!DM19),"",'DPW3'!DM19) | ¬¬IF(ISBLANK('DPW3'!DN19),"",'DPW3'!DN19) | ¬¬IF(ISBLANK('DPW3'!DO19),"",'DPW3'!DO19) | ¬¬IF(ISBLANK('DPW3'!DP19),"",'DPW3'!DP19) | ¬¬IF(ISBLANK('DPW3'!DQ19),"",'DPW3'!DQ19) | ¬¬IF(ISBLANK('DPW3'!DR19),"",'DPW3'!DR19) | ¬¬IF(ISBLANK('DPW3'!DS19),"",'DPW3'!DS19) | ¬¬IF(ISBLANK('DPW3'!DT19),"",'DPW3'!DT19) | ¬¬IF(ISBLANK('DPW3'!DU19),"",'DPW3'!DU19) | ¬¬IF(ISBLANK('DPW3'!DV19),"",'DPW3'!DV19) | ¬¬IF(ISBLANK('DPW3'!DW19),"",'DPW3'!DW19) | ¬¬IF(ISBLANK('DPW3'!DX19),"",'DPW3'!DX19) | ¬¬IF(ISBLANK('DPW3'!DY19),"",'DPW3'!DY19) | ¬¬IF(ISBLANK('DPW3'!DZ19),"",'DPW3'!DZ19) | ¬¬IF(ISBLANK('DPW3'!EA19),"",'DPW3'!EA19) | ¬¬IF(ISBLANK('DPW3'!EB19),"",'DPW3'!EB19) | ¬¬IF(ISBLANK('DPW3'!EC19),"",'DPW3'!EC19) | ¬¬IF(ISBLANK('DPW3'!ED19),"",'DPW3'!ED19)
¬¬A1558 | ¬¬IF(ISBLANK('DPW3'!RO18),"",'DPW3'!RO18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF19),"",'DPW3'!EF19) | ¬¬IF(ISBLANK('DPW3'!EG19),"",'DPW3'!EG19) | ¬¬IF(ISBLANK('DPW3'!EH19),"",'DPW3'!EH19) | ¬¬IF(ISBLANK('DPW3'!EI19),"",'DPW3'!EI19) | ¬¬IF(ISBLANK('DPW3'!EJ19),"",'DPW3'!EJ19) | ¬¬IF(ISBLANK('DPW3'!EK19),"",'DPW3'!EK19) | ¬¬IF(ISBLANK('DPW3'!EL19),"",'DPW3'!EL19) | ¬¬IF(ISBLANK('DPW3'!EM19),"",'DPW3'!EM19) | ¬¬IF(ISBLANK('DPW3'!EN19),"",'DPW3'!EN19) | ¬¬IF(ISBLANK('DPW3'!EO19),"",'DPW3'!EO19) | ¬¬IF(ISBLANK('DPW3'!EP19),"",'DPW3'!EP19) | ¬¬IF(ISBLANK('DPW3'!EQ19),"",'DPW3'!EQ19) | ¬¬IF(ISBLANK('DPW3'!ER19),"",'DPW3'!ER19) | ¬¬IF(ISBLANK('DPW3'!ES19),"",'DPW3'!ES19) | ¬¬IF(ISBLANK('DPW3'!ET19),"",'DPW3'!ET19) | ¬¬IF(ISBLANK('DPW3'!EU19),"",'DPW3'!EU19) | ¬¬IF(ISBLANK('DPW3'!EV19),"",'DPW3'!EV19) | ¬¬IF(ISBLANK('DPW3'!EW19),"",'DPW3'!EW19) | ¬¬IF(ISBLANK('DPW3'!EX19),"",'DPW3'!EX19) | ¬¬IF(ISBLANK('DPW3'!EY19),"",'DPW3'!EY19) | ¬¬IF(ISBLANK('DPW3'!EZ19),"",'DPW3'!EZ19) | ¬¬IF(ISBLANK('DPW3'!FA19),"",'DPW3'!FA19) | ¬¬IF(ISBLANK('DPW3'!FB19),"",'DPW3'!FB19) | ¬¬IF(ISBLANK('DPW3'!FC19),"",'DPW3'!FC19) | ¬¬IF(ISBLANK('DPW3'!FD19),"",'DPW3'!FD19) | ¬¬IF(ISBLANK('DPW3'!FE19),"",'DPW3'!FE19) | ¬¬IF(ISBLANK('DPW3'!FF19),"",'DPW3'!FF19) | ¬¬IF(ISBLANK('DPW3'!FG19),"",'DPW3'!FG19) | ¬¬IF(ISBLANK('DPW3'!FH19),"",'DPW3'!FH19) | ¬¬IF(ISBLANK('DPW3'!FI19),"",'DPW3'!FI19) | ¬¬IF(ISBLANK('DPW3'!FJ19),"",'DPW3'!FJ19) | ¬¬IF(ISBLANK('DPW3'!FK19),"",'DPW3'!FK19) | ¬¬IF(ISBLANK('DPW3'!FL19),"",'DPW3'!FL19) | ¬¬IF(ISBLANK('DPW3'!FM19),"",'DPW3'!FM19) | ¬¬IF(ISBLANK('DPW3'!FN19),"",'DPW3'!FN19) | ¬¬IF(ISBLANK('DPW3'!FO19),"",'DPW3'!FO19) | ¬¬IF(ISBLANK('DPW3'!FP19),"",'DPW3'!FP19) | ¬¬IF(ISBLANK('DPW3'!FQ19),"",'DPW3'!FQ19) | ¬¬IF(ISBLANK('DPW3'!FR19),"",'DPW3'!FR19) | ¬¬IF(ISBLANK('DPW3'!FS19),"",'DPW3'!FS19)
¬¬A1559 | ¬¬IF(ISBLANK('DPW3'!TD18),"",'DPW3'!TD18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU19),"",'DPW3'!FU19) | ¬¬IF(ISBLANK('DPW3'!FV19),"",'DPW3'!FV19) | ¬¬IF(ISBLANK('DPW3'!FW19),"",'DPW3'!FW19) | ¬¬IF(ISBLANK('DPW3'!FX19),"",'DPW3'!FX19) | ¬¬IF(ISBLANK('DPW3'!FY19),"",'DPW3'!FY19) | ¬¬IF(ISBLANK('DPW3'!FZ19),"",'DPW3'!FZ19) | ¬¬IF(ISBLANK('DPW3'!GA19),"",'DPW3'!GA19) | ¬¬IF(ISBLANK('DPW3'!GB19),"",'DPW3'!GB19) | ¬¬IF(ISBLANK('DPW3'!GC19),"",'DPW3'!GC19) | ¬¬IF(ISBLANK('DPW3'!GD19),"",'DPW3'!GD19) | ¬¬IF(ISBLANK('DPW3'!GE19),"",'DPW3'!GE19) | ¬¬IF(ISBLANK('DPW3'!GF19),"",'DPW3'!GF19) | ¬¬IF(ISBLANK('DPW3'!GG19),"",'DPW3'!GG19) | ¬¬IF(ISBLANK('DPW3'!GH19),"",'DPW3'!GH19) | ¬¬IF(ISBLANK('DPW3'!GI19),"",'DPW3'!GI19) | ¬¬IF(ISBLANK('DPW3'!GJ19),"",'DPW3'!GJ19) | ¬¬IF(ISBLANK('DPW3'!GK19),"",'DPW3'!GK19) | ¬¬IF(ISBLANK('DPW3'!GL19),"",'DPW3'!GL19) | ¬¬IF(ISBLANK('DPW3'!GM19),"",'DPW3'!GM19) | ¬¬IF(ISBLANK('DPW3'!GN19),"",'DPW3'!GN19) | ¬¬IF(ISBLANK('DPW3'!GO19),"",'DPW3'!GO19) | ¬¬IF(ISBLANK('DPW3'!GP19),"",'DPW3'!GP19) | ¬¬IF(ISBLANK('DPW3'!GQ19),"",'DPW3'!GQ19) | ¬¬IF(ISBLANK('DPW3'!GR19),"",'DPW3'!GR19) | ¬¬IF(ISBLANK('DPW3'!GS19),"",'DPW3'!GS19) | ¬¬IF(ISBLANK('DPW3'!GT19),"",'DPW3'!GT19) | ¬¬IF(ISBLANK('DPW3'!GU19),"",'DPW3'!GU19) | ¬¬IF(ISBLANK('DPW3'!GV19),"",'DPW3'!GV19) | ¬¬IF(ISBLANK('DPW3'!GW19),"",'DPW3'!GW19) | ¬¬IF(ISBLANK('DPW3'!GX19),"",'DPW3'!GX19) | ¬¬IF(ISBLANK('DPW3'!GY19),"",'DPW3'!GY19) | ¬¬IF(ISBLANK('DPW3'!GZ19),"",'DPW3'!GZ19) | ¬¬IF(ISBLANK('DPW3'!HA19),"",'DPW3'!HA19) | ¬¬IF(ISBLANK('DPW3'!HB19),"",'DPW3'!HB19) | ¬¬IF(ISBLANK('DPW3'!HC19),"",'DPW3'!HC19) | ¬¬IF(ISBLANK('DPW3'!HD19),"",'DPW3'!HD19) | ¬¬IF(ISBLANK('DPW3'!HE19),"",'DPW3'!HE19) | ¬¬IF(ISBLANK('DPW3'!HF19),"",'DPW3'!HF19) | ¬¬IF(ISBLANK('DPW3'!HG19),"",'DPW3'!HG19) | ¬¬IF(ISBLANK('DPW3'!HH19),"",'DPW3'!HH19)
¬¬A1560 | ¬¬IF(ISBLANK('DPW3'!US18),"",'DPW3'!US18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ19),"",'DPW3'!HJ19) | ¬¬IF(ISBLANK('DPW3'!HK19),"",'DPW3'!HK19) | ¬¬IF(ISBLANK('DPW3'!HL19),"",'DPW3'!HL19) | ¬¬IF(ISBLANK('DPW3'!HM19),"",'DPW3'!HM19) | ¬¬IF(ISBLANK('DPW3'!HN19),"",'DPW3'!HN19) | ¬¬IF(ISBLANK('DPW3'!HO19),"",'DPW3'!HO19) | ¬¬IF(ISBLANK('DPW3'!HP19),"",'DPW3'!HP19) | ¬¬IF(ISBLANK('DPW3'!HQ19),"",'DPW3'!HQ19) | ¬¬IF(ISBLANK('DPW3'!HR19),"",'DPW3'!HR19) | ¬¬IF(ISBLANK('DPW3'!HS19),"",'DPW3'!HS19) | ¬¬IF(ISBLANK('DPW3'!HT19),"",'DPW3'!HT19) | ¬¬IF(ISBLANK('DPW3'!HU19),"",'DPW3'!HU19) | ¬¬IF(ISBLANK('DPW3'!HV19),"",'DPW3'!HV19) | ¬¬IF(ISBLANK('DPW3'!HW19),"",'DPW3'!HW19) | ¬¬IF(ISBLANK('DPW3'!HX19),"",'DPW3'!HX19) | ¬¬IF(ISBLANK('DPW3'!HY19),"",'DPW3'!HY19) | ¬¬IF(ISBLANK('DPW3'!HZ19),"",'DPW3'!HZ19) | ¬¬IF(ISBLANK('DPW3'!IA19),"",'DPW3'!IA19) | ¬¬IF(ISBLANK('DPW3'!IB19),"",'DPW3'!IB19) | ¬¬IF(ISBLANK('DPW3'!IC19),"",'DPW3'!IC19) | ¬¬IF(ISBLANK('DPW3'!ID19),"",'DPW3'!ID19) | ¬¬IF(ISBLANK('DPW3'!IE19),"",'DPW3'!IE19) | ¬¬IF(ISBLANK('DPW3'!IF19),"",'DPW3'!IF19) | ¬¬IF(ISBLANK('DPW3'!IG19),"",'DPW3'!IG19) | ¬¬IF(ISBLANK('DPW3'!IH19),"",'DPW3'!IH19) | ¬¬IF(ISBLANK('DPW3'!II19),"",'DPW3'!II19) | ¬¬IF(ISBLANK('DPW3'!IJ19),"",'DPW3'!IJ19) | ¬¬IF(ISBLANK('DPW3'!IK19),"",'DPW3'!IK19) | ¬¬IF(ISBLANK('DPW3'!IL19),"",'DPW3'!IL19) | ¬¬IF(ISBLANK('DPW3'!IM19),"",'DPW3'!IM19) | ¬¬IF(ISBLANK('DPW3'!IN19),"",'DPW3'!IN19) | ¬¬IF(ISBLANK('DPW3'!IO19),"",'DPW3'!IO19) | ¬¬IF(ISBLANK('DPW3'!IP19),"",'DPW3'!IP19) | ¬¬IF(ISBLANK('DPW3'!IQ19),"",'DPW3'!IQ19) | ¬¬IF(ISBLANK('DPW3'!IR19),"",'DPW3'!IR19) | ¬¬IF(ISBLANK('DPW3'!IS19),"",'DPW3'!IS19) | ¬¬IF(ISBLANK('DPW3'!IT19),"",'DPW3'!IT19) | ¬¬IF(ISBLANK('DPW3'!IU19),"",'DPW3'!IU19) | ¬¬IF(ISBLANK('DPW3'!IV19),"",'DPW3'!IV19) | ¬¬IF(ISBLANK('DPW3'!IW19),"",'DPW3'!IW19)
¬¬A1561 | ¬¬IF(ISBLANK('DPW3'!WH18),"",'DPW3'!WH18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY19),"",'DPW3'!IY19) | ¬¬IF(ISBLANK('DPW3'!IZ19),"",'DPW3'!IZ19) | ¬¬IF(ISBLANK('DPW3'!JA19),"",'DPW3'!JA19) | ¬¬IF(ISBLANK('DPW3'!JB19),"",'DPW3'!JB19) | ¬¬IF(ISBLANK('DPW3'!JC19),"",'DPW3'!JC19) | ¬¬IF(ISBLANK('DPW3'!JD19),"",'DPW3'!JD19) | ¬¬IF(ISBLANK('DPW3'!JE19),"",'DPW3'!JE19) | ¬¬IF(ISBLANK('DPW3'!JF19),"",'DPW3'!JF19) | ¬¬IF(ISBLANK('DPW3'!JG19),"",'DPW3'!JG19) | ¬¬IF(ISBLANK('DPW3'!JH19),"",'DPW3'!JH19) | ¬¬IF(ISBLANK('DPW3'!JI19),"",'DPW3'!JI19) | ¬¬IF(ISBLANK('DPW3'!JJ19),"",'DPW3'!JJ19) | ¬¬IF(ISBLANK('DPW3'!JK19),"",'DPW3'!JK19) | ¬¬IF(ISBLANK('DPW3'!JL19),"",'DPW3'!JL19) | ¬¬IF(ISBLANK('DPW3'!JM19),"",'DPW3'!JM19) | ¬¬IF(ISBLANK('DPW3'!JN19),"",'DPW3'!JN19) | ¬¬IF(ISBLANK('DPW3'!JO19),"",'DPW3'!JO19) | ¬¬IF(ISBLANK('DPW3'!JP19),"",'DPW3'!JP19) | ¬¬IF(ISBLANK('DPW3'!JQ19),"",'DPW3'!JQ19) | ¬¬IF(ISBLANK('DPW3'!JR19),"",'DPW3'!JR19) | ¬¬IF(ISBLANK('DPW3'!JS19),"",'DPW3'!JS19) | ¬¬IF(ISBLANK('DPW3'!JT19),"",'DPW3'!JT19) | ¬¬IF(ISBLANK('DPW3'!JU19),"",'DPW3'!JU19) | ¬¬IF(ISBLANK('DPW3'!JV19),"",'DPW3'!JV19) | ¬¬IF(ISBLANK('DPW3'!JW19),"",'DPW3'!JW19) | ¬¬IF(ISBLANK('DPW3'!JX19),"",'DPW3'!JX19) | ¬¬IF(ISBLANK('DPW3'!JY19),"",'DPW3'!JY19) | ¬¬IF(ISBLANK('DPW3'!JZ19),"",'DPW3'!JZ19) | ¬¬IF(ISBLANK('DPW3'!KA19),"",'DPW3'!KA19) | ¬¬IF(ISBLANK('DPW3'!KB19),"",'DPW3'!KB19) | ¬¬IF(ISBLANK('DPW3'!KC19),"",'DPW3'!KC19) | ¬¬IF(ISBLANK('DPW3'!KD19),"",'DPW3'!KD19) | ¬¬IF(ISBLANK('DPW3'!KE19),"",'DPW3'!KE19) | ¬¬IF(ISBLANK('DPW3'!KF19),"",'DPW3'!KF19) | ¬¬IF(ISBLANK('DPW3'!KG19),"",'DPW3'!KG19) | ¬¬IF(ISBLANK('DPW3'!KH19),"",'DPW3'!KH19) | ¬¬IF(ISBLANK('DPW3'!KI19),"",'DPW3'!KI19) | ¬¬IF(ISBLANK('DPW3'!KJ19),"",'DPW3'!KJ19) | ¬¬IF(ISBLANK('DPW3'!KK19),"",'DPW3'!KK19) | ¬¬IF(ISBLANK('DPW3'!KL19),"",'DPW3'!KL19)
¬¬A1562 | ¬¬IF(ISBLANK('DPW3'!XW18),"",'DPW3'!XW18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN19),"",'DPW3'!KN19) | ¬¬IF(ISBLANK('DPW3'!KO19),"",'DPW3'!KO19) | ¬¬IF(ISBLANK('DPW3'!KP19),"",'DPW3'!KP19) | ¬¬IF(ISBLANK('DPW3'!KQ19),"",'DPW3'!KQ19) | ¬¬IF(ISBLANK('DPW3'!KR19),"",'DPW3'!KR19) | ¬¬IF(ISBLANK('DPW3'!KS19),"",'DPW3'!KS19) | ¬¬IF(ISBLANK('DPW3'!KT19),"",'DPW3'!KT19) | ¬¬IF(ISBLANK('DPW3'!KU19),"",'DPW3'!KU19) | ¬¬IF(ISBLANK('DPW3'!KV19),"",'DPW3'!KV19) | ¬¬IF(ISBLANK('DPW3'!KW19),"",'DPW3'!KW19) | ¬¬IF(ISBLANK('DPW3'!KX19),"",'DPW3'!KX19) | ¬¬IF(ISBLANK('DPW3'!KY19),"",'DPW3'!KY19) | ¬¬IF(ISBLANK('DPW3'!KZ19),"",'DPW3'!KZ19) | ¬¬IF(ISBLANK('DPW3'!LA19),"",'DPW3'!LA19) | ¬¬IF(ISBLANK('DPW3'!LB19),"",'DPW3'!LB19) | ¬¬IF(ISBLANK('DPW3'!LC19),"",'DPW3'!LC19) | ¬¬IF(ISBLANK('DPW3'!LD19),"",'DPW3'!LD19) | ¬¬IF(ISBLANK('DPW3'!LE19),"",'DPW3'!LE19) | ¬¬IF(ISBLANK('DPW3'!LF19),"",'DPW3'!LF19) | ¬¬IF(ISBLANK('DPW3'!LG19),"",'DPW3'!LG19) | ¬¬IF(ISBLANK('DPW3'!LH19),"",'DPW3'!LH19) | ¬¬IF(ISBLANK('DPW3'!LI19),"",'DPW3'!LI19) | ¬¬IF(ISBLANK('DPW3'!LJ19),"",'DPW3'!LJ19) | ¬¬IF(ISBLANK('DPW3'!LK19),"",'DPW3'!LK19) | ¬¬IF(ISBLANK('DPW3'!LL19),"",'DPW3'!LL19) | ¬¬IF(ISBLANK('DPW3'!LM19),"",'DPW3'!LM19) | ¬¬IF(ISBLANK('DPW3'!LN19),"",'DPW3'!LN19) | ¬¬IF(ISBLANK('DPW3'!LO19),"",'DPW3'!LO19) | ¬¬IF(ISBLANK('DPW3'!LP19),"",'DPW3'!LP19) | ¬¬IF(ISBLANK('DPW3'!LQ19),"",'DPW3'!LQ19) | ¬¬IF(ISBLANK('DPW3'!LR19),"",'DPW3'!LR19) | ¬¬IF(ISBLANK('DPW3'!LS19),"",'DPW3'!LS19) | ¬¬IF(ISBLANK('DPW3'!LT19),"",'DPW3'!LT19) | ¬¬IF(ISBLANK('DPW3'!LU19),"",'DPW3'!LU19) | ¬¬IF(ISBLANK('DPW3'!LV19),"",'DPW3'!LV19) | ¬¬IF(ISBLANK('DPW3'!LW19),"",'DPW3'!LW19) | ¬¬IF(ISBLANK('DPW3'!LX19),"",'DPW3'!LX19) | ¬¬IF(ISBLANK('DPW3'!LY19),"",'DPW3'!LY19) | ¬¬IF(ISBLANK('DPW3'!LZ19),"",'DPW3'!LZ19) | ¬¬IF(ISBLANK('DPW3'!MA19),"",'DPW3'!MA19)
¬¬A1563 | ¬¬IF(ISBLANK('DPW3'!ZL18),"",'DPW3'!ZL18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MC19),"",'DPW3'!MC19)
¬¬A1564 | ¬¬IF(ISBLANK('DPW3'!ZM18),"",'DPW3'!ZM18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MD19),"",'DPW3'!MD19)
¬¬A1565 | ¬¬IF(ISBLANK('DPW3'!ZN18),"",'DPW3'!ZN18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!ML19),"",'DPW3'!ML19)
¬¬A1566 | ¬¬IF(ISBLANK('DPW3'!ZO18),"",'DPW3'!ZO18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MF19),"",'DPW3'!MF19)
¬¬A1567 | ¬¬IF(ISBLANK('DPW3'!ZP18),"",'DPW3'!ZP18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MG19),"",'DPW3'!MG19)
¬¬A1568 | ¬¬IF(ISBLANK('DPW3'!ZQ18),"",'DPW3'!ZQ18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MH19),"",'DPW3'!MH19)
¬¬A1569 | ¬¬IF(ISBLANK('DPW3'!ZR18),"",'DPW3'!ZR18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MI19),"",'DPW3'!MI19)
¬¬A1570 | ¬¬IF(ISBLANK('DPW3'!ZS18),"",'DPW3'!ZS18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ19),"",'DPW3'!MJ19)
¬¬A1571 | ¬¬IF(ISBLANK('DPW3'!ZT18),"",'DPW3'!ZT18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MK19),"",'DPW3'!MK19)
¬¬A1572 | ¬¬IF(ISBLANK('DPW3'!ZV18),"",'DPW3'!ZV18) | ¬¬'DPW3'!F18 & "," & 'DPW3'!G18 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H18),"",'DPW3'!H18) | Delta | ¬¬IF(ISBLANK('DPW3'!MM19),"",'DPW3'!MM19)
¬¬A1573 | ¬¬IF(ISBLANK('DPW3'!MT20),"",'DPW3'!MT20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!K20),"",'DPW3'!K20)
¬¬A1574 | ¬¬IF(ISBLANK('DPW3'!MV20),"",'DPW3'!MV20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M20),"",'DPW3'!M20) | ¬¬IF(ISBLANK('DPW3'!N20),"",'DPW3'!N20) | ¬¬IF(ISBLANK('DPW3'!O20),"",'DPW3'!O20) | ¬¬IF(ISBLANK('DPW3'!P20),"",'DPW3'!P20) | ¬¬IF(ISBLANK('DPW3'!Q20),"",'DPW3'!Q20) | ¬¬IF(ISBLANK('DPW3'!R20),"",'DPW3'!R20) | ¬¬IF(ISBLANK('DPW3'!S20),"",'DPW3'!S20) | ¬¬IF(ISBLANK('DPW3'!T20),"",'DPW3'!T20) | ¬¬IF(ISBLANK('DPW3'!U20),"",'DPW3'!U20) | ¬¬IF(ISBLANK('DPW3'!V20),"",'DPW3'!V20) | ¬¬IF(ISBLANK('DPW3'!W20),"",'DPW3'!W20) | ¬¬IF(ISBLANK('DPW3'!X20),"",'DPW3'!X20) | ¬¬IF(ISBLANK('DPW3'!Y20),"",'DPW3'!Y20) | ¬¬IF(ISBLANK('DPW3'!Z20),"",'DPW3'!Z20) | ¬¬IF(ISBLANK('DPW3'!AA20),"",'DPW3'!AA20) | ¬¬IF(ISBLANK('DPW3'!AB20),"",'DPW3'!AB20) | ¬¬IF(ISBLANK('DPW3'!AC20),"",'DPW3'!AC20) | ¬¬IF(ISBLANK('DPW3'!AD20),"",'DPW3'!AD20) | ¬¬IF(ISBLANK('DPW3'!AE20),"",'DPW3'!AE20) | ¬¬IF(ISBLANK('DPW3'!AF20),"",'DPW3'!AF20) | ¬¬IF(ISBLANK('DPW3'!AG20),"",'DPW3'!AG20) | ¬¬IF(ISBLANK('DPW3'!AH20),"",'DPW3'!AH20) | ¬¬IF(ISBLANK('DPW3'!AI20),"",'DPW3'!AI20) | ¬¬IF(ISBLANK('DPW3'!AJ20),"",'DPW3'!AJ20) | ¬¬IF(ISBLANK('DPW3'!AK20),"",'DPW3'!AK20) | ¬¬IF(ISBLANK('DPW3'!AL20),"",'DPW3'!AL20) | ¬¬IF(ISBLANK('DPW3'!AM20),"",'DPW3'!AM20) | ¬¬IF(ISBLANK('DPW3'!AN20),"",'DPW3'!AN20) | ¬¬IF(ISBLANK('DPW3'!AO20),"",'DPW3'!AO20) | ¬¬IF(ISBLANK('DPW3'!AP20),"",'DPW3'!AP20) | ¬¬IF(ISBLANK('DPW3'!AQ20),"",'DPW3'!AQ20) | ¬¬IF(ISBLANK('DPW3'!AR20),"",'DPW3'!AR20) | ¬¬IF(ISBLANK('DPW3'!AS20),"",'DPW3'!AS20) | ¬¬IF(ISBLANK('DPW3'!AT20),"",'DPW3'!AT20) | ¬¬IF(ISBLANK('DPW3'!AU20),"",'DPW3'!AU20) | ¬¬IF(ISBLANK('DPW3'!AV20),"",'DPW3'!AV20) | ¬¬IF(ISBLANK('DPW3'!AW20),"",'DPW3'!AW20) | ¬¬IF(ISBLANK('DPW3'!AX20),"",'DPW3'!AX20) | ¬¬IF(ISBLANK('DPW3'!AY20),"",'DPW3'!AY20) | ¬¬IF(ISBLANK('DPW3'!AZ20),"",'DPW3'!AZ20)
¬¬A1575 | ¬¬IF(ISBLANK('DPW3'!OK20),"",'DPW3'!OK20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB20),"",'DPW3'!BB20) | ¬¬IF(ISBLANK('DPW3'!BC20),"",'DPW3'!BC20) | ¬¬IF(ISBLANK('DPW3'!BD20),"",'DPW3'!BD20) | ¬¬IF(ISBLANK('DPW3'!BE20),"",'DPW3'!BE20) | ¬¬IF(ISBLANK('DPW3'!BF20),"",'DPW3'!BF20) | ¬¬IF(ISBLANK('DPW3'!BG20),"",'DPW3'!BG20) | ¬¬IF(ISBLANK('DPW3'!BH20),"",'DPW3'!BH20) | ¬¬IF(ISBLANK('DPW3'!BI20),"",'DPW3'!BI20) | ¬¬IF(ISBLANK('DPW3'!BJ20),"",'DPW3'!BJ20) | ¬¬IF(ISBLANK('DPW3'!BK20),"",'DPW3'!BK20) | ¬¬IF(ISBLANK('DPW3'!BL20),"",'DPW3'!BL20) | ¬¬IF(ISBLANK('DPW3'!BM20),"",'DPW3'!BM20) | ¬¬IF(ISBLANK('DPW3'!BN20),"",'DPW3'!BN20) | ¬¬IF(ISBLANK('DPW3'!BO20),"",'DPW3'!BO20) | ¬¬IF(ISBLANK('DPW3'!BP20),"",'DPW3'!BP20) | ¬¬IF(ISBLANK('DPW3'!BQ20),"",'DPW3'!BQ20) | ¬¬IF(ISBLANK('DPW3'!BR20),"",'DPW3'!BR20) | ¬¬IF(ISBLANK('DPW3'!BS20),"",'DPW3'!BS20) | ¬¬IF(ISBLANK('DPW3'!BT20),"",'DPW3'!BT20) | ¬¬IF(ISBLANK('DPW3'!BU20),"",'DPW3'!BU20) | ¬¬IF(ISBLANK('DPW3'!BV20),"",'DPW3'!BV20) | ¬¬IF(ISBLANK('DPW3'!BW20),"",'DPW3'!BW20) | ¬¬IF(ISBLANK('DPW3'!BX20),"",'DPW3'!BX20) | ¬¬IF(ISBLANK('DPW3'!BY20),"",'DPW3'!BY20) | ¬¬IF(ISBLANK('DPW3'!BZ20),"",'DPW3'!BZ20) | ¬¬IF(ISBLANK('DPW3'!CA20),"",'DPW3'!CA20) | ¬¬IF(ISBLANK('DPW3'!CB20),"",'DPW3'!CB20) | ¬¬IF(ISBLANK('DPW3'!CC20),"",'DPW3'!CC20) | ¬¬IF(ISBLANK('DPW3'!CD20),"",'DPW3'!CD20) | ¬¬IF(ISBLANK('DPW3'!CE20),"",'DPW3'!CE20) | ¬¬IF(ISBLANK('DPW3'!CF20),"",'DPW3'!CF20) | ¬¬IF(ISBLANK('DPW3'!CG20),"",'DPW3'!CG20) | ¬¬IF(ISBLANK('DPW3'!CH20),"",'DPW3'!CH20) | ¬¬IF(ISBLANK('DPW3'!CI20),"",'DPW3'!CI20) | ¬¬IF(ISBLANK('DPW3'!CJ20),"",'DPW3'!CJ20) | ¬¬IF(ISBLANK('DPW3'!CK20),"",'DPW3'!CK20) | ¬¬IF(ISBLANK('DPW3'!CL20),"",'DPW3'!CL20) | ¬¬IF(ISBLANK('DPW3'!CM20),"",'DPW3'!CM20) | ¬¬IF(ISBLANK('DPW3'!CN20),"",'DPW3'!CN20) | ¬¬IF(ISBLANK('DPW3'!CO20),"",'DPW3'!CO20)
¬¬A1576 | ¬¬IF(ISBLANK('DPW3'!PZ20),"",'DPW3'!PZ20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ20),"",'DPW3'!CQ20) | ¬¬IF(ISBLANK('DPW3'!CR20),"",'DPW3'!CR20) | ¬¬IF(ISBLANK('DPW3'!CS20),"",'DPW3'!CS20) | ¬¬IF(ISBLANK('DPW3'!CT20),"",'DPW3'!CT20) | ¬¬IF(ISBLANK('DPW3'!CU20),"",'DPW3'!CU20) | ¬¬IF(ISBLANK('DPW3'!CV20),"",'DPW3'!CV20) | ¬¬IF(ISBLANK('DPW3'!CW20),"",'DPW3'!CW20) | ¬¬IF(ISBLANK('DPW3'!CX20),"",'DPW3'!CX20) | ¬¬IF(ISBLANK('DPW3'!CY20),"",'DPW3'!CY20) | ¬¬IF(ISBLANK('DPW3'!CZ20),"",'DPW3'!CZ20) | ¬¬IF(ISBLANK('DPW3'!DA20),"",'DPW3'!DA20) | ¬¬IF(ISBLANK('DPW3'!DB20),"",'DPW3'!DB20) | ¬¬IF(ISBLANK('DPW3'!DC20),"",'DPW3'!DC20) | ¬¬IF(ISBLANK('DPW3'!DD20),"",'DPW3'!DD20) | ¬¬IF(ISBLANK('DPW3'!DE20),"",'DPW3'!DE20) | ¬¬IF(ISBLANK('DPW3'!DF20),"",'DPW3'!DF20) | ¬¬IF(ISBLANK('DPW3'!DG20),"",'DPW3'!DG20) | ¬¬IF(ISBLANK('DPW3'!DH20),"",'DPW3'!DH20) | ¬¬IF(ISBLANK('DPW3'!DI20),"",'DPW3'!DI20) | ¬¬IF(ISBLANK('DPW3'!DJ20),"",'DPW3'!DJ20) | ¬¬IF(ISBLANK('DPW3'!DK20),"",'DPW3'!DK20) | ¬¬IF(ISBLANK('DPW3'!DL20),"",'DPW3'!DL20) | ¬¬IF(ISBLANK('DPW3'!DM20),"",'DPW3'!DM20) | ¬¬IF(ISBLANK('DPW3'!DN20),"",'DPW3'!DN20) | ¬¬IF(ISBLANK('DPW3'!DO20),"",'DPW3'!DO20) | ¬¬IF(ISBLANK('DPW3'!DP20),"",'DPW3'!DP20) | ¬¬IF(ISBLANK('DPW3'!DQ20),"",'DPW3'!DQ20) | ¬¬IF(ISBLANK('DPW3'!DR20),"",'DPW3'!DR20) | ¬¬IF(ISBLANK('DPW3'!DS20),"",'DPW3'!DS20) | ¬¬IF(ISBLANK('DPW3'!DT20),"",'DPW3'!DT20) | ¬¬IF(ISBLANK('DPW3'!DU20),"",'DPW3'!DU20) | ¬¬IF(ISBLANK('DPW3'!DV20),"",'DPW3'!DV20) | ¬¬IF(ISBLANK('DPW3'!DW20),"",'DPW3'!DW20) | ¬¬IF(ISBLANK('DPW3'!DX20),"",'DPW3'!DX20) | ¬¬IF(ISBLANK('DPW3'!DY20),"",'DPW3'!DY20) | ¬¬IF(ISBLANK('DPW3'!DZ20),"",'DPW3'!DZ20) | ¬¬IF(ISBLANK('DPW3'!EA20),"",'DPW3'!EA20) | ¬¬IF(ISBLANK('DPW3'!EB20),"",'DPW3'!EB20) | ¬¬IF(ISBLANK('DPW3'!EC20),"",'DPW3'!EC20) | ¬¬IF(ISBLANK('DPW3'!ED20),"",'DPW3'!ED20)
¬¬A1577 | ¬¬IF(ISBLANK('DPW3'!RO20),"",'DPW3'!RO20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF20),"",'DPW3'!EF20) | ¬¬IF(ISBLANK('DPW3'!EG20),"",'DPW3'!EG20) | ¬¬IF(ISBLANK('DPW3'!EH20),"",'DPW3'!EH20) | ¬¬IF(ISBLANK('DPW3'!EI20),"",'DPW3'!EI20) | ¬¬IF(ISBLANK('DPW3'!EJ20),"",'DPW3'!EJ20) | ¬¬IF(ISBLANK('DPW3'!EK20),"",'DPW3'!EK20) | ¬¬IF(ISBLANK('DPW3'!EL20),"",'DPW3'!EL20) | ¬¬IF(ISBLANK('DPW3'!EM20),"",'DPW3'!EM20) | ¬¬IF(ISBLANK('DPW3'!EN20),"",'DPW3'!EN20) | ¬¬IF(ISBLANK('DPW3'!EO20),"",'DPW3'!EO20) | ¬¬IF(ISBLANK('DPW3'!EP20),"",'DPW3'!EP20) | ¬¬IF(ISBLANK('DPW3'!EQ20),"",'DPW3'!EQ20) | ¬¬IF(ISBLANK('DPW3'!ER20),"",'DPW3'!ER20) | ¬¬IF(ISBLANK('DPW3'!ES20),"",'DPW3'!ES20) | ¬¬IF(ISBLANK('DPW3'!ET20),"",'DPW3'!ET20) | ¬¬IF(ISBLANK('DPW3'!EU20),"",'DPW3'!EU20) | ¬¬IF(ISBLANK('DPW3'!EV20),"",'DPW3'!EV20) | ¬¬IF(ISBLANK('DPW3'!EW20),"",'DPW3'!EW20) | ¬¬IF(ISBLANK('DPW3'!EX20),"",'DPW3'!EX20) | ¬¬IF(ISBLANK('DPW3'!EY20),"",'DPW3'!EY20) | ¬¬IF(ISBLANK('DPW3'!EZ20),"",'DPW3'!EZ20) | ¬¬IF(ISBLANK('DPW3'!FA20),"",'DPW3'!FA20) | ¬¬IF(ISBLANK('DPW3'!FB20),"",'DPW3'!FB20) | ¬¬IF(ISBLANK('DPW3'!FC20),"",'DPW3'!FC20) | ¬¬IF(ISBLANK('DPW3'!FD20),"",'DPW3'!FD20) | ¬¬IF(ISBLANK('DPW3'!FE20),"",'DPW3'!FE20) | ¬¬IF(ISBLANK('DPW3'!FF20),"",'DPW3'!FF20) | ¬¬IF(ISBLANK('DPW3'!FG20),"",'DPW3'!FG20) | ¬¬IF(ISBLANK('DPW3'!FH20),"",'DPW3'!FH20) | ¬¬IF(ISBLANK('DPW3'!FI20),"",'DPW3'!FI20) | ¬¬IF(ISBLANK('DPW3'!FJ20),"",'DPW3'!FJ20) | ¬¬IF(ISBLANK('DPW3'!FK20),"",'DPW3'!FK20) | ¬¬IF(ISBLANK('DPW3'!FL20),"",'DPW3'!FL20) | ¬¬IF(ISBLANK('DPW3'!FM20),"",'DPW3'!FM20) | ¬¬IF(ISBLANK('DPW3'!FN20),"",'DPW3'!FN20) | ¬¬IF(ISBLANK('DPW3'!FO20),"",'DPW3'!FO20) | ¬¬IF(ISBLANK('DPW3'!FP20),"",'DPW3'!FP20) | ¬¬IF(ISBLANK('DPW3'!FQ20),"",'DPW3'!FQ20) | ¬¬IF(ISBLANK('DPW3'!FR20),"",'DPW3'!FR20) | ¬¬IF(ISBLANK('DPW3'!FS20),"",'DPW3'!FS20)
¬¬A1578 | ¬¬IF(ISBLANK('DPW3'!TD20),"",'DPW3'!TD20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU20),"",'DPW3'!FU20) | ¬¬IF(ISBLANK('DPW3'!FV20),"",'DPW3'!FV20) | ¬¬IF(ISBLANK('DPW3'!FW20),"",'DPW3'!FW20) | ¬¬IF(ISBLANK('DPW3'!FX20),"",'DPW3'!FX20) | ¬¬IF(ISBLANK('DPW3'!FY20),"",'DPW3'!FY20) | ¬¬IF(ISBLANK('DPW3'!FZ20),"",'DPW3'!FZ20) | ¬¬IF(ISBLANK('DPW3'!GA20),"",'DPW3'!GA20) | ¬¬IF(ISBLANK('DPW3'!GB20),"",'DPW3'!GB20) | ¬¬IF(ISBLANK('DPW3'!GC20),"",'DPW3'!GC20) | ¬¬IF(ISBLANK('DPW3'!GD20),"",'DPW3'!GD20) | ¬¬IF(ISBLANK('DPW3'!GE20),"",'DPW3'!GE20) | ¬¬IF(ISBLANK('DPW3'!GF20),"",'DPW3'!GF20) | ¬¬IF(ISBLANK('DPW3'!GG20),"",'DPW3'!GG20) | ¬¬IF(ISBLANK('DPW3'!GH20),"",'DPW3'!GH20) | ¬¬IF(ISBLANK('DPW3'!GI20),"",'DPW3'!GI20) | ¬¬IF(ISBLANK('DPW3'!GJ20),"",'DPW3'!GJ20) | ¬¬IF(ISBLANK('DPW3'!GK20),"",'DPW3'!GK20) | ¬¬IF(ISBLANK('DPW3'!GL20),"",'DPW3'!GL20) | ¬¬IF(ISBLANK('DPW3'!GM20),"",'DPW3'!GM20) | ¬¬IF(ISBLANK('DPW3'!GN20),"",'DPW3'!GN20) | ¬¬IF(ISBLANK('DPW3'!GO20),"",'DPW3'!GO20) | ¬¬IF(ISBLANK('DPW3'!GP20),"",'DPW3'!GP20) | ¬¬IF(ISBLANK('DPW3'!GQ20),"",'DPW3'!GQ20) | ¬¬IF(ISBLANK('DPW3'!GR20),"",'DPW3'!GR20) | ¬¬IF(ISBLANK('DPW3'!GS20),"",'DPW3'!GS20) | ¬¬IF(ISBLANK('DPW3'!GT20),"",'DPW3'!GT20) | ¬¬IF(ISBLANK('DPW3'!GU20),"",'DPW3'!GU20) | ¬¬IF(ISBLANK('DPW3'!GV20),"",'DPW3'!GV20) | ¬¬IF(ISBLANK('DPW3'!GW20),"",'DPW3'!GW20) | ¬¬IF(ISBLANK('DPW3'!GX20),"",'DPW3'!GX20) | ¬¬IF(ISBLANK('DPW3'!GY20),"",'DPW3'!GY20) | ¬¬IF(ISBLANK('DPW3'!GZ20),"",'DPW3'!GZ20) | ¬¬IF(ISBLANK('DPW3'!HA20),"",'DPW3'!HA20) | ¬¬IF(ISBLANK('DPW3'!HB20),"",'DPW3'!HB20) | ¬¬IF(ISBLANK('DPW3'!HC20),"",'DPW3'!HC20) | ¬¬IF(ISBLANK('DPW3'!HD20),"",'DPW3'!HD20) | ¬¬IF(ISBLANK('DPW3'!HE20),"",'DPW3'!HE20) | ¬¬IF(ISBLANK('DPW3'!HF20),"",'DPW3'!HF20) | ¬¬IF(ISBLANK('DPW3'!HG20),"",'DPW3'!HG20) | ¬¬IF(ISBLANK('DPW3'!HH20),"",'DPW3'!HH20)
¬¬A1579 | ¬¬IF(ISBLANK('DPW3'!US20),"",'DPW3'!US20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ20),"",'DPW3'!HJ20) | ¬¬IF(ISBLANK('DPW3'!HK20),"",'DPW3'!HK20) | ¬¬IF(ISBLANK('DPW3'!HL20),"",'DPW3'!HL20) | ¬¬IF(ISBLANK('DPW3'!HM20),"",'DPW3'!HM20) | ¬¬IF(ISBLANK('DPW3'!HN20),"",'DPW3'!HN20) | ¬¬IF(ISBLANK('DPW3'!HO20),"",'DPW3'!HO20) | ¬¬IF(ISBLANK('DPW3'!HP20),"",'DPW3'!HP20) | ¬¬IF(ISBLANK('DPW3'!HQ20),"",'DPW3'!HQ20) | ¬¬IF(ISBLANK('DPW3'!HR20),"",'DPW3'!HR20) | ¬¬IF(ISBLANK('DPW3'!HS20),"",'DPW3'!HS20) | ¬¬IF(ISBLANK('DPW3'!HT20),"",'DPW3'!HT20) | ¬¬IF(ISBLANK('DPW3'!HU20),"",'DPW3'!HU20) | ¬¬IF(ISBLANK('DPW3'!HV20),"",'DPW3'!HV20) | ¬¬IF(ISBLANK('DPW3'!HW20),"",'DPW3'!HW20) | ¬¬IF(ISBLANK('DPW3'!HX20),"",'DPW3'!HX20) | ¬¬IF(ISBLANK('DPW3'!HY20),"",'DPW3'!HY20) | ¬¬IF(ISBLANK('DPW3'!HZ20),"",'DPW3'!HZ20) | ¬¬IF(ISBLANK('DPW3'!IA20),"",'DPW3'!IA20) | ¬¬IF(ISBLANK('DPW3'!IB20),"",'DPW3'!IB20) | ¬¬IF(ISBLANK('DPW3'!IC20),"",'DPW3'!IC20) | ¬¬IF(ISBLANK('DPW3'!ID20),"",'DPW3'!ID20) | ¬¬IF(ISBLANK('DPW3'!IE20),"",'DPW3'!IE20) | ¬¬IF(ISBLANK('DPW3'!IF20),"",'DPW3'!IF20) | ¬¬IF(ISBLANK('DPW3'!IG20),"",'DPW3'!IG20) | ¬¬IF(ISBLANK('DPW3'!IH20),"",'DPW3'!IH20) | ¬¬IF(ISBLANK('DPW3'!II20),"",'DPW3'!II20) | ¬¬IF(ISBLANK('DPW3'!IJ20),"",'DPW3'!IJ20) | ¬¬IF(ISBLANK('DPW3'!IK20),"",'DPW3'!IK20) | ¬¬IF(ISBLANK('DPW3'!IL20),"",'DPW3'!IL20) | ¬¬IF(ISBLANK('DPW3'!IM20),"",'DPW3'!IM20) | ¬¬IF(ISBLANK('DPW3'!IN20),"",'DPW3'!IN20) | ¬¬IF(ISBLANK('DPW3'!IO20),"",'DPW3'!IO20) | ¬¬IF(ISBLANK('DPW3'!IP20),"",'DPW3'!IP20) | ¬¬IF(ISBLANK('DPW3'!IQ20),"",'DPW3'!IQ20) | ¬¬IF(ISBLANK('DPW3'!IR20),"",'DPW3'!IR20) | ¬¬IF(ISBLANK('DPW3'!IS20),"",'DPW3'!IS20) | ¬¬IF(ISBLANK('DPW3'!IT20),"",'DPW3'!IT20) | ¬¬IF(ISBLANK('DPW3'!IU20),"",'DPW3'!IU20) | ¬¬IF(ISBLANK('DPW3'!IV20),"",'DPW3'!IV20) | ¬¬IF(ISBLANK('DPW3'!IW20),"",'DPW3'!IW20)
¬¬A1580 | ¬¬IF(ISBLANK('DPW3'!WH20),"",'DPW3'!WH20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY20),"",'DPW3'!IY20) | ¬¬IF(ISBLANK('DPW3'!IZ20),"",'DPW3'!IZ20) | ¬¬IF(ISBLANK('DPW3'!JA20),"",'DPW3'!JA20) | ¬¬IF(ISBLANK('DPW3'!JB20),"",'DPW3'!JB20) | ¬¬IF(ISBLANK('DPW3'!JC20),"",'DPW3'!JC20) | ¬¬IF(ISBLANK('DPW3'!JD20),"",'DPW3'!JD20) | ¬¬IF(ISBLANK('DPW3'!JE20),"",'DPW3'!JE20) | ¬¬IF(ISBLANK('DPW3'!JF20),"",'DPW3'!JF20) | ¬¬IF(ISBLANK('DPW3'!JG20),"",'DPW3'!JG20) | ¬¬IF(ISBLANK('DPW3'!JH20),"",'DPW3'!JH20) | ¬¬IF(ISBLANK('DPW3'!JI20),"",'DPW3'!JI20) | ¬¬IF(ISBLANK('DPW3'!JJ20),"",'DPW3'!JJ20) | ¬¬IF(ISBLANK('DPW3'!JK20),"",'DPW3'!JK20) | ¬¬IF(ISBLANK('DPW3'!JL20),"",'DPW3'!JL20) | ¬¬IF(ISBLANK('DPW3'!JM20),"",'DPW3'!JM20) | ¬¬IF(ISBLANK('DPW3'!JN20),"",'DPW3'!JN20) | ¬¬IF(ISBLANK('DPW3'!JO20),"",'DPW3'!JO20) | ¬¬IF(ISBLANK('DPW3'!JP20),"",'DPW3'!JP20) | ¬¬IF(ISBLANK('DPW3'!JQ20),"",'DPW3'!JQ20) | ¬¬IF(ISBLANK('DPW3'!JR20),"",'DPW3'!JR20) | ¬¬IF(ISBLANK('DPW3'!JS20),"",'DPW3'!JS20) | ¬¬IF(ISBLANK('DPW3'!JT20),"",'DPW3'!JT20) | ¬¬IF(ISBLANK('DPW3'!JU20),"",'DPW3'!JU20) | ¬¬IF(ISBLANK('DPW3'!JV20),"",'DPW3'!JV20) | ¬¬IF(ISBLANK('DPW3'!JW20),"",'DPW3'!JW20) | ¬¬IF(ISBLANK('DPW3'!JX20),"",'DPW3'!JX20) | ¬¬IF(ISBLANK('DPW3'!JY20),"",'DPW3'!JY20) | ¬¬IF(ISBLANK('DPW3'!JZ20),"",'DPW3'!JZ20) | ¬¬IF(ISBLANK('DPW3'!KA20),"",'DPW3'!KA20) | ¬¬IF(ISBLANK('DPW3'!KB20),"",'DPW3'!KB20) | ¬¬IF(ISBLANK('DPW3'!KC20),"",'DPW3'!KC20) | ¬¬IF(ISBLANK('DPW3'!KD20),"",'DPW3'!KD20) | ¬¬IF(ISBLANK('DPW3'!KE20),"",'DPW3'!KE20) | ¬¬IF(ISBLANK('DPW3'!KF20),"",'DPW3'!KF20) | ¬¬IF(ISBLANK('DPW3'!KG20),"",'DPW3'!KG20) | ¬¬IF(ISBLANK('DPW3'!KH20),"",'DPW3'!KH20) | ¬¬IF(ISBLANK('DPW3'!KI20),"",'DPW3'!KI20) | ¬¬IF(ISBLANK('DPW3'!KJ20),"",'DPW3'!KJ20) | ¬¬IF(ISBLANK('DPW3'!KK20),"",'DPW3'!KK20) | ¬¬IF(ISBLANK('DPW3'!KL20),"",'DPW3'!KL20)
¬¬A1581 | ¬¬IF(ISBLANK('DPW3'!XW20),"",'DPW3'!XW20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN20),"",'DPW3'!KN20) | ¬¬IF(ISBLANK('DPW3'!KO20),"",'DPW3'!KO20) | ¬¬IF(ISBLANK('DPW3'!KP20),"",'DPW3'!KP20) | ¬¬IF(ISBLANK('DPW3'!KQ20),"",'DPW3'!KQ20) | ¬¬IF(ISBLANK('DPW3'!KR20),"",'DPW3'!KR20) | ¬¬IF(ISBLANK('DPW3'!KS20),"",'DPW3'!KS20) | ¬¬IF(ISBLANK('DPW3'!KT20),"",'DPW3'!KT20) | ¬¬IF(ISBLANK('DPW3'!KU20),"",'DPW3'!KU20) | ¬¬IF(ISBLANK('DPW3'!KV20),"",'DPW3'!KV20) | ¬¬IF(ISBLANK('DPW3'!KW20),"",'DPW3'!KW20) | ¬¬IF(ISBLANK('DPW3'!KX20),"",'DPW3'!KX20) | ¬¬IF(ISBLANK('DPW3'!KY20),"",'DPW3'!KY20) | ¬¬IF(ISBLANK('DPW3'!KZ20),"",'DPW3'!KZ20) | ¬¬IF(ISBLANK('DPW3'!LA20),"",'DPW3'!LA20) | ¬¬IF(ISBLANK('DPW3'!LB20),"",'DPW3'!LB20) | ¬¬IF(ISBLANK('DPW3'!LC20),"",'DPW3'!LC20) | ¬¬IF(ISBLANK('DPW3'!LD20),"",'DPW3'!LD20) | ¬¬IF(ISBLANK('DPW3'!LE20),"",'DPW3'!LE20) | ¬¬IF(ISBLANK('DPW3'!LF20),"",'DPW3'!LF20) | ¬¬IF(ISBLANK('DPW3'!LG20),"",'DPW3'!LG20) | ¬¬IF(ISBLANK('DPW3'!LH20),"",'DPW3'!LH20) | ¬¬IF(ISBLANK('DPW3'!LI20),"",'DPW3'!LI20) | ¬¬IF(ISBLANK('DPW3'!LJ20),"",'DPW3'!LJ20) | ¬¬IF(ISBLANK('DPW3'!LK20),"",'DPW3'!LK20) | ¬¬IF(ISBLANK('DPW3'!LL20),"",'DPW3'!LL20) | ¬¬IF(ISBLANK('DPW3'!LM20),"",'DPW3'!LM20) | ¬¬IF(ISBLANK('DPW3'!LN20),"",'DPW3'!LN20) | ¬¬IF(ISBLANK('DPW3'!LO20),"",'DPW3'!LO20) | ¬¬IF(ISBLANK('DPW3'!LP20),"",'DPW3'!LP20) | ¬¬IF(ISBLANK('DPW3'!LQ20),"",'DPW3'!LQ20) | ¬¬IF(ISBLANK('DPW3'!LR20),"",'DPW3'!LR20) | ¬¬IF(ISBLANK('DPW3'!LS20),"",'DPW3'!LS20) | ¬¬IF(ISBLANK('DPW3'!LT20),"",'DPW3'!LT20) | ¬¬IF(ISBLANK('DPW3'!LU20),"",'DPW3'!LU20) | ¬¬IF(ISBLANK('DPW3'!LV20),"",'DPW3'!LV20) | ¬¬IF(ISBLANK('DPW3'!LW20),"",'DPW3'!LW20) | ¬¬IF(ISBLANK('DPW3'!LX20),"",'DPW3'!LX20) | ¬¬IF(ISBLANK('DPW3'!LY20),"",'DPW3'!LY20) | ¬¬IF(ISBLANK('DPW3'!LZ20),"",'DPW3'!LZ20) | ¬¬IF(ISBLANK('DPW3'!MA20),"",'DPW3'!MA20)
¬¬A1582 | ¬¬IF(ISBLANK('DPW3'!ZL20),"",'DPW3'!ZL20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MC20),"",'DPW3'!MC20)
¬¬A1583 | ¬¬IF(ISBLANK('DPW3'!ZM20),"",'DPW3'!ZM20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MD20),"",'DPW3'!MD20)
¬¬A1584 | ¬¬IF(ISBLANK('DPW3'!ZN20),"",'DPW3'!ZN20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!ML20),"",'DPW3'!ML20)
¬¬A1585 | ¬¬IF(ISBLANK('DPW3'!ZO20),"",'DPW3'!ZO20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MF20),"",'DPW3'!MF20)
¬¬A1586 | ¬¬IF(ISBLANK('DPW3'!ZP20),"",'DPW3'!ZP20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MG20),"",'DPW3'!MG20)
¬¬A1587 | ¬¬IF(ISBLANK('DPW3'!ZQ20),"",'DPW3'!ZQ20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MH20),"",'DPW3'!MH20)
¬¬A1588 | ¬¬IF(ISBLANK('DPW3'!ZR20),"",'DPW3'!ZR20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MI20),"",'DPW3'!MI20)
¬¬A1589 | ¬¬IF(ISBLANK('DPW3'!ZS20),"",'DPW3'!ZS20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ20),"",'DPW3'!MJ20)
¬¬A1590 | ¬¬IF(ISBLANK('DPW3'!ZT20),"",'DPW3'!ZT20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MK20),"",'DPW3'!MK20)
¬¬A1591 | ¬¬IF(ISBLANK('DPW3'!ZV20),"",'DPW3'!ZV20) | ¬¬'DPW3'!F20 & "," & 'DPW3'!G20 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H20),"",'DPW3'!H20) | Delta | ¬¬IF(ISBLANK('DPW3'!MM20),"",'DPW3'!MM20)
¬¬A1592 | ¬¬IF(ISBLANK('DPW3'!MT21),"",'DPW3'!MT21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!K21),"",'DPW3'!K21)
¬¬A1593 | ¬¬IF(ISBLANK('DPW3'!MV21),"",'DPW3'!MV21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M21),"",'DPW3'!M21) | ¬¬IF(ISBLANK('DPW3'!N21),"",'DPW3'!N21) | ¬¬IF(ISBLANK('DPW3'!O21),"",'DPW3'!O21) | ¬¬IF(ISBLANK('DPW3'!P21),"",'DPW3'!P21) | ¬¬IF(ISBLANK('DPW3'!Q21),"",'DPW3'!Q21) | ¬¬IF(ISBLANK('DPW3'!R21),"",'DPW3'!R21) | ¬¬IF(ISBLANK('DPW3'!S21),"",'DPW3'!S21) | ¬¬IF(ISBLANK('DPW3'!T21),"",'DPW3'!T21) | ¬¬IF(ISBLANK('DPW3'!U21),"",'DPW3'!U21) | ¬¬IF(ISBLANK('DPW3'!V21),"",'DPW3'!V21) | ¬¬IF(ISBLANK('DPW3'!W21),"",'DPW3'!W21) | ¬¬IF(ISBLANK('DPW3'!X21),"",'DPW3'!X21) | ¬¬IF(ISBLANK('DPW3'!Y21),"",'DPW3'!Y21) | ¬¬IF(ISBLANK('DPW3'!Z21),"",'DPW3'!Z21) | ¬¬IF(ISBLANK('DPW3'!AA21),"",'DPW3'!AA21) | ¬¬IF(ISBLANK('DPW3'!AB21),"",'DPW3'!AB21) | ¬¬IF(ISBLANK('DPW3'!AC21),"",'DPW3'!AC21) | ¬¬IF(ISBLANK('DPW3'!AD21),"",'DPW3'!AD21) | ¬¬IF(ISBLANK('DPW3'!AE21),"",'DPW3'!AE21) | ¬¬IF(ISBLANK('DPW3'!AF21),"",'DPW3'!AF21) | ¬¬IF(ISBLANK('DPW3'!AG21),"",'DPW3'!AG21) | ¬¬IF(ISBLANK('DPW3'!AH21),"",'DPW3'!AH21) | ¬¬IF(ISBLANK('DPW3'!AI21),"",'DPW3'!AI21) | ¬¬IF(ISBLANK('DPW3'!AJ21),"",'DPW3'!AJ21) | ¬¬IF(ISBLANK('DPW3'!AK21),"",'DPW3'!AK21) | ¬¬IF(ISBLANK('DPW3'!AL21),"",'DPW3'!AL21) | ¬¬IF(ISBLANK('DPW3'!AM21),"",'DPW3'!AM21) | ¬¬IF(ISBLANK('DPW3'!AN21),"",'DPW3'!AN21) | ¬¬IF(ISBLANK('DPW3'!AO21),"",'DPW3'!AO21) | ¬¬IF(ISBLANK('DPW3'!AP21),"",'DPW3'!AP21) | ¬¬IF(ISBLANK('DPW3'!AQ21),"",'DPW3'!AQ21) | ¬¬IF(ISBLANK('DPW3'!AR21),"",'DPW3'!AR21) | ¬¬IF(ISBLANK('DPW3'!AS21),"",'DPW3'!AS21) | ¬¬IF(ISBLANK('DPW3'!AT21),"",'DPW3'!AT21) | ¬¬IF(ISBLANK('DPW3'!AU21),"",'DPW3'!AU21) | ¬¬IF(ISBLANK('DPW3'!AV21),"",'DPW3'!AV21) | ¬¬IF(ISBLANK('DPW3'!AW21),"",'DPW3'!AW21) | ¬¬IF(ISBLANK('DPW3'!AX21),"",'DPW3'!AX21) | ¬¬IF(ISBLANK('DPW3'!AY21),"",'DPW3'!AY21) | ¬¬IF(ISBLANK('DPW3'!AZ21),"",'DPW3'!AZ21)
¬¬A1594 | ¬¬IF(ISBLANK('DPW3'!OK21),"",'DPW3'!OK21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB21),"",'DPW3'!BB21) | ¬¬IF(ISBLANK('DPW3'!BC21),"",'DPW3'!BC21) | ¬¬IF(ISBLANK('DPW3'!BD21),"",'DPW3'!BD21) | ¬¬IF(ISBLANK('DPW3'!BE21),"",'DPW3'!BE21) | ¬¬IF(ISBLANK('DPW3'!BF21),"",'DPW3'!BF21) | ¬¬IF(ISBLANK('DPW3'!BG21),"",'DPW3'!BG21) | ¬¬IF(ISBLANK('DPW3'!BH21),"",'DPW3'!BH21) | ¬¬IF(ISBLANK('DPW3'!BI21),"",'DPW3'!BI21) | ¬¬IF(ISBLANK('DPW3'!BJ21),"",'DPW3'!BJ21) | ¬¬IF(ISBLANK('DPW3'!BK21),"",'DPW3'!BK21) | ¬¬IF(ISBLANK('DPW3'!BL21),"",'DPW3'!BL21) | ¬¬IF(ISBLANK('DPW3'!BM21),"",'DPW3'!BM21) | ¬¬IF(ISBLANK('DPW3'!BN21),"",'DPW3'!BN21) | ¬¬IF(ISBLANK('DPW3'!BO21),"",'DPW3'!BO21) | ¬¬IF(ISBLANK('DPW3'!BP21),"",'DPW3'!BP21) | ¬¬IF(ISBLANK('DPW3'!BQ21),"",'DPW3'!BQ21) | ¬¬IF(ISBLANK('DPW3'!BR21),"",'DPW3'!BR21) | ¬¬IF(ISBLANK('DPW3'!BS21),"",'DPW3'!BS21) | ¬¬IF(ISBLANK('DPW3'!BT21),"",'DPW3'!BT21) | ¬¬IF(ISBLANK('DPW3'!BU21),"",'DPW3'!BU21) | ¬¬IF(ISBLANK('DPW3'!BV21),"",'DPW3'!BV21) | ¬¬IF(ISBLANK('DPW3'!BW21),"",'DPW3'!BW21) | ¬¬IF(ISBLANK('DPW3'!BX21),"",'DPW3'!BX21) | ¬¬IF(ISBLANK('DPW3'!BY21),"",'DPW3'!BY21) | ¬¬IF(ISBLANK('DPW3'!BZ21),"",'DPW3'!BZ21) | ¬¬IF(ISBLANK('DPW3'!CA21),"",'DPW3'!CA21) | ¬¬IF(ISBLANK('DPW3'!CB21),"",'DPW3'!CB21) | ¬¬IF(ISBLANK('DPW3'!CC21),"",'DPW3'!CC21) | ¬¬IF(ISBLANK('DPW3'!CD21),"",'DPW3'!CD21) | ¬¬IF(ISBLANK('DPW3'!CE21),"",'DPW3'!CE21) | ¬¬IF(ISBLANK('DPW3'!CF21),"",'DPW3'!CF21) | ¬¬IF(ISBLANK('DPW3'!CG21),"",'DPW3'!CG21) | ¬¬IF(ISBLANK('DPW3'!CH21),"",'DPW3'!CH21) | ¬¬IF(ISBLANK('DPW3'!CI21),"",'DPW3'!CI21) | ¬¬IF(ISBLANK('DPW3'!CJ21),"",'DPW3'!CJ21) | ¬¬IF(ISBLANK('DPW3'!CK21),"",'DPW3'!CK21) | ¬¬IF(ISBLANK('DPW3'!CL21),"",'DPW3'!CL21) | ¬¬IF(ISBLANK('DPW3'!CM21),"",'DPW3'!CM21) | ¬¬IF(ISBLANK('DPW3'!CN21),"",'DPW3'!CN21) | ¬¬IF(ISBLANK('DPW3'!CO21),"",'DPW3'!CO21)
¬¬A1595 | ¬¬IF(ISBLANK('DPW3'!PZ21),"",'DPW3'!PZ21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ21),"",'DPW3'!CQ21) | ¬¬IF(ISBLANK('DPW3'!CR21),"",'DPW3'!CR21) | ¬¬IF(ISBLANK('DPW3'!CS21),"",'DPW3'!CS21) | ¬¬IF(ISBLANK('DPW3'!CT21),"",'DPW3'!CT21) | ¬¬IF(ISBLANK('DPW3'!CU21),"",'DPW3'!CU21) | ¬¬IF(ISBLANK('DPW3'!CV21),"",'DPW3'!CV21) | ¬¬IF(ISBLANK('DPW3'!CW21),"",'DPW3'!CW21) | ¬¬IF(ISBLANK('DPW3'!CX21),"",'DPW3'!CX21) | ¬¬IF(ISBLANK('DPW3'!CY21),"",'DPW3'!CY21) | ¬¬IF(ISBLANK('DPW3'!CZ21),"",'DPW3'!CZ21) | ¬¬IF(ISBLANK('DPW3'!DA21),"",'DPW3'!DA21) | ¬¬IF(ISBLANK('DPW3'!DB21),"",'DPW3'!DB21) | ¬¬IF(ISBLANK('DPW3'!DC21),"",'DPW3'!DC21) | ¬¬IF(ISBLANK('DPW3'!DD21),"",'DPW3'!DD21) | ¬¬IF(ISBLANK('DPW3'!DE21),"",'DPW3'!DE21) | ¬¬IF(ISBLANK('DPW3'!DF21),"",'DPW3'!DF21) | ¬¬IF(ISBLANK('DPW3'!DG21),"",'DPW3'!DG21) | ¬¬IF(ISBLANK('DPW3'!DH21),"",'DPW3'!DH21) | ¬¬IF(ISBLANK('DPW3'!DI21),"",'DPW3'!DI21) | ¬¬IF(ISBLANK('DPW3'!DJ21),"",'DPW3'!DJ21) | ¬¬IF(ISBLANK('DPW3'!DK21),"",'DPW3'!DK21) | ¬¬IF(ISBLANK('DPW3'!DL21),"",'DPW3'!DL21) | ¬¬IF(ISBLANK('DPW3'!DM21),"",'DPW3'!DM21) | ¬¬IF(ISBLANK('DPW3'!DN21),"",'DPW3'!DN21) | ¬¬IF(ISBLANK('DPW3'!DO21),"",'DPW3'!DO21) | ¬¬IF(ISBLANK('DPW3'!DP21),"",'DPW3'!DP21) | ¬¬IF(ISBLANK('DPW3'!DQ21),"",'DPW3'!DQ21) | ¬¬IF(ISBLANK('DPW3'!DR21),"",'DPW3'!DR21) | ¬¬IF(ISBLANK('DPW3'!DS21),"",'DPW3'!DS21) | ¬¬IF(ISBLANK('DPW3'!DT21),"",'DPW3'!DT21) | ¬¬IF(ISBLANK('DPW3'!DU21),"",'DPW3'!DU21) | ¬¬IF(ISBLANK('DPW3'!DV21),"",'DPW3'!DV21) | ¬¬IF(ISBLANK('DPW3'!DW21),"",'DPW3'!DW21) | ¬¬IF(ISBLANK('DPW3'!DX21),"",'DPW3'!DX21) | ¬¬IF(ISBLANK('DPW3'!DY21),"",'DPW3'!DY21) | ¬¬IF(ISBLANK('DPW3'!DZ21),"",'DPW3'!DZ21) | ¬¬IF(ISBLANK('DPW3'!EA21),"",'DPW3'!EA21) | ¬¬IF(ISBLANK('DPW3'!EB21),"",'DPW3'!EB21) | ¬¬IF(ISBLANK('DPW3'!EC21),"",'DPW3'!EC21) | ¬¬IF(ISBLANK('DPW3'!ED21),"",'DPW3'!ED21)
¬¬A1596 | ¬¬IF(ISBLANK('DPW3'!RO21),"",'DPW3'!RO21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF21),"",'DPW3'!EF21) | ¬¬IF(ISBLANK('DPW3'!EG21),"",'DPW3'!EG21) | ¬¬IF(ISBLANK('DPW3'!EH21),"",'DPW3'!EH21) | ¬¬IF(ISBLANK('DPW3'!EI21),"",'DPW3'!EI21) | ¬¬IF(ISBLANK('DPW3'!EJ21),"",'DPW3'!EJ21) | ¬¬IF(ISBLANK('DPW3'!EK21),"",'DPW3'!EK21) | ¬¬IF(ISBLANK('DPW3'!EL21),"",'DPW3'!EL21) | ¬¬IF(ISBLANK('DPW3'!EM21),"",'DPW3'!EM21) | ¬¬IF(ISBLANK('DPW3'!EN21),"",'DPW3'!EN21) | ¬¬IF(ISBLANK('DPW3'!EO21),"",'DPW3'!EO21) | ¬¬IF(ISBLANK('DPW3'!EP21),"",'DPW3'!EP21) | ¬¬IF(ISBLANK('DPW3'!EQ21),"",'DPW3'!EQ21) | ¬¬IF(ISBLANK('DPW3'!ER21),"",'DPW3'!ER21) | ¬¬IF(ISBLANK('DPW3'!ES21),"",'DPW3'!ES21) | ¬¬IF(ISBLANK('DPW3'!ET21),"",'DPW3'!ET21) | ¬¬IF(ISBLANK('DPW3'!EU21),"",'DPW3'!EU21) | ¬¬IF(ISBLANK('DPW3'!EV21),"",'DPW3'!EV21) | ¬¬IF(ISBLANK('DPW3'!EW21),"",'DPW3'!EW21) | ¬¬IF(ISBLANK('DPW3'!EX21),"",'DPW3'!EX21) | ¬¬IF(ISBLANK('DPW3'!EY21),"",'DPW3'!EY21) | ¬¬IF(ISBLANK('DPW3'!EZ21),"",'DPW3'!EZ21) | ¬¬IF(ISBLANK('DPW3'!FA21),"",'DPW3'!FA21) | ¬¬IF(ISBLANK('DPW3'!FB21),"",'DPW3'!FB21) | ¬¬IF(ISBLANK('DPW3'!FC21),"",'DPW3'!FC21) | ¬¬IF(ISBLANK('DPW3'!FD21),"",'DPW3'!FD21) | ¬¬IF(ISBLANK('DPW3'!FE21),"",'DPW3'!FE21) | ¬¬IF(ISBLANK('DPW3'!FF21),"",'DPW3'!FF21) | ¬¬IF(ISBLANK('DPW3'!FG21),"",'DPW3'!FG21) | ¬¬IF(ISBLANK('DPW3'!FH21),"",'DPW3'!FH21) | ¬¬IF(ISBLANK('DPW3'!FI21),"",'DPW3'!FI21) | ¬¬IF(ISBLANK('DPW3'!FJ21),"",'DPW3'!FJ21) | ¬¬IF(ISBLANK('DPW3'!FK21),"",'DPW3'!FK21) | ¬¬IF(ISBLANK('DPW3'!FL21),"",'DPW3'!FL21) | ¬¬IF(ISBLANK('DPW3'!FM21),"",'DPW3'!FM21) | ¬¬IF(ISBLANK('DPW3'!FN21),"",'DPW3'!FN21) | ¬¬IF(ISBLANK('DPW3'!FO21),"",'DPW3'!FO21) | ¬¬IF(ISBLANK('DPW3'!FP21),"",'DPW3'!FP21) | ¬¬IF(ISBLANK('DPW3'!FQ21),"",'DPW3'!FQ21) | ¬¬IF(ISBLANK('DPW3'!FR21),"",'DPW3'!FR21) | ¬¬IF(ISBLANK('DPW3'!FS21),"",'DPW3'!FS21)
¬¬A1597 | ¬¬IF(ISBLANK('DPW3'!TD21),"",'DPW3'!TD21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU21),"",'DPW3'!FU21) | ¬¬IF(ISBLANK('DPW3'!FV21),"",'DPW3'!FV21) | ¬¬IF(ISBLANK('DPW3'!FW21),"",'DPW3'!FW21) | ¬¬IF(ISBLANK('DPW3'!FX21),"",'DPW3'!FX21) | ¬¬IF(ISBLANK('DPW3'!FY21),"",'DPW3'!FY21) | ¬¬IF(ISBLANK('DPW3'!FZ21),"",'DPW3'!FZ21) | ¬¬IF(ISBLANK('DPW3'!GA21),"",'DPW3'!GA21) | ¬¬IF(ISBLANK('DPW3'!GB21),"",'DPW3'!GB21) | ¬¬IF(ISBLANK('DPW3'!GC21),"",'DPW3'!GC21) | ¬¬IF(ISBLANK('DPW3'!GD21),"",'DPW3'!GD21) | ¬¬IF(ISBLANK('DPW3'!GE21),"",'DPW3'!GE21) | ¬¬IF(ISBLANK('DPW3'!GF21),"",'DPW3'!GF21) | ¬¬IF(ISBLANK('DPW3'!GG21),"",'DPW3'!GG21) | ¬¬IF(ISBLANK('DPW3'!GH21),"",'DPW3'!GH21) | ¬¬IF(ISBLANK('DPW3'!GI21),"",'DPW3'!GI21) | ¬¬IF(ISBLANK('DPW3'!GJ21),"",'DPW3'!GJ21) | ¬¬IF(ISBLANK('DPW3'!GK21),"",'DPW3'!GK21) | ¬¬IF(ISBLANK('DPW3'!GL21),"",'DPW3'!GL21) | ¬¬IF(ISBLANK('DPW3'!GM21),"",'DPW3'!GM21) | ¬¬IF(ISBLANK('DPW3'!GN21),"",'DPW3'!GN21) | ¬¬IF(ISBLANK('DPW3'!GO21),"",'DPW3'!GO21) | ¬¬IF(ISBLANK('DPW3'!GP21),"",'DPW3'!GP21) | ¬¬IF(ISBLANK('DPW3'!GQ21),"",'DPW3'!GQ21) | ¬¬IF(ISBLANK('DPW3'!GR21),"",'DPW3'!GR21) | ¬¬IF(ISBLANK('DPW3'!GS21),"",'DPW3'!GS21) | ¬¬IF(ISBLANK('DPW3'!GT21),"",'DPW3'!GT21) | ¬¬IF(ISBLANK('DPW3'!GU21),"",'DPW3'!GU21) | ¬¬IF(ISBLANK('DPW3'!GV21),"",'DPW3'!GV21) | ¬¬IF(ISBLANK('DPW3'!GW21),"",'DPW3'!GW21) | ¬¬IF(ISBLANK('DPW3'!GX21),"",'DPW3'!GX21) | ¬¬IF(ISBLANK('DPW3'!GY21),"",'DPW3'!GY21) | ¬¬IF(ISBLANK('DPW3'!GZ21),"",'DPW3'!GZ21) | ¬¬IF(ISBLANK('DPW3'!HA21),"",'DPW3'!HA21) | ¬¬IF(ISBLANK('DPW3'!HB21),"",'DPW3'!HB21) | ¬¬IF(ISBLANK('DPW3'!HC21),"",'DPW3'!HC21) | ¬¬IF(ISBLANK('DPW3'!HD21),"",'DPW3'!HD21) | ¬¬IF(ISBLANK('DPW3'!HE21),"",'DPW3'!HE21) | ¬¬IF(ISBLANK('DPW3'!HF21),"",'DPW3'!HF21) | ¬¬IF(ISBLANK('DPW3'!HG21),"",'DPW3'!HG21) | ¬¬IF(ISBLANK('DPW3'!HH21),"",'DPW3'!HH21)
¬¬A1598 | ¬¬IF(ISBLANK('DPW3'!US21),"",'DPW3'!US21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ21),"",'DPW3'!HJ21) | ¬¬IF(ISBLANK('DPW3'!HK21),"",'DPW3'!HK21) | ¬¬IF(ISBLANK('DPW3'!HL21),"",'DPW3'!HL21) | ¬¬IF(ISBLANK('DPW3'!HM21),"",'DPW3'!HM21) | ¬¬IF(ISBLANK('DPW3'!HN21),"",'DPW3'!HN21) | ¬¬IF(ISBLANK('DPW3'!HO21),"",'DPW3'!HO21) | ¬¬IF(ISBLANK('DPW3'!HP21),"",'DPW3'!HP21) | ¬¬IF(ISBLANK('DPW3'!HQ21),"",'DPW3'!HQ21) | ¬¬IF(ISBLANK('DPW3'!HR21),"",'DPW3'!HR21) | ¬¬IF(ISBLANK('DPW3'!HS21),"",'DPW3'!HS21) | ¬¬IF(ISBLANK('DPW3'!HT21),"",'DPW3'!HT21) | ¬¬IF(ISBLANK('DPW3'!HU21),"",'DPW3'!HU21) | ¬¬IF(ISBLANK('DPW3'!HV21),"",'DPW3'!HV21) | ¬¬IF(ISBLANK('DPW3'!HW21),"",'DPW3'!HW21) | ¬¬IF(ISBLANK('DPW3'!HX21),"",'DPW3'!HX21) | ¬¬IF(ISBLANK('DPW3'!HY21),"",'DPW3'!HY21) | ¬¬IF(ISBLANK('DPW3'!HZ21),"",'DPW3'!HZ21) | ¬¬IF(ISBLANK('DPW3'!IA21),"",'DPW3'!IA21) | ¬¬IF(ISBLANK('DPW3'!IB21),"",'DPW3'!IB21) | ¬¬IF(ISBLANK('DPW3'!IC21),"",'DPW3'!IC21) | ¬¬IF(ISBLANK('DPW3'!ID21),"",'DPW3'!ID21) | ¬¬IF(ISBLANK('DPW3'!IE21),"",'DPW3'!IE21) | ¬¬IF(ISBLANK('DPW3'!IF21),"",'DPW3'!IF21) | ¬¬IF(ISBLANK('DPW3'!IG21),"",'DPW3'!IG21) | ¬¬IF(ISBLANK('DPW3'!IH21),"",'DPW3'!IH21) | ¬¬IF(ISBLANK('DPW3'!II21),"",'DPW3'!II21) | ¬¬IF(ISBLANK('DPW3'!IJ21),"",'DPW3'!IJ21) | ¬¬IF(ISBLANK('DPW3'!IK21),"",'DPW3'!IK21) | ¬¬IF(ISBLANK('DPW3'!IL21),"",'DPW3'!IL21) | ¬¬IF(ISBLANK('DPW3'!IM21),"",'DPW3'!IM21) | ¬¬IF(ISBLANK('DPW3'!IN21),"",'DPW3'!IN21) | ¬¬IF(ISBLANK('DPW3'!IO21),"",'DPW3'!IO21) | ¬¬IF(ISBLANK('DPW3'!IP21),"",'DPW3'!IP21) | ¬¬IF(ISBLANK('DPW3'!IQ21),"",'DPW3'!IQ21) | ¬¬IF(ISBLANK('DPW3'!IR21),"",'DPW3'!IR21) | ¬¬IF(ISBLANK('DPW3'!IS21),"",'DPW3'!IS21) | ¬¬IF(ISBLANK('DPW3'!IT21),"",'DPW3'!IT21) | ¬¬IF(ISBLANK('DPW3'!IU21),"",'DPW3'!IU21) | ¬¬IF(ISBLANK('DPW3'!IV21),"",'DPW3'!IV21) | ¬¬IF(ISBLANK('DPW3'!IW21),"",'DPW3'!IW21)
¬¬A1599 | ¬¬IF(ISBLANK('DPW3'!WH21),"",'DPW3'!WH21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY21),"",'DPW3'!IY21) | ¬¬IF(ISBLANK('DPW3'!IZ21),"",'DPW3'!IZ21) | ¬¬IF(ISBLANK('DPW3'!JA21),"",'DPW3'!JA21) | ¬¬IF(ISBLANK('DPW3'!JB21),"",'DPW3'!JB21) | ¬¬IF(ISBLANK('DPW3'!JC21),"",'DPW3'!JC21) | ¬¬IF(ISBLANK('DPW3'!JD21),"",'DPW3'!JD21) | ¬¬IF(ISBLANK('DPW3'!JE21),"",'DPW3'!JE21) | ¬¬IF(ISBLANK('DPW3'!JF21),"",'DPW3'!JF21) | ¬¬IF(ISBLANK('DPW3'!JG21),"",'DPW3'!JG21) | ¬¬IF(ISBLANK('DPW3'!JH21),"",'DPW3'!JH21) | ¬¬IF(ISBLANK('DPW3'!JI21),"",'DPW3'!JI21) | ¬¬IF(ISBLANK('DPW3'!JJ21),"",'DPW3'!JJ21) | ¬¬IF(ISBLANK('DPW3'!JK21),"",'DPW3'!JK21) | ¬¬IF(ISBLANK('DPW3'!JL21),"",'DPW3'!JL21) | ¬¬IF(ISBLANK('DPW3'!JM21),"",'DPW3'!JM21) | ¬¬IF(ISBLANK('DPW3'!JN21),"",'DPW3'!JN21) | ¬¬IF(ISBLANK('DPW3'!JO21),"",'DPW3'!JO21) | ¬¬IF(ISBLANK('DPW3'!JP21),"",'DPW3'!JP21) | ¬¬IF(ISBLANK('DPW3'!JQ21),"",'DPW3'!JQ21) | ¬¬IF(ISBLANK('DPW3'!JR21),"",'DPW3'!JR21) | ¬¬IF(ISBLANK('DPW3'!JS21),"",'DPW3'!JS21) | ¬¬IF(ISBLANK('DPW3'!JT21),"",'DPW3'!JT21) | ¬¬IF(ISBLANK('DPW3'!JU21),"",'DPW3'!JU21) | ¬¬IF(ISBLANK('DPW3'!JV21),"",'DPW3'!JV21) | ¬¬IF(ISBLANK('DPW3'!JW21),"",'DPW3'!JW21) | ¬¬IF(ISBLANK('DPW3'!JX21),"",'DPW3'!JX21) | ¬¬IF(ISBLANK('DPW3'!JY21),"",'DPW3'!JY21) | ¬¬IF(ISBLANK('DPW3'!JZ21),"",'DPW3'!JZ21) | ¬¬IF(ISBLANK('DPW3'!KA21),"",'DPW3'!KA21) | ¬¬IF(ISBLANK('DPW3'!KB21),"",'DPW3'!KB21) | ¬¬IF(ISBLANK('DPW3'!KC21),"",'DPW3'!KC21) | ¬¬IF(ISBLANK('DPW3'!KD21),"",'DPW3'!KD21) | ¬¬IF(ISBLANK('DPW3'!KE21),"",'DPW3'!KE21) | ¬¬IF(ISBLANK('DPW3'!KF21),"",'DPW3'!KF21) | ¬¬IF(ISBLANK('DPW3'!KG21),"",'DPW3'!KG21) | ¬¬IF(ISBLANK('DPW3'!KH21),"",'DPW3'!KH21) | ¬¬IF(ISBLANK('DPW3'!KI21),"",'DPW3'!KI21) | ¬¬IF(ISBLANK('DPW3'!KJ21),"",'DPW3'!KJ21) | ¬¬IF(ISBLANK('DPW3'!KK21),"",'DPW3'!KK21) | ¬¬IF(ISBLANK('DPW3'!KL21),"",'DPW3'!KL21)
¬¬A1600 | ¬¬IF(ISBLANK('DPW3'!XW21),"",'DPW3'!XW21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN21),"",'DPW3'!KN21) | ¬¬IF(ISBLANK('DPW3'!KO21),"",'DPW3'!KO21) | ¬¬IF(ISBLANK('DPW3'!KP21),"",'DPW3'!KP21) | ¬¬IF(ISBLANK('DPW3'!KQ21),"",'DPW3'!KQ21) | ¬¬IF(ISBLANK('DPW3'!KR21),"",'DPW3'!KR21) | ¬¬IF(ISBLANK('DPW3'!KS21),"",'DPW3'!KS21) | ¬¬IF(ISBLANK('DPW3'!KT21),"",'DPW3'!KT21) | ¬¬IF(ISBLANK('DPW3'!KU21),"",'DPW3'!KU21) | ¬¬IF(ISBLANK('DPW3'!KV21),"",'DPW3'!KV21) | ¬¬IF(ISBLANK('DPW3'!KW21),"",'DPW3'!KW21) | ¬¬IF(ISBLANK('DPW3'!KX21),"",'DPW3'!KX21) | ¬¬IF(ISBLANK('DPW3'!KY21),"",'DPW3'!KY21) | ¬¬IF(ISBLANK('DPW3'!KZ21),"",'DPW3'!KZ21) | ¬¬IF(ISBLANK('DPW3'!LA21),"",'DPW3'!LA21) | ¬¬IF(ISBLANK('DPW3'!LB21),"",'DPW3'!LB21) | ¬¬IF(ISBLANK('DPW3'!LC21),"",'DPW3'!LC21) | ¬¬IF(ISBLANK('DPW3'!LD21),"",'DPW3'!LD21) | ¬¬IF(ISBLANK('DPW3'!LE21),"",'DPW3'!LE21) | ¬¬IF(ISBLANK('DPW3'!LF21),"",'DPW3'!LF21) | ¬¬IF(ISBLANK('DPW3'!LG21),"",'DPW3'!LG21) | ¬¬IF(ISBLANK('DPW3'!LH21),"",'DPW3'!LH21) | ¬¬IF(ISBLANK('DPW3'!LI21),"",'DPW3'!LI21) | ¬¬IF(ISBLANK('DPW3'!LJ21),"",'DPW3'!LJ21) | ¬¬IF(ISBLANK('DPW3'!LK21),"",'DPW3'!LK21) | ¬¬IF(ISBLANK('DPW3'!LL21),"",'DPW3'!LL21) | ¬¬IF(ISBLANK('DPW3'!LM21),"",'DPW3'!LM21) | ¬¬IF(ISBLANK('DPW3'!LN21),"",'DPW3'!LN21) | ¬¬IF(ISBLANK('DPW3'!LO21),"",'DPW3'!LO21) | ¬¬IF(ISBLANK('DPW3'!LP21),"",'DPW3'!LP21) | ¬¬IF(ISBLANK('DPW3'!LQ21),"",'DPW3'!LQ21) | ¬¬IF(ISBLANK('DPW3'!LR21),"",'DPW3'!LR21) | ¬¬IF(ISBLANK('DPW3'!LS21),"",'DPW3'!LS21) | ¬¬IF(ISBLANK('DPW3'!LT21),"",'DPW3'!LT21) | ¬¬IF(ISBLANK('DPW3'!LU21),"",'DPW3'!LU21) | ¬¬IF(ISBLANK('DPW3'!LV21),"",'DPW3'!LV21) | ¬¬IF(ISBLANK('DPW3'!LW21),"",'DPW3'!LW21) | ¬¬IF(ISBLANK('DPW3'!LX21),"",'DPW3'!LX21) | ¬¬IF(ISBLANK('DPW3'!LY21),"",'DPW3'!LY21) | ¬¬IF(ISBLANK('DPW3'!LZ21),"",'DPW3'!LZ21) | ¬¬IF(ISBLANK('DPW3'!MA21),"",'DPW3'!MA21)
¬¬A1601 | ¬¬IF(ISBLANK('DPW3'!ZL21),"",'DPW3'!ZL21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MC21),"",'DPW3'!MC21)
¬¬A1602 | ¬¬IF(ISBLANK('DPW3'!ZM21),"",'DPW3'!ZM21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MD21),"",'DPW3'!MD21)
¬¬A1603 | ¬¬IF(ISBLANK('DPW3'!ZN21),"",'DPW3'!ZN21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!ML21),"",'DPW3'!ML21)
¬¬A1604 | ¬¬IF(ISBLANK('DPW3'!ZO21),"",'DPW3'!ZO21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MF21),"",'DPW3'!MF21)
¬¬A1605 | ¬¬IF(ISBLANK('DPW3'!ZP21),"",'DPW3'!ZP21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MG21),"",'DPW3'!MG21)
¬¬A1606 | ¬¬IF(ISBLANK('DPW3'!ZQ21),"",'DPW3'!ZQ21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MH21),"",'DPW3'!MH21)
¬¬A1607 | ¬¬IF(ISBLANK('DPW3'!ZR21),"",'DPW3'!ZR21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MI21),"",'DPW3'!MI21)
¬¬A1608 | ¬¬IF(ISBLANK('DPW3'!ZS21),"",'DPW3'!ZS21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ21),"",'DPW3'!MJ21)
¬¬A1609 | ¬¬IF(ISBLANK('DPW3'!ZT21),"",'DPW3'!ZT21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MK21),"",'DPW3'!MK21)
¬¬A1610 | ¬¬IF(ISBLANK('DPW3'!ZV21),"",'DPW3'!ZV21) | ¬¬'DPW3'!F21 & "," & 'DPW3'!G21 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H21),"",'DPW3'!H21) | Delta | ¬¬IF(ISBLANK('DPW3'!MM21),"",'DPW3'!MM21)
¬¬A1611 | ¬¬IF(ISBLANK('DPW3'!MT22),"",'DPW3'!MT22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!K22),"",'DPW3'!K22)
¬¬A1612 | ¬¬IF(ISBLANK('DPW3'!MV22),"",'DPW3'!MV22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M22),"",'DPW3'!M22) | ¬¬IF(ISBLANK('DPW3'!N22),"",'DPW3'!N22) | ¬¬IF(ISBLANK('DPW3'!O22),"",'DPW3'!O22) | ¬¬IF(ISBLANK('DPW3'!P22),"",'DPW3'!P22) | ¬¬IF(ISBLANK('DPW3'!Q22),"",'DPW3'!Q22) | ¬¬IF(ISBLANK('DPW3'!R22),"",'DPW3'!R22) | ¬¬IF(ISBLANK('DPW3'!S22),"",'DPW3'!S22) | ¬¬IF(ISBLANK('DPW3'!T22),"",'DPW3'!T22) | ¬¬IF(ISBLANK('DPW3'!U22),"",'DPW3'!U22) | ¬¬IF(ISBLANK('DPW3'!V22),"",'DPW3'!V22) | ¬¬IF(ISBLANK('DPW3'!W22),"",'DPW3'!W22) | ¬¬IF(ISBLANK('DPW3'!X22),"",'DPW3'!X22) | ¬¬IF(ISBLANK('DPW3'!Y22),"",'DPW3'!Y22) | ¬¬IF(ISBLANK('DPW3'!Z22),"",'DPW3'!Z22) | ¬¬IF(ISBLANK('DPW3'!AA22),"",'DPW3'!AA22) | ¬¬IF(ISBLANK('DPW3'!AB22),"",'DPW3'!AB22) | ¬¬IF(ISBLANK('DPW3'!AC22),"",'DPW3'!AC22) | ¬¬IF(ISBLANK('DPW3'!AD22),"",'DPW3'!AD22) | ¬¬IF(ISBLANK('DPW3'!AE22),"",'DPW3'!AE22) | ¬¬IF(ISBLANK('DPW3'!AF22),"",'DPW3'!AF22) | ¬¬IF(ISBLANK('DPW3'!AG22),"",'DPW3'!AG22) | ¬¬IF(ISBLANK('DPW3'!AH22),"",'DPW3'!AH22) | ¬¬IF(ISBLANK('DPW3'!AI22),"",'DPW3'!AI22) | ¬¬IF(ISBLANK('DPW3'!AJ22),"",'DPW3'!AJ22) | ¬¬IF(ISBLANK('DPW3'!AK22),"",'DPW3'!AK22) | ¬¬IF(ISBLANK('DPW3'!AL22),"",'DPW3'!AL22) | ¬¬IF(ISBLANK('DPW3'!AM22),"",'DPW3'!AM22) | ¬¬IF(ISBLANK('DPW3'!AN22),"",'DPW3'!AN22) | ¬¬IF(ISBLANK('DPW3'!AO22),"",'DPW3'!AO22) | ¬¬IF(ISBLANK('DPW3'!AP22),"",'DPW3'!AP22) | ¬¬IF(ISBLANK('DPW3'!AQ22),"",'DPW3'!AQ22) | ¬¬IF(ISBLANK('DPW3'!AR22),"",'DPW3'!AR22) | ¬¬IF(ISBLANK('DPW3'!AS22),"",'DPW3'!AS22) | ¬¬IF(ISBLANK('DPW3'!AT22),"",'DPW3'!AT22) | ¬¬IF(ISBLANK('DPW3'!AU22),"",'DPW3'!AU22) | ¬¬IF(ISBLANK('DPW3'!AV22),"",'DPW3'!AV22) | ¬¬IF(ISBLANK('DPW3'!AW22),"",'DPW3'!AW22) | ¬¬IF(ISBLANK('DPW3'!AX22),"",'DPW3'!AX22) | ¬¬IF(ISBLANK('DPW3'!AY22),"",'DPW3'!AY22) | ¬¬IF(ISBLANK('DPW3'!AZ22),"",'DPW3'!AZ22)
¬¬A1613 | ¬¬IF(ISBLANK('DPW3'!OK22),"",'DPW3'!OK22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB22),"",'DPW3'!BB22) | ¬¬IF(ISBLANK('DPW3'!BC22),"",'DPW3'!BC22) | ¬¬IF(ISBLANK('DPW3'!BD22),"",'DPW3'!BD22) | ¬¬IF(ISBLANK('DPW3'!BE22),"",'DPW3'!BE22) | ¬¬IF(ISBLANK('DPW3'!BF22),"",'DPW3'!BF22) | ¬¬IF(ISBLANK('DPW3'!BG22),"",'DPW3'!BG22) | ¬¬IF(ISBLANK('DPW3'!BH22),"",'DPW3'!BH22) | ¬¬IF(ISBLANK('DPW3'!BI22),"",'DPW3'!BI22) | ¬¬IF(ISBLANK('DPW3'!BJ22),"",'DPW3'!BJ22) | ¬¬IF(ISBLANK('DPW3'!BK22),"",'DPW3'!BK22) | ¬¬IF(ISBLANK('DPW3'!BL22),"",'DPW3'!BL22) | ¬¬IF(ISBLANK('DPW3'!BM22),"",'DPW3'!BM22) | ¬¬IF(ISBLANK('DPW3'!BN22),"",'DPW3'!BN22) | ¬¬IF(ISBLANK('DPW3'!BO22),"",'DPW3'!BO22) | ¬¬IF(ISBLANK('DPW3'!BP22),"",'DPW3'!BP22) | ¬¬IF(ISBLANK('DPW3'!BQ22),"",'DPW3'!BQ22) | ¬¬IF(ISBLANK('DPW3'!BR22),"",'DPW3'!BR22) | ¬¬IF(ISBLANK('DPW3'!BS22),"",'DPW3'!BS22) | ¬¬IF(ISBLANK('DPW3'!BT22),"",'DPW3'!BT22) | ¬¬IF(ISBLANK('DPW3'!BU22),"",'DPW3'!BU22) | ¬¬IF(ISBLANK('DPW3'!BV22),"",'DPW3'!BV22) | ¬¬IF(ISBLANK('DPW3'!BW22),"",'DPW3'!BW22) | ¬¬IF(ISBLANK('DPW3'!BX22),"",'DPW3'!BX22) | ¬¬IF(ISBLANK('DPW3'!BY22),"",'DPW3'!BY22) | ¬¬IF(ISBLANK('DPW3'!BZ22),"",'DPW3'!BZ22) | ¬¬IF(ISBLANK('DPW3'!CA22),"",'DPW3'!CA22) | ¬¬IF(ISBLANK('DPW3'!CB22),"",'DPW3'!CB22) | ¬¬IF(ISBLANK('DPW3'!CC22),"",'DPW3'!CC22) | ¬¬IF(ISBLANK('DPW3'!CD22),"",'DPW3'!CD22) | ¬¬IF(ISBLANK('DPW3'!CE22),"",'DPW3'!CE22) | ¬¬IF(ISBLANK('DPW3'!CF22),"",'DPW3'!CF22) | ¬¬IF(ISBLANK('DPW3'!CG22),"",'DPW3'!CG22) | ¬¬IF(ISBLANK('DPW3'!CH22),"",'DPW3'!CH22) | ¬¬IF(ISBLANK('DPW3'!CI22),"",'DPW3'!CI22) | ¬¬IF(ISBLANK('DPW3'!CJ22),"",'DPW3'!CJ22) | ¬¬IF(ISBLANK('DPW3'!CK22),"",'DPW3'!CK22) | ¬¬IF(ISBLANK('DPW3'!CL22),"",'DPW3'!CL22) | ¬¬IF(ISBLANK('DPW3'!CM22),"",'DPW3'!CM22) | ¬¬IF(ISBLANK('DPW3'!CN22),"",'DPW3'!CN22) | ¬¬IF(ISBLANK('DPW3'!CO22),"",'DPW3'!CO22)
¬¬A1614 | ¬¬IF(ISBLANK('DPW3'!PZ22),"",'DPW3'!PZ22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ22),"",'DPW3'!CQ22) | ¬¬IF(ISBLANK('DPW3'!CR22),"",'DPW3'!CR22) | ¬¬IF(ISBLANK('DPW3'!CS22),"",'DPW3'!CS22) | ¬¬IF(ISBLANK('DPW3'!CT22),"",'DPW3'!CT22) | ¬¬IF(ISBLANK('DPW3'!CU22),"",'DPW3'!CU22) | ¬¬IF(ISBLANK('DPW3'!CV22),"",'DPW3'!CV22) | ¬¬IF(ISBLANK('DPW3'!CW22),"",'DPW3'!CW22) | ¬¬IF(ISBLANK('DPW3'!CX22),"",'DPW3'!CX22) | ¬¬IF(ISBLANK('DPW3'!CY22),"",'DPW3'!CY22) | ¬¬IF(ISBLANK('DPW3'!CZ22),"",'DPW3'!CZ22) | ¬¬IF(ISBLANK('DPW3'!DA22),"",'DPW3'!DA22) | ¬¬IF(ISBLANK('DPW3'!DB22),"",'DPW3'!DB22) | ¬¬IF(ISBLANK('DPW3'!DC22),"",'DPW3'!DC22) | ¬¬IF(ISBLANK('DPW3'!DD22),"",'DPW3'!DD22) | ¬¬IF(ISBLANK('DPW3'!DE22),"",'DPW3'!DE22) | ¬¬IF(ISBLANK('DPW3'!DF22),"",'DPW3'!DF22) | ¬¬IF(ISBLANK('DPW3'!DG22),"",'DPW3'!DG22) | ¬¬IF(ISBLANK('DPW3'!DH22),"",'DPW3'!DH22) | ¬¬IF(ISBLANK('DPW3'!DI22),"",'DPW3'!DI22) | ¬¬IF(ISBLANK('DPW3'!DJ22),"",'DPW3'!DJ22) | ¬¬IF(ISBLANK('DPW3'!DK22),"",'DPW3'!DK22) | ¬¬IF(ISBLANK('DPW3'!DL22),"",'DPW3'!DL22) | ¬¬IF(ISBLANK('DPW3'!DM22),"",'DPW3'!DM22) | ¬¬IF(ISBLANK('DPW3'!DN22),"",'DPW3'!DN22) | ¬¬IF(ISBLANK('DPW3'!DO22),"",'DPW3'!DO22) | ¬¬IF(ISBLANK('DPW3'!DP22),"",'DPW3'!DP22) | ¬¬IF(ISBLANK('DPW3'!DQ22),"",'DPW3'!DQ22) | ¬¬IF(ISBLANK('DPW3'!DR22),"",'DPW3'!DR22) | ¬¬IF(ISBLANK('DPW3'!DS22),"",'DPW3'!DS22) | ¬¬IF(ISBLANK('DPW3'!DT22),"",'DPW3'!DT22) | ¬¬IF(ISBLANK('DPW3'!DU22),"",'DPW3'!DU22) | ¬¬IF(ISBLANK('DPW3'!DV22),"",'DPW3'!DV22) | ¬¬IF(ISBLANK('DPW3'!DW22),"",'DPW3'!DW22) | ¬¬IF(ISBLANK('DPW3'!DX22),"",'DPW3'!DX22) | ¬¬IF(ISBLANK('DPW3'!DY22),"",'DPW3'!DY22) | ¬¬IF(ISBLANK('DPW3'!DZ22),"",'DPW3'!DZ22) | ¬¬IF(ISBLANK('DPW3'!EA22),"",'DPW3'!EA22) | ¬¬IF(ISBLANK('DPW3'!EB22),"",'DPW3'!EB22) | ¬¬IF(ISBLANK('DPW3'!EC22),"",'DPW3'!EC22) | ¬¬IF(ISBLANK('DPW3'!ED22),"",'DPW3'!ED22)
¬¬A1615 | ¬¬IF(ISBLANK('DPW3'!RO22),"",'DPW3'!RO22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF22),"",'DPW3'!EF22) | ¬¬IF(ISBLANK('DPW3'!EG22),"",'DPW3'!EG22) | ¬¬IF(ISBLANK('DPW3'!EH22),"",'DPW3'!EH22) | ¬¬IF(ISBLANK('DPW3'!EI22),"",'DPW3'!EI22) | ¬¬IF(ISBLANK('DPW3'!EJ22),"",'DPW3'!EJ22) | ¬¬IF(ISBLANK('DPW3'!EK22),"",'DPW3'!EK22) | ¬¬IF(ISBLANK('DPW3'!EL22),"",'DPW3'!EL22) | ¬¬IF(ISBLANK('DPW3'!EM22),"",'DPW3'!EM22) | ¬¬IF(ISBLANK('DPW3'!EN22),"",'DPW3'!EN22) | ¬¬IF(ISBLANK('DPW3'!EO22),"",'DPW3'!EO22) | ¬¬IF(ISBLANK('DPW3'!EP22),"",'DPW3'!EP22) | ¬¬IF(ISBLANK('DPW3'!EQ22),"",'DPW3'!EQ22) | ¬¬IF(ISBLANK('DPW3'!ER22),"",'DPW3'!ER22) | ¬¬IF(ISBLANK('DPW3'!ES22),"",'DPW3'!ES22) | ¬¬IF(ISBLANK('DPW3'!ET22),"",'DPW3'!ET22) | ¬¬IF(ISBLANK('DPW3'!EU22),"",'DPW3'!EU22) | ¬¬IF(ISBLANK('DPW3'!EV22),"",'DPW3'!EV22) | ¬¬IF(ISBLANK('DPW3'!EW22),"",'DPW3'!EW22) | ¬¬IF(ISBLANK('DPW3'!EX22),"",'DPW3'!EX22) | ¬¬IF(ISBLANK('DPW3'!EY22),"",'DPW3'!EY22) | ¬¬IF(ISBLANK('DPW3'!EZ22),"",'DPW3'!EZ22) | ¬¬IF(ISBLANK('DPW3'!FA22),"",'DPW3'!FA22) | ¬¬IF(ISBLANK('DPW3'!FB22),"",'DPW3'!FB22) | ¬¬IF(ISBLANK('DPW3'!FC22),"",'DPW3'!FC22) | ¬¬IF(ISBLANK('DPW3'!FD22),"",'DPW3'!FD22) | ¬¬IF(ISBLANK('DPW3'!FE22),"",'DPW3'!FE22) | ¬¬IF(ISBLANK('DPW3'!FF22),"",'DPW3'!FF22) | ¬¬IF(ISBLANK('DPW3'!FG22),"",'DPW3'!FG22) | ¬¬IF(ISBLANK('DPW3'!FH22),"",'DPW3'!FH22) | ¬¬IF(ISBLANK('DPW3'!FI22),"",'DPW3'!FI22) | ¬¬IF(ISBLANK('DPW3'!FJ22),"",'DPW3'!FJ22) | ¬¬IF(ISBLANK('DPW3'!FK22),"",'DPW3'!FK22) | ¬¬IF(ISBLANK('DPW3'!FL22),"",'DPW3'!FL22) | ¬¬IF(ISBLANK('DPW3'!FM22),"",'DPW3'!FM22) | ¬¬IF(ISBLANK('DPW3'!FN22),"",'DPW3'!FN22) | ¬¬IF(ISBLANK('DPW3'!FO22),"",'DPW3'!FO22) | ¬¬IF(ISBLANK('DPW3'!FP22),"",'DPW3'!FP22) | ¬¬IF(ISBLANK('DPW3'!FQ22),"",'DPW3'!FQ22) | ¬¬IF(ISBLANK('DPW3'!FR22),"",'DPW3'!FR22) | ¬¬IF(ISBLANK('DPW3'!FS22),"",'DPW3'!FS22)
¬¬A1616 | ¬¬IF(ISBLANK('DPW3'!TD22),"",'DPW3'!TD22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU22),"",'DPW3'!FU22) | ¬¬IF(ISBLANK('DPW3'!FV22),"",'DPW3'!FV22) | ¬¬IF(ISBLANK('DPW3'!FW22),"",'DPW3'!FW22) | ¬¬IF(ISBLANK('DPW3'!FX22),"",'DPW3'!FX22) | ¬¬IF(ISBLANK('DPW3'!FY22),"",'DPW3'!FY22) | ¬¬IF(ISBLANK('DPW3'!FZ22),"",'DPW3'!FZ22) | ¬¬IF(ISBLANK('DPW3'!GA22),"",'DPW3'!GA22) | ¬¬IF(ISBLANK('DPW3'!GB22),"",'DPW3'!GB22) | ¬¬IF(ISBLANK('DPW3'!GC22),"",'DPW3'!GC22) | ¬¬IF(ISBLANK('DPW3'!GD22),"",'DPW3'!GD22) | ¬¬IF(ISBLANK('DPW3'!GE22),"",'DPW3'!GE22) | ¬¬IF(ISBLANK('DPW3'!GF22),"",'DPW3'!GF22) | ¬¬IF(ISBLANK('DPW3'!GG22),"",'DPW3'!GG22) | ¬¬IF(ISBLANK('DPW3'!GH22),"",'DPW3'!GH22) | ¬¬IF(ISBLANK('DPW3'!GI22),"",'DPW3'!GI22) | ¬¬IF(ISBLANK('DPW3'!GJ22),"",'DPW3'!GJ22) | ¬¬IF(ISBLANK('DPW3'!GK22),"",'DPW3'!GK22) | ¬¬IF(ISBLANK('DPW3'!GL22),"",'DPW3'!GL22) | ¬¬IF(ISBLANK('DPW3'!GM22),"",'DPW3'!GM22) | ¬¬IF(ISBLANK('DPW3'!GN22),"",'DPW3'!GN22) | ¬¬IF(ISBLANK('DPW3'!GO22),"",'DPW3'!GO22) | ¬¬IF(ISBLANK('DPW3'!GP22),"",'DPW3'!GP22) | ¬¬IF(ISBLANK('DPW3'!GQ22),"",'DPW3'!GQ22) | ¬¬IF(ISBLANK('DPW3'!GR22),"",'DPW3'!GR22) | ¬¬IF(ISBLANK('DPW3'!GS22),"",'DPW3'!GS22) | ¬¬IF(ISBLANK('DPW3'!GT22),"",'DPW3'!GT22) | ¬¬IF(ISBLANK('DPW3'!GU22),"",'DPW3'!GU22) | ¬¬IF(ISBLANK('DPW3'!GV22),"",'DPW3'!GV22) | ¬¬IF(ISBLANK('DPW3'!GW22),"",'DPW3'!GW22) | ¬¬IF(ISBLANK('DPW3'!GX22),"",'DPW3'!GX22) | ¬¬IF(ISBLANK('DPW3'!GY22),"",'DPW3'!GY22) | ¬¬IF(ISBLANK('DPW3'!GZ22),"",'DPW3'!GZ22) | ¬¬IF(ISBLANK('DPW3'!HA22),"",'DPW3'!HA22) | ¬¬IF(ISBLANK('DPW3'!HB22),"",'DPW3'!HB22) | ¬¬IF(ISBLANK('DPW3'!HC22),"",'DPW3'!HC22) | ¬¬IF(ISBLANK('DPW3'!HD22),"",'DPW3'!HD22) | ¬¬IF(ISBLANK('DPW3'!HE22),"",'DPW3'!HE22) | ¬¬IF(ISBLANK('DPW3'!HF22),"",'DPW3'!HF22) | ¬¬IF(ISBLANK('DPW3'!HG22),"",'DPW3'!HG22) | ¬¬IF(ISBLANK('DPW3'!HH22),"",'DPW3'!HH22)
¬¬A1617 | ¬¬IF(ISBLANK('DPW3'!US22),"",'DPW3'!US22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ22),"",'DPW3'!HJ22) | ¬¬IF(ISBLANK('DPW3'!HK22),"",'DPW3'!HK22) | ¬¬IF(ISBLANK('DPW3'!HL22),"",'DPW3'!HL22) | ¬¬IF(ISBLANK('DPW3'!HM22),"",'DPW3'!HM22) | ¬¬IF(ISBLANK('DPW3'!HN22),"",'DPW3'!HN22) | ¬¬IF(ISBLANK('DPW3'!HO22),"",'DPW3'!HO22) | ¬¬IF(ISBLANK('DPW3'!HP22),"",'DPW3'!HP22) | ¬¬IF(ISBLANK('DPW3'!HQ22),"",'DPW3'!HQ22) | ¬¬IF(ISBLANK('DPW3'!HR22),"",'DPW3'!HR22) | ¬¬IF(ISBLANK('DPW3'!HS22),"",'DPW3'!HS22) | ¬¬IF(ISBLANK('DPW3'!HT22),"",'DPW3'!HT22) | ¬¬IF(ISBLANK('DPW3'!HU22),"",'DPW3'!HU22) | ¬¬IF(ISBLANK('DPW3'!HV22),"",'DPW3'!HV22) | ¬¬IF(ISBLANK('DPW3'!HW22),"",'DPW3'!HW22) | ¬¬IF(ISBLANK('DPW3'!HX22),"",'DPW3'!HX22) | ¬¬IF(ISBLANK('DPW3'!HY22),"",'DPW3'!HY22) | ¬¬IF(ISBLANK('DPW3'!HZ22),"",'DPW3'!HZ22) | ¬¬IF(ISBLANK('DPW3'!IA22),"",'DPW3'!IA22) | ¬¬IF(ISBLANK('DPW3'!IB22),"",'DPW3'!IB22) | ¬¬IF(ISBLANK('DPW3'!IC22),"",'DPW3'!IC22) | ¬¬IF(ISBLANK('DPW3'!ID22),"",'DPW3'!ID22) | ¬¬IF(ISBLANK('DPW3'!IE22),"",'DPW3'!IE22) | ¬¬IF(ISBLANK('DPW3'!IF22),"",'DPW3'!IF22) | ¬¬IF(ISBLANK('DPW3'!IG22),"",'DPW3'!IG22) | ¬¬IF(ISBLANK('DPW3'!IH22),"",'DPW3'!IH22) | ¬¬IF(ISBLANK('DPW3'!II22),"",'DPW3'!II22) | ¬¬IF(ISBLANK('DPW3'!IJ22),"",'DPW3'!IJ22) | ¬¬IF(ISBLANK('DPW3'!IK22),"",'DPW3'!IK22) | ¬¬IF(ISBLANK('DPW3'!IL22),"",'DPW3'!IL22) | ¬¬IF(ISBLANK('DPW3'!IM22),"",'DPW3'!IM22) | ¬¬IF(ISBLANK('DPW3'!IN22),"",'DPW3'!IN22) | ¬¬IF(ISBLANK('DPW3'!IO22),"",'DPW3'!IO22) | ¬¬IF(ISBLANK('DPW3'!IP22),"",'DPW3'!IP22) | ¬¬IF(ISBLANK('DPW3'!IQ22),"",'DPW3'!IQ22) | ¬¬IF(ISBLANK('DPW3'!IR22),"",'DPW3'!IR22) | ¬¬IF(ISBLANK('DPW3'!IS22),"",'DPW3'!IS22) | ¬¬IF(ISBLANK('DPW3'!IT22),"",'DPW3'!IT22) | ¬¬IF(ISBLANK('DPW3'!IU22),"",'DPW3'!IU22) | ¬¬IF(ISBLANK('DPW3'!IV22),"",'DPW3'!IV22) | ¬¬IF(ISBLANK('DPW3'!IW22),"",'DPW3'!IW22)
¬¬A1618 | ¬¬IF(ISBLANK('DPW3'!WH22),"",'DPW3'!WH22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY22),"",'DPW3'!IY22) | ¬¬IF(ISBLANK('DPW3'!IZ22),"",'DPW3'!IZ22) | ¬¬IF(ISBLANK('DPW3'!JA22),"",'DPW3'!JA22) | ¬¬IF(ISBLANK('DPW3'!JB22),"",'DPW3'!JB22) | ¬¬IF(ISBLANK('DPW3'!JC22),"",'DPW3'!JC22) | ¬¬IF(ISBLANK('DPW3'!JD22),"",'DPW3'!JD22) | ¬¬IF(ISBLANK('DPW3'!JE22),"",'DPW3'!JE22) | ¬¬IF(ISBLANK('DPW3'!JF22),"",'DPW3'!JF22) | ¬¬IF(ISBLANK('DPW3'!JG22),"",'DPW3'!JG22) | ¬¬IF(ISBLANK('DPW3'!JH22),"",'DPW3'!JH22) | ¬¬IF(ISBLANK('DPW3'!JI22),"",'DPW3'!JI22) | ¬¬IF(ISBLANK('DPW3'!JJ22),"",'DPW3'!JJ22) | ¬¬IF(ISBLANK('DPW3'!JK22),"",'DPW3'!JK22) | ¬¬IF(ISBLANK('DPW3'!JL22),"",'DPW3'!JL22) | ¬¬IF(ISBLANK('DPW3'!JM22),"",'DPW3'!JM22) | ¬¬IF(ISBLANK('DPW3'!JN22),"",'DPW3'!JN22) | ¬¬IF(ISBLANK('DPW3'!JO22),"",'DPW3'!JO22) | ¬¬IF(ISBLANK('DPW3'!JP22),"",'DPW3'!JP22) | ¬¬IF(ISBLANK('DPW3'!JQ22),"",'DPW3'!JQ22) | ¬¬IF(ISBLANK('DPW3'!JR22),"",'DPW3'!JR22) | ¬¬IF(ISBLANK('DPW3'!JS22),"",'DPW3'!JS22) | ¬¬IF(ISBLANK('DPW3'!JT22),"",'DPW3'!JT22) | ¬¬IF(ISBLANK('DPW3'!JU22),"",'DPW3'!JU22) | ¬¬IF(ISBLANK('DPW3'!JV22),"",'DPW3'!JV22) | ¬¬IF(ISBLANK('DPW3'!JW22),"",'DPW3'!JW22) | ¬¬IF(ISBLANK('DPW3'!JX22),"",'DPW3'!JX22) | ¬¬IF(ISBLANK('DPW3'!JY22),"",'DPW3'!JY22) | ¬¬IF(ISBLANK('DPW3'!JZ22),"",'DPW3'!JZ22) | ¬¬IF(ISBLANK('DPW3'!KA22),"",'DPW3'!KA22) | ¬¬IF(ISBLANK('DPW3'!KB22),"",'DPW3'!KB22) | ¬¬IF(ISBLANK('DPW3'!KC22),"",'DPW3'!KC22) | ¬¬IF(ISBLANK('DPW3'!KD22),"",'DPW3'!KD22) | ¬¬IF(ISBLANK('DPW3'!KE22),"",'DPW3'!KE22) | ¬¬IF(ISBLANK('DPW3'!KF22),"",'DPW3'!KF22) | ¬¬IF(ISBLANK('DPW3'!KG22),"",'DPW3'!KG22) | ¬¬IF(ISBLANK('DPW3'!KH22),"",'DPW3'!KH22) | ¬¬IF(ISBLANK('DPW3'!KI22),"",'DPW3'!KI22) | ¬¬IF(ISBLANK('DPW3'!KJ22),"",'DPW3'!KJ22) | ¬¬IF(ISBLANK('DPW3'!KK22),"",'DPW3'!KK22) | ¬¬IF(ISBLANK('DPW3'!KL22),"",'DPW3'!KL22)
¬¬A1619 | ¬¬IF(ISBLANK('DPW3'!XW22),"",'DPW3'!XW22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN22),"",'DPW3'!KN22) | ¬¬IF(ISBLANK('DPW3'!KO22),"",'DPW3'!KO22) | ¬¬IF(ISBLANK('DPW3'!KP22),"",'DPW3'!KP22) | ¬¬IF(ISBLANK('DPW3'!KQ22),"",'DPW3'!KQ22) | ¬¬IF(ISBLANK('DPW3'!KR22),"",'DPW3'!KR22) | ¬¬IF(ISBLANK('DPW3'!KS22),"",'DPW3'!KS22) | ¬¬IF(ISBLANK('DPW3'!KT22),"",'DPW3'!KT22) | ¬¬IF(ISBLANK('DPW3'!KU22),"",'DPW3'!KU22) | ¬¬IF(ISBLANK('DPW3'!KV22),"",'DPW3'!KV22) | ¬¬IF(ISBLANK('DPW3'!KW22),"",'DPW3'!KW22) | ¬¬IF(ISBLANK('DPW3'!KX22),"",'DPW3'!KX22) | ¬¬IF(ISBLANK('DPW3'!KY22),"",'DPW3'!KY22) | ¬¬IF(ISBLANK('DPW3'!KZ22),"",'DPW3'!KZ22) | ¬¬IF(ISBLANK('DPW3'!LA22),"",'DPW3'!LA22) | ¬¬IF(ISBLANK('DPW3'!LB22),"",'DPW3'!LB22) | ¬¬IF(ISBLANK('DPW3'!LC22),"",'DPW3'!LC22) | ¬¬IF(ISBLANK('DPW3'!LD22),"",'DPW3'!LD22) | ¬¬IF(ISBLANK('DPW3'!LE22),"",'DPW3'!LE22) | ¬¬IF(ISBLANK('DPW3'!LF22),"",'DPW3'!LF22) | ¬¬IF(ISBLANK('DPW3'!LG22),"",'DPW3'!LG22) | ¬¬IF(ISBLANK('DPW3'!LH22),"",'DPW3'!LH22) | ¬¬IF(ISBLANK('DPW3'!LI22),"",'DPW3'!LI22) | ¬¬IF(ISBLANK('DPW3'!LJ22),"",'DPW3'!LJ22) | ¬¬IF(ISBLANK('DPW3'!LK22),"",'DPW3'!LK22) | ¬¬IF(ISBLANK('DPW3'!LL22),"",'DPW3'!LL22) | ¬¬IF(ISBLANK('DPW3'!LM22),"",'DPW3'!LM22) | ¬¬IF(ISBLANK('DPW3'!LN22),"",'DPW3'!LN22) | ¬¬IF(ISBLANK('DPW3'!LO22),"",'DPW3'!LO22) | ¬¬IF(ISBLANK('DPW3'!LP22),"",'DPW3'!LP22) | ¬¬IF(ISBLANK('DPW3'!LQ22),"",'DPW3'!LQ22) | ¬¬IF(ISBLANK('DPW3'!LR22),"",'DPW3'!LR22) | ¬¬IF(ISBLANK('DPW3'!LS22),"",'DPW3'!LS22) | ¬¬IF(ISBLANK('DPW3'!LT22),"",'DPW3'!LT22) | ¬¬IF(ISBLANK('DPW3'!LU22),"",'DPW3'!LU22) | ¬¬IF(ISBLANK('DPW3'!LV22),"",'DPW3'!LV22) | ¬¬IF(ISBLANK('DPW3'!LW22),"",'DPW3'!LW22) | ¬¬IF(ISBLANK('DPW3'!LX22),"",'DPW3'!LX22) | ¬¬IF(ISBLANK('DPW3'!LY22),"",'DPW3'!LY22) | ¬¬IF(ISBLANK('DPW3'!LZ22),"",'DPW3'!LZ22) | ¬¬IF(ISBLANK('DPW3'!MA22),"",'DPW3'!MA22)
¬¬A1620 | ¬¬IF(ISBLANK('DPW3'!ZL22),"",'DPW3'!ZL22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MC22),"",'DPW3'!MC22)
¬¬A1621 | ¬¬IF(ISBLANK('DPW3'!ZM22),"",'DPW3'!ZM22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MD22),"",'DPW3'!MD22)
¬¬A1622 | ¬¬IF(ISBLANK('DPW3'!ZN22),"",'DPW3'!ZN22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!ML22),"",'DPW3'!ML22)
¬¬A1623 | ¬¬IF(ISBLANK('DPW3'!ZO22),"",'DPW3'!ZO22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MF22),"",'DPW3'!MF22)
¬¬A1624 | ¬¬IF(ISBLANK('DPW3'!ZP22),"",'DPW3'!ZP22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MG22),"",'DPW3'!MG22)
¬¬A1625 | ¬¬IF(ISBLANK('DPW3'!ZQ22),"",'DPW3'!ZQ22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MH22),"",'DPW3'!MH22)
¬¬A1626 | ¬¬IF(ISBLANK('DPW3'!ZR22),"",'DPW3'!ZR22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MI22),"",'DPW3'!MI22)
¬¬A1627 | ¬¬IF(ISBLANK('DPW3'!ZS22),"",'DPW3'!ZS22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ22),"",'DPW3'!MJ22)
¬¬A1628 | ¬¬IF(ISBLANK('DPW3'!ZT22),"",'DPW3'!ZT22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MK22),"",'DPW3'!MK22)
¬¬A1629 | ¬¬IF(ISBLANK('DPW3'!ZV22),"",'DPW3'!ZV22) | ¬¬'DPW3'!F22 & "," & 'DPW3'!G22 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H22),"",'DPW3'!H22) | Delta | ¬¬IF(ISBLANK('DPW3'!MM22),"",'DPW3'!MM22)
¬¬A1630 | ¬¬IF(ISBLANK('DPW3'!MT23),"",'DPW3'!MT23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!MT7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!K23),"",'DPW3'!K23)
¬¬A1631 | ¬¬IF(ISBLANK('DPW3'!MV23),"",'DPW3'!MV23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!MV7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!M23),"",'DPW3'!M23) | ¬¬IF(ISBLANK('DPW3'!N23),"",'DPW3'!N23) | ¬¬IF(ISBLANK('DPW3'!O23),"",'DPW3'!O23) | ¬¬IF(ISBLANK('DPW3'!P23),"",'DPW3'!P23) | ¬¬IF(ISBLANK('DPW3'!Q23),"",'DPW3'!Q23) | ¬¬IF(ISBLANK('DPW3'!R23),"",'DPW3'!R23) | ¬¬IF(ISBLANK('DPW3'!S23),"",'DPW3'!S23) | ¬¬IF(ISBLANK('DPW3'!T23),"",'DPW3'!T23) | ¬¬IF(ISBLANK('DPW3'!U23),"",'DPW3'!U23) | ¬¬IF(ISBLANK('DPW3'!V23),"",'DPW3'!V23) | ¬¬IF(ISBLANK('DPW3'!W23),"",'DPW3'!W23) | ¬¬IF(ISBLANK('DPW3'!X23),"",'DPW3'!X23) | ¬¬IF(ISBLANK('DPW3'!Y23),"",'DPW3'!Y23) | ¬¬IF(ISBLANK('DPW3'!Z23),"",'DPW3'!Z23) | ¬¬IF(ISBLANK('DPW3'!AA23),"",'DPW3'!AA23) | ¬¬IF(ISBLANK('DPW3'!AB23),"",'DPW3'!AB23) | ¬¬IF(ISBLANK('DPW3'!AC23),"",'DPW3'!AC23) | ¬¬IF(ISBLANK('DPW3'!AD23),"",'DPW3'!AD23) | ¬¬IF(ISBLANK('DPW3'!AE23),"",'DPW3'!AE23) | ¬¬IF(ISBLANK('DPW3'!AF23),"",'DPW3'!AF23) | ¬¬IF(ISBLANK('DPW3'!AG23),"",'DPW3'!AG23) | ¬¬IF(ISBLANK('DPW3'!AH23),"",'DPW3'!AH23) | ¬¬IF(ISBLANK('DPW3'!AI23),"",'DPW3'!AI23) | ¬¬IF(ISBLANK('DPW3'!AJ23),"",'DPW3'!AJ23) | ¬¬IF(ISBLANK('DPW3'!AK23),"",'DPW3'!AK23) | ¬¬IF(ISBLANK('DPW3'!AL23),"",'DPW3'!AL23) | ¬¬IF(ISBLANK('DPW3'!AM23),"",'DPW3'!AM23) | ¬¬IF(ISBLANK('DPW3'!AN23),"",'DPW3'!AN23) | ¬¬IF(ISBLANK('DPW3'!AO23),"",'DPW3'!AO23) | ¬¬IF(ISBLANK('DPW3'!AP23),"",'DPW3'!AP23) | ¬¬IF(ISBLANK('DPW3'!AQ23),"",'DPW3'!AQ23) | ¬¬IF(ISBLANK('DPW3'!AR23),"",'DPW3'!AR23) | ¬¬IF(ISBLANK('DPW3'!AS23),"",'DPW3'!AS23) | ¬¬IF(ISBLANK('DPW3'!AT23),"",'DPW3'!AT23) | ¬¬IF(ISBLANK('DPW3'!AU23),"",'DPW3'!AU23) | ¬¬IF(ISBLANK('DPW3'!AV23),"",'DPW3'!AV23) | ¬¬IF(ISBLANK('DPW3'!AW23),"",'DPW3'!AW23) | ¬¬IF(ISBLANK('DPW3'!AX23),"",'DPW3'!AX23) | ¬¬IF(ISBLANK('DPW3'!AY23),"",'DPW3'!AY23) | ¬¬IF(ISBLANK('DPW3'!AZ23),"",'DPW3'!AZ23)
¬¬A1632 | ¬¬IF(ISBLANK('DPW3'!OK23),"",'DPW3'!OK23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!OK7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!BB23),"",'DPW3'!BB23) | ¬¬IF(ISBLANK('DPW3'!BC23),"",'DPW3'!BC23) | ¬¬IF(ISBLANK('DPW3'!BD23),"",'DPW3'!BD23) | ¬¬IF(ISBLANK('DPW3'!BE23),"",'DPW3'!BE23) | ¬¬IF(ISBLANK('DPW3'!BF23),"",'DPW3'!BF23) | ¬¬IF(ISBLANK('DPW3'!BG23),"",'DPW3'!BG23) | ¬¬IF(ISBLANK('DPW3'!BH23),"",'DPW3'!BH23) | ¬¬IF(ISBLANK('DPW3'!BI23),"",'DPW3'!BI23) | ¬¬IF(ISBLANK('DPW3'!BJ23),"",'DPW3'!BJ23) | ¬¬IF(ISBLANK('DPW3'!BK23),"",'DPW3'!BK23) | ¬¬IF(ISBLANK('DPW3'!BL23),"",'DPW3'!BL23) | ¬¬IF(ISBLANK('DPW3'!BM23),"",'DPW3'!BM23) | ¬¬IF(ISBLANK('DPW3'!BN23),"",'DPW3'!BN23) | ¬¬IF(ISBLANK('DPW3'!BO23),"",'DPW3'!BO23) | ¬¬IF(ISBLANK('DPW3'!BP23),"",'DPW3'!BP23) | ¬¬IF(ISBLANK('DPW3'!BQ23),"",'DPW3'!BQ23) | ¬¬IF(ISBLANK('DPW3'!BR23),"",'DPW3'!BR23) | ¬¬IF(ISBLANK('DPW3'!BS23),"",'DPW3'!BS23) | ¬¬IF(ISBLANK('DPW3'!BT23),"",'DPW3'!BT23) | ¬¬IF(ISBLANK('DPW3'!BU23),"",'DPW3'!BU23) | ¬¬IF(ISBLANK('DPW3'!BV23),"",'DPW3'!BV23) | ¬¬IF(ISBLANK('DPW3'!BW23),"",'DPW3'!BW23) | ¬¬IF(ISBLANK('DPW3'!BX23),"",'DPW3'!BX23) | ¬¬IF(ISBLANK('DPW3'!BY23),"",'DPW3'!BY23) | ¬¬IF(ISBLANK('DPW3'!BZ23),"",'DPW3'!BZ23) | ¬¬IF(ISBLANK('DPW3'!CA23),"",'DPW3'!CA23) | ¬¬IF(ISBLANK('DPW3'!CB23),"",'DPW3'!CB23) | ¬¬IF(ISBLANK('DPW3'!CC23),"",'DPW3'!CC23) | ¬¬IF(ISBLANK('DPW3'!CD23),"",'DPW3'!CD23) | ¬¬IF(ISBLANK('DPW3'!CE23),"",'DPW3'!CE23) | ¬¬IF(ISBLANK('DPW3'!CF23),"",'DPW3'!CF23) | ¬¬IF(ISBLANK('DPW3'!CG23),"",'DPW3'!CG23) | ¬¬IF(ISBLANK('DPW3'!CH23),"",'DPW3'!CH23) | ¬¬IF(ISBLANK('DPW3'!CI23),"",'DPW3'!CI23) | ¬¬IF(ISBLANK('DPW3'!CJ23),"",'DPW3'!CJ23) | ¬¬IF(ISBLANK('DPW3'!CK23),"",'DPW3'!CK23) | ¬¬IF(ISBLANK('DPW3'!CL23),"",'DPW3'!CL23) | ¬¬IF(ISBLANK('DPW3'!CM23),"",'DPW3'!CM23) | ¬¬IF(ISBLANK('DPW3'!CN23),"",'DPW3'!CN23) | ¬¬IF(ISBLANK('DPW3'!CO23),"",'DPW3'!CO23)
¬¬A1633 | ¬¬IF(ISBLANK('DPW3'!PZ23),"",'DPW3'!PZ23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!PZ7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!CQ23),"",'DPW3'!CQ23) | ¬¬IF(ISBLANK('DPW3'!CR23),"",'DPW3'!CR23) | ¬¬IF(ISBLANK('DPW3'!CS23),"",'DPW3'!CS23) | ¬¬IF(ISBLANK('DPW3'!CT23),"",'DPW3'!CT23) | ¬¬IF(ISBLANK('DPW3'!CU23),"",'DPW3'!CU23) | ¬¬IF(ISBLANK('DPW3'!CV23),"",'DPW3'!CV23) | ¬¬IF(ISBLANK('DPW3'!CW23),"",'DPW3'!CW23) | ¬¬IF(ISBLANK('DPW3'!CX23),"",'DPW3'!CX23) | ¬¬IF(ISBLANK('DPW3'!CY23),"",'DPW3'!CY23) | ¬¬IF(ISBLANK('DPW3'!CZ23),"",'DPW3'!CZ23) | ¬¬IF(ISBLANK('DPW3'!DA23),"",'DPW3'!DA23) | ¬¬IF(ISBLANK('DPW3'!DB23),"",'DPW3'!DB23) | ¬¬IF(ISBLANK('DPW3'!DC23),"",'DPW3'!DC23) | ¬¬IF(ISBLANK('DPW3'!DD23),"",'DPW3'!DD23) | ¬¬IF(ISBLANK('DPW3'!DE23),"",'DPW3'!DE23) | ¬¬IF(ISBLANK('DPW3'!DF23),"",'DPW3'!DF23) | ¬¬IF(ISBLANK('DPW3'!DG23),"",'DPW3'!DG23) | ¬¬IF(ISBLANK('DPW3'!DH23),"",'DPW3'!DH23) | ¬¬IF(ISBLANK('DPW3'!DI23),"",'DPW3'!DI23) | ¬¬IF(ISBLANK('DPW3'!DJ23),"",'DPW3'!DJ23) | ¬¬IF(ISBLANK('DPW3'!DK23),"",'DPW3'!DK23) | ¬¬IF(ISBLANK('DPW3'!DL23),"",'DPW3'!DL23) | ¬¬IF(ISBLANK('DPW3'!DM23),"",'DPW3'!DM23) | ¬¬IF(ISBLANK('DPW3'!DN23),"",'DPW3'!DN23) | ¬¬IF(ISBLANK('DPW3'!DO23),"",'DPW3'!DO23) | ¬¬IF(ISBLANK('DPW3'!DP23),"",'DPW3'!DP23) | ¬¬IF(ISBLANK('DPW3'!DQ23),"",'DPW3'!DQ23) | ¬¬IF(ISBLANK('DPW3'!DR23),"",'DPW3'!DR23) | ¬¬IF(ISBLANK('DPW3'!DS23),"",'DPW3'!DS23) | ¬¬IF(ISBLANK('DPW3'!DT23),"",'DPW3'!DT23) | ¬¬IF(ISBLANK('DPW3'!DU23),"",'DPW3'!DU23) | ¬¬IF(ISBLANK('DPW3'!DV23),"",'DPW3'!DV23) | ¬¬IF(ISBLANK('DPW3'!DW23),"",'DPW3'!DW23) | ¬¬IF(ISBLANK('DPW3'!DX23),"",'DPW3'!DX23) | ¬¬IF(ISBLANK('DPW3'!DY23),"",'DPW3'!DY23) | ¬¬IF(ISBLANK('DPW3'!DZ23),"",'DPW3'!DZ23) | ¬¬IF(ISBLANK('DPW3'!EA23),"",'DPW3'!EA23) | ¬¬IF(ISBLANK('DPW3'!EB23),"",'DPW3'!EB23) | ¬¬IF(ISBLANK('DPW3'!EC23),"",'DPW3'!EC23) | ¬¬IF(ISBLANK('DPW3'!ED23),"",'DPW3'!ED23)
¬¬A1634 | ¬¬IF(ISBLANK('DPW3'!RO23),"",'DPW3'!RO23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!RO7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!EF23),"",'DPW3'!EF23) | ¬¬IF(ISBLANK('DPW3'!EG23),"",'DPW3'!EG23) | ¬¬IF(ISBLANK('DPW3'!EH23),"",'DPW3'!EH23) | ¬¬IF(ISBLANK('DPW3'!EI23),"",'DPW3'!EI23) | ¬¬IF(ISBLANK('DPW3'!EJ23),"",'DPW3'!EJ23) | ¬¬IF(ISBLANK('DPW3'!EK23),"",'DPW3'!EK23) | ¬¬IF(ISBLANK('DPW3'!EL23),"",'DPW3'!EL23) | ¬¬IF(ISBLANK('DPW3'!EM23),"",'DPW3'!EM23) | ¬¬IF(ISBLANK('DPW3'!EN23),"",'DPW3'!EN23) | ¬¬IF(ISBLANK('DPW3'!EO23),"",'DPW3'!EO23) | ¬¬IF(ISBLANK('DPW3'!EP23),"",'DPW3'!EP23) | ¬¬IF(ISBLANK('DPW3'!EQ23),"",'DPW3'!EQ23) | ¬¬IF(ISBLANK('DPW3'!ER23),"",'DPW3'!ER23) | ¬¬IF(ISBLANK('DPW3'!ES23),"",'DPW3'!ES23) | ¬¬IF(ISBLANK('DPW3'!ET23),"",'DPW3'!ET23) | ¬¬IF(ISBLANK('DPW3'!EU23),"",'DPW3'!EU23) | ¬¬IF(ISBLANK('DPW3'!EV23),"",'DPW3'!EV23) | ¬¬IF(ISBLANK('DPW3'!EW23),"",'DPW3'!EW23) | ¬¬IF(ISBLANK('DPW3'!EX23),"",'DPW3'!EX23) | ¬¬IF(ISBLANK('DPW3'!EY23),"",'DPW3'!EY23) | ¬¬IF(ISBLANK('DPW3'!EZ23),"",'DPW3'!EZ23) | ¬¬IF(ISBLANK('DPW3'!FA23),"",'DPW3'!FA23) | ¬¬IF(ISBLANK('DPW3'!FB23),"",'DPW3'!FB23) | ¬¬IF(ISBLANK('DPW3'!FC23),"",'DPW3'!FC23) | ¬¬IF(ISBLANK('DPW3'!FD23),"",'DPW3'!FD23) | ¬¬IF(ISBLANK('DPW3'!FE23),"",'DPW3'!FE23) | ¬¬IF(ISBLANK('DPW3'!FF23),"",'DPW3'!FF23) | ¬¬IF(ISBLANK('DPW3'!FG23),"",'DPW3'!FG23) | ¬¬IF(ISBLANK('DPW3'!FH23),"",'DPW3'!FH23) | ¬¬IF(ISBLANK('DPW3'!FI23),"",'DPW3'!FI23) | ¬¬IF(ISBLANK('DPW3'!FJ23),"",'DPW3'!FJ23) | ¬¬IF(ISBLANK('DPW3'!FK23),"",'DPW3'!FK23) | ¬¬IF(ISBLANK('DPW3'!FL23),"",'DPW3'!FL23) | ¬¬IF(ISBLANK('DPW3'!FM23),"",'DPW3'!FM23) | ¬¬IF(ISBLANK('DPW3'!FN23),"",'DPW3'!FN23) | ¬¬IF(ISBLANK('DPW3'!FO23),"",'DPW3'!FO23) | ¬¬IF(ISBLANK('DPW3'!FP23),"",'DPW3'!FP23) | ¬¬IF(ISBLANK('DPW3'!FQ23),"",'DPW3'!FQ23) | ¬¬IF(ISBLANK('DPW3'!FR23),"",'DPW3'!FR23) | ¬¬IF(ISBLANK('DPW3'!FS23),"",'DPW3'!FS23)
¬¬A1635 | ¬¬IF(ISBLANK('DPW3'!TD23),"",'DPW3'!TD23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!TD7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!FU23),"",'DPW3'!FU23) | ¬¬IF(ISBLANK('DPW3'!FV23),"",'DPW3'!FV23) | ¬¬IF(ISBLANK('DPW3'!FW23),"",'DPW3'!FW23) | ¬¬IF(ISBLANK('DPW3'!FX23),"",'DPW3'!FX23) | ¬¬IF(ISBLANK('DPW3'!FY23),"",'DPW3'!FY23) | ¬¬IF(ISBLANK('DPW3'!FZ23),"",'DPW3'!FZ23) | ¬¬IF(ISBLANK('DPW3'!GA23),"",'DPW3'!GA23) | ¬¬IF(ISBLANK('DPW3'!GB23),"",'DPW3'!GB23) | ¬¬IF(ISBLANK('DPW3'!GC23),"",'DPW3'!GC23) | ¬¬IF(ISBLANK('DPW3'!GD23),"",'DPW3'!GD23) | ¬¬IF(ISBLANK('DPW3'!GE23),"",'DPW3'!GE23) | ¬¬IF(ISBLANK('DPW3'!GF23),"",'DPW3'!GF23) | ¬¬IF(ISBLANK('DPW3'!GG23),"",'DPW3'!GG23) | ¬¬IF(ISBLANK('DPW3'!GH23),"",'DPW3'!GH23) | ¬¬IF(ISBLANK('DPW3'!GI23),"",'DPW3'!GI23) | ¬¬IF(ISBLANK('DPW3'!GJ23),"",'DPW3'!GJ23) | ¬¬IF(ISBLANK('DPW3'!GK23),"",'DPW3'!GK23) | ¬¬IF(ISBLANK('DPW3'!GL23),"",'DPW3'!GL23) | ¬¬IF(ISBLANK('DPW3'!GM23),"",'DPW3'!GM23) | ¬¬IF(ISBLANK('DPW3'!GN23),"",'DPW3'!GN23) | ¬¬IF(ISBLANK('DPW3'!GO23),"",'DPW3'!GO23) | ¬¬IF(ISBLANK('DPW3'!GP23),"",'DPW3'!GP23) | ¬¬IF(ISBLANK('DPW3'!GQ23),"",'DPW3'!GQ23) | ¬¬IF(ISBLANK('DPW3'!GR23),"",'DPW3'!GR23) | ¬¬IF(ISBLANK('DPW3'!GS23),"",'DPW3'!GS23) | ¬¬IF(ISBLANK('DPW3'!GT23),"",'DPW3'!GT23) | ¬¬IF(ISBLANK('DPW3'!GU23),"",'DPW3'!GU23) | ¬¬IF(ISBLANK('DPW3'!GV23),"",'DPW3'!GV23) | ¬¬IF(ISBLANK('DPW3'!GW23),"",'DPW3'!GW23) | ¬¬IF(ISBLANK('DPW3'!GX23),"",'DPW3'!GX23) | ¬¬IF(ISBLANK('DPW3'!GY23),"",'DPW3'!GY23) | ¬¬IF(ISBLANK('DPW3'!GZ23),"",'DPW3'!GZ23) | ¬¬IF(ISBLANK('DPW3'!HA23),"",'DPW3'!HA23) | ¬¬IF(ISBLANK('DPW3'!HB23),"",'DPW3'!HB23) | ¬¬IF(ISBLANK('DPW3'!HC23),"",'DPW3'!HC23) | ¬¬IF(ISBLANK('DPW3'!HD23),"",'DPW3'!HD23) | ¬¬IF(ISBLANK('DPW3'!HE23),"",'DPW3'!HE23) | ¬¬IF(ISBLANK('DPW3'!HF23),"",'DPW3'!HF23) | ¬¬IF(ISBLANK('DPW3'!HG23),"",'DPW3'!HG23) | ¬¬IF(ISBLANK('DPW3'!HH23),"",'DPW3'!HH23)
¬¬A1636 | ¬¬IF(ISBLANK('DPW3'!US23),"",'DPW3'!US23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!US7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!HJ23),"",'DPW3'!HJ23) | ¬¬IF(ISBLANK('DPW3'!HK23),"",'DPW3'!HK23) | ¬¬IF(ISBLANK('DPW3'!HL23),"",'DPW3'!HL23) | ¬¬IF(ISBLANK('DPW3'!HM23),"",'DPW3'!HM23) | ¬¬IF(ISBLANK('DPW3'!HN23),"",'DPW3'!HN23) | ¬¬IF(ISBLANK('DPW3'!HO23),"",'DPW3'!HO23) | ¬¬IF(ISBLANK('DPW3'!HP23),"",'DPW3'!HP23) | ¬¬IF(ISBLANK('DPW3'!HQ23),"",'DPW3'!HQ23) | ¬¬IF(ISBLANK('DPW3'!HR23),"",'DPW3'!HR23) | ¬¬IF(ISBLANK('DPW3'!HS23),"",'DPW3'!HS23) | ¬¬IF(ISBLANK('DPW3'!HT23),"",'DPW3'!HT23) | ¬¬IF(ISBLANK('DPW3'!HU23),"",'DPW3'!HU23) | ¬¬IF(ISBLANK('DPW3'!HV23),"",'DPW3'!HV23) | ¬¬IF(ISBLANK('DPW3'!HW23),"",'DPW3'!HW23) | ¬¬IF(ISBLANK('DPW3'!HX23),"",'DPW3'!HX23) | ¬¬IF(ISBLANK('DPW3'!HY23),"",'DPW3'!HY23) | ¬¬IF(ISBLANK('DPW3'!HZ23),"",'DPW3'!HZ23) | ¬¬IF(ISBLANK('DPW3'!IA23),"",'DPW3'!IA23) | ¬¬IF(ISBLANK('DPW3'!IB23),"",'DPW3'!IB23) | ¬¬IF(ISBLANK('DPW3'!IC23),"",'DPW3'!IC23) | ¬¬IF(ISBLANK('DPW3'!ID23),"",'DPW3'!ID23) | ¬¬IF(ISBLANK('DPW3'!IE23),"",'DPW3'!IE23) | ¬¬IF(ISBLANK('DPW3'!IF23),"",'DPW3'!IF23) | ¬¬IF(ISBLANK('DPW3'!IG23),"",'DPW3'!IG23) | ¬¬IF(ISBLANK('DPW3'!IH23),"",'DPW3'!IH23) | ¬¬IF(ISBLANK('DPW3'!II23),"",'DPW3'!II23) | ¬¬IF(ISBLANK('DPW3'!IJ23),"",'DPW3'!IJ23) | ¬¬IF(ISBLANK('DPW3'!IK23),"",'DPW3'!IK23) | ¬¬IF(ISBLANK('DPW3'!IL23),"",'DPW3'!IL23) | ¬¬IF(ISBLANK('DPW3'!IM23),"",'DPW3'!IM23) | ¬¬IF(ISBLANK('DPW3'!IN23),"",'DPW3'!IN23) | ¬¬IF(ISBLANK('DPW3'!IO23),"",'DPW3'!IO23) | ¬¬IF(ISBLANK('DPW3'!IP23),"",'DPW3'!IP23) | ¬¬IF(ISBLANK('DPW3'!IQ23),"",'DPW3'!IQ23) | ¬¬IF(ISBLANK('DPW3'!IR23),"",'DPW3'!IR23) | ¬¬IF(ISBLANK('DPW3'!IS23),"",'DPW3'!IS23) | ¬¬IF(ISBLANK('DPW3'!IT23),"",'DPW3'!IT23) | ¬¬IF(ISBLANK('DPW3'!IU23),"",'DPW3'!IU23) | ¬¬IF(ISBLANK('DPW3'!IV23),"",'DPW3'!IV23) | ¬¬IF(ISBLANK('DPW3'!IW23),"",'DPW3'!IW23)
¬¬A1637 | ¬¬IF(ISBLANK('DPW3'!WH23),"",'DPW3'!WH23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!WH7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!IY23),"",'DPW3'!IY23) | ¬¬IF(ISBLANK('DPW3'!IZ23),"",'DPW3'!IZ23) | ¬¬IF(ISBLANK('DPW3'!JA23),"",'DPW3'!JA23) | ¬¬IF(ISBLANK('DPW3'!JB23),"",'DPW3'!JB23) | ¬¬IF(ISBLANK('DPW3'!JC23),"",'DPW3'!JC23) | ¬¬IF(ISBLANK('DPW3'!JD23),"",'DPW3'!JD23) | ¬¬IF(ISBLANK('DPW3'!JE23),"",'DPW3'!JE23) | ¬¬IF(ISBLANK('DPW3'!JF23),"",'DPW3'!JF23) | ¬¬IF(ISBLANK('DPW3'!JG23),"",'DPW3'!JG23) | ¬¬IF(ISBLANK('DPW3'!JH23),"",'DPW3'!JH23) | ¬¬IF(ISBLANK('DPW3'!JI23),"",'DPW3'!JI23) | ¬¬IF(ISBLANK('DPW3'!JJ23),"",'DPW3'!JJ23) | ¬¬IF(ISBLANK('DPW3'!JK23),"",'DPW3'!JK23) | ¬¬IF(ISBLANK('DPW3'!JL23),"",'DPW3'!JL23) | ¬¬IF(ISBLANK('DPW3'!JM23),"",'DPW3'!JM23) | ¬¬IF(ISBLANK('DPW3'!JN23),"",'DPW3'!JN23) | ¬¬IF(ISBLANK('DPW3'!JO23),"",'DPW3'!JO23) | ¬¬IF(ISBLANK('DPW3'!JP23),"",'DPW3'!JP23) | ¬¬IF(ISBLANK('DPW3'!JQ23),"",'DPW3'!JQ23) | ¬¬IF(ISBLANK('DPW3'!JR23),"",'DPW3'!JR23) | ¬¬IF(ISBLANK('DPW3'!JS23),"",'DPW3'!JS23) | ¬¬IF(ISBLANK('DPW3'!JT23),"",'DPW3'!JT23) | ¬¬IF(ISBLANK('DPW3'!JU23),"",'DPW3'!JU23) | ¬¬IF(ISBLANK('DPW3'!JV23),"",'DPW3'!JV23) | ¬¬IF(ISBLANK('DPW3'!JW23),"",'DPW3'!JW23) | ¬¬IF(ISBLANK('DPW3'!JX23),"",'DPW3'!JX23) | ¬¬IF(ISBLANK('DPW3'!JY23),"",'DPW3'!JY23) | ¬¬IF(ISBLANK('DPW3'!JZ23),"",'DPW3'!JZ23) | ¬¬IF(ISBLANK('DPW3'!KA23),"",'DPW3'!KA23) | ¬¬IF(ISBLANK('DPW3'!KB23),"",'DPW3'!KB23) | ¬¬IF(ISBLANK('DPW3'!KC23),"",'DPW3'!KC23) | ¬¬IF(ISBLANK('DPW3'!KD23),"",'DPW3'!KD23) | ¬¬IF(ISBLANK('DPW3'!KE23),"",'DPW3'!KE23) | ¬¬IF(ISBLANK('DPW3'!KF23),"",'DPW3'!KF23) | ¬¬IF(ISBLANK('DPW3'!KG23),"",'DPW3'!KG23) | ¬¬IF(ISBLANK('DPW3'!KH23),"",'DPW3'!KH23) | ¬¬IF(ISBLANK('DPW3'!KI23),"",'DPW3'!KI23) | ¬¬IF(ISBLANK('DPW3'!KJ23),"",'DPW3'!KJ23) | ¬¬IF(ISBLANK('DPW3'!KK23),"",'DPW3'!KK23) | ¬¬IF(ISBLANK('DPW3'!KL23),"",'DPW3'!KL23)
¬¬A1638 | ¬¬IF(ISBLANK('DPW3'!XW23),"",'DPW3'!XW23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!XW7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | [15 empty] | ¬¬IF(ISBLANK('DPW3'!KN23),"",'DPW3'!KN23) | ¬¬IF(ISBLANK('DPW3'!KO23),"",'DPW3'!KO23) | ¬¬IF(ISBLANK('DPW3'!KP23),"",'DPW3'!KP23) | ¬¬IF(ISBLANK('DPW3'!KQ23),"",'DPW3'!KQ23) | ¬¬IF(ISBLANK('DPW3'!KR23),"",'DPW3'!KR23) | ¬¬IF(ISBLANK('DPW3'!KS23),"",'DPW3'!KS23) | ¬¬IF(ISBLANK('DPW3'!KT23),"",'DPW3'!KT23) | ¬¬IF(ISBLANK('DPW3'!KU23),"",'DPW3'!KU23) | ¬¬IF(ISBLANK('DPW3'!KV23),"",'DPW3'!KV23) | ¬¬IF(ISBLANK('DPW3'!KW23),"",'DPW3'!KW23) | ¬¬IF(ISBLANK('DPW3'!KX23),"",'DPW3'!KX23) | ¬¬IF(ISBLANK('DPW3'!KY23),"",'DPW3'!KY23) | ¬¬IF(ISBLANK('DPW3'!KZ23),"",'DPW3'!KZ23) | ¬¬IF(ISBLANK('DPW3'!LA23),"",'DPW3'!LA23) | ¬¬IF(ISBLANK('DPW3'!LB23),"",'DPW3'!LB23) | ¬¬IF(ISBLANK('DPW3'!LC23),"",'DPW3'!LC23) | ¬¬IF(ISBLANK('DPW3'!LD23),"",'DPW3'!LD23) | ¬¬IF(ISBLANK('DPW3'!LE23),"",'DPW3'!LE23) | ¬¬IF(ISBLANK('DPW3'!LF23),"",'DPW3'!LF23) | ¬¬IF(ISBLANK('DPW3'!LG23),"",'DPW3'!LG23) | ¬¬IF(ISBLANK('DPW3'!LH23),"",'DPW3'!LH23) | ¬¬IF(ISBLANK('DPW3'!LI23),"",'DPW3'!LI23) | ¬¬IF(ISBLANK('DPW3'!LJ23),"",'DPW3'!LJ23) | ¬¬IF(ISBLANK('DPW3'!LK23),"",'DPW3'!LK23) | ¬¬IF(ISBLANK('DPW3'!LL23),"",'DPW3'!LL23) | ¬¬IF(ISBLANK('DPW3'!LM23),"",'DPW3'!LM23) | ¬¬IF(ISBLANK('DPW3'!LN23),"",'DPW3'!LN23) | ¬¬IF(ISBLANK('DPW3'!LO23),"",'DPW3'!LO23) | ¬¬IF(ISBLANK('DPW3'!LP23),"",'DPW3'!LP23) | ¬¬IF(ISBLANK('DPW3'!LQ23),"",'DPW3'!LQ23) | ¬¬IF(ISBLANK('DPW3'!LR23),"",'DPW3'!LR23) | ¬¬IF(ISBLANK('DPW3'!LS23),"",'DPW3'!LS23) | ¬¬IF(ISBLANK('DPW3'!LT23),"",'DPW3'!LT23) | ¬¬IF(ISBLANK('DPW3'!LU23),"",'DPW3'!LU23) | ¬¬IF(ISBLANK('DPW3'!LV23),"",'DPW3'!LV23) | ¬¬IF(ISBLANK('DPW3'!LW23),"",'DPW3'!LW23) | ¬¬IF(ISBLANK('DPW3'!LX23),"",'DPW3'!LX23) | ¬¬IF(ISBLANK('DPW3'!LY23),"",'DPW3'!LY23) | ¬¬IF(ISBLANK('DPW3'!LZ23),"",'DPW3'!LZ23) | ¬¬IF(ISBLANK('DPW3'!MA23),"",'DPW3'!MA23)
¬¬A1639 | ¬¬IF(ISBLANK('DPW3'!ZL23),"",'DPW3'!ZL23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZL7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MC23),"",'DPW3'!MC23)
¬¬A1640 | ¬¬IF(ISBLANK('DPW3'!ZM23),"",'DPW3'!ZM23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZM7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MD23),"",'DPW3'!MD23)
¬¬A1641 | ¬¬IF(ISBLANK('DPW3'!ZN23),"",'DPW3'!ZN23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZN7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!ML23),"",'DPW3'!ML23)
¬¬A1642 | ¬¬IF(ISBLANK('DPW3'!ZO23),"",'DPW3'!ZO23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZO7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MF23),"",'DPW3'!MF23)
¬¬A1643 | ¬¬IF(ISBLANK('DPW3'!ZP23),"",'DPW3'!ZP23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZP7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MG23),"",'DPW3'!MG23)
¬¬A1644 | ¬¬IF(ISBLANK('DPW3'!ZQ23),"",'DPW3'!ZQ23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZQ7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MH23),"",'DPW3'!MH23)
¬¬A1645 | ¬¬IF(ISBLANK('DPW3'!ZR23),"",'DPW3'!ZR23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZR7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MI23),"",'DPW3'!MI23)
¬¬A1646 | ¬¬IF(ISBLANK('DPW3'!ZS23),"",'DPW3'!ZS23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZS7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ23),"",'DPW3'!MJ23)
¬¬A1647 | ¬¬IF(ISBLANK('DPW3'!ZT23),"",'DPW3'!ZT23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZT7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MK23),"",'DPW3'!MK23)
¬¬A1648 | ¬¬IF(ISBLANK('DPW3'!ZV23),"",'DPW3'!ZV23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZV7 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MM23),"",'DPW3'!MM23)
¬¬A1649 | ¬¬IF(ISBLANK('DPW3'!ZS23),"",'DPW3'!ZS23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZS5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MJ23),"",'DPW3'!MJ23)
¬¬A1650 | ¬¬IF(ISBLANK('DPW3'!ZT23),"",'DPW3'!ZT23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZT5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MK23),"",'DPW3'!MK23)
¬¬A1651 | ¬¬IF(ISBLANK('DPW3'!ZV23),"",'DPW3'!ZV23) | ¬¬'DPW3'!F23 & "," & 'DPW3'!G23 & "," & 'DPW3'!ZV5 | ¬¬IF(ISBLANK('DPW3'!H23),"",'DPW3'!H23) | Delta | ¬¬IF(ISBLANK('DPW3'!MM23),"",'DPW3'!MM23)

## F_Outputs
PDC_Draft Data
Acronym | Reference | Item description | Unit | Model | Constant | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2025-30 | 2024-25 Q4 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | 2030-31 Q1 | 2030-31 Q2 | 2030-31 Q3 | 2030-31 Q4 | 2031-32 Q1 | 2031-32 Q2 | 2031-32 Q3 | 2031-32 Q4 | 2032-33 Q1 | 2032-33 Q2 | 2032-33 Q3 | 2032-33 Q4 | 2033-34 Q1 | 2033-34 Q2 | 2033-34 Q3 | 2033-34 Q4 | 2034-35 Q1 | 2034-35 Q2 | 2034-35 Q3 | 2034-35 Q4
TMS | PCD_DPB1_MRBASE | Mains renewals - base,Base wholesale water model funded renewals in kilometres,PCD output (cumulative) - Target | km | Delta |  |  |  | 73.2344 | 170.8802 | 292.9374 | 390.5832 | 488.229
TMS | PCD_DPB1_MRBASE_T | Mains renewals - base,Base wholesale water model funded renewals in kilometres,PCD output by 2029-30 (Target) | km | Delta | [7 empty] | 488.229 |  |  |  |  | 0
TMS | PCD_DPB1_MRBASE_O | Mains renewals - base,Base wholesale water model funded renewals in kilometres,PCD output (cumulative) - Outturn & Forecast | km | Delta |  |  |  | 78.0343 | 170.9263 | 273.0143 | 379.0233 | 488.3793
TMS | PCD_DPB1_MRBASE_OT | Mains renewals - base,Base wholesale water model funded renewals in kilometres,PCD output by 2029-30 (Outturn & Forecast) | km | Delta | [7 empty] | 488.3793 |  |  |  |  | 0
TMS | PCD_DPB1_MRBASE_P | Mains renewals - base,Base wholesale water model funded renewals in kilometres,Performance | km | Delta | [7 empty] | 1.0003
TMS | PCD_DPB1_MRAH | Mains renewals - asset health adjustment,Base asset health adjustment renewals in kilometres,PCD output (cumulative) - Target | km | Delta |  |  |  | 9.1088 | 21.2538 | 36.4351 | 48.5801 | 60.7251
TMS | PCD_DPB1_MRAH_T | Mains renewals - asset health adjustment,Base asset health adjustment renewals in kilometres,PCD output by 2029-30 (Target) | km | Delta | [7 empty] | 60.7251 |  |  |  |  | 0
TMS | PCD_DPB1_MRAH_O | Mains renewals - asset health adjustment,Base asset health adjustment renewals in kilometres,PCD output (cumulative) - Outturn & Forecast | km | Delta |  |  |  | 7.424 | 23.141 | 35.637 | 48.837 | 62.637
TMS | PCD_DPB1_MRAH_OT | Mains renewals - asset health adjustment,Base asset health adjustment renewals in kilometres,PCD output by 2029-30 (Outturn & Forecast) | km | Delta | [7 empty] | 62.637 |  |  |  |  | 0
TMS | PCD_DPB1_MRAH_P | Mains renewals - asset health adjustment,Base asset health adjustment renewals in kilometres,Performance | km | Delta | [7 empty] | 1.0315
TMS | PCD_DPB1_MRENHLEA | Mains renewals - enhancement leakage,Enhancement leakage renewals in kilometres,PCD output (cumulative) - Target | km | Delta |  |  |  | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPB1_MRENHLEA_T | Mains renewals - enhancement leakage,Enhancement leakage renewals in kilometres,PCD output by 2029-30 (Target) | km | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPB1_MRENHLEA_O | Mains renewals - enhancement leakage,Enhancement leakage renewals in kilometres,PCD output (cumulative) - Outturn & Forecast | km | Delta
TMS | PCD_DPB1_MRENHLEA_OT | Mains renewals - enhancement leakage,Enhancement leakage renewals in kilometres,PCD output by 2029-30 (Outturn & Forecast) | km | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPB1_MRENHLEA_P | Mains renewals - enhancement leakage,Enhancement leakage renewals in kilometres,Performance | km | Delta
TMS | PCD_DPB2_MR_BASE | Mains renewals - base,Base wholesale water model funded renewals expenditure,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 55.5668 | 129.656 | 222.2674 | 296.3565 | 370.4457
TMS | PCD_DPB2_MR_BASE_T | Mains renewals - base,Base wholesale water model funded renewals expenditure,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 370.4457 |  |  |  |  | 0
TMS | PCD_DPB2_MR_BASE_O | Mains renewals - base,Base wholesale water model funded renewals expenditure,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  |  |  | 86.3121 | 208.6979 | 335.6396 | 472.7817 | 612.5975
TMS | PCD_DPB2_MR_BASE_OT | Mains renewals - base,Base wholesale water model funded renewals expenditure,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 612.5975 |  |  |  |  | 0
TMS | PCD_DPB2_MR_BASE_P | Mains renewals - base,Base wholesale water model funded renewals expenditure,Performance | £m | Delta | [7 empty] | 1.6537
TMS | PCD_DPB2_MR_AH | Mains renewals - asset health adjustment,Base asset health adjustment renewals expenditure,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 10.5203 | 24.5474 | 42.0812 | 56.1083 | 70.1354
TMS | PCD_DPB2_MR_AH_T | Mains renewals - asset health adjustment,Base asset health adjustment renewals expenditure,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 70.1354 |  |  |  |  | 0
TMS | PCD_DPB2_MR_AH_O | Mains renewals - asset health adjustment,Base asset health adjustment renewals expenditure,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  |  |  | 14.6163 | 34.0702 | 51.7424 | 71.7946 | 93.613
TMS | PCD_DPB2_MR_AH_OT | Mains renewals - asset health adjustment,Base asset health adjustment renewals expenditure,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 93.613 |  |  |  |  | 0
TMS | PCD_DPB2_MR_AH_P | Mains renewals - asset health adjustment,Base asset health adjustment renewals expenditure,Performance | £m | Delta | [7 empty] | 1.3347
TMS | PCD_DPB2_MR_ENHLEA | Mains renewals - enhancement leakage,Enhancement leakage renewals expenditure,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta | [7 empty] | 0
TMS | PCD_DPB2_MR_ENHLEA_T | Mains renewals - enhancement leakage,Enhancement leakage renewals expenditure,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPB2_MR_ENHLEA_O | Mains renewals - enhancement leakage,Enhancement leakage renewals expenditure,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPB2_MR_ENHLEA_OT | Mains renewals - enhancement leakage,Enhancement leakage renewals expenditure,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPB2_MR_ENHLEA_P | Mains renewals - enhancement leakage,Enhancement leakage renewals expenditure,Performance | £m | Delta
TMS | PCD_DPB2_WN_RFT | Water network reinforcement,Water network reinforcement expenditure,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 31.5204 | 62.7508 | 94.0153 | 125.1037 | 155.9137
TMS | PCD_DPB2_WN_RFT_T | Water network reinforcement,Water network reinforcement expenditure,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 155.9137 |  |  |  |  | 0
TMS | PCD_DPB2_WN_RFT_O | Water network reinforcement,Water network reinforcement expenditure,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  |  |  | 28.1695 | 66.4617 | 92.9814 | 123.1365 | 157.2182
TMS | PCD_DPB2_WN_RFT_OT | Water network reinforcement,Water network reinforcement expenditure,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 157.2182 |  |  |  |  | 0
TMS | PCD_DPB2_WN_RFT_P | Water network reinforcement,Water network reinforcement expenditure,Performance | £m | Delta | [7 empty] | 1.0084
TMS | PCD_DPB2_WWN_RFT | Wastewater network reinforcement,Wastewater network reinforcement expenditure,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 24.5146 | 48.9294 | 73.2562 | 97.5065 | 121.6776
TMS | PCD_DPB2_WWN_RFT_T | Wastewater network reinforcement,Wastewater network reinforcement expenditure,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 121.6776 |  |  |  |  | 0
TMS | PCD_DPB2_WWN_RFT_O | Wastewater network reinforcement,Wastewater network reinforcement expenditure,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  |  |  | 18.1407 | 56.8485 | 79.009 | 99.9376 | 122.8328
TMS | PCD_DPB2_WWN_RFT_OT | Wastewater network reinforcement,Wastewater network reinforcement expenditure,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 122.8328 |  |  |  |  | 0
TMS | PCD_DPB2_WWN_RFT_P | Wastewater network reinforcement,Wastewater network reinforcement expenditure,Performance | £m | Delta | [7 empty] | 1.0095
TMS | PCD_DPWW1_FMS | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_FMS_T | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_FMS_O | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_FMS_OT | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_FMS_P | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,Performance | Nr | Delta
TMS | PCD_DPWW1_FMC | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_FMC_T | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_FMC_O | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_FMC_OT | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_FMC_P | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,Performance | Nr | Delta
TMS | PCD_DPWW1_CWQM | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_CWQM_T | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CWQM_O | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_CWQM_OT | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_CWQM_P | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),Performance | Nr | Delta
TMS | PCD_DPWW1_SPSO1 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 0 | 26 | 26 | 26 | 26
TMS | PCD_DPWW1_SPSO1_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 26 |  |  |  |  | 0
TMS | PCD_DPWW1_SPSO1_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,PCD output (cumulative) - Outturn & Forecast | Nr | Delta | [7 empty] | 10 | 10 | 10 | 10 | 10 | 10
TMS | PCD_DPWW1_SPSO1_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 10 |  |  |  |  | 10
TMS | PCD_DPWW1_SPSO1_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,Performance | Nr | Delta | [7 empty] | 0.38462
TMS | PCD_DPWW1_SPSO2 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_SPSO2_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_SPSO2_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_SPSO2_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_SPSO2_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,Performance | Nr | Delta
TMS | PCD_DPWW1_SPSO3 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_SPSO3_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_SPSO3_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_SPSO3_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_SPSO3_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,Performance | Nr | Delta
TMS | PCD_DPWW1_SPSO4 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 0 | 17.1852 | 17.1852 | 17.1852 | 22
TMS | PCD_DPWW1_SPSO4_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 22 |  |  |  |  | 0
TMS | PCD_DPWW1_SPSO4_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,PCD output (cumulative) - Outturn & Forecast | Nr | Delta | [7 empty] | 38 | 38 | 38 | 38 | 38 | 38
TMS | PCD_DPWW1_SPSO4_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 38 |  |  |  |  | 38
TMS | PCD_DPWW1_SPSO4_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,Performance | Nr | Delta | [7 empty] | 1.7273
TMS | PCD_DPWW1_SPSO5 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_SPSO5_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_SPSO5_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_SPSO5_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_SPSO5_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,Performance | Nr | Delta
TMS | PCD_DPWW1_SOFW1 | Storm Overflow - Wetland,Number of schemes,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 0 | 0 | 0 | 3 | 6
TMS | PCD_DPWW1_SOFW1_T | Storm Overflow - Wetland,Number of schemes,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 6 |  |  |  |  | 0
TMS | PCD_DPWW1_SOFW1_O | Storm Overflow - Wetland,Number of schemes,PCD output (cumulative) - Outturn & Forecast | Nr | Delta | [6 empty] | 2 | 2 | 3 | 3 | 6 | 6 | 6
TMS | PCD_DPWW1_SOFW1_OT | Storm Overflow - Wetland,Number of schemes,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 2 |  |  |  |  | 6
TMS | PCD_DPWW1_SOFW1_P | Storm Overflow - Wetland,Number of schemes,Performance | Nr | Delta | [7 empty] | 0.33333
TMS | PCD_DPWW1_SOFW2 | Storm Overflow - Wetland,Wetland area delivered,PCD output (cumulative) - Target` | ha | Delta |  |  |  | 0 | 0 | 0 | 2.83 | 7.931
TMS | PCD_DPWW1_SOFW2_T | Storm Overflow - Wetland,Wetland area delivered,PCD output by 2029-30 (Target) | ha | Delta | [7 empty] | 7.931 |  |  |  |  | 0
TMS | PCD_DPWW1_SOFW2_O | Storm Overflow - Wetland,Wetland area delivered,PCD output (cumulative) - Outturn & Forecast | ha | Delta | [6 empty] | 2.361 | 2.361 | 2.83 | 2.83 | 7.931 | 7.931 | 7.931
TMS | PCD_DPWW1_SOFW2_OT | Storm Overflow - Wetland,Wetland area delivered,PCD output by 2029-30 (Outturn & Forecast) | ha | Delta | [7 empty] | 2.361 |  |  |  |  | 7.931
TMS | PCD_DPWW1_SOFW2_P | Storm Overflow - Wetland,Wetland area delivered,Performance | ha | Delta | [7 empty] | 0.29769
TMS | PCD_DPWW1_SOFS | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_SOFS_T | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_SOFS_O | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_SOFS_OT | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_SOFS_P | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,Performance | Nr | Delta
TMS | PCD_DPWW1_TCR1 | Treatment for chemical removal (WINEP/NEP),Total number of schemes with a treatment solution delivered to meet compliance,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 0 | 0 | 0 | 0 | 7
TMS | PCD_DPWW1_TCR1_T | Treatment for chemical removal (WINEP/NEP),Total number of schemes with a treatment solution delivered to meet compliance,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 7 |  |  |  |  | 0
TMS | PCD_DPWW1_TCR1_O | Treatment for chemical removal (WINEP/NEP),Total number of schemes with a treatment solution delivered to meet compliance,PCD output (cumulative) - Outturn & Forecast | Nr | Delta | [8 empty] | 3 | 4 | 5 | 7 | 7
TMS | PCD_DPWW1_TCR1_OT | Treatment for chemical removal (WINEP/NEP),Total number of schemes with a treatment solution delivered to meet compliance,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [12 empty] | 7
TMS | PCD_DPWW1_TCR1_P | Treatment for chemical removal (WINEP/NEP),Total number of schemes with a treatment solution delivered to meet compliance,Performance | Nr | Delta
TMS | PCD_DPWW1_TCR2 | Treatment for chemical removal (WINEP/NEP),Population equivalent served by schemes with a treatment solution being delivered to meet compliance,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 0 | 0 | 0 | 0 | 243105
TMS | PCD_DPWW1_TCR2_T | Treatment for chemical removal (WINEP/NEP),Population equivalent served by schemes with a treatment solution being delivered to meet compliance,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 243105 |  |  |  |  | 0
TMS | PCD_DPWW1_TCR2_O | Treatment for chemical removal (WINEP/NEP),Population equivalent served by schemes with a treatment solution being delivered to meet compliance,PCD output (cumulative) - Outturn & Forecast | Nr | Delta | [8 empty] | 17473 | 33539 | 113791 | 243105 | 243105
TMS | PCD_DPWW1_TCR2_OT | Treatment for chemical removal (WINEP/NEP),Population equivalent served by schemes with a treatment solution being delivered to meet compliance,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [12 empty] | 243105
TMS | PCD_DPWW1_TCR2_P | Treatment for chemical removal (WINEP/NEP),Population equivalent served by schemes with a treatment solution being delivered to meet compliance,Performance | Nr | Delta
TMS | PCD_DPWW1_TNR1 | Treatment for total nitrogen removal (WINEP/NEP) ,Total number of schemes delivered to meet compliance,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_TNR1_T | Treatment for total nitrogen removal (WINEP/NEP) ,Total number of schemes delivered to meet compliance,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_TNR1_O | Treatment for total nitrogen removal (WINEP/NEP) ,Total number of schemes delivered to meet compliance,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_TNR1_OT | Treatment for total nitrogen removal (WINEP/NEP) ,Total number of schemes delivered to meet compliance,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_TNR1_P | Treatment for total nitrogen removal (WINEP/NEP) ,Total number of schemes delivered to meet compliance,Performance | Nr | Delta
TMS | PCD_DPWW1_TNR2 | Treatment for total nitrogen removal (WINEP/NEP) ,Population equivalent served by schemes delivered to meet compliance,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_TNR2_T | Treatment for total nitrogen removal (WINEP/NEP) ,Population equivalent served by schemes delivered to meet compliance,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_TNR2_O | Treatment for total nitrogen removal (WINEP/NEP) ,Population equivalent served by schemes delivered to meet compliance,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_TNR2_OT | Treatment for total nitrogen removal (WINEP/NEP) ,Population equivalent served by schemes delivered to meet compliance,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_TNR2_P | Treatment for total nitrogen removal (WINEP/NEP) ,Population equivalent served by schemes delivered to meet compliance,Performance | Nr | Delta
TMS | PCD_DPWW1_NBS_SOL | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_NBS_SOL_T | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_NBS_SOL_O | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_NBS_SOL_OT | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_NBS_SOL_P | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,Performance | Nr | Delta
TMS | PCD_DPWW1_CS1 | Catchment solutions (WINEP/NEP),Total number of CNB solutions delivered to meet compliance (allowance/7),PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_CS1_T | Catchment solutions (WINEP/NEP),Total number of CNB solutions delivered to meet compliance (allowance/7),PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CS1_O | Catchment solutions (WINEP/NEP),Total number of CNB solutions delivered to meet compliance (allowance/7),PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_CS1_OT | Catchment solutions (WINEP/NEP),Total number of CNB solutions delivered to meet compliance (allowance/7),PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_CS1_P | Catchment solutions (WINEP/NEP),Total number of CNB solutions delivered to meet compliance (allowance/7),Performance | Nr | Delta
TMS | PCD_DPWW1_CS2 | Catchment solutions (WINEP/NEP),Total number of CP solutions delivered to meet compliance (allowance/6),PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_CS2_T | Catchment solutions (WINEP/NEP),Total number of CP solutions delivered to meet compliance (allowance/6),PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CS2_O | Catchment solutions (WINEP/NEP),Total number of CP solutions delivered to meet compliance (allowance/6),PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_CS2_OT | Catchment solutions (WINEP/NEP),Total number of CP solutions delivered to meet compliance (allowance/6),PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_CS2_P | Catchment solutions (WINEP/NEP),Total number of CP solutions delivered to meet compliance (allowance/6),Performance | Nr | Delta
TMS | PCD_DPWW1_MBT1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes delivered,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_MBT1_T | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes delivered,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_MBT1_O | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes delivered,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_MBT1_OT | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes delivered,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_MBT1_P | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes delivered,Performance | Nr | Delta
TMS | PCD_DPWW1_MBT2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Current population equivalent served by STWs with tightened/new microbiological standards,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_MBT2_T | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Current population equivalent served by STWs with tightened/new microbiological standards,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_MBT2_O | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Current population equivalent served by STWs with tightened/new microbiological standards,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_MBT2_OT | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Current population equivalent served by STWs with tightened/new microbiological standards,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_MBT2_P | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Current population equivalent served by STWs with tightened/new microbiological standards,Performance | Nr | Delta
TMS | PCD_DPWW1_STR | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_STR_T | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_STR_O | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_STR_OT | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_STR_P | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,Performance | Nr | Delta
TMS | PCD_DPWW1_25EP | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_25EP_T | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_25EP_O | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_25EP_OT | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_25EP_P | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,Performance | Nr | Delta
TMS | PCD_DPWW1_WINIVG | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 147.6918 | 288.8815 | 431 | 431 | 431
TMS | PCD_DPWW1_WINIVG_T | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 431 |  |  |  |  | 0
TMS | PCD_DPWW1_WINIVG_O | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,PCD output (cumulative) - Outturn & Forecast | Nr | Delta |  |  |  |  | 366 | 421 | 421 | 426 | 427 | 427 | 427 | 427 | 427
TMS | PCD_DPWW1_WINIVG_OT | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 426 |  |  |  |  | 427
TMS | PCD_DPWW1_WINIVG_P | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,Performance | Nr | Delta | [7 empty] | 0.9884
TMS | PCD_DPWW1_ADWIN1 | Advanced WINEP,Number of restoration plans developed and designed,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_ADWIN1_T | Advanced WINEP,Number of restoration plans developed and designed,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_ADWIN1_O | Advanced WINEP,Number of restoration plans developed and designed,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_ADWIN1_OT | Advanced WINEP,Number of restoration plans developed and designed,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_ADWIN1_P | Advanced WINEP,Number of restoration plans developed and designed,Performance | Nr | Delta
TMS | PCD_DPWW1_ADWIN2 | Advanced WINEP,Partnership funding,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_ADWIN2_T | Advanced WINEP,Partnership funding,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_ADWIN2_O | Advanced WINEP,Partnership funding,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_ADWIN2_OT | Advanced WINEP,Partnership funding,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_ADWIN2_P | Advanced WINEP,Partnership funding,Performance | % | Delta
TMS | PCD_DPWW1_ADWIN3 | Advanced WINEP,Equivalent storage avoided,PCD output (cumulative) - Target` | m3 | Delta
TMS | PCD_DPWW1_ADWIN3_T | Advanced WINEP,Equivalent storage avoided,PCD output by 2029-30 (Target) | m3 | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_ADWIN3_O | Advanced WINEP,Equivalent storage avoided,PCD output (cumulative) - Outturn & Forecast | m3 | Delta
TMS | PCD_DPWW1_ADWIN3_OT | Advanced WINEP,Equivalent storage avoided,PCD output by 2029-30 (Outturn & Forecast) | m3 | Delta
TMS | PCD_DPWW1_ADWIN3_P | Advanced WINEP,Equivalent storage avoided,Performance | m3 | Delta
TMS | PCD_DPWW1_SSTT | Sludge storage -Tanks,Volume of Sludge Storage delivered,PCD output (cumulative) - Target` | m3 | Delta
TMS | PCD_DPWW1_SSTT_T | Sludge storage -Tanks,Volume of Sludge Storage delivered,PCD output by 2029-30 (Target) | m3 | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_SSTT_O | Sludge storage -Tanks,Volume of Sludge Storage delivered,PCD output (cumulative) - Outturn & Forecast | m3 | Delta
TMS | PCD_DPWW1_SSTT_OT | Sludge storage -Tanks,Volume of Sludge Storage delivered,PCD output by 2029-30 (Outturn & Forecast) | m3 | Delta
TMS | PCD_DPWW1_SSTT_P | Sludge storage -Tanks,Volume of Sludge Storage delivered,Performance | m3 | Delta
TMS | PCD_DPWW1_SSCP | Sludge storage (cake pads),Sludge Storage area delivered,PCD output (cumulative) - Target` | m2 | Delta
TMS | PCD_DPWW1_SSCP_T | Sludge storage (cake pads),Sludge Storage area delivered,PCD output by 2029-30 (Target) | m2 | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_SSCP_O | Sludge storage (cake pads),Sludge Storage area delivered,PCD output (cumulative) - Outturn & Forecast | m2 | Delta
TMS | PCD_DPWW1_SSCP_OT | Sludge storage (cake pads),Sludge Storage area delivered,PCD output by 2029-30 (Outturn & Forecast) | m2 | Delta
TMS | PCD_DPWW1_SSCP_P | Sludge storage (cake pads),Sludge Storage area delivered,Performance | m2 | Delta
TMS | PCD_DPWW1_STDW | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,PCD output (cumulative) - Target` | ttds/yr | Delta
TMS | PCD_DPWW1_STDW_T | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,PCD output by 2029-30 (Target) | ttds/yr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_STDW_O | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,PCD output (cumulative) - Outturn & Forecast | ttds/yr | Delta
TMS | PCD_DPWW1_STDW_OT | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,PCD output by 2029-30 (Outturn & Forecast) | ttds/yr | Delta
TMS | PCD_DPWW1_STDW_P | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,Performance | ttds/yr | Delta
TMS | PCD_DPWW1_STOTH1 | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,PCD output (cumulative) - Target` | ttds/yr | Delta
TMS | PCD_DPWW1_STOTH1_T | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,PCD output by 2029-30 (Target) | ttds/yr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_STOTH1_O | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,PCD output (cumulative) - Outturn & Forecast | ttds/yr | Delta
TMS | PCD_DPWW1_STOTH1_OT | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,PCD output by 2029-30 (Outturn & Forecast) | ttds/yr | Delta
TMS | PCD_DPWW1_STOTH1_P | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,Performance | ttds/yr | Delta
TMS | PCD_DPWW1_STOTH2 | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,PCD output (cumulative) - Target` | 000m3/month | Delta
TMS | PCD_DPWW1_STOTH2_T | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,PCD output by 2029-30 (Target) | 000m3/month | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_STOTH2_O | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,PCD output (cumulative) - Outturn & Forecast | 000m3/month | Delta
TMS | PCD_DPWW1_STOTH2_OT | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,PCD output by 2029-30 (Outturn & Forecast) | 000m3/month | Delta
TMS | PCD_DPWW1_STOTH2_P | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,Performance | 000m3/month | Delta
TMS | PCD_DPWW1_BIO_IED | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,PCD output (cumulative) - Target` | Nr | Delta |  |  | 25 | 0 | 2 | 2 | 5 | 25
TMS | PCD_DPWW1_BIO_IED_T | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 25 |  |  |  |  | 0
TMS | PCD_DPWW1_BIO_IED_O | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,PCD output (cumulative) - Outturn & Forecast | Nr | Delta |  |  |  |  | 1 | 1 | 1 | 2 | 2 | 7 | 15 | 19 | 21
TMS | PCD_DPWW1_BIO_IED_OT | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 2 |  |  |  |  | 21
TMS | PCD_DPWW1_BIO_IED_P | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,Performance | Nr | Delta | [7 empty] | 0.08
TMS | PCD_DPWW1_CCUP | Climate change uplift,Spend on schemes for power and flood resilience delivered:,PCD output (cumulative) - Target` | % | Delta |  |  |  | 3.6303 | 11.8661 | 25.9213 | 60.893 | 100
TMS | PCD_DPWW1_CCUP_T | Climate change uplift,Spend on schemes for power and flood resilience delivered:,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 100 |  |  |  |  | 0
TMS | PCD_DPWW1_CCUP_O | Climate change uplift,Spend on schemes for power and flood resilience delivered:,PCD output (cumulative) - Outturn & Forecast | % | Delta |  |  | 0 | 0.94269 | 2.9226 | 14.503 | 84.6168 | 90.4548 | 91.4265 | 91.4265 | 91.4265 | 91.4265 | 91.4265
TMS | PCD_DPWW1_CCUP_OT | Climate change uplift,Spend on schemes for power and flood resilience delivered:,PCD output by 2029-30 (Outturn & Forecast) | % | Delta | [7 empty] | 90.4548 |  |  |  |  | 91.4265
TMS | PCD_DPWW1_CCUP_P | Climate change uplift,Spend on schemes for power and flood resilience delivered:,Performance | % | Delta | [7 empty] | 0.90455
TMS | PCD_DPWW1_CER1 | Coastal Erosion Risk,Crosby Rising Main,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_CER1_T | Coastal Erosion Risk,Crosby Rising Main,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CER1_O | Coastal Erosion Risk,Crosby Rising Main,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_CER1_OT | Coastal Erosion Risk,Crosby Rising Main,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_CER1_P | Coastal Erosion Risk,Crosby Rising Main,Performance | % | Delta
TMS | PCD_DPWW1_CER2 | Coastal Erosion Risk,Halcroft Cottages Sewer,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_CER2_T | Coastal Erosion Risk,Halcroft Cottages Sewer,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CER2_O | Coastal Erosion Risk,Halcroft Cottages Sewer,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_CER2_OT | Coastal Erosion Risk,Halcroft Cottages Sewer,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_CER2_P | Coastal Erosion Risk,Halcroft Cottages Sewer,Performance | % | Delta
TMS | PCD_DPWW1_CER3 | Coastal Erosion Risk,London Road Terrace Sewer,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_CER3_T | Coastal Erosion Risk,London Road Terrace Sewer,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CER3_O | Coastal Erosion Risk,London Road Terrace Sewer,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_CER3_OT | Coastal Erosion Risk,London Road Terrace Sewer,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_CER3_P | Coastal Erosion Risk,London Road Terrace Sewer,Performance | % | Delta
TMS | PCD_DPWW1_CER4 | Coastal Erosion Risk,Rhodes Business Park Sewer,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_CER4_T | Coastal Erosion Risk,Rhodes Business Park Sewer,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CER4_O | Coastal Erosion Risk,Rhodes Business Park Sewer,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_CER4_OT | Coastal Erosion Risk,Rhodes Business Park Sewer,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_CER4_P | Coastal Erosion Risk,Rhodes Business Park Sewer,Performance | % | Delta
TMS | PCD_DPWW1_CER5 | Coastal Erosion Risk,Leyland WwTW,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_CER5_T | Coastal Erosion Risk,Leyland WwTW,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CER5_O | Coastal Erosion Risk,Leyland WwTW,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_CER5_OT | Coastal Erosion Risk,Leyland WwTW,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_CER5_P | Coastal Erosion Risk,Leyland WwTW,Performance | % | Delta
TMS | PCD_DPWW1_CER6 | Coastal Erosion Risk,Bowdon WwTW,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_CER6_T | Coastal Erosion Risk,Bowdon WwTW,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_CER6_O | Coastal Erosion Risk,Bowdon WwTW,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_CER6_OT | Coastal Erosion Risk,Bowdon WwTW,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_CER6_P | Coastal Erosion Risk,Bowdon WwTW,Performance | % | Delta
TMS | PCD_DPWW1_INF | Infiltration,Total length (in metre) of sewer effectively sealed / lined,PCD output (cumulative) - Target` | m | Delta
TMS | PCD_DPWW1_INF_T | Infiltration,Total length (in metre) of sewer effectively sealed / lined,PCD output by 2029-30 (Target) | m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_INF_O | Infiltration,Total length (in metre) of sewer effectively sealed / lined,PCD output (cumulative) - Outturn & Forecast | m | Delta
TMS | PCD_DPWW1_INF_OT | Infiltration,Total length (in metre) of sewer effectively sealed / lined,PCD output by 2029-30 (Outturn & Forecast) | m | Delta
TMS | PCD_DPWW1_INF_P | Infiltration,Total length (in metre) of sewer effectively sealed / lined,Performance | m | Delta
TMS | PCD_DPWW1_WWPF1 | WW Partnership Funding,spend on schemes for power and flood resilience delivered:,PCD output (cumulative) - Target` | % | Delta
TMS | PCD_DPWW1_WWPF1_T | WW Partnership Funding,spend on schemes for power and flood resilience delivered:,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_WWPF1_O | WW Partnership Funding,spend on schemes for power and flood resilience delivered:,PCD output (cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPWW1_WWPF1_OT | WW Partnership Funding,spend on schemes for power and flood resilience delivered:,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPWW1_WWPF1_P | WW Partnership Funding,spend on schemes for power and flood resilience delivered:,Performance | % | Delta
TMS | PCD_DPWW1_WWPF2 | WW Partnership Funding,Minimum number of schemes delivered,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_WWPF2_T | WW Partnership Funding,Minimum number of schemes delivered,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_WWPF2_O | WW Partnership Funding,Minimum number of schemes delivered,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_WWPF2_OT | WW Partnership Funding,Minimum number of schemes delivered,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_WWPF2_P | WW Partnership Funding,Minimum number of schemes delivered,Performance | Nr | Delta
TMS | PCD_DPWW1_RRM1 | Rainwater management,Total storage volume provided via SuDS solutions,PCD output (cumulative) - Target` | Cubic metre | Delta
TMS | PCD_DPWW1_RRM1_T | Rainwater management,Total storage volume provided via SuDS solutions,PCD output by 2029-30 (Target) | Cubic metre | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_RRM1_O | Rainwater management,Total storage volume provided via SuDS solutions,PCD output (cumulative) - Outturn & Forecast | Cubic metre | Delta
TMS | PCD_DPWW1_RRM1_OT | Rainwater management,Total storage volume provided via SuDS solutions,PCD output by 2029-30 (Outturn & Forecast) | Cubic metre | Delta
TMS | PCD_DPWW1_RRM1_P | Rainwater management,Total storage volume provided via SuDS solutions,Performance | Cubic metre | Delta
TMS | PCD_DPWW1_RRM2 | Rainwater management,Completion of named schemes,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_RRM2_T | Rainwater management,Completion of named schemes,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_RRM2_O | Rainwater management,Completion of named schemes,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_RRM2_OT | Rainwater management,Completion of named schemes,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_RRM2_P | Rainwater management,Completion of named schemes,Performance | Nr | Delta
TMS | PCD_DPWW1_FP2 | Flood and power,Flooding resilience scheme unit rate,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_FP2_T | Flood and power,Flooding resilience scheme unit rate,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_FP2_O | Flood and power,Flooding resilience scheme unit rate,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_FP2_OT | Flood and power,Flooding resilience scheme unit rate,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_FP2_P | Flood and power,Flooding resilience scheme unit rate,Performance | Nr | Delta
TMS | PCD_DPWW1_FP3 | Flood and power,Power resilience scheme unit rate,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_FP3_T | Flood and power,Power resilience scheme unit rate,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_FP3_O | Flood and power,Power resilience scheme unit rate,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_FP3_OT | Flood and power,Power resilience scheme unit rate,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_FP3_P | Flood and power,Power resilience scheme unit rate,Performance | Nr | Delta
TMS | PCD_DPWW1_FTS | First time sewerage ,Number of connected properties served by S101A schemes,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_FTS_T | First time sewerage ,Number of connected properties served by S101A schemes,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_FTS_O | First time sewerage ,Number of connected properties served by S101A schemes,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_FTS_OT | First time sewerage ,Number of connected properties served by S101A schemes,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_FTS_P | First time sewerage ,Number of connected properties served by S101A schemes,Performance | Nr | Delta
TMS | PCD_DPWW1_GRC1 | PR19 Green recovery carryover,Storage in the network close to Nuttall Road combined sewer overflow,PCD output (cumulative) - Target` | m3 | Delta
TMS | PCD_DPWW1_GRC1_T | PR19 Green recovery carryover,Storage in the network close to Nuttall Road combined sewer overflow,PCD output by 2029-30 (Target) | m3 | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_GRC1_O | PR19 Green recovery carryover,Storage in the network close to Nuttall Road combined sewer overflow,PCD output (cumulative) - Outturn & Forecast | m3 | Delta
TMS | PCD_DPWW1_GRC1_OT | PR19 Green recovery carryover,Storage in the network close to Nuttall Road combined sewer overflow,PCD output by 2029-30 (Outturn & Forecast) | m3 | Delta
TMS | PCD_DPWW1_GRC1_P | PR19 Green recovery carryover,Storage in the network close to Nuttall Road combined sewer overflow,Performance | m3 | Delta
TMS | PCD_DPWW1_GRC2 | PR19 Green recovery carryover,Storm tank capacity at Bury wastewater treatment works ,PCD output (cumulative) - Target` | m3 | Delta
TMS | PCD_DPWW1_GRC2_T | PR19 Green recovery carryover,Storm tank capacity at Bury wastewater treatment works ,PCD output by 2029-30 (Target) | m3 | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_GRC2_O | PR19 Green recovery carryover,Storm tank capacity at Bury wastewater treatment works ,PCD output (cumulative) - Outturn & Forecast | m3 | Delta
TMS | PCD_DPWW1_GRC2_OT | PR19 Green recovery carryover,Storm tank capacity at Bury wastewater treatment works ,PCD output by 2029-30 (Outturn & Forecast) | m3 | Delta
TMS | PCD_DPWW1_GRC2_P | PR19 Green recovery carryover,Storm tank capacity at Bury wastewater treatment works ,Performance | m3 | Delta
TMS | PCD_DPWW1_SOFES | Storm overflows,Equivalent storage,PCD output (cumulative) - Target` | m3 | Delta |  |  |  | 0 | 10557.9405 | 73905.5835 | 126695.286 | 211158.81
TMS | PCD_DPWW1_SOFES_T | Storm overflows,Equivalent storage,PCD output by 2029-30 (Target) | m3 | Delta | [7 empty] | 211158.81 |  |  |  |  | 0
TMS | PCD_DPWW1_SOFES_O | Storm overflows,Equivalent storage,PCD output (cumulative) - Outturn & Forecast | m3 | Delta |  |  |  |  | 3462.4 | 25124.73 | 69755.31 | 113903.52 | 176066.19 | 185919.23 | 211158.81 | 211158.81 | 211158.81
TMS | PCD_DPWW1_SOFES_OT | Storm overflows,Equivalent storage,PCD output by 2029-30 (Outturn & Forecast) | m3 | Delta | [7 empty] | 113903.52 |  |  |  |  | 211158.81
TMS | PCD_DPWW1_SOFES_P | Storm overflows,Equivalent storage,Performance | m3 | Delta | [7 empty] | 0.53942
TMS | PCD_DPWW1_FTFT | Flow to Full Treatment,litres per second,PCD output (cumulative) - Target` | l/s | Delta |  |  |  | 0 | 66.965 | 468.755 | 803.58 | 1339.3
TMS | PCD_DPWW1_FTFT_T | Flow to Full Treatment,litres per second,PCD output by 2029-30 (Target) | l/s | Delta | [7 empty] | 1339.3 |  |  |  |  | 0
TMS | PCD_DPWW1_FTFT_O | Flow to Full Treatment,litres per second,PCD output (cumulative) - Outturn & Forecast | l/s | Delta |  |  |  |  | 12.6 | 39.8 | 66.3 | 253.7 | 505.9 | 555.9 | 1339.3 | 1339.3 | 1339.3
TMS | PCD_DPWW1_FTFT_OT | Flow to Full Treatment,litres per second,PCD output by 2029-30 (Outturn & Forecast) | l/s | Delta | [7 empty] | 253.7 |  |  |  |  | 1339.3
TMS | PCD_DPWW1_FTFT_P | Flow to Full Treatment,litres per second,Performance | l/s | Delta | [7 empty] | 0.18943
TMS | PCD_DPWW1_PRMVL | P-removal,Population equivalent served,PCD output (cumulative) - Target` | 000s | Delta |  |  |  | 0 | 0 | 992.4325 | 2381.8379 | 3969.7299
TMS | PCD_DPWW1_PRMVL_T | P-removal,Population equivalent served,PCD output by 2029-30 (Target) | 000s | Delta | [7 empty] | 3969.7299 |  |  |  |  | 0
TMS | PCD_DPWW1_PRMVL_O | P-removal,Population equivalent served,PCD output (cumulative) - Outturn & Forecast | 000s | Delta |  |  |  | 13.0146 | 13.0146 | 13.0146 | 22.2501 | 866.1171 | 1623.1382 | 2838.9477 | 3478.1102 | 3969.3453 | 3969.7301
TMS | PCD_DPWW1_PRMVL_OT | P-removal,Population equivalent served,PCD output by 2029-30 (Outturn & Forecast) | 000s | Delta | [7 empty] | 866.1171 |  |  |  |  | 3969.7301
TMS | PCD_DPWW1_PRMVL_P | P-removal,Population equivalent served,Performance | 000s | Delta | [7 empty] | 0.21818
TMS | PCD_DPWW1_GSTW | Growth to Sewerage Treatment Works,Added Process Capacity in PE,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 0 | 0 | 0 | 3630.8805 | 93769.523
TMS | PCD_DPWW1_GSTW_T | Growth to Sewerage Treatment Works,Added Process Capacity in PE,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 93769.523 |  |  |  |  | 0
TMS | PCD_DPWW1_GSTW_O | Growth to Sewerage Treatment Works,Added Process Capacity in PE,PCD output (cumulative) - Outturn & Forecast | Nr | Delta | [7 empty] | 24093.9665 | 38053.5445 | 57349.2977 | 93769.5209 | 93769.5209 | 93769.5209
TMS | PCD_DPWW1_GSTW_OT | Growth to Sewerage Treatment Works,Added Process Capacity in PE,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 24093.9665 |  |  |  |  | 93769.5209
TMS | PCD_DPWW1_GSTW_P | Growth to Sewerage Treatment Works,Added Process Capacity in PE,Performance | Nr | Delta | [7 empty] | 0.25695
TMS | PCD_DPWW1_TTSP | Treatment for tightening of sanitary parameters,Population equivalent served,PCD output (cumulative) - Target` | 000s | Delta |  |  |  | 55.0287 | 137.9683 | 231.0587 | 491.4389 | 492.7439
TMS | PCD_DPWW1_TTSP_T | Treatment for tightening of sanitary parameters,Population equivalent served,PCD output by 2029-30 (Target) | 000s | Delta | [7 empty] | 492.7439 |  |  |  |  | 0
TMS | PCD_DPWW1_TTSP_O | Treatment for tightening of sanitary parameters,Population equivalent served,PCD output (cumulative) - Outturn & Forecast | 000s | Delta |  |  |  | 63.3417 | 63.3417 | 156.4322 | 167.7582 | 414.7444 | 415.1494 | 415.2211 | 492.7439 | 492.7439 | 492.7439
TMS | PCD_DPWW1_TTSP_OT | Treatment for tightening of sanitary parameters,Population equivalent served,PCD output by 2029-30 (Outturn & Forecast) | 000s | Delta | [7 empty] | 414.7444 |  |  |  |  | 492.7439
TMS | PCD_DPWW1_TTSP_P | Treatment for tightening of sanitary parameters,Population equivalent served,Performance | 000s | Delta | [7 empty] | 0.8417
TMS | PCD_DPWW1_PR19WINCA | PR19 WINEP Carryover actions,Number of schemes,PCD output (cumulative) - Target` | Nr | Delta |  |  |  | 27 | 34 | 55 | 62 | 66
TMS | PCD_DPWW1_PR19WINCA_T | PR19 WINEP Carryover actions,Number of schemes,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 66 |  |  |  |  | 0
TMS | PCD_DPWW1_PR19WINCA_O | PR19 WINEP Carryover actions,Number of schemes,PCD output (cumulative) - Outturn & Forecast | Nr | Delta |  |  | 9 | 20 | 25 | 35 | 53 | 62 | 65 | 66 | 66 | 66 | 66
TMS | PCD_DPWW1_PR19WINCA_OT | PR19 WINEP Carryover actions,Number of schemes,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 62 |  |  |  |  | 66
TMS | PCD_DPWW1_PR19WINCA_P | PR19 WINEP Carryover actions,Number of schemes,Performance | Nr | Delta | [7 empty] | 0.93939
TMS | PCD_DPWW1_GGR1 | Greenhouse gas reduction (net zero),tCO2e,PCD output (cumulative) - Target` | tonnes | Delta
TMS | PCD_DPWW1_GGR1_T | Greenhouse gas reduction (net zero),tCO2e,PCD output by 2029-30 (Target) | tonnes | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_GGR1_O | Greenhouse gas reduction (net zero),tCO2e,PCD output (cumulative) - Outturn & Forecast | tonnes | Delta
TMS | PCD_DPWW1_GGR1_OT | Greenhouse gas reduction (net zero),tCO2e,PCD output by 2029-30 (Outturn & Forecast) | tonnes | Delta
TMS | PCD_DPWW1_GGR1_P | Greenhouse gas reduction (net zero),tCO2e,Performance | tonnes | Delta
TMS | PCD_DPWW1_GGR2 | Greenhouse gas reduction (net zero),Number of sites,PCD output (cumulative) - Target` | Nr | Delta
TMS | PCD_DPWW1_GGR2_T | Greenhouse gas reduction (net zero),Number of sites,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW1_GGR2_O | Greenhouse gas reduction (net zero),Number of sites,PCD output (cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPWW1_GGR2_OT | Greenhouse gas reduction (net zero),Number of sites,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPWW1_GGR2_P | Greenhouse gas reduction (net zero),Number of sites,Performance | Nr | Delta
TMS | PCD_DPWW2_FMS_NP | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_FMS | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_FMS_T | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FMS_O | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPWW2_FMS_OT | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FMS_P | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring permits only or simple schemes delivered,Performance | £m | Delta
TMS | PCD_DPWW2_FMC_NP | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_FMC | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_FMC_T | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FMC_O | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_FMC_OT | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FMC_P | Flow monitoring at sewage treatment works; (WINEP/NEP) ,Number of flow monitoring complex schemes delivered,Performance | £m | Delta
TMS | PCD_DPWW2_CWQM_NP | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_CWQM | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_CWQM_T | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CWQM_O | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_CWQM_OT | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CWQM_P | Continuous river water quality monitoring (CWQM),Continuous river water quality monitoring (CWQM),Performance | £m | Delta
TMS | PCD_DPWW2_SPSO1_NP | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta | [13 empty] | 0.14293
TMS | PCD_DPWW2_SPSO1 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 1.4883 | 2.9753 | 3.3463 | 3.5314 | 3.7162
TMS | PCD_DPWW2_SPSO1_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 3.7162 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO1_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 0.14561 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933
TMS | PCD_DPWW2_SPSO1_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0.39933 |  |  |  |  | 0.39933
TMS | PCD_DPWW2_SPSO1_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only,Performance | £m | Delta | [7 empty] | 0.10746
TMS | PCD_DPWW2_SPSO2_NP | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SPSO2 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_SPSO2_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO2_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_SPSO2_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO2_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils,Performance | £m | Delta
TMS | PCD_DPWW2_SPSO3_NP | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SPSO3 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_SPSO3_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO3_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_SPSO3_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO3_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF,Performance | £m | Delta
TMS | PCD_DPWW2_SPSO4_NP | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta | [13 empty] | 0.25331
TMS | PCD_DPWW2_SPSO4 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 2.2317 | 4.4616 | 5.018 | 5.2956 | 5.5727
TMS | PCD_DPWW2_SPSO4_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 5.5727 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO4_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 0.14561 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933 | 0.39933
TMS | PCD_DPWW2_SPSO4_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0.39933 |  |  |  |  | 0.39933
TMS | PCD_DPWW2_SPSO4_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils,Performance | £m | Delta | [7 empty] | 0.071658
TMS | PCD_DPWW2_SPSO5_NP | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SPSO5 | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_SPSO5_T | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO5_O | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_SPSO5_OT | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SPSO5_P | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP),Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only,Performance | £m | Delta
TMS | PCD_DPWW2_SOFW1_NP | Storm Overflow - Wetland,Number of schemes,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SOFW1 | Storm Overflow - Wetland,Number of schemes,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 2.2636 | 4.445 | 13.0605 | 30.6829 | 63.11
TMS | PCD_DPWW2_SOFW1_T | Storm Overflow - Wetland,Number of schemes,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 63.11 |  |  |  |  | 0
TMS | PCD_DPWW2_SOFW1_O | Storm Overflow - Wetland,Number of schemes,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 0.19208 | 0.68705 | 5.5111 | 23.7075 | 47.6612 | 47.8735 | 47.9257 | 47.9257 | 47.9257 | 47.9257
TMS | PCD_DPWW2_SOFW1_OT | Storm Overflow - Wetland,Number of schemes,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 47.6612 |  |  |  |  | 47.9257
TMS | PCD_DPWW2_SOFW1_P | Storm Overflow - Wetland,Number of schemes,Performance | £m | Delta | [7 empty] | 0.75521
TMS | PCD_DPWW2_SOFW2_NP | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SOFW2 | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_SOFW2_T | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SOFW2_O | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_SOFW2_OT | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SOFW2_P | Storm Overflow - Screens ,Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions,Performance | £m | Delta
TMS | PCD_DPWW2_TCR1_NP | Treatment for chemical removal (WINEP/NEP),Treatment for chemical removal (WINEP/NEP),Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_TCR1 | Treatment for chemical removal (WINEP/NEP),Treatment for chemical removal (WINEP/NEP),PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 0.41431 | 0.69141 | 20.2728 | 68.6705 | 189.2081
TMS | PCD_DPWW2_TCR1_T | Treatment for chemical removal (WINEP/NEP),Treatment for chemical removal (WINEP/NEP),PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 189.2081 |  |  |  |  | 0
TMS | PCD_DPWW2_TCR1_O | Treatment for chemical removal (WINEP/NEP),Treatment for chemical removal (WINEP/NEP),Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 10.6741 | 25.3715 | 39.3939 | 65.7745 | 101.0777 | 121.6611 | 144.0868 | 156.2303 | 158.2824 | 158.7503
TMS | PCD_DPWW2_TCR1_OT | Treatment for chemical removal (WINEP/NEP),Treatment for chemical removal (WINEP/NEP),Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 101.0777 |  |  |  |  | 158.7503
TMS | PCD_DPWW2_TCR1_P | Treatment for chemical removal (WINEP/NEP),Treatment for chemical removal (WINEP/NEP),Performance | £m | Delta | [7 empty] | 0.53421
TMS | PCD_DPWW2_TNR1_NP | Treatment for total nitrogen removal (WINEP/NEP) ,Treatment for total nitrogen removal (WINEP/NEP) ,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_TNR1 | Treatment for total nitrogen removal (WINEP/NEP) ,Treatment for total nitrogen removal (WINEP/NEP) ,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_TNR1_T | Treatment for total nitrogen removal (WINEP/NEP) ,Treatment for total nitrogen removal (WINEP/NEP) ,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_TNR1_O | Treatment for total nitrogen removal (WINEP/NEP) ,Treatment for total nitrogen removal (WINEP/NEP) ,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_TNR1_OT | Treatment for total nitrogen removal (WINEP/NEP) ,Treatment for total nitrogen removal (WINEP/NEP) ,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_TNR1_P | Treatment for total nitrogen removal (WINEP/NEP) ,Treatment for total nitrogen removal (WINEP/NEP) ,Performance | £m | Delta
TMS | PCD_DPWW2_NBS_SOL_NP | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_NBS_SOL | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_NBS_SOL_T | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_NBS_SOL_O | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_NBS_SOL_OT | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_NBS_SOL_P | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Total number of site treatment solutions delivered to meet compliance,Performance | £m | Delta
TMS | PCD_DPWW2_CS1_NP | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_CS1 | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_CS1_T | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CS1_O | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_CS1_OT | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CS1_P | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP),Performance | £m | Delta
TMS | PCD_DPWW2_CS2_NP | Catchment solutions - Catchment Permitting (WINEP/NEP),Catchment solutions - Catchment Permitting (WINEP/NEP),Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_CS2 | Catchment solutions - Catchment Permitting (WINEP/NEP),Catchment solutions - Catchment Permitting (WINEP/NEP),PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_CS2_T | Catchment solutions - Catchment Permitting (WINEP/NEP),Catchment solutions - Catchment Permitting (WINEP/NEP),PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CS2_O | Catchment solutions - Catchment Permitting (WINEP/NEP),Catchment solutions - Catchment Permitting (WINEP/NEP),Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_CS2_OT | Catchment solutions - Catchment Permitting (WINEP/NEP),Catchment solutions - Catchment Permitting (WINEP/NEP),Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CS2_P | Catchment solutions - Catchment Permitting (WINEP/NEP),Catchment solutions - Catchment Permitting (WINEP/NEP),Performance | £m | Delta
TMS | PCD_DPWW2_MBT1_NP | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_MBT1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_MBT1_T | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_MBT1_O | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_MBT1_OT | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_MBT1_P | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Performance | £m | Delta
TMS | PCD_DPWW2_STR_NP | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_STR | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_STR_T | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STR_O | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_STR_OT | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STR_P | Septic tank replacements - treatment solution; (WINEP/NEP),Total number of septic tank replacement or flow diversion schemes delivered,Performance | £m | Delta
TMS | PCD_DPWW2_25EP_NP | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_25EP | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_25EP_T | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_25EP_O | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_25EP_OT | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_25EP_P | 25 year environment plan; (WINEP/NEP),Number of schemes delivered,Performance | £m | Delta
TMS | PCD_DPWW2_WINIVG_NP | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta | [13 empty] | 0.09365
TMS | PCD_DPWW2_WINIVG | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 17.1647 | 33.0977 | 39.359 | 40.227 | 40.3631
TMS | PCD_DPWW2_WINIVG_T | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 40.3631 |  |  |  |  | 0
TMS | PCD_DPWW2_WINIVG_O | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 0.39325 | 23.1961 | 25.8478 | 28.4627 | 29.3644 | 29.3644 | 29.3644 | 29.3644 | 29.3644 | 29.3644
TMS | PCD_DPWW2_WINIVG_OT | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 29.3644 |  |  |  |  | 29.3644
TMS | PCD_DPWW2_WINIVG_P | WINEP Investigations (wastewater),Number of satisfactorily completed WINEP / NEP investigations - all categories,Performance | £m | Delta | [7 empty] | 0.72751
TMS | PCD_DPWW2_ADWIN1_NP | Advanced WINEP,Advanced WINEP,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_ADWIN1 | Advanced WINEP,Advanced WINEP,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_ADWIN1_T | Advanced WINEP,Advanced WINEP,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_ADWIN1_O | Advanced WINEP,Advanced WINEP,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_ADWIN1_OT | Advanced WINEP,Advanced WINEP,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_ADWIN1_P | Advanced WINEP,Advanced WINEP,Performance | £m | Delta
TMS | PCD_DPWW2_ADWIN2_NP | Advanced WINEP,Equivalent storage avoided,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_ADWIN2 | Advanced WINEP,Equivalent storage avoided,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_ADWIN2_T | Advanced WINEP,Equivalent storage avoided,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_ADWIN2_O | Advanced WINEP,Equivalent storage avoided,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_ADWIN2_OT | Advanced WINEP,Equivalent storage avoided,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_ADWIN2_P | Advanced WINEP,Equivalent storage avoided,Performance | £m | Delta
TMS | PCD_DPWW2_SSTT_NP | Sludge storage -Tanks,Volume of Sludge Storage delivered,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SSTT | Sludge storage -Tanks,Volume of Sludge Storage delivered,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_SSTT_T | Sludge storage -Tanks,Volume of Sludge Storage delivered,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SSTT_O | Sludge storage -Tanks,Volume of Sludge Storage delivered,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_SSTT_OT | Sludge storage -Tanks,Volume of Sludge Storage delivered,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SSTT_P | Sludge storage -Tanks,Volume of Sludge Storage delivered,Performance | £m | Delta
TMS | PCD_DPWW2_SSCP_NP | Sludge storage (cake pads),Sludge Storage area delivered,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SSCP | Sludge storage (cake pads),Sludge Storage area delivered,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_SSCP_T | Sludge storage (cake pads),Sludge Storage area delivered,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SSCP_O | Sludge storage (cake pads),Sludge Storage area delivered,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_SSCP_OT | Sludge storage (cake pads),Sludge Storage area delivered,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_SSCP_P | Sludge storage (cake pads),Sludge Storage area delivered,Performance | £m | Delta
TMS | PCD_DPWW2_STDW_NP | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_STDW | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_STDW_T | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STDW_O | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_STDW_OT | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STDW_P | Sludge thickening and dewatering ,Tonnes of dry solids/ year ,Performance | £m | Delta
TMS | PCD_DPWW2_STOTH1_NP | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_STOTH1 | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_STOTH1_T | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STOTH1_O | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_STOTH1_OT | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STOTH1_P | Sludge treatment (Other),Sludge throughput Dryer/Pelletiser installed plant capacity,Performance | £m | Delta
TMS | PCD_DPWW2_STOTH2_NP | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_STOTH2 | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_STOTH2_T | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STOTH2_O | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_STOTH2_OT | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_STOTH2_P | Sludge treatment (Other),Sludge Throughput P Recovery installed plant capacity,Performance | £m | Delta
TMS | PCD_DPWW2_BIO_IED_NP | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_BIO_IED | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 18.5794 | 36.6273 | 80.8486 | 152.7866 | 290.4916
TMS | PCD_DPWW2_BIO_IED_T | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 290.4916 |  |  |  |  | 0
TMS | PCD_DPWW2_BIO_IED_O | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 2.6857 | 20.1125 | 51.1926 | 111.1971 | 187.1411 | 252.7659 | 298.1067 | 370.7528 | 417.3658 | 427.1801
TMS | PCD_DPWW2_BIO_IED_OT | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 187.1411 |  |  |  |  | 427.1801
TMS | PCD_DPWW2_BIO_IED_P | Bioresources - IED and Reg changes,Number of sites achieving IED compliance,Performance | £m | Delta | [7 empty] | 0.64422
TMS | PCD_DPWW2_CCUP_NP | Climate change uplift,Spend on schemes for power and flood resilience delivered:,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta | [13 empty] | 0.31203
TMS | PCD_DPWW2_CCUP | Climate change uplift,Spend on schemes for power and flood resilience delivered:,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 1.2546 | 2.2253 | 7.1047 | 15.2641 | 31.2031
TMS | PCD_DPWW2_CCUP_T | Climate change uplift,Spend on schemes for power and flood resilience delivered:,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 31.2031 |  |  |  |  | 0
TMS | PCD_DPWW2_CCUP_O | Climate change uplift,Spend on schemes for power and flood resilience delivered:,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 0.29415 | 0.91193 | 4.5254 | 26.4031 | 28.2247 | 28.5279 | 28.5279 | 28.5279 | 28.5279 | 28.5279
TMS | PCD_DPWW2_CCUP_OT | Climate change uplift,Spend on schemes for power and flood resilience delivered:,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 28.2247 |  |  |  |  | 28.5279
TMS | PCD_DPWW2_CCUP_P | Climate change uplift,Spend on schemes for power and flood resilience delivered:,Performance | £m | Delta | [7 empty] | 0.90455
TMS | PCD_DPWW2_CER1_NP | Coastal Erosion Risk,Coastal Erosion Risk,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_CER1 | Coastal Erosion Risk,Coastal Erosion Risk,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_CER1_T | Coastal Erosion Risk,Coastal Erosion Risk,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CER1_O | Coastal Erosion Risk,Coastal Erosion Risk,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_CER1_OT | Coastal Erosion Risk,Coastal Erosion Risk,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_CER1_P | Coastal Erosion Risk,Coastal Erosion Risk,Performance | £m | Delta
TMS | PCD_DPWW2_INF_NP | Infiltration,Total length (in metre) of sewer effectively sealed / lined,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_INF | Infiltration,Total length (in metre) of sewer effectively sealed / lined,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_INF_T | Infiltration,Total length (in metre) of sewer effectively sealed / lined,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_INF_O | Infiltration,Total length (in metre) of sewer effectively sealed / lined,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_INF_OT | Infiltration,Total length (in metre) of sewer effectively sealed / lined,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_INF_P | Infiltration,Total length (in metre) of sewer effectively sealed / lined,Performance | £m | Delta
TMS | PCD_DPWW2_WWPF1_NP | WW Partnership Funding,WW Partnership Funding,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_WWPF1 | WW Partnership Funding,WW Partnership Funding,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_WWPF1_T | WW Partnership Funding,WW Partnership Funding,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_WWPF1_O | WW Partnership Funding,WW Partnership Funding,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_WWPF1_OT | WW Partnership Funding,WW Partnership Funding,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_WWPF1_P | WW Partnership Funding,WW Partnership Funding,Performance | £m | Delta
TMS | PCD_DPWW2_RRM_NP | Rainwater management,Rainwater management,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_RRM | Rainwater management,Rainwater management,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_RRM_T | Rainwater management,Rainwater management,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_RRM_O | Rainwater management,Rainwater management,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_RRM_OT | Rainwater management,Rainwater management,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_RRM_P | Rainwater management,Rainwater management,Performance | £m | Delta
TMS | PCD_DPWW2_FP_NP | Flood and power,Flooding resilience scheme unit rate,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_FP | Flood and power,Flooding resilience scheme unit rate,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_FP_T | Flood and power,Flooding resilience scheme unit rate,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FP_O | Flood and power,Flooding resilience scheme unit rate,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_FP_OT | Flood and power,Flooding resilience scheme unit rate,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FP_P | Flood and power,Flooding resilience scheme unit rate,Performance | £m | Delta
TMS | PCD_DPWW2_FP1_NP | Flood and power,Power resilience scheme unit rate,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_FP1 | Flood and power,Power resilience scheme unit rate,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_FP1_T | Flood and power,Power resilience scheme unit rate,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FP1_O | Flood and power,Power resilience scheme unit rate,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_FP1_OT | Flood and power,Power resilience scheme unit rate,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FP1_P | Flood and power,Power resilience scheme unit rate,Performance | £m | Delta
TMS | PCD_DPWW2_FTS_NP | First time sewerage ,Number of connected properties served by S101A schemes,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_FTS | First time sewerage ,Number of connected properties served by S101A schemes,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_FTS_T | First time sewerage ,Number of connected properties served by S101A schemes,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FTS_O | First time sewerage ,Number of connected properties served by S101A schemes,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_FTS_OT | First time sewerage ,Number of connected properties served by S101A schemes,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_FTS_P | First time sewerage ,Number of connected properties served by S101A schemes,Performance | £m | Delta
TMS | PCD_DPWW2_PR19GRC_NP | PR19 Green recovery carryover,PR19 Green recovery carryover,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_PR19GRC | PR19 Green recovery carryover,PR19 Green recovery carryover,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_PR19GRC_T | PR19 Green recovery carryover,PR19 Green recovery carryover,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_PR19GRC_O | PR19 Green recovery carryover,PR19 Green recovery carryover,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_PR19GRC_OT | PR19 Green recovery carryover,PR19 Green recovery carryover,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_PR19GRC_P | PR19 Green recovery carryover,PR19 Green recovery carryover,Performance | £m | Delta
TMS | PCD_DPWW2_SOFES_NP | Storm overflows,Equivalent storage,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_SOFES | Storm overflows,Equivalent storage,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 18.7044 | 36.7306 | 107.9232 | 253.5419 | 521.4971
TMS | PCD_DPWW2_SOFES_T | Storm overflows,Equivalent storage,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 521.4971 |  |  |  |  | 0
TMS | PCD_DPWW2_SOFES_O | Storm overflows,Equivalent storage,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 13.4138 | 50.6767 | 135.2456 | 364.8899 | 539.5852 | 551.8582 | 552.9837 | 552.9837 | 552.9837 | 552.9837
TMS | PCD_DPWW2_SOFES_OT | Storm overflows,Equivalent storage,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 539.5852 |  |  |  |  | 552.9837
TMS | PCD_DPWW2_SOFES_P | Storm overflows,Equivalent storage,Performance | £m | Delta | [7 empty] | 1.0347
TMS | PCD_DPWW2_FTFT_NP | Flow to Full Treatment,litres per second,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_FTFT | Flow to Full Treatment,litres per second,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 4.8532 | 9.5304 | 28.0025 | 65.7859 | 135.3115
TMS | PCD_DPWW2_FTFT_T | Flow to Full Treatment,litres per second,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 135.3115 |  |  |  |  | 0
TMS | PCD_DPWW2_FTFT_O | Flow to Full Treatment,litres per second,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 1.0869 | 3.5764 | 12.8964 | 64.2148 | 124.4539 | 129.8484 | 130.356 | 130.356 | 130.356 | 130.356
TMS | PCD_DPWW2_FTFT_OT | Flow to Full Treatment,litres per second,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 124.4539 |  |  |  |  | 130.356
TMS | PCD_DPWW2_FTFT_P | Flow to Full Treatment,litres per second,Performance | £m | Delta | [7 empty] | 0.91976
TMS | PCD_DPWW2_PRMVL_NP | P-removal,Population equivalent served,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_PRMVL | P-removal,Population equivalent served,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 26.1686 | 64.2431 | 231.8319 | 594.7064 | 1183.2158
TMS | PCD_DPWW2_PRMVL_T | P-removal,Population equivalent served,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 1183.2158 |  |  |  |  | 0
TMS | PCD_DPWW2_PRMVL_O | P-removal,Population equivalent served,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 24.7863 | 111.3063 | 272.2784 | 719.9538 | 993.7957 | 1154.123 | 1248.6534 | 1272.5443 | 1278.3424 | 1278.9117
TMS | PCD_DPWW2_PRMVL_OT | P-removal,Population equivalent served,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 993.7957 |  |  |  |  | 1278.9117
TMS | PCD_DPWW2_PRMVL_P | P-removal,Population equivalent served,Performance | £m | Delta | [7 empty] | 0.83991
TMS | PCD_DPWW2_GSTW_NP | Growth to Sewerage Treatment Works,Added Process Capacity in PE,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_GSTW | Growth to Sewerage Treatment Works,Added Process Capacity in PE,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 0 | 0 | 0 | 51.664 | 172.9
TMS | PCD_DPWW2_GSTW_T | Growth to Sewerage Treatment Works,Added Process Capacity in PE,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 172.9 |  |  |  |  | 0
TMS | PCD_DPWW2_GSTW_O | Growth to Sewerage Treatment Works,Added Process Capacity in PE,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 4.3122 | 28.7012 | 74.6741 | 196.1264 | 280.1188 | 339.8374 | 387.2904 | 432.5825 | 432.7223 | 432.7223
TMS | PCD_DPWW2_GSTW_OT | Growth to Sewerage Treatment Works,Added Process Capacity in PE,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 280.1188 |  |  |  |  | 432.7223
TMS | PCD_DPWW2_GSTW_P | Growth to Sewerage Treatment Works,Added Process Capacity in PE,Performance | £m | Delta | [7 empty] | 1.6201
TMS | PCD_DPWW2_TTSP_NP | Treatment for tightening of sanitary parameters,Population equivalent served,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_TTSP | Treatment for tightening of sanitary parameters,Population equivalent served,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 31.5783 | 61.5704 | 62.1922 | 62.8826 | 68.9935
TMS | PCD_DPWW2_TTSP_T | Treatment for tightening of sanitary parameters,Population equivalent served,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 68.9935 |  |  |  |  | 0
TMS | PCD_DPWW2_TTSP_O | Treatment for tightening of sanitary parameters,Population equivalent served,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 0 | 15.4167 | 28.5308 | 40.8871 | 67.0129 | 77.4824 | 79.9768 | 82.0272 | 83.5591 | 83.9328 | 84.0064
TMS | PCD_DPWW2_TTSP_OT | Treatment for tightening of sanitary parameters,Population equivalent served,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 77.4824 |  |  |  |  | 84.0064
TMS | PCD_DPWW2_TTSP_P | Treatment for tightening of sanitary parameters,Population equivalent served,Performance | £m | Delta | [7 empty] | 1.123
TMS | PCD_DPWW2_PR19WINCA_NP | PR19 WINEP Carryover actions,Number of schemes,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_PR19WINCA | PR19 WINEP Carryover actions,Number of schemes,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 201.3239 | 402.6477 | 603.9716 | 805.2955 | 1006.6194
TMS | PCD_DPWW2_PR19WINCA_T | PR19 WINEP Carryover actions,Number of schemes,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 1006.6194 |  |  |  |  | 0
TMS | PCD_DPWW2_PR19WINCA_O | PR19 WINEP Carryover actions,Number of schemes,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 134.4761 | 194.337 | 323.7492 | 552.1707 | 776.6019 | 923.2801 | 983.6342 | 1026.3073 | 1035.1271 | 1035.1271 | 1035.1271
TMS | PCD_DPWW2_PR19WINCA_OT | PR19 WINEP Carryover actions,Number of schemes,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 923.2801 |  |  |  |  | 1035.1271
TMS | PCD_DPWW2_PR19WINCA_P | PR19 WINEP Carryover actions,Number of schemes,Performance | £m | Delta | [7 empty] | 0.91721
TMS | PCD_DPWW2_GGR1_NP | Greenhouse gas reduction (net zero),tCO2e/Number of sites,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_GGR1 | Greenhouse gas reduction (net zero),tCO2e/Number of sites,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_GGR1_T | Greenhouse gas reduction (net zero),tCO2e/Number of sites,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_GGR1_O | Greenhouse gas reduction (net zero),tCO2e/Number of sites,Total Expenditure by 2034-35 (Allowance) | £m | Delta
TMS | PCD_DPWW2_GGR1_OT | Greenhouse gas reduction (net zero),tCO2e/Number of sites,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_GGR1_P | Greenhouse gas reduction (net zero),tCO2e/Number of sites,Performance | £m | Delta
TMS | PCD_DPWW2_OTH1_NP | Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_OTH1 | Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total other non - PCD enhancement wastewater/bioresources expenditure, totex,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPWW2_OTH1_T | Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total other non - PCD enhancement wastewater/bioresources expenditure, totex,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPWW2_OTH1_O | Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 186.902 | 443.3964 | 667.0377 | 981.281 | 1201.9849 | 1647.8499 | 1843.189 | 1880.4465 | 1899.7175 | 1921.407 | 1927.5534
TMS | PCD_DPWW2_OTH1_OT | Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 1647.8499 |  |  |  |  | 1927.5534
TMS | PCD_DPWW2_OTH1_P | Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Total other non - PCD enhancement wastewater/bioresources expenditure, totex,Performance | £m | Delta
TMS | PCD_DPWW2_OTH2_NP | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Non delivery PCD payment (£m/Driver) in 2022-23 prices | £m | Delta
TMS | PCD_DPWW2_OTH2 | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 326.0249 | 659.2458 | 1202.9312 | 2150.3344 | 3712.2023 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW2_OTH2_T | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta | [7 empty] | 3712.2023 |  |  |  |  | 0
TMS | PCD_DPWW2_OTH2_O | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total Expenditure by 2034-35 (Allowance) | £m | Delta |  |  | 321.3781 | 711.2799 | 1284.656 | 2196.7027 | 3647.1281 | 4980.8339 | 5563.4584 | 5856.8748 | 6040.47 | 6117.1363 | 6134.2077
TMS | PCD_DPWW2_OTH2_OT | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 4980.8339 |  |  |  |  | 6134.2077
TMS | PCD_DPWW2_OTH2_P | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex,Performance | £m | Delta | [7 empty] | 1.3417
TMS | PCD_DPWW3_SOW1_NR | Storm Overflow - Wetland,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 6
TMS | PCD_DPWW3_SOW1_S0 | Storm Overflow - Wetland,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOW1_DLY | Storm Overflow - Wetland,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR | Storm Overflow - Wetland,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR | Storm Overflow - Wetland,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS | Storm Overflow - Wetland,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS | Storm Overflow - Wetland,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP | Storm Overflow - Wetland,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI | Storm Overflow - Wetland,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI | Storm Overflow - Wetland,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI | Storm Overflow - Wetland,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER | Storm Overflow - Wetland,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS | Storm Overflow - Wetland,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE | Storm Overflow - Wetland,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOW1_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 6 | 6 | 6 | 6 | 6 | 5 | 5 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOW1_DLY_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_S1 | Storm Overflow - Wetland,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOW1_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOW1_DLY_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_S2 | Storm Overflow - Wetland,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOW1_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 1 | 2 | 2 | 3 | 1 | 2 | 1 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOW1_DLY_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_S3 | Storm Overflow - Wetland,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOW1_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 1
TMS | PCD_DPWW3_SOW1_DLY_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_S4 | Storm Overflow - Wetland,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOW1_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3
TMS | PCD_DPWW3_SOW1_DLY_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_S5 | Storm Overflow - Wetland,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOW1_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 2 | 2 | 2 | 2
TMS | PCD_DPWW3_SOW1_DLY_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta | 1
TMS | PCD_DPWW3_SOW1_DIR_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_S6 | Storm Overflow - Wetland,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta | 1
TMS | PCD_DPWW3_SOW1_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOW1_DLY_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_S7 | Storm Overflow - Wetland,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOW1_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
TMS | PCD_DPWW3_SOW1_DLY_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOW1_DIR_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCR_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCS_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSCS_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPP_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOW1_DTPI_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOW1_DCI_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DSI_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOW1_DER_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOW1_RS_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOW1_DPLE_ST | Storm Overflow - Wetland,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_NR | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 7
TMS | PCD_DPWW3_TCR1_S0 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TCR1_DLY | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 7 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 3 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TCR1_DLY_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_S1 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 2 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TCR1_DLY_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_S2 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 0 | 0 | 0 | 2 | 2 | 1 | 2 | 1 | 0 | 0 | 0
TMS | PCD_DPWW3_TCR1_DLY_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_S3 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 5 | 6 | 6 | 5
TMS | PCD_DPWW3_TCR1_DLY_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_S4 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2
TMS | PCD_DPWW3_TCR1_DLY_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_S5 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TCR1_DLY_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_S6 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TCR1_DLY_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_S7 | Treatment for chemical removal (WINEP/NEP),Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TCR1_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
TMS | PCD_DPWW3_TCR1_DLY_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TCR1_DIR_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCR_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCS_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSCS_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPP_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TCR1_DTPI_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TCR1_DCI_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DSI_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_TCR1_DER_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TCR1_RS_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TCR1_DPLE_ST | Treatment for chemical removal (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_NR | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 0
TMS | PCD_DPWW3_TNR1_S0 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_S1 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_S2 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_S3 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_S4 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_S5 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_S6 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_S7 | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TNR1_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TNR1_DLY_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TNR1_DIR_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCR_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCS_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSCS_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPP_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TNR1_DTPI_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TNR1_DCI_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DSI_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_TNR1_DER_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TNR1_RS_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TNR1_DPLE_ST | Treatment for total nitrogen removal (WINEP/NEP) ,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_NR | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 0
TMS | PCD_DPWW3_NBS_SOL_S0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_S1 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_S2 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_S3 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_S4 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_S5 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_S6 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_S7 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_NBS_SOL_DLY_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DIR_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCR_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCS_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSCS_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPP_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DTPI_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DCI_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DSI_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DER_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_RS_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_NBS_SOL_DPLE_ST | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_NR | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 0
TMS | PCD_DPWW3_MBT1_S0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_S1 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_S2 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_S3 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_S4 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_S5 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_S6 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_S7 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_MBT1_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_MBT1_DLY_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_MBT1_DIR_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCR_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCS_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSCS_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPP_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_MBT1_DTPI_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_MBT1_DCI_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DSI_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_MBT1_DER_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_MBT1_RS_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_MBT1_DPLE_ST | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP),Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_NR | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 0
TMS | PCD_DPWW3_SSCP_S0 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_S1 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_S2 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_S3 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_S4 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_S5 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_S6 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_S7 | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SSCP_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SSCP_DLY_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SSCP_DIR_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCR_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCS_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSCS_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPP_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SSCP_DTPI_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SSCP_DCI_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DSI_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_SSCP_DER_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SSCP_RS_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SSCP_DPLE_ST | Sludge storage (cake pads) - Sludge Storage area delivered,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_NR | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 0
TMS | PCD_DPWW3_STOTH1_S0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_S1 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_S2 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_S3 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_S4 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_S5 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_S6 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_S7 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH1_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH1_DLY_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DIR_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCR_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCS_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSCS_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPP_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DTPI_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DCI_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DSI_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DER_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH1_RS_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH1_DPLE_ST | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_NR | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 0
TMS | PCD_DPWW3_STOTH2_S0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_S1 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_S2 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_S3 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_S4 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_S5 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_S6 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_S7 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_STOTH2_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_STOTH2_DLY_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DIR_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCR_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCS_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSCS_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPP_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DTPI_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DCI_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DSI_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DER_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_STOTH2_RS_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_STOTH2_DPLE_ST | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_NR | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 25
TMS | PCD_DPWW3_BIO_IED_S0 | Bioresources - IED and Reg changes,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_BIO_IED_DLY | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE | Bioresources - IED and Reg changes,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 2 | 24 | 24 | 22 | 22 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 18 | 18 | 10 | 9
TMS | PCD_DPWW3_BIO_IED_DLY_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_S1 | Bioresources - IED and Reg changes,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 1 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 9
TMS | PCD_DPWW3_BIO_IED_DLY_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_S2 | Bioresources - IED and Reg changes,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 3
TMS | PCD_DPWW3_BIO_IED_DLY_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_S3 | Bioresources - IED and Reg changes,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 2
TMS | PCD_DPWW3_BIO_IED_DLY_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_S4 | Bioresources - IED and Reg changes,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_BIO_IED_DLY_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_S5 | Bioresources - IED and Reg changes,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2
TMS | PCD_DPWW3_BIO_IED_DLY_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_S6 | Bioresources - IED and Reg changes,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_BIO_IED_DLY_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_S7 | Bioresources - IED and Reg changes,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25
TMS | PCD_DPWW3_BIO_IED_DLY_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DIR_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCR_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCS_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSCS_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPP_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DTPI_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DCI_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DSI_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DER_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_RS_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_BIO_IED_DPLE_ST | Bioresources - IED and Reg changes,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_NR | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 106
TMS | PCD_DPWW3_SOES_S0 | Storm overflows - Equivalent storage,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 3 | 3 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOES_DLY | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE | Storm overflows - Equivalent storage,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 103 | 103 | 105 | 105 | 106 | 98 | 90 | 47 | 28 | 23 | 7 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOES_DLY_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_S1 | Storm overflows - Equivalent storage,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 8 | 16 | 55 | 69 | 67 | 47 | 26 | 20 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOES_DLY_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_S2 | Storm overflows - Equivalent storage,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 7 | 11 | 42 | 62 | 62 | 33 | 18 | 14 | 5 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOES_DLY_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_S3 | Storm overflows - Equivalent storage,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 5 | 8 | 36 | 50 | 50 | 58 | 54 | 33 | 26 | 17
TMS | PCD_DPWW3_SOES_DLY_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_S4 | Storm overflows - Equivalent storage,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 17 | 15 | 16
TMS | PCD_DPWW3_SOES_DLY_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_S5 | Storm overflows - Equivalent storage,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 5 | 8 | 11 | 16 | 28 | 33 | 42 | 43 | 49 | 56 | 65 | 73
TMS | PCD_DPWW3_SOES_DLY_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta | 14
TMS | PCD_DPWW3_SOES_DIR_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_S6 | Storm overflows - Equivalent storage,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta | 14
TMS | PCD_DPWW3_SOES_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_SOES_DLY_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_S7 | Storm overflows - Equivalent storage,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_SOES_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106 | 106
TMS | PCD_DPWW3_SOES_DLY_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_SOES_DIR_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCR_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_SOES_DCS_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_SOES_DSCS_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_SOES_DPP_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_SOES_DTPI_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_SOES_DCI_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DSI_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_SOES_DER_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_SOES_RS_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_SOES_DPLE_ST | Storm overflows - Equivalent storage,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_NR | Flow to Full Treatment,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 17
TMS | PCD_DPWW3_FTFT_S0 | Flow to Full Treatment,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_FTFT_DLY | Flow to Full Treatment,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR | Flow to Full Treatment,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR | Flow to Full Treatment,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS | Flow to Full Treatment,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS | Flow to Full Treatment,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP | Flow to Full Treatment,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI | Flow to Full Treatment,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI | Flow to Full Treatment,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI | Flow to Full Treatment,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER | Flow to Full Treatment,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS | Flow to Full Treatment,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE | Flow to Full Treatment,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_S1 | Flow to Full Treatment,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 16 | 16 | 17 | 17 | 17 | 16 | 13 | 8 | 7 | 7 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_FTFT_DLY_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_S1 | Flow to Full Treatment,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_S2 | Flow to Full Treatment,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 3 | 7 | 8 | 7 | 8 | 6 | 7 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_FTFT_DLY_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_S2 | Flow to Full Treatment,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_S3 | Flow to Full Treatment,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 6 | 5 | 4 | 4 | 5 | 3 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_FTFT_DLY_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_S3 | Flow to Full Treatment,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_S4 | Flow to Full Treatment,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 7 | 7 | 8 | 10 | 12 | 9 | 8 | 5
TMS | PCD_DPWW3_FTFT_DLY_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_S4 | Flow to Full Treatment,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_S5 | Flow to Full Treatment,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3
TMS | PCD_DPWW3_FTFT_DLY_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_S5 | Flow to Full Treatment,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_S6 | Flow to Full Treatment,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 3 | 3 | 3 | 4 | 4 | 5 | 7 | 7 | 9
TMS | PCD_DPWW3_FTFT_DLY_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_S6 | Flow to Full Treatment,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_S7 | Flow to Full Treatment,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_FTFT_DLY_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_S7 | Flow to Full Treatment,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_FTFT_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17
TMS | PCD_DPWW3_FTFT_DLY_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_FTFT_DIR_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCR_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCS_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSCS_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPP_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_FTFT_DTPI_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_FTFT_DCI_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DSI_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_FTFT_DER_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_FTFT_RS_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_FTFT_DPLE_ST | Flow to Full Treatment,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_NR | P-removal,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 98
TMS | PCD_DPWW3_PRMVL_S0 | P-removal,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PRMVL_DLY | P-removal,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR | P-removal,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR | P-removal,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS | P-removal,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS | P-removal,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP | P-removal,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI | P-removal,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI | P-removal,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI | P-removal,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER | P-removal,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS | P-removal,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE | P-removal,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_S1 | P-removal,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 89 | 87 | 88 | 85 | 82 | 76 | 61 | 25 | 18 | 7 | 5 | 4 | 3 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPWW3_PRMVL_DLY_S1 | P-removal,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR_S1 | P-removal,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_S1 | P-removal,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_S1 | P-removal,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_S1 | P-removal,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_S1 | P-removal,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_S1 | P-removal,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_S1 | P-removal,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_S1 | P-removal,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_S1 | P-removal,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_S1 | P-removal,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_S1 | P-removal,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_S2 | P-removal,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 3 | 5 | 3 | 4 | 6 | 11 | 24 | 57 | 58 | 64 | 51 | 26 | 8 | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PRMVL_DLY_S2 | P-removal,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR_S2 | P-removal,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_S2 | P-removal,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_S2 | P-removal,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_S2 | P-removal,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_S2 | P-removal,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_S2 | P-removal,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_S2 | P-removal,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_S2 | P-removal,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_S2 | P-removal,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_S2 | P-removal,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_S2 | P-removal,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_S3 | P-removal,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 1 | 3 | 3 | 4 | 3 | 5 | 7 | 10 | 10 | 21 | 40 | 43 | 24 | 8 | 4 | 3 | 3 | 1 | 0 | 0
TMS | PCD_DPWW3_PRMVL_DLY_S3 | P-removal,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR_S3 | P-removal,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_S3 | P-removal,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_S3 | P-removal,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_S3 | P-removal,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_S3 | P-removal,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_S3 | P-removal,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_S3 | P-removal,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_S3 | P-removal,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_S3 | P-removal,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_S3 | P-removal,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_S3 | P-removal,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_S4 | P-removal,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 2 | 1 | 3 | 3 | 3 | 6 | 11 | 15 | 22 | 37 | 61 | 75 | 79 | 71 | 64 | 49 | 33 | 16
TMS | PCD_DPWW3_PRMVL_DLY_S4 | P-removal,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR_S4 | P-removal,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_S4 | P-removal,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_S4 | P-removal,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_S4 | P-removal,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_S4 | P-removal,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_S4 | P-removal,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_S4 | P-removal,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_S4 | P-removal,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_S4 | P-removal,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_S4 | P-removal,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_S4 | P-removal,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_S5 | P-removal,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 5 | 7 | 13 | 21 | 38 | 54 | 45
TMS | PCD_DPWW3_PRMVL_DLY_S5 | P-removal,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR_S5 | P-removal,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_S5 | P-removal,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_S5 | P-removal,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_S5 | P-removal,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_S5 | P-removal,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_S5 | P-removal,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_S5 | P-removal,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_S5 | P-removal,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_S5 | P-removal,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_S5 | P-removal,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_S5 | P-removal,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_S6 | P-removal,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 4 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 9 | 9 | 9 | 10 | 36
TMS | PCD_DPWW3_PRMVL_DLY_S6 | P-removal,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta | 2
TMS | PCD_DPWW3_PRMVL_DIR_S6 | P-removal,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_S6 | P-removal,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_S6 | P-removal,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_S6 | P-removal,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_S6 | P-removal,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_S6 | P-removal,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_S6 | P-removal,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_S6 | P-removal,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_S6 | P-removal,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_S6 | P-removal,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_S6 | P-removal,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_S7 | P-removal,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PRMVL_DLY_S7 | P-removal,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR_S7 | P-removal,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_S7 | P-removal,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_S7 | P-removal,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_S7 | P-removal,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_S7 | P-removal,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_S7 | P-removal,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_S7 | P-removal,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_S7 | P-removal,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_S7 | P-removal,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_S7 | P-removal,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_S7 | P-removal,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PRMVL_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98
TMS | PCD_DPWW3_PRMVL_DLY_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DIR_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCR_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCS_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSCS_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPP_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DTPI_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DCI_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DSI_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DER_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PRMVL_RS_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PRMVL_DPLE_ST | P-removal,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_NR | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 15
TMS | PCD_DPWW3_GSTW_S0 | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GSTW_DLY | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE | Growth to Sewerage Treatment Works,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 15 | 15 | 15 | 14 | 14 | 10 | 9 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GSTW_DLY_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_S1 | Growth to Sewerage Treatment Works,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 1 | 1 | 5 | 5 | 11 | 10 | 9 | 8 | 5 | 4 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GSTW_DLY_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_S2 | Growth to Sewerage Treatment Works,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 5 | 5 | 4 | 5 | 5 | 5 | 1 | 1 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GSTW_DLY_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_S3 | Growth to Sewerage Treatment Works,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 6 | 6 | 9 | 10 | 14 | 13 | 13 | 8 | 6 | 3
TMS | PCD_DPWW3_GSTW_DLY_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_S4 | Growth to Sewerage Treatment Works,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 5 | 6 | 4
TMS | PCD_DPWW3_GSTW_DLY_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_S5 | Growth to Sewerage Treatment Works,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 8
TMS | PCD_DPWW3_GSTW_DLY_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta | 1
TMS | PCD_DPWW3_GSTW_DIR_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_S6 | Growth to Sewerage Treatment Works,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GSTW_DLY_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_S7 | Growth to Sewerage Treatment Works,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GSTW_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
TMS | PCD_DPWW3_GSTW_DLY_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GSTW_DIR_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCR_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCS_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSCS_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPP_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GSTW_DTPI_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GSTW_DCI_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DSI_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_GSTW_DER_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GSTW_RS_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GSTW_DPLE_ST | Growth to Sewerage Treatment Works,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_NR | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 21
TMS | PCD_DPWW3_TTSP_S0 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TTSP_DLY | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE | Treatment for tightening of sanitary parameters,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 17 | 15 | 15 | 10 | 9 | 9 | 8 | 5 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TTSP_DLY_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_S1 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 4 | 3 | 3 | 6 | 6 | 1 | 2 | 4 | 5 | 9 | 9 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TTSP_DLY_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_S2 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 1 | 1 | 3 | 1 | 6 | 5 | 3 | 2 | 0 | 0 | 4 | 8 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TTSP_DLY_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_S3 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 2 | 2 | 2 | 0 | 0 | 1 | 4 | 5 | 7 | 3 | 3 | 3 | 6 | 10 | 10 | 8 | 8 | 7 | 3 | 2
TMS | PCD_DPWW3_TTSP_DLY_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_S4 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 4 | 4 | 5 | 5 | 5 | 5 | 5 | 6 | 10 | 5
TMS | PCD_DPWW3_TTSP_DLY_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_S5 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 8 | 8 | 8 | 8 | 14
TMS | PCD_DPWW3_TTSP_DLY_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_S6 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_TTSP_DLY_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_S7 | Treatment for tightening of sanitary parameters,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_TTSP_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21
TMS | PCD_DPWW3_TTSP_DLY_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_TTSP_DIR_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCR_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCS_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSCS_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPP_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_TTSP_DTPI_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_TTSP_DCI_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DSI_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_TTSP_DER_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_TTSP_RS_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_TTSP_DPLE_ST | Treatment for tightening of sanitary parameters,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_NR | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 68
TMS | PCD_DPWW3_PR19WINCA_S0 | PR19 WINEP Carryover actions,Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PR19WINCA_DLY | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE | PR19 WINEP Carryover actions,Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 4 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PR19WINCA_DLY_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_S1 | PR19 WINEP Carryover actions,Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 42 | 41 | 37 | 31 | 28 | 22 | 19 | 10 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PR19WINCA_DLY_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_S2 | PR19 WINEP Carryover actions,Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 1 | 3 | 4 | 5 | 5 | 10 | 7 | 9 | 8 | 4 | 4 | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PR19WINCA_DLY_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_S3 | PR19 WINEP Carryover actions,Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 12 | 13 | 15 | 19 | 13 | 15 | 22 | 29 | 33 | 37 | 37 | 35 | 34 | 31 | 22 | 19 | 14 | 11 | 11 | 9 | 3
TMS | PCD_DPWW3_PR19WINCA_DLY_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_S4 | PR19 WINEP Carryover actions,Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PR19WINCA_DLY_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_S5 | PR19 WINEP Carryover actions,Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 9 | 9 | 10 | 11 | 20 | 20 | 20 | 20 | 23 | 25 | 26 | 30 | 33 | 36 | 45 | 49 | 54 | 57 | 57 | 59 | 65
TMS | PCD_DPWW3_PR19WINCA_DLY_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta | 11
TMS | PCD_DPWW3_PR19WINCA_DIR_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta | 4 +3 TBC as these are PCDWW35 CONTRIBUTOR
TMS | PCD_DPWW3_PR19WINCA_DSCS_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Third-party interface | Nr | Delta | 1
TMS | PCD_DPWW3_PR19WINCA_DCI_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_S6 | PR19 WINEP Carryover actions,Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_PR19WINCA_DLY_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_S7 | PR19 WINEP Carryover actions,Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68
TMS | PCD_DPWW3_PR19WINCA_DLY_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DIR_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCR_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCS_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSCS_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPP_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DTPI_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DCI_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DSI_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DER_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_RS_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_PR19WINCA_DPLE_ST | PR19 WINEP Carryover actions,Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_NR | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Number of Schemes (Nr) | Nr | Delta | 0
TMS | PCD_DPWW3_GGR1_S0 | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Programme level efficiency | Nr | Delta
TMS | PCD_DPWW3_GGR1_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),IM1 has yet to be achieved | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPWW3_GGR1_DLY_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM | Nr | Delta
TMS | PCD_DPWW3_GGR1_DIR_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Lack of internal resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCR_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Lack of supply chain resourcing | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCS_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Change in solution (IM2) | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSCS_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Supply chain capacity | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPP_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Land and planning permission | Nr | Delta
TMS | PCD_DPWW3_GGR1_DTPI_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Third-party interface | Nr | Delta
TMS | PCD_DPWW3_GGR1_DCI_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Contractual issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DSI_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Sites issues | Nr | Delta
TMS | PCD_DPWW3_GGR1_DER_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Environmental risks | Nr | Delta
TMS | PCD_DPWW3_GGR1_RS_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPWW3_GGR1_DPLE_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Programme level efficiency | Nr | Delta
TMS | PCD_DPW1_BIOCON1 | Biodiversity and Conservation hectares,Hectares of environmental improvement,PCD Output (Cumulative) - Target | ha | Delta
TMS | PCD_DPW1_BIOCON1_T | Biodiversity and Conservation hectares,Hectares of environmental improvement,PCD output by 2029-30 (Target) | ha | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_BIOCON1_O | Biodiversity and Conservation hectares,Hectares of environmental improvement,PCD Output (Cumulative) - Outturn & Forecast | ha | Delta
TMS | PCD_DPW1_BIOCON1_OT | Biodiversity and Conservation hectares,Hectares of environmental improvement,PCD output by 2029-30 (Outturn & Forecast) | ha | Delta
TMS | PCD_DPW1_BIOCON1_P | Biodiversity and Conservation hectares,Hectares of environmental improvement,Performance (Output) | ha | Delta
TMS | PCD_DPW1_BIOCON2 | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,PCD Output (Cumulative) - Target | km | Delta
TMS | PCD_DPW1_BIOCON2_T | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,PCD output by 2029-30 (Target) | km | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_BIOCON2_O | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,PCD Output (Cumulative) - Outturn & Forecast | km | Delta
TMS | PCD_DPW1_BIOCON2_OT | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,PCD output by 2029-30 (Outturn & Forecast) | km | Delta
TMS | PCD_DPW1_BIOCON2_P | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,Performance (Output) | km | Delta
TMS | PCD_DPW1_DWPA | Drinking Water Protected Areas,No Deterioration and Implementation actions,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_DWPA_T | Drinking Water Protected Areas,No Deterioration and Implementation actions,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_DWPA_O | Drinking Water Protected Areas,No Deterioration and Implementation actions,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_DWPA_OT | Drinking Water Protected Areas,No Deterioration and Implementation actions,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_DWPA_P | Drinking Water Protected Areas,No Deterioration and Implementation actions,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_WFDI | Water Framework Directive interconnector,Length of WFD interconnector,PCD Output (Cumulative) - Target | km | Delta |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5
TMS | PCD_DPW1_WFDI_T | Water Framework Directive interconnector,Length of WFD interconnector,PCD output by 2029-30 (Target) | km | Delta | [7 empty] | 9.5 |  |  |  |  | 9.5
TMS | PCD_DPW1_WFDI_O | Water Framework Directive interconnector,Length of WFD interconnector,PCD Output (Cumulative) - Outturn & Forecast | km | Delta | [7 empty] | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5
TMS | PCD_DPW1_WFDI_OT | Water Framework Directive interconnector,Length of WFD interconnector,PCD output by 2029-30 (Outturn & Forecast) | km | Delta | [7 empty] | 9.5 |  |  |  |  | 9.5
TMS | PCD_DPW1_WFDI_P | Water Framework Directive interconnector,Length of WFD interconnector,Performance (Output) | km | Delta | [7 empty] | 1 |  |  |  |  | 1
TMS | PCD_DPW1_WFDA | Water Framework Directive actions,Other WFD actions,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19 | 19 | 19 | 19
TMS | PCD_DPW1_WFDA_T | Water Framework Directive actions,Other WFD actions,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 19 |  |  |  |  | 19
TMS | PCD_DPW1_WFDA_O | Water Framework Directive actions,Other WFD actions,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta | [7 empty] | 19 | 19 | 19 | 19 | 19 | 19
TMS | PCD_DPW1_WFDA_OT | Water Framework Directive actions,Other WFD actions,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 19 |  |  |  |  | 19
TMS | PCD_DPW1_WFDA_P | Water Framework Directive actions,Other WFD actions,Performance (Output) | Nr | Delta | [7 empty] | 1 |  |  |  |  | 1
TMS | PCD_DPW1_WIVG | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,PCD Output (Cumulative) - Target | Nr | Delta |  |  |  | 0 | 0 | 37 | 37 | 37
TMS | PCD_DPW1_WIVG_T | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 37 |  |  |  |  | 0
TMS | PCD_DPW1_WIVG_O | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  |  | 22 | 35 | 35 | 37 | 37 | 37 | 37 | 37 | 37
TMS | PCD_DPW1_WIVG_OT | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 37 |  |  |  |  | 37
TMS | PCD_DPW1_WIVG_P | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,Performance (Output) | Nr | Delta | [7 empty] | 1
TMS | PCD_DPW1_RWD | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,PCD Output (Cumulative) - Target | Nr | Delta | [9 empty] | 5 | 5 | 5 | 6
TMS | PCD_DPW1_RWD_T | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 6
TMS | PCD_DPW1_RWD_O | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_RWD_OT | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RWD_P | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,Performance (Output) | Nr | Delta | [12 empty] | 0
TMS | PCD_DPW1_LEAD1 | Lead,Lead communication pipes replaced/relined,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 8000 | 19500 | 31000 | 42500 | 54000
TMS | PCD_DPW1_LEAD1_T | Lead,Lead communication pipes replaced/relined,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 54000 |  |  |  |  | 0
TMS | PCD_DPW1_LEAD1_O | Lead,Lead communication pipes replaced/relined,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 6222 | 18375 | 30250 | 42125 | 54000
TMS | PCD_DPW1_LEAD1_OT | Lead,Lead communication pipes replaced/relined,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 54000
TMS | PCD_DPW1_LEAD1_P | Lead,Lead communication pipes replaced/relined,Performance (Output) | Nr | Delta | [7 empty] | 1
TMS | PCD_DPW1_LEAD2 | Lead,Lead external supply pipes replaced/relined - Non-schools,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_LEAD2_T | Lead,Lead external supply pipes replaced/relined - Non-schools,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_LEAD2_O | Lead,Lead external supply pipes replaced/relined - Non-schools,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_LEAD2_OT | Lead,Lead external supply pipes replaced/relined - Non-schools,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_LEAD2_P | Lead,Lead external supply pipes replaced/relined - Non-schools,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_LEAD3 | Lead,Lead external supply pipes replaced/relined - Schools,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_LEAD3_T | Lead,Lead external supply pipes replaced/relined - Schools,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_LEAD3_O | Lead,Lead external supply pipes replaced/relined - Schools,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_LEAD3_OT | Lead,Lead external supply pipes replaced/relined - Schools,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_LEAD3_P | Lead,Lead external supply pipes replaced/relined - Schools,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_LEAD4 | Lead,Lead internal supply pipes replaced/relined - Non-schools,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_LEAD4_T | Lead,Lead internal supply pipes replaced/relined - Non-schools,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_LEAD4_O | Lead,Lead internal supply pipes replaced/relined - Non-schools,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_LEAD4_OT | Lead,Lead internal supply pipes replaced/relined - Non-schools,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_LEAD4_P | Lead,Lead internal supply pipes replaced/relined - Non-schools,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_LEAD5 | Lead,Lead internal supply pipes replaced/relined - Schools,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_LEAD5_T | Lead,Lead internal supply pipes replaced/relined - Schools,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_LEAD5_O | Lead,Lead internal supply pipes replaced/relined - Schools,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_LEAD5_OT | Lead,Lead internal supply pipes replaced/relined - Schools,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_LEAD5_P | Lead,Lead internal supply pipes replaced/relined - Schools,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_WRESUP | W Resilience CC Uplift,Spend on scheme as a % of allowance,PCD Output (Cumulative) - Target | % | Delta | [7 empty] | 100
TMS | PCD_DPW1_WRESUP_T | W Resilience CC Uplift,Spend on scheme as a % of allowance,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 100 |  |  |  |  | 0
TMS | PCD_DPW1_WRESUP_O | W Resilience CC Uplift,Spend on scheme as a % of allowance,PCD Output (Cumulative) - Outturn & Forecast | % | Delta |  | 0 | 0 | 3.1888 | 13.219 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654 | 15.6654
TMS | PCD_DPW1_WRESUP_OT | W Resilience CC Uplift,Spend on scheme as a % of allowance,PCD output by 2029-30 (Outturn & Forecast) | % | Delta | [7 empty] | 15.6654 |  |  |  |  | 15.6654
TMS | PCD_DPW1_WRESUP_P | W Resilience CC Uplift,Spend on scheme as a % of allowance,Performance (Output) | % | Delta | [7 empty] | 0.15665
TMS | PCD_DPW1_MTR1 | Metering,New installations,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 69816 | 139633 | 209449 | 279266 | 349082
TMS | PCD_DPW1_MTR1_T | Metering,New installations,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 349082 |  |  |  |  | 0
TMS | PCD_DPW1_MTR1_O | Metering,New installations,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 99861 | 181638 | 245466 | 296811 | 349081 | 349081 | 349081 | 349081 | 349081 | 349081
TMS | PCD_DPW1_MTR1_OT | Metering,New installations,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 349081 |  |  |  |  | 349081
TMS | PCD_DPW1_MTR1_P | Metering,New installations,Performance (Output) | Nr | Delta | [7 empty] | 1
TMS | PCD_DPW1_MTR2 | Metering,Household meter upgrades,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 129098 | 258196 | 387294 | 516392 | 645490
TMS | PCD_DPW1_MTR2_T | Metering,Household meter upgrades,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 645490 |  |  |  |  | 0
TMS | PCD_DPW1_MTR2_O | Metering,Household meter upgrades,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 145741 | 314801 | 466801 | 585998 | 694491 | 694491 | 694491 | 694491 | 694491 | 694491
TMS | PCD_DPW1_MTR2_OT | Metering,Household meter upgrades,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 694491 |  |  |  |  | 694491
TMS | PCD_DPW1_MTR2_P | Metering,Household meter upgrades,Performance (Output) | Nr | Delta | [7 empty] | 1.0759
TMS | PCD_DPW1_MTR3 | Metering,Non household meter upgrades,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 22657 | 45315 | 67971 | 90629 | 113286
TMS | PCD_DPW1_MTR3_T | Metering,Non household meter upgrades,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 113286 |  |  |  |  | 0
TMS | PCD_DPW1_MTR3_O | Metering,Non household meter upgrades,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 24418 | 51185 | 79685 | 107685 | 128286 | 128286 | 128286 | 128286 | 128286 | 128286
TMS | PCD_DPW1_MTR3_OT | Metering,Non household meter upgrades,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 128286 |  |  |  |  | 128286
TMS | PCD_DPW1_MTR3_P | Metering,Non household meter upgrades,Performance (Output) | Nr | Delta | [7 empty] | 1.1324
TMS | PCD_DPW1_MTR4 | Metering,Large bulk meters,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 875 | 1750 | 2625 | 3500 | 4375
TMS | PCD_DPW1_MTR4_T | Metering,Large bulk meters,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 4375 |  |  |  |  | 0
TMS | PCD_DPW1_MTR4_O | Metering,Large bulk meters,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 905 | 3050 | 5260 | 6818 | 9175 | 9175 | 9175 | 9175 | 9175 | 9175
TMS | PCD_DPW1_MTR4_OT | Metering,Large bulk meters,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 9175 |  |  |  |  | 9175
TMS | PCD_DPW1_MTR4_P | Metering,Large bulk meters,Performance (Output) | Nr | Delta | [7 empty] | 2.0971
TMS | PCD_DPW1_MTR5 | Metering,Small bulk meters,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 10184 | 20368 | 30552 | 40736 | 50920
TMS | PCD_DPW1_MTR5_T | Metering,Small bulk meters,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 50920 |  |  |  |  | 0
TMS | PCD_DPW1_MTR5_O | Metering,Small bulk meters,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 5626 | 17012 | 30782 | 42552 | 50920 | 50920 | 50920 | 50920 | 50920 | 50920
TMS | PCD_DPW1_MTR5_OT | Metering,Small bulk meters,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 50920 |  |  |  |  | 50920
TMS | PCD_DPW1_MTR5_P | Metering,Small bulk meters,Performance (Output) | Nr | Delta | [7 empty] | 1
TMS | PCD_DPW1_MTR6 | Metering,Meter Replacements,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 151755 | 303511 | 455266 | 607021 | 758776
TMS | PCD_DPW1_MTR6_T | Metering,Meter Replacements,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 758776 |  |  |  |  | 0
TMS | PCD_DPW1_MTR6_O | Metering,Meter Replacements,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 170421 | 368421.0338 | 548921.0338 | 696118.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338 | 825212.0338
TMS | PCD_DPW1_MTR6_OT | Metering,Meter Replacements,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 825212.0338 |  |  |  |  | 825212.0338
TMS | PCD_DPW1_MTR6_P | Metering,Meter Replacements,Performance (Output) | Nr | Delta | [7 empty] | 1.0876
TMS | PCD_DPW1_MTR7 | Metering,Connected meters,PCD Output (Cumulative) - Target | Nr | Delta |  | 0 | 0 | 0 | 116315 | 279157 | 488525 | 744419
TMS | PCD_DPW1_MTR7_T | Metering,Connected meters,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 744419 |  |  |  |  | 0
TMS | PCD_DPW1_MTR7_O | Metering,Connected meters,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta |  |  |  | 0 | 138275.5 | 340611.6 | 579595.8 | 831891.2 | 831891.2 | 831891.2 | 831891.2 | 831891.2 | 831891.2
TMS | PCD_DPW1_MTR7_OT | Metering,Connected meters,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [7 empty] | 831891.2 |  |  |  |  | 831891.2
TMS | PCD_DPW1_MTR7_P | Metering,Connected meters,Performance (Output) | Nr | Delta | [7 empty] | 1.1175
TMS | PCD_DPW1_SPL1 | Supply,WAFU Benefit [Base Overlap Schemes],PCD Output (Cumulative) - Target | Ml/d | Delta |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW1_SPL1_T | Supply,WAFU Benefit [Base Overlap Schemes],PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_SPL1_O | Supply,WAFU Benefit [Base Overlap Schemes],PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta
TMS | PCD_DPW1_SPL1_OT | Supply,WAFU Benefit [Base Overlap Schemes],PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta
TMS | PCD_DPW1_SPL1_P | Supply,WAFU Benefit [Base Overlap Schemes],Performance (Output) | Ml/d | Delta
TMS | PCD_DPW1_SPL2 | Supply,WAFU Benefit [Medium],PCD Output (Cumulative) - Target | Ml/d | Delta |  | 0 | 0 | 0 | 0 | 2.7 | 2.7 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76
TMS | PCD_DPW1_SPL2_T | Supply,WAFU Benefit [Medium],PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 20.76 |  |  |  |  | 20.76
TMS | PCD_DPW1_SPL2_O | Supply,WAFU Benefit [Medium],PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta | [7 empty] | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76
TMS | PCD_DPW1_SPL2_OT | Supply,WAFU Benefit [Medium],PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta | [7 empty] | 20.76 |  |  |  |  | 20.76
TMS | PCD_DPW1_SPL2_P | Supply,WAFU Benefit [Medium],Performance (Output) | Ml/d | Delta | [7 empty] | 1 |  |  |  |  | 1
TMS | PCD_DPW1_SPL3 | Supply,WAFU Benefit [Low],PCD Output (Cumulative) - Target | Ml/d | Delta |  | 0 | 0 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW1_SPL3_T | Supply,WAFU Benefit [Low],PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 22.6 |  |  |  |  | 0
TMS | PCD_DPW1_SPL3_O | Supply,WAFU Benefit [Low],PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta |  |  |  | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6
TMS | PCD_DPW1_SPL3_OT | Supply,WAFU Benefit [Low],PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta | [7 empty] | 22.6 |  |  |  |  | 22.6
TMS | PCD_DPW1_SPL3_P | Supply,WAFU Benefit [Low],Performance (Output) | Ml/d | Delta | [7 empty] | 1
TMS | PCD_DPW1_SPL4 | Supply,WAFU Benefit [Very Low],PCD Output (Cumulative) - Target | Ml/d | Delta |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW1_SPL4_T | Supply,WAFU Benefit [Very Low],PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_SPL4_O | Supply,WAFU Benefit [Very Low],PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW1_SPL4_OT | Supply,WAFU Benefit [Very Low],PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_SPL4_P | Supply,WAFU Benefit [Very Low],Performance (Output) | Ml/d | Delta
TMS | PCD_DPW1_SPL5 | Supply,WAFU Benefit [Total],PCD Output (Cumulative) - Target | Ml/d | Delta |  | 0 | 0 | 22.6 | 22.6 | 25.3 | 25.3 | 43.36 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76
TMS | PCD_DPW1_SPL5_T | Supply,WAFU Benefit [Total],PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 43.36 |  |  |  |  | 20.76
TMS | PCD_DPW1_SPL5_O | Supply,WAFU Benefit [Total],PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta |  | 0 | 0 | 22.6 | 22.6 | 22.6 | 22.6 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36
TMS | PCD_DPW1_SPL5_OT | Supply,WAFU Benefit [Total],PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta | [7 empty] | 43.36 |  |  |  |  | 43.36
TMS | PCD_DPW1_SPL5_P | Supply,WAFU Benefit [Total],Performance (Output) | Ml/d | Delta | [7 empty] | 1 |  |  |  |  | 2.0886
TMS | PCD_DPW1_SPLIN1 | Supply interconnectors,WAFU Benefit,PCD Output (Cumulative) - Target | Ml/d | Delta
TMS | PCD_DPW1_SPLIN1_T | Supply interconnectors,WAFU Benefit,PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_SPLIN1_O | Supply interconnectors,WAFU Benefit,PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta
TMS | PCD_DPW1_SPLIN1_OT | Supply interconnectors,WAFU Benefit,PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta
TMS | PCD_DPW1_SPLIN1_P | Supply interconnectors,WAFU Benefit,Performance (Output) | Ml/d | Delta
TMS | PCD_DPW1_SPLIN2 | Supply interconnectors,Pipeline length ,PCD Output (Cumulative) - Target | Km | Delta
TMS | PCD_DPW1_SPLIN2_T | Supply interconnectors,Pipeline length ,PCD output by 2029-30 (Target) | Km | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_SPLIN2_O | Supply interconnectors,Pipeline length ,PCD Output (Cumulative) - Outturn & Forecast | Km | Delta
TMS | PCD_DPW1_SPLIN2_OT | Supply interconnectors,Pipeline length ,PCD output by 2029-30 (Outturn & Forecast) | Km | Delta
TMS | PCD_DPW1_SPLIN2_P | Supply interconnectors,Pipeline length ,Performance (Output) | Km | Delta
TMS | PCD_DPW1_EFCY | Efficiency,Water demand savings (benefit),PCD Output (Cumulative) - Target | Ml/d | Delta
TMS | PCD_DPW1_EFCY_T | Efficiency,Water demand savings (benefit),PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_EFCY_O | Efficiency,Water demand savings (benefit),PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta
TMS | PCD_DPW1_EFCY_OT | Efficiency,Water demand savings (benefit),PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta
TMS | PCD_DPW1_EFCY_P | Efficiency,Water demand savings (benefit),Performance (Output) | Ml/d | Delta
TMS | PCD_DPW1_RESIN1 | Resilience Interconnector,Length of resilience interconnector,PCD Output (Cumulative) - Target | km | Delta
TMS | PCD_DPW1_RESIN1_T | Resilience Interconnector,Length of resilience interconnector,PCD output by 2029-30 (Target) | km | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RESIN1_O | Resilience Interconnector,Length of resilience interconnector,PCD Output (Cumulative) - Outturn & Forecast | km | Delta
TMS | PCD_DPW1_RESIN1_OT | Resilience Interconnector,Length of resilience interconnector,PCD output by 2029-30 (Outturn & Forecast) | km | Delta
TMS | PCD_DPW1_RESIN1_P | Resilience Interconnector,Length of resilience interconnector,Performance (Output) | km | Delta
TMS | PCD_DPW1_RESIN2 | Resilience Interconnector,Crossing connections improvement,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_RESIN2_T | Resilience Interconnector,Crossing connections improvement,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RESIN2_O | Resilience Interconnector,Crossing connections improvement,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_RESIN2_OT | Resilience Interconnector,Crossing connections improvement,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_RESIN2_P | Resilience Interconnector,Crossing connections improvement,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_RESIN3 | Resilience Interconnector,Additional storage at reservoirs,PCD Output (Cumulative) - Target | Ml | Delta
TMS | PCD_DPW1_RESIN3_T | Resilience Interconnector,Additional storage at reservoirs,PCD output by 2029-30 (Target) | Ml | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RESIN3_O | Resilience Interconnector,Additional storage at reservoirs,PCD Output (Cumulative) - Outturn & Forecast | Ml | Delta
TMS | PCD_DPW1_RESIN3_OT | Resilience Interconnector,Additional storage at reservoirs,PCD output by 2029-30 (Outturn & Forecast) | Ml | Delta
TMS | PCD_DPW1_RESIN3_P | Resilience Interconnector,Additional storage at reservoirs,Performance (Output) | Ml | Delta
TMS | PCD_DPW1_RESIN4 | Resilience Interconnector,Reservoir bypass,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_RESIN4_T | Resilience Interconnector,Reservoir bypass,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RESIN4_O | Resilience Interconnector,Reservoir bypass,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_RESIN4_OT | Resilience Interconnector,Reservoir bypass,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_RESIN4_P | Resilience Interconnector,Reservoir bypass,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_RES1 | Resilience ,Number of water treatment works with new equipment ,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_RES1_T | Resilience ,Number of water treatment works with new equipment ,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RES1_O | Resilience ,Number of water treatment works with new equipment ,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_RES1_OT | Resilience ,Number of water treatment works with new equipment ,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_RES1_P | Resilience ,Number of water treatment works with new equipment ,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_RES2 | Resilience ,Upgrade works at water treatment works,PCD Output (Cumulative) - Target | % | Delta
TMS | PCD_DPW1_RES2_T | Resilience ,Upgrade works at water treatment works,PCD output by 2029-30 (Target) | % | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RES2_O | Resilience ,Upgrade works at water treatment works,PCD Output (Cumulative) - Outturn & Forecast | % | Delta
TMS | PCD_DPW1_RES2_OT | Resilience ,Upgrade works at water treatment works,PCD output by 2029-30 (Outturn & Forecast) | % | Delta
TMS | PCD_DPW1_RES2_P | Resilience ,Upgrade works at water treatment works,Performance (Output) | % | Delta
TMS | PCD_DPW1_RES3 | Resilience ,Service reservoirs with new enhanced bypass provision,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_RES3_T | Resilience ,Service reservoirs with new enhanced bypass provision,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RES3_O | Resilience ,Service reservoirs with new enhanced bypass provision,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_RES3_OT | Resilience ,Service reservoirs with new enhanced bypass provision,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_RES3_P | Resilience ,Service reservoirs with new enhanced bypass provision,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_RES4 | Resilience,Installation of new equipment,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_RES4_T | Resilience,Installation of new equipment,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RES4_O | Resilience,Installation of new equipment,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_RES4_OT | Resilience,Installation of new equipment,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_RES4_P | Resilience,Installation of new equipment,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_RES5 | Resilience,Ml of additional service reservoir storage at service reservoirs,PCD Output (Cumulative) - Target | Ml | Delta
TMS | PCD_DPW1_RES5_T | Resilience,Ml of additional service reservoir storage at service reservoirs,PCD output by 2029-30 (Target) | Ml | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RES5_O | Resilience,Ml of additional service reservoir storage at service reservoirs,PCD Output (Cumulative) - Outturn & Forecast | Ml | Delta
TMS | PCD_DPW1_RES5_OT | Resilience,Ml of additional service reservoir storage at service reservoirs,PCD output by 2029-30 (Outturn & Forecast) | Ml | Delta
TMS | PCD_DPW1_RES5_P | Resilience,Ml of additional service reservoir storage at service reservoirs,Performance (Output) | Ml | Delta
TMS | PCD_DPW1_RES6 | Resilience,Ml/d of peak week production capacity of additional process stream,PCD Output (Cumulative) - Target | Ml/d | Delta
TMS | PCD_DPW1_RES6_T | Resilience,Ml/d of peak week production capacity of additional process stream,PCD output by 2029-30 (Target) | Ml/d | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RES6_O | Resilience,Ml/d of peak week production capacity of additional process stream,PCD Output (Cumulative) - Outturn & Forecast | Ml/d | Delta
TMS | PCD_DPW1_RES6_OT | Resilience,Ml/d of peak week production capacity of additional process stream,PCD output by 2029-30 (Outturn & Forecast) | Ml/d | Delta
TMS | PCD_DPW1_RES6_P | Resilience,Ml/d of peak week production capacity of additional process stream,Performance (Output) | Ml/d | Delta
TMS | PCD_DPW1_RES7 | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_RES7_T | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_RES7_O | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_RES7_OT | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_RES7_P | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,Performance (Output) | Nr | Delta
TMS | PCD_DPW1_CYBR | Cyber,Legal instruments,PCD Output (Cumulative) - Target | Nr | Delta | [9 empty] | 1 | 1 | 1 | 1
TMS | PCD_DPW1_CYBR_T | Cyber,Legal instruments,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 1
TMS | PCD_DPW1_CYBR_O | Cyber,Legal instruments,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta | [8 empty] | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW1_CYBR_OT | Cyber,Legal instruments,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [12 empty] | 1
TMS | PCD_DPW1_CYBR_P | Cyber,Legal instruments,Performance (Output) | Nr | Delta | [12 empty] | 1
TMS | PCD_DPW1_SEMD | SEMD,Legal instruments,PCD Output (Cumulative) - Target | Nr | Delta | [8 empty] | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW1_SEMD_T | SEMD,Legal instruments,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 1
TMS | PCD_DPW1_SEMD_O | SEMD,Legal instruments,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta | [8 empty] | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW1_SEMD_OT | SEMD,Legal instruments,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta | [12 empty] | 1
TMS | PCD_DPW1_SEMD_P | SEMD,Legal instruments,Performance (Output) | Nr | Delta | [12 empty] | 1
TMS | PCD_DPW1_GGR1 | Greenhouse gas reduction (net zero),tCO2e,PCD Output (Cumulative) - Target | tonnes | Delta
TMS | PCD_DPW1_GGR1_T | Greenhouse gas reduction (net zero),tCO2e,PCD output by 2029-30 (Target) | tonnes | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_GGR1_O | Greenhouse gas reduction (net zero),tCO2e,PCD Output (Cumulative) - Outturn & Forecast | tonnes | Delta
TMS | PCD_DPW1_GGR1_OT | Greenhouse gas reduction (net zero),tCO2e,PCD output by 2029-30 (Outturn & Forecast) | tonnes | Delta
TMS | PCD_DPW1_GGR1_P | Greenhouse gas reduction (net zero),tCO2e,Performance (Output) | tonnes | Delta
TMS | PCD_DPW1_GGR | Greenhouse gas reduction (net zero),Number of hectares,PCD Output (Cumulative) - Target | Nr | Delta
TMS | PCD_DPW1_GGR_T | Greenhouse gas reduction (net zero),Number of hectares,PCD output by 2029-30 (Target) | Nr | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW1_GGR_O | Greenhouse gas reduction (net zero),Number of hectares,PCD Output (Cumulative) - Outturn & Forecast | Nr | Delta
TMS | PCD_DPW1_GGR_OT | Greenhouse gas reduction (net zero),Number of hectares,PCD output by 2029-30 (Outturn & Forecast) | Nr | Delta
TMS | PCD_DPW1_GGR_P | Greenhouse gas reduction (net zero),Number of hectares,Performance (Output) | Nr | Delta
TMS | PCD_DPW2_BIOCON1_NP | Biodiversity and Conservation hectares,Hectares of environmental improvement,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_BIOCON1 | Biodiversity and Conservation hectares,Hectares of environmental improvement,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_BIOCON1_T | Biodiversity and Conservation hectares,Hectares of environmental improvement,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_BIOCON1_O | Biodiversity and Conservation hectares,Hectares of environmental improvement,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_BIOCON1_OT | Biodiversity and Conservation hectares,Hectares of environmental improvement,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_BIOCON1_P | Biodiversity and Conservation hectares,Hectares of environmental improvement,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_BIOCON2_NP | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_BIOCON2 | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_BIOCON2_T | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_BIOCON2_O | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_BIOCON2_OT | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_BIOCON2_P | Biodiversity and Conservation kilometres,Kilometres of environmental improvement,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_DWPA_NP | Drinking Water Protected Areas,No Deterioration and Implementation actions,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_DWPA | Drinking Water Protected Areas,No Deterioration and Implementation actions,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_DWPA_T | Drinking Water Protected Areas,No Deterioration and Implementation actions,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_DWPA_O | Drinking Water Protected Areas,No Deterioration and Implementation actions,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_DWPA_OT | Drinking Water Protected Areas,No Deterioration and Implementation actions,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_DWPA_P | Drinking Water Protected Areas,No Deterioration and Implementation actions,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_WFDI_NP | Water Framework Directive interconnector,Length of WFD interconnector,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 2.8971
TMS | PCD_DPW2_WFDI | Water Framework Directive interconnector,Length of WFD interconnector,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 0.64263 | 2.1634 | 5.1229 | 10.3129 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222
TMS | PCD_DPW2_WFDI_T | Water Framework Directive interconnector,Length of WFD interconnector,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 27.5222 |  |  |  |  | 27.5222
TMS | PCD_DPW2_WFDI_O | Water Framework Directive interconnector,Length of WFD interconnector,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 0.085785 | 0.15477 | 0.7828 | 1.3994 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004 | 2.004
TMS | PCD_DPW2_WFDI_OT | Water Framework Directive interconnector,Length of WFD interconnector,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 2.004 |  |  |  |  | 2.004
TMS | PCD_DPW2_WFDI_P | Water Framework Directive interconnector,Length of WFD interconnector,Performance (Expenditure) | £m | Delta | [7 empty] | 0.072813 |  |  |  |  | 0.072813
TMS | PCD_DPW2_WFDA_NP | Water Framework Directive actions,Other WFD actions,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 1.0004
TMS | PCD_DPW2_WFDA | Water Framework Directive actions,Other WFD actions,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 0.44384 | 1.4942 | 3.5382 | 7.1227 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085
TMS | PCD_DPW2_WFDA_T | Water Framework Directive actions,Other WFD actions,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 19.0085 |  |  |  |  | 19.0085
TMS | PCD_DPW2_WFDA_O | Water Framework Directive actions,Other WFD actions,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0.055 | 0.42319 | 2.6442 | 7.4164 | 19.2107 | 23.5481 | 23.6262 | 23.629 | 23.629 | 23.629 | 23.629
TMS | PCD_DPW2_WFDA_OT | Water Framework Directive actions,Other WFD actions,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 23.5481 |  |  |  |  | 23.629
TMS | PCD_DPW2_WFDA_P | Water Framework Directive actions,Other WFD actions,Performance (Expenditure) | £m | Delta | [7 empty] | 1.2388 |  |  |  |  | 1.2431
TMS | PCD_DPW2_WIVG_NP | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 0.471
TMS | PCD_DPW2_WIVG | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  | 0 | 0 | 5.5903 | 11.601 | 13.5926 | 15.5641 | 17.427
TMS | PCD_DPW2_WIVG_T | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 17.427 |  |  |  |  | 0
TMS | PCD_DPW2_WIVG_O | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 1.6196 | 7.1759 | 12.6193 | 21.2562 | 31.8677 | 31.9892 | 31.9892 | 31.9892 | 31.9892 | 31.9892
TMS | PCD_DPW2_WIVG_OT | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 31.8677 |  |  |  |  | 31.9892
TMS | PCD_DPW2_WIVG_P | Water WINEP/NEP Investigations,Water WINEP/NEP Investigations,Performance (Expenditure) | £m | Delta | [7 empty] | 1.8286
TMS | PCD_DPW2_RWD_NP | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RWD | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RWD_T | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RWD_O | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RWD_OT | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RWD_P | Raw Water Deterioration and Taste, Odour and Colour,Legal instruments,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_LEAD1_NP | Lead,Lead communication pipes replaced/relined,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 0.0015441
TMS | PCD_DPW2_LEAD1 | Lead,Lead communication pipes replaced/relined,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 11.3753 | 29.1756 | 48.392 | 67.462 | 83.384
TMS | PCD_DPW2_LEAD1_T | Lead,Lead communication pipes replaced/relined,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 83.384 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD1_O | Lead,Lead communication pipes replaced/relined,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 7.7785 | 24.472 | 40.2264 | 56.1587 | 72.2989 | 72.2989 | 72.2989 | 72.2989 | 72.2989 | 72.2989
TMS | PCD_DPW2_LEAD1_OT | Lead,Lead communication pipes replaced/relined,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 72.2989 |  |  |  |  | 72.2989
TMS | PCD_DPW2_LEAD1_P | Lead,Lead communication pipes replaced/relined,Performance (Expenditure) | £m | Delta | [7 empty] | 0.86706
TMS | PCD_DPW2_LEAD2_NP | Lead,Lead external supply pipes replaced/relined - Non-schools,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_LEAD2 | Lead,Lead external supply pipes replaced/relined - Non-schools,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_LEAD2_T | Lead,Lead external supply pipes replaced/relined - Non-schools,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD2_O | Lead,Lead external supply pipes replaced/relined - Non-schools,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_LEAD2_OT | Lead,Lead external supply pipes replaced/relined - Non-schools,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD2_P | Lead,Lead external supply pipes replaced/relined - Non-schools,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_LEAD3_NP | Lead,Lead external supply pipes replaced/relined - Schools,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_LEAD3 | Lead,Lead external supply pipes replaced/relined - Schools,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_LEAD3_T | Lead,Lead external supply pipes replaced/relined - Schools,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD3_O | Lead,Lead external supply pipes replaced/relined - Schools,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_LEAD3_OT | Lead,Lead external supply pipes replaced/relined - Schools,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD3_P | Lead,Lead external supply pipes replaced/relined - Schools,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_LEAD4_NP | Lead,Lead internal supply pipes replaced/relined - Non-schools,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_LEAD4 | Lead,Lead internal supply pipes replaced/relined - Non-schools,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_LEAD4_T | Lead,Lead internal supply pipes replaced/relined - Non-schools,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD4_O | Lead,Lead internal supply pipes replaced/relined - Non-schools,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_LEAD4_OT | Lead,Lead internal supply pipes replaced/relined - Non-schools,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD4_P | Lead,Lead internal supply pipes replaced/relined - Non-schools,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_LEAD5_NP | Lead,Lead internal supply pipes replaced/relined - Schools,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_LEAD5 | Lead,Lead internal supply pipes replaced/relined - Schools,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_LEAD5_T | Lead,Lead internal supply pipes replaced/relined - Schools,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD5_O | Lead,Lead internal supply pipes replaced/relined - Schools,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_LEAD5_OT | Lead,Lead internal supply pipes replaced/relined - Schools,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_LEAD5_P | Lead,Lead internal supply pipes replaced/relined - Schools,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_WRESUP_NP | W Resilience CC Uplift,Spend on scheme as a % of allowance,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 0.3291
TMS | PCD_DPW2_WRESUP | W Resilience CC Uplift,Spend on scheme as a % of allowance,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  | 0 | 4.0293 | 11.3859 | 18.6016 | 26.0632 | 32.9099
TMS | PCD_DPW2_WRESUP_T | W Resilience CC Uplift,Spend on scheme as a % of allowance,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 32.9099 |  |  |  |  | 0
TMS | PCD_DPW2_WRESUP_O | W Resilience CC Uplift,Spend on scheme as a % of allowance,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 1.0494 | 4.3504 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555 | 5.1555
TMS | PCD_DPW2_WRESUP_OT | W Resilience CC Uplift,Spend on scheme as a % of allowance,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 5.1555 |  |  |  |  | 5.1555
TMS | PCD_DPW2_WRESUP_P | W Resilience CC Uplift,Spend on scheme as a % of allowance,Performance (Expenditure) | £m | Delta | [7 empty] | 0.15665
TMS | PCD_DPW2_MTR1_NP | Metering,New installations,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 0.00041923
TMS | PCD_DPW2_MTR1 | Metering,New installations,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  | 0 | 29.269 | 58.5384 | 87.8074 | 117.0768 | 146.3458
TMS | PCD_DPW2_MTR1_T | Metering,New installations,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 146.3458 |  |  |  |  | 0
TMS | PCD_DPW2_MTR1_O | Metering,New installations,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 52.0547 | 89.3931 | 119.8258 | 147.1651 | 176.3068 | 176.3068 | 176.3068 | 176.3068 | 176.3068 | 176.3068
TMS | PCD_DPW2_MTR1_OT | Metering,New installations,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 176.3068 |  |  |  |  | 176.3068
TMS | PCD_DPW2_MTR1_P | Metering,New installations,Performance (Expenditure) | £m | Delta | [7 empty] | 1.2047
TMS | PCD_DPW2_MTR2_NP | Metering,Household meter upgrades,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 3.2257e-05
TMS | PCD_DPW2_MTR2 | Metering,Household meter upgrades,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  | 0 | 4.1643 | 8.3286 | 12.4929 | 16.6572 | 20.8214
TMS | PCD_DPW2_MTR2_T | Metering,Household meter upgrades,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 20.8214 |  |  |  |  | 0
TMS | PCD_DPW2_MTR2_O | Metering,Household meter upgrades,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 8.0067 | 17.433 | 25.9817 | 32.7611 | 38.9923 | 38.9923 | 38.9923 | 38.9923 | 38.9923 | 38.9923
TMS | PCD_DPW2_MTR2_OT | Metering,Household meter upgrades,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 38.9923 |  |  |  |  | 38.9923
TMS | PCD_DPW2_MTR2_P | Metering,Household meter upgrades,Performance (Expenditure) | £m | Delta | [7 empty] | 1.8727
TMS | PCD_DPW2_MTR3_NP | Metering,Non household meter upgrades,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 3.2257e-05
TMS | PCD_DPW2_MTR3 | Metering,Non household meter upgrades,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  | 0 | 0.73084 | 1.4617 | 2.1925 | 2.9234 | 3.6542
TMS | PCD_DPW2_MTR3_T | Metering,Non household meter upgrades,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 3.6542 |  |  |  |  | 0
TMS | PCD_DPW2_MTR3_O | Metering,Non household meter upgrades,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 1.3225 | 2.7939 | 4.3741 | 5.9441 | 7.1106 | 7.1106 | 7.1106 | 7.1106 | 7.1106 | 7.1106
TMS | PCD_DPW2_MTR3_OT | Metering,Non household meter upgrades,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 7.1106 |  |  |  |  | 7.1106
TMS | PCD_DPW2_MTR3_P | Metering,Non household meter upgrades,Performance (Expenditure) | £m | Delta | [7 empty] | 1.9458
TMS | PCD_DPW2_MTR4_NP | Metering,Large bulk meters,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 0.0035777
TMS | PCD_DPW2_MTR4 | Metering,Large bulk meters,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  | 0 | 3.1305 | 6.261 | 9.3915 | 12.522 | 15.6525
TMS | PCD_DPW2_MTR4_T | Metering,Large bulk meters,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 15.6525 |  |  |  |  | 0
TMS | PCD_DPW2_MTR4_O | Metering,Large bulk meters,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 5.1906 | 16.9522 | 28.4961 | 37.3949 | 49.1827 | 49.1827 | 49.1827 | 49.1827 | 49.1827 | 49.1827
TMS | PCD_DPW2_MTR4_OT | Metering,Large bulk meters,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 49.1827 |  |  |  |  | 49.1827
TMS | PCD_DPW2_MTR4_P | Metering,Large bulk meters,Performance (Expenditure) | £m | Delta | [7 empty] | 3.1422
TMS | PCD_DPW2_MTR5_NP | Metering,Small bulk meters,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 0.0005835
TMS | PCD_DPW2_MTR5 | Metering,Small bulk meters,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  | 0 | 5.9423 | 11.8847 | 17.827 | 23.7693 | 29.7117
TMS | PCD_DPW2_MTR5_T | Metering,Small bulk meters,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 29.7117 |  |  |  |  | 0
TMS | PCD_DPW2_MTR5_O | Metering,Small bulk meters,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 3.0632 | 9.1954 | 15.8885 | 21.649 | 25.8727 | 25.8727 | 25.8727 | 25.8727 | 25.8727 | 25.8727
TMS | PCD_DPW2_MTR5_OT | Metering,Small bulk meters,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 25.8727 |  |  |  |  | 25.8727
TMS | PCD_DPW2_MTR5_P | Metering,Small bulk meters,Performance (Expenditure) | £m | Delta | [7 empty] | 0.87079
TMS | PCD_DPW2_MTR6_NP | Metering,Meter Replacements,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 0.00012131
TMS | PCD_DPW2_MTR6 | Metering,Meter Replacements,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  | 0 | 18.4094 | 36.8189 | 55.2283 | 73.6377 | 92.0471
TMS | PCD_DPW2_MTR6_T | Metering,Meter Replacements,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 92.0471 |  |  |  |  | 0
TMS | PCD_DPW2_MTR6_O | Metering,Meter Replacements,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 20.634 | 51.3401 | 81.6051 | 106.4687 | 129.633 | 129.633 | 129.633 | 129.633 | 129.633 | 129.633
TMS | PCD_DPW2_MTR6_OT | Metering,Meter Replacements,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 129.633 |  |  |  |  | 129.633
TMS | PCD_DPW2_MTR6_P | Metering,Meter Replacements,Performance (Expenditure) | £m | Delta | [7 empty] | 1.4083
TMS | PCD_DPW2_MTR7_NP | Metering,Connected meters,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 4.9836e-05
TMS | PCD_DPW2_MTR7 | Metering,Connected meters,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  | 0 | 0 | 11.5934 | 23.1869 | 34.7803 | 46.3738 | 57.9672
TMS | PCD_DPW2_MTR7_T | Metering,Connected meters,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 57.9672 |  |  |  |  | 0
TMS | PCD_DPW2_MTR7_O | Metering,Connected meters,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 7.041 | 14.0284 | 21.148 | 28.4423 | 35.8935 | 35.8935 | 35.8935 | 35.8935 | 35.8935 | 35.8935
TMS | PCD_DPW2_MTR7_OT | Metering,Connected meters,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 35.8935 |  |  |  |  | 35.8935
TMS | PCD_DPW2_MTR7_P | Metering,Connected meters,Performance (Expenditure) | £m | Delta | [7 empty] | 0.6192
TMS | PCD_DPW2_SPL1_NP | Supply,WAFU Benefit [Base Overlap Schemes],Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_SPL1 | Supply,WAFU Benefit [Base Overlap Schemes],PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_SPL1_T | Supply,WAFU Benefit [Base Overlap Schemes],Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPL1_O | Supply,WAFU Benefit [Base Overlap Schemes],PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_SPL1_OT | Supply,WAFU Benefit [Base Overlap Schemes],Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPL1_P | Supply,WAFU Benefit [Base Overlap Schemes],Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_SPL2_NP | Supply,WAFU Benefit [Medium],Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_SPL2 | Supply,WAFU Benefit [Medium],PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 6.9099 | 18.3405 | 40.1917 | 61.3835 | 80.1504
TMS | PCD_DPW2_SPL2_T | Supply,WAFU Benefit [Medium],Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 80.1504 |  |  |  |  | 0
TMS | PCD_DPW2_SPL2_O | Supply,WAFU Benefit [Medium],PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 1.136 | 5.8859 | 20.617 | 38.7641 | 48.8532 | 49.0116 | 49.0879 | 49.0879 | 49.0879 | 49.0879
TMS | PCD_DPW2_SPL2_OT | Supply,WAFU Benefit [Medium],Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 48.8532 |  |  |  |  | 49.0879
TMS | PCD_DPW2_SPL2_P | Supply,WAFU Benefit [Medium],Performance (Expenditure) | £m | Delta | [7 empty] | 0.60952
TMS | PCD_DPW2_SPL3_NP | Supply,WAFU Benefit [Low],Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_SPL3 | Supply,WAFU Benefit [Low],PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 3.0306 | 6.105 | 9.2251 | 12.3899 | 15.6013
TMS | PCD_DPW2_SPL3_T | Supply,WAFU Benefit [Low],Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 15.6013 |  |  |  |  | 0
TMS | PCD_DPW2_SPL3_O | Supply,WAFU Benefit [Low],PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 2.2322 | 4.4185 | 7.0806 | 9.863 | 12.6349 | 15.4058 | 18.1751 | 18.1751 | 18.1751 | 18.1751 | 18.1751 | 18.1751
TMS | PCD_DPW2_SPL3_OT | Supply,WAFU Benefit [Low],Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 18.1751 |  |  |  |  | 18.1751
TMS | PCD_DPW2_SPL3_P | Supply,WAFU Benefit [Low],Performance (Expenditure) | £m | Delta | [7 empty] | 1.165
TMS | PCD_DPW2_SPL4_NP | Supply,WAFU Benefit [Very Low],Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_SPL4 | Supply,WAFU Benefit [Very Low],PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_SPL4_T | Supply,WAFU Benefit [Very Low],Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPL4_O | Supply,WAFU Benefit [Very Low],PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_SPL4_OT | Supply,WAFU Benefit [Very Low],Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPL4_P | Supply,WAFU Benefit [Very Low],Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_SPL5_NP | Supply,WAFU Benefit [Total],Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_SPL5 | Supply,WAFU Benefit [Total],PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 9.9405 | 24.4456 | 49.4168 | 73.7734 | 95.7517
TMS | PCD_DPW2_SPL5_T | Supply,WAFU Benefit [Total],Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 95.7517 |  |  |  |  | 0
TMS | PCD_DPW2_SPL5_O | Supply,WAFU Benefit [Total],PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 2.2322 | 4.4185 | 8.2166 | 15.749 | 33.2519 | 54.1699 | 67.0283 | 67.1866 | 67.2629 | 67.2629 | 67.2629 | 67.2629
TMS | PCD_DPW2_SPL5_OT | Supply,WAFU Benefit [Total],Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 67.0283 |  |  |  |  | 67.2629
TMS | PCD_DPW2_SPL5_P | Supply,WAFU Benefit [Total],Performance (Expenditure) | £m | Delta | [7 empty] | 0.70002
TMS | PCD_DPW2_SPLIN1_NP | Supply interconnectors,WAFU Benefit,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_SPLIN1 | Supply interconnectors,WAFU Benefit,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_SPLIN1_T | Supply interconnectors,WAFU Benefit,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPLIN1_O | Supply interconnectors,WAFU Benefit,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_SPLIN1_OT | Supply interconnectors,WAFU Benefit,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPLIN1_P | Supply interconnectors,WAFU Benefit,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_SPLIN2_NP | Supply interconnectors,Pipeline length ,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | Km | Delta
TMS | PCD_DPW2_SPLIN2 | Supply interconnectors,Pipeline length ,PCD Total Expenditure (Cumulative) - Allowance (£m) | Km | Delta
TMS | PCD_DPW2_SPLIN2_T | Supply interconnectors,Pipeline length ,Total Expenditure by 2029-30 (Allowance) | Km | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPLIN2_O | Supply interconnectors,Pipeline length ,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | Km | Delta
TMS | PCD_DPW2_SPLIN2_OT | Supply interconnectors,Pipeline length ,Total Expenditure by 2029-30 (Outturn & Forecast) | Km | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_SPLIN2_P | Supply interconnectors,Pipeline length ,Performance (Expenditure) | Km | Delta
TMS | PCD_DPW2_EFCY_NP | Efficiency,Water demand savings (benefit),Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_EFCY | Efficiency,Water demand savings (benefit),PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_EFCY_T | Efficiency,Water demand savings (benefit),Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_EFCY_O | Efficiency,Water demand savings (benefit),PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_EFCY_OT | Efficiency,Water demand savings (benefit),Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_EFCY_P | Efficiency,Water demand savings (benefit),Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RESIN1_NP | Resilience Interconnector,Length of resilience interconnector,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RESIN1 | Resilience Interconnector,Length of resilience interconnector,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RESIN1_T | Resilience Interconnector,Length of resilience interconnector,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN1_O | Resilience Interconnector,Length of resilience interconnector,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RESIN1_OT | Resilience Interconnector,Length of resilience interconnector,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN1_P | Resilience Interconnector,Length of resilience interconnector,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RESIN2_NP | Resilience Interconnector,Crossing connections improvement,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RESIN2 | Resilience Interconnector,Crossing connections improvement,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RESIN2_T | Resilience Interconnector,Crossing connections improvement,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN2_O | Resilience Interconnector,Crossing connections improvement,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RESIN2_OT | Resilience Interconnector,Crossing connections improvement,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN2_P | Resilience Interconnector,Crossing connections improvement,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RESIN3_NP | Resilience Interconnector,Additional storage at reservoirs,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RESIN3 | Resilience Interconnector,Additional storage at reservoirs,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RESIN3_T | Resilience Interconnector,Additional storage at reservoirs,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN3_O | Resilience Interconnector,Additional storage at reservoirs,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RESIN3_OT | Resilience Interconnector,Additional storage at reservoirs,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN3_P | Resilience Interconnector,Additional storage at reservoirs,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RESIN4_NP | Resilience Interconnector,Reservoir bypass,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RESIN4 | Resilience Interconnector,Reservoir bypass,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RESIN4_T | Resilience Interconnector,Reservoir bypass,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN4_O | Resilience Interconnector,Reservoir bypass,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RESIN4_OT | Resilience Interconnector,Reservoir bypass,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RESIN4_P | Resilience Interconnector,Reservoir bypass,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES1_NP | Resilience ,Number of water treatment works with new equipment ,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES1 | Resilience ,Number of water treatment works with new equipment ,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RES1_T | Resilience ,Number of water treatment works with new equipment ,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES1_O | Resilience ,Number of water treatment works with new equipment ,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES1_OT | Resilience ,Number of water treatment works with new equipment ,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES1_P | Resilience ,Number of water treatment works with new equipment ,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES2_NP | Resilience ,Upgrade works at water treatment works,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES2 | Resilience ,Upgrade works at water treatment works,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RES2_T | Resilience ,Upgrade works at water treatment works,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES2_O | Resilience ,Upgrade works at water treatment works,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES2_OT | Resilience ,Upgrade works at water treatment works,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES2_P | Resilience ,Upgrade works at water treatment works,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES3_NP | Resilience ,Service reservoirs with new enhanced bypass provision,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES3 | Resilience ,Service reservoirs with new enhanced bypass provision,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES3_T | Resilience ,Service reservoirs with new enhanced bypass provision,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES3_O | Resilience ,Service reservoirs with new enhanced bypass provision,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES3_OT | Resilience ,Service reservoirs with new enhanced bypass provision,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES3_P | Resilience ,Service reservoirs with new enhanced bypass provision,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES4_NP | Resilience,Installation of new equipment,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES4 | Resilience,Installation of new equipment,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RES4_T | Resilience,Installation of new equipment,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES4_O | Resilience,Installation of new equipment,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES4_OT | Resilience,Installation of new equipment,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES4_P | Resilience,Installation of new equipment,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES5_NP | Resilience,Ml of additional service reservoir storage at service reservoirs,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES5 | Resilience,Ml of additional service reservoir storage at service reservoirs,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES5_T | Resilience,Ml of additional service reservoir storage at service reservoirs,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES5_O | Resilience,Ml of additional service reservoir storage at service reservoirs,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES5_OT | Resilience,Ml of additional service reservoir storage at service reservoirs,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES5_P | Resilience,Ml of additional service reservoir storage at service reservoirs,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES6_NP | Resilience,Ml/d of peak week production capacity of additional process stream,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES6 | Resilience,Ml/d of peak week production capacity of additional process stream,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES6_T | Resilience,Ml/d of peak week production capacity of additional process stream,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES6_O | Resilience,Ml/d of peak week production capacity of additional process stream,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES6_OT | Resilience,Ml/d of peak week production capacity of additional process stream,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES6_P | Resilience,Ml/d of peak week production capacity of additional process stream,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES7_NP | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES7 | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RES7_T | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES7_O | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES7_OT | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES7_P | Resilience,Number of raw water reservoirs with the delivery of specified safety improvements,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_RES8_NP | Resilience,Reservoirs - spend on MITIOS (Measures in the Interest of Safety),Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_RES8 | Resilience,Reservoirs - spend on MITIOS (Measures in the Interest of Safety),PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_RES8_T | Resilience,Reservoirs - spend on MITIOS (Measures in the Interest of Safety),Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES8_O | Resilience,Reservoirs - spend on MITIOS (Measures in the Interest of Safety),PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_RES8_OT | Resilience,Reservoirs - spend on MITIOS (Measures in the Interest of Safety),Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_RES8_P | Resilience,Reservoirs - spend on MITIOS (Measures in the Interest of Safety),Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_CYBR_NP | Cyber,Legal instruments,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 112.0115
TMS | PCD_DPW2_CYBR | Cyber,Legal instruments,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 25.9834 | 47.7608 | 68.3195 | 90.9236 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115
TMS | PCD_DPW2_CYBR_T | Cyber,Legal instruments,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 112.0115 |  |  |  |  | 112.0115
TMS | PCD_DPW2_CYBR_O | Cyber,Legal instruments,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 9.6532 | 23.4709 | 47.8109 | 77.4377 | 103.5306 | 104.8426 | 104.8426 | 104.8426 | 104.8426 | 104.8426
TMS | PCD_DPW2_CYBR_OT | Cyber,Legal instruments,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 103.5306 |  |  |  |  | 104.8426
TMS | PCD_DPW2_CYBR_P | Cyber,Legal instruments,Performance (Expenditure) | £m | Delta | [7 empty] | 0.92429 |  |  |  |  | 0.936
TMS | PCD_DPW2_SEMD_NP | SEMD,Legal instruments,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta | [13 empty] | 28.088
TMS | PCD_DPW2_SEMD | SEMD,Legal instruments,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  |  |  | 2.2744 | 5.5131 | 9.9145 | 17.8311 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088
TMS | PCD_DPW2_SEMD_T | SEMD,Legal instruments,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 28.088 |  |  |  |  | 28.088
TMS | PCD_DPW2_SEMD_O | SEMD,Legal instruments,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 0 | 0 | 1.81 | 6.261 | 12.1236 | 21.6335 | 29.8096 | 29.8096 | 29.8096 | 29.8096 | 29.8096 | 29.8096
TMS | PCD_DPW2_SEMD_OT | SEMD,Legal instruments,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 29.8096 |  |  |  |  | 29.8096
TMS | PCD_DPW2_SEMD_P | SEMD,Legal instruments,Performance (Expenditure) | £m | Delta | [7 empty] | 1.0613 |  |  |  |  | 1.0613
TMS | PCD_DPW2_GGR_NP | Greenhouse gas reduction (net zero),Number of hectares,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_GGR | Greenhouse gas reduction (net zero),Number of hectares,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_GGR_T | Greenhouse gas reduction (net zero),Number of hectares,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_GGR_O | Greenhouse gas reduction (net zero),Number of hectares,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta
TMS | PCD_DPW2_GGR_OT | Greenhouse gas reduction (net zero),Number of hectares,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_GGR_P | Greenhouse gas reduction (net zero),Number of hectares,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_NONPCD1_NP | Total other non - PCD enhancement water expenditure, totex,Total other non - PCD enhancement water expenditure, totex,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_NONPCD1 | Total other non - PCD enhancement water expenditure, totex,Total other non - PCD enhancement water expenditure, totex,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta
TMS | PCD_DPW2_NONPCD1_T | Total other non - PCD enhancement water expenditure, totex,Total other non - PCD enhancement water expenditure, totex,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 0 |  |  |  |  | 0
TMS | PCD_DPW2_NONPCD1_O | Total other non - PCD enhancement water expenditure, totex,Total other non - PCD enhancement water expenditure, totex,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 85.087 | 206.401 | 520.4182 | 991.1657 | 1696.2395 | 2489.0562 | 3272.127 | 3639.5756 | 3961.559 | 4240.5066 | 4396.6537 | 4364.9218
TMS | PCD_DPW2_NONPCD1_OT | Total other non - PCD enhancement water expenditure, totex,Total other non - PCD enhancement water expenditure, totex,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 3272.127 |  |  |  |  | 4364.9218
TMS | PCD_DPW2_NONPCD1_P | Total other non - PCD enhancement water expenditure, totex,Total other non - PCD enhancement water expenditure, totex,Performance (Expenditure) | £m | Delta
TMS | PCD_DPW2_NONPCD2_NP | Total PCD and non - PCD enhancement expenditure; water totex,Total PCD and non - PCD enhancement expenditure; water totex,Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | £m | Delta
TMS | PCD_DPW2_NONPCD2 | Total PCD and non - PCD enhancement expenditure; water totex,Total PCD and non - PCD enhancement expenditure; water totex,PCD Total Expenditure (Cumulative) - Allowance (£m) | £m | Delta |  | 0 | 0 | 133.5195 | 280.0197 | 436.618 | 602.0132 | 782.3029 | 186.6302 | 186.6302 | 186.6302 | 186.6302 | 186.6302
TMS | PCD_DPW2_NONPCD2_T | Total PCD and non - PCD enhancement expenditure; water totex,Total PCD and non - PCD enhancement expenditure; water totex,Total Expenditure by 2029-30 (Allowance) | £m | Delta | [7 empty] | 782.3029 |  |  |  |  | 186.6302
TMS | PCD_DPW2_NONPCD2_O | Total PCD and non - PCD enhancement expenditure; water totex,Total PCD and non - PCD enhancement expenditure; water totex,PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | £m | Delta |  | 87.3192 | 210.8745 | 648.3671 | 1276.5797 | 2152.9455 | 3125.3031 | 4070.3612 | 4439.4798 | 4761.5422 | 5040.4898 | 5196.6369 | 5164.905
TMS | PCD_DPW2_NONPCD2_OT | Total PCD and non - PCD enhancement expenditure; water totex,Total PCD and non - PCD enhancement expenditure; water totex,Total Expenditure by 2029-30 (Outturn & Forecast) | £m | Delta | [7 empty] | 4070.3612 |  |  |  |  | 5164.905
TMS | PCD_DPW2_NONPCD2_P | Total PCD and non - PCD enhancement expenditure; water totex,Total PCD and non - PCD enhancement expenditure; water totex,Performance (Expenditure) | £m | Delta | [7 empty] | 5.2031 |  |  |  |  | 27.6745
TMS | PCD_DPW3_WFDI1_NR | Water Framework Directive interconnector - LengthNumber of Schemes with IMs (Nr) | Nr | Delta | 7
TMS | PCD_DPW3_WFDI1_S0 | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 5 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WFDI1_DLY | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE | Water Framework Directive interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 3 | 4 | 5 | 5 | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WFDI1_DLY_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_S1 | Water Framework Directive interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WFDI1_DLY_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_S2 | Water Framework Directive interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WFDI1_DLY_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_S3 | Water Framework Directive interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WFDI1_DLY_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_S4 | Water Framework Directive interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WFDI1_DLY_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_S5 | Water Framework Directive interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
TMS | PCD_DPW3_WFDI1_DLY_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta | 5
TMS | PCD_DPW3_WFDI1_DIR_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_S6 | Water Framework Directive interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WFDI1_DLY_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_S7 | Water Framework Directive interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WFDI1ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7
TMS | PCD_DPW3_WFDI1_DLY_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WFDI1_DIR_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSCR_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCS_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSPC_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPP_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WFDI1_DTPI_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WFDI1_DCI_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DSI_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WFDI1_DER_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WFDI1_RS_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WFDI1_DPLE_ST | Water Framework Directive interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_NR | Raw Water Deterioration and Taste, Odour and ColourNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RWD_S0 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_S1 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_S2 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_S3 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_S4 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_S5 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_S6 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWD_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_S7 | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RWDST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RWD_DLY_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RWD_DIR_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RWD_DSCR_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RWD_DCS_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RWD_DSPC_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RWD_DPP_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RWD_DTPI_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RWD_DCI_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RWD_DSI_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RWD_DER_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RWD_RS_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RWD_DPLE_ST | Raw Water Deterioration and Taste, Odour and Colour,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_NR | W Resilience CC UpliftNumber of Schemes with IMs (Nr) | Nr | Delta | 1
TMS | PCD_DPW3_WRESUP_S0 | W Resilience CC Uplift,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WRESUP_DLY | W Resilience CC Uplift,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE | W Resilience CC Uplift,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WRESUP_DLY_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_S1 | W Resilience CC Uplift,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WRESUP_DLY_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_S2 | W Resilience CC Uplift,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WRESUP_DLY_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_S3 | W Resilience CC Uplift,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WRESUP_DLY_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_S4 | W Resilience CC Uplift,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WRESUP_DLY_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_S5 | W Resilience CC Uplift,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW3_WRESUP_DLY_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_S6 | W Resilience CC Uplift,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUP_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_WRESUP_DLY_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_S7 | W Resilience CC Uplift,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_WRESUPST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW3_WRESUP_DLY_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_WRESUP_DIR_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSCR_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCS_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSPC_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPP_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_WRESUP_DTPI_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_WRESUP_DCI_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DSI_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_WRESUP_DER_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_WRESUP_RS_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_WRESUP_DPLE_ST | W Resilience CC Uplift,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_NR | Supply - WAFU Benefit [Total]Number of Schemes with IMs (Nr) | Nr | Delta | 3
TMS | PCD_DPW3_SPL5_S0 | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 3 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPL5_DLY | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE | Supply - WAFU Benefit [Total],Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPL5_DLY_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_S1 | Supply - WAFU Benefit [Total],Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPL5_DLY_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_S2 | Supply - WAFU Benefit [Total],Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPL5_DLY_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_S3 | Supply - WAFU Benefit [Total],Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPL5_DLY_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_S4 | Supply - WAFU Benefit [Total],Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPL5_DLY_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_S5 | Supply - WAFU Benefit [Total],Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
TMS | PCD_DPW3_SPL5_DLY_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_S6 | Supply - WAFU Benefit [Total],Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPL5_DLY_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_S7 | Supply - WAFU Benefit [Total],Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPL5ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3
TMS | PCD_DPW3_SPL5_DLY_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPL5_DIR_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPL5_DSCR_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPL5_DCS_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPL5_DSPC_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPL5_DPP_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPL5_DTPI_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPL5_DCI_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DSI_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPL5_DER_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPL5_RS_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPL5_DPLE_ST | Supply - WAFU Benefit [Total],Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_NR | Supply interconnectors - WAFU BenefitNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_SPLIN1_S0 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_S1 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_S2 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_S3 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_S4 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_S5 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_S6 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_S7 | Supply interconnectors - WAFU Benefit,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SPLIN1ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SPLIN1_DLY_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DIR_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSCR_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCS_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSPC_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPP_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DTPI_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DCI_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DSI_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DER_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SPLIN1_RS_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SPLIN1_DPLE_ST | Supply interconnectors - WAFU Benefit,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_NR | Resilience Interconnector - LengthNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RESIN1_S0 | Resilience Interconnector - Length,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY | Resilience Interconnector - Length,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE | Resilience Interconnector - Length,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_S1 | Resilience Interconnector - Length,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_S2 | Resilience Interconnector - Length,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_S3 | Resilience Interconnector - Length,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_S4 | Resilience Interconnector - Length,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_S5 | Resilience Interconnector - Length,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_S6 | Resilience Interconnector - Length,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_S7 | Resilience Interconnector - Length,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RESIN1ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RESIN1_DLY_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RESIN1_DIR_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSCR_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCS_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSPC_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPP_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RESIN1_DTPI_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RESIN1_DCI_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DSI_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RESIN1_DER_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RESIN1_RS_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RESIN1_DPLE_ST | Resilience Interconnector - Length,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_NR | Resilience - Number of water treatment works with new equipment Number of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RES1_S0 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_S1 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_S2 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_S3 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_S4 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_S5 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_S6 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_S7 | Resilience - Number of water treatment works with new equipment ,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES1ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES1_DLY_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES1_DIR_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES1_DSCR_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES1_DCS_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES1_DSPC_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES1_DPP_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES1_DTPI_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES1_DCI_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES1_DSI_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES1_DER_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES1_RS_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES1_DPLE_ST | Resilience - Number of water treatment works with new equipment ,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_NR | Resilience - Upgrade works at water treatment worksNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RES2_S0 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_S1 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_S2 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_S3 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_S4 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_S5 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_S6 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_S7 | Resilience - Upgrade works at water treatment works,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES2ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES2_DLY_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES2_DIR_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES2_DSCR_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES2_DCS_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES2_DSPC_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES2_DPP_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES2_DTPI_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES2_DCI_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES2_DSI_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES2_DER_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES2_RS_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES2_DPLE_ST | Resilience - Upgrade works at water treatment works,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_NR | Resilience - Service reservoirs with new enhanced bypass provisionNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RES3_S0 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_S1 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_S2 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_S3 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_S4 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_S5 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_S6 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_S7 | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES3ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES3_DLY_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES3_DIR_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES3_DSCR_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES3_DCS_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES3_DSPC_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES3_DPP_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES3_DTPI_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES3_DCI_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES3_DSI_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES3_DER_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES3_RS_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES3_DPLE_ST | Resilience - Service reservoirs with new enhanced bypass provision,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_NR | Resilience - Installation of new equipmentNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RES4_S0 | Resilience - Installation of new equipment,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY | Resilience - Installation of new equipment,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE | Resilience - Installation of new equipment,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_S1 | Resilience - Installation of new equipment,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_S2 | Resilience - Installation of new equipment,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_S3 | Resilience - Installation of new equipment,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_S4 | Resilience - Installation of new equipment,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_S5 | Resilience - Installation of new equipment,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_S6 | Resilience - Installation of new equipment,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_S7 | Resilience - Installation of new equipment,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES4ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES4_DLY_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES4_DIR_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES4_DSCR_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES4_DCS_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES4_DSPC_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES4_DPP_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES4_DTPI_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES4_DCI_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES4_DSI_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES4_DER_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES4_RS_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES4_DPLE_ST | Resilience - Installation of new equipment,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_NR | Resilience - Ml of additional service reservoir storage at service reservoirsNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RES5_S0 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_S1 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_S2 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_S3 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_S4 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_S5 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_S6 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_S7 | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES5ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES5_DLY_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES5_DIR_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES5_DSCR_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES5_DCS_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES5_DSPC_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES5_DPP_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES5_DTPI_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES5_DCI_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES5_DSI_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES5_DER_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES5_RS_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES5_DPLE_ST | Resilience - Ml of additional service reservoir storage at service reservoirs,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_NR | Resilience - Ml/d of peak week production capacity of additional process streamNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RES6_S0 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_S1 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_S2 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_S3 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_S4 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_S5 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_S6 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_S7 | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES6ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES6_DLY_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES6_DIR_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES6_DSCR_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES6_DCS_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES6_DSPC_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES6_DPP_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES6_DTPI_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES6_DCI_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES6_DSI_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES6_DER_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES6_RS_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES6_DPLE_ST | Resilience - Ml/d of peak week production capacity of additional process stream,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_NR | Resilience - Number of raw water reservoirs with the delivery of specified safety improvementsNumber of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_RES7_S0 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_S1 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_S2 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_S3 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_S4 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_S5 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_S6 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_S7 | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_RES7ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_RES7_DLY_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_RES7_DIR_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_RES7_DSCR_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_RES7_DCS_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_RES7_DSPC_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_RES7_DPP_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_RES7_DTPI_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_RES7_DCI_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_RES7_DSI_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_RES7_DER_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_RES7_RS_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_RES7_DPLE_ST | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_NR | Cyber - Legal instrumentsNumber of Schemes with IMs (Nr) | Nr | Delta | 1
TMS | PCD_DPW3_CYBR_S0 | Cyber - Legal instruments,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_CYBR_DLY | Cyber - Legal instruments,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE | Cyber - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_CYBR_DLY_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_S1 | Cyber - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_CYBR_DLY_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_S2 | Cyber - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_CYBR_DLY_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_S3 | Cyber - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_CYBR_DLY_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_S4 | Cyber - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_CYBR_DLY_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_S5 | Cyber - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW3_CYBR_DLY_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_S6 | Cyber - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBR_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_CYBR_DLY_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_S7 | Cyber - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_CYBRST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW3_CYBR_DLY_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_CYBR_DIR_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_CYBR_DSCR_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_CYBR_DCS_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_CYBR_DSPC_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_CYBR_DPP_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_CYBR_DTPI_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_CYBR_DCI_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DSI_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_CYBR_DER_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_CYBR_RS_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_CYBR_DPLE_ST | Cyber - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_NR | SEMD - Legal instrumentsNumber of Schemes with IMs (Nr) | Nr | Delta | 1
TMS | PCD_DPW3_SEMD_S0 | SEMD - Legal instruments,Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW3_SEMD_DLY | SEMD - Legal instruments,Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE | SEMD - Legal instruments,Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SEMD_DLY_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_S1 | SEMD - Legal instruments,Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SEMD_DLY_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_S2 | SEMD - Legal instruments,Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SEMD_DLY_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_S3 | SEMD - Legal instruments,Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SEMD_DLY_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_S4 | SEMD - Legal instruments,Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SEMD_DLY_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_S5 | SEMD - Legal instruments,Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SEMD_DLY_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_S6 | SEMD - Legal instruments,Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMD_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_SEMD_DLY_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_S7 | SEMD - Legal instruments,Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_SEMDST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
TMS | PCD_DPW3_SEMD_DLY_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_SEMD_DIR_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_SEMD_DSCR_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_SEMD_DCS_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_SEMD_DSPC_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_SEMD_DPP_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_SEMD_DTPI_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_SEMD_DCI_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DSI_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_SEMD_DER_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_SEMD_RS_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_SEMD_DPLE_ST | SEMD - Legal instruments,Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_NR | Greenhouse gas reduction (net zero)Number of Schemes with IMs (Nr) | Nr | Delta | 0
TMS | PCD_DPW3_GGR_S0 | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE | Greenhouse gas reduction (net zero),Number of schemes at Stage 0,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_S1 | Greenhouse gas reduction (net zero),Number of schemes at Stage 1,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_S2 | Greenhouse gas reduction (net zero),Number of schemes at Stage 2,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_S3 | Greenhouse gas reduction (net zero),Number of schemes at Stage 3,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_S4 | Greenhouse gas reduction (net zero),Number of schemes at Stage 4,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_S5 | Greenhouse gas reduction (net zero),Number of schemes at Stage 5,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_S6 | Greenhouse gas reduction (net zero),Number of schemes at Stage 6,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGR_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_S7 | Greenhouse gas reduction (net zero),Number of schemes at Stage 7,Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta
TMS | PCD_DPW3_GGRST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Number of Schemes with IMs (Nr) | Nr | Delta | [14 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TMS | PCD_DPW3_GGR_DLY_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Total number of schemes with a 90+ day delay for any given IM, | Nr | Delta
TMS | PCD_DPW3_GGR_DIR_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - internal | Nr | Delta
TMS | PCD_DPW3_GGR_DSCR_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Lack of resources - external | Nr | Delta
TMS | PCD_DPW3_GGR_DCS_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Change in solution (IM2) | Nr | Delta
TMS | PCD_DPW3_GGR_DSPC_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Supply chain capacity | Nr | Delta
TMS | PCD_DPW3_GGR_DPP_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Land and planning permission | Nr | Delta
TMS | PCD_DPW3_GGR_DTPI_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Third-party interface | Nr | Delta
TMS | PCD_DPW3_GGR_DCI_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Contractual issues | Nr | Delta
TMS | PCD_DPW3_GGR_DSI_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Sites issues | Nr | Delta
TMS | PCD_DPW3_GGR_DER_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Environmental risks | Nr | Delta
TMS | PCD_DPW3_GGR_RS_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Regulatory Sign off Delay | Nr | Delta
TMS | PCD_DPW3_GGR_DPLE_ST | Greenhouse gas reduction (net zero),Number of schemes - total (Stage 0 to Stage 6),Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category,Programme level efficiency | Nr | Delta