## DPW1
DPW1 | [43 empty] | Ofwat Bon Numbers
Enhancement - PCD Output - Water - Programme Level
Header | Company | PCD Model | PCD Ref | PCD Applicable? Y/N | Line Description | PCD Output Description | Units | DPs | PCD Output (Cumulative) - Target | [11 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD Output (Cumulative) - Outturn & Forecast | [11 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP Reference |  |  | PCD Output (Cumulative) - Target | [11 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | PCD Output (Cumulative) - Outturn & Forecast | [11 empty] | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Performance (Output)
[9 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  |  |  | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Outturn & Forecast by 2029-30 |  | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | PCD Output Outturn & Forecast by 2034-35
Start_Data | [8 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [8 empty] | Start_BON | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation hectares | Hectares of environmental improvement | ha | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.1 |  |  | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1 | PCD_DPW1_BIOCON1_T | PCD_DPW1_BIOCON1_T | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_O | PCD_DPW1_BIOCON1_OT | PCD_DPW1_BIOCON1_OT | PCD_DPW1_BIOCON1_P | PCD_DPW1_BIOCON1_P
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation kilometres | Kilometres of environmental improvement | km | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.2 |  |  | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2 | PCD_DPW1_BIOCON2_T | PCD_DPW1_BIOCON2_T | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_O | PCD_DPW1_BIOCON2_OT | PCD_DPW1_BIOCON2_OT | PCD_DPW1_BIOCON2_P | PCD_DPW1_BIOCON2_P
| TMS | PR24CA106 Water WINEP | PCDW4 | 0 | Drinking Water Protected Areas | No Deterioration and Implementation actions | Nr | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.3 |  |  | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA | PCD_DPW1_DWPA_T | PCD_DPW1_DWPA_T | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_O | PCD_DPW1_DWPA_OT | PCD_DPW1_DWPA_OT | PCD_DPW1_DWPA_P | PCD_DPW1_DWPA_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive interconnector | Length of WFD interconnector | km | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 0 | 0 | 0 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 9.5 | 100% | 100% |  | Green | DPW1.4 |  |  | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI | PCD_DPW1_WFDI_T | PCD_DPW1_WFDI_T | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_O | PCD_DPW1_WFDI_OT | PCD_DPW1_WFDI_OT | PCD_DPW1_WFDI_P | PCD_DPW1_WFDI_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive actions | Other WFD actions | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 0 | 0 | 2 | 2 | 2 | 18 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 100% | 100% |  | Green | DPW1.5 |  |  | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA | PCD_DPW1_WFDA_T | PCD_DPW1_WFDA_T | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_O | PCD_DPW1_WFDA_OT | PCD_DPW1_WFDA_OT | PCD_DPW1_WFDA_P | PCD_DPW1_WFDA_P
| TMS | PR24CA106 Water WINEP | PCDW8 | Y | Water WINEP/NEP Investigations | Water WINEP/NEP Investigations | Nr | 0 |  |  | 0 | 0 | 37 | 37 | 37 | [5 empty] | 37 | 0 | 0 | 0 | 0 | 28 | 30 | 34 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 37 | 100% |  |  | Green | DPW1.6 |  |  | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG | PCD_DPW1_WIVG_T | PCD_DPW1_WIVG_T | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_O | PCD_DPW1_WIVG_OT | PCD_DPW1_WIVG_OT | PCD_DPW1_WIVG_P | PCD_DPW1_WIVG_P
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 | Y | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | Nr | 0 | [8 empty] | 5 | 5 | 5 | 6 | 0 | 6 | 0 | 0 | 0 | 0 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 |  | 100% |  | Green | DPW1.7 |  |  | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD | PCD_DPW1_RWD_T | PCD_DPW1_RWD_T | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_O | PCD_DPW1_RWD_OT | PCD_DPW1_RWD_OT | PCD_DPW1_RWD_P | PCD_DPW1_RWD_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead communication pipes replaced/relined | Nr | 0 | 0 | 0 | 8000 | 19500 | 31000 | 42500 | 54000 | [5 empty] | 54000 | 0 | 0 | 0 | 6500 | 18375 | 30250 | 42125 | 54000 | [5 empty] | 54000 | 0 | 100% |  |  | Green | DPW1.8 |  |  | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1 | PCD_DPW1_LEAD1_T | PCD_DPW1_LEAD1_T | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_O | PCD_DPW1_LEAD1_OT | PCD_DPW1_LEAD1_OT | PCD_DPW1_LEAD1_P | PCD_DPW1_LEAD1_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Non-schools | Nr | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.9 |  |  | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2 | PCD_DPW1_LEAD2_T | PCD_DPW1_LEAD2_T | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_O | PCD_DPW1_LEAD2_OT | PCD_DPW1_LEAD2_OT | PCD_DPW1_LEAD2_P | PCD_DPW1_LEAD2_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Schools | Nr | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.10 |  |  | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3 | PCD_DPW1_LEAD3_T | PCD_DPW1_LEAD3_T | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_O | PCD_DPW1_LEAD3_OT | PCD_DPW1_LEAD3_OT | PCD_DPW1_LEAD3_P | PCD_DPW1_LEAD3_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Non-schools | Nr | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.11 |  |  | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4 | PCD_DPW1_LEAD4_T | PCD_DPW1_LEAD4_T | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_O | PCD_DPW1_LEAD4_OT | PCD_DPW1_LEAD4_OT | PCD_DPW1_LEAD4_P | PCD_DPW1_LEAD4_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Schools | Nr | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.12 |  |  | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5 | PCD_DPW1_LEAD5_T | PCD_DPW1_LEAD5_T | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_O | PCD_DPW1_LEAD5_OT | PCD_DPW1_LEAD5_OT | PCD_DPW1_LEAD5_P | PCD_DPW1_LEAD5_P
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 | Y | W Resilience CC Uplift | Spend on scheme as a % of allowance | % | 0 | [6 empty] | 100 | [5 empty] | 100 | 0 | 0 | 0 | 2.862 | 13.3292 | 25.5561 | 62.6322 | 86.939 | 87.8488 | 88.0627 | 88.0627 | 88.0627 | 88.0627 | 86.939 | 88.0627 | 86.94% |  |  | Green | DPW1.13 |  |  | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP | PCD_DPW1_WRESUP_T | PCD_DPW1_WRESUP_T | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_O | PCD_DPW1_WRESUP_OT | PCD_DPW1_WRESUP_OT | PCD_DPW1_WRESUP_P | PCD_DPW1_WRESUP_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | New installations | Nr | 0 | 0 | 0 | 69816 | 139633 | 209449 | 279266 | 349082 | [5 empty] | 349082 | 0 | 0 | 0 | 69816 | 139633 | 209449 | 279266 | 349082 | [5 empty] | 349082 | 0 | 100% |  |  | Green | DPW1.14 |  |  | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1 | PCD_DPW1_MTR1_T | PCD_DPW1_MTR1_T | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_O | PCD_DPW1_MTR1_OT | PCD_DPW1_MTR1_OT | PCD_DPW1_MTR1_P | PCD_DPW1_MTR1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Household meter upgrades | Nr | 0 | 0 | 0 | 129098 | 258196 | 387294 | 516392 | 645490 | [5 empty] | 645490 | 0 | 0 | 0 | 129098 | 258196 | 387294 | 516392 | 645490 | [5 empty] | 645490 | 0 | 100% |  |  | Green | DPW1.15 |  |  | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2 | PCD_DPW1_MTR2_T | PCD_DPW1_MTR2_T | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_O | PCD_DPW1_MTR2_OT | PCD_DPW1_MTR2_OT | PCD_DPW1_MTR2_P | PCD_DPW1_MTR2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Non household meter upgrades | Nr | 0 | 0 | 0 | 22657 | 45315 | 67971 | 90629 | 113286 | [5 empty] | 113286 | 0 | 0 | 0 | 22657 | 45315 | 67971 | 90629 | 113286 | [5 empty] | 113286 | 0 | 100% |  |  | Green | DPW1.16 |  |  | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3 | PCD_DPW1_MTR3_T | PCD_DPW1_MTR3_T | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_O | PCD_DPW1_MTR3_OT | PCD_DPW1_MTR3_OT | PCD_DPW1_MTR3_P | PCD_DPW1_MTR3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Large bulk meters | Nr | 0 | 0 | 0 | 875 | 1750 | 2625 | 3500 | 4375 | [5 empty] | 4375 | 0 | 0 | 0 | 875 | 1750 | 2625 | 3500 | 4375 | [5 empty] | 4375 | 0 | 100% |  |  | Green | DPW1.17 |  |  | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4 | PCD_DPW1_MTR4_T | PCD_DPW1_MTR4_T | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_O | PCD_DPW1_MTR4_OT | PCD_DPW1_MTR4_OT | PCD_DPW1_MTR4_P | PCD_DPW1_MTR4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Small bulk meters | Nr | 0 | 0 | 0 | 10184 | 20368 | 30552 | 40736 | 50920 | [5 empty] | 50920 | 0 | 0 | 0 | 10184 | 20368 | 30552 | 40736 | 50920 | [5 empty] | 50920 | 0 | 100% |  |  | Green | DPW1.18 |  |  | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5 | PCD_DPW1_MTR5_T | PCD_DPW1_MTR5_T | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_O | PCD_DPW1_MTR5_OT | PCD_DPW1_MTR5_OT | PCD_DPW1_MTR5_P | PCD_DPW1_MTR5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Meter Replacements | Nr | 0 | 0 | 0 | 151755 | 303511 | 455266 | 607021 | 758776 | [5 empty] | 758776 | 0 | 0 | 0 | 151755 | 303511 | 455266 | 607021 | 758776 | [5 empty] | 758776 | 0 | 100% |  |  | Green | DPW1.19 |  |  | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6 | PCD_DPW1_MTR6_T | PCD_DPW1_MTR6_T | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_O | PCD_DPW1_MTR6_OT | PCD_DPW1_MTR6_OT | PCD_DPW1_MTR6_P | PCD_DPW1_MTR6_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Connected meters | Nr | 0 | 0 | 0 | 0 | 116315 | 279157 | 488525 | 744419 | [5 empty] | 744419 | 0 | 0 | 0 | 0 | 116315 | 279157 | 488525 | 744419 | [5 empty] | 744419 | 0 | 100% |  |  | Green | DPW1.20 |  |  | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7 | PCD_DPW1_MTR7_T | PCD_DPW1_MTR7_T | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_O | PCD_DPW1_MTR7_OT | PCD_DPW1_MTR7_OT | PCD_DPW1_MTR7_P | PCD_DPW1_MTR7_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Base Overlap Schemes] | Ml/d | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | DPW1.21 |  |  | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1 | PCD_DPW1_SPL1_T | PCD_DPW1_SPL1_T | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_O | PCD_DPW1_SPL1_OT | PCD_DPW1_SPL1_OT | PCD_DPW1_SPL1_P | PCD_DPW1_SPL1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Medium] | Ml/d | 3 | 0 | 0 | 0 | 0 | 2.7 | 2.7 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 0 | 0 | 0 | 0 | 0 | 0 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 100% | 100% |  | Green | DPW1.22 |  |  | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2 | PCD_DPW1_SPL2_T | PCD_DPW1_SPL2_T | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_O | PCD_DPW1_SPL2_OT | PCD_DPW1_SPL2_OT | PCD_DPW1_SPL2_P | PCD_DPW1_SPL2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Low] | Ml/d | 3 | 0 | 0 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 0 | 0 | 0 | 0 | 0 | 22.6 | 0 | 0 | 0 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 22.6 | 100% |  |  | Green | DPW1.23 |  |  | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3 | PCD_DPW1_SPL3_T | PCD_DPW1_SPL3_T | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_O | PCD_DPW1_SPL3_OT | PCD_DPW1_SPL3_OT | PCD_DPW1_SPL3_P | PCD_DPW1_SPL3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Very Low] | Ml/d | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | DPW1.24 |  |  | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4 | PCD_DPW1_SPL4_T | PCD_DPW1_SPL4_T | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_O | PCD_DPW1_SPL4_OT | PCD_DPW1_SPL4_OT | PCD_DPW1_SPL4_P | PCD_DPW1_SPL4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Total] | Ml/d | 3 | 0 | 0 | 22.6 | 22.6 | 25.3 | 25.3 | 43.36 | 20.76 | 20.76 | 20.76 | 20.76 | 20.76 | 43.36 | 20.76 | 0 | 0 | 22.6 | 22.6 | 22.6 | 22.6 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 43.36 | 100% | 208.9% |  | Green | DPW1.25 |  |  | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5 | PCD_DPW1_SPL5_T | PCD_DPW1_SPL5_T | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_O | PCD_DPW1_SPL5_OT | PCD_DPW1_SPL5_OT | PCD_DPW1_SPL5_P | PCD_DPW1_SPL5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | WAFU Benefit | Ml/d | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.26 |  |  | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1 | PCD_DPW1_SPLIN1_T | PCD_DPW1_SPLIN1_T | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_O | PCD_DPW1_SPLIN1_OT | PCD_DPW1_SPLIN1_OT | PCD_DPW1_SPLIN1_P | PCD_DPW1_SPLIN1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | Pipeline length | Km | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.27 |  |  | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2 | PCD_DPW1_SPLIN2_T | PCD_DPW1_SPLIN2_T | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_O | PCD_DPW1_SPLIN2_OT | PCD_DPW1_SPLIN2_OT | PCD_DPW1_SPLIN2_P | PCD_DPW1_SPLIN2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW9 | 0 | Efficiency | Water demand savings (benefit) | Ml/d | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.28 |  |  | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY | PCD_DPW1_EFCY_T | PCD_DPW1_EFCY_T | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_O | PCD_DPW1_EFCY_OT | PCD_DPW1_EFCY_OT | PCD_DPW1_EFCY_P | PCD_DPW1_EFCY_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Length of resilience interconnector | km | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.29 |  |  | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1 | PCD_DPW1_RESIN1_T | PCD_DPW1_RESIN1_T | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_O | PCD_DPW1_RESIN1_OT | PCD_DPW1_RESIN1_OT | PCD_DPW1_RESIN1_P | PCD_DPW1_RESIN1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Crossing connections improvement | Nr | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.30 |  |  | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2 | PCD_DPW1_RESIN2_T | PCD_DPW1_RESIN2_T | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_O | PCD_DPW1_RESIN2_OT | PCD_DPW1_RESIN2_OT | PCD_DPW1_RESIN2_P | PCD_DPW1_RESIN2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Additional storage at reservoirs | Ml | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.31 |  |  | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3 | PCD_DPW1_RESIN3_T | PCD_DPW1_RESIN3_T | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_O | PCD_DPW1_RESIN3_OT | PCD_DPW1_RESIN3_OT | PCD_DPW1_RESIN3_P | PCD_DPW1_RESIN3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Reservoir bypass | Nr | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.32 |  |  | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4 | PCD_DPW1_RESIN4_T | PCD_DPW1_RESIN4_T | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_O | PCD_DPW1_RESIN4_OT | PCD_DPW1_RESIN4_OT | PCD_DPW1_RESIN4_P | PCD_DPW1_RESIN4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Number of water treatment works with new equipment | Nr | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.33 |  |  | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1 | PCD_DPW1_RES1_T | PCD_DPW1_RES1_T | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_O | PCD_DPW1_RES1_OT | PCD_DPW1_RES1_OT | PCD_DPW1_RES1_P | PCD_DPW1_RES1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Upgrade works at water treatment works | % | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.34 |  |  | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2 | PCD_DPW1_RES2_T | PCD_DPW1_RES2_T | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_O | PCD_DPW1_RES2_OT | PCD_DPW1_RES2_OT | PCD_DPW1_RES2_P | PCD_DPW1_RES2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Service reservoirs with new enhanced bypass provision | Nr | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.35 |  |  | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3 | PCD_DPW1_RES3_T | PCD_DPW1_RES3_T | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_O | PCD_DPW1_RES3_OT | PCD_DPW1_RES3_OT | PCD_DPW1_RES3_P | PCD_DPW1_RES3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Installation of new equipment | Nr | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.36 |  |  | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4 | PCD_DPW1_RES4_T | PCD_DPW1_RES4_T | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_O | PCD_DPW1_RES4_OT | PCD_DPW1_RES4_OT | PCD_DPW1_RES4_P | PCD_DPW1_RES4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml of additional service reservoir storage at service reservoirs | Ml | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.37 |  |  | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5 | PCD_DPW1_RES5_T | PCD_DPW1_RES5_T | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_O | PCD_DPW1_RES5_OT | PCD_DPW1_RES5_OT | PCD_DPW1_RES5_P | PCD_DPW1_RES5_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml/d of peak week production capacity of additional process stream | Ml/d | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.38 |  |  | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6 | PCD_DPW1_RES6_T | PCD_DPW1_RES6_T | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_O | PCD_DPW1_RES6_OT | PCD_DPW1_RES6_OT | PCD_DPW1_RES6_P | PCD_DPW1_RES6_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16c | Y | Resilience | Number of raw water reservoirs with the delivery of specified safety improvements | Nr | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.39 |  |  | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7 | PCD_DPW1_RES7_T | PCD_DPW1_RES7_T | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_O | PCD_DPW1_RES7_OT | PCD_DPW1_RES7_OT | PCD_DPW1_RES7_P | PCD_DPW1_RES7_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17b | Y | Cyber | Legal instruments | Nr | 0 | [8 empty] | 1 | 1 | 1 | 1 | 0 | 1 | [8 empty] | 1 | 1 | 1 | 1 | 0 | 1 |  | 100% |  | Green | DPW1.40 |  |  | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR | PCD_DPW1_CYBR_T | PCD_DPW1_CYBR_T | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_O | PCD_DPW1_CYBR_OT | PCD_DPW1_CYBR_OT | PCD_DPW1_CYBR_P | PCD_DPW1_CYBR_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17a | Y | SEMD | Legal instruments | Nr | 0 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 1 | [7 empty] | 1 | 1 | 1 | 1 | 1 | 0 | 1 |  | 100% |  | Green | DPW1.41 |  |  | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD | PCD_DPW1_SEMD_T | PCD_DPW1_SEMD_T | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_O | PCD_DPW1_SEMD_OT | PCD_DPW1_SEMD_OT | PCD_DPW1_SEMD_P | PCD_DPW1_SEMD_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | tCO2e | tonnes | 3 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.42 |  |  | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1 | PCD_DPW1_GGR1_T | PCD_DPW1_GGR1_T | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_O | PCD_DPW1_GGR1_OT | PCD_DPW1_GGR1_OT | PCD_DPW1_GGR1_P | PCD_DPW1_GGR1_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of hectares | Nr | 0 | [12 empty] | 0 | 0 | [12 empty] | 0 | 0 |  |  |  |  | DPW1.43 |  |  | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR | PCD_DPW1_GGR_T | PCD_DPW1_GGR_T | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_O | PCD_DPW1_GGR_OT | PCD_DPW1_GGR_OT | PCD_DPW1_GGR_P | PCD_DPW1_GGR_P
[42 empty] | End_Data | [31 empty] | End_BON

## DPWW1
Ofwat Bon Numbers
Enhancement PCD output - wastewater - Programme level
Header | Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | PCD output (cumulative) - Target | [10 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP reference |  |  | PCD output (cumulative) - Target` | [10 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Performance
[9 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  |  |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%)
Start_Data | [8 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [8 empty] | Start_BON | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA110 Wastewater flow and monitoring | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring permits only or simple schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.1 |  |  | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS | PCD_DPWW1_FMS_T | PCD_DPWW1_FMS_T | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_O | PCD_DPWW1_FMS_OT | PCD_DPWW1_FMS_OT | PCD_DPWW1_FMS_P | PCD_DPWW1_FMS_P
| TMS |  | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring complex schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.2 |  |  | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC | PCD_DPWW1_FMC_T | PCD_DPWW1_FMC_T | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_O | PCD_DPWW1_FMC_OT | PCD_DPWW1_FMC_OT | PCD_DPWW1_FMC_P | PCD_DPWW1_FMC_P
| TMS |  | PCDWW2b | 0 | Continuous river water quality monitoring (CWQM) | Continuous river water quality monitoring (CWQM) | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.3 |  |  | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM | PCD_DPWW1_CWQM_T | PCD_DPWW1_CWQM_T | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_O | PCD_DPWW1_CWQM_OT | PCD_DPWW1_CWQM_OT | PCD_DPWW1_CWQM_P | PCD_DPWW1_CWQM_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only | Nr | 0 |  | 0 | 26 | 26 | 26 | 26 | [5 empty] | 26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 10 | 0 | 10 | 0% |  |  | Red | DPWW1.4 |  |  | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1 | PCD_DPWW1_SPSO1_T | PCD_DPWW1_SPSO1_T | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_O | PCD_DPWW1_SPSO1_OT | PCD_DPWW1_SPSO1_OT | PCD_DPWW1_SPSO1_P | PCD_DPWW1_SPSO1_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.5 |  |  | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2 | PCD_DPWW1_SPSO2_T | PCD_DPWW1_SPSO2_T | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_O | PCD_DPWW1_SPSO2_OT | PCD_DPWW1_SPSO2_OT | PCD_DPWW1_SPSO2_P | PCD_DPWW1_SPSO2_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.6 |  |  | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3 | PCD_DPWW1_SPSO3_T | PCD_DPWW1_SPSO3_T | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_O | PCD_DPWW1_SPSO3_OT | PCD_DPWW1_SPSO3_OT | PCD_DPWW1_SPSO3_P | PCD_DPWW1_SPSO3_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils | Nr | 0 |  | 0 | 17.1852 | 17.1852 | 17.1852 | 22 | [5 empty] | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 38 | 38 | 0 | 38 | 0% |  |  | Red | DPWW1.7 |  |  | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4 | PCD_DPWW1_SPSO4_T | PCD_DPWW1_SPSO4_T | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_O | PCD_DPWW1_SPSO4_OT | PCD_DPWW1_SPSO4_OT | PCD_DPWW1_SPSO4_P | PCD_DPWW1_SPSO4_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.8 |  |  | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5 | PCD_DPWW1_SPSO5_T | PCD_DPWW1_SPSO5_T | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_O | PCD_DPWW1_SPSO5_OT | PCD_DPWW1_SPSO5_OT | PCD_DPWW1_SPSO5_P | PCD_DPWW1_SPSO5_P
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes | Nr | 0 |  | 0 | 0 | 0 | 3 | 6 | [5 empty] | 6 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 6 | 6 | 6 | 2 | 6 | 33.33% |  |  | Red | DPWW1.9 |  |  | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1 | PCD_DPWW1_SOFW1_T | PCD_DPWW1_SOFW1_T | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_O | PCD_DPWW1_SOFW1_OT | PCD_DPWW1_SOFW1_OT | PCD_DPWW1_SOFW1_P | PCD_DPWW1_SOFW1_P
| TMS |  | PCDWW5b | Y | Storm Overflow - Wetland | Wetland area delivered | ha | 0 |  | 0 | 0 | 0 | 2.83 | 7.931 | [5 empty] | 7.931 | 0 | 0 | 0 | 0 | 1.11 | 2.361 | 2.361 | 2.83 | 2.83 | 7.931 | 7.931 | 7.931 | 2.361 | 7.931 | 29.77% |  |  | Red | DPWW1.10 |  |  | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2 | PCD_DPWW1_SOFW2_T | PCD_DPWW1_SOFW2_T | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_O | PCD_DPWW1_SOFW2_OT | PCD_DPWW1_SOFW2_OT | PCD_DPWW1_SOFW2_P | PCD_DPWW1_SOFW2_P
| TMS |  | PCDWW6 | 0 | Storm Overflow - Screens | Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.11 |  |  | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS | PCD_DPWW1_SOFS_T | PCD_DPWW1_SOFS_T | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_O | PCD_DPWW1_SOFS_OT | PCD_DPWW1_SOFS_OT | PCD_DPWW1_SOFS_P | PCD_DPWW1_SOFS_P
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Total number of schemes with a treatment solution delivered to meet compliance | Nr | 0 |  | 0 | 0 | 0 | 0 | 7 | [5 empty] | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 4 | 5 | 7 | 7 | 0 | 7 | 0% |  |  | Red | DPWW1.12 |  |  | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1 | PCD_DPWW1_TCR1_T | PCD_DPWW1_TCR1_T | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_O | PCD_DPWW1_TCR1_OT | PCD_DPWW1_TCR1_OT | PCD_DPWW1_TCR1_P | PCD_DPWW1_TCR1_P
| TMS |  | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Population equivalent served by schemes with a treatment solution being delivered to meet compliance | Nr | 0 |  | 0 | 0 | 0 | 0 | 243105 | [5 empty] | 243105 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 17473 | 33539 | 113791 | 243105 | 243105 | 0 | 243105 | 0% |  |  | Red | DPWW1.13 |  |  | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2 | PCD_DPWW1_TCR2_T | PCD_DPWW1_TCR2_T | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_O | PCD_DPWW1_TCR2_OT | PCD_DPWW1_TCR2_OT | PCD_DPWW1_TCR2_P | PCD_DPWW1_TCR2_P
| TMS |  | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Total number of schemes delivered to meet compliance | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.14 |  |  | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1 | PCD_DPWW1_TNR1_T | PCD_DPWW1_TNR1_T | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_O | PCD_DPWW1_TNR1_OT | PCD_DPWW1_TNR1_OT | PCD_DPWW1_TNR1_P | PCD_DPWW1_TNR1_P
| TMS |  | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Population equivalent served by schemes delivered to meet compliance | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.15 |  |  | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2 | PCD_DPWW1_TNR2_T | PCD_DPWW1_TNR2_T | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_O | PCD_DPWW1_TNR2_OT | PCD_DPWW1_TNR2_OT | PCD_DPWW1_TNR2_P | PCD_DPWW1_TNR2_P
| TMS |  | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Total number of site treatment solutions delivered to meet compliance | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.16 |  |  | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL | PCD_DPWW1_NBS_SOL_T | PCD_DPWW1_NBS_SOL_T | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_O | PCD_DPWW1_NBS_SOL_OT | PCD_DPWW1_NBS_SOL_OT | PCD_DPWW1_NBS_SOL_P | PCD_DPWW1_NBS_SOL_P
| TMS |  | PCDWW13a | 0 | Catchment solutions (WINEP/NEP) | Total number of CNB solutions delivered to meet compliance (allowance/7) | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.17 |  |  | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1 | PCD_DPWW1_CS1_T | PCD_DPWW1_CS1_T | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_O | PCD_DPWW1_CS1_OT | PCD_DPWW1_CS1_OT | PCD_DPWW1_CS1_P | PCD_DPWW1_CS1_P
| TMS |  | PCDWW13a | 0 | Catchment solutions (WINEP/NEP) | Total number of CP solutions delivered to meet compliance (allowance/6) | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.18 |  |  | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2 | PCD_DPWW1_CS2_T | PCD_DPWW1_CS2_T | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_O | PCD_DPWW1_CS2_OT | PCD_DPWW1_CS2_OT | PCD_DPWW1_CS2_P | PCD_DPWW1_CS2_P
| TMS |  | PCDWW14 |  | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.19 |  |  | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1 | PCD_DPWW1_MBT1_T | PCD_DPWW1_MBT1_T | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_O | PCD_DPWW1_MBT1_OT | PCD_DPWW1_MBT1_OT | PCD_DPWW1_MBT1_P | PCD_DPWW1_MBT1_P
| TMS |  | PCDWW14 |  | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Current population equivalent served by STWs with tightened/new microbiological standards | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.20 |  |  | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2 | PCD_DPWW1_MBT2_T | PCD_DPWW1_MBT2_T | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_O | PCD_DPWW1_MBT2_OT | PCD_DPWW1_MBT2_OT | PCD_DPWW1_MBT2_P | PCD_DPWW1_MBT2_P
| TMS |  | PCDWW15 | 0 | Septic tank replacements - treatment solution; (WINEP/NEP) | Total number of septic tank replacement or flow diversion schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.21 |  |  | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR | PCD_DPWW1_STR_T | PCD_DPWW1_STR_T | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_O | PCD_DPWW1_STR_OT | PCD_DPWW1_STR_OT | PCD_DPWW1_STR_P | PCD_DPWW1_STR_P
| TMS |  | PCDWW17 | 0 | 25 year environment plan; (WINEP/NEP) | Number of schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.22 |  |  | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP | PCD_DPWW1_25EP_T | PCD_DPWW1_25EP_T | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_O | PCD_DPWW1_25EP_OT | PCD_DPWW1_25EP_OT | PCD_DPWW1_25EP_P | PCD_DPWW1_25EP_P
| TMS | PR24CA112 Wastewater Other WINEP | PCDWW18 | Y | WINEP Investigations (wastewater) | Number of satisfactorily completed WINEP / NEP investigations - all categories | Nr | 0 |  | 147.6918 | 288.8815 | 431 | 431 | 431 | [5 empty] | 431 | 0 | 0 | 4 | 371 | 402 | 402 | 430 | 431 | 431 | 431 | 431 | 431 | 430 | 431 | 99.77% |  |  | Green | DPWW1.23 |  |  | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG | PCD_DPWW1_WINIVG_T | PCD_DPWW1_WINIVG_T | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_O | PCD_DPWW1_WINIVG_OT | PCD_DPWW1_WINIVG_OT | PCD_DPWW1_WINIVG_P | PCD_DPWW1_WINIVG_P
| TMS |  | PCDWW23a | 0 | Advanced WINEP | Number of restoration plans developed and designed | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.24 |  |  | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1 | PCD_DPWW1_ADWIN1_T | PCD_DPWW1_ADWIN1_T | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_O | PCD_DPWW1_ADWIN1_OT | PCD_DPWW1_ADWIN1_OT | PCD_DPWW1_ADWIN1_P | PCD_DPWW1_ADWIN1_P
| TMS |  | PCDWW23a | 0 | Advanced WINEP | Partnership funding | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.25 |  |  | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2 | PCD_DPWW1_ADWIN2_T | PCD_DPWW1_ADWIN2_T | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_O | PCD_DPWW1_ADWIN2_OT | PCD_DPWW1_ADWIN2_OT | PCD_DPWW1_ADWIN2_P | PCD_DPWW1_ADWIN2_P
| TMS |  | PCDWW23b | 0 | Advanced WINEP | Equivalent storage avoided | m3 | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.26 |  |  | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3 | PCD_DPWW1_ADWIN3_T | PCD_DPWW1_ADWIN3_T | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_O | PCD_DPWW1_ADWIN3_OT | PCD_DPWW1_ADWIN3_OT | PCD_DPWW1_ADWIN3_P | PCD_DPWW1_ADWIN3_P
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24a | 0 | Sludge storage -Tanks | Volume of Sludge Storage delivered | m3 | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.27 |  |  | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT | PCD_DPWW1_SSTT_T | PCD_DPWW1_SSTT_T | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_O | PCD_DPWW1_SSTT_OT | PCD_DPWW1_SSTT_OT | PCD_DPWW1_SSTT_P | PCD_DPWW1_SSTT_P
| TMS |  | PCDWW24b | 0 | Sludge storage (cake pads) | Sludge Storage area delivered | m2 | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.28 |  |  | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP | PCD_DPWW1_SSCP_T | PCD_DPWW1_SSCP_T | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_O | PCD_DPWW1_SSCP_OT | PCD_DPWW1_SSCP_OT | PCD_DPWW1_SSCP_P | PCD_DPWW1_SSCP_P
| TMS |  | PCDWW25a | 0 | Sludge thickening and dewatering | Tonnes of dry solids/ year | ttds/yr | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.29 |  |  | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW | PCD_DPWW1_STDW_T | PCD_DPWW1_STDW_T | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_O | PCD_DPWW1_STDW_OT | PCD_DPWW1_STDW_OT | PCD_DPWW1_STDW_P | PCD_DPWW1_STDW_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge throughput Dryer/Pelletiser installed plant capacity | ttds/yr | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.30 |  |  | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1 | PCD_DPWW1_STOTH1_T | PCD_DPWW1_STOTH1_T | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_O | PCD_DPWW1_STOTH1_OT | PCD_DPWW1_STOTH1_OT | PCD_DPWW1_STOTH1_P | PCD_DPWW1_STOTH1_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge Throughput P Recovery installed plant capacity | 000m3/month | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.31 |  |  | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2 | PCD_DPWW1_STOTH2_T | PCD_DPWW1_STOTH2_T | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_O | PCD_DPWW1_STOTH2_OT | PCD_DPWW1_STOTH2_OT | PCD_DPWW1_STOTH2_P | PCD_DPWW1_STOTH2_P
| TMS |  | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of sites achieving IED compliance | Nr | 0 | 25 | 0 | 2 | 2 | 5 | 25 | [5 empty] | 25 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 7 | 15 | 19 | 21 | 2 | 21 | 8% |  |  | Red | DPWW1.32 |  |  | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED | PCD_DPWW1_BIO_IED_T | PCD_DPWW1_BIO_IED_T | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_O | PCD_DPWW1_BIO_IED_OT | PCD_DPWW1_BIO_IED_OT | PCD_DPWW1_BIO_IED_P | PCD_DPWW1_BIO_IED_P
| TMS | PR24CA116 Wastewater Other | PCDWW32 | Y | Climate change uplift | Spend on schemes for power and flood resilience delivered: | % | 0 |  | 3.6303 | 11.8661 | 25.9213 | 60.893 | 100 | [5 empty] | 100 | 0 | 0 | 3.6303 | 11.8661 | 25.9213 | 60.893 | 89.4283 | 91.635 | 91.7363 | 91.7363 | 91.7363 | 91.7363 | 89.4283 | 91.7363 | 89.43% |  |  | Red | DPWW1.33 |  |  | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP | PCD_DPWW1_CCUP_T | PCD_DPWW1_CCUP_T | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_O | PCD_DPWW1_CCUP_OT | PCD_DPWW1_CCUP_OT | PCD_DPWW1_CCUP_P | PCD_DPWW1_CCUP_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Crosby Rising Main | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.34 |  |  | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1 | PCD_DPWW1_CER1_T | PCD_DPWW1_CER1_T | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_O | PCD_DPWW1_CER1_OT | PCD_DPWW1_CER1_OT | PCD_DPWW1_CER1_P | PCD_DPWW1_CER1_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Halcroft Cottages Sewer | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.35 |  |  | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2 | PCD_DPWW1_CER2_T | PCD_DPWW1_CER2_T | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_O | PCD_DPWW1_CER2_OT | PCD_DPWW1_CER2_OT | PCD_DPWW1_CER2_P | PCD_DPWW1_CER2_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | London Road Terrace Sewer | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.36 |  |  | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3 | PCD_DPWW1_CER3_T | PCD_DPWW1_CER3_T | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_O | PCD_DPWW1_CER3_OT | PCD_DPWW1_CER3_OT | PCD_DPWW1_CER3_P | PCD_DPWW1_CER3_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Rhodes Business Park Sewer | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.37 |  |  | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4 | PCD_DPWW1_CER4_T | PCD_DPWW1_CER4_T | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_O | PCD_DPWW1_CER4_OT | PCD_DPWW1_CER4_OT | PCD_DPWW1_CER4_P | PCD_DPWW1_CER4_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Leyland WwTW | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.38 |  |  | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5 | PCD_DPWW1_CER5_T | PCD_DPWW1_CER5_T | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_O | PCD_DPWW1_CER5_OT | PCD_DPWW1_CER5_OT | PCD_DPWW1_CER5_P | PCD_DPWW1_CER5_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Bowdon WwTW | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.39 |  |  | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6 | PCD_DPWW1_CER6_T | PCD_DPWW1_CER6_T | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_O | PCD_DPWW1_CER6_OT | PCD_DPWW1_CER6_OT | PCD_DPWW1_CER6_P | PCD_DPWW1_CER6_P
| TMS |  | PCDWW32d | 0 | Infiltration | Total length (in metre) of sewer effectively sealed / lined | m | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.40 |  |  | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF | PCD_DPWW1_INF_T | PCD_DPWW1_INF_T | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_O | PCD_DPWW1_INF_OT | PCD_DPWW1_INF_OT | PCD_DPWW1_INF_P | PCD_DPWW1_INF_P
| TMS |  | PCDWW32e | 0 | WW Partnership Funding | spend on schemes for power and flood resilience delivered: | % | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.41 |  |  | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1 | PCD_DPWW1_WWPF1_T | PCD_DPWW1_WWPF1_T | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_O | PCD_DPWW1_WWPF1_OT | PCD_DPWW1_WWPF1_OT | PCD_DPWW1_WWPF1_P | PCD_DPWW1_WWPF1_P
| TMS |  | PCDWW32e | 0 | WW Partnership Funding | Minimum number of schemes delivered | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.42 |  |  | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2 | PCD_DPWW1_WWPF2_T | PCD_DPWW1_WWPF2_T | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_O | PCD_DPWW1_WWPF2_OT | PCD_DPWW1_WWPF2_OT | PCD_DPWW1_WWPF2_P | PCD_DPWW1_WWPF2_P
| TMS |  | PCDWW32f | 0 | Rainwater management | Total storage volume provided via SuDS solutions | Cubic metre | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.43 |  |  | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1 | PCD_DPWW1_RRM1_T | PCD_DPWW1_RRM1_T | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_O | PCD_DPWW1_RRM1_OT | PCD_DPWW1_RRM1_OT | PCD_DPWW1_RRM1_P | PCD_DPWW1_RRM1_P
| TMS |  | PCDWW32f | 0 | Rainwater management | Completion of named schemes | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.44 |  |  | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2 | PCD_DPWW1_RRM2_T | PCD_DPWW1_RRM2_T | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_O | PCD_DPWW1_RRM2_OT | PCD_DPWW1_RRM2_OT | PCD_DPWW1_RRM2_P | PCD_DPWW1_RRM2_P
| TMS |  | PCDWW32g | 0 | Flood and power | Flooding resilience scheme unit rate | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.45 |  |  | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2 | PCD_DPWW1_FP2_T | PCD_DPWW1_FP2_T | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_O | PCD_DPWW1_FP2_OT | PCD_DPWW1_FP2_OT | PCD_DPWW1_FP2_P | PCD_DPWW1_FP2_P
| TMS |  | PCDWW32g | 0 | Flood and power | Power resilience scheme unit rate | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.46 |  |  | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3 | PCD_DPWW1_FP3_T | PCD_DPWW1_FP3_T | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_O | PCD_DPWW1_FP3_OT | PCD_DPWW1_FP3_OT | PCD_DPWW1_FP3_P | PCD_DPWW1_FP3_P
| TMS |  | PCDWW29 | 0 | First time sewerage | Number of connected properties served by S101A schemes | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.47 |  |  | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS | PCD_DPWW1_FTS_T | PCD_DPWW1_FTS_T | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_O | PCD_DPWW1_FTS_OT | PCD_DPWW1_FTS_OT | PCD_DPWW1_FTS_P | PCD_DPWW1_FTS_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW36 | 0 | PR19 Green recovery carryover | Storage in the network close to Nuttall Road combined sewer overflow | m3 | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.48 |  |  | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1 | PCD_DPWW1_GRC1_T | PCD_DPWW1_GRC1_T | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_O | PCD_DPWW1_GRC1_OT | PCD_DPWW1_GRC1_OT | PCD_DPWW1_GRC1_P | PCD_DPWW1_GRC1_P
| TMS |  | PCDWW36 | 0 | PR19 Green recovery carryover | Storm tank capacity at Bury wastewater treatment works | m3 | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.49 |  |  | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2 | PCD_DPWW1_GRC2_T | PCD_DPWW1_GRC2_T | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_O | PCD_DPWW1_GRC2_OT | PCD_DPWW1_GRC2_OT | PCD_DPWW1_GRC2_P | PCD_DPWW1_GRC2_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows | Equivalent storage | m3 | 3 |  | 0 | 10557.9405 | 73905.5835 | 126695.286 | 211158.81 | [5 empty] | 211158.81 | 0 | 0 | 0 | 2077.82 | 20896.83 | 68481.2 | 114534.5 | 177455.23 | 185869.17 | 211158.81 | 211158.81 | 211158.81 | 114534.5 | 211158.81 | 54.24% |  |  | Red | DPWW1.50 |  |  | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES | PCD_DPWW1_SOFES_T | PCD_DPWW1_SOFES_T | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_O | PCD_DPWW1_SOFES_OT | PCD_DPWW1_SOFES_OT | PCD_DPWW1_SOFES_P | PCD_DPWW1_SOFES_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | litres per second | l/s | 3 |  | 0 | 66.965 | 468.755 | 803.58 | 1339.3 | [5 empty] | 1339.3 | 0 | 0 | 0 | 0 | 0 | 32.8 | 232.8 | 485 | 535 | 1339.3 | 1339.3 | 1339.3 | 232.8 | 1339.3 | 17.38% |  |  | Red | DPWW1.51 |  |  | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT | PCD_DPWW1_FTFT_T | PCD_DPWW1_FTFT_T | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_O | PCD_DPWW1_FTFT_OT | PCD_DPWW1_FTFT_OT | PCD_DPWW1_FTFT_P | PCD_DPWW1_FTFT_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Population equivalent served | 000s | 3 |  | 0 | 0 | 992.4325 | 2381.8379 | 3969.7299 | [5 empty] | 3969.7299 | 0 | 0 | 7.3361 | 7.3361 | 7.3361 | 241.3729 | 866.6689 | 1623.69 | 2838.9477 | 3478.1102 | 3969.3453 | 3969.7301 | 866.6689 | 3969.7301 | 21.83% |  |  | Red | DPWW1.52 |  |  | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL | PCD_DPWW1_PRMVL_T | PCD_DPWW1_PRMVL_T | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_O | PCD_DPWW1_PRMVL_OT | PCD_DPWW1_PRMVL_OT | PCD_DPWW1_PRMVL_P | PCD_DPWW1_PRMVL_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Added Process Capacity in PE | Nr | 3 |  | 0 | 0 | 0 | 3630.8805 | 93769.523 | [5 empty] | 93769.523 | 0 | 0 | 0 | 0 | 0 | 0 | 20711.6927 | 40051.2656 | 59347.0188 | 92671.9055 | 93769.5209 | 93769.5209 | 20711.6927 | 93769.5209 | 22.09% |  |  | Red | DPWW1.53 |  |  | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW | PCD_DPWW1_GSTW_T | PCD_DPWW1_GSTW_T | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_O | PCD_DPWW1_GSTW_OT | PCD_DPWW1_GSTW_OT | PCD_DPWW1_GSTW_P | PCD_DPWW1_GSTW_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Population equivalent served | 000s | 3 |  | 55.0287 | 137.9683 | 231.0587 | 491.4389 | 492.7439 | [5 empty] | 492.7439 | 0 | 0 | 0 | 7.8826 | 100.9731 | 115.1954 | 168.3684 | 168.7734 | 415.2211 | 492.7439 | 492.7439 | 492.7439 | 168.3684 | 492.7439 | 34.17% |  |  | Red | DPWW1.54 |  |  | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP | PCD_DPWW1_TTSP_T | PCD_DPWW1_TTSP_T | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_O | PCD_DPWW1_TTSP_OT | PCD_DPWW1_TTSP_OT | PCD_DPWW1_TTSP_P | PCD_DPWW1_TTSP_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes | Nr | 0 |  | 27 | 34 | 55 | 62 | 66 | [5 empty] | 66 | 0 | 9 | 22 | 27 | 42 | 58 | 64 | 68 | 68 | 68 | 68 | 68 | 64 | 68 | 96.97% |  |  | Red | DPWW1.55 |  |  | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA | PCD_DPWW1_PR19WINCA_T | PCD_DPWW1_PR19WINCA_T | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_O | PCD_DPWW1_PR19WINCA_OT | PCD_DPWW1_PR19WINCA_OT | PCD_DPWW1_PR19WINCA_P | PCD_DPWW1_PR19WINCA_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | tCO2e | tonnes | 3 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.56 |  |  | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1 | PCD_DPWW1_GGR1_T | PCD_DPWW1_GGR1_T | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_O | PCD_DPWW1_GGR1_OT | PCD_DPWW1_GGR1_OT | PCD_DPWW1_GGR1_P | PCD_DPWW1_GGR1_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of sites | Nr | 0 | [11 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPWW1.57 |  |  | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2 | PCD_DPWW1_GGR2_T | PCD_DPWW1_GGR2_T | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_O | PCD_DPWW1_GGR2_OT | PCD_DPWW1_GGR2_OT | PCD_DPWW1_GGR2_P | PCD_DPWW1_GGR2_P
[40 empty] | End_Data | [29 empty] | End_BON

## DPW2
DPW2 | [42 empty] | Ofwat Bon Numbers
Enhancement PCD Expenditure - Water - Progamme Level
[43 empty] | _NP | [12 empty] | _T | _T | [12 empty] | _OT | _OT | _P | _P
Header | Company | PCD Model | PCD Ref | PCD applicable to company | Line Description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [11 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [11 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [11 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [11 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance (Expenditure)
[10 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 CPIH prices | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%)
Start_Data | [9 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [6 empty] | Start_BON | 2025-30 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation hectares | Hectares of environmental improvement | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.1 |  |  | PCD_DPW2_BIOCON1_NP | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1 | PCD_DPW2_BIOCON1_T | PCD_DPW2_BIOCON1_T | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_O | PCD_DPW2_BIOCON1_OT | PCD_DPW2_BIOCON1_OT | PCD_DPW2_BIOCON1_P | PCD_DPW2_BIOCON1_P
| TMS | PR24CA106 Water WINEP | PCDW1 | 0 | Biodiversity and Conservation kilometres | Kilometres of environmental improvement | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.2 |  |  | PCD_DPW2_BIOCON2_NP | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2 | PCD_DPW2_BIOCON2_T | PCD_DPW2_BIOCON2_T | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_O | PCD_DPW2_BIOCON2_OT | PCD_DPW2_BIOCON2_OT | PCD_DPW2_BIOCON2_P | PCD_DPW2_BIOCON2_P
| TMS | PR24CA106 Water WINEP | PCDW4 | 0 | Drinking Water Protected Areas | No Deterioration and Implementation actions | £m | 0 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.3 |  |  | PCD_DPW2_DWPA_NP | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA | PCD_DPW2_DWPA_T | PCD_DPW2_DWPA_T | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_O | PCD_DPW2_DWPA_OT | PCD_DPW2_DWPA_OT | PCD_DPW2_DWPA_P | PCD_DPW2_DWPA_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive interconnector | Length of WFD interconnector | £m | 3 | 2.8971 |  |  | 0.64263 | 2.1634 | 5.1229 | 10.3129 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 27.5222 | 0 | 0 | 0 | 0.17749 | 3.554 | 8.6188 | 15.319 | 15.4034 | 15.4875 | 15.4878 | 15.4878 | 15.4878 | 15.319 | 15.4878 | 55.66% | 56.27% | DPW2.4 |  |  | PCD_DPW2_WFDI_NP | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI | PCD_DPW2_WFDI_T | PCD_DPW2_WFDI_T | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_O | PCD_DPW2_WFDI_OT | PCD_DPW2_WFDI_OT | PCD_DPW2_WFDI_P | PCD_DPW2_WFDI_P
| TMS | PR24CA106 Water WINEP | PCDW5 | Y | Water Framework Directive actions | Other WFD actions | £m | 0 | 1.0004 |  |  | 0.44384 | 1.4942 | 3.5382 | 7.1227 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 19.0085 | 0 | 0.055163 | 1.6869 | 3.5833 | 13.155 | 21.9058 | 22.3247 | 22.3666 | 22.3666 | 22.3666 | 22.3666 | 22.3666 | 22.3247 | 22.3666 | 117.4% | 117.7% | DPW2.5 |  |  | PCD_DPW2_WFDA_NP | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA | PCD_DPW2_WFDA_T | PCD_DPW2_WFDA_T | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_O | PCD_DPW2_WFDA_OT | PCD_DPW2_WFDA_OT | PCD_DPW2_WFDA_P | PCD_DPW2_WFDA_P
| TMS | PR24CA106 Water WINEP | PCDW8 | Y | Water WINEP/NEP Investigations | Water WINEP/NEP Investigations | £m | 3 | 0.471 | 0 | 0 | 5.5903 | 11.601 | 13.5926 | 15.5641 | 17.427 | [5 empty] | 17.427 | 0 | 0 | 0.0081028 | 5.5978 | 12.3008 | 13.9485 | 15.6351 | 17.2129 | 17.2195 | 17.2211 | 17.2211 | 17.2211 | 17.2211 | 17.2129 | 17.2211 | 98.77% |  | DPW2.6 |  |  | PCD_DPW2_WIVG_NP | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG | PCD_DPW2_WIVG_T | PCD_DPW2_WIVG_T | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_O | PCD_DPW2_WIVG_OT | PCD_DPW2_WIVG_OT | PCD_DPW2_WIVG_P | PCD_DPW2_WIVG_P
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 | Y | Raw Water Deterioration and Taste, Odour and Colour | Legal instruments | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.7 |  |  | PCD_DPW2_RWD_NP | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD | PCD_DPW2_RWD_T | PCD_DPW2_RWD_T | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_O | PCD_DPW2_RWD_OT | PCD_DPW2_RWD_OT | PCD_DPW2_RWD_P | PCD_DPW2_RWD_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead communication pipes replaced/relined | £m | 3 | 0.0015441 |  |  | 11.3753 | 29.1756 | 48.392 | 67.462 | 83.384 | [5 empty] | 83.384 | 0 | 0 | 0 | 10.5781 | 25.7394 | 40.7947 | 55.8583 | 70.9011 | 70.9011 | 70.9011 | 70.9011 | 70.9011 | 70.9011 | 70.9011 | 70.9011 | 85.03% |  | DPW2.8 |  |  | PCD_DPW2_LEAD1_NP | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1 | PCD_DPW2_LEAD1_T | PCD_DPW2_LEAD1_T | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_O | PCD_DPW2_LEAD1_OT | PCD_DPW2_LEAD1_OT | PCD_DPW2_LEAD1_P | PCD_DPW2_LEAD1_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Non-schools | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.9 |  |  | PCD_DPW2_LEAD2_NP | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2 | PCD_DPW2_LEAD2_T | PCD_DPW2_LEAD2_T | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_O | PCD_DPW2_LEAD2_OT | PCD_DPW2_LEAD2_OT | PCD_DPW2_LEAD2_P | PCD_DPW2_LEAD2_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead external supply pipes replaced/relined - Schools | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.10 |  |  | PCD_DPW2_LEAD3_NP | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3 | PCD_DPW2_LEAD3_T | PCD_DPW2_LEAD3_T | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_O | PCD_DPW2_LEAD3_OT | PCD_DPW2_LEAD3_OT | PCD_DPW2_LEAD3_P | PCD_DPW2_LEAD3_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Non-schools | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.11 |  |  | PCD_DPW2_LEAD4_NP | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4 | PCD_DPW2_LEAD4_T | PCD_DPW2_LEAD4_T | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_O | PCD_DPW2_LEAD4_OT | PCD_DPW2_LEAD4_OT | PCD_DPW2_LEAD4_P | PCD_DPW2_LEAD4_P
| TMS | PR24CA108 Water quality | PCDW15 | Y | Lead | Lead internal supply pipes replaced/relined - Schools | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.12 |  |  | PCD_DPW2_LEAD5_NP | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5 | PCD_DPW2_LEAD5_T | PCD_DPW2_LEAD5_T | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_O | PCD_DPW2_LEAD5_OT | PCD_DPW2_LEAD5_OT | PCD_DPW2_LEAD5_P | PCD_DPW2_LEAD5_P
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 | Y | W Resilience CC Uplift | Spend on scheme as a % of allowance | £m | 3 | 0.3291 |  | 0 | 4.0293 | 11.3859 | 18.6016 | 26.0632 | 32.9099 | [5 empty] | 32.9099 | 0 | 0 | 0 | 0.94188 | 4.3866 | 8.4105 | 20.6122 | 28.6115 | 28.9109 | 28.9813 | 28.9813 | 28.9813 | 28.9813 | 28.6115 | 28.9813 | 86.94% |  | DPW2.13 |  |  | PCD_DPW2_WRESUP_NP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP | PCD_DPW2_WRESUP_T | PCD_DPW2_WRESUP_T | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_O | PCD_DPW2_WRESUP_OT | PCD_DPW2_WRESUP_OT | PCD_DPW2_WRESUP_P | PCD_DPW2_WRESUP_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | New installations | £m | 3 | 0.00041923 |  | 0 | 29.269 | 58.5384 | 87.8074 | 117.0768 | 146.3458 | [5 empty] | 146.3458 | 0 | 0 | 0 | 29.1751 | 57.74 | 85.6951 | 113.6503 | 141.6054 | 141.6054 | 141.6054 | 141.6054 | 141.6054 | 141.6054 | 141.6054 | 141.6054 | 96.76% |  | DPW2.14 |  |  | PCD_DPW2_MTR1_NP | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1 | PCD_DPW2_MTR1_T | PCD_DPW2_MTR1_T | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_O | PCD_DPW2_MTR1_OT | PCD_DPW2_MTR1_OT | PCD_DPW2_MTR1_P | PCD_DPW2_MTR1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Household meter upgrades | £m | 3 | 3.2257e-05 |  | 0 | 4.1643 | 8.3286 | 12.4929 | 16.6572 | 20.8214 | [5 empty] | 20.8214 | 0 | 0 | 0 | 9.3363 | 18.6726 | 28.009 | 37.3453 | 46.6816 | 46.6816 | 46.6816 | 46.6816 | 46.6816 | 46.6816 | 46.6816 | 46.6816 | 224.2% |  | DPW2.15 |  |  | PCD_DPW2_MTR2_NP | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2 | PCD_DPW2_MTR2_T | PCD_DPW2_MTR2_T | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_O | PCD_DPW2_MTR2_OT | PCD_DPW2_MTR2_OT | PCD_DPW2_MTR2_P | PCD_DPW2_MTR2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Non household meter upgrades | £m | 3 | 3.2257e-05 |  | 0 | 0.73084 | 1.4617 | 2.1925 | 2.9234 | 3.6542 | [5 empty] | 3.6542 | 0 | 0 | 0 | 1.7105 | 3.421 | 5.1315 | 6.842 | 8.5525 | 8.5525 | 8.5525 | 8.5525 | 8.5525 | 8.5525 | 8.5525 | 8.5525 | 234% |  | DPW2.16 |  |  | PCD_DPW2_MTR3_NP | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3 | PCD_DPW2_MTR3_T | PCD_DPW2_MTR3_T | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_O | PCD_DPW2_MTR3_OT | PCD_DPW2_MTR3_OT | PCD_DPW2_MTR3_P | PCD_DPW2_MTR3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Large bulk meters | £m | 3 | 0.0035777 |  | 0 | 3.1305 | 6.261 | 9.3915 | 12.522 | 15.6525 | [5 empty] | 15.6525 | 0 | 0 | 0 | 2.9916 | 5.9833 | 8.9749 | 11.9665 | 14.9582 | 14.9582 | 14.9582 | 14.9582 | 14.9582 | 14.9582 | 14.9582 | 14.9582 | 95.56% |  | DPW2.17 |  |  | PCD_DPW2_MTR4_NP | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4 | PCD_DPW2_MTR4_T | PCD_DPW2_MTR4_T | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_O | PCD_DPW2_MTR4_OT | PCD_DPW2_MTR4_OT | PCD_DPW2_MTR4_P | PCD_DPW2_MTR4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Small bulk meters | £m | 3 | 0.0005835 |  | 0 | 5.9423 | 11.8847 | 17.827 | 23.7693 | 29.7117 | [5 empty] | 29.7117 | 0 | 0 | 0 | 6.0343 | 12.0686 | 18.1029 | 24.1372 | 30.1715 | 30.1715 | 30.1715 | 30.1715 | 30.1715 | 30.1715 | 30.1715 | 30.1715 | 101.5% |  | DPW2.18 |  |  | PCD_DPW2_MTR5_NP | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5 | PCD_DPW2_MTR5_T | PCD_DPW2_MTR5_T | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_O | PCD_DPW2_MTR5_OT | PCD_DPW2_MTR5_OT | PCD_DPW2_MTR5_P | PCD_DPW2_MTR5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Meter Replacements | £m | 3 | 0.00012131 |  | 0 | 18.4094 | 36.8189 | 55.2283 | 73.6377 | 92.0471 | [5 empty] | 92.0471 | 0 | 0 | 0 | 25.0203 | 50.0406 | 75.061 | 100.0813 | 125.1016 | 125.1016 | 125.1016 | 125.1016 | 125.1016 | 125.1016 | 125.1016 | 125.1016 | 135.9% |  | DPW2.19 |  |  | PCD_DPW2_MTR6_NP | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6 | PCD_DPW2_MTR6_T | PCD_DPW2_MTR6_T | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_O | PCD_DPW2_MTR6_OT | PCD_DPW2_MTR6_OT | PCD_DPW2_MTR6_P | PCD_DPW2_MTR6_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW12 | Y | Metering | Connected meters | £m | 3 | 4.9836e-05 | 0 | 0 | 11.5934 | 23.1869 | 34.7803 | 46.3738 | 57.9672 | [5 empty] | 57.9672 | 0 | 0 | 0 | 6.3575 | 8.8652 | 11.7723 | 15.0454 | 18.7043 | 18.7043 | 18.7043 | 18.7043 | 18.7043 | 18.7043 | 18.7043 | 18.7043 | 32.27% |  | DPW2.20 |  |  | PCD_DPW2_MTR7_NP | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7 | PCD_DPW2_MTR7_T | PCD_DPW2_MTR7_T | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_O | PCD_DPW2_MTR7_OT | PCD_DPW2_MTR7_OT | PCD_DPW2_MTR7_P | PCD_DPW2_MTR7_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Base Overlap Schemes] | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.21 |  |  | PCD_DPW2_SPL1_NP | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1 | PCD_DPW2_SPL1_T | PCD_DPW2_SPL1_T | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_O | PCD_DPW2_SPL1_OT | PCD_DPW2_SPL1_OT | PCD_DPW2_SPL1_P | PCD_DPW2_SPL1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Medium] | £m | 3 |  |  |  | 6.9099 | 18.3405 | 40.1917 | 61.3835 | 80.1504 | [5 empty] | 80.1504 | 0 | 0 | 0 | 1.3086 | 9.0064 | 26.6948 | 45.9702 | 56.6456 | 56.6456 | 56.6456 | 56.6456 | 56.6456 | 56.6456 | 56.6456 | 56.6456 | 70.67% |  | DPW2.22 |  |  | PCD_DPW2_SPL2_NP | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2 | PCD_DPW2_SPL2_T | PCD_DPW2_SPL2_T | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_O | PCD_DPW2_SPL2_OT | PCD_DPW2_SPL2_OT | PCD_DPW2_SPL2_P | PCD_DPW2_SPL2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Low] | £m | 3 |  |  |  | 3.0306 | 6.105 | 9.2251 | 12.3899 | 15.6013 | [5 empty] | 15.6013 | 0 | 2.2322 | 4.4185 | 7.2606 | 10.0991 | 12.9321 | 15.7609 | 18.5898 | 18.5898 | 18.5898 | 18.5898 | 18.5898 | 18.5898 | 18.5898 | 18.5898 | 119.2% |  | DPW2.23 |  |  | PCD_DPW2_SPL3_NP | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3 | PCD_DPW2_SPL3_T | PCD_DPW2_SPL3_T | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_O | PCD_DPW2_SPL3_OT | PCD_DPW2_SPL3_OT | PCD_DPW2_SPL3_P | PCD_DPW2_SPL3_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Very Low] | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.24 |  |  | PCD_DPW2_SPL4_NP | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4 | PCD_DPW2_SPL4_T | PCD_DPW2_SPL4_T | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_O | PCD_DPW2_SPL4_OT | PCD_DPW2_SPL4_OT | PCD_DPW2_SPL4_P | PCD_DPW2_SPL4_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a | Y | Supply | WAFU Benefit [Total] | £m | 3 |  |  |  | 9.9405 | 24.4456 | 49.4168 | 73.7734 | 95.7517 | [5 empty] | 95.7517 | 0 | 0 | 0 | 8.5692 | 19.1055 | 39.6269 | 61.7311 | 75.2354 | 75.2354 | 75.2354 | 75.2354 | 75.2354 | 75.2354 | 75.2354 | 75.2354 | 78.57% |  | DPW2.25 |  |  | PCD_DPW2_SPL5_NP | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5 | PCD_DPW2_SPL5_T | PCD_DPW2_SPL5_T | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_O | PCD_DPW2_SPL5_OT | PCD_DPW2_SPL5_OT | PCD_DPW2_SPL5_P | PCD_DPW2_SPL5_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | WAFU Benefit | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.26 |  |  | PCD_DPW2_SPLIN1_NP | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1 | PCD_DPW2_SPLIN1_T | PCD_DPW2_SPLIN1_T | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_O | PCD_DPW2_SPLIN1_OT | PCD_DPW2_SPLIN1_OT | PCD_DPW2_SPLIN1_P | PCD_DPW2_SPLIN1_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b | 0 | Supply interconnectors | Pipeline length | Km | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.27 |  |  | PCD_DPW2_SPLIN2_NP | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2 | PCD_DPW2_SPLIN2_T | PCD_DPW2_SPLIN2_T | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_O | PCD_DPW2_SPLIN2_OT | PCD_DPW2_SPLIN2_OT | PCD_DPW2_SPLIN2_P | PCD_DPW2_SPLIN2_P
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW9 | 0 | Efficiency | Water demand savings (benefit) | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.28 |  |  | PCD_DPW2_EFCY_NP | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY | PCD_DPW2_EFCY_T | PCD_DPW2_EFCY_T | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_O | PCD_DPW2_EFCY_OT | PCD_DPW2_EFCY_OT | PCD_DPW2_EFCY_P | PCD_DPW2_EFCY_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Length of resilience interconnector | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.29 |  |  | PCD_DPW2_RESIN1_NP | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1 | PCD_DPW2_RESIN1_T | PCD_DPW2_RESIN1_T | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_O | PCD_DPW2_RESIN1_OT | PCD_DPW2_RESIN1_OT | PCD_DPW2_RESIN1_P | PCD_DPW2_RESIN1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Crossing connections improvement | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.30 |  |  | PCD_DPW2_RESIN2_NP | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2 | PCD_DPW2_RESIN2_T | PCD_DPW2_RESIN2_T | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_O | PCD_DPW2_RESIN2_OT | PCD_DPW2_RESIN2_OT | PCD_DPW2_RESIN2_P | PCD_DPW2_RESIN2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Additional storage at reservoirs | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.31 |  |  | PCD_DPW2_RESIN3_NP | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3 | PCD_DPW2_RESIN3_T | PCD_DPW2_RESIN3_T | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_O | PCD_DPW2_RESIN3_OT | PCD_DPW2_RESIN3_OT | PCD_DPW2_RESIN3_P | PCD_DPW2_RESIN3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16b | 0 | Resilience Interconnector | Reservoir bypass | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.32 |  |  | PCD_DPW2_RESIN4_NP | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4 | PCD_DPW2_RESIN4_T | PCD_DPW2_RESIN4_T | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_O | PCD_DPW2_RESIN4_OT | PCD_DPW2_RESIN4_OT | PCD_DPW2_RESIN4_P | PCD_DPW2_RESIN4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Number of water treatment works with new equipment | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.33 |  |  | PCD_DPW2_RES1_NP | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1 | PCD_DPW2_RES1_T | PCD_DPW2_RES1_T | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_O | PCD_DPW2_RES1_OT | PCD_DPW2_RES1_OT | PCD_DPW2_RES1_P | PCD_DPW2_RES1_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Upgrade works at water treatment works | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.34 |  |  | PCD_DPW2_RES2_NP | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2 | PCD_DPW2_RES2_T | PCD_DPW2_RES2_T | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_O | PCD_DPW2_RES2_OT | PCD_DPW2_RES2_OT | PCD_DPW2_RES2_P | PCD_DPW2_RES2_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Service reservoirs with new enhanced bypass provision | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.35 |  |  | PCD_DPW2_RES3_NP | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3 | PCD_DPW2_RES3_T | PCD_DPW2_RES3_T | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_O | PCD_DPW2_RES3_OT | PCD_DPW2_RES3_OT | PCD_DPW2_RES3_P | PCD_DPW2_RES3_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Installation of new equipment | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.36 |  |  | PCD_DPW2_RES4_NP | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4 | PCD_DPW2_RES4_T | PCD_DPW2_RES4_T | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_O | PCD_DPW2_RES4_OT | PCD_DPW2_RES4_OT | PCD_DPW2_RES4_P | PCD_DPW2_RES4_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml of additional service reservoir storage at service reservoirs | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.37 |  |  | PCD_DPW2_RES5_NP | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5 | PCD_DPW2_RES5_T | PCD_DPW2_RES5_T | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_O | PCD_DPW2_RES5_OT | PCD_DPW2_RES5_OT | PCD_DPW2_RES5_P | PCD_DPW2_RES5_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16a | 0 | Resilience | Ml/d of peak week production capacity of additional process stream | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.38 |  |  | PCD_DPW2_RES6_NP | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6 | PCD_DPW2_RES6_T | PCD_DPW2_RES6_T | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_O | PCD_DPW2_RES6_OT | PCD_DPW2_RES6_OT | PCD_DPW2_RES6_P | PCD_DPW2_RES6_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16c | 0 | Resilience | Number of raw water reservoirs with the delivery of specified safety improvements | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.39 |  |  | PCD_DPW2_RES7_NP | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7 | PCD_DPW2_RES7_T | PCD_DPW2_RES7_T | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_O | PCD_DPW2_RES7_OT | PCD_DPW2_RES7_OT | PCD_DPW2_RES7_P | PCD_DPW2_RES6_P
| TMS | PR24CA109 Water Resilience and Security | PCDW16c | 0 | Resilience | Reservoirs - spend on MITIOS (Measures in the Interest of Safety) | £m | 3 | [13 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPW2.40 |  |  | PCD_DPW2_RES8_NP | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8 | PCD_DPW2_RES8_T | PCD_DPW2_RES8_T | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_O | PCD_DPW2_RES8_OT | PCD_DPW2_RES8_OT | PCD_DPW2_RES8_P | PCD_DPW2_RES8_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17b | Y | Cyber | Legal instruments | £m | 3 | 112.0115 |  |  | 25.9834 | 47.7608 | 68.3195 | 90.9236 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 112.0115 | 0 | 0 | 19.0705 | 48.0883 | 72.8448 | 86.6581 | 102.1947 | 102.1947 | 102.1947 | 102.1947 | 102.1947 | 102.1947 | 102.1947 | 102.1947 | 91.24% | 91.24% | DPW2.41 |  |  | PCD_DPW2_CYBR_NP | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR | PCD_DPW2_CYBR_T | PCD_DPW2_CYBR_T | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_O | PCD_DPW2_CYBR_OT | PCD_DPW2_CYBR_OT | PCD_DPW2_CYBR_P | PCD_DPW2_CYBR_P
| TMS | PR24CA109 Water Resilience and Security | PCDW17a | Y | SEMD | Legal instruments | £m | 3 | 28.088 |  |  | 2.2744 | 5.5131 | 9.9145 | 17.8311 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 28.088 | 0 | 0 | 7.3726 | 12.6009 | 17.8194 | 23.0252 | 28.226 | 28.226 | 28.226 | 28.226 | 28.226 | 28.226 | 28.226 | 28.226 | 100.5% | 100.5% | DPW2.42 |  |  | PCD_DPW2_SEMD_NP | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD | PCD_DPW2_SEMD_T | PCD_DPW2_SEMD_T | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_O | PCD_DPW2_SEMD_OT | PCD_DPW2_SEMD_OT | PCD_DPW2_SEMD_P | PCD_DPW2_SEMD_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of hectares | £m | 3 | [13 empty] | 0 | 0 | 0.12742 | 0.939 | 5.9344 | 10.52 | 10.52 | 10.52 | 10.52 | 10.52 | 10.52 | 10.52 | 10.52 | 10.52 | 10.52 | 10.52 |  |  | DPW2.43 |  |  | PCD_DPW2_GGR_NP | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR | PCD_DPW2_GGR_T | PCD_DPW2_GGR_T | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_O | PCD_DPW2_GGR_OT | PCD_DPW2_GGR_OT | PCD_DPW2_GGR_P | PCD_DPW2_GGR_P
NONPCD1 | TMS |  |  |  | Total other non - PCD enhancement water expenditure, totex | Total other non - PCD enhancement water expenditure, totex | £m | 3 | [13 empty] | 0 | 0 | 84.96 | 205.4618 | 477.1885 | 814.3108 | 1244.7715 | 1734.7611 | 2619.6739 | 2770.9684 | 2832.674 | 2841.196 | 2845.2333 | 2846.2157 | 2619.6739 | 2846.2157 |  |  | DPW2.44 |  |  | PCD_DPW2_NONPCD1_NP | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1 | PCD_DPW2_NONPCD1_T | PCD_DPW2_NONPCD1_T | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_O | PCD_DPW2_NONPCD1_OT | PCD_DPW2_NONPCD1_OT | PCD_DPW2_NONPCD1_P | PCD_DPW2_NONPCD1_P
NONPCD2 | TMS |  |  |  | Total PCD and non - PCD enhancement expenditure; water totex | Total PCD and non - PCD enhancement expenditure; water totex | £m | 3 |  | 0 | 0 | 143.4601 | 304.4653 | 486.0348 | 675.7866 | 878.0546 | 186.6302 | 186.6302 | 186.6302 | 186.6302 | 186.6302 | 878.0546 | 186.6302 | 87.3196 | 210.8826 | 626.1346 | 1126.7099 | 1737.8188 | 2410.1246 | 3451.2298 | 3602.9566 | 3664.8183 | 3673.3406 | 3677.3778 | 3678.3602 | 3451.2298 | 3678.3602 | 393.1% | 1971% | DPW2.45 |  |  | PCD_DPW2_NONPCD2_NP | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2 | PCD_DPW2_NONPCD2_T | PCD_DPW2_NONPCD2_T | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_O | PCD_DPW2_NONPCD2_OT | PCD_DPW2_NONPCD2_OT | PCD_DPW2_NONPCD2_P | PCD_DPW2_NONPCD2_P
[41 empty] | End_Data | [32 empty] | End_BON

## DPWW2
DPWW2 | [41 empty] | Ofwat Bon Numbers
Enhancement PCD expenditure - wastewater - Programme level
Header | Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance
[10 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%)
Start_Data | [9 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [6 empty] | Start_BON | 2025-30 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA110 Wastewater flow and monitoring | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring permits only or simple schemes delivered | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.1 |  |  | PCD_DPWW2_FMS_NP | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS | PCD_DPWW2_FMS_T | PCD_DPWW2_FMS_T | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_O | PCD_DPWW2_FMS_OT | PCD_DPWW2_FMS_OT | PCD_DPWW2_FMS_P | PCD_DPWW2_FMS_P
| TMS |  | PCDWW2a | 0 | Flow monitoring at sewage treatment works; (WINEP/NEP) | Number of flow monitoring complex schemes delivered | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.2 |  |  | PCD_DPWW2_FMC_NP | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC | PCD_DPWW2_FMC_T | PCD_DPWW2_FMC_T | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_O | PCD_DPWW2_FMC_OT | PCD_DPWW2_FMC_OT | PCD_DPWW2_FMC_P | PCD_DPWW2_FMC_P
| TMS |  | PCDWW2b | 0 | Continuous river water quality monitoring (CWQM) | Continuous river water quality monitoring (CWQM) | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.3 |  |  | PCD_DPWW2_CWQM_NP | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM | PCD_DPWW2_CWQM_T | PCD_DPWW2_CWQM_T | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_O | PCD_DPWW2_CWQM_OT | PCD_DPWW2_CWQM_OT | PCD_DPWW2_CWQM_P | PCD_DPWW2_CWQM_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM only | £m | 3 | 0.14293 |  | 1.4883 | 2.9753 | 3.3463 | 3.5314 | 3.7162 | [5 empty] | 3.7162 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21279 | 0.70486 | 1.4791 | 3.9076 | 4.312 | 4.355 | 0.21279 | 4.355 | 5.726% |  | DPWW2.4 |  |  | PCD_DPWW2_SPSO1_NP | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1 | PCD_DPWW2_SPSO1_T | PCD_DPWW2_SPSO1_T | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_O | PCD_DPWW2_SPSO1_OT | PCD_DPWW2_SPSO1_OT | PCD_DPWW2_SPSO1_P | PCD_DPWW2_SPSO1_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + civils | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.5 |  |  | PCD_DPWW2_SPSO2_NP | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2 | PCD_DPWW2_SPSO2_T | PCD_DPWW2_SPSO2_T | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_O | PCD_DPWW2_SPSO2_OT | PCD_DPWW2_SPSO2_OT | PCD_DPWW2_SPSO2_P | PCD_DPWW2_SPSO2_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.6 |  |  | PCD_DPWW2_SPSO3_NP | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3 | PCD_DPWW2_SPSO3_T | PCD_DPWW2_SPSO3_T | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_O | PCD_DPWW2_SPSO3_OT | PCD_DPWW2_SPSO3_OT | PCD_DPWW2_SPSO3_P | PCD_DPWW2_SPSO3_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - EDM + PFF + civils | £m | 3 | 0.25331 |  | 2.2317 | 4.4616 | 5.018 | 5.2956 | 5.5727 | [5 empty] | 5.5727 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3124 | 1.0348 | 2.1715 | 5.7367 | 6.3304 | 6.3935 | 0.3124 | 6.3935 | 5.606% |  | DPWW2.7 |  |  | PCD_DPWW2_SPSO4_NP | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4 | PCD_DPWW2_SPSO4_T | PCD_DPWW2_SPSO4_T | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_O | PCD_DPWW2_SPSO4_OT | PCD_DPWW2_SPSO4_OT | PCD_DPWW2_SPSO4_P | PCD_DPWW2_SPSO4_P
| TMS |  | PCDWW3 | Y | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | Number of MCERTs monitoring schemes at SPS emergency overflows - Permits only | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.8 |  |  | PCD_DPWW2_SPSO5_NP | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5 | PCD_DPWW2_SPSO5_T | PCD_DPWW2_SPSO5_T | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_O | PCD_DPWW2_SPSO5_OT | PCD_DPWW2_SPSO5_OT | PCD_DPWW2_SPSO5_P | PCD_DPWW2_SPSO5_P
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes | £m | 3 |  |  | 2.2636 | 4.445 | 13.0605 | 30.6829 | 63.11 | [5 empty] | 63.11 | 0 | 0 | 0.94617 | 9.0304 | 18.9009 | 30.8736 | 44.9823 | 59.9396 | 71.0714 | 76.4123 | 76.4123 | 76.4123 | 44.9823 | 76.4123 | 71.28% |  | DPWW2.9 |  |  | PCD_DPWW2_SOFW1_NP | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1 | PCD_DPWW2_SOFW1_T | PCD_DPWW2_SOFW1_T | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_O | PCD_DPWW2_SOFW1_OT | PCD_DPWW2_SOFW1_OT | PCD_DPWW2_SOFW1_P | PCD_DPWW2_SOFW1_P
| TMS |  | PCDWW6 | 0 | Storm Overflow - Screens | Number of EnvAct_IMP5 compliant screens installed and operational at screen only solutions | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.10 |  |  | PCD_DPWW2_SOFW2_NP | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2 | PCD_DPWW2_SOFW2_T | PCD_DPWW2_SOFW2_T | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_O | PCD_DPWW2_SOFW2_OT | PCD_DPWW2_SOFW2_OT | PCD_DPWW2_SOFW2_P | PCD_DPWW2_SOFW2_P
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Treatment for chemical removal (WINEP/NEP) | £m | 3 |  |  | 0.41431 | 0.69141 | 20.2728 | 68.6705 | 189.2081 | [5 empty] | 189.2081 | 0 | 0 | 2.3277 | 19.1472 | 47.7407 | 77.534 | 115.5298 | 148.2002 | 165.6182 | 174.2563 | 175.8185 | 176.4379 | 115.5298 | 176.4379 | 61.06% |  | DPWW2.11 |  |  | PCD_DPWW2_TCR1_NP | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1 | PCD_DPWW2_TCR1_T | PCD_DPWW2_TCR1_T | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_O | PCD_DPWW2_TCR1_OT | PCD_DPWW2_TCR1_OT | PCD_DPWW2_TCR1_P | PCD_DPWW2_TCR1_P
| TMS |  | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Treatment for total nitrogen removal (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.12 |  |  | PCD_DPWW2_TNR1_NP | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1 | PCD_DPWW2_TNR1_T | PCD_DPWW2_TNR1_T | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_O | PCD_DPWW2_TNR1_OT | PCD_DPWW2_TNR1_OT | PCD_DPWW2_TNR1_P | PCD_DPWW2_TNR1_P
| TMS |  | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Total number of site treatment solutions delivered to meet compliance | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.13 |  |  | PCD_DPWW2_NBS_SOL_NP | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL | PCD_DPWW2_NBS_SOL_T | PCD_DPWW2_NBS_SOL_T | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_O | PCD_DPWW2_NBS_SOL_OT | PCD_DPWW2_NBS_SOL_OT | PCD_DPWW2_NBS_SOL_P | PCD_DPWW2_NBS_SOL_P
| TMS |  | PCDWW13a | 0 | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP) | Catchment solutions - Catchment Nutrient Balancing (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.14 |  |  | PCD_DPWW2_CS1_NP | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1 | PCD_DPWW2_CS1_T | PCD_DPWW2_CS1_T | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_O | PCD_DPWW2_CS1_OT | PCD_DPWW2_CS1_OT | PCD_DPWW2_CS1_P | PCD_DPWW2_CS1_P
| TMS |  | PCDWW13a | 0 | Catchment solutions - Catchment Permitting (WINEP/NEP) | Catchment solutions - Catchment Permitting (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.15 |  |  | PCD_DPWW2_CS2_NP | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2 | PCD_DPWW2_CS2_T | PCD_DPWW2_CS2_T | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_O | PCD_DPWW2_CS2_OT | PCD_DPWW2_CS2_OT | PCD_DPWW2_CS2_P | PCD_DPWW2_CS2_P
| TMS |  | PCDWW14 |  | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.16 |  |  | PCD_DPWW2_MBT1_NP | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1 | PCD_DPWW2_MBT1_T | PCD_DPWW2_MBT1_T | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_O | PCD_DPWW2_MBT1_OT | PCD_DPWW2_MBT1_OT | PCD_DPWW2_MBT1_P | PCD_DPWW2_MBT1_P
| TMS |  | PCDWW15 | 0 | Septic tank replacements - treatment solution; (WINEP/NEP) | Total number of septic tank replacement or flow diversion schemes delivered | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.17 |  |  | PCD_DPWW2_STR_NP | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR | PCD_DPWW2_STR_T | PCD_DPWW2_STR_T | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_O | PCD_DPWW2_STR_OT | PCD_DPWW2_STR_OT | PCD_DPWW2_STR_P | PCD_DPWW2_STR_P
| TMS |  | PCDWW17 | 0 | 25 year environment plan; (WINEP/NEP) | Number of schemes delivered | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.18 |  |  | PCD_DPWW2_25EP_NP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP | PCD_DPWW2_25EP_T | PCD_DPWW2_25EP_T | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_O | PCD_DPWW2_25EP_OT | PCD_DPWW2_25EP_OT | PCD_DPWW2_25EP_P | PCD_DPWW2_25EP_P
| TMS | PR24CA112 Wastewater Other WINEP | PCDWW18 | Y | WINEP Investigations (wastewater) | Number of satisfactorily completed WINEP / NEP investigations - all categories | £m | 3 | 0.09365 |  | 17.1647 | 33.0977 | 39.359 | 40.227 | 40.3631 | [5 empty] | 40.3631 | 0 | 9.9522 | 29.326 | 45.5734 | 50.5148 | 51.5934 | 52.0024 | 52.0229 | 52.0253 | 52.0254 | 52.0254 | 52.0254 | 52.0024 | 52.0254 | 128.8% |  | DPWW2.19 |  |  | PCD_DPWW2_WINIVG_NP | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG | PCD_DPWW2_WINIVG_T | PCD_DPWW2_WINIVG_T | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_O | PCD_DPWW2_WINIVG_OT | PCD_DPWW2_WINIVG_OT | PCD_DPWW2_WINIVG_P | PCD_DPWW2_WINIVG_P
| TMS |  | PCDWW23a | 0 | Advanced WINEP | Advanced WINEP | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.20 |  |  | PCD_DPWW2_ADWIN1_NP | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1 | PCD_DPWW2_ADWIN1_T | PCD_DPWW2_ADWIN1_T | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_O | PCD_DPWW2_ADWIN1_OT | PCD_DPWW2_ADWIN1_OT | PCD_DPWW2_ADWIN1_P | PCD_DPWW2_ADWIN1_P
| TMS |  | PCDWW23b | 0 | Advanced WINEP | Equivalent storage avoided | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.21 |  |  | PCD_DPWW2_ADWIN2_NP | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2 | PCD_DPWW2_ADWIN2_T | PCD_DPWW2_ADWIN2_T | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_O | PCD_DPWW2_ADWIN2_OT | PCD_DPWW2_ADWIN2_OT | PCD_DPWW2_ADWIN2_P | PCD_DPWW2_ADWIN2_P
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24a | 0 | Sludge storage -Tanks | Volume of Sludge Storage delivered | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.22 |  |  | PCD_DPWW2_SSTT_NP | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT | PCD_DPWW2_SSTT_T | PCD_DPWW2_SSTT_T | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_O | PCD_DPWW2_SSTT_OT | PCD_DPWW2_SSTT_OT | PCD_DPWW2_SSTT_P | PCD_DPWW2_SSTT_P
| TMS |  | PCDWW24b | 0 | Sludge storage (cake pads) | Sludge Storage area delivered | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.23 |  |  | PCD_DPWW2_SSCP_NP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP | PCD_DPWW2_SSCP_T | PCD_DPWW2_SSCP_T | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_O | PCD_DPWW2_SSCP_OT | PCD_DPWW2_SSCP_OT | PCD_DPWW2_SSCP_P | PCD_DPWW2_SSCP_P
| TMS |  | PCDWW25a | 0 | Sludge thickening and dewatering | Tonnes of dry solids/ year | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.24 |  |  | PCD_DPWW2_STDW_NP | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW | PCD_DPWW2_STDW_T | PCD_DPWW2_STDW_T | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_O | PCD_DPWW2_STDW_OT | PCD_DPWW2_STDW_OT | PCD_DPWW2_STDW_P | PCD_DPWW2_STDW_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge throughput Dryer/Pelletiser installed plant capacity | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.25 |  |  | PCD_DPWW2_STOTH1_NP | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1 | PCD_DPWW2_STOTH1_T | PCD_DPWW2_STOTH1_T | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_O | PCD_DPWW2_STOTH1_OT | PCD_DPWW2_STOTH1_OT | PCD_DPWW2_STOTH1_P | PCD_DPWW2_STOTH1_P
| TMS |  | PCDWW25b | 0 | Sludge treatment (Other) | Sludge Throughput P Recovery installed plant capacity | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.26 |  |  | PCD_DPWW2_STOTH2_NP | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2 | PCD_DPWW2_STOTH2_T | PCD_DPWW2_STOTH2_T | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_O | PCD_DPWW2_STOTH2_OT | PCD_DPWW2_STOTH2_OT | PCD_DPWW2_STOTH2_P | PCD_DPWW2_STOTH2_P
| TMS |  | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of sites achieving IED compliance | £m | 3 |  |  | 18.5794 | 36.6273 | 80.8486 | 152.7866 | 290.4916 | [5 empty] | 290.4916 | 0 | 0 | 25.9656 | 53.1471 | 80.2297 | 111.4448 | 151.5941 | 201.6994 | 274.2638 | 348.9262 | 392.2057 | 418.003 | 151.5941 | 418.003 | 52.19% |  | DPWW2.27 |  |  | PCD_DPWW2_BIO_IED_NP | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED | PCD_DPWW2_BIO_IED_T | PCD_DPWW2_BIO_IED_T | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_O | PCD_DPWW2_BIO_IED_OT | PCD_DPWW2_BIO_IED_OT | PCD_DPWW2_BIO_IED_P | PCD_DPWW2_BIO_IED_P
| TMS | PR24CA116 Wastewater Other | PCDWW32 | Y | Climate change uplift | Spend on schemes for power and flood resilience delivered: | £m | 3 | 0.31203 |  | 1.2546 | 2.2253 | 7.1047 | 15.2641 | 31.2031 | [5 empty] | 31.2031 | 0 | 0 | 1.1328 | 3.7026 | 8.0883 | 19.0005 | 27.9044 | 28.593 | 28.6246 | 28.6246 | 28.6246 | 28.6246 | 27.9044 | 28.6246 | 89.43% |  | DPWW2.28 |  |  | PCD_DPWW2_CCUP_NP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP | PCD_DPWW2_CCUP_T | PCD_DPWW2_CCUP_T | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_O | PCD_DPWW2_CCUP_OT | PCD_DPWW2_CCUP_OT | PCD_DPWW2_CCUP_P | PCD_DPWW2_CCUP_P
| TMS |  | PCDWW32b | 0 | Coastal Erosion Risk | Coastal Erosion Risk | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.29 |  |  | PCD_DPWW2_CER1_NP | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1 | PCD_DPWW2_CER1_T | PCD_DPWW2_CER1_T | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_O | PCD_DPWW2_CER1_OT | PCD_DPWW2_CER1_OT | PCD_DPWW2_CER1_P | PCD_DPWW2_CER1_P
| TMS |  | PCDWW32d | 0 | Infiltration | Total length (in metre) of sewer effectively sealed / lined | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.30 |  |  | PCD_DPWW2_INF_NP | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF | PCD_DPWW2_INF_T | PCD_DPWW2_INF_T | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_O | PCD_DPWW2_INF_OT | PCD_DPWW2_INF_OT | PCD_DPWW2_INF_P | PCD_DPWW2_INF_P
| TMS |  | PCDWW32e | 0 | WW Partnership Funding | WW Partnership Funding | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.31 |  |  | PCD_DPWW2_WWPF1_NP | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1 | PCD_DPWW2_WWPF1_T | PCD_DPWW2_WWPF1_T | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_O | PCD_DPWW2_WWPF1_OT | PCD_DPWW2_WWPF1_OT | PCD_DPWW2_WWPF1_P | PCD_DPWW2_WWPF1_P
| TMS |  | PCDWW32f | 0 | Rainwater management | Rainwater management | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.32 |  |  | PCD_DPWW2_RRM_NP | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM | PCD_DPWW2_RRM_T | PCD_DPWW2_RRM_T | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_O | PCD_DPWW2_RRM_OT | PCD_DPWW2_RRM_OT | PCD_DPWW2_RRM_P | PCD_DPWW2_RRM_P
| TMS |  | PCDWW32g | 0 | Flood and power | Flooding resilience scheme unit rate | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.33 |  |  | PCD_DPWW2_FP_NP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP | PCD_DPWW2_FP_T | PCD_DPWW2_FP_T | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_O | PCD_DPWW2_FP_OT | PCD_DPWW2_FP_OT | PCD_DPWW2_FP_P | PCD_DPWW2_FP_P
| TMS |  | PCDWW32g | 0 | Flood and power | Power resilience scheme unit rate | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.34 |  |  | PCD_DPWW2_FP1_NP | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1 | PCD_DPWW2_FP1_T | PCD_DPWW2_FP1_T | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_O | PCD_DPWW2_FP1_OT | PCD_DPWW2_FP1_OT | PCD_DPWW2_FP1_P | PCD_DPWW2_FP1_P
| TMS |  | PCDWW29 | 0 | First time sewerage | Number of connected properties served by S101A schemes | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.35 |  |  | PCD_DPWW2_FTS_NP | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS | PCD_DPWW2_FTS_T | PCD_DPWW2_FTS_T | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_O | PCD_DPWW2_FTS_OT | PCD_DPWW2_FTS_OT | PCD_DPWW2_FTS_P | PCD_DPWW2_FTS_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW36 | 0 | PR19 Green recovery carryover | PR19 Green recovery carryover | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.36 |  |  | PCD_DPWW2_PR19GRC_NP | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC | PCD_DPWW2_PR19GRC_T | PCD_DPWW2_PR19GRC_T | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_O | PCD_DPWW2_PR19GRC_OT | PCD_DPWW2_PR19GRC_OT | PCD_DPWW2_PR19GRC_P | PCD_DPWW2_PR19GRC_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows | Equivalent storage | £m | 3 |  |  | 18.7044 | 36.7306 | 107.9232 | 253.5419 | 521.4971 | [5 empty] | 521.4971 | 0 | 0 | 8.8282 | 88.9176 | 189.2832 | 335.1878 | 437.3999 | 488.3382 | 509.813 | 518.1402 | 518.1316 | 518.1316 | 437.3999 | 518.1316 | 83.87% |  | DPWW2.37 |  |  | PCD_DPWW2_SOFES_NP | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES | PCD_DPWW2_SOFES_T | PCD_DPWW2_SOFES_T | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_O | PCD_DPWW2_SOFES_OT | PCD_DPWW2_SOFES_OT | PCD_DPWW2_SOFES_P | PCD_DPWW2_SOFES_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | litres per second | £m | 3 |  |  | 4.8532 | 9.5304 | 28.0025 | 65.7859 | 135.3115 | [5 empty] | 135.3115 | 0 | 0 | 1.8463 | 8.806 | 24.2692 | 63.2635 | 98.5648 | 119.8218 | 135.1611 | 141.6121 | 141.6121 | 141.6121 | 98.5648 | 141.6121 | 72.84% |  | DPWW2.38 |  |  | PCD_DPWW2_FTFT_NP | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT | PCD_DPWW2_FTFT_T | PCD_DPWW2_FTFT_T | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_O | PCD_DPWW2_FTFT_OT | PCD_DPWW2_FTFT_OT | PCD_DPWW2_FTFT_P | PCD_DPWW2_FTFT_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Population equivalent served | £m | 3 |  |  | 26.1686 | 64.2431 | 231.8319 | 594.7064 | 1183.2158 | [5 empty] | 1183.2158 | 0 | 0.0136 | 29.0602 | 81.6479 | 188.6815 | 397.8819 | 659.0278 | 1217.7707 | 1217.7707 | 1217.7707 | 1217.7707 | 1217.7707 | 659.0278 | 1217.7707 | 55.7% |  | DPWW2.39 |  |  | PCD_DPWW2_PRMVL_NP | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL | PCD_DPWW2_PRMVL_T | PCD_DPWW2_PRMVL_T | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_O | PCD_DPWW2_PRMVL_OT | PCD_DPWW2_PRMVL_OT | PCD_DPWW2_PRMVL_P | PCD_DPWW2_PRMVL_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Added Process Capacity in PE | £m | 3 |  |  | 0 | 0 | 0 | 51.664 | 172.9 | [5 empty] | 172.9 | 0 | -0.017207 | 4.6353 | 19.3326 | 51.3082 | 145.1444 | 249.2554 | 363.0022 | 434.9066 | 459.5631 | 464.4499 | 464.8435 | 249.2554 | 464.8435 | 144.2% |  | DPWW2.40 |  |  | PCD_DPWW2_GSTW_NP | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW | PCD_DPWW2_GSTW_T | PCD_DPWW2_GSTW_T | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_O | PCD_DPWW2_GSTW_OT | PCD_DPWW2_GSTW_OT | PCD_DPWW2_GSTW_P | PCD_DPWW2_GSTW_P
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Population equivalent served | £m | 3 |  |  | 31.5783 | 61.5704 | 62.1922 | 62.8826 | 68.9935 | [5 empty] | 68.9935 | 0 | 8.2775e-05 | 5.0853 | 16.1657 | 29.0462 | 48.5607 | 60.4104 | 73.0445 | 73.0445 | 73.0445 | 73.0445 | 73.0445 | 60.4104 | 73.0445 | 87.56% |  | DPWW2.41 |  |  | PCD_DPWW2_TTSP_NP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP | PCD_DPWW2_TTSP_T | PCD_DPWW2_TTSP_T | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_O | PCD_DPWW2_TTSP_OT | PCD_DPWW2_TTSP_OT | PCD_DPWW2_TTSP_P | PCD_DPWW2_TTSP_P
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes | £m | 3 |  |  | 201.3239 | 402.6477 | 603.9716 | 805.2955 | 1006.6194 | [5 empty] | 1006.6194 | 0 | 150.2821 | 264.8964 | 531.0252 | 900.3807 | 1178.4407 | 1367.6883 | 1523.7651 | 1523.7651 | 1523.7651 | 1523.7651 | 1523.7651 | 1367.6883 | 1523.7651 | 135.9% |  | DPWW2.42 |  |  | PCD_DPWW2_PR19WINCA_NP | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA | PCD_DPWW2_PR19WINCA_T | PCD_DPWW2_PR19WINCA_T | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_O | PCD_DPWW2_PR19WINCA_OT | PCD_DPWW2_PR19WINCA_OT | PCD_DPWW2_PR19WINCA_P | PCD_DPWW2_PR19WINCA_P
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | tCO2e/Number of sites | £m | 3 | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | DPWW2.43 |  |  | PCD_DPWW2_GGR1_NP | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1 | PCD_DPWW2_GGR1_T | PCD_DPWW2_GGR1_T | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_O | PCD_DPWW2_GGR1_OT | PCD_DPWW2_GGR1_OT | PCD_DPWW2_GGR1_P | PCD_DPWW2_GGR1_P
[21 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 0 |  |  |  | Total other non - PCD enhancement wastewater/bioresources expenditure, totex | Total other non - PCD enhancement wastewater/bioresources expenditure, totex | £m | 3 | [12 empty] | 0 | 0 | 186.9023 | 430.1042 | 743.2365 | 1186.3179 | 1636.502 | 2104.7579 | 2551.5868 | 2759.3645 | 2855.2663 | 2926.0995 | 2932.5801 | 2104.7579 | 2932.5801 |  |  | DPWW2.44 |  |  | PCD_DPWW2_OTH1_NP | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1 | PCD_DPWW2_OTH1_T | PCD_DPWW2_OTH1_T | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_O | PCD_DPWW2_OTH1_OT | PCD_DPWW2_OTH1_OT | PCD_DPWW2_OTH1_P | PCD_DPWW2_OTH1_P
| 0 |  |  |  | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex | Total PCD and non - PCD enhancement expenditure; wastewater/bioresources totex | £m | 3 |  |  | 326.0249 | 659.2458 | 1202.9312 | 2150.3344 | 3712.2023 | 0 | 0 | 0 | 0 | 0 | 3712.2023 | 0 | 347.133 | 804.154 | 1619.7322 | 2774.7613 | 4095.4271 | 5369.6428 | 6829.524 | 7249.0794 | 7479.0512 | 7600.6024 | 7633.9994 | 5369.6428 | 7633.9994 | 144.6% |  | DPWW2.45 |  |  | PCD_DPWW2_OTH2_NP | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2 | PCD_DPWW2_OTH2_T | PCD_DPWW2_OTH2_T | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_O | PCD_DPWW2_OTH2_OT | PCD_DPWW2_OTH2_OT | PCD_DPWW2_OTH2_P | PCD_DPWW2_OTH2_P
[39 empty] | End_Data | [30 empty] | End_BON

## DPW3
DPW3
[109 empty] | _DLY | _IR | _SCR | _CS | _SCS | _PP | _TPI | _CI | _SI | _ER | _RS | _PLE
Interim Milestones - Water - Programme Level
| Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | Total Number of Schemes with IMs (Nr) | [41 empty] | Total number of schemes with a 90+ day delay by IM (No.) | Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category | [10 empty] | DP Reference |  | Number of Schemes with IMs (Nr) |  | Number of schemes at Stage 0: IM1 has yet to be achieved | [41 empty] | _DLY: Total number of schemes with a 90+ day delay for any given IM; _IR: Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category
[10 empty] | Pre - AMP8 | AMP8 | [19 empty] | AMP9 | [20 empty] | Lack of internal resourcing | Lack of supply chain resourcing | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency |  |  |  |  | Pre - AMP8 | AMP8 | [19 empty] | AMP9 | [21 empty] | Lack of resources - internal | Lack of resources - external | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency
Start_Dta | [6 empty] | Nr | 0 | 0 | Pre 2025-26 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | 2030-31 Q1 | 2030-31 Q2 | 2030-31 Q3 | 2030-31 Q4 | 2031-32 Q1 | 2031-32 Q2 | 2031-32 Q3 | 2031-32 Q4 | 2032-33 Q1 | 2032-33 Q2 | 2032-33 Q3 | 2032-33 Q4 | 2033-34 Q1 | 2033-34 Q2 | 2033-34 Q3 | 2033-34 Q4 | 2034-35 Q1 | 2034-35 Q2 | 2034-35 Q3 | 2034-35 Q4 | [13 empty] | Start_BON | Constant |  | 2024-25 Q4 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | 2030-31 Q1 | 2030-31 Q2 | 2030-31 Q3 | 2030-31 Q4 | 2031-32 Q1 | 2031-32 Q2 | 2031-32 Q3 | 2031-32 Q4 | 2032-33 Q1 | 2032-33 Q2 | 2032-33 Q3 | 2032-33 Q4 | 2033-34 Q1 | 2033-34 Q2 | 2033-34 Q3 | 2033-34 Q4 | 2034-35 Q1 | 2034-35 Q2 | 2034-35 Q3 | 2034-35 Q4 |  | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant | Constant
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 0 | Nr | 0 | 7 | 6 | [52 empty] | DPW3.1 |  | PCD_DPW3_WFDI1_NR | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 | PCD_DPW3_WFDI1_S0 |  | PCD_DPW3_WFDI1_DLY | PCD_DPW3_WFDI1_DIR | PCD_DPW3_WFDI1_DSCR | PCD_DPW3_WFDI1_DCS | PCD_DPW3_WFDI1_DSPC | PCD_DPW3_WFDI1_DPP | PCD_DPW3_WFDI1_DTPI | PCD_DPW3_WFDI1_DCI | PCD_DPW3_WFDI1_DSI | PCD_DPW3_WFDI1_DER | PCD_DPW3_WFDI1_RS | PCD_DPW3_WFDI1_DPLE
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 5 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | PCD_DPW3_WFDI1_S1 | _S1 | PCD_DPW3_WFDI1_DLY_S1 | PCD_DPW3_WFDI1_DIR_S1 | PCD_DPW3_WFDI1_DSCR_S1 | PCD_DPW3_WFDI1_DCS_S1 | PCD_DPW3_WFDI1_DSPC_S1 | PCD_DPW3_WFDI1_DPP_S1 | PCD_DPW3_WFDI1_DTPI_S1 | PCD_DPW3_WFDI1_DCI_S1 | PCD_DPW3_WFDI1_DSI_S1 | PCD_DPW3_WFDI1_DER_S1 | PCD_DPW3_WFDI1_RS_S1 | PCD_DPW3_WFDI1_DPLE_S1
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 2 | Nr | 0 |  | 1 | 1 | 2 | 3 | 3 | 4 | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | PCD_DPW3_WFDI1_S2 | _S2 | PCD_DPW3_WFDI1_DLY_S2 | PCD_DPW3_WFDI1_DIR_S2 | PCD_DPW3_WFDI1_DSCR_S2 | PCD_DPW3_WFDI1_DCS_S2 | PCD_DPW3_WFDI1_DSPC_S2 | PCD_DPW3_WFDI1_DPP_S2 | PCD_DPW3_WFDI1_DTPI_S2 | PCD_DPW3_WFDI1_DCI_S2 | PCD_DPW3_WFDI1_DSI_S2 | PCD_DPW3_WFDI1_DER_S2 | PCD_DPW3_WFDI1_RS_S2 | PCD_DPW3_WFDI1_DPLE_S2
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 1 | 0 | 0 | 0 | 2 | 1 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | PCD_DPW3_WFDI1_S3 | _S3 | PCD_DPW3_WFDI1_DLY_S3 | PCD_DPW3_WFDI1_DIR_S3 | PCD_DPW3_WFDI1_DSCR_S3 | PCD_DPW3_WFDI1_DCS_S3 | PCD_DPW3_WFDI1_DSPC_S3 | PCD_DPW3_WFDI1_DPP_S3 | PCD_DPW3_WFDI1_DTPI_S3 | PCD_DPW3_WFDI1_DCI_S3 | PCD_DPW3_WFDI1_DSI_S3 | PCD_DPW3_WFDI1_DER_S3 | PCD_DPW3_WFDI1_RS_S3 | PCD_DPW3_WFDI1_DPLE_S3
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 1 | 1 | 2 | 1 | 1 | 1 | 1 | 2 | 4 | 4 | 5 | 5 | 5 | 4 | 4 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | PCD_DPW3_WFDI1_S4 | _S4 | PCD_DPW3_WFDI1_DLY_S4 | PCD_DPW3_WFDI1_DIR_S4 | PCD_DPW3_WFDI1_DSCR_S4 | PCD_DPW3_WFDI1_DCS_S4 | PCD_DPW3_WFDI1_DSPC_S4 | PCD_DPW3_WFDI1_DPP_S4 | PCD_DPW3_WFDI1_DTPI_S4 | PCD_DPW3_WFDI1_DCI_S4 | PCD_DPW3_WFDI1_DSI_S4 | PCD_DPW3_WFDI1_DER_S4 | PCD_DPW3_WFDI1_RS_S4 | PCD_DPW3_WFDI1_DPLE_S4
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | PCD_DPW3_WFDI1_S5 | _S5 | PCD_DPW3_WFDI1_DLY_S5 | PCD_DPW3_WFDI1_DIR_S5 | PCD_DPW3_WFDI1_DSCR_S5 | PCD_DPW3_WFDI1_DCS_S5 | PCD_DPW3_WFDI1_DSPC_S5 | PCD_DPW3_WFDI1_DPP_S5 | PCD_DPW3_WFDI1_DTPI_S5 | PCD_DPW3_WFDI1_DCI_S5 | PCD_DPW3_WFDI1_DSI_S5 | PCD_DPW3_WFDI1_DER_S5 | PCD_DPW3_WFDI1_RS_S5 | PCD_DPW3_WFDI1_DPLE_S5
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 | 3 | 6 | 6 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | PCD_DPW3_WFDI1_S6 | _S6 | PCD_DPW3_WFDI1_DLY_S6 | PCD_DPW3_WFDI1_DIR_S6 | PCD_DPW3_WFDI1_DSCR_S6 | PCD_DPW3_WFDI1_DCS_S6 | PCD_DPW3_WFDI1_DSPC_S6 | PCD_DPW3_WFDI1_DPP_S6 | PCD_DPW3_WFDI1_DTPI_S6 | PCD_DPW3_WFDI1_DCI_S6 | PCD_DPW3_WFDI1_DSI_S6 | PCD_DPW3_WFDI1_DER_S6 | PCD_DPW3_WFDI1_RS_S6 | PCD_DPW3_WFDI1_DPLE_S6
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | PCD_DPW3_WFDI1_S7 | _S7 | PCD_DPW3_WFDI1_DLY_S7 | PCD_DPW3_WFDI1_DIR_S7 | PCD_DPW3_WFDI1_DSCR_S7 | PCD_DPW3_WFDI1_DCS_S7 | PCD_DPW3_WFDI1_DSPC_S7 | PCD_DPW3_WFDI1_DPP_S7 | PCD_DPW3_WFDI1_DTPI_S7 | PCD_DPW3_WFDI1_DCI_S7 | PCD_DPW3_WFDI1_DSI_S7 | PCD_DPW3_WFDI1_DER_S7 | PCD_DPW3_WFDI1_RS_S7 | PCD_DPW3_WFDI1_DPLE_S7
| TMS | PR24CA106 Water WINEP | PCDW5 |  | Water Framework Directive interconnector - Length | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [12 empty] | DPW3.1 |  |  | PCD_DPW3_WFDI1 | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | PCD_DPW3_WFDI1ST | _ST | PCD_DPW3_WFDI1_DLY_ST | PCD_DPW3_WFDI1_DIR_ST | PCD_DPW3_WFDI1_DSCR_ST | PCD_DPW3_WFDI1_DCS_ST | PCD_DPW3_WFDI1_DSPC_ST | PCD_DPW3_WFDI1_DPP_ST | PCD_DPW3_WFDI1_DTPI_ST | PCD_DPW3_WFDI1_DCI_ST | PCD_DPW3_WFDI1_DSI_ST | PCD_DPW3_WFDI1_DER_ST | PCD_DPW3_WFDI1_RS_ST | PCD_DPW3_WFDI1_DPLE_ST
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 0 | Nr | 0 | 6 | 6 | 2 | 2 | [50 empty] | DPW3.2 |  | PCD_DPW3_RWD_NR | PCD_DPW3_RWD | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 | PCD_DPW3_RWD_S0 |  | PCD_DPW3_RWD_DLY | PCD_DPW3_RWD_DIR | PCD_DPW3_RWD_DSCR | PCD_DPW3_RWD_DCS | PCD_DPW3_RWD_DSPC | PCD_DPW3_RWD_DPP | PCD_DPW3_RWD_DTPI | PCD_DPW3_RWD_DCI | PCD_DPW3_RWD_DSI | PCD_DPW3_RWD_DER | PCD_DPW3_RWD_RS | PCD_DPW3_RWD_DPLE
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 4 | 4 | 6 | 6 | 6 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 | PCD_DPW3_RWD_S1 |  | PCD_DPW3_RWD_DLY_S1 | PCD_DPW3_RWD_DIR_S1 | PCD_DPW3_RWD_DSCR_S1 | PCD_DPW3_RWD_DCS_S1 | PCD_DPW3_RWD_DSPC_S1 | PCD_DPW3_RWD_DPP_S1 | PCD_DPW3_RWD_DTPI_S1 | PCD_DPW3_RWD_DCI_S1 | PCD_DPW3_RWD_DSI_S1 | PCD_DPW3_RWD_DER_S1 | PCD_DPW3_RWD_RS_S1 | PCD_DPW3_RWD_DPLE_S1
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 | PCD_DPW3_RWD_S2 |  | PCD_DPW3_RWD_DLY_S2 | PCD_DPW3_RWD_DIR_S2 | PCD_DPW3_RWD_DSCR_S2 | PCD_DPW3_RWD_DCS_S2 | PCD_DPW3_RWD_DSPC_S2 | PCD_DPW3_RWD_DPP_S2 | PCD_DPW3_RWD_DTPI_S2 | PCD_DPW3_RWD_DCI_S2 | PCD_DPW3_RWD_DSI_S2 | PCD_DPW3_RWD_DER_S2 | PCD_DPW3_RWD_RS_S2 | PCD_DPW3_RWD_DPLE_S2
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 | PCD_DPW3_RWD_S3 |  | PCD_DPW3_RWD_DLY_S3 | PCD_DPW3_RWD_DIR_S3 | PCD_DPW3_RWD_DSCR_S3 | PCD_DPW3_RWD_DCS_S3 | PCD_DPW3_RWD_DSPC_S3 | PCD_DPW3_RWD_DPP_S3 | PCD_DPW3_RWD_DTPI_S3 | PCD_DPW3_RWD_DCI_S3 | PCD_DPW3_RWD_DSI_S3 | PCD_DPW3_RWD_DER_S3 | PCD_DPW3_RWD_RS_S3 | PCD_DPW3_RWD_DPLE_S3
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 | PCD_DPW3_RWD_S4 |  | PCD_DPW3_RWD_DLY_S4 | PCD_DPW3_RWD_DIR_S4 | PCD_DPW3_RWD_DSCR_S4 | PCD_DPW3_RWD_DCS_S4 | PCD_DPW3_RWD_DSPC_S4 | PCD_DPW3_RWD_DPP_S4 | PCD_DPW3_RWD_DTPI_S4 | PCD_DPW3_RWD_DCI_S4 | PCD_DPW3_RWD_DSI_S4 | PCD_DPW3_RWD_DER_S4 | PCD_DPW3_RWD_RS_S4 | PCD_DPW3_RWD_DPLE_S4
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 | PCD_DPW3_RWD_S5 |  | PCD_DPW3_RWD_DLY_S5 | PCD_DPW3_RWD_DIR_S5 | PCD_DPW3_RWD_DSCR_S5 | PCD_DPW3_RWD_DCS_S5 | PCD_DPW3_RWD_DSPC_S5 | PCD_DPW3_RWD_DPP_S5 | PCD_DPW3_RWD_DTPI_S5 | PCD_DPW3_RWD_DCI_S5 | PCD_DPW3_RWD_DSI_S5 | PCD_DPW3_RWD_DER_S5 | PCD_DPW3_RWD_RS_S5 | PCD_DPW3_RWD_DPLE_S5
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 | PCD_DPW3_RWD_S6 |  | PCD_DPW3_RWD_DLY_S6 | PCD_DPW3_RWD_DIR_S6 | PCD_DPW3_RWD_DSCR_S6 | PCD_DPW3_RWD_DCS_S6 | PCD_DPW3_RWD_DSPC_S6 | PCD_DPW3_RWD_DPP_S6 | PCD_DPW3_RWD_DTPI_S6 | PCD_DPW3_RWD_DCI_S6 | PCD_DPW3_RWD_DSI_S6 | PCD_DPW3_RWD_DER_S6 | PCD_DPW3_RWD_RS_S6 | PCD_DPW3_RWD_DPLE_S6
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 | PCD_DPW3_RWD_S7 |  | PCD_DPW3_RWD_DLY_S7 | PCD_DPW3_RWD_DIR_S7 | PCD_DPW3_RWD_DSCR_S7 | PCD_DPW3_RWD_DCS_S7 | PCD_DPW3_RWD_DSPC_S7 | PCD_DPW3_RWD_DPP_S7 | PCD_DPW3_RWD_DTPI_S7 | PCD_DPW3_RWD_DCI_S7 | PCD_DPW3_RWD_DSI_S7 | PCD_DPW3_RWD_DER_S7 | PCD_DPW3_RWD_RS_S7 | PCD_DPW3_RWD_DPLE_S7
| TMS | PR24CA108 Water quality | PCDW14, PCDW13 |  | Raw Water Deterioration and Taste, Odour and Colour | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [12 empty] | DPW3.2 |  |  | PCD_DPW3_RWD | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST | PCD_DPW3_RWDST |  | PCD_DPW3_RWD_DLY_ST | PCD_DPW3_RWD_DIR_ST | PCD_DPW3_RWD_DSCR_ST | PCD_DPW3_RWD_DCS_ST | PCD_DPW3_RWD_DSPC_ST | PCD_DPW3_RWD_DPP_ST | PCD_DPW3_RWD_DTPI_ST | PCD_DPW3_RWD_DCI_ST | PCD_DPW3_RWD_DSI_ST | PCD_DPW3_RWD_DER_ST | PCD_DPW3_RWD_RS_ST | PCD_DPW3_RWD_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 0 | Nr | 0 | 3 | 3 | 2 | [51 empty] | DPW3.3 |  | PCD_DPW3_WRESUP_NR | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 | PCD_DPW3_WRESUP_S0 |  | PCD_DPW3_WRESUP_DLY | PCD_DPW3_WRESUP_DIR | PCD_DPW3_WRESUP_DSCR | PCD_DPW3_WRESUP_DCS | PCD_DPW3_WRESUP_DSPC | PCD_DPW3_WRESUP_DPP | PCD_DPW3_WRESUP_DTPI | PCD_DPW3_WRESUP_DCI | PCD_DPW3_WRESUP_DSI | PCD_DPW3_WRESUP_DER | PCD_DPW3_WRESUP_RS | PCD_DPW3_WRESUP_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 1 | 3 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 | PCD_DPW3_WRESUP_S1 |  | PCD_DPW3_WRESUP_DLY_S1 | PCD_DPW3_WRESUP_DIR_S1 | PCD_DPW3_WRESUP_DSCR_S1 | PCD_DPW3_WRESUP_DCS_S1 | PCD_DPW3_WRESUP_DSPC_S1 | PCD_DPW3_WRESUP_DPP_S1 | PCD_DPW3_WRESUP_DTPI_S1 | PCD_DPW3_WRESUP_DCI_S1 | PCD_DPW3_WRESUP_DSI_S1 | PCD_DPW3_WRESUP_DER_S1 | PCD_DPW3_WRESUP_RS_S1 | PCD_DPW3_WRESUP_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 1 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 | PCD_DPW3_WRESUP_S2 |  | PCD_DPW3_WRESUP_DLY_S2 | PCD_DPW3_WRESUP_DIR_S2 | PCD_DPW3_WRESUP_DSCR_S2 | PCD_DPW3_WRESUP_DCS_S2 | PCD_DPW3_WRESUP_DSPC_S2 | PCD_DPW3_WRESUP_DPP_S2 | PCD_DPW3_WRESUP_DTPI_S2 | PCD_DPW3_WRESUP_DCI_S2 | PCD_DPW3_WRESUP_DSI_S2 | PCD_DPW3_WRESUP_DER_S2 | PCD_DPW3_WRESUP_RS_S2 | PCD_DPW3_WRESUP_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 | PCD_DPW3_WRESUP_S3 |  | PCD_DPW3_WRESUP_DLY_S3 | PCD_DPW3_WRESUP_DIR_S3 | PCD_DPW3_WRESUP_DSCR_S3 | PCD_DPW3_WRESUP_DCS_S3 | PCD_DPW3_WRESUP_DSPC_S3 | PCD_DPW3_WRESUP_DPP_S3 | PCD_DPW3_WRESUP_DTPI_S3 | PCD_DPW3_WRESUP_DCI_S3 | PCD_DPW3_WRESUP_DSI_S3 | PCD_DPW3_WRESUP_DER_S3 | PCD_DPW3_WRESUP_RS_S3 | PCD_DPW3_WRESUP_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 | PCD_DPW3_WRESUP_S4 |  | PCD_DPW3_WRESUP_DLY_S4 | PCD_DPW3_WRESUP_DIR_S4 | PCD_DPW3_WRESUP_DSCR_S4 | PCD_DPW3_WRESUP_DCS_S4 | PCD_DPW3_WRESUP_DSPC_S4 | PCD_DPW3_WRESUP_DPP_S4 | PCD_DPW3_WRESUP_DTPI_S4 | PCD_DPW3_WRESUP_DCI_S4 | PCD_DPW3_WRESUP_DSI_S4 | PCD_DPW3_WRESUP_DER_S4 | PCD_DPW3_WRESUP_RS_S4 | PCD_DPW3_WRESUP_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 | PCD_DPW3_WRESUP_S5 |  | PCD_DPW3_WRESUP_DLY_S5 | PCD_DPW3_WRESUP_DIR_S5 | PCD_DPW3_WRESUP_DSCR_S5 | PCD_DPW3_WRESUP_DCS_S5 | PCD_DPW3_WRESUP_DSPC_S5 | PCD_DPW3_WRESUP_DPP_S5 | PCD_DPW3_WRESUP_DTPI_S5 | PCD_DPW3_WRESUP_DCI_S5 | PCD_DPW3_WRESUP_DSI_S5 | PCD_DPW3_WRESUP_DER_S5 | PCD_DPW3_WRESUP_RS_S5 | PCD_DPW3_WRESUP_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 | PCD_DPW3_WRESUP_S6 |  | PCD_DPW3_WRESUP_DLY_S6 | PCD_DPW3_WRESUP_DIR_S6 | PCD_DPW3_WRESUP_DSCR_S6 | PCD_DPW3_WRESUP_DCS_S6 | PCD_DPW3_WRESUP_DSPC_S6 | PCD_DPW3_WRESUP_DPP_S6 | PCD_DPW3_WRESUP_DTPI_S6 | PCD_DPW3_WRESUP_DCI_S6 | PCD_DPW3_WRESUP_DSI_S6 | PCD_DPW3_WRESUP_DER_S6 | PCD_DPW3_WRESUP_RS_S6 | PCD_DPW3_WRESUP_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 | PCD_DPW3_WRESUP_S7 |  | PCD_DPW3_WRESUP_DLY_S7 | PCD_DPW3_WRESUP_DIR_S7 | PCD_DPW3_WRESUP_DSCR_S7 | PCD_DPW3_WRESUP_DCS_S7 | PCD_DPW3_WRESUP_DSPC_S7 | PCD_DPW3_WRESUP_DPP_S7 | PCD_DPW3_WRESUP_DTPI_S7 | PCD_DPW3_WRESUP_DCI_S7 | PCD_DPW3_WRESUP_DSI_S7 | PCD_DPW3_WRESUP_DER_S7 | PCD_DPW3_WRESUP_RS_S7 | PCD_DPW3_WRESUP_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDWW32 |  | W Resilience CC Uplift | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [12 empty] | DPW3.3 |  |  | PCD_DPW3_WRESUP | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST | PCD_DPW3_WRESUPST |  | PCD_DPW3_WRESUP_DLY_ST | PCD_DPW3_WRESUP_DIR_ST | PCD_DPW3_WRESUP_DSCR_ST | PCD_DPW3_WRESUP_DCS_ST | PCD_DPW3_WRESUP_DSPC_ST | PCD_DPW3_WRESUP_DPP_ST | PCD_DPW3_WRESUP_DTPI_ST | PCD_DPW3_WRESUP_DCI_ST | PCD_DPW3_WRESUP_DSI_ST | PCD_DPW3_WRESUP_DER_ST | PCD_DPW3_WRESUP_RS_ST | PCD_DPW3_WRESUP_DPLE_ST
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 0 | Nr | 0 | 3 | 1 | [52 empty] | DPW3.4 |  | PCD_DPW3_SPL5_NR | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 | PCD_DPW3_SPL5_S0 |  | PCD_DPW3_SPL5_DLY | PCD_DPW3_SPL5_DIR | PCD_DPW3_SPL5_DSCR | PCD_DPW3_SPL5_DCS | PCD_DPW3_SPL5_DSPC | PCD_DPW3_SPL5_DPP | PCD_DPW3_SPL5_DTPI | PCD_DPW3_SPL5_DCI | PCD_DPW3_SPL5_DSI | PCD_DPW3_SPL5_DER | PCD_DPW3_SPL5_RS | PCD_DPW3_SPL5_DPLE
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 1 | Nr | 0 |  | 2 | 3 | 3 | 3 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 | PCD_DPW3_SPL5_S1 |  | PCD_DPW3_SPL5_DLY_S1 | PCD_DPW3_SPL5_DIR_S1 | PCD_DPW3_SPL5_DSCR_S1 | PCD_DPW3_SPL5_DCS_S1 | PCD_DPW3_SPL5_DSPC_S1 | PCD_DPW3_SPL5_DPP_S1 | PCD_DPW3_SPL5_DTPI_S1 | PCD_DPW3_SPL5_DCI_S1 | PCD_DPW3_SPL5_DSI_S1 | PCD_DPW3_SPL5_DER_S1 | PCD_DPW3_SPL5_RS_S1 | PCD_DPW3_SPL5_DPLE_S1
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 | PCD_DPW3_SPL5_S2 |  | PCD_DPW3_SPL5_DLY_S2 | PCD_DPW3_SPL5_DIR_S2 | PCD_DPW3_SPL5_DSCR_S2 | PCD_DPW3_SPL5_DCS_S2 | PCD_DPW3_SPL5_DSPC_S2 | PCD_DPW3_SPL5_DPP_S2 | PCD_DPW3_SPL5_DTPI_S2 | PCD_DPW3_SPL5_DCI_S2 | PCD_DPW3_SPL5_DSI_S2 | PCD_DPW3_SPL5_DER_S2 | PCD_DPW3_SPL5_RS_S2 | PCD_DPW3_SPL5_DPLE_S2
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 | PCD_DPW3_SPL5_S3 |  | PCD_DPW3_SPL5_DLY_S3 | PCD_DPW3_SPL5_DIR_S3 | PCD_DPW3_SPL5_DSCR_S3 | PCD_DPW3_SPL5_DCS_S3 | PCD_DPW3_SPL5_DSPC_S3 | PCD_DPW3_SPL5_DPP_S3 | PCD_DPW3_SPL5_DTPI_S3 | PCD_DPW3_SPL5_DCI_S3 | PCD_DPW3_SPL5_DSI_S3 | PCD_DPW3_SPL5_DER_S3 | PCD_DPW3_SPL5_RS_S3 | PCD_DPW3_SPL5_DPLE_S3
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 | PCD_DPW3_SPL5_S4 |  | PCD_DPW3_SPL5_DLY_S4 | PCD_DPW3_SPL5_DIR_S4 | PCD_DPW3_SPL5_DSCR_S4 | PCD_DPW3_SPL5_DCS_S4 | PCD_DPW3_SPL5_DSPC_S4 | PCD_DPW3_SPL5_DPP_S4 | PCD_DPW3_SPL5_DTPI_S4 | PCD_DPW3_SPL5_DCI_S4 | PCD_DPW3_SPL5_DSI_S4 | PCD_DPW3_SPL5_DER_S4 | PCD_DPW3_SPL5_RS_S4 | PCD_DPW3_SPL5_DPLE_S4
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 | PCD_DPW3_SPL5_S5 |  | PCD_DPW3_SPL5_DLY_S5 | PCD_DPW3_SPL5_DIR_S5 | PCD_DPW3_SPL5_DSCR_S5 | PCD_DPW3_SPL5_DCS_S5 | PCD_DPW3_SPL5_DSPC_S5 | PCD_DPW3_SPL5_DPP_S5 | PCD_DPW3_SPL5_DTPI_S5 | PCD_DPW3_SPL5_DCI_S5 | PCD_DPW3_SPL5_DSI_S5 | PCD_DPW3_SPL5_DER_S5 | PCD_DPW3_SPL5_RS_S5 | PCD_DPW3_SPL5_DPLE_S5
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 | PCD_DPW3_SPL5_S6 |  | PCD_DPW3_SPL5_DLY_S6 | PCD_DPW3_SPL5_DIR_S6 | PCD_DPW3_SPL5_DSCR_S6 | PCD_DPW3_SPL5_DCS_S6 | PCD_DPW3_SPL5_DSPC_S6 | PCD_DPW3_SPL5_DPP_S6 | PCD_DPW3_SPL5_DTPI_S6 | PCD_DPW3_SPL5_DCI_S6 | PCD_DPW3_SPL5_DSI_S6 | PCD_DPW3_SPL5_DER_S6 | PCD_DPW3_SPL5_RS_S6 | PCD_DPW3_SPL5_DPLE_S6
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 | PCD_DPW3_SPL5_S7 |  | PCD_DPW3_SPL5_DLY_S7 | PCD_DPW3_SPL5_DIR_S7 | PCD_DPW3_SPL5_DSCR_S7 | PCD_DPW3_SPL5_DCS_S7 | PCD_DPW3_SPL5_DSPC_S7 | PCD_DPW3_SPL5_DPP_S7 | PCD_DPW3_SPL5_DTPI_S7 | PCD_DPW3_SPL5_DCI_S7 | PCD_DPW3_SPL5_DSI_S7 | PCD_DPW3_SPL5_DER_S7 | PCD_DPW3_SPL5_RS_S7 | PCD_DPW3_SPL5_DPLE_S7
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11a |  | Supply - WAFU Benefit [Total] | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | [12 empty] | DPW3.4 |  |  | PCD_DPW3_SPL5 | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST | PCD_DPW3_SPL5ST |  | PCD_DPW3_SPL5_DLY_ST | PCD_DPW3_SPL5_DIR_ST | PCD_DPW3_SPL5_DSCR_ST | PCD_DPW3_SPL5_DCS_ST | PCD_DPW3_SPL5_DSPC_ST | PCD_DPW3_SPL5_DPP_ST | PCD_DPW3_SPL5_DTPI_ST | PCD_DPW3_SPL5_DCI_ST | PCD_DPW3_SPL5_DSI_ST | PCD_DPW3_SPL5_DER_ST | PCD_DPW3_SPL5_RS_ST | PCD_DPW3_SPL5_DPLE_ST
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.5 |  | PCD_DPW3_SPLIN1_NR | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 | PCD_DPW3_SPLIN1_S0 |  | PCD_DPW3_SPLIN1_DLY | PCD_DPW3_SPLIN1_DIR | PCD_DPW3_SPLIN1_DSCR | PCD_DPW3_SPLIN1_DCS | PCD_DPW3_SPLIN1_DSPC | PCD_DPW3_SPLIN1_DPP | PCD_DPW3_SPLIN1_DTPI | PCD_DPW3_SPLIN1_DCI | PCD_DPW3_SPLIN1_DSI | PCD_DPW3_SPLIN1_DER | PCD_DPW3_SPLIN1_RS | PCD_DPW3_SPLIN1_DPLE
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 | PCD_DPW3_SPLIN1_S1 |  | PCD_DPW3_SPLIN1_DLY_S1 | PCD_DPW3_SPLIN1_DIR_S1 | PCD_DPW3_SPLIN1_DSCR_S1 | PCD_DPW3_SPLIN1_DCS_S1 | PCD_DPW3_SPLIN1_DSPC_S1 | PCD_DPW3_SPLIN1_DPP_S1 | PCD_DPW3_SPLIN1_DTPI_S1 | PCD_DPW3_SPLIN1_DCI_S1 | PCD_DPW3_SPLIN1_DSI_S1 | PCD_DPW3_SPLIN1_DER_S1 | PCD_DPW3_SPLIN1_RS_S1 | PCD_DPW3_SPLIN1_DPLE_S1
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 | PCD_DPW3_SPLIN1_S2 |  | PCD_DPW3_SPLIN1_DLY_S2 | PCD_DPW3_SPLIN1_DIR_S2 | PCD_DPW3_SPLIN1_DSCR_S2 | PCD_DPW3_SPLIN1_DCS_S2 | PCD_DPW3_SPLIN1_DSPC_S2 | PCD_DPW3_SPLIN1_DPP_S2 | PCD_DPW3_SPLIN1_DTPI_S2 | PCD_DPW3_SPLIN1_DCI_S2 | PCD_DPW3_SPLIN1_DSI_S2 | PCD_DPW3_SPLIN1_DER_S2 | PCD_DPW3_SPLIN1_RS_S2 | PCD_DPW3_SPLIN1_DPLE_S2
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 | PCD_DPW3_SPLIN1_S3 |  | PCD_DPW3_SPLIN1_DLY_S3 | PCD_DPW3_SPLIN1_DIR_S3 | PCD_DPW3_SPLIN1_DSCR_S3 | PCD_DPW3_SPLIN1_DCS_S3 | PCD_DPW3_SPLIN1_DSPC_S3 | PCD_DPW3_SPLIN1_DPP_S3 | PCD_DPW3_SPLIN1_DTPI_S3 | PCD_DPW3_SPLIN1_DCI_S3 | PCD_DPW3_SPLIN1_DSI_S3 | PCD_DPW3_SPLIN1_DER_S3 | PCD_DPW3_SPLIN1_RS_S3 | PCD_DPW3_SPLIN1_DPLE_S3
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 | PCD_DPW3_SPLIN1_S4 |  | PCD_DPW3_SPLIN1_DLY_S4 | PCD_DPW3_SPLIN1_DIR_S4 | PCD_DPW3_SPLIN1_DSCR_S4 | PCD_DPW3_SPLIN1_DCS_S4 | PCD_DPW3_SPLIN1_DSPC_S4 | PCD_DPW3_SPLIN1_DPP_S4 | PCD_DPW3_SPLIN1_DTPI_S4 | PCD_DPW3_SPLIN1_DCI_S4 | PCD_DPW3_SPLIN1_DSI_S4 | PCD_DPW3_SPLIN1_DER_S4 | PCD_DPW3_SPLIN1_RS_S4 | PCD_DPW3_SPLIN1_DPLE_S4
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 | PCD_DPW3_SPLIN1_S5 |  | PCD_DPW3_SPLIN1_DLY_S5 | PCD_DPW3_SPLIN1_DIR_S5 | PCD_DPW3_SPLIN1_DSCR_S5 | PCD_DPW3_SPLIN1_DCS_S5 | PCD_DPW3_SPLIN1_DSPC_S5 | PCD_DPW3_SPLIN1_DPP_S5 | PCD_DPW3_SPLIN1_DTPI_S5 | PCD_DPW3_SPLIN1_DCI_S5 | PCD_DPW3_SPLIN1_DSI_S5 | PCD_DPW3_SPLIN1_DER_S5 | PCD_DPW3_SPLIN1_RS_S5 | PCD_DPW3_SPLIN1_DPLE_S5
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 | PCD_DPW3_SPLIN1_S6 |  | PCD_DPW3_SPLIN1_DLY_S6 | PCD_DPW3_SPLIN1_DIR_S6 | PCD_DPW3_SPLIN1_DSCR_S6 | PCD_DPW3_SPLIN1_DCS_S6 | PCD_DPW3_SPLIN1_DSPC_S6 | PCD_DPW3_SPLIN1_DPP_S6 | PCD_DPW3_SPLIN1_DTPI_S6 | PCD_DPW3_SPLIN1_DCI_S6 | PCD_DPW3_SPLIN1_DSI_S6 | PCD_DPW3_SPLIN1_DER_S6 | PCD_DPW3_SPLIN1_RS_S6 | PCD_DPW3_SPLIN1_DPLE_S6
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 | PCD_DPW3_SPLIN1_S7 |  | PCD_DPW3_SPLIN1_DLY_S7 | PCD_DPW3_SPLIN1_DIR_S7 | PCD_DPW3_SPLIN1_DSCR_S7 | PCD_DPW3_SPLIN1_DCS_S7 | PCD_DPW3_SPLIN1_DSPC_S7 | PCD_DPW3_SPLIN1_DPP_S7 | PCD_DPW3_SPLIN1_DTPI_S7 | PCD_DPW3_SPLIN1_DCI_S7 | PCD_DPW3_SPLIN1_DSI_S7 | PCD_DPW3_SPLIN1_DER_S7 | PCD_DPW3_SPLIN1_RS_S7 | PCD_DPW3_SPLIN1_DPLE_S7
| TMS | PR24CA107 Water Supply and Demand Balance | PCDW11b |  | Supply interconnectors - WAFU Benefit | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.5 |  |  | PCD_DPW3_SPLIN1 | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST | PCD_DPW3_SPLIN1ST |  | PCD_DPW3_SPLIN1_DLY_ST | PCD_DPW3_SPLIN1_DIR_ST | PCD_DPW3_SPLIN1_DSCR_ST | PCD_DPW3_SPLIN1_DCS_ST | PCD_DPW3_SPLIN1_DSPC_ST | PCD_DPW3_SPLIN1_DPP_ST | PCD_DPW3_SPLIN1_DTPI_ST | PCD_DPW3_SPLIN1_DCI_ST | PCD_DPW3_SPLIN1_DSI_ST | PCD_DPW3_SPLIN1_DER_ST | PCD_DPW3_SPLIN1_RS_ST | PCD_DPW3_SPLIN1_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.6 |  | PCD_DPW3_RESIN1_NR | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 | PCD_DPW3_RESIN1_S0 |  | PCD_DPW3_RESIN1_DLY | PCD_DPW3_RESIN1_DIR | PCD_DPW3_RESIN1_DSCR | PCD_DPW3_RESIN1_DCS | PCD_DPW3_RESIN1_DSPC | PCD_DPW3_RESIN1_DPP | PCD_DPW3_RESIN1_DTPI | PCD_DPW3_RESIN1_DCI | PCD_DPW3_RESIN1_DSI | PCD_DPW3_RESIN1_DER | PCD_DPW3_RESIN1_RS | PCD_DPW3_RESIN1_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 | PCD_DPW3_RESIN1_S1 |  | PCD_DPW3_RESIN1_DLY_S1 | PCD_DPW3_RESIN1_DIR_S1 | PCD_DPW3_RESIN1_DSCR_S1 | PCD_DPW3_RESIN1_DCS_S1 | PCD_DPW3_RESIN1_DSPC_S1 | PCD_DPW3_RESIN1_DPP_S1 | PCD_DPW3_RESIN1_DTPI_S1 | PCD_DPW3_RESIN1_DCI_S1 | PCD_DPW3_RESIN1_DSI_S1 | PCD_DPW3_RESIN1_DER_S1 | PCD_DPW3_RESIN1_RS_S1 | PCD_DPW3_RESIN1_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 | PCD_DPW3_RESIN1_S2 |  | PCD_DPW3_RESIN1_DLY_S2 | PCD_DPW3_RESIN1_DIR_S2 | PCD_DPW3_RESIN1_DSCR_S2 | PCD_DPW3_RESIN1_DCS_S2 | PCD_DPW3_RESIN1_DSPC_S2 | PCD_DPW3_RESIN1_DPP_S2 | PCD_DPW3_RESIN1_DTPI_S2 | PCD_DPW3_RESIN1_DCI_S2 | PCD_DPW3_RESIN1_DSI_S2 | PCD_DPW3_RESIN1_DER_S2 | PCD_DPW3_RESIN1_RS_S2 | PCD_DPW3_RESIN1_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 | PCD_DPW3_RESIN1_S3 |  | PCD_DPW3_RESIN1_DLY_S3 | PCD_DPW3_RESIN1_DIR_S3 | PCD_DPW3_RESIN1_DSCR_S3 | PCD_DPW3_RESIN1_DCS_S3 | PCD_DPW3_RESIN1_DSPC_S3 | PCD_DPW3_RESIN1_DPP_S3 | PCD_DPW3_RESIN1_DTPI_S3 | PCD_DPW3_RESIN1_DCI_S3 | PCD_DPW3_RESIN1_DSI_S3 | PCD_DPW3_RESIN1_DER_S3 | PCD_DPW3_RESIN1_RS_S3 | PCD_DPW3_RESIN1_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 | PCD_DPW3_RESIN1_S4 |  | PCD_DPW3_RESIN1_DLY_S4 | PCD_DPW3_RESIN1_DIR_S4 | PCD_DPW3_RESIN1_DSCR_S4 | PCD_DPW3_RESIN1_DCS_S4 | PCD_DPW3_RESIN1_DSPC_S4 | PCD_DPW3_RESIN1_DPP_S4 | PCD_DPW3_RESIN1_DTPI_S4 | PCD_DPW3_RESIN1_DCI_S4 | PCD_DPW3_RESIN1_DSI_S4 | PCD_DPW3_RESIN1_DER_S4 | PCD_DPW3_RESIN1_RS_S4 | PCD_DPW3_RESIN1_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 | PCD_DPW3_RESIN1_S5 |  | PCD_DPW3_RESIN1_DLY_S5 | PCD_DPW3_RESIN1_DIR_S5 | PCD_DPW3_RESIN1_DSCR_S5 | PCD_DPW3_RESIN1_DCS_S5 | PCD_DPW3_RESIN1_DSPC_S5 | PCD_DPW3_RESIN1_DPP_S5 | PCD_DPW3_RESIN1_DTPI_S5 | PCD_DPW3_RESIN1_DCI_S5 | PCD_DPW3_RESIN1_DSI_S5 | PCD_DPW3_RESIN1_DER_S5 | PCD_DPW3_RESIN1_RS_S5 | PCD_DPW3_RESIN1_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 | PCD_DPW3_RESIN1_S6 |  | PCD_DPW3_RESIN1_DLY_S6 | PCD_DPW3_RESIN1_DIR_S6 | PCD_DPW3_RESIN1_DSCR_S6 | PCD_DPW3_RESIN1_DCS_S6 | PCD_DPW3_RESIN1_DSPC_S6 | PCD_DPW3_RESIN1_DPP_S6 | PCD_DPW3_RESIN1_DTPI_S6 | PCD_DPW3_RESIN1_DCI_S6 | PCD_DPW3_RESIN1_DSI_S6 | PCD_DPW3_RESIN1_DER_S6 | PCD_DPW3_RESIN1_RS_S6 | PCD_DPW3_RESIN1_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 | PCD_DPW3_RESIN1_S7 |  | PCD_DPW3_RESIN1_DLY_S7 | PCD_DPW3_RESIN1_DIR_S7 | PCD_DPW3_RESIN1_DSCR_S7 | PCD_DPW3_RESIN1_DCS_S7 | PCD_DPW3_RESIN1_DSPC_S7 | PCD_DPW3_RESIN1_DPP_S7 | PCD_DPW3_RESIN1_DTPI_S7 | PCD_DPW3_RESIN1_DCI_S7 | PCD_DPW3_RESIN1_DSI_S7 | PCD_DPW3_RESIN1_DER_S7 | PCD_DPW3_RESIN1_RS_S7 | PCD_DPW3_RESIN1_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16b |  | Resilience Interconnector - Length | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.6 |  |  | PCD_DPW3_RESIN1 | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST | PCD_DPW3_RESIN1ST |  | PCD_DPW3_RESIN1_DLY_ST | PCD_DPW3_RESIN1_DIR_ST | PCD_DPW3_RESIN1_DSCR_ST | PCD_DPW3_RESIN1_DCS_ST | PCD_DPW3_RESIN1_DSPC_ST | PCD_DPW3_RESIN1_DPP_ST | PCD_DPW3_RESIN1_DTPI_ST | PCD_DPW3_RESIN1_DCI_ST | PCD_DPW3_RESIN1_DSI_ST | PCD_DPW3_RESIN1_DER_ST | PCD_DPW3_RESIN1_RS_ST | PCD_DPW3_RESIN1_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.7 |  | PCD_DPW3_RES1_NR | PCD_DPW3_RES1 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 | PCD_DPW3_RES1_S0 |  | PCD_DPW3_RES1_DLY | PCD_DPW3_RES1_DIR | PCD_DPW3_RES1_DSCR | PCD_DPW3_RES1_DCS | PCD_DPW3_RES1_DSPC | PCD_DPW3_RES1_DPP | PCD_DPW3_RES1_DTPI | PCD_DPW3_RES1_DCI | PCD_DPW3_RES1_DSI | PCD_DPW3_RES1_DER | PCD_DPW3_RES1_RS | PCD_DPW3_RES1_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 | PCD_DPW3_RES1_S1 |  | PCD_DPW3_RES1_DLY_S1 | PCD_DPW3_RES1_DIR_S1 | PCD_DPW3_RES1_DSCR_S1 | PCD_DPW3_RES1_DCS_S1 | PCD_DPW3_RES1_DSPC_S1 | PCD_DPW3_RES1_DPP_S1 | PCD_DPW3_RES1_DTPI_S1 | PCD_DPW3_RES1_DCI_S1 | PCD_DPW3_RES1_DSI_S1 | PCD_DPW3_RES1_DER_S1 | PCD_DPW3_RES1_RS_S1 | PCD_DPW3_RES1_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 | PCD_DPW3_RES1_S2 |  | PCD_DPW3_RES1_DLY_S2 | PCD_DPW3_RES1_DIR_S2 | PCD_DPW3_RES1_DSCR_S2 | PCD_DPW3_RES1_DCS_S2 | PCD_DPW3_RES1_DSPC_S2 | PCD_DPW3_RES1_DPP_S2 | PCD_DPW3_RES1_DTPI_S2 | PCD_DPW3_RES1_DCI_S2 | PCD_DPW3_RES1_DSI_S2 | PCD_DPW3_RES1_DER_S2 | PCD_DPW3_RES1_RS_S2 | PCD_DPW3_RES1_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 | PCD_DPW3_RES1_S3 |  | PCD_DPW3_RES1_DLY_S3 | PCD_DPW3_RES1_DIR_S3 | PCD_DPW3_RES1_DSCR_S3 | PCD_DPW3_RES1_DCS_S3 | PCD_DPW3_RES1_DSPC_S3 | PCD_DPW3_RES1_DPP_S3 | PCD_DPW3_RES1_DTPI_S3 | PCD_DPW3_RES1_DCI_S3 | PCD_DPW3_RES1_DSI_S3 | PCD_DPW3_RES1_DER_S3 | PCD_DPW3_RES1_RS_S3 | PCD_DPW3_RES1_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 | PCD_DPW3_RES1_S4 |  | PCD_DPW3_RES1_DLY_S4 | PCD_DPW3_RES1_DIR_S4 | PCD_DPW3_RES1_DSCR_S4 | PCD_DPW3_RES1_DCS_S4 | PCD_DPW3_RES1_DSPC_S4 | PCD_DPW3_RES1_DPP_S4 | PCD_DPW3_RES1_DTPI_S4 | PCD_DPW3_RES1_DCI_S4 | PCD_DPW3_RES1_DSI_S4 | PCD_DPW3_RES1_DER_S4 | PCD_DPW3_RES1_RS_S4 | PCD_DPW3_RES1_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 | PCD_DPW3_RES1_S5 |  | PCD_DPW3_RES1_DLY_S5 | PCD_DPW3_RES1_DIR_S5 | PCD_DPW3_RES1_DSCR_S5 | PCD_DPW3_RES1_DCS_S5 | PCD_DPW3_RES1_DSPC_S5 | PCD_DPW3_RES1_DPP_S5 | PCD_DPW3_RES1_DTPI_S5 | PCD_DPW3_RES1_DCI_S5 | PCD_DPW3_RES1_DSI_S5 | PCD_DPW3_RES1_DER_S5 | PCD_DPW3_RES1_RS_S5 | PCD_DPW3_RES1_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 | PCD_DPW3_RES1_S6 |  | PCD_DPW3_RES1_DLY_S6 | PCD_DPW3_RES1_DIR_S6 | PCD_DPW3_RES1_DSCR_S6 | PCD_DPW3_RES1_DCS_S6 | PCD_DPW3_RES1_DSPC_S6 | PCD_DPW3_RES1_DPP_S6 | PCD_DPW3_RES1_DTPI_S6 | PCD_DPW3_RES1_DCI_S6 | PCD_DPW3_RES1_DSI_S6 | PCD_DPW3_RES1_DER_S6 | PCD_DPW3_RES1_RS_S6 | PCD_DPW3_RES1_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 | PCD_DPW3_RES1_S7 |  | PCD_DPW3_RES1_DLY_S7 | PCD_DPW3_RES1_DIR_S7 | PCD_DPW3_RES1_DSCR_S7 | PCD_DPW3_RES1_DCS_S7 | PCD_DPW3_RES1_DSPC_S7 | PCD_DPW3_RES1_DPP_S7 | PCD_DPW3_RES1_DTPI_S7 | PCD_DPW3_RES1_DCI_S7 | PCD_DPW3_RES1_DSI_S7 | PCD_DPW3_RES1_DER_S7 | PCD_DPW3_RES1_RS_S7 | PCD_DPW3_RES1_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Number of water treatment works with new equipment | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.7 |  |  | PCD_DPW3_RES1 | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST | PCD_DPW3_RES1ST |  | PCD_DPW3_RES1_DLY_ST | PCD_DPW3_RES1_DIR_ST | PCD_DPW3_RES1_DSCR_ST | PCD_DPW3_RES1_DCS_ST | PCD_DPW3_RES1_DSPC_ST | PCD_DPW3_RES1_DPP_ST | PCD_DPW3_RES1_DTPI_ST | PCD_DPW3_RES1_DCI_ST | PCD_DPW3_RES1_DSI_ST | PCD_DPW3_RES1_DER_ST | PCD_DPW3_RES1_RS_ST | PCD_DPW3_RES1_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.8 |  | PCD_DPW3_RES2_NR | PCD_DPW3_RES2 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 | PCD_DPW3_RES2_S0 |  | PCD_DPW3_RES2_DLY | PCD_DPW3_RES2_DIR | PCD_DPW3_RES2_DSCR | PCD_DPW3_RES2_DCS | PCD_DPW3_RES2_DSPC | PCD_DPW3_RES2_DPP | PCD_DPW3_RES2_DTPI | PCD_DPW3_RES2_DCI | PCD_DPW3_RES2_DSI | PCD_DPW3_RES2_DER | PCD_DPW3_RES2_RS | PCD_DPW3_RES2_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 | PCD_DPW3_RES2_S1 |  | PCD_DPW3_RES2_DLY_S1 | PCD_DPW3_RES2_DIR_S1 | PCD_DPW3_RES2_DSCR_S1 | PCD_DPW3_RES2_DCS_S1 | PCD_DPW3_RES2_DSPC_S1 | PCD_DPW3_RES2_DPP_S1 | PCD_DPW3_RES2_DTPI_S1 | PCD_DPW3_RES2_DCI_S1 | PCD_DPW3_RES2_DSI_S1 | PCD_DPW3_RES2_DER_S1 | PCD_DPW3_RES2_RS_S1 | PCD_DPW3_RES2_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 | PCD_DPW3_RES2_S2 |  | PCD_DPW3_RES2_DLY_S2 | PCD_DPW3_RES2_DIR_S2 | PCD_DPW3_RES2_DSCR_S2 | PCD_DPW3_RES2_DCS_S2 | PCD_DPW3_RES2_DSPC_S2 | PCD_DPW3_RES2_DPP_S2 | PCD_DPW3_RES2_DTPI_S2 | PCD_DPW3_RES2_DCI_S2 | PCD_DPW3_RES2_DSI_S2 | PCD_DPW3_RES2_DER_S2 | PCD_DPW3_RES2_RS_S2 | PCD_DPW3_RES2_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 | PCD_DPW3_RES2_S3 |  | PCD_DPW3_RES2_DLY_S3 | PCD_DPW3_RES2_DIR_S3 | PCD_DPW3_RES2_DSCR_S3 | PCD_DPW3_RES2_DCS_S3 | PCD_DPW3_RES2_DSPC_S3 | PCD_DPW3_RES2_DPP_S3 | PCD_DPW3_RES2_DTPI_S3 | PCD_DPW3_RES2_DCI_S3 | PCD_DPW3_RES2_DSI_S3 | PCD_DPW3_RES2_DER_S3 | PCD_DPW3_RES2_RS_S3 | PCD_DPW3_RES2_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 | PCD_DPW3_RES2_S4 |  | PCD_DPW3_RES2_DLY_S4 | PCD_DPW3_RES2_DIR_S4 | PCD_DPW3_RES2_DSCR_S4 | PCD_DPW3_RES2_DCS_S4 | PCD_DPW3_RES2_DSPC_S4 | PCD_DPW3_RES2_DPP_S4 | PCD_DPW3_RES2_DTPI_S4 | PCD_DPW3_RES2_DCI_S4 | PCD_DPW3_RES2_DSI_S4 | PCD_DPW3_RES2_DER_S4 | PCD_DPW3_RES2_RS_S4 | PCD_DPW3_RES2_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 | PCD_DPW3_RES2_S5 |  | PCD_DPW3_RES2_DLY_S5 | PCD_DPW3_RES2_DIR_S5 | PCD_DPW3_RES2_DSCR_S5 | PCD_DPW3_RES2_DCS_S5 | PCD_DPW3_RES2_DSPC_S5 | PCD_DPW3_RES2_DPP_S5 | PCD_DPW3_RES2_DTPI_S5 | PCD_DPW3_RES2_DCI_S5 | PCD_DPW3_RES2_DSI_S5 | PCD_DPW3_RES2_DER_S5 | PCD_DPW3_RES2_RS_S5 | PCD_DPW3_RES2_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 | PCD_DPW3_RES2_S6 |  | PCD_DPW3_RES2_DLY_S6 | PCD_DPW3_RES2_DIR_S6 | PCD_DPW3_RES2_DSCR_S6 | PCD_DPW3_RES2_DCS_S6 | PCD_DPW3_RES2_DSPC_S6 | PCD_DPW3_RES2_DPP_S6 | PCD_DPW3_RES2_DTPI_S6 | PCD_DPW3_RES2_DCI_S6 | PCD_DPW3_RES2_DSI_S6 | PCD_DPW3_RES2_DER_S6 | PCD_DPW3_RES2_RS_S6 | PCD_DPW3_RES2_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 | PCD_DPW3_RES2_S7 |  | PCD_DPW3_RES2_DLY_S7 | PCD_DPW3_RES2_DIR_S7 | PCD_DPW3_RES2_DSCR_S7 | PCD_DPW3_RES2_DCS_S7 | PCD_DPW3_RES2_DSPC_S7 | PCD_DPW3_RES2_DPP_S7 | PCD_DPW3_RES2_DTPI_S7 | PCD_DPW3_RES2_DCI_S7 | PCD_DPW3_RES2_DSI_S7 | PCD_DPW3_RES2_DER_S7 | PCD_DPW3_RES2_RS_S7 | PCD_DPW3_RES2_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Upgrade works at water treatment works | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.8 |  |  | PCD_DPW3_RES2 | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST | PCD_DPW3_RES2ST |  | PCD_DPW3_RES2_DLY_ST | PCD_DPW3_RES2_DIR_ST | PCD_DPW3_RES2_DSCR_ST | PCD_DPW3_RES2_DCS_ST | PCD_DPW3_RES2_DSPC_ST | PCD_DPW3_RES2_DPP_ST | PCD_DPW3_RES2_DTPI_ST | PCD_DPW3_RES2_DCI_ST | PCD_DPW3_RES2_DSI_ST | PCD_DPW3_RES2_DER_ST | PCD_DPW3_RES2_RS_ST | PCD_DPW3_RES2_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.9 |  | PCD_DPW3_RES3_NR | PCD_DPW3_RES3 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 | PCD_DPW3_RES3_S0 |  | PCD_DPW3_RES3_DLY | PCD_DPW3_RES3_DIR | PCD_DPW3_RES3_DSCR | PCD_DPW3_RES3_DCS | PCD_DPW3_RES3_DSPC | PCD_DPW3_RES3_DPP | PCD_DPW3_RES3_DTPI | PCD_DPW3_RES3_DCI | PCD_DPW3_RES3_DSI | PCD_DPW3_RES3_DER | PCD_DPW3_RES3_RS | PCD_DPW3_RES3_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 | PCD_DPW3_RES3_S1 |  | PCD_DPW3_RES3_DLY_S1 | PCD_DPW3_RES3_DIR_S1 | PCD_DPW3_RES3_DSCR_S1 | PCD_DPW3_RES3_DCS_S1 | PCD_DPW3_RES3_DSPC_S1 | PCD_DPW3_RES3_DPP_S1 | PCD_DPW3_RES3_DTPI_S1 | PCD_DPW3_RES3_DCI_S1 | PCD_DPW3_RES3_DSI_S1 | PCD_DPW3_RES3_DER_S1 | PCD_DPW3_RES3_RS_S1 | PCD_DPW3_RES3_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 | PCD_DPW3_RES3_S2 |  | PCD_DPW3_RES3_DLY_S2 | PCD_DPW3_RES3_DIR_S2 | PCD_DPW3_RES3_DSCR_S2 | PCD_DPW3_RES3_DCS_S2 | PCD_DPW3_RES3_DSPC_S2 | PCD_DPW3_RES3_DPP_S2 | PCD_DPW3_RES3_DTPI_S2 | PCD_DPW3_RES3_DCI_S2 | PCD_DPW3_RES3_DSI_S2 | PCD_DPW3_RES3_DER_S2 | PCD_DPW3_RES3_RS_S2 | PCD_DPW3_RES3_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 | PCD_DPW3_RES3_S3 |  | PCD_DPW3_RES3_DLY_S3 | PCD_DPW3_RES3_DIR_S3 | PCD_DPW3_RES3_DSCR_S3 | PCD_DPW3_RES3_DCS_S3 | PCD_DPW3_RES3_DSPC_S3 | PCD_DPW3_RES3_DPP_S3 | PCD_DPW3_RES3_DTPI_S3 | PCD_DPW3_RES3_DCI_S3 | PCD_DPW3_RES3_DSI_S3 | PCD_DPW3_RES3_DER_S3 | PCD_DPW3_RES3_RS_S3 | PCD_DPW3_RES3_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 | PCD_DPW3_RES3_S4 |  | PCD_DPW3_RES3_DLY_S4 | PCD_DPW3_RES3_DIR_S4 | PCD_DPW3_RES3_DSCR_S4 | PCD_DPW3_RES3_DCS_S4 | PCD_DPW3_RES3_DSPC_S4 | PCD_DPW3_RES3_DPP_S4 | PCD_DPW3_RES3_DTPI_S4 | PCD_DPW3_RES3_DCI_S4 | PCD_DPW3_RES3_DSI_S4 | PCD_DPW3_RES3_DER_S4 | PCD_DPW3_RES3_RS_S4 | PCD_DPW3_RES3_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 | PCD_DPW3_RES3_S5 |  | PCD_DPW3_RES3_DLY_S5 | PCD_DPW3_RES3_DIR_S5 | PCD_DPW3_RES3_DSCR_S5 | PCD_DPW3_RES3_DCS_S5 | PCD_DPW3_RES3_DSPC_S5 | PCD_DPW3_RES3_DPP_S5 | PCD_DPW3_RES3_DTPI_S5 | PCD_DPW3_RES3_DCI_S5 | PCD_DPW3_RES3_DSI_S5 | PCD_DPW3_RES3_DER_S5 | PCD_DPW3_RES3_RS_S5 | PCD_DPW3_RES3_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 | PCD_DPW3_RES3_S6 |  | PCD_DPW3_RES3_DLY_S6 | PCD_DPW3_RES3_DIR_S6 | PCD_DPW3_RES3_DSCR_S6 | PCD_DPW3_RES3_DCS_S6 | PCD_DPW3_RES3_DSPC_S6 | PCD_DPW3_RES3_DPP_S6 | PCD_DPW3_RES3_DTPI_S6 | PCD_DPW3_RES3_DCI_S6 | PCD_DPW3_RES3_DSI_S6 | PCD_DPW3_RES3_DER_S6 | PCD_DPW3_RES3_RS_S6 | PCD_DPW3_RES3_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 | PCD_DPW3_RES3_S7 |  | PCD_DPW3_RES3_DLY_S7 | PCD_DPW3_RES3_DIR_S7 | PCD_DPW3_RES3_DSCR_S7 | PCD_DPW3_RES3_DCS_S7 | PCD_DPW3_RES3_DSPC_S7 | PCD_DPW3_RES3_DPP_S7 | PCD_DPW3_RES3_DTPI_S7 | PCD_DPW3_RES3_DCI_S7 | PCD_DPW3_RES3_DSI_S7 | PCD_DPW3_RES3_DER_S7 | PCD_DPW3_RES3_RS_S7 | PCD_DPW3_RES3_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Service reservoirs with new enhanced bypass provision | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.9 |  |  | PCD_DPW3_RES3 | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST | PCD_DPW3_RES3ST |  | PCD_DPW3_RES3_DLY_ST | PCD_DPW3_RES3_DIR_ST | PCD_DPW3_RES3_DSCR_ST | PCD_DPW3_RES3_DCS_ST | PCD_DPW3_RES3_DSPC_ST | PCD_DPW3_RES3_DPP_ST | PCD_DPW3_RES3_DTPI_ST | PCD_DPW3_RES3_DCI_ST | PCD_DPW3_RES3_DSI_ST | PCD_DPW3_RES3_DER_ST | PCD_DPW3_RES3_RS_ST | PCD_DPW3_RES3_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.10 |  | PCD_DPW3_RES4_NR | PCD_DPW3_RES4 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 | PCD_DPW3_RES4_S0 |  | PCD_DPW3_RES4_DLY | PCD_DPW3_RES4_DIR | PCD_DPW3_RES4_DSCR | PCD_DPW3_RES4_DCS | PCD_DPW3_RES4_DSPC | PCD_DPW3_RES4_DPP | PCD_DPW3_RES4_DTPI | PCD_DPW3_RES4_DCI | PCD_DPW3_RES4_DSI | PCD_DPW3_RES4_DER | PCD_DPW3_RES4_RS | PCD_DPW3_RES4_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 | PCD_DPW3_RES4_S1 |  | PCD_DPW3_RES4_DLY_S1 | PCD_DPW3_RES4_DIR_S1 | PCD_DPW3_RES4_DSCR_S1 | PCD_DPW3_RES4_DCS_S1 | PCD_DPW3_RES4_DSPC_S1 | PCD_DPW3_RES4_DPP_S1 | PCD_DPW3_RES4_DTPI_S1 | PCD_DPW3_RES4_DCI_S1 | PCD_DPW3_RES4_DSI_S1 | PCD_DPW3_RES4_DER_S1 | PCD_DPW3_RES4_RS_S1 | PCD_DPW3_RES4_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 | PCD_DPW3_RES4_S2 |  | PCD_DPW3_RES4_DLY_S2 | PCD_DPW3_RES4_DIR_S2 | PCD_DPW3_RES4_DSCR_S2 | PCD_DPW3_RES4_DCS_S2 | PCD_DPW3_RES4_DSPC_S2 | PCD_DPW3_RES4_DPP_S2 | PCD_DPW3_RES4_DTPI_S2 | PCD_DPW3_RES4_DCI_S2 | PCD_DPW3_RES4_DSI_S2 | PCD_DPW3_RES4_DER_S2 | PCD_DPW3_RES4_RS_S2 | PCD_DPW3_RES4_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 | PCD_DPW3_RES4_S3 |  | PCD_DPW3_RES4_DLY_S3 | PCD_DPW3_RES4_DIR_S3 | PCD_DPW3_RES4_DSCR_S3 | PCD_DPW3_RES4_DCS_S3 | PCD_DPW3_RES4_DSPC_S3 | PCD_DPW3_RES4_DPP_S3 | PCD_DPW3_RES4_DTPI_S3 | PCD_DPW3_RES4_DCI_S3 | PCD_DPW3_RES4_DSI_S3 | PCD_DPW3_RES4_DER_S3 | PCD_DPW3_RES4_RS_S3 | PCD_DPW3_RES4_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 | PCD_DPW3_RES4_S4 |  | PCD_DPW3_RES4_DLY_S4 | PCD_DPW3_RES4_DIR_S4 | PCD_DPW3_RES4_DSCR_S4 | PCD_DPW3_RES4_DCS_S4 | PCD_DPW3_RES4_DSPC_S4 | PCD_DPW3_RES4_DPP_S4 | PCD_DPW3_RES4_DTPI_S4 | PCD_DPW3_RES4_DCI_S4 | PCD_DPW3_RES4_DSI_S4 | PCD_DPW3_RES4_DER_S4 | PCD_DPW3_RES4_RS_S4 | PCD_DPW3_RES4_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 | PCD_DPW3_RES4_S5 |  | PCD_DPW3_RES4_DLY_S5 | PCD_DPW3_RES4_DIR_S5 | PCD_DPW3_RES4_DSCR_S5 | PCD_DPW3_RES4_DCS_S5 | PCD_DPW3_RES4_DSPC_S5 | PCD_DPW3_RES4_DPP_S5 | PCD_DPW3_RES4_DTPI_S5 | PCD_DPW3_RES4_DCI_S5 | PCD_DPW3_RES4_DSI_S5 | PCD_DPW3_RES4_DER_S5 | PCD_DPW3_RES4_RS_S5 | PCD_DPW3_RES4_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 | PCD_DPW3_RES4_S6 |  | PCD_DPW3_RES4_DLY_S6 | PCD_DPW3_RES4_DIR_S6 | PCD_DPW3_RES4_DSCR_S6 | PCD_DPW3_RES4_DCS_S6 | PCD_DPW3_RES4_DSPC_S6 | PCD_DPW3_RES4_DPP_S6 | PCD_DPW3_RES4_DTPI_S6 | PCD_DPW3_RES4_DCI_S6 | PCD_DPW3_RES4_DSI_S6 | PCD_DPW3_RES4_DER_S6 | PCD_DPW3_RES4_RS_S6 | PCD_DPW3_RES4_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 | PCD_DPW3_RES4_S7 |  | PCD_DPW3_RES4_DLY_S7 | PCD_DPW3_RES4_DIR_S7 | PCD_DPW3_RES4_DSCR_S7 | PCD_DPW3_RES4_DCS_S7 | PCD_DPW3_RES4_DSPC_S7 | PCD_DPW3_RES4_DPP_S7 | PCD_DPW3_RES4_DTPI_S7 | PCD_DPW3_RES4_DCI_S7 | PCD_DPW3_RES4_DSI_S7 | PCD_DPW3_RES4_DER_S7 | PCD_DPW3_RES4_RS_S7 | PCD_DPW3_RES4_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Installation of new equipment | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.10 |  |  | PCD_DPW3_RES4 | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST | PCD_DPW3_RES4ST |  | PCD_DPW3_RES4_DLY_ST | PCD_DPW3_RES4_DIR_ST | PCD_DPW3_RES4_DSCR_ST | PCD_DPW3_RES4_DCS_ST | PCD_DPW3_RES4_DSPC_ST | PCD_DPW3_RES4_DPP_ST | PCD_DPW3_RES4_DTPI_ST | PCD_DPW3_RES4_DCI_ST | PCD_DPW3_RES4_DSI_ST | PCD_DPW3_RES4_DER_ST | PCD_DPW3_RES4_RS_ST | PCD_DPW3_RES4_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.11 |  | PCD_DPW3_RES5_NR | PCD_DPW3_RES5 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 | PCD_DPW3_RES5_S0 |  | PCD_DPW3_RES5_DLY | PCD_DPW3_RES5_DIR | PCD_DPW3_RES5_DSCR | PCD_DPW3_RES5_DCS | PCD_DPW3_RES5_DSPC | PCD_DPW3_RES5_DPP | PCD_DPW3_RES5_DTPI | PCD_DPW3_RES5_DCI | PCD_DPW3_RES5_DSI | PCD_DPW3_RES5_DER | PCD_DPW3_RES5_RS | PCD_DPW3_RES5_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 | PCD_DPW3_RES5_S1 |  | PCD_DPW3_RES5_DLY_S1 | PCD_DPW3_RES5_DIR_S1 | PCD_DPW3_RES5_DSCR_S1 | PCD_DPW3_RES5_DCS_S1 | PCD_DPW3_RES5_DSPC_S1 | PCD_DPW3_RES5_DPP_S1 | PCD_DPW3_RES5_DTPI_S1 | PCD_DPW3_RES5_DCI_S1 | PCD_DPW3_RES5_DSI_S1 | PCD_DPW3_RES5_DER_S1 | PCD_DPW3_RES5_RS_S1 | PCD_DPW3_RES5_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 | PCD_DPW3_RES5_S2 |  | PCD_DPW3_RES5_DLY_S2 | PCD_DPW3_RES5_DIR_S2 | PCD_DPW3_RES5_DSCR_S2 | PCD_DPW3_RES5_DCS_S2 | PCD_DPW3_RES5_DSPC_S2 | PCD_DPW3_RES5_DPP_S2 | PCD_DPW3_RES5_DTPI_S2 | PCD_DPW3_RES5_DCI_S2 | PCD_DPW3_RES5_DSI_S2 | PCD_DPW3_RES5_DER_S2 | PCD_DPW3_RES5_RS_S2 | PCD_DPW3_RES5_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 | PCD_DPW3_RES5_S3 |  | PCD_DPW3_RES5_DLY_S3 | PCD_DPW3_RES5_DIR_S3 | PCD_DPW3_RES5_DSCR_S3 | PCD_DPW3_RES5_DCS_S3 | PCD_DPW3_RES5_DSPC_S3 | PCD_DPW3_RES5_DPP_S3 | PCD_DPW3_RES5_DTPI_S3 | PCD_DPW3_RES5_DCI_S3 | PCD_DPW3_RES5_DSI_S3 | PCD_DPW3_RES5_DER_S3 | PCD_DPW3_RES5_RS_S3 | PCD_DPW3_RES5_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 | PCD_DPW3_RES5_S4 |  | PCD_DPW3_RES5_DLY_S4 | PCD_DPW3_RES5_DIR_S4 | PCD_DPW3_RES5_DSCR_S4 | PCD_DPW3_RES5_DCS_S4 | PCD_DPW3_RES5_DSPC_S4 | PCD_DPW3_RES5_DPP_S4 | PCD_DPW3_RES5_DTPI_S4 | PCD_DPW3_RES5_DCI_S4 | PCD_DPW3_RES5_DSI_S4 | PCD_DPW3_RES5_DER_S4 | PCD_DPW3_RES5_RS_S4 | PCD_DPW3_RES5_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 | PCD_DPW3_RES5_S5 |  | PCD_DPW3_RES5_DLY_S5 | PCD_DPW3_RES5_DIR_S5 | PCD_DPW3_RES5_DSCR_S5 | PCD_DPW3_RES5_DCS_S5 | PCD_DPW3_RES5_DSPC_S5 | PCD_DPW3_RES5_DPP_S5 | PCD_DPW3_RES5_DTPI_S5 | PCD_DPW3_RES5_DCI_S5 | PCD_DPW3_RES5_DSI_S5 | PCD_DPW3_RES5_DER_S5 | PCD_DPW3_RES5_RS_S5 | PCD_DPW3_RES5_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 | PCD_DPW3_RES5_S6 |  | PCD_DPW3_RES5_DLY_S6 | PCD_DPW3_RES5_DIR_S6 | PCD_DPW3_RES5_DSCR_S6 | PCD_DPW3_RES5_DCS_S6 | PCD_DPW3_RES5_DSPC_S6 | PCD_DPW3_RES5_DPP_S6 | PCD_DPW3_RES5_DTPI_S6 | PCD_DPW3_RES5_DCI_S6 | PCD_DPW3_RES5_DSI_S6 | PCD_DPW3_RES5_DER_S6 | PCD_DPW3_RES5_RS_S6 | PCD_DPW3_RES5_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 | PCD_DPW3_RES5_S7 |  | PCD_DPW3_RES5_DLY_S7 | PCD_DPW3_RES5_DIR_S7 | PCD_DPW3_RES5_DSCR_S7 | PCD_DPW3_RES5_DCS_S7 | PCD_DPW3_RES5_DSPC_S7 | PCD_DPW3_RES5_DPP_S7 | PCD_DPW3_RES5_DTPI_S7 | PCD_DPW3_RES5_DCI_S7 | PCD_DPW3_RES5_DSI_S7 | PCD_DPW3_RES5_DER_S7 | PCD_DPW3_RES5_RS_S7 | PCD_DPW3_RES5_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml of additional service reservoir storage at service reservoirs | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.11 |  |  | PCD_DPW3_RES5 | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST | PCD_DPW3_RES5ST |  | PCD_DPW3_RES5_DLY_ST | PCD_DPW3_RES5_DIR_ST | PCD_DPW3_RES5_DSCR_ST | PCD_DPW3_RES5_DCS_ST | PCD_DPW3_RES5_DSPC_ST | PCD_DPW3_RES5_DPP_ST | PCD_DPW3_RES5_DTPI_ST | PCD_DPW3_RES5_DCI_ST | PCD_DPW3_RES5_DSI_ST | PCD_DPW3_RES5_DER_ST | PCD_DPW3_RES5_RS_ST | PCD_DPW3_RES5_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.12 |  | PCD_DPW3_RES6_NR | PCD_DPW3_RES6 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 | PCD_DPW3_RES6_S0 |  | PCD_DPW3_RES6_DLY | PCD_DPW3_RES6_DIR | PCD_DPW3_RES6_DSCR | PCD_DPW3_RES6_DCS | PCD_DPW3_RES6_DSPC | PCD_DPW3_RES6_DPP | PCD_DPW3_RES6_DTPI | PCD_DPW3_RES6_DCI | PCD_DPW3_RES6_DSI | PCD_DPW3_RES6_DER | PCD_DPW3_RES6_RS | PCD_DPW3_RES6_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 | PCD_DPW3_RES6_S1 |  | PCD_DPW3_RES6_DLY_S1 | PCD_DPW3_RES6_DIR_S1 | PCD_DPW3_RES6_DSCR_S1 | PCD_DPW3_RES6_DCS_S1 | PCD_DPW3_RES6_DSPC_S1 | PCD_DPW3_RES6_DPP_S1 | PCD_DPW3_RES6_DTPI_S1 | PCD_DPW3_RES6_DCI_S1 | PCD_DPW3_RES6_DSI_S1 | PCD_DPW3_RES6_DER_S1 | PCD_DPW3_RES6_RS_S1 | PCD_DPW3_RES6_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 | PCD_DPW3_RES6_S2 |  | PCD_DPW3_RES6_DLY_S2 | PCD_DPW3_RES6_DIR_S2 | PCD_DPW3_RES6_DSCR_S2 | PCD_DPW3_RES6_DCS_S2 | PCD_DPW3_RES6_DSPC_S2 | PCD_DPW3_RES6_DPP_S2 | PCD_DPW3_RES6_DTPI_S2 | PCD_DPW3_RES6_DCI_S2 | PCD_DPW3_RES6_DSI_S2 | PCD_DPW3_RES6_DER_S2 | PCD_DPW3_RES6_RS_S2 | PCD_DPW3_RES6_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 | PCD_DPW3_RES6_S3 |  | PCD_DPW3_RES6_DLY_S3 | PCD_DPW3_RES6_DIR_S3 | PCD_DPW3_RES6_DSCR_S3 | PCD_DPW3_RES6_DCS_S3 | PCD_DPW3_RES6_DSPC_S3 | PCD_DPW3_RES6_DPP_S3 | PCD_DPW3_RES6_DTPI_S3 | PCD_DPW3_RES6_DCI_S3 | PCD_DPW3_RES6_DSI_S3 | PCD_DPW3_RES6_DER_S3 | PCD_DPW3_RES6_RS_S3 | PCD_DPW3_RES6_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 | PCD_DPW3_RES6_S4 |  | PCD_DPW3_RES6_DLY_S4 | PCD_DPW3_RES6_DIR_S4 | PCD_DPW3_RES6_DSCR_S4 | PCD_DPW3_RES6_DCS_S4 | PCD_DPW3_RES6_DSPC_S4 | PCD_DPW3_RES6_DPP_S4 | PCD_DPW3_RES6_DTPI_S4 | PCD_DPW3_RES6_DCI_S4 | PCD_DPW3_RES6_DSI_S4 | PCD_DPW3_RES6_DER_S4 | PCD_DPW3_RES6_RS_S4 | PCD_DPW3_RES6_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 | PCD_DPW3_RES6_S5 |  | PCD_DPW3_RES6_DLY_S5 | PCD_DPW3_RES6_DIR_S5 | PCD_DPW3_RES6_DSCR_S5 | PCD_DPW3_RES6_DCS_S5 | PCD_DPW3_RES6_DSPC_S5 | PCD_DPW3_RES6_DPP_S5 | PCD_DPW3_RES6_DTPI_S5 | PCD_DPW3_RES6_DCI_S5 | PCD_DPW3_RES6_DSI_S5 | PCD_DPW3_RES6_DER_S5 | PCD_DPW3_RES6_RS_S5 | PCD_DPW3_RES6_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 | PCD_DPW3_RES6_S6 |  | PCD_DPW3_RES6_DLY_S6 | PCD_DPW3_RES6_DIR_S6 | PCD_DPW3_RES6_DSCR_S6 | PCD_DPW3_RES6_DCS_S6 | PCD_DPW3_RES6_DSPC_S6 | PCD_DPW3_RES6_DPP_S6 | PCD_DPW3_RES6_DTPI_S6 | PCD_DPW3_RES6_DCI_S6 | PCD_DPW3_RES6_DSI_S6 | PCD_DPW3_RES6_DER_S6 | PCD_DPW3_RES6_RS_S6 | PCD_DPW3_RES6_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 | PCD_DPW3_RES6_S7 |  | PCD_DPW3_RES6_DLY_S7 | PCD_DPW3_RES6_DIR_S7 | PCD_DPW3_RES6_DSCR_S7 | PCD_DPW3_RES6_DCS_S7 | PCD_DPW3_RES6_DSPC_S7 | PCD_DPW3_RES6_DPP_S7 | PCD_DPW3_RES6_DTPI_S7 | PCD_DPW3_RES6_DCI_S7 | PCD_DPW3_RES6_DSI_S7 | PCD_DPW3_RES6_DER_S7 | PCD_DPW3_RES6_RS_S7 | PCD_DPW3_RES6_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16a |  | Resilience - Ml/d of peak week production capacity of additional process stream | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.12 |  |  | PCD_DPW3_RES6 | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST | PCD_DPW3_RES6ST |  | PCD_DPW3_RES6_DLY_ST | PCD_DPW3_RES6_DIR_ST | PCD_DPW3_RES6_DSCR_ST | PCD_DPW3_RES6_DCS_ST | PCD_DPW3_RES6_DSPC_ST | PCD_DPW3_RES6_DPP_ST | PCD_DPW3_RES6_DTPI_ST | PCD_DPW3_RES6_DCI_ST | PCD_DPW3_RES6_DSI_ST | PCD_DPW3_RES6_DER_ST | PCD_DPW3_RES6_RS_ST | PCD_DPW3_RES6_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.13 |  | PCD_DPW3_RES7_NR | PCD_DPW3_RES7 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 | PCD_DPW3_RES7_S0 |  | PCD_DPW3_RES7_DLY | PCD_DPW3_RES7_DIR | PCD_DPW3_RES7_DSCR | PCD_DPW3_RES7_DCS | PCD_DPW3_RES7_DSPC | PCD_DPW3_RES7_DPP | PCD_DPW3_RES7_DTPI | PCD_DPW3_RES7_DCI | PCD_DPW3_RES7_DSI | PCD_DPW3_RES7_DER | PCD_DPW3_RES7_RS | PCD_DPW3_RES7_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 | PCD_DPW3_RES7_S1 |  | PCD_DPW3_RES7_DLY_S1 | PCD_DPW3_RES7_DIR_S1 | PCD_DPW3_RES7_DSCR_S1 | PCD_DPW3_RES7_DCS_S1 | PCD_DPW3_RES7_DSPC_S1 | PCD_DPW3_RES7_DPP_S1 | PCD_DPW3_RES7_DTPI_S1 | PCD_DPW3_RES7_DCI_S1 | PCD_DPW3_RES7_DSI_S1 | PCD_DPW3_RES7_DER_S1 | PCD_DPW3_RES7_RS_S1 | PCD_DPW3_RES7_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 | PCD_DPW3_RES7_S2 |  | PCD_DPW3_RES7_DLY_S2 | PCD_DPW3_RES7_DIR_S2 | PCD_DPW3_RES7_DSCR_S2 | PCD_DPW3_RES7_DCS_S2 | PCD_DPW3_RES7_DSPC_S2 | PCD_DPW3_RES7_DPP_S2 | PCD_DPW3_RES7_DTPI_S2 | PCD_DPW3_RES7_DCI_S2 | PCD_DPW3_RES7_DSI_S2 | PCD_DPW3_RES7_DER_S2 | PCD_DPW3_RES7_RS_S2 | PCD_DPW3_RES7_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 | PCD_DPW3_RES7_S3 |  | PCD_DPW3_RES7_DLY_S3 | PCD_DPW3_RES7_DIR_S3 | PCD_DPW3_RES7_DSCR_S3 | PCD_DPW3_RES7_DCS_S3 | PCD_DPW3_RES7_DSPC_S3 | PCD_DPW3_RES7_DPP_S3 | PCD_DPW3_RES7_DTPI_S3 | PCD_DPW3_RES7_DCI_S3 | PCD_DPW3_RES7_DSI_S3 | PCD_DPW3_RES7_DER_S3 | PCD_DPW3_RES7_RS_S3 | PCD_DPW3_RES7_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 | PCD_DPW3_RES7_S4 |  | PCD_DPW3_RES7_DLY_S4 | PCD_DPW3_RES7_DIR_S4 | PCD_DPW3_RES7_DSCR_S4 | PCD_DPW3_RES7_DCS_S4 | PCD_DPW3_RES7_DSPC_S4 | PCD_DPW3_RES7_DPP_S4 | PCD_DPW3_RES7_DTPI_S4 | PCD_DPW3_RES7_DCI_S4 | PCD_DPW3_RES7_DSI_S4 | PCD_DPW3_RES7_DER_S4 | PCD_DPW3_RES7_RS_S4 | PCD_DPW3_RES7_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 | PCD_DPW3_RES7_S5 |  | PCD_DPW3_RES7_DLY_S5 | PCD_DPW3_RES7_DIR_S5 | PCD_DPW3_RES7_DSCR_S5 | PCD_DPW3_RES7_DCS_S5 | PCD_DPW3_RES7_DSPC_S5 | PCD_DPW3_RES7_DPP_S5 | PCD_DPW3_RES7_DTPI_S5 | PCD_DPW3_RES7_DCI_S5 | PCD_DPW3_RES7_DSI_S5 | PCD_DPW3_RES7_DER_S5 | PCD_DPW3_RES7_RS_S5 | PCD_DPW3_RES7_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 | PCD_DPW3_RES7_S6 |  | PCD_DPW3_RES7_DLY_S6 | PCD_DPW3_RES7_DIR_S6 | PCD_DPW3_RES7_DSCR_S6 | PCD_DPW3_RES7_DCS_S6 | PCD_DPW3_RES7_DSPC_S6 | PCD_DPW3_RES7_DPP_S6 | PCD_DPW3_RES7_DTPI_S6 | PCD_DPW3_RES7_DCI_S6 | PCD_DPW3_RES7_DSI_S6 | PCD_DPW3_RES7_DER_S6 | PCD_DPW3_RES7_RS_S6 | PCD_DPW3_RES7_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 | PCD_DPW3_RES7_S7 |  | PCD_DPW3_RES7_DLY_S7 | PCD_DPW3_RES7_DIR_S7 | PCD_DPW3_RES7_DSCR_S7 | PCD_DPW3_RES7_DCS_S7 | PCD_DPW3_RES7_DSPC_S7 | PCD_DPW3_RES7_DPP_S7 | PCD_DPW3_RES7_DTPI_S7 | PCD_DPW3_RES7_DCI_S7 | PCD_DPW3_RES7_DSI_S7 | PCD_DPW3_RES7_DER_S7 | PCD_DPW3_RES7_RS_S7 | PCD_DPW3_RES7_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW16c |  | Resilience - Number of raw water reservoirs with the delivery of specified safety improvements | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.13 |  |  | PCD_DPW3_RES7 | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST | PCD_DPW3_RES7ST |  | PCD_DPW3_RES7_DLY_ST | PCD_DPW3_RES7_DIR_ST | PCD_DPW3_RES7_DSCR_ST | PCD_DPW3_RES7_DCS_ST | PCD_DPW3_RES7_DSPC_ST | PCD_DPW3_RES7_DPP_ST | PCD_DPW3_RES7_DTPI_ST | PCD_DPW3_RES7_DCI_ST | PCD_DPW3_RES7_DSI_ST | PCD_DPW3_RES7_DER_ST | PCD_DPW3_RES7_RS_ST | PCD_DPW3_RES7_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 0 | Nr | 0 | 1 | [53 empty] | DPW3.14 |  | PCD_DPW3_CYBR_NR | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 | PCD_DPW3_CYBR_S0 |  | PCD_DPW3_CYBR_DLY | PCD_DPW3_CYBR_DIR | PCD_DPW3_CYBR_DSCR | PCD_DPW3_CYBR_DCS | PCD_DPW3_CYBR_DSPC | PCD_DPW3_CYBR_DPP | PCD_DPW3_CYBR_DTPI | PCD_DPW3_CYBR_DCI | PCD_DPW3_CYBR_DSI | PCD_DPW3_CYBR_DER | PCD_DPW3_CYBR_RS | PCD_DPW3_CYBR_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 | PCD_DPW3_CYBR_S1 |  | PCD_DPW3_CYBR_DLY_S1 | PCD_DPW3_CYBR_DIR_S1 | PCD_DPW3_CYBR_DSCR_S1 | PCD_DPW3_CYBR_DCS_S1 | PCD_DPW3_CYBR_DSPC_S1 | PCD_DPW3_CYBR_DPP_S1 | PCD_DPW3_CYBR_DTPI_S1 | PCD_DPW3_CYBR_DCI_S1 | PCD_DPW3_CYBR_DSI_S1 | PCD_DPW3_CYBR_DER_S1 | PCD_DPW3_CYBR_RS_S1 | PCD_DPW3_CYBR_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 | PCD_DPW3_CYBR_S2 |  | PCD_DPW3_CYBR_DLY_S2 | PCD_DPW3_CYBR_DIR_S2 | PCD_DPW3_CYBR_DSCR_S2 | PCD_DPW3_CYBR_DCS_S2 | PCD_DPW3_CYBR_DSPC_S2 | PCD_DPW3_CYBR_DPP_S2 | PCD_DPW3_CYBR_DTPI_S2 | PCD_DPW3_CYBR_DCI_S2 | PCD_DPW3_CYBR_DSI_S2 | PCD_DPW3_CYBR_DER_S2 | PCD_DPW3_CYBR_RS_S2 | PCD_DPW3_CYBR_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 | PCD_DPW3_CYBR_S3 |  | PCD_DPW3_CYBR_DLY_S3 | PCD_DPW3_CYBR_DIR_S3 | PCD_DPW3_CYBR_DSCR_S3 | PCD_DPW3_CYBR_DCS_S3 | PCD_DPW3_CYBR_DSPC_S3 | PCD_DPW3_CYBR_DPP_S3 | PCD_DPW3_CYBR_DTPI_S3 | PCD_DPW3_CYBR_DCI_S3 | PCD_DPW3_CYBR_DSI_S3 | PCD_DPW3_CYBR_DER_S3 | PCD_DPW3_CYBR_RS_S3 | PCD_DPW3_CYBR_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 | PCD_DPW3_CYBR_S4 |  | PCD_DPW3_CYBR_DLY_S4 | PCD_DPW3_CYBR_DIR_S4 | PCD_DPW3_CYBR_DSCR_S4 | PCD_DPW3_CYBR_DCS_S4 | PCD_DPW3_CYBR_DSPC_S4 | PCD_DPW3_CYBR_DPP_S4 | PCD_DPW3_CYBR_DTPI_S4 | PCD_DPW3_CYBR_DCI_S4 | PCD_DPW3_CYBR_DSI_S4 | PCD_DPW3_CYBR_DER_S4 | PCD_DPW3_CYBR_RS_S4 | PCD_DPW3_CYBR_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 | PCD_DPW3_CYBR_S5 |  | PCD_DPW3_CYBR_DLY_S5 | PCD_DPW3_CYBR_DIR_S5 | PCD_DPW3_CYBR_DSCR_S5 | PCD_DPW3_CYBR_DCS_S5 | PCD_DPW3_CYBR_DSPC_S5 | PCD_DPW3_CYBR_DPP_S5 | PCD_DPW3_CYBR_DTPI_S5 | PCD_DPW3_CYBR_DCI_S5 | PCD_DPW3_CYBR_DSI_S5 | PCD_DPW3_CYBR_DER_S5 | PCD_DPW3_CYBR_RS_S5 | PCD_DPW3_CYBR_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 6 | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 | PCD_DPW3_CYBR_S6 |  | PCD_DPW3_CYBR_DLY_S6 | PCD_DPW3_CYBR_DIR_S6 | PCD_DPW3_CYBR_DSCR_S6 | PCD_DPW3_CYBR_DCS_S6 | PCD_DPW3_CYBR_DSPC_S6 | PCD_DPW3_CYBR_DPP_S6 | PCD_DPW3_CYBR_DTPI_S6 | PCD_DPW3_CYBR_DCI_S6 | PCD_DPW3_CYBR_DSI_S6 | PCD_DPW3_CYBR_DER_S6 | PCD_DPW3_CYBR_RS_S6 | PCD_DPW3_CYBR_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 | PCD_DPW3_CYBR_S7 |  | PCD_DPW3_CYBR_DLY_S7 | PCD_DPW3_CYBR_DIR_S7 | PCD_DPW3_CYBR_DSCR_S7 | PCD_DPW3_CYBR_DCS_S7 | PCD_DPW3_CYBR_DSPC_S7 | PCD_DPW3_CYBR_DPP_S7 | PCD_DPW3_CYBR_DTPI_S7 | PCD_DPW3_CYBR_DCI_S7 | PCD_DPW3_CYBR_DSI_S7 | PCD_DPW3_CYBR_DER_S7 | PCD_DPW3_CYBR_RS_S7 | PCD_DPW3_CYBR_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW17b |  | Cyber - Legal instruments | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.14 |  |  | PCD_DPW3_CYBR | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST | PCD_DPW3_CYBRST |  | PCD_DPW3_CYBR_DLY_ST | PCD_DPW3_CYBR_DIR_ST | PCD_DPW3_CYBR_DSCR_ST | PCD_DPW3_CYBR_DCS_ST | PCD_DPW3_CYBR_DSPC_ST | PCD_DPW3_CYBR_DPP_ST | PCD_DPW3_CYBR_DTPI_ST | PCD_DPW3_CYBR_DCI_ST | PCD_DPW3_CYBR_DSI_ST | PCD_DPW3_CYBR_DER_ST | PCD_DPW3_CYBR_RS_ST | PCD_DPW3_CYBR_DPLE_ST
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 0 | Nr | 0 | 1 | [53 empty] | DPW3.15 |  | PCD_DPW3_SEMD_NR | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 | PCD_DPW3_SEMD_S0 |  | PCD_DPW3_SEMD_DLY | PCD_DPW3_SEMD_DIR | PCD_DPW3_SEMD_DSCR | PCD_DPW3_SEMD_DCS | PCD_DPW3_SEMD_DSPC | PCD_DPW3_SEMD_DPP | PCD_DPW3_SEMD_DTPI | PCD_DPW3_SEMD_DCI | PCD_DPW3_SEMD_DSI | PCD_DPW3_SEMD_DER | PCD_DPW3_SEMD_RS | PCD_DPW3_SEMD_DPLE
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 1 | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 | PCD_DPW3_SEMD_S1 |  | PCD_DPW3_SEMD_DLY_S1 | PCD_DPW3_SEMD_DIR_S1 | PCD_DPW3_SEMD_DSCR_S1 | PCD_DPW3_SEMD_DCS_S1 | PCD_DPW3_SEMD_DSPC_S1 | PCD_DPW3_SEMD_DPP_S1 | PCD_DPW3_SEMD_DTPI_S1 | PCD_DPW3_SEMD_DCI_S1 | PCD_DPW3_SEMD_DSI_S1 | PCD_DPW3_SEMD_DER_S1 | PCD_DPW3_SEMD_RS_S1 | PCD_DPW3_SEMD_DPLE_S1
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 | PCD_DPW3_SEMD_S2 |  | PCD_DPW3_SEMD_DLY_S2 | PCD_DPW3_SEMD_DIR_S2 | PCD_DPW3_SEMD_DSCR_S2 | PCD_DPW3_SEMD_DCS_S2 | PCD_DPW3_SEMD_DSPC_S2 | PCD_DPW3_SEMD_DPP_S2 | PCD_DPW3_SEMD_DTPI_S2 | PCD_DPW3_SEMD_DCI_S2 | PCD_DPW3_SEMD_DSI_S2 | PCD_DPW3_SEMD_DER_S2 | PCD_DPW3_SEMD_RS_S2 | PCD_DPW3_SEMD_DPLE_S2
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 | PCD_DPW3_SEMD_S3 |  | PCD_DPW3_SEMD_DLY_S3 | PCD_DPW3_SEMD_DIR_S3 | PCD_DPW3_SEMD_DSCR_S3 | PCD_DPW3_SEMD_DCS_S3 | PCD_DPW3_SEMD_DSPC_S3 | PCD_DPW3_SEMD_DPP_S3 | PCD_DPW3_SEMD_DTPI_S3 | PCD_DPW3_SEMD_DCI_S3 | PCD_DPW3_SEMD_DSI_S3 | PCD_DPW3_SEMD_DER_S3 | PCD_DPW3_SEMD_RS_S3 | PCD_DPW3_SEMD_DPLE_S3
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 | PCD_DPW3_SEMD_S4 |  | PCD_DPW3_SEMD_DLY_S4 | PCD_DPW3_SEMD_DIR_S4 | PCD_DPW3_SEMD_DSCR_S4 | PCD_DPW3_SEMD_DCS_S4 | PCD_DPW3_SEMD_DSPC_S4 | PCD_DPW3_SEMD_DPP_S4 | PCD_DPW3_SEMD_DTPI_S4 | PCD_DPW3_SEMD_DCI_S4 | PCD_DPW3_SEMD_DSI_S4 | PCD_DPW3_SEMD_DER_S4 | PCD_DPW3_SEMD_RS_S4 | PCD_DPW3_SEMD_DPLE_S4
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 | PCD_DPW3_SEMD_S5 |  | PCD_DPW3_SEMD_DLY_S5 | PCD_DPW3_SEMD_DIR_S5 | PCD_DPW3_SEMD_DSCR_S5 | PCD_DPW3_SEMD_DCS_S5 | PCD_DPW3_SEMD_DSPC_S5 | PCD_DPW3_SEMD_DPP_S5 | PCD_DPW3_SEMD_DTPI_S5 | PCD_DPW3_SEMD_DCI_S5 | PCD_DPW3_SEMD_DSI_S5 | PCD_DPW3_SEMD_DER_S5 | PCD_DPW3_SEMD_RS_S5 | PCD_DPW3_SEMD_DPLE_S5
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 | PCD_DPW3_SEMD_S6 |  | PCD_DPW3_SEMD_DLY_S6 | PCD_DPW3_SEMD_DIR_S6 | PCD_DPW3_SEMD_DSCR_S6 | PCD_DPW3_SEMD_DCS_S6 | PCD_DPW3_SEMD_DSPC_S6 | PCD_DPW3_SEMD_DPP_S6 | PCD_DPW3_SEMD_DTPI_S6 | PCD_DPW3_SEMD_DCI_S6 | PCD_DPW3_SEMD_DSI_S6 | PCD_DPW3_SEMD_DER_S6 | PCD_DPW3_SEMD_RS_S6 | PCD_DPW3_SEMD_DPLE_S6
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 | PCD_DPW3_SEMD_S7 |  | PCD_DPW3_SEMD_DLY_S7 | PCD_DPW3_SEMD_DIR_S7 | PCD_DPW3_SEMD_DSCR_S7 | PCD_DPW3_SEMD_DCS_S7 | PCD_DPW3_SEMD_DSPC_S7 | PCD_DPW3_SEMD_DPP_S7 | PCD_DPW3_SEMD_DTPI_S7 | PCD_DPW3_SEMD_DCI_S7 | PCD_DPW3_SEMD_DSI_S7 | PCD_DPW3_SEMD_DER_S7 | PCD_DPW3_SEMD_RS_S7 | PCD_DPW3_SEMD_DPLE_S7
| TMS | PR24CA109 Water Resilience and Security | PCDW17a |  | SEMD - Legal instruments | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPW3.15 |  |  | PCD_DPW3_SEMD | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST | PCD_DPW3_SEMDST |  | PCD_DPW3_SEMD_DLY_ST | PCD_DPW3_SEMD_DIR_ST | PCD_DPW3_SEMD_DSCR_ST | PCD_DPW3_SEMD_DCS_ST | PCD_DPW3_SEMD_DSPC_ST | PCD_DPW3_SEMD_DPP_ST | PCD_DPW3_SEMD_DTPI_ST | PCD_DPW3_SEMD_DCI_ST | PCD_DPW3_SEMD_DSI_ST | PCD_DPW3_SEMD_DER_ST | PCD_DPW3_SEMD_RS_ST | PCD_DPW3_SEMD_DPLE_ST
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 0 | Nr | 0 | 0 | [53 empty] | DPW3.16 |  | PCD_DPW3_GGR_NR | PCD_DPW3_GGR | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 | PCD_DPW3_GGR_S0 |  | PCD_DPW3_GGR_DLY | PCD_DPW3_GGR_DIR | PCD_DPW3_GGR_DSCR | PCD_DPW3_GGR_DCS | PCD_DPW3_GGR_DSPC | PCD_DPW3_GGR_DPP | PCD_DPW3_GGR_DTPI | PCD_DPW3_GGR_DCI | PCD_DPW3_GGR_DSI | PCD_DPW3_GGR_DER | PCD_DPW3_GGR_RS | PCD_DPW3_GGR_DPLE
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 | PCD_DPW3_GGR_S1 |  | PCD_DPW3_GGR_DLY_S1 | PCD_DPW3_GGR_DIR_S1 | PCD_DPW3_GGR_DSCR_S1 | PCD_DPW3_GGR_DCS_S1 | PCD_DPW3_GGR_DSPC_S1 | PCD_DPW3_GGR_DPP_S1 | PCD_DPW3_GGR_DTPI_S1 | PCD_DPW3_GGR_DCI_S1 | PCD_DPW3_GGR_DSI_S1 | PCD_DPW3_GGR_DER_S1 | PCD_DPW3_GGR_RS_S1 | PCD_DPW3_GGR_DPLE_S1
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 | PCD_DPW3_GGR_S2 |  | PCD_DPW3_GGR_DLY_S2 | PCD_DPW3_GGR_DIR_S2 | PCD_DPW3_GGR_DSCR_S2 | PCD_DPW3_GGR_DCS_S2 | PCD_DPW3_GGR_DSPC_S2 | PCD_DPW3_GGR_DPP_S2 | PCD_DPW3_GGR_DTPI_S2 | PCD_DPW3_GGR_DCI_S2 | PCD_DPW3_GGR_DSI_S2 | PCD_DPW3_GGR_DER_S2 | PCD_DPW3_GGR_RS_S2 | PCD_DPW3_GGR_DPLE_S2
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 | PCD_DPW3_GGR_S3 |  | PCD_DPW3_GGR_DLY_S3 | PCD_DPW3_GGR_DIR_S3 | PCD_DPW3_GGR_DSCR_S3 | PCD_DPW3_GGR_DCS_S3 | PCD_DPW3_GGR_DSPC_S3 | PCD_DPW3_GGR_DPP_S3 | PCD_DPW3_GGR_DTPI_S3 | PCD_DPW3_GGR_DCI_S3 | PCD_DPW3_GGR_DSI_S3 | PCD_DPW3_GGR_DER_S3 | PCD_DPW3_GGR_RS_S3 | PCD_DPW3_GGR_DPLE_S3
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 | PCD_DPW3_GGR_S4 |  | PCD_DPW3_GGR_DLY_S4 | PCD_DPW3_GGR_DIR_S4 | PCD_DPW3_GGR_DSCR_S4 | PCD_DPW3_GGR_DCS_S4 | PCD_DPW3_GGR_DSPC_S4 | PCD_DPW3_GGR_DPP_S4 | PCD_DPW3_GGR_DTPI_S4 | PCD_DPW3_GGR_DCI_S4 | PCD_DPW3_GGR_DSI_S4 | PCD_DPW3_GGR_DER_S4 | PCD_DPW3_GGR_RS_S4 | PCD_DPW3_GGR_DPLE_S4
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 | PCD_DPW3_GGR_S5 |  | PCD_DPW3_GGR_DLY_S5 | PCD_DPW3_GGR_DIR_S5 | PCD_DPW3_GGR_DSCR_S5 | PCD_DPW3_GGR_DCS_S5 | PCD_DPW3_GGR_DSPC_S5 | PCD_DPW3_GGR_DPP_S5 | PCD_DPW3_GGR_DTPI_S5 | PCD_DPW3_GGR_DCI_S5 | PCD_DPW3_GGR_DSI_S5 | PCD_DPW3_GGR_DER_S5 | PCD_DPW3_GGR_RS_S5 | PCD_DPW3_GGR_DPLE_S5
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 | PCD_DPW3_GGR_S6 |  | PCD_DPW3_GGR_DLY_S6 | PCD_DPW3_GGR_DIR_S6 | PCD_DPW3_GGR_DSCR_S6 | PCD_DPW3_GGR_DCS_S6 | PCD_DPW3_GGR_DSPC_S6 | PCD_DPW3_GGR_DPP_S6 | PCD_DPW3_GGR_DTPI_S6 | PCD_DPW3_GGR_DCI_S6 | PCD_DPW3_GGR_DSI_S6 | PCD_DPW3_GGR_DER_S6 | PCD_DPW3_GGR_RS_S6 | PCD_DPW3_GGR_DPLE_S6
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes at Stage 7 | Nr | 0 | [54 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 | PCD_DPW3_GGR_S7 |  | PCD_DPW3_GGR_DLY_S7 | PCD_DPW3_GGR_DIR_S7 | PCD_DPW3_GGR_DSCR_S7 | PCD_DPW3_GGR_DCS_S7 | PCD_DPW3_GGR_DSPC_S7 | PCD_DPW3_GGR_DPP_S7 | PCD_DPW3_GGR_DTPI_S7 | PCD_DPW3_GGR_DCI_S7 | PCD_DPW3_GGR_DSI_S7 | PCD_DPW3_GGR_DER_S7 | PCD_DPW3_GGR_RS_S7 | PCD_DPW3_GGR_DPLE_S7
| TMS | PR24CA118 Net Zero | PCDWW34 |  | Greenhouse gas reduction (net zero) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPW3.16 |  |  | PCD_DPW3_GGR | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST | PCD_DPW3_GGRST |  | PCD_DPW3_GGR_DLY_ST | PCD_DPW3_GGR_DIR_ST | PCD_DPW3_GGR_DSCR_ST | PCD_DPW3_GGR_DCS_ST | PCD_DPW3_GGR_DSPC_ST | PCD_DPW3_GGR_DPP_ST | PCD_DPW3_GGR_DTPI_ST | PCD_DPW3_GGR_DCI_ST | PCD_DPW3_GGR_DSI_ST | PCD_DPW3_GGR_DER_ST | PCD_DPW3_GGR_RS_ST | PCD_DPW3_GGR_DPLE_ST

## DPWW3
DPWW3
Interim Milestones - Wastewater - Programme level
| Company | PCD Model | PCD Ref | PCD applicable to company | Line description | PCD Output Description | Units | DPs | Number of Schemes (Nr) | [21 empty] | Total number of schemes with a 90+ day delay for any given IM | Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category | [10 empty] | DP reference |  |  | Number of Schemes (Nr) | IM1 has yet to be achieved | [20 empty] | Total number of schemes with a 90+ day delay for any given IM | Reasons for delay - Number of delayed schemes falling into each 'primary reason for delay' category
Data_Start | [9 empty] | Pre 2025-26 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 |  | Lack of internal resourcing | Lack of supply chain resourcing | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency |  |  | BON_Start | Constant | 2024-25 Q4 | 2025-26 Q1 | 2025-26 Q2 | 2025-26 Q3 | 2025-26 Q4 | 2026-27 Q1 | 2026-27 Q2 | 2026-27 Q3 | 2026-27 Q4 | 2027-28 Q1 | 2027-28 Q2 | 2027-28 Q3 | 2027-28 Q4 | 2028-29 Q1 | 2028-29 Q2 | 2028-29 Q3 | 2028-29 Q4 | 2029-30 Q1 | 2029-30 Q2 | 2029-30 Q3 | 2029-30 Q4 | Conatant | Lack of internal resourcing | Lack of supply chain resourcing | Change in solution (IM2) | Supply chain capacity | Land and planning permission | Third-party interface | Contractual issues | Sites issues | Environmental risks | Regulatory Sign off Delay | Programme level efficiency
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 0 | Nr | 0 | 6 | 6 | [32 empty] | DPWW3.1 |  | PCD_DPWW3_SOW1 | PCD_DPWW3_SOW1_NR | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_S0 | PCD_DPWW3_SOW1_DLY | PCD_DPWW3_SOW1_DIR | PCD_DPWW3_SOW1_DSCR | PCD_DPWW3_SOW1_DCS | PCD_DPWW3_SOW1_DSCS | PCD_DPWW3_SOW1_DPP | PCD_DPWW3_SOW1_DTPI | PCD_DPWW3_SOW1_DCI | PCD_DPWW3_SOW1_DSI | PCD_DPWW3_SOW1_DER | PCD_DPWW3_SOW1_RS | PCD_DPWW3_SOW1_DPLE
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 6 | 6 | 5 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S1 |  | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_S1 | PCD_DPWW3_SOW1_DLY_S1 | PCD_DPWW3_SOW1_DIR_S1 | PCD_DPWW3_SOW1_DSCR_S1 | PCD_DPWW3_SOW1_DCS_S1 | PCD_DPWW3_SOW1_DSCS_S1 | PCD_DPWW3_SOW1_DPP_S1 | PCD_DPWW3_SOW1_DTPI_S1 | PCD_DPWW3_SOW1_DCI_S1 | PCD_DPWW3_SOW1_DSI_S1 | PCD_DPWW3_SOW1_DER_S1 | PCD_DPWW3_SOW1_RS_S1 | PCD_DPWW3_SOW1_DPLE_S1
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 1 | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S2 |  | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_S2 | PCD_DPWW3_SOW1_DLY_S2 | PCD_DPWW3_SOW1_DIR_S2 | PCD_DPWW3_SOW1_DSCR_S2 | PCD_DPWW3_SOW1_DCS_S2 | PCD_DPWW3_SOW1_DSCS_S2 | PCD_DPWW3_SOW1_DPP_S2 | PCD_DPWW3_SOW1_DTPI_S2 | PCD_DPWW3_SOW1_DCI_S2 | PCD_DPWW3_SOW1_DSI_S2 | PCD_DPWW3_SOW1_DER_S2 | PCD_DPWW3_SOW1_RS_S2 | PCD_DPWW3_SOW1_DPLE_S2
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S3 |  | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_S3 | PCD_DPWW3_SOW1_DLY_S3 | PCD_DPWW3_SOW1_DIR_S3 | PCD_DPWW3_SOW1_DSCR_S3 | PCD_DPWW3_SOW1_DCS_S3 | PCD_DPWW3_SOW1_DSCS_S3 | PCD_DPWW3_SOW1_DPP_S3 | PCD_DPWW3_SOW1_DTPI_S3 | PCD_DPWW3_SOW1_DCI_S3 | PCD_DPWW3_SOW1_DSI_S3 | PCD_DPWW3_SOW1_DER_S3 | PCD_DPWW3_SOW1_RS_S3 | PCD_DPWW3_SOW1_DPLE_S3
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 3 | 3 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 4 | 4 | [12 empty] | DPWW3.1 |  | _S4 |  | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_S4 | PCD_DPWW3_SOW1_DLY_S4 | PCD_DPWW3_SOW1_DIR_S4 | PCD_DPWW3_SOW1_DSCR_S4 | PCD_DPWW3_SOW1_DCS_S4 | PCD_DPWW3_SOW1_DSCS_S4 | PCD_DPWW3_SOW1_DPP_S4 | PCD_DPWW3_SOW1_DTPI_S4 | PCD_DPWW3_SOW1_DCI_S4 | PCD_DPWW3_SOW1_DSI_S4 | PCD_DPWW3_SOW1_DER_S4 | PCD_DPWW3_SOW1_RS_S4 | PCD_DPWW3_SOW1_DPLE_S4
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.1 |  | _S5 |  | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_S5 | PCD_DPWW3_SOW1_DLY_S5 | PCD_DPWW3_SOW1_DIR_S5 | PCD_DPWW3_SOW1_DSCR_S5 | PCD_DPWW3_SOW1_DCS_S5 | PCD_DPWW3_SOW1_DSCS_S5 | PCD_DPWW3_SOW1_DPP_S5 | PCD_DPWW3_SOW1_DTPI_S5 | PCD_DPWW3_SOW1_DCI_S5 | PCD_DPWW3_SOW1_DSI_S5 | PCD_DPWW3_SOW1_DER_S5 | PCD_DPWW3_SOW1_RS_S5 | PCD_DPWW3_SOW1_DPLE_S5
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 2 | 2 | 2 | 2 | 2 | [12 empty] | DPWW3.1 |  | _S6 |  | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_S6 | PCD_DPWW3_SOW1_DLY_S6 | PCD_DPWW3_SOW1_DIR_S6 | PCD_DPWW3_SOW1_DSCR_S6 | PCD_DPWW3_SOW1_DCS_S6 | PCD_DPWW3_SOW1_DSCS_S6 | PCD_DPWW3_SOW1_DPP_S6 | PCD_DPWW3_SOW1_DTPI_S6 | PCD_DPWW3_SOW1_DCI_S6 | PCD_DPWW3_SOW1_DSI_S6 | PCD_DPWW3_SOW1_DER_S6 | PCD_DPWW3_SOW1_RS_S6 | PCD_DPWW3_SOW1_DPLE_S6
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.1 |  | _S7 |  | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_S7 | PCD_DPWW3_SOW1_DLY_S7 | PCD_DPWW3_SOW1_DIR_S7 | PCD_DPWW3_SOW1_DSCR_S7 | PCD_DPWW3_SOW1_DCS_S7 | PCD_DPWW3_SOW1_DSCS_S7 | PCD_DPWW3_SOW1_DPP_S7 | PCD_DPWW3_SOW1_DTPI_S7 | PCD_DPWW3_SOW1_DCI_S7 | PCD_DPWW3_SOW1_DSI_S7 | PCD_DPWW3_SOW1_DER_S7 | PCD_DPWW3_SOW1_RS_S7 | PCD_DPWW3_SOW1_DPLE_S7
| TMS | PR24CA115 Wastewater Other Storm Overflow | PCDWW5b | Y | Storm Overflow - Wetland | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | [12 empty] | DPWW3.1 |  | _ST |  | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_ST | PCD_DPWW3_SOW1_DLY_ST | PCD_DPWW3_SOW1_DIR_ST | PCD_DPWW3_SOW1_DSCR_ST | PCD_DPWW3_SOW1_DCS_ST | PCD_DPWW3_SOW1_DSCS_ST | PCD_DPWW3_SOW1_DPP_ST | PCD_DPWW3_SOW1_DTPI_ST | PCD_DPWW3_SOW1_DCI_ST | PCD_DPWW3_SOW1_DSI_ST | PCD_DPWW3_SOW1_DER_ST | PCD_DPWW3_SOW1_RS_ST | PCD_DPWW3_SOW1_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 7 | 7 | [32 empty] | DPWW3.2 |  | PCD_DPWW3_TCR1 | PCD_DPWW3_TCR1_NR | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_S0 | PCD_DPWW3_TCR1_DLY | PCD_DPWW3_TCR1_DIR | PCD_DPWW3_TCR1_DSCR | PCD_DPWW3_TCR1_DCS | PCD_DPWW3_TCR1_DSCS | PCD_DPWW3_TCR1_DPP | PCD_DPWW3_TCR1_DTPI | PCD_DPWW3_TCR1_DCI | PCD_DPWW3_TCR1_DSI | PCD_DPWW3_TCR1_DER | PCD_DPWW3_TCR1_RS | PCD_DPWW3_TCR1_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 5 | 5 | 3 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | _S1 |  | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_S1 | PCD_DPWW3_TCR1_DLY_S1 | PCD_DPWW3_TCR1_DIR_S1 | PCD_DPWW3_TCR1_DSCR_S1 | PCD_DPWW3_TCR1_DCS_S1 | PCD_DPWW3_TCR1_DSCS_S1 | PCD_DPWW3_TCR1_DPP_S1 | PCD_DPWW3_TCR1_DTPI_S1 | PCD_DPWW3_TCR1_DCI_S1 | PCD_DPWW3_TCR1_DSI_S1 | PCD_DPWW3_TCR1_DER_S1 | PCD_DPWW3_TCR1_RS_S1 | PCD_DPWW3_TCR1_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 2 | 3 | 3 | 3 | 4 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | [12 empty] | DPWW3.2 |  | _S2 |  | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_S2 | PCD_DPWW3_TCR1_DLY_S2 | PCD_DPWW3_TCR1_DIR_S2 | PCD_DPWW3_TCR1_DSCR_S2 | PCD_DPWW3_TCR1_DCS_S2 | PCD_DPWW3_TCR1_DSCS_S2 | PCD_DPWW3_TCR1_DPP_S2 | PCD_DPWW3_TCR1_DTPI_S2 | PCD_DPWW3_TCR1_DCI_S2 | PCD_DPWW3_TCR1_DSI_S2 | PCD_DPWW3_TCR1_DER_S2 | PCD_DPWW3_TCR1_RS_S2 | PCD_DPWW3_TCR1_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [12 empty] | DPWW3.2 |  | _S3 |  | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_S3 | PCD_DPWW3_TCR1_DLY_S3 | PCD_DPWW3_TCR1_DIR_S3 | PCD_DPWW3_TCR1_DSCR_S3 | PCD_DPWW3_TCR1_DCS_S3 | PCD_DPWW3_TCR1_DSCS_S3 | PCD_DPWW3_TCR1_DPP_S3 | PCD_DPWW3_TCR1_DTPI_S3 | PCD_DPWW3_TCR1_DCI_S3 | PCD_DPWW3_TCR1_DSI_S3 | PCD_DPWW3_TCR1_DER_S3 | PCD_DPWW3_TCR1_RS_S3 | PCD_DPWW3_TCR1_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | 6 | 6 | 6 | 6 | 6 | 3 | 3 | [12 empty] | DPWW3.2 |  | _S4 |  | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_S4 | PCD_DPWW3_TCR1_DLY_S4 | PCD_DPWW3_TCR1_DIR_S4 | PCD_DPWW3_TCR1_DSCR_S4 | PCD_DPWW3_TCR1_DCS_S4 | PCD_DPWW3_TCR1_DSCS_S4 | PCD_DPWW3_TCR1_DPP_S4 | PCD_DPWW3_TCR1_DTPI_S4 | PCD_DPWW3_TCR1_DCI_S4 | PCD_DPWW3_TCR1_DSI_S4 | PCD_DPWW3_TCR1_DER_S4 | PCD_DPWW3_TCR1_RS_S4 | PCD_DPWW3_TCR1_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | [12 empty] | DPWW3.2 |  | _S5 |  | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_S5 | PCD_DPWW3_TCR1_DLY_S5 | PCD_DPWW3_TCR1_DIR_S5 | PCD_DPWW3_TCR1_DSCR_S5 | PCD_DPWW3_TCR1_DCS_S5 | PCD_DPWW3_TCR1_DSCS_S5 | PCD_DPWW3_TCR1_DPP_S5 | PCD_DPWW3_TCR1_DTPI_S5 | PCD_DPWW3_TCR1_DCI_S5 | PCD_DPWW3_TCR1_DSI_S5 | PCD_DPWW3_TCR1_DER_S5 | PCD_DPWW3_TCR1_RS_S5 | PCD_DPWW3_TCR1_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.2 |  | _S6 |  | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_S6 | PCD_DPWW3_TCR1_DLY_S6 | PCD_DPWW3_TCR1_DIR_S6 | PCD_DPWW3_TCR1_DSCR_S6 | PCD_DPWW3_TCR1_DCS_S6 | PCD_DPWW3_TCR1_DSCS_S6 | PCD_DPWW3_TCR1_DPP_S6 | PCD_DPWW3_TCR1_DTPI_S6 | PCD_DPWW3_TCR1_DCI_S6 | PCD_DPWW3_TCR1_DSI_S6 | PCD_DPWW3_TCR1_DER_S6 | PCD_DPWW3_TCR1_RS_S6 | PCD_DPWW3_TCR1_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.2 |  | _S7 |  | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_S7 | PCD_DPWW3_TCR1_DLY_S7 | PCD_DPWW3_TCR1_DIR_S7 | PCD_DPWW3_TCR1_DSCR_S7 | PCD_DPWW3_TCR1_DCS_S7 | PCD_DPWW3_TCR1_DSCS_S7 | PCD_DPWW3_TCR1_DPP_S7 | PCD_DPWW3_TCR1_DTPI_S7 | PCD_DPWW3_TCR1_DCI_S7 | PCD_DPWW3_TCR1_DSI_S7 | PCD_DPWW3_TCR1_DER_S7 | PCD_DPWW3_TCR1_RS_S7 | PCD_DPWW3_TCR1_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW7 | Y | Treatment for chemical removal (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | [12 empty] | DPWW3.2 |  | _ST |  | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_ST | PCD_DPWW3_TCR1_DLY_ST | PCD_DPWW3_TCR1_DIR_ST | PCD_DPWW3_TCR1_DSCR_ST | PCD_DPWW3_TCR1_DCS_ST | PCD_DPWW3_TCR1_DSCS_ST | PCD_DPWW3_TCR1_DPP_ST | PCD_DPWW3_TCR1_DTPI_ST | PCD_DPWW3_TCR1_DCI_ST | PCD_DPWW3_TCR1_DSI_ST | PCD_DPWW3_TCR1_DER_ST | PCD_DPWW3_TCR1_RS_ST | PCD_DPWW3_TCR1_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | [32 empty] | DPWW3.3 |  | PCD_DPWW3_TNR1 | PCD_DPWW3_TNR1_NR | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_S0 | PCD_DPWW3_TNR1_DLY | PCD_DPWW3_TNR1_DIR | PCD_DPWW3_TNR1_DSCR | PCD_DPWW3_TNR1_DCS | PCD_DPWW3_TNR1_DSCS | PCD_DPWW3_TNR1_DPP | PCD_DPWW3_TNR1_DTPI | PCD_DPWW3_TNR1_DCI | PCD_DPWW3_TNR1_DSI | PCD_DPWW3_TNR1_DER | PCD_DPWW3_TNR1_RS | PCD_DPWW3_TNR1_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S1 |  | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_S1 | PCD_DPWW3_TNR1_DLY_S1 | PCD_DPWW3_TNR1_DIR_S1 | PCD_DPWW3_TNR1_DSCR_S1 | PCD_DPWW3_TNR1_DCS_S1 | PCD_DPWW3_TNR1_DSCS_S1 | PCD_DPWW3_TNR1_DPP_S1 | PCD_DPWW3_TNR1_DTPI_S1 | PCD_DPWW3_TNR1_DCI_S1 | PCD_DPWW3_TNR1_DSI_S1 | PCD_DPWW3_TNR1_DER_S1 | PCD_DPWW3_TNR1_RS_S1 | PCD_DPWW3_TNR1_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S2 |  | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_S2 | PCD_DPWW3_TNR1_DLY_S2 | PCD_DPWW3_TNR1_DIR_S2 | PCD_DPWW3_TNR1_DSCR_S2 | PCD_DPWW3_TNR1_DCS_S2 | PCD_DPWW3_TNR1_DSCS_S2 | PCD_DPWW3_TNR1_DPP_S2 | PCD_DPWW3_TNR1_DTPI_S2 | PCD_DPWW3_TNR1_DCI_S2 | PCD_DPWW3_TNR1_DSI_S2 | PCD_DPWW3_TNR1_DER_S2 | PCD_DPWW3_TNR1_RS_S2 | PCD_DPWW3_TNR1_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S3 |  | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_S3 | PCD_DPWW3_TNR1_DLY_S3 | PCD_DPWW3_TNR1_DIR_S3 | PCD_DPWW3_TNR1_DSCR_S3 | PCD_DPWW3_TNR1_DCS_S3 | PCD_DPWW3_TNR1_DSCS_S3 | PCD_DPWW3_TNR1_DPP_S3 | PCD_DPWW3_TNR1_DTPI_S3 | PCD_DPWW3_TNR1_DCI_S3 | PCD_DPWW3_TNR1_DSI_S3 | PCD_DPWW3_TNR1_DER_S3 | PCD_DPWW3_TNR1_RS_S3 | PCD_DPWW3_TNR1_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S4 |  | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_S4 | PCD_DPWW3_TNR1_DLY_S4 | PCD_DPWW3_TNR1_DIR_S4 | PCD_DPWW3_TNR1_DSCR_S4 | PCD_DPWW3_TNR1_DCS_S4 | PCD_DPWW3_TNR1_DSCS_S4 | PCD_DPWW3_TNR1_DPP_S4 | PCD_DPWW3_TNR1_DTPI_S4 | PCD_DPWW3_TNR1_DCI_S4 | PCD_DPWW3_TNR1_DSI_S4 | PCD_DPWW3_TNR1_DER_S4 | PCD_DPWW3_TNR1_RS_S4 | PCD_DPWW3_TNR1_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S5 |  | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_S5 | PCD_DPWW3_TNR1_DLY_S5 | PCD_DPWW3_TNR1_DIR_S5 | PCD_DPWW3_TNR1_DSCR_S5 | PCD_DPWW3_TNR1_DCS_S5 | PCD_DPWW3_TNR1_DSCS_S5 | PCD_DPWW3_TNR1_DPP_S5 | PCD_DPWW3_TNR1_DTPI_S5 | PCD_DPWW3_TNR1_DCI_S5 | PCD_DPWW3_TNR1_DSI_S5 | PCD_DPWW3_TNR1_DER_S5 | PCD_DPWW3_TNR1_RS_S5 | PCD_DPWW3_TNR1_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _S6 |  | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_S6 | PCD_DPWW3_TNR1_DLY_S6 | PCD_DPWW3_TNR1_DIR_S6 | PCD_DPWW3_TNR1_DSCR_S6 | PCD_DPWW3_TNR1_DCS_S6 | PCD_DPWW3_TNR1_DSCS_S6 | PCD_DPWW3_TNR1_DPP_S6 | PCD_DPWW3_TNR1_DTPI_S6 | PCD_DPWW3_TNR1_DCI_S6 | PCD_DPWW3_TNR1_DSI_S6 | PCD_DPWW3_TNR1_DER_S6 | PCD_DPWW3_TNR1_RS_S6 | PCD_DPWW3_TNR1_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.3 |  | _S7 |  | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_S7 | PCD_DPWW3_TNR1_DLY_S7 | PCD_DPWW3_TNR1_DIR_S7 | PCD_DPWW3_TNR1_DSCR_S7 | PCD_DPWW3_TNR1_DCS_S7 | PCD_DPWW3_TNR1_DSCS_S7 | PCD_DPWW3_TNR1_DPP_S7 | PCD_DPWW3_TNR1_DTPI_S7 | PCD_DPWW3_TNR1_DCI_S7 | PCD_DPWW3_TNR1_DSI_S7 | PCD_DPWW3_TNR1_DER_S7 | PCD_DPWW3_TNR1_RS_S7 | PCD_DPWW3_TNR1_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW9 | 0 | Treatment for total nitrogen removal (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.3 |  | _ST |  | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_ST | PCD_DPWW3_TNR1_DLY_ST | PCD_DPWW3_TNR1_DIR_ST | PCD_DPWW3_TNR1_DSCR_ST | PCD_DPWW3_TNR1_DCS_ST | PCD_DPWW3_TNR1_DSCS_ST | PCD_DPWW3_TNR1_DPP_ST | PCD_DPWW3_TNR1_DTPI_ST | PCD_DPWW3_TNR1_DCI_ST | PCD_DPWW3_TNR1_DSI_ST | PCD_DPWW3_TNR1_DER_ST | PCD_DPWW3_TNR1_RS_ST | PCD_DPWW3_TNR1_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | [32 empty] | DPWW3.4 |  | PCD_DPWW3_NBS_SOL | PCD_DPWW3_NBS_SOL_NR | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_S0 | PCD_DPWW3_NBS_SOL_DLY | PCD_DPWW3_NBS_SOL_DIR | PCD_DPWW3_NBS_SOL_DSCR | PCD_DPWW3_NBS_SOL_DCS | PCD_DPWW3_NBS_SOL_DSCS | PCD_DPWW3_NBS_SOL_DPP | PCD_DPWW3_NBS_SOL_DTPI | PCD_DPWW3_NBS_SOL_DCI | PCD_DPWW3_NBS_SOL_DSI | PCD_DPWW3_NBS_SOL_DER | PCD_DPWW3_NBS_SOL_RS | PCD_DPWW3_NBS_SOL_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S1 |  | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_S1 | PCD_DPWW3_NBS_SOL_DLY_S1 | PCD_DPWW3_NBS_SOL_DIR_S1 | PCD_DPWW3_NBS_SOL_DSCR_S1 | PCD_DPWW3_NBS_SOL_DCS_S1 | PCD_DPWW3_NBS_SOL_DSCS_S1 | PCD_DPWW3_NBS_SOL_DPP_S1 | PCD_DPWW3_NBS_SOL_DTPI_S1 | PCD_DPWW3_NBS_SOL_DCI_S1 | PCD_DPWW3_NBS_SOL_DSI_S1 | PCD_DPWW3_NBS_SOL_DER_S1 | PCD_DPWW3_NBS_SOL_RS_S1 | PCD_DPWW3_NBS_SOL_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S2 |  | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_S2 | PCD_DPWW3_NBS_SOL_DLY_S2 | PCD_DPWW3_NBS_SOL_DIR_S2 | PCD_DPWW3_NBS_SOL_DSCR_S2 | PCD_DPWW3_NBS_SOL_DCS_S2 | PCD_DPWW3_NBS_SOL_DSCS_S2 | PCD_DPWW3_NBS_SOL_DPP_S2 | PCD_DPWW3_NBS_SOL_DTPI_S2 | PCD_DPWW3_NBS_SOL_DCI_S2 | PCD_DPWW3_NBS_SOL_DSI_S2 | PCD_DPWW3_NBS_SOL_DER_S2 | PCD_DPWW3_NBS_SOL_RS_S2 | PCD_DPWW3_NBS_SOL_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S3 |  | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_S3 | PCD_DPWW3_NBS_SOL_DLY_S3 | PCD_DPWW3_NBS_SOL_DIR_S3 | PCD_DPWW3_NBS_SOL_DSCR_S3 | PCD_DPWW3_NBS_SOL_DCS_S3 | PCD_DPWW3_NBS_SOL_DSCS_S3 | PCD_DPWW3_NBS_SOL_DPP_S3 | PCD_DPWW3_NBS_SOL_DTPI_S3 | PCD_DPWW3_NBS_SOL_DCI_S3 | PCD_DPWW3_NBS_SOL_DSI_S3 | PCD_DPWW3_NBS_SOL_DER_S3 | PCD_DPWW3_NBS_SOL_RS_S3 | PCD_DPWW3_NBS_SOL_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S4 |  | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_S4 | PCD_DPWW3_NBS_SOL_DLY_S4 | PCD_DPWW3_NBS_SOL_DIR_S4 | PCD_DPWW3_NBS_SOL_DSCR_S4 | PCD_DPWW3_NBS_SOL_DCS_S4 | PCD_DPWW3_NBS_SOL_DSCS_S4 | PCD_DPWW3_NBS_SOL_DPP_S4 | PCD_DPWW3_NBS_SOL_DTPI_S4 | PCD_DPWW3_NBS_SOL_DCI_S4 | PCD_DPWW3_NBS_SOL_DSI_S4 | PCD_DPWW3_NBS_SOL_DER_S4 | PCD_DPWW3_NBS_SOL_RS_S4 | PCD_DPWW3_NBS_SOL_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S5 |  | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_S5 | PCD_DPWW3_NBS_SOL_DLY_S5 | PCD_DPWW3_NBS_SOL_DIR_S5 | PCD_DPWW3_NBS_SOL_DSCR_S5 | PCD_DPWW3_NBS_SOL_DCS_S5 | PCD_DPWW3_NBS_SOL_DSCS_S5 | PCD_DPWW3_NBS_SOL_DPP_S5 | PCD_DPWW3_NBS_SOL_DTPI_S5 | PCD_DPWW3_NBS_SOL_DCI_S5 | PCD_DPWW3_NBS_SOL_DSI_S5 | PCD_DPWW3_NBS_SOL_DER_S5 | PCD_DPWW3_NBS_SOL_RS_S5 | PCD_DPWW3_NBS_SOL_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _S6 |  | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_S6 | PCD_DPWW3_NBS_SOL_DLY_S6 | PCD_DPWW3_NBS_SOL_DIR_S6 | PCD_DPWW3_NBS_SOL_DSCR_S6 | PCD_DPWW3_NBS_SOL_DCS_S6 | PCD_DPWW3_NBS_SOL_DSCS_S6 | PCD_DPWW3_NBS_SOL_DPP_S6 | PCD_DPWW3_NBS_SOL_DTPI_S6 | PCD_DPWW3_NBS_SOL_DCI_S6 | PCD_DPWW3_NBS_SOL_DSI_S6 | PCD_DPWW3_NBS_SOL_DER_S6 | PCD_DPWW3_NBS_SOL_RS_S6 | PCD_DPWW3_NBS_SOL_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.4 |  | _S7 |  | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_S7 | PCD_DPWW3_NBS_SOL_DLY_S7 | PCD_DPWW3_NBS_SOL_DIR_S7 | PCD_DPWW3_NBS_SOL_DSCR_S7 | PCD_DPWW3_NBS_SOL_DCS_S7 | PCD_DPWW3_NBS_SOL_DSCS_S7 | PCD_DPWW3_NBS_SOL_DPP_S7 | PCD_DPWW3_NBS_SOL_DTPI_S7 | PCD_DPWW3_NBS_SOL_DCI_S7 | PCD_DPWW3_NBS_SOL_DSI_S7 | PCD_DPWW3_NBS_SOL_DER_S7 | PCD_DPWW3_NBS_SOL_RS_S7 | PCD_DPWW3_NBS_SOL_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW11 | 0 | Nature based solutions for treatment for nutrients and/or sanitary determinands (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.4 |  | _ST |  | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_ST | PCD_DPWW3_NBS_SOL_DLY_ST | PCD_DPWW3_NBS_SOL_DIR_ST | PCD_DPWW3_NBS_SOL_DSCR_ST | PCD_DPWW3_NBS_SOL_DCS_ST | PCD_DPWW3_NBS_SOL_DSCS_ST | PCD_DPWW3_NBS_SOL_DPP_ST | PCD_DPWW3_NBS_SOL_DTPI_ST | PCD_DPWW3_NBS_SOL_DCI_ST | PCD_DPWW3_NBS_SOL_DSI_ST | PCD_DPWW3_NBS_SOL_DER_ST | PCD_DPWW3_NBS_SOL_RS_ST | PCD_DPWW3_NBS_SOL_DPLE_ST
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | [32 empty] | DPWW3.5 |  | PCD_DPWW3_MBT1 | PCD_DPWW3_MBT1_NR | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_S0 | PCD_DPWW3_MBT1_DLY | PCD_DPWW3_MBT1_DIR | PCD_DPWW3_MBT1_DSCR | PCD_DPWW3_MBT1_DCS | PCD_DPWW3_MBT1_DSCS | PCD_DPWW3_MBT1_DPP | PCD_DPWW3_MBT1_DTPI | PCD_DPWW3_MBT1_DCI | PCD_DPWW3_MBT1_DSI | PCD_DPWW3_MBT1_DER | PCD_DPWW3_MBT1_RS | PCD_DPWW3_MBT1_DPLE
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S1 |  | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_S1 | PCD_DPWW3_MBT1_DLY_S1 | PCD_DPWW3_MBT1_DIR_S1 | PCD_DPWW3_MBT1_DSCR_S1 | PCD_DPWW3_MBT1_DCS_S1 | PCD_DPWW3_MBT1_DSCS_S1 | PCD_DPWW3_MBT1_DPP_S1 | PCD_DPWW3_MBT1_DTPI_S1 | PCD_DPWW3_MBT1_DCI_S1 | PCD_DPWW3_MBT1_DSI_S1 | PCD_DPWW3_MBT1_DER_S1 | PCD_DPWW3_MBT1_RS_S1 | PCD_DPWW3_MBT1_DPLE_S1
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S2 |  | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_S2 | PCD_DPWW3_MBT1_DLY_S2 | PCD_DPWW3_MBT1_DIR_S2 | PCD_DPWW3_MBT1_DSCR_S2 | PCD_DPWW3_MBT1_DCS_S2 | PCD_DPWW3_MBT1_DSCS_S2 | PCD_DPWW3_MBT1_DPP_S2 | PCD_DPWW3_MBT1_DTPI_S2 | PCD_DPWW3_MBT1_DCI_S2 | PCD_DPWW3_MBT1_DSI_S2 | PCD_DPWW3_MBT1_DER_S2 | PCD_DPWW3_MBT1_RS_S2 | PCD_DPWW3_MBT1_DPLE_S2
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S3 |  | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_S3 | PCD_DPWW3_MBT1_DLY_S3 | PCD_DPWW3_MBT1_DIR_S3 | PCD_DPWW3_MBT1_DSCR_S3 | PCD_DPWW3_MBT1_DCS_S3 | PCD_DPWW3_MBT1_DSCS_S3 | PCD_DPWW3_MBT1_DPP_S3 | PCD_DPWW3_MBT1_DTPI_S3 | PCD_DPWW3_MBT1_DCI_S3 | PCD_DPWW3_MBT1_DSI_S3 | PCD_DPWW3_MBT1_DER_S3 | PCD_DPWW3_MBT1_RS_S3 | PCD_DPWW3_MBT1_DPLE_S3
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S4 |  | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_S4 | PCD_DPWW3_MBT1_DLY_S4 | PCD_DPWW3_MBT1_DIR_S4 | PCD_DPWW3_MBT1_DSCR_S4 | PCD_DPWW3_MBT1_DCS_S4 | PCD_DPWW3_MBT1_DSCS_S4 | PCD_DPWW3_MBT1_DPP_S4 | PCD_DPWW3_MBT1_DTPI_S4 | PCD_DPWW3_MBT1_DCI_S4 | PCD_DPWW3_MBT1_DSI_S4 | PCD_DPWW3_MBT1_DER_S4 | PCD_DPWW3_MBT1_RS_S4 | PCD_DPWW3_MBT1_DPLE_S4
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S5 |  | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_S5 | PCD_DPWW3_MBT1_DLY_S5 | PCD_DPWW3_MBT1_DIR_S5 | PCD_DPWW3_MBT1_DSCR_S5 | PCD_DPWW3_MBT1_DCS_S5 | PCD_DPWW3_MBT1_DSCS_S5 | PCD_DPWW3_MBT1_DPP_S5 | PCD_DPWW3_MBT1_DTPI_S5 | PCD_DPWW3_MBT1_DCI_S5 | PCD_DPWW3_MBT1_DSI_S5 | PCD_DPWW3_MBT1_DER_S5 | PCD_DPWW3_MBT1_RS_S5 | PCD_DPWW3_MBT1_DPLE_S5
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _S6 |  | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_S6 | PCD_DPWW3_MBT1_DLY_S6 | PCD_DPWW3_MBT1_DIR_S6 | PCD_DPWW3_MBT1_DSCR_S6 | PCD_DPWW3_MBT1_DCS_S6 | PCD_DPWW3_MBT1_DSCS_S6 | PCD_DPWW3_MBT1_DPP_S6 | PCD_DPWW3_MBT1_DTPI_S6 | PCD_DPWW3_MBT1_DCI_S6 | PCD_DPWW3_MBT1_DSI_S6 | PCD_DPWW3_MBT1_DER_S6 | PCD_DPWW3_MBT1_RS_S6 | PCD_DPWW3_MBT1_DPLE_S6
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.5 |  | _S7 |  | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_S7 | PCD_DPWW3_MBT1_DLY_S7 | PCD_DPWW3_MBT1_DIR_S7 | PCD_DPWW3_MBT1_DSCR_S7 | PCD_DPWW3_MBT1_DCS_S7 | PCD_DPWW3_MBT1_DSCS_S7 | PCD_DPWW3_MBT1_DPP_S7 | PCD_DPWW3_MBT1_DTPI_S7 | PCD_DPWW3_MBT1_DCI_S7 | PCD_DPWW3_MBT1_DSI_S7 | PCD_DPWW3_MBT1_DER_S7 | PCD_DPWW3_MBT1_RS_S7 | PCD_DPWW3_MBT1_DPLE_S7
| TMS | PR24CA111 Wastewater Treatment | PCDWW14 | 0 | Microbiological treatment - bathing waters, coastal and inland (WINEP/NEP) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.5 |  | _ST |  | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_ST | PCD_DPWW3_MBT1_DLY_ST | PCD_DPWW3_MBT1_DIR_ST | PCD_DPWW3_MBT1_DSCR_ST | PCD_DPWW3_MBT1_DCS_ST | PCD_DPWW3_MBT1_DSCS_ST | PCD_DPWW3_MBT1_DPP_ST | PCD_DPWW3_MBT1_DTPI_ST | PCD_DPWW3_MBT1_DCI_ST | PCD_DPWW3_MBT1_DSI_ST | PCD_DPWW3_MBT1_DER_ST | PCD_DPWW3_MBT1_RS_ST | PCD_DPWW3_MBT1_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | [32 empty] | DPWW3.6 |  | PCD_DPWW3_SSCP | PCD_DPWW3_SSCP_NR | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_S0 | PCD_DPWW3_SSCP_DLY | PCD_DPWW3_SSCP_DIR | PCD_DPWW3_SSCP_DSCR | PCD_DPWW3_SSCP_DCS | PCD_DPWW3_SSCP_DSCS | PCD_DPWW3_SSCP_DPP | PCD_DPWW3_SSCP_DTPI | PCD_DPWW3_SSCP_DCI | PCD_DPWW3_SSCP_DSI | PCD_DPWW3_SSCP_DER | PCD_DPWW3_SSCP_RS | PCD_DPWW3_SSCP_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S1 |  | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_S1 | PCD_DPWW3_SSCP_DLY_S1 | PCD_DPWW3_SSCP_DIR_S1 | PCD_DPWW3_SSCP_DSCR_S1 | PCD_DPWW3_SSCP_DCS_S1 | PCD_DPWW3_SSCP_DSCS_S1 | PCD_DPWW3_SSCP_DPP_S1 | PCD_DPWW3_SSCP_DTPI_S1 | PCD_DPWW3_SSCP_DCI_S1 | PCD_DPWW3_SSCP_DSI_S1 | PCD_DPWW3_SSCP_DER_S1 | PCD_DPWW3_SSCP_RS_S1 | PCD_DPWW3_SSCP_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S2 |  | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_S2 | PCD_DPWW3_SSCP_DLY_S2 | PCD_DPWW3_SSCP_DIR_S2 | PCD_DPWW3_SSCP_DSCR_S2 | PCD_DPWW3_SSCP_DCS_S2 | PCD_DPWW3_SSCP_DSCS_S2 | PCD_DPWW3_SSCP_DPP_S2 | PCD_DPWW3_SSCP_DTPI_S2 | PCD_DPWW3_SSCP_DCI_S2 | PCD_DPWW3_SSCP_DSI_S2 | PCD_DPWW3_SSCP_DER_S2 | PCD_DPWW3_SSCP_RS_S2 | PCD_DPWW3_SSCP_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S3 |  | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_S3 | PCD_DPWW3_SSCP_DLY_S3 | PCD_DPWW3_SSCP_DIR_S3 | PCD_DPWW3_SSCP_DSCR_S3 | PCD_DPWW3_SSCP_DCS_S3 | PCD_DPWW3_SSCP_DSCS_S3 | PCD_DPWW3_SSCP_DPP_S3 | PCD_DPWW3_SSCP_DTPI_S3 | PCD_DPWW3_SSCP_DCI_S3 | PCD_DPWW3_SSCP_DSI_S3 | PCD_DPWW3_SSCP_DER_S3 | PCD_DPWW3_SSCP_RS_S3 | PCD_DPWW3_SSCP_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S4 |  | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_S4 | PCD_DPWW3_SSCP_DLY_S4 | PCD_DPWW3_SSCP_DIR_S4 | PCD_DPWW3_SSCP_DSCR_S4 | PCD_DPWW3_SSCP_DCS_S4 | PCD_DPWW3_SSCP_DSCS_S4 | PCD_DPWW3_SSCP_DPP_S4 | PCD_DPWW3_SSCP_DTPI_S4 | PCD_DPWW3_SSCP_DCI_S4 | PCD_DPWW3_SSCP_DSI_S4 | PCD_DPWW3_SSCP_DER_S4 | PCD_DPWW3_SSCP_RS_S4 | PCD_DPWW3_SSCP_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S5 |  | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_S5 | PCD_DPWW3_SSCP_DLY_S5 | PCD_DPWW3_SSCP_DIR_S5 | PCD_DPWW3_SSCP_DSCR_S5 | PCD_DPWW3_SSCP_DCS_S5 | PCD_DPWW3_SSCP_DSCS_S5 | PCD_DPWW3_SSCP_DPP_S5 | PCD_DPWW3_SSCP_DTPI_S5 | PCD_DPWW3_SSCP_DCI_S5 | PCD_DPWW3_SSCP_DSI_S5 | PCD_DPWW3_SSCP_DER_S5 | PCD_DPWW3_SSCP_RS_S5 | PCD_DPWW3_SSCP_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _S6 |  | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_S6 | PCD_DPWW3_SSCP_DLY_S6 | PCD_DPWW3_SSCP_DIR_S6 | PCD_DPWW3_SSCP_DSCR_S6 | PCD_DPWW3_SSCP_DCS_S6 | PCD_DPWW3_SSCP_DSCS_S6 | PCD_DPWW3_SSCP_DPP_S6 | PCD_DPWW3_SSCP_DTPI_S6 | PCD_DPWW3_SSCP_DCI_S6 | PCD_DPWW3_SSCP_DSI_S6 | PCD_DPWW3_SSCP_DER_S6 | PCD_DPWW3_SSCP_RS_S6 | PCD_DPWW3_SSCP_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.6 |  | _S7 |  | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_S7 | PCD_DPWW3_SSCP_DLY_S7 | PCD_DPWW3_SSCP_DIR_S7 | PCD_DPWW3_SSCP_DSCR_S7 | PCD_DPWW3_SSCP_DCS_S7 | PCD_DPWW3_SSCP_DSCS_S7 | PCD_DPWW3_SSCP_DPP_S7 | PCD_DPWW3_SSCP_DTPI_S7 | PCD_DPWW3_SSCP_DCI_S7 | PCD_DPWW3_SSCP_DSI_S7 | PCD_DPWW3_SSCP_DER_S7 | PCD_DPWW3_SSCP_RS_S7 | PCD_DPWW3_SSCP_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW24b | 0 | Sludge storage (cake pads) - Sludge Storage area delivered | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.6 |  | _ST |  | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_ST | PCD_DPWW3_SSCP_DLY_ST | PCD_DPWW3_SSCP_DIR_ST | PCD_DPWW3_SSCP_DSCR_ST | PCD_DPWW3_SSCP_DCS_ST | PCD_DPWW3_SSCP_DSCS_ST | PCD_DPWW3_SSCP_DPP_ST | PCD_DPWW3_SSCP_DTPI_ST | PCD_DPWW3_SSCP_DCI_ST | PCD_DPWW3_SSCP_DSI_ST | PCD_DPWW3_SSCP_DER_ST | PCD_DPWW3_SSCP_RS_ST | PCD_DPWW3_SSCP_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | [32 empty] | DPWW3.7 |  | PCD_DPWW3_STOTH1 | PCD_DPWW3_STOTH1_NR | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_S0 | PCD_DPWW3_STOTH1_DLY | PCD_DPWW3_STOTH1_DIR | PCD_DPWW3_STOTH1_DSCR | PCD_DPWW3_STOTH1_DCS | PCD_DPWW3_STOTH1_DSCS | PCD_DPWW3_STOTH1_DPP | PCD_DPWW3_STOTH1_DTPI | PCD_DPWW3_STOTH1_DCI | PCD_DPWW3_STOTH1_DSI | PCD_DPWW3_STOTH1_DER | PCD_DPWW3_STOTH1_RS | PCD_DPWW3_STOTH1_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S1 |  | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_S1 | PCD_DPWW3_STOTH1_DLY_S1 | PCD_DPWW3_STOTH1_DIR_S1 | PCD_DPWW3_STOTH1_DSCR_S1 | PCD_DPWW3_STOTH1_DCS_S1 | PCD_DPWW3_STOTH1_DSCS_S1 | PCD_DPWW3_STOTH1_DPP_S1 | PCD_DPWW3_STOTH1_DTPI_S1 | PCD_DPWW3_STOTH1_DCI_S1 | PCD_DPWW3_STOTH1_DSI_S1 | PCD_DPWW3_STOTH1_DER_S1 | PCD_DPWW3_STOTH1_RS_S1 | PCD_DPWW3_STOTH1_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S2 |  | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_S2 | PCD_DPWW3_STOTH1_DLY_S2 | PCD_DPWW3_STOTH1_DIR_S2 | PCD_DPWW3_STOTH1_DSCR_S2 | PCD_DPWW3_STOTH1_DCS_S2 | PCD_DPWW3_STOTH1_DSCS_S2 | PCD_DPWW3_STOTH1_DPP_S2 | PCD_DPWW3_STOTH1_DTPI_S2 | PCD_DPWW3_STOTH1_DCI_S2 | PCD_DPWW3_STOTH1_DSI_S2 | PCD_DPWW3_STOTH1_DER_S2 | PCD_DPWW3_STOTH1_RS_S2 | PCD_DPWW3_STOTH1_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S3 |  | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_S3 | PCD_DPWW3_STOTH1_DLY_S3 | PCD_DPWW3_STOTH1_DIR_S3 | PCD_DPWW3_STOTH1_DSCR_S3 | PCD_DPWW3_STOTH1_DCS_S3 | PCD_DPWW3_STOTH1_DSCS_S3 | PCD_DPWW3_STOTH1_DPP_S3 | PCD_DPWW3_STOTH1_DTPI_S3 | PCD_DPWW3_STOTH1_DCI_S3 | PCD_DPWW3_STOTH1_DSI_S3 | PCD_DPWW3_STOTH1_DER_S3 | PCD_DPWW3_STOTH1_RS_S3 | PCD_DPWW3_STOTH1_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S4 |  | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_S4 | PCD_DPWW3_STOTH1_DLY_S4 | PCD_DPWW3_STOTH1_DIR_S4 | PCD_DPWW3_STOTH1_DSCR_S4 | PCD_DPWW3_STOTH1_DCS_S4 | PCD_DPWW3_STOTH1_DSCS_S4 | PCD_DPWW3_STOTH1_DPP_S4 | PCD_DPWW3_STOTH1_DTPI_S4 | PCD_DPWW3_STOTH1_DCI_S4 | PCD_DPWW3_STOTH1_DSI_S4 | PCD_DPWW3_STOTH1_DER_S4 | PCD_DPWW3_STOTH1_RS_S4 | PCD_DPWW3_STOTH1_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S5 |  | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_S5 | PCD_DPWW3_STOTH1_DLY_S5 | PCD_DPWW3_STOTH1_DIR_S5 | PCD_DPWW3_STOTH1_DSCR_S5 | PCD_DPWW3_STOTH1_DCS_S5 | PCD_DPWW3_STOTH1_DSCS_S5 | PCD_DPWW3_STOTH1_DPP_S5 | PCD_DPWW3_STOTH1_DTPI_S5 | PCD_DPWW3_STOTH1_DCI_S5 | PCD_DPWW3_STOTH1_DSI_S5 | PCD_DPWW3_STOTH1_DER_S5 | PCD_DPWW3_STOTH1_RS_S5 | PCD_DPWW3_STOTH1_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _S6 |  | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_S6 | PCD_DPWW3_STOTH1_DLY_S6 | PCD_DPWW3_STOTH1_DIR_S6 | PCD_DPWW3_STOTH1_DSCR_S6 | PCD_DPWW3_STOTH1_DCS_S6 | PCD_DPWW3_STOTH1_DSCS_S6 | PCD_DPWW3_STOTH1_DPP_S6 | PCD_DPWW3_STOTH1_DTPI_S6 | PCD_DPWW3_STOTH1_DCI_S6 | PCD_DPWW3_STOTH1_DSI_S6 | PCD_DPWW3_STOTH1_DER_S6 | PCD_DPWW3_STOTH1_RS_S6 | PCD_DPWW3_STOTH1_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.7 |  | _S7 |  | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_S7 | PCD_DPWW3_STOTH1_DLY_S7 | PCD_DPWW3_STOTH1_DIR_S7 | PCD_DPWW3_STOTH1_DSCR_S7 | PCD_DPWW3_STOTH1_DCS_S7 | PCD_DPWW3_STOTH1_DSCS_S7 | PCD_DPWW3_STOTH1_DPP_S7 | PCD_DPWW3_STOTH1_DTPI_S7 | PCD_DPWW3_STOTH1_DCI_S7 | PCD_DPWW3_STOTH1_DSI_S7 | PCD_DPWW3_STOTH1_DER_S7 | PCD_DPWW3_STOTH1_RS_S7 | PCD_DPWW3_STOTH1_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge throughput Dryer/Pelletiser installed plant capacity | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.7 |  | _ST |  | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_ST | PCD_DPWW3_STOTH1_DLY_ST | PCD_DPWW3_STOTH1_DIR_ST | PCD_DPWW3_STOTH1_DSCR_ST | PCD_DPWW3_STOTH1_DCS_ST | PCD_DPWW3_STOTH1_DSCS_ST | PCD_DPWW3_STOTH1_DPP_ST | PCD_DPWW3_STOTH1_DTPI_ST | PCD_DPWW3_STOTH1_DCI_ST | PCD_DPWW3_STOTH1_DSI_ST | PCD_DPWW3_STOTH1_DER_ST | PCD_DPWW3_STOTH1_RS_ST | PCD_DPWW3_STOTH1_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | [32 empty] | DPWW3.8 |  | PCD_DPWW3_STOTH2 | PCD_DPWW3_STOTH2_NR | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_S0 | PCD_DPWW3_STOTH2_DLY | PCD_DPWW3_STOTH2_DIR | PCD_DPWW3_STOTH2_DSCR | PCD_DPWW3_STOTH2_DCS | PCD_DPWW3_STOTH2_DSCS | PCD_DPWW3_STOTH2_DPP | PCD_DPWW3_STOTH2_DTPI | PCD_DPWW3_STOTH2_DCI | PCD_DPWW3_STOTH2_DSI | PCD_DPWW3_STOTH2_DER | PCD_DPWW3_STOTH2_RS | PCD_DPWW3_STOTH2_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S1 |  | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_S1 | PCD_DPWW3_STOTH2_DLY_S1 | PCD_DPWW3_STOTH2_DIR_S1 | PCD_DPWW3_STOTH2_DSCR_S1 | PCD_DPWW3_STOTH2_DCS_S1 | PCD_DPWW3_STOTH2_DSCS_S1 | PCD_DPWW3_STOTH2_DPP_S1 | PCD_DPWW3_STOTH2_DTPI_S1 | PCD_DPWW3_STOTH2_DCI_S1 | PCD_DPWW3_STOTH2_DSI_S1 | PCD_DPWW3_STOTH2_DER_S1 | PCD_DPWW3_STOTH2_RS_S1 | PCD_DPWW3_STOTH2_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S2 |  | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_S2 | PCD_DPWW3_STOTH2_DLY_S2 | PCD_DPWW3_STOTH2_DIR_S2 | PCD_DPWW3_STOTH2_DSCR_S2 | PCD_DPWW3_STOTH2_DCS_S2 | PCD_DPWW3_STOTH2_DSCS_S2 | PCD_DPWW3_STOTH2_DPP_S2 | PCD_DPWW3_STOTH2_DTPI_S2 | PCD_DPWW3_STOTH2_DCI_S2 | PCD_DPWW3_STOTH2_DSI_S2 | PCD_DPWW3_STOTH2_DER_S2 | PCD_DPWW3_STOTH2_RS_S2 | PCD_DPWW3_STOTH2_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S3 |  | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_S3 | PCD_DPWW3_STOTH2_DLY_S3 | PCD_DPWW3_STOTH2_DIR_S3 | PCD_DPWW3_STOTH2_DSCR_S3 | PCD_DPWW3_STOTH2_DCS_S3 | PCD_DPWW3_STOTH2_DSCS_S3 | PCD_DPWW3_STOTH2_DPP_S3 | PCD_DPWW3_STOTH2_DTPI_S3 | PCD_DPWW3_STOTH2_DCI_S3 | PCD_DPWW3_STOTH2_DSI_S3 | PCD_DPWW3_STOTH2_DER_S3 | PCD_DPWW3_STOTH2_RS_S3 | PCD_DPWW3_STOTH2_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S4 |  | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_S4 | PCD_DPWW3_STOTH2_DLY_S4 | PCD_DPWW3_STOTH2_DIR_S4 | PCD_DPWW3_STOTH2_DSCR_S4 | PCD_DPWW3_STOTH2_DCS_S4 | PCD_DPWW3_STOTH2_DSCS_S4 | PCD_DPWW3_STOTH2_DPP_S4 | PCD_DPWW3_STOTH2_DTPI_S4 | PCD_DPWW3_STOTH2_DCI_S4 | PCD_DPWW3_STOTH2_DSI_S4 | PCD_DPWW3_STOTH2_DER_S4 | PCD_DPWW3_STOTH2_RS_S4 | PCD_DPWW3_STOTH2_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S5 |  | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_S5 | PCD_DPWW3_STOTH2_DLY_S5 | PCD_DPWW3_STOTH2_DIR_S5 | PCD_DPWW3_STOTH2_DSCR_S5 | PCD_DPWW3_STOTH2_DCS_S5 | PCD_DPWW3_STOTH2_DSCS_S5 | PCD_DPWW3_STOTH2_DPP_S5 | PCD_DPWW3_STOTH2_DTPI_S5 | PCD_DPWW3_STOTH2_DCI_S5 | PCD_DPWW3_STOTH2_DSI_S5 | PCD_DPWW3_STOTH2_DER_S5 | PCD_DPWW3_STOTH2_RS_S5 | PCD_DPWW3_STOTH2_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _S6 |  | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_S6 | PCD_DPWW3_STOTH2_DLY_S6 | PCD_DPWW3_STOTH2_DIR_S6 | PCD_DPWW3_STOTH2_DSCR_S6 | PCD_DPWW3_STOTH2_DCS_S6 | PCD_DPWW3_STOTH2_DSCS_S6 | PCD_DPWW3_STOTH2_DPP_S6 | PCD_DPWW3_STOTH2_DTPI_S6 | PCD_DPWW3_STOTH2_DCI_S6 | PCD_DPWW3_STOTH2_DSI_S6 | PCD_DPWW3_STOTH2_DER_S6 | PCD_DPWW3_STOTH2_RS_S6 | PCD_DPWW3_STOTH2_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.8 |  | _S7 |  | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_S7 | PCD_DPWW3_STOTH2_DLY_S7 | PCD_DPWW3_STOTH2_DIR_S7 | PCD_DPWW3_STOTH2_DSCR_S7 | PCD_DPWW3_STOTH2_DCS_S7 | PCD_DPWW3_STOTH2_DSCS_S7 | PCD_DPWW3_STOTH2_DPP_S7 | PCD_DPWW3_STOTH2_DTPI_S7 | PCD_DPWW3_STOTH2_DCI_S7 | PCD_DPWW3_STOTH2_DSI_S7 | PCD_DPWW3_STOTH2_DER_S7 | PCD_DPWW3_STOTH2_RS_S7 | PCD_DPWW3_STOTH2_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW25b | 0 | Sludge treatment (Other) - Sludge Throughput P Recovery installed plant capacity | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.8 |  | _ST |  | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_ST | PCD_DPWW3_STOTH2_DLY_ST | PCD_DPWW3_STOTH2_DIR_ST | PCD_DPWW3_STOTH2_DSCR_ST | PCD_DPWW3_STOTH2_DCS_ST | PCD_DPWW3_STOTH2_DSCS_ST | PCD_DPWW3_STOTH2_DPP_ST | PCD_DPWW3_STOTH2_DTPI_ST | PCD_DPWW3_STOTH2_DCI_ST | PCD_DPWW3_STOTH2_DSI_ST | PCD_DPWW3_STOTH2_DER_ST | PCD_DPWW3_STOTH2_RS_ST | PCD_DPWW3_STOTH2_DPLE_ST
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 0 | Nr | 0 | 25 | 25 | 0 | [31 empty] | DPWW3.9 |  | PCD_DPWW3_BIO_IED | PCD_DPWW3_BIO_IED_NR | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_S0 | PCD_DPWW3_BIO_IED_DLY | PCD_DPWW3_BIO_IED_DIR | PCD_DPWW3_BIO_IED_DSCR | PCD_DPWW3_BIO_IED_DCS | PCD_DPWW3_BIO_IED_DSCS | PCD_DPWW3_BIO_IED_DPP | PCD_DPWW3_BIO_IED_DTPI | PCD_DPWW3_BIO_IED_DCI | PCD_DPWW3_BIO_IED_DSI | PCD_DPWW3_BIO_IED_DER | PCD_DPWW3_BIO_IED_RS | PCD_DPWW3_BIO_IED_DPLE
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 25 | 24 | 24 | 22 | 19 | 19 | 19 | 19 | 19 | 19 | 19 | 18 | 18 | 18 | 18 | 18 | 18 | 16 | 14 | 13 | [12 empty] | DPWW3.9 |  | _S1 |  | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_S1 | PCD_DPWW3_BIO_IED_DLY_S1 | PCD_DPWW3_BIO_IED_DIR_S1 | PCD_DPWW3_BIO_IED_DSCR_S1 | PCD_DPWW3_BIO_IED_DCS_S1 | PCD_DPWW3_BIO_IED_DSCS_S1 | PCD_DPWW3_BIO_IED_DPP_S1 | PCD_DPWW3_BIO_IED_DTPI_S1 | PCD_DPWW3_BIO_IED_DCI_S1 | PCD_DPWW3_BIO_IED_DSI_S1 | PCD_DPWW3_BIO_IED_DER_S1 | PCD_DPWW3_BIO_IED_RS_S1 | PCD_DPWW3_BIO_IED_DPLE_S1
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 1 | 0 | 2 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 5 | 4 | 3 | [12 empty] | DPWW3.9 |  | _S2 |  | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_S2 | PCD_DPWW3_BIO_IED_DLY_S2 | PCD_DPWW3_BIO_IED_DIR_S2 | PCD_DPWW3_BIO_IED_DSCR_S2 | PCD_DPWW3_BIO_IED_DCS_S2 | PCD_DPWW3_BIO_IED_DSCS_S2 | PCD_DPWW3_BIO_IED_DPP_S2 | PCD_DPWW3_BIO_IED_DTPI_S2 | PCD_DPWW3_BIO_IED_DCI_S2 | PCD_DPWW3_BIO_IED_DSI_S2 | PCD_DPWW3_BIO_IED_DER_S2 | PCD_DPWW3_BIO_IED_RS_S2 | PCD_DPWW3_BIO_IED_DPLE_S2
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 1 | 4 | 6 | [12 empty] | DPWW3.9 |  | _S3 |  | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_S3 | PCD_DPWW3_BIO_IED_DLY_S3 | PCD_DPWW3_BIO_IED_DIR_S3 | PCD_DPWW3_BIO_IED_DSCR_S3 | PCD_DPWW3_BIO_IED_DCS_S3 | PCD_DPWW3_BIO_IED_DSCS_S3 | PCD_DPWW3_BIO_IED_DPP_S3 | PCD_DPWW3_BIO_IED_DTPI_S3 | PCD_DPWW3_BIO_IED_DCI_S3 | PCD_DPWW3_BIO_IED_DSI_S3 | PCD_DPWW3_BIO_IED_DER_S3 | PCD_DPWW3_BIO_IED_RS_S3 | PCD_DPWW3_BIO_IED_DPLE_S3
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | [12 empty] | DPWW3.9 |  | _S4 |  | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_S4 | PCD_DPWW3_BIO_IED_DLY_S4 | PCD_DPWW3_BIO_IED_DIR_S4 | PCD_DPWW3_BIO_IED_DSCR_S4 | PCD_DPWW3_BIO_IED_DCS_S4 | PCD_DPWW3_BIO_IED_DSCS_S4 | PCD_DPWW3_BIO_IED_DPP_S4 | PCD_DPWW3_BIO_IED_DTPI_S4 | PCD_DPWW3_BIO_IED_DCI_S4 | PCD_DPWW3_BIO_IED_DSI_S4 | PCD_DPWW3_BIO_IED_DER_S4 | PCD_DPWW3_BIO_IED_RS_S4 | PCD_DPWW3_BIO_IED_DPLE_S4
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | [12 empty] | DPWW3.9 |  | _S5 |  | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_S5 | PCD_DPWW3_BIO_IED_DLY_S5 | PCD_DPWW3_BIO_IED_DIR_S5 | PCD_DPWW3_BIO_IED_DSCR_S5 | PCD_DPWW3_BIO_IED_DCS_S5 | PCD_DPWW3_BIO_IED_DSCS_S5 | PCD_DPWW3_BIO_IED_DPP_S5 | PCD_DPWW3_BIO_IED_DTPI_S5 | PCD_DPWW3_BIO_IED_DCI_S5 | PCD_DPWW3_BIO_IED_DSI_S5 | PCD_DPWW3_BIO_IED_DER_S5 | PCD_DPWW3_BIO_IED_RS_S5 | PCD_DPWW3_BIO_IED_DPLE_S5
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 | [12 empty] | DPWW3.9 |  | _S6 |  | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_S6 | PCD_DPWW3_BIO_IED_DLY_S6 | PCD_DPWW3_BIO_IED_DIR_S6 | PCD_DPWW3_BIO_IED_DSCR_S6 | PCD_DPWW3_BIO_IED_DCS_S6 | PCD_DPWW3_BIO_IED_DSCS_S6 | PCD_DPWW3_BIO_IED_DPP_S6 | PCD_DPWW3_BIO_IED_DTPI_S6 | PCD_DPWW3_BIO_IED_DCI_S6 | PCD_DPWW3_BIO_IED_DSI_S6 | PCD_DPWW3_BIO_IED_DER_S6 | PCD_DPWW3_BIO_IED_RS_S6 | PCD_DPWW3_BIO_IED_DPLE_S6
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.9 |  | _S7 |  | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_S7 | PCD_DPWW3_BIO_IED_DLY_S7 | PCD_DPWW3_BIO_IED_DIR_S7 | PCD_DPWW3_BIO_IED_DSCR_S7 | PCD_DPWW3_BIO_IED_DCS_S7 | PCD_DPWW3_BIO_IED_DSCS_S7 | PCD_DPWW3_BIO_IED_DPP_S7 | PCD_DPWW3_BIO_IED_DTPI_S7 | PCD_DPWW3_BIO_IED_DCI_S7 | PCD_DPWW3_BIO_IED_DSI_S7 | PCD_DPWW3_BIO_IED_DER_S7 | PCD_DPWW3_BIO_IED_RS_S7 | PCD_DPWW3_BIO_IED_DPLE_S7
| TMS | PR24CA114 Wastewater Bioresources | PCDWW30 | Y | Bioresources - IED and Reg changes | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | [12 empty] | DPWW3.9 |  | _ST |  | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_ST | PCD_DPWW3_BIO_IED_DLY_ST | PCD_DPWW3_BIO_IED_DIR_ST | PCD_DPWW3_BIO_IED_DSCR_ST | PCD_DPWW3_BIO_IED_DCS_ST | PCD_DPWW3_BIO_IED_DSCS_ST | PCD_DPWW3_BIO_IED_DPP_ST | PCD_DPWW3_BIO_IED_DTPI_ST | PCD_DPWW3_BIO_IED_DCI_ST | PCD_DPWW3_BIO_IED_DSI_ST | PCD_DPWW3_BIO_IED_DER_ST | PCD_DPWW3_BIO_IED_RS_ST | PCD_DPWW3_BIO_IED_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 0 | Nr | 0 | 105 | 105 | [32 empty] | DPWW3.10 |  | PCD_DPWW3_SOES | PCD_DPWW3_SOES_NR | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_S0 | PCD_DPWW3_SOES_DLY | PCD_DPWW3_SOES_DIR | PCD_DPWW3_SOES_DSCR | PCD_DPWW3_SOES_DCS | PCD_DPWW3_SOES_DSCS | PCD_DPWW3_SOES_DPP | PCD_DPWW3_SOES_DTPI | PCD_DPWW3_SOES_DCI | PCD_DPWW3_SOES_DSI | PCD_DPWW3_SOES_DER | PCD_DPWW3_SOES_RS | PCD_DPWW3_SOES_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 105 | 104 | 99 | 89 | 81 | 75 | 70 | 69 | 53 | 42 | 34 | 10 | 5 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.10 |  | _S1 |  | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_S1 | PCD_DPWW3_SOES_DLY_S1 | PCD_DPWW3_SOES_DIR_S1 | PCD_DPWW3_SOES_DSCR_S1 | PCD_DPWW3_SOES_DCS_S1 | PCD_DPWW3_SOES_DSCS_S1 | PCD_DPWW3_SOES_DPP_S1 | PCD_DPWW3_SOES_DTPI_S1 | PCD_DPWW3_SOES_DCI_S1 | PCD_DPWW3_SOES_DSI_S1 | PCD_DPWW3_SOES_DER_S1 | PCD_DPWW3_SOES_RS_S1 | PCD_DPWW3_SOES_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 1 | 6 | 16 | 20 | 24 | 20 | 14 | 20 | 27 | 22 | 42 | 38 | 23 | 13 | 6 | 4 | 1 | 0 | 0 | [12 empty] | DPWW3.10 |  | _S2 |  | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_S2 | PCD_DPWW3_SOES_DLY_S2 | PCD_DPWW3_SOES_DIR_S2 | PCD_DPWW3_SOES_DSCR_S2 | PCD_DPWW3_SOES_DCS_S2 | PCD_DPWW3_SOES_DSCS_S2 | PCD_DPWW3_SOES_DPP_S2 | PCD_DPWW3_SOES_DTPI_S2 | PCD_DPWW3_SOES_DCI_S2 | PCD_DPWW3_SOES_DSI_S2 | PCD_DPWW3_SOES_DER_S2 | PCD_DPWW3_SOES_RS_S2 | PCD_DPWW3_SOES_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 4 | 3 | 9 | 11 | 16 | 9 | 16 | 8 | 12 | 17 | 14 | 18 | 13 | 11 | 2 | 0 | [12 empty] | DPWW3.10 |  | _S3 |  | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_S3 | PCD_DPWW3_SOES_DLY_S3 | PCD_DPWW3_SOES_DIR_S3 | PCD_DPWW3_SOES_DSCR_S3 | PCD_DPWW3_SOES_DCS_S3 | PCD_DPWW3_SOES_DSCS_S3 | PCD_DPWW3_SOES_DPP_S3 | PCD_DPWW3_SOES_DTPI_S3 | PCD_DPWW3_SOES_DCI_S3 | PCD_DPWW3_SOES_DSI_S3 | PCD_DPWW3_SOES_DER_S3 | PCD_DPWW3_SOES_RS_S3 | PCD_DPWW3_SOES_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 8 | 12 | 19 | 22 | 28 | 31 | 28 | 32 | 37 | 41 | 38 | 42 | 32 | [12 empty] | DPWW3.10 |  | _S4 |  | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_S4 | PCD_DPWW3_SOES_DLY_S4 | PCD_DPWW3_SOES_DIR_S4 | PCD_DPWW3_SOES_DSCR_S4 | PCD_DPWW3_SOES_DCS_S4 | PCD_DPWW3_SOES_DSCS_S4 | PCD_DPWW3_SOES_DPP_S4 | PCD_DPWW3_SOES_DTPI_S4 | PCD_DPWW3_SOES_DCI_S4 | PCD_DPWW3_SOES_DSI_S4 | PCD_DPWW3_SOES_DER_S4 | PCD_DPWW3_SOES_RS_S4 | PCD_DPWW3_SOES_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 1 | 5 | 8 | 0 | 2 | 16 | 25 | 0 | 3 | 11 | 17 | 0 | [12 empty] | DPWW3.10 |  | _S5 |  | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_S5 | PCD_DPWW3_SOES_DLY_S5 | PCD_DPWW3_SOES_DIR_S5 | PCD_DPWW3_SOES_DSCR_S5 | PCD_DPWW3_SOES_DCS_S5 | PCD_DPWW3_SOES_DSCS_S5 | PCD_DPWW3_SOES_DPP_S5 | PCD_DPWW3_SOES_DTPI_S5 | PCD_DPWW3_SOES_DCI_S5 | PCD_DPWW3_SOES_DSI_S5 | PCD_DPWW3_SOES_DER_S5 | PCD_DPWW3_SOES_RS_S5 | PCD_DPWW3_SOES_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 17 | 17 | 17 | 17 | 44 | 44 | 44 | 44 | 73 | [12 empty] | DPWW3.10 |  | _S6 |  | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_S6 | PCD_DPWW3_SOES_DLY_S6 | PCD_DPWW3_SOES_DIR_S6 | PCD_DPWW3_SOES_DSCR_S6 | PCD_DPWW3_SOES_DCS_S6 | PCD_DPWW3_SOES_DSCS_S6 | PCD_DPWW3_SOES_DPP_S6 | PCD_DPWW3_SOES_DTPI_S6 | PCD_DPWW3_SOES_DCI_S6 | PCD_DPWW3_SOES_DSI_S6 | PCD_DPWW3_SOES_DER_S6 | PCD_DPWW3_SOES_RS_S6 | PCD_DPWW3_SOES_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.10 |  | _S7 |  | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_S7 | PCD_DPWW3_SOES_DLY_S7 | PCD_DPWW3_SOES_DIR_S7 | PCD_DPWW3_SOES_DSCR_S7 | PCD_DPWW3_SOES_DCS_S7 | PCD_DPWW3_SOES_DSCS_S7 | PCD_DPWW3_SOES_DPP_S7 | PCD_DPWW3_SOES_DTPI_S7 | PCD_DPWW3_SOES_DCI_S7 | PCD_DPWW3_SOES_DSI_S7 | PCD_DPWW3_SOES_DER_S7 | PCD_DPWW3_SOES_RS_S7 | PCD_DPWW3_SOES_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW5 | Y | Storm overflows - Equivalent storage | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | 105 | [12 empty] | DPWW3.10 |  | _ST |  | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_ST | PCD_DPWW3_SOES_DLY_ST | PCD_DPWW3_SOES_DIR_ST | PCD_DPWW3_SOES_DSCR_ST | PCD_DPWW3_SOES_DCS_ST | PCD_DPWW3_SOES_DSCS_ST | PCD_DPWW3_SOES_DPP_ST | PCD_DPWW3_SOES_DTPI_ST | PCD_DPWW3_SOES_DCI_ST | PCD_DPWW3_SOES_DSI_ST | PCD_DPWW3_SOES_DER_ST | PCD_DPWW3_SOES_RS_ST | PCD_DPWW3_SOES_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 0 | Nr | 0 | 17 | 17 | [32 empty] | DPWW3.11 |  | PCD_DPWW3_FTFT | PCD_DPWW3_FTFT_NR | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_S0 | PCD_DPWW3_FTFT_DLY | PCD_DPWW3_FTFT_DIR | PCD_DPWW3_FTFT_DSCR | PCD_DPWW3_FTFT_DCS | PCD_DPWW3_FTFT_DSCS | PCD_DPWW3_FTFT_DPP | PCD_DPWW3_FTFT_DTPI | PCD_DPWW3_FTFT_DCI | PCD_DPWW3_FTFT_DSI | PCD_DPWW3_FTFT_DER | PCD_DPWW3_FTFT_RS | PCD_DPWW3_FTFT_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 17 | 16 | 15 | 15 | 14 | 13 | 12 | 12 | 12 | 8 | 4 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.11 |  | _S1 |  | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_S1 | PCD_DPWW3_FTFT_DLY_S1 | PCD_DPWW3_FTFT_DIR_S1 | PCD_DPWW3_FTFT_DSCR_S1 | PCD_DPWW3_FTFT_DCS_S1 | PCD_DPWW3_FTFT_DSCS_S1 | PCD_DPWW3_FTFT_DPP_S1 | PCD_DPWW3_FTFT_DTPI_S1 | PCD_DPWW3_FTFT_DCI_S1 | PCD_DPWW3_FTFT_DSI_S1 | PCD_DPWW3_FTFT_DER_S1 | PCD_DPWW3_FTFT_RS_S1 | PCD_DPWW3_FTFT_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 1 | 2 | 2 | 3 | 3 | 3 | 3 | 1 | 5 | 8 | 8 | 8 | 4 | 1 | 1 | 1 | 0 | 0 | 0 | [12 empty] | DPWW3.11 |  | _S2 |  | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_S2 | PCD_DPWW3_FTFT_DLY_S2 | PCD_DPWW3_FTFT_DIR_S2 | PCD_DPWW3_FTFT_DSCR_S2 | PCD_DPWW3_FTFT_DCS_S2 | PCD_DPWW3_FTFT_DSCS_S2 | PCD_DPWW3_FTFT_DPP_S2 | PCD_DPWW3_FTFT_DTPI_S2 | PCD_DPWW3_FTFT_DCI_S2 | PCD_DPWW3_FTFT_DSI_S2 | PCD_DPWW3_FTFT_DER_S2 | PCD_DPWW3_FTFT_RS_S2 | PCD_DPWW3_FTFT_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | 2 | 2 | 3 | 2 | 4 | 6 | 6 | 3 | 1 | 0 | 0 | [12 empty] | DPWW3.11 |  | _S3 |  | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_S3 | PCD_DPWW3_FTFT_DLY_S3 | PCD_DPWW3_FTFT_DIR_S3 | PCD_DPWW3_FTFT_DSCR_S3 | PCD_DPWW3_FTFT_DCS_S3 | PCD_DPWW3_FTFT_DSCS_S3 | PCD_DPWW3_FTFT_DPP_S3 | PCD_DPWW3_FTFT_DTPI_S3 | PCD_DPWW3_FTFT_DCI_S3 | PCD_DPWW3_FTFT_DSI_S3 | PCD_DPWW3_FTFT_DER_S3 | PCD_DPWW3_FTFT_RS_S3 | PCD_DPWW3_FTFT_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 3 | 4 | 5 | 7 | 7 | 8 | 10 | 12 | 12 | 9 | [12 empty] | DPWW3.11 |  | _S4 |  | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_S4 | PCD_DPWW3_FTFT_DLY_S4 | PCD_DPWW3_FTFT_DIR_S4 | PCD_DPWW3_FTFT_DSCR_S4 | PCD_DPWW3_FTFT_DCS_S4 | PCD_DPWW3_FTFT_DSCS_S4 | PCD_DPWW3_FTFT_DPP_S4 | PCD_DPWW3_FTFT_DTPI_S4 | PCD_DPWW3_FTFT_DCI_S4 | PCD_DPWW3_FTFT_DSI_S4 | PCD_DPWW3_FTFT_DER_S4 | PCD_DPWW3_FTFT_RS_S4 | PCD_DPWW3_FTFT_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 2 | 3 | 0 | [12 empty] | DPWW3.11 |  | _S5 |  | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_S5 | PCD_DPWW3_FTFT_DLY_S5 | PCD_DPWW3_FTFT_DIR_S5 | PCD_DPWW3_FTFT_DSCR_S5 | PCD_DPWW3_FTFT_DCS_S5 | PCD_DPWW3_FTFT_DSCS_S5 | PCD_DPWW3_FTFT_DPP_S5 | PCD_DPWW3_FTFT_DTPI_S5 | PCD_DPWW3_FTFT_DCI_S5 | PCD_DPWW3_FTFT_DSI_S5 | PCD_DPWW3_FTFT_DER_S5 | PCD_DPWW3_FTFT_RS_S5 | PCD_DPWW3_FTFT_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 8 | [12 empty] | DPWW3.11 |  | _S6 |  | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_S6 | PCD_DPWW3_FTFT_DLY_S6 | PCD_DPWW3_FTFT_DIR_S6 | PCD_DPWW3_FTFT_DSCR_S6 | PCD_DPWW3_FTFT_DCS_S6 | PCD_DPWW3_FTFT_DSCS_S6 | PCD_DPWW3_FTFT_DPP_S6 | PCD_DPWW3_FTFT_DTPI_S6 | PCD_DPWW3_FTFT_DCI_S6 | PCD_DPWW3_FTFT_DSI_S6 | PCD_DPWW3_FTFT_DER_S6 | PCD_DPWW3_FTFT_RS_S6 | PCD_DPWW3_FTFT_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.11 |  | _S7 |  | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_S7 | PCD_DPWW3_FTFT_DLY_S7 | PCD_DPWW3_FTFT_DIR_S7 | PCD_DPWW3_FTFT_DSCR_S7 | PCD_DPWW3_FTFT_DCS_S7 | PCD_DPWW3_FTFT_DSCS_S7 | PCD_DPWW3_FTFT_DPP_S7 | PCD_DPWW3_FTFT_DTPI_S7 | PCD_DPWW3_FTFT_DCI_S7 | PCD_DPWW3_FTFT_DSI_S7 | PCD_DPWW3_FTFT_DER_S7 | PCD_DPWW3_FTFT_RS_S7 | PCD_DPWW3_FTFT_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW4 | Y | Flow to Full Treatment | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | 17 | [12 empty] | DPWW3.11 |  | _ST |  | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_ST | PCD_DPWW3_FTFT_DLY_ST | PCD_DPWW3_FTFT_DIR_ST | PCD_DPWW3_FTFT_DSCR_ST | PCD_DPWW3_FTFT_DCS_ST | PCD_DPWW3_FTFT_DSCS_ST | PCD_DPWW3_FTFT_DPP_ST | PCD_DPWW3_FTFT_DTPI_ST | PCD_DPWW3_FTFT_DCI_ST | PCD_DPWW3_FTFT_DSI_ST | PCD_DPWW3_FTFT_DER_ST | PCD_DPWW3_FTFT_RS_ST | PCD_DPWW3_FTFT_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 0 | Nr | 0 | 98 | 97 | [32 empty] | DPWW3.12 |  | PCD_DPWW3_PRMVL | PCD_DPWW3_PRMVL_NR | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_S0 | PCD_DPWW3_PRMVL_DLY | PCD_DPWW3_PRMVL_DIR | PCD_DPWW3_PRMVL_DSCR | PCD_DPWW3_PRMVL_DCS | PCD_DPWW3_PRMVL_DSCS | PCD_DPWW3_PRMVL_DPP | PCD_DPWW3_PRMVL_DTPI | PCD_DPWW3_PRMVL_DCI | PCD_DPWW3_PRMVL_DSI | PCD_DPWW3_PRMVL_DER | PCD_DPWW3_PRMVL_RS | PCD_DPWW3_PRMVL_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 1 | Nr | 0 |  | 1 | 82 | 75 | 72 | 65 | 59 | 56 | 56 | 48 | 41 | 25 | 22 | 18 | 11 | 6 | 6 | 6 | 4 | 1 | 1 | 1 | [12 empty] | DPWW3.12 |  | _S1 |  | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_S1 | PCD_DPWW3_PRMVL_DLY_S1 | PCD_DPWW3_PRMVL_DIR_S1 | PCD_DPWW3_PRMVL_DSCR_S1 | PCD_DPWW3_PRMVL_DCS_S1 | PCD_DPWW3_PRMVL_DSCS_S1 | PCD_DPWW3_PRMVL_DPP_S1 | PCD_DPWW3_PRMVL_DTPI_S1 | PCD_DPWW3_PRMVL_DCI_S1 | PCD_DPWW3_PRMVL_DSI_S1 | PCD_DPWW3_PRMVL_DER_S1 | PCD_DPWW3_PRMVL_RS_S1 | PCD_DPWW3_PRMVL_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 10 | 17 | 19 | 20 | 16 | 19 | 14 | 12 | 17 | 31 | 33 | 27 | 15 | 19 | 17 | 4 | 4 | 6 | 5 | 3 | [12 empty] | DPWW3.12 |  | _S2 |  | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_S2 | PCD_DPWW3_PRMVL_DLY_S2 | PCD_DPWW3_PRMVL_DIR_S2 | PCD_DPWW3_PRMVL_DSCR_S2 | PCD_DPWW3_PRMVL_DCS_S2 | PCD_DPWW3_PRMVL_DSCS_S2 | PCD_DPWW3_PRMVL_DPP_S2 | PCD_DPWW3_PRMVL_DTPI_S2 | PCD_DPWW3_PRMVL_DCI_S2 | PCD_DPWW3_PRMVL_DSI_S2 | PCD_DPWW3_PRMVL_DER_S2 | PCD_DPWW3_PRMVL_RS_S2 | PCD_DPWW3_PRMVL_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 3 | 3 | 4 | 7 | 17 | 11 | 12 | 15 | 12 | 4 | 3 | 12 | 31 | 21 | 4 | 14 | 14 | 3 | 2 | 3 | [12 empty] | DPWW3.12 |  | _S3 |  | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_S3 | PCD_DPWW3_PRMVL_DLY_S3 | PCD_DPWW3_PRMVL_DIR_S3 | PCD_DPWW3_PRMVL_DSCR_S3 | PCD_DPWW3_PRMVL_DCS_S3 | PCD_DPWW3_PRMVL_DSCS_S3 | PCD_DPWW3_PRMVL_DPP_S3 | PCD_DPWW3_PRMVL_DTPI_S3 | PCD_DPWW3_PRMVL_DCI_S3 | PCD_DPWW3_PRMVL_DSI_S3 | PCD_DPWW3_PRMVL_DER_S3 | PCD_DPWW3_PRMVL_RS_S3 | PCD_DPWW3_PRMVL_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 2 | 2 | 2 | 5 | 5 | 11 | 15 | 22 | 27 | 37 | 36 | 37 | 37 | 48 | 46 | 42 | 44 | 56 | 42 | 41 | [12 empty] | DPWW3.12 |  | _S4 |  | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_S4 | PCD_DPWW3_PRMVL_DLY_S4 | PCD_DPWW3_PRMVL_DIR_S4 | PCD_DPWW3_PRMVL_DSCR_S4 | PCD_DPWW3_PRMVL_DCS_S4 | PCD_DPWW3_PRMVL_DSCS_S4 | PCD_DPWW3_PRMVL_DPP_S4 | PCD_DPWW3_PRMVL_DTPI_S4 | PCD_DPWW3_PRMVL_DCI_S4 | PCD_DPWW3_PRMVL_DSI_S4 | PCD_DPWW3_PRMVL_DER_S4 | PCD_DPWW3_PRMVL_RS_S4 | PCD_DPWW3_PRMVL_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 3 | 3 | 24 | 26 | 26 | 26 | 42 | 17 | [12 empty] | DPWW3.12 |  | _S5 |  | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_S5 | PCD_DPWW3_PRMVL_DLY_S5 | PCD_DPWW3_PRMVL_DIR_S5 | PCD_DPWW3_PRMVL_DSCR_S5 | PCD_DPWW3_PRMVL_DCS_S5 | PCD_DPWW3_PRMVL_DSCS_S5 | PCD_DPWW3_PRMVL_DPP_S5 | PCD_DPWW3_PRMVL_DTPI_S5 | PCD_DPWW3_PRMVL_DCI_S5 | PCD_DPWW3_PRMVL_DSI_S5 | PCD_DPWW3_PRMVL_DER_S5 | PCD_DPWW3_PRMVL_RS_S5 | PCD_DPWW3_PRMVL_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 6 | 6 | 6 | 6 | 33 | [12 empty] | DPWW3.12 |  | _S6 |  | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_S6 | PCD_DPWW3_PRMVL_DLY_S6 | PCD_DPWW3_PRMVL_DIR_S6 | PCD_DPWW3_PRMVL_DSCR_S6 | PCD_DPWW3_PRMVL_DCS_S6 | PCD_DPWW3_PRMVL_DSCS_S6 | PCD_DPWW3_PRMVL_DPP_S6 | PCD_DPWW3_PRMVL_DTPI_S6 | PCD_DPWW3_PRMVL_DCI_S6 | PCD_DPWW3_PRMVL_DSI_S6 | PCD_DPWW3_PRMVL_DER_S6 | PCD_DPWW3_PRMVL_RS_S6 | PCD_DPWW3_PRMVL_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.12 |  | _S7 |  | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_S7 | PCD_DPWW3_PRMVL_DLY_S7 | PCD_DPWW3_PRMVL_DIR_S7 | PCD_DPWW3_PRMVL_DSCR_S7 | PCD_DPWW3_PRMVL_DCS_S7 | PCD_DPWW3_PRMVL_DSCS_S7 | PCD_DPWW3_PRMVL_DPP_S7 | PCD_DPWW3_PRMVL_DTPI_S7 | PCD_DPWW3_PRMVL_DCI_S7 | PCD_DPWW3_PRMVL_DSI_S7 | PCD_DPWW3_PRMVL_DER_S7 | PCD_DPWW3_PRMVL_RS_S7 | PCD_DPWW3_PRMVL_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW10 | Y | P-removal | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | 98 | [12 empty] | DPWW3.12 |  | _ST |  | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_ST | PCD_DPWW3_PRMVL_DLY_ST | PCD_DPWW3_PRMVL_DIR_ST | PCD_DPWW3_PRMVL_DSCR_ST | PCD_DPWW3_PRMVL_DCS_ST | PCD_DPWW3_PRMVL_DSCS_ST | PCD_DPWW3_PRMVL_DPP_ST | PCD_DPWW3_PRMVL_DTPI_ST | PCD_DPWW3_PRMVL_DCI_ST | PCD_DPWW3_PRMVL_DSI_ST | PCD_DPWW3_PRMVL_DER_ST | PCD_DPWW3_PRMVL_RS_ST | PCD_DPWW3_PRMVL_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 0 | Nr | 0 | 15 | 15 | [32 empty] | DPWW3.13 |  | PCD_DPWW3_GSTW | PCD_DPWW3_GSTW_NR | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_S0 | PCD_DPWW3_GSTW_DLY | PCD_DPWW3_GSTW_DIR | PCD_DPWW3_GSTW_DSCR | PCD_DPWW3_GSTW_DCS | PCD_DPWW3_GSTW_DSCS | PCD_DPWW3_GSTW_DPP | PCD_DPWW3_GSTW_DTPI | PCD_DPWW3_GSTW_DCI | PCD_DPWW3_GSTW_DSI | PCD_DPWW3_GSTW_DER | PCD_DPWW3_GSTW_RS | PCD_DPWW3_GSTW_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 14 | 11 | 9 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 5 | 5 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | [12 empty] | DPWW3.13 |  | _S1 |  | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_S1 | PCD_DPWW3_GSTW_DLY_S1 | PCD_DPWW3_GSTW_DIR_S1 | PCD_DPWW3_GSTW_DSCR_S1 | PCD_DPWW3_GSTW_DCS_S1 | PCD_DPWW3_GSTW_DSCS_S1 | PCD_DPWW3_GSTW_DPP_S1 | PCD_DPWW3_GSTW_DTPI_S1 | PCD_DPWW3_GSTW_DCI_S1 | PCD_DPWW3_GSTW_DSI_S1 | PCD_DPWW3_GSTW_DER_S1 | PCD_DPWW3_GSTW_RS_S1 | PCD_DPWW3_GSTW_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 1 | 4 | 6 | 7 | 3 | 3 | 3 | 2 | 0 | 0 | 0 | 2 | 2 | 3 | 3 | 1 | 1 | 1 | 2 | 2 | [12 empty] | DPWW3.13 |  | _S2 |  | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_S2 | PCD_DPWW3_GSTW_DLY_S2 | PCD_DPWW3_GSTW_DIR_S2 | PCD_DPWW3_GSTW_DSCR_S2 | PCD_DPWW3_GSTW_DCS_S2 | PCD_DPWW3_GSTW_DSCS_S2 | PCD_DPWW3_GSTW_DPP_S2 | PCD_DPWW3_GSTW_DTPI_S2 | PCD_DPWW3_GSTW_DCI_S2 | PCD_DPWW3_GSTW_DSI_S2 | PCD_DPWW3_GSTW_DER_S2 | PCD_DPWW3_GSTW_RS_S2 | PCD_DPWW3_GSTW_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 1 | 5 | 4 | 0 | 1 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 2 | 3 | 2 | 1 | 2 | [12 empty] | DPWW3.13 |  | _S3 |  | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_S3 | PCD_DPWW3_GSTW_DLY_S3 | PCD_DPWW3_GSTW_DIR_S3 | PCD_DPWW3_GSTW_DSCR_S3 | PCD_DPWW3_GSTW_DCS_S3 | PCD_DPWW3_GSTW_DSCS_S3 | PCD_DPWW3_GSTW_DPP_S3 | PCD_DPWW3_GSTW_DTPI_S3 | PCD_DPWW3_GSTW_DCI_S3 | PCD_DPWW3_GSTW_DSI_S3 | PCD_DPWW3_GSTW_DER_S3 | PCD_DPWW3_GSTW_RS_S3 | PCD_DPWW3_GSTW_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 5 | 5 | 5 | 6 | 8 | 8 | 8 | 8 | 3 | 2 | 2 | 4 | 3 | 3 | [12 empty] | DPWW3.13 |  | _S4 |  | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_S4 | PCD_DPWW3_GSTW_DLY_S4 | PCD_DPWW3_GSTW_DIR_S4 | PCD_DPWW3_GSTW_DSCR_S4 | PCD_DPWW3_GSTW_DCS_S4 | PCD_DPWW3_GSTW_DSCS_S4 | PCD_DPWW3_GSTW_DPP_S4 | PCD_DPWW3_GSTW_DTPI_S4 | PCD_DPWW3_GSTW_DCI_S4 | PCD_DPWW3_GSTW_DSI_S4 | PCD_DPWW3_GSTW_DER_S4 | PCD_DPWW3_GSTW_RS_S4 | PCD_DPWW3_GSTW_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 6 | 6 | 6 | 8 | 1 | [12 empty] | DPWW3.13 |  | _S5 |  | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_S5 | PCD_DPWW3_GSTW_DLY_S5 | PCD_DPWW3_GSTW_DIR_S5 | PCD_DPWW3_GSTW_DSCR_S5 | PCD_DPWW3_GSTW_DCS_S5 | PCD_DPWW3_GSTW_DSCS_S5 | PCD_DPWW3_GSTW_DPP_S5 | PCD_DPWW3_GSTW_DTPI_S5 | PCD_DPWW3_GSTW_DCI_S5 | PCD_DPWW3_GSTW_DSI_S5 | PCD_DPWW3_GSTW_DER_S5 | PCD_DPWW3_GSTW_RS_S5 | PCD_DPWW3_GSTW_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | [12 empty] | DPWW3.13 |  | _S6 |  | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_S6 | PCD_DPWW3_GSTW_DLY_S6 | PCD_DPWW3_GSTW_DIR_S6 | PCD_DPWW3_GSTW_DSCR_S6 | PCD_DPWW3_GSTW_DCS_S6 | PCD_DPWW3_GSTW_DSCS_S6 | PCD_DPWW3_GSTW_DPP_S6 | PCD_DPWW3_GSTW_DTPI_S6 | PCD_DPWW3_GSTW_DCI_S6 | PCD_DPWW3_GSTW_DSI_S6 | PCD_DPWW3_GSTW_DER_S6 | PCD_DPWW3_GSTW_RS_S6 | PCD_DPWW3_GSTW_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.13 |  | _S7 |  | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_S7 | PCD_DPWW3_GSTW_DLY_S7 | PCD_DPWW3_GSTW_DIR_S7 | PCD_DPWW3_GSTW_DSCR_S7 | PCD_DPWW3_GSTW_DCS_S7 | PCD_DPWW3_GSTW_DSCS_S7 | PCD_DPWW3_GSTW_DPP_S7 | PCD_DPWW3_GSTW_DTPI_S7 | PCD_DPWW3_GSTW_DCI_S7 | PCD_DPWW3_GSTW_DSI_S7 | PCD_DPWW3_GSTW_DER_S7 | PCD_DPWW3_GSTW_RS_S7 | PCD_DPWW3_GSTW_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW27 | Y | Growth to Sewerage Treatment Works | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | [12 empty] | DPWW3.13 |  | _ST |  | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_ST | PCD_DPWW3_GSTW_DLY_ST | PCD_DPWW3_GSTW_DIR_ST | PCD_DPWW3_GSTW_DSCR_ST | PCD_DPWW3_GSTW_DCS_ST | PCD_DPWW3_GSTW_DSCS_ST | PCD_DPWW3_GSTW_DPP_ST | PCD_DPWW3_GSTW_DTPI_ST | PCD_DPWW3_GSTW_DCI_ST | PCD_DPWW3_GSTW_DSI_ST | PCD_DPWW3_GSTW_DER_ST | PCD_DPWW3_GSTW_RS_ST | PCD_DPWW3_GSTW_DPLE_ST
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 0 | Nr | 0 | 21 | 20 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | [13 empty] | DPWW3.14 |  | PCD_DPWW3_TTSP | PCD_DPWW3_TTSP_NR | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_S0 | PCD_DPWW3_TTSP_DLY | PCD_DPWW3_TTSP_DIR | PCD_DPWW3_TTSP_DSCR | PCD_DPWW3_TTSP_DCS | PCD_DPWW3_TTSP_DSCS | PCD_DPWW3_TTSP_DPP | PCD_DPWW3_TTSP_DTPI | PCD_DPWW3_TTSP_DCI | PCD_DPWW3_TTSP_DSI | PCD_DPWW3_TTSP_DER | PCD_DPWW3_TTSP_RS | PCD_DPWW3_TTSP_DPLE
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 1 | Nr | 0 |  | 1 | 12 | 11 | 10 | 9 | 5 | 4 | 4 | 4 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.14 |  | _S1 |  | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_S1 | PCD_DPWW3_TTSP_DLY_S1 | PCD_DPWW3_TTSP_DIR_S1 | PCD_DPWW3_TTSP_DSCR_S1 | PCD_DPWW3_TTSP_DCS_S1 | PCD_DPWW3_TTSP_DSCS_S1 | PCD_DPWW3_TTSP_DPP_S1 | PCD_DPWW3_TTSP_DTPI_S1 | PCD_DPWW3_TTSP_DCI_S1 | PCD_DPWW3_TTSP_DSI_S1 | PCD_DPWW3_TTSP_DER_S1 | PCD_DPWW3_TTSP_RS_S1 | PCD_DPWW3_TTSP_DPLE_S1
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 2 | 3 | 4 | 3 | 6 | 6 | 6 | 1 | 3 | 3 | 3 | 2 | 3 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.14 |  | _S2 |  | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_S2 | PCD_DPWW3_TTSP_DLY_S2 | PCD_DPWW3_TTSP_DIR_S2 | PCD_DPWW3_TTSP_DSCR_S2 | PCD_DPWW3_TTSP_DCS_S2 | PCD_DPWW3_TTSP_DSCS_S2 | PCD_DPWW3_TTSP_DPP_S2 | PCD_DPWW3_TTSP_DTPI_S2 | PCD_DPWW3_TTSP_DCI_S2 | PCD_DPWW3_TTSP_DSI_S2 | PCD_DPWW3_TTSP_DER_S2 | PCD_DPWW3_TTSP_RS_S2 | PCD_DPWW3_TTSP_DPLE_S2
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 2 | 2 | 1 | 2 | 3 | 2 | 0 | 5 | 5 | 1 | 1 | 2 | 2 | 1 | 0 | 2 | 2 | 1 | 0 | 0 | [12 empty] | DPWW3.14 |  | _S3 |  | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_S3 | PCD_DPWW3_TTSP_DLY_S3 | PCD_DPWW3_TTSP_DIR_S3 | PCD_DPWW3_TTSP_DSCR_S3 | PCD_DPWW3_TTSP_DCS_S3 | PCD_DPWW3_TTSP_DSCS_S3 | PCD_DPWW3_TTSP_DPP_S3 | PCD_DPWW3_TTSP_DTPI_S3 | PCD_DPWW3_TTSP_DCI_S3 | PCD_DPWW3_TTSP_DSI_S3 | PCD_DPWW3_TTSP_DER_S3 | PCD_DPWW3_TTSP_RS_S3 | PCD_DPWW3_TTSP_DPLE_S3
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 4 | 4 | 4 | 4 | 4 | 6 | 7 | 7 | 7 | 11 | 8 | 9 | 9 | 11 | 7 | 6 | 6 | 7 | 5 | 5 | [12 empty] | DPWW3.14 |  | _S4 |  | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_S4 | PCD_DPWW3_TTSP_DLY_S4 | PCD_DPWW3_TTSP_DIR_S4 | PCD_DPWW3_TTSP_DSCR_S4 | PCD_DPWW3_TTSP_DCS_S4 | PCD_DPWW3_TTSP_DSCS_S4 | PCD_DPWW3_TTSP_DPP_S4 | PCD_DPWW3_TTSP_DTPI_S4 | PCD_DPWW3_TTSP_DCI_S4 | PCD_DPWW3_TTSP_DSI_S4 | PCD_DPWW3_TTSP_DER_S4 | PCD_DPWW3_TTSP_RS_S4 | PCD_DPWW3_TTSP_DPLE_S4
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 1 | 2 | 2 | 2 | 3 | 1 | 1 | 1 | 4 | 3 | 3 | 3 | 8 | 6 | 6 | 6 | 9 | 3 | [12 empty] | DPWW3.14 |  | _S5 |  | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_S5 | PCD_DPWW3_TTSP_DLY_S5 | PCD_DPWW3_TTSP_DIR_S5 | PCD_DPWW3_TTSP_DSCR_S5 | PCD_DPWW3_TTSP_DCS_S5 | PCD_DPWW3_TTSP_DSCS_S5 | PCD_DPWW3_TTSP_DPP_S5 | PCD_DPWW3_TTSP_DTPI_S5 | PCD_DPWW3_TTSP_DCI_S5 | PCD_DPWW3_TTSP_DSI_S5 | PCD_DPWW3_TTSP_DER_S5 | PCD_DPWW3_TTSP_RS_S5 | PCD_DPWW3_TTSP_DPLE_S5
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 2 | 2 | 3 | 3 | 3 | 3 | 6 | 6 | 6 | 6 | 13 | [12 empty] | DPWW3.14 |  | _S6 |  | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_S6 | PCD_DPWW3_TTSP_DLY_S6 | PCD_DPWW3_TTSP_DIR_S6 | PCD_DPWW3_TTSP_DSCR_S6 | PCD_DPWW3_TTSP_DCS_S6 | PCD_DPWW3_TTSP_DSCS_S6 | PCD_DPWW3_TTSP_DPP_S6 | PCD_DPWW3_TTSP_DTPI_S6 | PCD_DPWW3_TTSP_DCI_S6 | PCD_DPWW3_TTSP_DSI_S6 | PCD_DPWW3_TTSP_DER_S6 | PCD_DPWW3_TTSP_RS_S6 | PCD_DPWW3_TTSP_DPLE_S6
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.14 |  | _S7 |  | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_S7 | PCD_DPWW3_TTSP_DLY_S7 | PCD_DPWW3_TTSP_DIR_S7 | PCD_DPWW3_TTSP_DSCR_S7 | PCD_DPWW3_TTSP_DCS_S7 | PCD_DPWW3_TTSP_DSCS_S7 | PCD_DPWW3_TTSP_DPP_S7 | PCD_DPWW3_TTSP_DTPI_S7 | PCD_DPWW3_TTSP_DCI_S7 | PCD_DPWW3_TTSP_DSI_S7 | PCD_DPWW3_TTSP_DER_S7 | PCD_DPWW3_TTSP_RS_S7 | PCD_DPWW3_TTSP_DPLE_S7
| TMS | PR24CA113 Wastewater scheme level PCDs | PCDWW12 | Y | Treatment for tightening of sanitary parameters | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | 21 | [12 empty] | DPWW3.14 |  | _ST |  | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_ST | PCD_DPWW3_TTSP_DLY_ST | PCD_DPWW3_TTSP_DIR_ST | PCD_DPWW3_TTSP_DSCR_ST | PCD_DPWW3_TTSP_DCS_ST | PCD_DPWW3_TTSP_DSCS_ST | PCD_DPWW3_TTSP_DPP_ST | PCD_DPWW3_TTSP_DTPI_ST | PCD_DPWW3_TTSP_DCI_ST | PCD_DPWW3_TTSP_DSI_ST | PCD_DPWW3_TTSP_DER_ST | PCD_DPWW3_TTSP_RS_ST | PCD_DPWW3_TTSP_DPLE_ST
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 0 | Nr | 0 | 68 | 4 | [32 empty] | DPWW3.15 |  | PCD_DPWW3_PR19WINCA | PCD_DPWW3_PR19WINCA_NR | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_S0 | PCD_DPWW3_PR19WINCA_DLY | PCD_DPWW3_PR19WINCA_DIR | PCD_DPWW3_PR19WINCA_DSCR | PCD_DPWW3_PR19WINCA_DCS | PCD_DPWW3_PR19WINCA_DSCS | PCD_DPWW3_PR19WINCA_DPP | PCD_DPWW3_PR19WINCA_DTPI | PCD_DPWW3_PR19WINCA_DCI | PCD_DPWW3_PR19WINCA_DSI | PCD_DPWW3_PR19WINCA_DER | PCD_DPWW3_PR19WINCA_RS | PCD_DPWW3_PR19WINCA_DPLE
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 1 | Nr | 0 |  | 22 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S1 |  | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_S1 | PCD_DPWW3_PR19WINCA_DLY_S1 | PCD_DPWW3_PR19WINCA_DIR_S1 | PCD_DPWW3_PR19WINCA_DSCR_S1 | PCD_DPWW3_PR19WINCA_DCS_S1 | PCD_DPWW3_PR19WINCA_DSCS_S1 | PCD_DPWW3_PR19WINCA_DPP_S1 | PCD_DPWW3_PR19WINCA_DTPI_S1 | PCD_DPWW3_PR19WINCA_DCI_S1 | PCD_DPWW3_PR19WINCA_DSI_S1 | PCD_DPWW3_PR19WINCA_DER_S1 | PCD_DPWW3_PR19WINCA_RS_S1 | PCD_DPWW3_PR19WINCA_DPLE_S1
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 2 | Nr | 0 |  | 34 | 43 | 37 | 27 | 11 | 9 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S2 |  | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_S2 | PCD_DPWW3_PR19WINCA_DLY_S2 | PCD_DPWW3_PR19WINCA_DIR_S2 | PCD_DPWW3_PR19WINCA_DSCR_S2 | PCD_DPWW3_PR19WINCA_DCS_S2 | PCD_DPWW3_PR19WINCA_DSCS_S2 | PCD_DPWW3_PR19WINCA_DPP_S2 | PCD_DPWW3_PR19WINCA_DTPI_S2 | PCD_DPWW3_PR19WINCA_DCI_S2 | PCD_DPWW3_PR19WINCA_DSI_S2 | PCD_DPWW3_PR19WINCA_DER_S2 | PCD_DPWW3_PR19WINCA_RS_S2 | PCD_DPWW3_PR19WINCA_DPLE_S2
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 3 | Nr | 0 |  | 8 | 3 | 6 | 8 | 19 | 12 | 7 | 10 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S3 |  | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_S3 | PCD_DPWW3_PR19WINCA_DLY_S3 | PCD_DPWW3_PR19WINCA_DIR_S3 | PCD_DPWW3_PR19WINCA_DSCR_S3 | PCD_DPWW3_PR19WINCA_DCS_S3 | PCD_DPWW3_PR19WINCA_DSCS_S3 | PCD_DPWW3_PR19WINCA_DPP_S3 | PCD_DPWW3_PR19WINCA_DTPI_S3 | PCD_DPWW3_PR19WINCA_DCI_S3 | PCD_DPWW3_PR19WINCA_DSI_S3 | PCD_DPWW3_PR19WINCA_DER_S3 | PCD_DPWW3_PR19WINCA_RS_S3 | PCD_DPWW3_PR19WINCA_DPLE_S3
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 12 | 12 | 13 | 16 | 25 | 32 | 34 | 36 | 35 | 35 | 30 | 26 | 22 | 12 | 11 | 10 | 9 | 7 | 6 | 4 | [12 empty] | DPWW3.15 |  | _S4 |  | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_S4 | PCD_DPWW3_PR19WINCA_DLY_S4 | PCD_DPWW3_PR19WINCA_DIR_S4 | PCD_DPWW3_PR19WINCA_DSCR_S4 | PCD_DPWW3_PR19WINCA_DCS_S4 | PCD_DPWW3_PR19WINCA_DSCS_S4 | PCD_DPWW3_PR19WINCA_DPP_S4 | PCD_DPWW3_PR19WINCA_DTPI_S4 | PCD_DPWW3_PR19WINCA_DCI_S4 | PCD_DPWW3_PR19WINCA_DSI_S4 | PCD_DPWW3_PR19WINCA_DER_S4 | PCD_DPWW3_PR19WINCA_RS_S4 | PCD_DPWW3_PR19WINCA_DPLE_S4
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.15 |  | _S5 |  | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_S5 | PCD_DPWW3_PR19WINCA_DLY_S5 | PCD_DPWW3_PR19WINCA_DIR_S5 | PCD_DPWW3_PR19WINCA_DSCR_S5 | PCD_DPWW3_PR19WINCA_DCS_S5 | PCD_DPWW3_PR19WINCA_DSCS_S5 | PCD_DPWW3_PR19WINCA_DPP_S5 | PCD_DPWW3_PR19WINCA_DTPI_S5 | PCD_DPWW3_PR19WINCA_DCI_S5 | PCD_DPWW3_PR19WINCA_DSI_S5 | PCD_DPWW3_PR19WINCA_DER_S5 | PCD_DPWW3_PR19WINCA_RS_S5 | PCD_DPWW3_PR19WINCA_DPLE_S5
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 9 | 9 | 20 | 22 | 22 | 23 | 23 | 27 | 31 | 33 | 38 | 42 | 46 | 56 | 57 | 58 | 59 | 61 | 62 | 64 | [12 empty] | DPWW3.15 |  | _S6 |  | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_S6 | PCD_DPWW3_PR19WINCA_DLY_S6 | PCD_DPWW3_PR19WINCA_DIR_S6 | PCD_DPWW3_PR19WINCA_DSCR_S6 | PCD_DPWW3_PR19WINCA_DCS_S6 | PCD_DPWW3_PR19WINCA_DSCS_S6 | PCD_DPWW3_PR19WINCA_DPP_S6 | PCD_DPWW3_PR19WINCA_DTPI_S6 | PCD_DPWW3_PR19WINCA_DCI_S6 | PCD_DPWW3_PR19WINCA_DSI_S6 | PCD_DPWW3_PR19WINCA_DER_S6 | PCD_DPWW3_PR19WINCA_RS_S6 | PCD_DPWW3_PR19WINCA_DPLE_S6
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.15 |  | _S7 |  | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_S7 | PCD_DPWW3_PR19WINCA_DLY_S7 | PCD_DPWW3_PR19WINCA_DIR_S7 | PCD_DPWW3_PR19WINCA_DSCR_S7 | PCD_DPWW3_PR19WINCA_DCS_S7 | PCD_DPWW3_PR19WINCA_DSCS_S7 | PCD_DPWW3_PR19WINCA_DPP_S7 | PCD_DPWW3_PR19WINCA_DTPI_S7 | PCD_DPWW3_PR19WINCA_DCI_S7 | PCD_DPWW3_PR19WINCA_DSI_S7 | PCD_DPWW3_PR19WINCA_DER_S7 | PCD_DPWW3_PR19WINCA_RS_S7 | PCD_DPWW3_PR19WINCA_DPLE_S7
| TMS | PR24CA117 WINEP and GER Carryover | PCDWW35 | Y | PR19 WINEP Carryover actions | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | 68 | [12 empty] | DPWW3.15 |  | _ST |  | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_ST | PCD_DPWW3_PR19WINCA_DLY_ST | PCD_DPWW3_PR19WINCA_DIR_ST | PCD_DPWW3_PR19WINCA_DSCR_ST | PCD_DPWW3_PR19WINCA_DCS_ST | PCD_DPWW3_PR19WINCA_DSCS_ST | PCD_DPWW3_PR19WINCA_DPP_ST | PCD_DPWW3_PR19WINCA_DTPI_ST | PCD_DPWW3_PR19WINCA_DCI_ST | PCD_DPWW3_PR19WINCA_DSI_ST | PCD_DPWW3_PR19WINCA_DER_ST | PCD_DPWW3_PR19WINCA_RS_ST | PCD_DPWW3_PR19WINCA_DPLE_ST
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 0 | Nr | 0 | 0 | 0 | [32 empty] | DPWW3.16 |  | PCD_DPWW3_GGR1 | PCD_DPWW3_GGR1_NR | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_S0 | PCD_DPWW3_GGR1_DLY | PCD_DPWW3_GGR1_DIR | PCD_DPWW3_GGR1_DSCR | PCD_DPWW3_GGR1_DCS | PCD_DPWW3_GGR1_DSCS | PCD_DPWW3_GGR1_DPP | PCD_DPWW3_GGR1_DTPI | PCD_DPWW3_GGR1_DCI | PCD_DPWW3_GGR1_DSI | PCD_DPWW3_GGR1_DER | PCD_DPWW3_GGR1_RS | PCD_DPWW3_GGR1_DPLE
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 1 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S1 |  | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_S1 | PCD_DPWW3_GGR1_DLY_S1 | PCD_DPWW3_GGR1_DIR_S1 | PCD_DPWW3_GGR1_DSCR_S1 | PCD_DPWW3_GGR1_DCS_S1 | PCD_DPWW3_GGR1_DSCS_S1 | PCD_DPWW3_GGR1_DPP_S1 | PCD_DPWW3_GGR1_DTPI_S1 | PCD_DPWW3_GGR1_DCI_S1 | PCD_DPWW3_GGR1_DSI_S1 | PCD_DPWW3_GGR1_DER_S1 | PCD_DPWW3_GGR1_RS_S1 | PCD_DPWW3_GGR1_DPLE_S1
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 2 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S2 |  | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_S2 | PCD_DPWW3_GGR1_DLY_S2 | PCD_DPWW3_GGR1_DIR_S2 | PCD_DPWW3_GGR1_DSCR_S2 | PCD_DPWW3_GGR1_DCS_S2 | PCD_DPWW3_GGR1_DSCS_S2 | PCD_DPWW3_GGR1_DPP_S2 | PCD_DPWW3_GGR1_DTPI_S2 | PCD_DPWW3_GGR1_DCI_S2 | PCD_DPWW3_GGR1_DSI_S2 | PCD_DPWW3_GGR1_DER_S2 | PCD_DPWW3_GGR1_RS_S2 | PCD_DPWW3_GGR1_DPLE_S2
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 3 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S3 |  | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_S3 | PCD_DPWW3_GGR1_DLY_S3 | PCD_DPWW3_GGR1_DIR_S3 | PCD_DPWW3_GGR1_DSCR_S3 | PCD_DPWW3_GGR1_DCS_S3 | PCD_DPWW3_GGR1_DSCS_S3 | PCD_DPWW3_GGR1_DPP_S3 | PCD_DPWW3_GGR1_DTPI_S3 | PCD_DPWW3_GGR1_DCI_S3 | PCD_DPWW3_GGR1_DSI_S3 | PCD_DPWW3_GGR1_DER_S3 | PCD_DPWW3_GGR1_RS_S3 | PCD_DPWW3_GGR1_DPLE_S3
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 4 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S4 |  | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_S4 | PCD_DPWW3_GGR1_DLY_S4 | PCD_DPWW3_GGR1_DIR_S4 | PCD_DPWW3_GGR1_DSCR_S4 | PCD_DPWW3_GGR1_DCS_S4 | PCD_DPWW3_GGR1_DSCS_S4 | PCD_DPWW3_GGR1_DPP_S4 | PCD_DPWW3_GGR1_DTPI_S4 | PCD_DPWW3_GGR1_DCI_S4 | PCD_DPWW3_GGR1_DSI_S4 | PCD_DPWW3_GGR1_DER_S4 | PCD_DPWW3_GGR1_RS_S4 | PCD_DPWW3_GGR1_DPLE_S4
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 5 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S5 |  | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_S5 | PCD_DPWW3_GGR1_DLY_S5 | PCD_DPWW3_GGR1_DIR_S5 | PCD_DPWW3_GGR1_DSCR_S5 | PCD_DPWW3_GGR1_DCS_S5 | PCD_DPWW3_GGR1_DSCS_S5 | PCD_DPWW3_GGR1_DPP_S5 | PCD_DPWW3_GGR1_DTPI_S5 | PCD_DPWW3_GGR1_DCI_S5 | PCD_DPWW3_GGR1_DSI_S5 | PCD_DPWW3_GGR1_DER_S5 | PCD_DPWW3_GGR1_RS_S5 | PCD_DPWW3_GGR1_DPLE_S5
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 6 | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _S6 |  | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_S6 | PCD_DPWW3_GGR1_DLY_S6 | PCD_DPWW3_GGR1_DIR_S6 | PCD_DPWW3_GGR1_DSCR_S6 | PCD_DPWW3_GGR1_DCS_S6 | PCD_DPWW3_GGR1_DSCS_S6 | PCD_DPWW3_GGR1_DPP_S6 | PCD_DPWW3_GGR1_DTPI_S6 | PCD_DPWW3_GGR1_DCI_S6 | PCD_DPWW3_GGR1_DSI_S6 | PCD_DPWW3_GGR1_DER_S6 | PCD_DPWW3_GGR1_RS_S6 | PCD_DPWW3_GGR1_DPLE_S6
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes at Stage 7 | Nr | 0 | [34 empty] | DPWW3.16 |  | _S7 |  | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_S7 | PCD_DPWW3_GGR1_DLY_S7 | PCD_DPWW3_GGR1_DIR_S7 | PCD_DPWW3_GGR1_DSCR_S7 | PCD_DPWW3_GGR1_DCS_S7 | PCD_DPWW3_GGR1_DSCS_S7 | PCD_DPWW3_GGR1_DPP_S7 | PCD_DPWW3_GGR1_DTPI_S7 | PCD_DPWW3_GGR1_DCI_S7 | PCD_DPWW3_GGR1_DSI_S7 | PCD_DPWW3_GGR1_DER_S7 | PCD_DPWW3_GGR1_RS_S7 | PCD_DPWW3_GGR1_DPLE_S7
| TMS | PR24CA118 Net Zero | PCDWW34 | 0 | Greenhouse gas reduction (net zero) | Number of schemes - total (Stage 0 to Stage 6) | Nr | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [12 empty] | DPWW3.16 |  | _ST |  | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_ST | PCD_DPWW3_GGR1_DLY_ST | PCD_DPWW3_GGR1_DIR_ST | PCD_DPWW3_GGR1_DSCR_ST | PCD_DPWW3_GGR1_DCS_ST | PCD_DPWW3_GGR1_DSCS_ST | PCD_DPWW3_GGR1_DPP_ST | PCD_DPWW3_GGR1_DTPI_ST | PCD_DPWW3_GGR1_DCI_ST | PCD_DPWW3_GGR1_DSI_ST | PCD_DPWW3_GGR1_DER_ST | PCD_DPWW3_GGR1_RS_ST | PCD_DPWW3_GGR1_DPLE_ST
[44 empty] | Data_End | [35 empty] | BON_End

## DPW4
DPW4
Scheme-level data - Water - Enhanced engagement, Large gated, Critical High-profile schemes
| Company | Scheme name | Scheme ID | WINEP/NEP ID | Enhancement line description | PCD reference | Type of scheme (retained/dropped/added) | Name of the substituted scheme | Original regulatory date [if relevant] | Current regulatory date [if relevant] | Interim milestone completion dates - Baseline | [6 empty] | Current interim milestone | Interim milestone completion dates - Forecast | [6 empty] | Primary reson for delay where IM date moves more than 90 days later than baseline | Spend to date (£m) - cumulative | Forecast expenditure to complete scheme (£m) - cumulative | Forecast outturn cost (£m) | % Spend to date | Baseline expenditure profile (£m) - cumulative | [7 empty] | Forecast expenditure profile (£m) - cumulative | [7 empty] | Critical high profile (Yes/No) | Type of scheme (enhanced engagement, large gated, other) | AMP
[31 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9
[11 empty] | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 |  | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 | [5 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total
| TMS | Metering Programme | Multiple |  | Metering | PCDW12 | Retained |  |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 0 | 385.775 | 385.775 | 0% | 0 | 0 | 80.6257 | 156.7914 | 232.7466 | 309.0679 | 385.775 | 385.775 | 0 | 0 | 80.6257 | 156.7914 | 232.7466 | 309.0679 | 385.775 | 385.775 | No | Other | AMP8
| TMS | Network PS Power Restart | UBA8.WAT.S30939 |  | Climate change uplift | PCDWW32 | Retained |  |  |  | 2025-09-01 | 2025-10-01 | 2026-01-01 | 2026-03-01 | 2030-02-28 | 2030-02-28 |  |  | 2025-09-01 | 2025-10-01 | 2026-01-01 | 2026-03-01 | 2030-02-28 | 2030-02-28 |  |  | 0 | 3.1762 | 3.1762 | 0% | 0 | 0 | 0.51118 | 1.1774 | 1.8437 | 2.5099 | 3.1762 | 3.1762 | 0 | 0 | 0.51118 | 1.1774 | 1.8437 | 2.5099 | 3.1762 | 3.1762 | No | Other | AMP8
| TMS | Faringdon Suction Main Transfer Cap | UBA8.WAT.S37590 |  | Climate change uplift | PCDWW32 | Retained |  |  |  | 2025-08-12 | 2026-06-03 | 2027-06-29 | 2028-02-18 | 2030-01-29 | 2029-11-23 |  |  | 2025-08-12 | 2026-06-03 | 2027-06-29 | 2028-02-18 | 2030-01-29 | 2029-11-23 |  |  | 0 | 25.8052 | 25.8052 | 0% | 0 | 0 | 0.4307 | 3.2092 | 6.5668 | 18.1023 | 25.4353 | 25.8052 | 0 | 0 | 0.4307 | 3.2092 | 6.5668 | 18.1023 | 25.4353 | 25.8052 | No | Other | AMP8
| TMS | Bradfield College Sluice Fish Pass Stdy | UBA8.WAT.S40860 | 08TW100205a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  | 0 | 0.27126 | 0.27126 | 0% | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | No | Other | AMP8
| TMS | Bradfield WTW Sustainability Reduction | UBA8.WAT.S38441 | 08TW100003a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2025-07-10 | 2026-07-28 | 2026-12-18 | 2028-09-12 | 2028-09-12 |  |  | 2024-06-19 | 2025-07-10 | 2026-07-28 | 2026-12-18 | 2028-09-12 | 2028-09-12 |  |  | 0.00023902 | 2.2463 | 2.2466 | 0.01064% | 0 | 0.00023902 | 0.30938 | 0.60649 | 1.8282 | 2.2239 | 2.2463 | 2.2463 | 0 | 0.00023902 | 0.30938 | 0.60649 | 1.8282 | 2.2239 | 2.2463 | 2.2463 | No | Other | AMP8
| TMS | Coppermills UV Treatment Design Work | UBA8.WAT.S40977 |  | Raw Water Deterioration and Taste, Odour and Colour | PCDW14, PCDW13 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-12-16 | 2026-10-15 | 2026-10-15 | 2027-03-01 | 2027-08-16 | 2027-08-16 |  |  | 2025-12-16 | 2026-10-15 | 2026-10-15 | 2027-03-01 | 2027-08-16 | 2027-08-16 |  |  | 0 | 4.9109 | 4.9109 | 0% | 0 | 0 | 0.81153 | 4.7088 | 4.9109 | 4.9109 | 4.9109 | 4.9109 | 0 | 0 | 0.81153 | 4.7088 | 4.9109 | 4.9109 | 4.9109 | 4.9109 | No | Large Gated | AMP8
| TMS | DrWPA INV Nitrate in groundwater Cleeve | UBA8.WAT.S38741 | 08TW100047a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-04-01 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 2025-04-01 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 0 | 0.55051 | 0.55051 | 0% | 0 | 0 | 0.22021 | 0.44041 | 0.49546 | 0.52299 | 0.55051 | 0.55051 | 0 | 0 | 0.22021 | 0.44041 | 0.49546 | 0.52299 | 0.55051 | 0.55051 | No | Other | AMP8
| TMS | Fish pass at Everington R. Pang Study | UBA8.WAT.S40861 | 08TW100206a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  | 0 | 0.27126 | 0.27126 | 0% | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | No | Other | AMP8
| TMS | Hornsey Bromate Removal (New Gauge Abs) | L784 | 08TW100032a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-14 | 2025-07-16 | 2026-07-23 | 2027-01-18 | 2029-02-05 | 2029-02-05 |  |  | 2024-06-14 | 2025-07-16 | 2026-07-23 | 2027-01-18 | 2029-02-05 | 2029-02-05 |  |  | 0.054924 | 7.9317 | 7.9866 | 0.6877% | 0 | 0.054924 | 0.41272 | 0.95297 | 4.7677 | 7.8506 | 7.918 | 7.9317 | 0 | 0.054924 | 0.41272 | 0.95297 | 4.7677 | 7.8506 | 7.918 | 7.9317 | No | Other | AMP8
| TMS | INNS Company wide plan | UBA8.WAT.S38605 | 08TW100041a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2030-03-31 | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 0 | 0.4 | 0.4 | 0% | 0 | 0 | 0.08 | 0.16 | 0.24 | 0.32 | 0.4 | 0.4 | 0 | 0 | 0.08 | 0.16 | 0.24 | 0.32 | 0.4 | 0.4 | No | Other | AMP8
| TMS | Kempton UV Treatment Design Work | UBA8.WAT.S40978 |  | Raw Water Deterioration and Taste, Odour and Colour | PCDW14, PCDW13 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-12-16 | 2026-10-15 | 2026-10-15 | 2027-03-01 | 2027-08-16 | 2027-08-16 |  |  | 2025-12-16 | 2026-10-15 | 2026-10-15 | 2027-03-01 | 2027-08-16 | 2027-08-16 |  |  | 0 | 2.1834 | 2.1834 | 0% | 0 | 0 | 0.37928 | 2.0945 | 2.1834 | 2.1834 | 2.1834 | 2.1834 | 0 | 0 | 0.37928 | 2.0945 | 2.1834 | 2.1834 | 2.1834 | 2.1834 | No | Large Gated | AMP8
| TMS | Lead Strategy | Lead Strategy |  | Raw Water Deterioration and Taste, Odour and Colour | PCDW14, PCDW13 | Retained |  | 2031-04-30 | 2031-04-30 | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 0 | 0.2 | 0.2 | 0% | 0 | 0 | 0 | 0.05 | 0.1 | 0.15 | 0.2 | 0.2 | 0 | 0 | 0 | 0.05 | 0.1 | 0.15 | 0.2 | 0.2 | No | Other | AMP8
| TMS | Low Flow investigations | UBA8.WAT.S38636 | 08TW100040a, 08TW100039a, 08TW100038a, 08TW100037a, 08TW100036a, 08TW100035a, 08TW100034a, 08TW100031a, 08TW100030a, 08TW100029a, 08TW100029b, 08TW100029c, 08TW100030b, 08TW100030d, 08TW100030c, 08TW100030e, 08TW100030f | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 4.9912 | 4.9912 | 0% | 0 | 0 | 2.4956 | 4.9912 | 4.9912 | 4.9912 | 4.9912 | 4.9912 | 0 | 0 | 2.4956 | 4.9912 | 4.9912 | 4.9912 | 4.9912 | 4.9912 | No | Other | AMP8
| TMS | Netley WTW Sustain license reduction | UBA8.WAT.S38445 | 08TW100002a | Water Framework Directive interconnector | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2020-05-29 | 2021-03-24 | 2023-09-28 | 2024-03-18 | 2026-12-17 | 2026-12-17 |  |  | 2020-05-29 | 2021-03-24 | 2023-09-28 | 2024-03-18 | 2026-12-17 | 2026-12-17 |  |  | 0 | 15.4878 | 15.4878 | 0% | 0 | 0 | 0 | 0.17749 | 3.554 | 8.6188 | 15.319 | 15.4878 | 0 | 0 | 0 | 0.17749 | 3.554 | 8.6188 | 15.319 | 15.4878 | No | Other | AMP8
| TMS | Non-SRO Additional fund for DD Response | UBA8.WAT.S42273 |  | Supply | PCDW11a | Retained |  |  |  |  | 2030-01-08 | 2030-01-08 | 2030-01-08 | 2030-01-08 | 2030-01-08 |  |  |  | 2030-01-08 | 2030-01-08 | 2030-01-08 | 2030-01-08 | 2030-01-08 |  |  | 0 | 51.5769 | 51.5769 | 0% | 0 | 0 | 0.66234 | 7.6636 | 23.2323 | 40.944 | 51.5769 | 51.5769 | 0 | 0 | 0.66234 | 7.6636 | 23.2323 | 40.944 | 51.5769 | 51.5769 | No | Other | AMP8
| TMS | PFAS Strategy | PFAS Strategy |  | Raw Water Deterioration and Taste, Odour and Colour | PCDW14, PCDW13 | Retained |  | 2031-04-30 | 2031-04-30 | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 2025-04-01 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 0 | 0.2 | 0.2 | 0% | 0 | 0 | 0 | 0.05 | 0.1 | 0.15 | 0.2 | 0.2 | 0 | 0 | 0 | 0.05 | 0.1 | 0.15 | 0.2 | 0.2 | No | Other | AMP8
| TMS | PR24 Digital Cyber Enhancement Case | UBA8.WAT.S41624, UBA8.WAT.S41624.OX |  | Cyber | PCDW17b | Retained |  | 2030-04-30 | 2030-04-30 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 102.1947 | 102.1947 | 0% | 0 | 0 | 19.0705 | 48.0883 | 72.8448 | 86.6581 | 102.1947 | 102.1947 | 0 | 0 | 19.0705 | 48.0883 | 72.8448 | 86.6581 | 102.1947 | 102.1947 | No | Other | AMP8
| TMS | PR24 SEMD - ESS/OT | UBA8.WAT.S41877 |  | Gated scheme - NO PCD | Gated scheme - NO PCD | Retained |  | 2035-03-31 | 2035-03-31 | 2025-04-02 | 2026-06-17 | 2027-05-27 | 2027-12-20 | 2031-12-19 | 2031-12-19 |  |  | 2025-04-02 | 2026-06-17 | 2027-05-27 | 2027-12-20 | 2031-12-19 | 2031-12-19 |  |  | 0 | 27.9708 | 27.9708 | 0% | 0 | 0 | 1.3555 | 4.1129 | 7.5336 | 11.1688 | 15.3341 | 27.9708 | 0 | 0 | 1.3555 | 4.1129 | 7.5336 | 11.1688 | 15.3341 | 27.9708 | No | Large Gated | AMP8
| TMS | PR24 SEMD - Patrol and Response | UBA8.WAT.S41876 |  | Gated scheme - NO PCD | Gated scheme - NO PCD | Retained |  |  |  | 2025-04-01 | 2027-01-19 | 2027-11-08 | 2028-07-27 | 2029-04-16 | 2029-04-16 |  |  | 2025-04-01 | 2027-01-19 | 2027-11-08 | 2028-07-27 | 2029-04-16 | 2029-04-16 |  |  | 0 | 3.4018 | 3.4018 | 0% | 0 | 0 | 0.68053 | 1.361 | 2.0416 | 2.7221 | 3.4018 | 3.4018 | 0 | 0 | 0.68053 | 1.361 | 2.0416 | 2.7221 | 3.4018 | 3.4018 | No | Large Gated | AMP8
| TMS | PR24 WINEP New gauge investigation | UBA8.WAT.S40116 | 08TW100032a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-09-01 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 |  |  | 2025-09-01 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 |  |  | 0 | 1.0061 | 1.0061 | 0% | 0 | 0 | 0.50304 | 1.0061 | 1.0061 | 1.0061 | 1.0061 | 1.0061 | 0 | 0 | 0.50304 | 1.0061 | 1.0061 | 1.0061 | 1.0061 | 1.0061 | No | Other | AMP8
| TMS | PR24 WINEP WFD_IMP_PHYSHAB GSK weir | UBA8.WAT.S40792 | 08TW101456a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  | 0 | 0.21701 | 0.21701 | 0% | 0 | 0 | 0.043401 | 0.086805 | 0.13021 | 0.17361 | 0.21701 | 0.21701 | 0 | 0 | 0.043401 | 0.086805 | 0.13021 | 0.17361 | 0.21701 | 0.21701 | No | Other | AMP8
| TMS | PR24 WINEP WFD_IMP_PHYSHAB Newmans Weir | UBA8.WAT.S40790 | 08TW101458a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  | 0 | 0.14105 | 0.14105 | 0% | 0 | 0 | 0.027125 | 0.054251 | 0.081375 | 0.1085 | 0.14105 | 0.14105 | 0 | 0 | 0.027125 | 0.054251 | 0.081375 | 0.1085 | 0.14105 | 0.14105 | No | Other | AMP8
| TMS | PR24 WINEP WFD_INV_PHYSHAB Ware Lock | UBA8.WAT.S40793 | 08TW101455a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-04-01 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 2025-04-01 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 | 2027-04-30 |  |  | 0 | 0.21701 | 0.21701 | 0% | 0 | 0 | 0.1085 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | 0 | 0 | 0.1085 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | No | Other | AMP8
| TMS | PR24 WINEP WFD_INV_WRFlow Crane | UBA8.WAT.S40123 | 08TW101379a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.15091 | 0.15091 | 0% | 0 | 0 | 0.050305 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | 0 | 0 | 0.050305 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | No | Other | AMP8
| TMS | Reduce Abstraction vulnerable source INV | UBA8.WAT.S39358 | 08TW101405b, 08TW101405c, 08TW101405d, 08TW101405e, 08TW101405f, 08TW101405g, 08TW101405h, 08TW101405i, 08TW101405j, 08TW101405k, 08TW101405l, 08TW101405m, 08TW101405a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 4.8827 | 4.8827 | 0% | 0 | 0 | 0.97655 | 1.9531 | 2.9296 | 3.9062 | 4.8827 | 4.8827 | 0 | 0 | 0.97655 | 1.9531 | 2.9296 | 3.9062 | 4.8827 | 4.8827 | No | Other | AMP8
| TMS | Reducing the risk of lead | UBA8.WAT.S39253 |  | Lead | PCDW15 | Retained |  | 2030-03-31 | 2030-03-31 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 70.9011 | 70.9011 | 0% | 0 | 0 | 10.5781 | 25.7394 | 40.7947 | 55.8583 | 70.9011 | 70.9011 | 0 | 0 | 10.5781 | 25.7394 | 40.7947 | 55.8583 | 70.9011 | 70.9011 | No | Other | AMP8
| TMS | River Restoration (RR) LND | L898 | 08TW100028a, 08TW100027a, 09TW100013a, 09TW100014a, 08TW100020a, 08TW100025a, 08TW100026a, 08TW100033a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2025-10-15 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  |  | 2024-09-18 | 2025-10-15 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  |  | 0 | 6.5119 | 6.5119 | 0% | 0 | 0 | 0.35944 | 0.83964 | 3.7092 | 6.4504 | 6.5075 | 6.5119 | 0 | 0 | 0.35944 | 0.83964 | 3.7092 | 6.4504 | 6.5075 | 6.5119 | No | Other | AMP8
| TMS | River Restoration (RR) TV | L896 | 08TW100023a, 08TW100022a, 08TW104006a, 08TW104007a, 08TW100024a, 08TW100021a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2026-08-28 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  |  | 2024-09-18 | 2026-08-28 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  |  | 0 | 3.1726 | 3.1726 | 0% | 0 | 0 | 0.47668 | 0.8106 | 2.011 | 3.147 | 3.1709 | 3.1726 | 0 | 0 | 0.47668 | 0.8106 | 2.011 | 3.147 | 3.1709 | 3.1726 | No | Other | AMP8
| TMS | River Restoration (RR) TV | L896 | 08TW100207a, 08TW100208a, 08TW100209a, 08TW100210a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-09-18 | 2026-08-28 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  |  | 2024-09-18 | 2026-08-28 | 2027-01-05 | 2027-05-05 | 2029-01-12 | 2029-01-12 |  |  | 0 | 1.0384 | 1.0384 | 0% | 0 | 0 | 0.14964 | 0.99515 | 1.0384 | 1.0384 | 1.0384 | 1.0384 | 0 | 0 | 0.14964 | 0.99515 | 1.0384 | 1.0384 | 1.0384 | 1.0384 | No | Other | AMP8
| TMS | SEMD - CAT 3-5 | L827 |  | Gated scheme - NO PCD | Gated scheme - NO PCD | Retained |  | 2035-03-31 | 2035-03-31 | 2024-05-21 | 2026-08-19 | 2027-07-06 | 2028-02-10 | 2033-01-21 | 2033-01-21 |  |  | 2024-05-21 | 2026-08-19 | 2027-07-06 | 2028-02-10 | 2033-01-21 | 2033-01-21 |  |  | 0.21674 | 307.8251 | 308.0419 | 0.07036% | 0 | 0.21674 | 4.1002 | 15.0664 | 81.1088 | 124.1679 | 190.294 | 307.8251 | 0 | 0.21674 | 4.1002 | 15.0664 | 81.1088 | 124.1679 | 190.294 | 307.8251 | No | Large Gated | AMP8
| TMS | SEMD Alternative water supply | UBA8.WAT.S41951 |  | SEMD | PCDW17a | Retained |  | 2030-09-30 | 2030-09-30 | [16 empty] | 0 | 28.226 | 28.226 | 0% | 0 | 0 | 7.3726 | 12.6009 | 17.8194 | 23.0252 | 28.226 | 28.226 | 0 | 0 | 7.3726 | 12.6009 | 17.8194 | 23.0252 | 28.226 | 28.226 | No | Other | AMP8
| TMS | SEMD Ashford Common WTW | L744 |  | Gated scheme - NO PCD | Gated scheme - NO PCD | Retained |  | 2028-01-06 | 2028-01-06 | 2024-05-22 | 2025-01-23 | 2025-11-19 | 2027-08-31 | 2028-10-10 | 2028-10-10 |  |  | 2024-05-22 | 2025-01-23 | 2025-11-19 | 2027-08-31 | 2028-10-10 | 2028-10-10 |  |  | 0.22511 | 37.956 | 38.1811 | 0.5896% | 0 | 0.22511 | 1.2927 | 11.6689 | 31.1833 | 37.5756 | 37.9157 | 37.956 | 0 | 0.22511 | 1.2927 | 11.6689 | 31.1833 | 37.5756 | 37.9157 | 37.956 | No | Large Gated | AMP8
| TMS | SEMD Systems and sites CNI Package 11 | UBA8.WAT.S40056 |  | Gated scheme - NO PCD | Gated scheme - NO PCD | Retained |  | 2035-03-31 | 2035-03-31 | 2025-04-23 | 2026-06-15 | 2027-05-27 | 2028-01-04 | 2032-12-22 | 2032-12-22 |  |  | 2025-04-23 | 2026-06-15 | 2027-05-27 | 2028-01-04 | 2032-12-22 | 2032-12-22 |  |  | 0 | 1.4012 | 1.4012 | 0% | 0 | 0 | 0.067856 | 0.20606 | 0.36475 | 0.51332 | 0.66015 | 1.4012 | 0 | 0 | 0.067856 | 0.20606 | 0.36475 | 0.51332 | 0.66015 | 1.4012 | No | Large Gated | AMP8
| TMS | Tidmarsh Mill Fish Pass feasibility | UBA8.WAT.S41654 | 08TW100212a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-04-01 | 2025-12-02 | 2026-10-26 | 2027-04-01 | 2029-08-22 | 2029-08-22 |  |  | 2025-04-01 | 2025-12-02 | 2026-10-26 | 2027-04-01 | 2029-08-22 | 2029-08-22 |  |  | 0.0059479 | 0.2729 | 0.27885 | 2.133% | 0 | 0.0059479 | 0.019387 | 0.063418 | 0.13505 | 0.24733 | 0.27027 | 0.2729 | 0 | 0.0059479 | 0.019387 | 0.063418 | 0.13505 | 0.24733 | 0.27027 | 0.2729 | No | Other | AMP8
| TMS | Upper Swells -Donnington Main Upsize | UBA8.WAT.S37803 | 08TW100046a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2026-04-15 | 2027-05-27 | 2027-10-20 | 2029-07-12 | 2029-07-12 |  |  | 2024-06-19 | 2026-04-15 | 2027-05-27 | 2027-10-20 | 2029-07-12 | 2029-07-12 |  |  | 0 | 2.5001 | 2.5001 | 0% | 0 | 0 | 0.12462 | 0.36962 | 0.83486 | 2.2298 | 2.478 | 2.5001 | 0 | 0 | 0.12462 | 0.36962 | 0.83486 | 2.2298 | 2.478 | 2.5001 | No | Other | AMP8
| TMS | Whelford Mill Fish Pass feasibility | UBA8.WAT.S41653 | 08TW100214a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-04-01 | 2026-07-07 | 2027-05-27 | 2027-10-25 | 2030-03-21 | 2030-03-21 |  |  | 2025-04-01 | 2026-07-07 | 2027-05-27 | 2027-10-25 | 2030-03-21 | 2030-03-21 |  |  | 0.0021549 | 0.27336 | 0.27551 | 0.7821% | 0 | 0.0021549 | 0.01337 | 0.040108 | 0.07819 | 0.18551 | 0.26782 | 0.27336 | 0 | 0.0021549 | 0.01337 | 0.040108 | 0.07819 | 0.18551 | 0.26782 | 0.27336 | No | Other | AMP8
| TMS | WINEP Flow Investi deterioration risk | UBA8.WAT.S40788 | 08TW101460a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.14648 | 0.14648 | 0% | 0 | 0 | 0.029296 | 0.058592 | 0.087887 | 0.11718 | 0.14648 | 0.14648 | 0 | 0 | 0.029296 | 0.058592 | 0.087887 | 0.11718 | 0.14648 | 0.14648 | No | Other | AMP8
| TMS | WINEP Flow investn into deterioration WB | UBA8.WAT.S40781 | 08TW101467a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.14648 | 0.14648 | 0% | 0 | 0 | 0.029296 | 0.058592 | 0.087887 | 0.11718 | 0.14648 | 0.14648 | 0 | 0 | 0.029296 | 0.058592 | 0.087887 | 0.11718 | 0.14648 | 0.14648 | No | Other | AMP8
| TMS | WINEP Flow Upper Kennet investigation | UBA8.WAT.S40770 | 08TW104005a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.27126 | 0.27126 | 0% | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | No | Other | AMP8
| TMS | WINEP Hogsmill Enviro Destination Invest | UBA8.WAT.S40786 | 08TW101462a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.27126 | 0.27126 | 0% | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | 0 | 0 | 0.054255 | 0.10851 | 0.16276 | 0.21701 | 0.27126 | 0.27126 | No | Other | AMP8
| TMS | WINEP INV Environmental Destination | UBA8.WAT.S40117 | 08TW101373a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 |  |  | 2025-04-01 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 | 2027-01-04 |  |  | 0 | 0.50305 | 0.50305 | 0% | 0 | 0 | 0.15092 | 0.50305 | 0.50305 | 0.50305 | 0.50305 | 0.50305 | 0 | 0 | 0.15092 | 0.50305 | 0.50305 | 0.50305 | 0.50305 | 0.50305 | No | Other | AMP8
| TMS | WINEP modified WB Grimsbury Reservoir | UBA8.WAT.S40120 | 08TW101376a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.15091 | 0.15091 | 0% | 0 | 0 | 0.050305 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | 0 | 0 | 0.050305 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | 0.15091 | No | Other | AMP8
| TMS | WINEP modified WB Thames Cookham Egham | UBA8.WAT.S40121 | 08TW101377a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.16902 | 0.16902 | 0% | 0 | 0 | 0.05634 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | 0 | 0 | 0.05634 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | No | Other | AMP8
| TMS | WINEP modified WB Thames Egham Teddingto | UBA8.WAT.S40122 | 08TW101378a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.16902 | 0.16902 | 0% | 0 | 0 | 0.05634 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | 0 | 0 | 0.05634 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | 0.16902 | No | Other | AMP8
| TMS | WINEP Nrt New River Wells Chinnor licenc | UBA8.WAT.S38732 | 08TW100045a, 08TW100044a | Water Framework Directive actions | PCDW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-04-01 | 2025-06-13 | 2025-08-25 | 2025-11-06 | 2026-01-19 | 2026-01-19 |  |  | 2025-04-01 | 2025-06-13 | 2025-08-25 | 2025-11-06 | 2026-01-19 | 2026-01-19 |  |  | 0 | 0.0040245 | 0.0040245 | 0% | 0 | 0 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0 | 0 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | 0.0040245 | No | Other | AMP8
| TMS | WINEP Swan and Pike Weir | UBA8.WAT.S40791 | 08TW101457a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  |  | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 | 2026-12-21 |  |  | 0 | 0.18446 | 0.18446 | 0% | 0 | 0 | 0.036892 | 0.073784 | 0.11068 | 0.14757 | 0.18446 | 0.18446 | 0 | 0 | 0.036892 | 0.073784 | 0.11068 | 0.14757 | 0.18446 | 0.18446 | No | Other | AMP8
| TMS | WINEP WR Flow Unused licence investigate | UBA8.WAT.S40767 | 08TW104009a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-04-01 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.21701 | 0.21701 | 0% | 0 | 0 | 0.1085 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | 0 | 0 | 0.1085 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | 0.21701 | No | Other | AMP8
| TMS | WRFlow Woods Farm licence growth INV | UBA8.SEW.S40771 | 08TW104004a | Water WINEP/NEP Investigations | PCDW8 | Retained |  | 2026-12-31 | 2026-12-31 | 2025-01-20 | 2025-04-29 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 2025-01-20 | 2025-04-29 | 2026-12-31 | 2026-12-31 | 2026-12-31 | 2026-12-31 |  |  | 0 | 0.30838 | 0.30838 | 0% | 0 | 0 | 0.17578 | 0.30838 | 0.30838 | 0.30838 | 0.30838 | 0.30838 | 0 | 0 | 0.17578 | 0.30838 | 0.30838 | 0.30838 | 0.30838 | 0.30838 | No | Other | AMP8
| TMS | WRMP19_ML_ Didcot Raw Water Purchase | UBA8.WAT.S36984 |  | Supply | PCDW11a | Retained |  |  |  |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  |  | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 4.4185 | 18.5898 | 23.0083 | 19.2% | 2.2322 | 4.4185 | 7.2606 | 10.0991 | 12.9321 | 15.7609 | 18.5898 | 18.5898 | 2.2322 | 4.4185 | 7.2606 | 10.0991 | 12.9321 | 15.7609 | 18.5898 | 18.5898 | No | Other | AMP8
| TMS | WRMP19_ML_ Groundwater Addington | UBA8.WAT.S24423 |  | Supply | PCDW11a | Retained |  |  |  | 2024-04-18 | 2026-01-09 | 2027-07-14 | 2028-07-13 | 2030-02-06 | 2030-02-06 |  |  | 2024-04-18 | 2026-01-09 | 2027-07-14 | 2028-07-13 | 2030-02-06 | 2030-02-06 |  |  | 0 | 5.0688 | 5.0688 | 0% | 0 | 0 | 0.64627 | 1.3427 | 3.4625 | 5.0262 | 5.0688 | 5.0688 | 0 | 0 | 0.64627 | 1.3427 | 3.4625 | 5.0262 | 5.0688 | 5.0688 | No | Other | AMP8
| TMS | Hampton UV Treatment | L479 |  | Raw Water Deterioration and Taste, Odour and Colour | PCDW14, PCDW13 | Retained |  | 2031-04-30 | 2031-04-30 | 2023-09-20 | 2026-07-31 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  |  | 2023-09-20 | 2026-07-31 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  |  | 0.64744 | 61.0862 | 61.7337 | 1.049% | 0.12742 | 0.64744 | 2.0459 | 3.5248 | 20.2874 | 40.7314 | 60.7746 | 61.0862 | 0.12742 | 0.64744 | 2.0459 | 3.5248 | 20.2874 | 40.7314 | 60.7746 | 61.0862 | Yes | Large Gated | AMP8
| TMS | Ashford UV Treatment | L844 |  | Raw Water Deterioration and Taste, Odour and Colour | PCDW14, PCDW13 | Retained |  | 2031-04-30 | 2031-04-30 | 2024-03-22 | 2026-09-30 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  |  | 2024-03-22 | 2026-09-30 | 2027-03-31 | 2028-03-31 | 2030-03-31 | 2030-01-14 |  |  | 0.29199 | 96.453 | 96.745 | 0.3018% | 0 | 0.29199 | 2.6977 | 5.2207 | 31.7818 | 64.1886 | 95.9599 | 96.453 | 0 | 0.29199 | 2.6977 | 5.2207 | 31.7818 | 64.1886 | 95.9599 | 96.453 | Yes | Large Gated | AMP8
| TMS | Coppermills System Resilience | K665 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2031-01-31 | 2023-01-31 | 2023-07-18 | 2025-03-31 | 2026-09-23 | 2032-04-06 | 2031-03-31 |  | IM3 | 2023-01-31 | 2023-07-18 | 2025-03-31 | 2026-09-23 | 2032-04-06 | 2031-01-31 |  |  | 21.3033 | 443.8758 | 465.1791 | 4.58% | 7.8229 | 16.178 | 42.3529 | 134.2411 | 231.8907 | 330.7646 | 415.1053 | 466.2205 | 7.8229 | 16.178 | 41.9964 | 134.8099 | 232.3358 | 330.8511 | 414.886 | 465.1791 | No | Other | AMP7 carryover
| TMS | Hampton WTW TWRM Structural Fault WSSRP | L169.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2030-03-31 | 2021-10-26 | 2023-03-22 | 2029-06-01 | 2029-07-31 | 2030-03-29 | 2030-01-05 |  | IM2 | 2021-10-26 | 2023-03-22 | 2029-06-01 | 2029-07-31 | 2030-03-29 | 2029-11-05 |  |  | 0.25852 | 0.99318 | 1.2517 | 20.65% | 0.25714 | 0.25821 | 0.26034 | 0.38034 | 0.38238 | 0.38437 | 1.2555 | 1.2555 | 0.25714 | 0.25821 | 0.26012 | 0.37968 | 0.38171 | 0.3837 | 1.2517 | 1.2517 | No | Other | AMP7 carryover
| TMS | Hampton WTW GJ Vehicle Barrier (WSSRP) | L191.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2026-03-31 | 2021-10-26 | 2023-03-23 | 2023-09-22 | 2024-06-26 | 2026-02-16 | 2026-02-01 |  | IM4 | 2021-10-26 | 2023-03-23 | 2023-09-22 | 2024-06-26 | 2026-02-16 | 2025-12-01 |  |  | 1.4705 | 1.6488 | 3.1194 | 47.14% | 0.45672 | 1.2209 | 3.3138 | 3.3138 | 3.3138 | 3.3138 | 3.3138 | 3.3138 | 0.45672 | 1.2209 | 3.1188 | 3.1194 | 3.1194 | 3.1194 | 3.1194 | 3.1194 | No | Other | AMP7 carryover
| TMS | Hampton WTW Bulk Recycling (WSSRP) | L193.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2027-03-31 | 2021-10-26 | 2023-05-23 | 2026-07-06 | 2027-05-24 | 2028-12-01 | 2029-01-13 |  | IM2 | 2021-10-26 | 2023-05-23 | 2026-07-06 | 2027-05-24 | 2028-12-01 | 2028-11-13 |  |  | 1.1689 | 16.6896 | 17.8586 | 6.546% | 0.4173 | 1.0089 | 1.5775 | 2.5321 | 12.4296 | 17.713 | 17.8824 | 17.8824 | 0.4173 | 1.0089 | 1.6128 | 2.5639 | 12.4255 | 17.6898 | 17.8586 | 17.8586 | No | Other | AMP7 carryover
| TMS | Mogden TWRM Shaft Pump Out (WSSRP) | L204.01 |  | WSSRP | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  | 2028-03-31 | 2021-10-26 | 2023-05-23 | 2024-04-15 | 2025-09-17 | 2028-04-26 | 2028-04-28 |  | IM3 | 2021-10-26 | 2023-05-23 | 2024-04-15 | 2025-10-07 | 2028-05-05 | 2028-03-07 |  |  | 5.93 | 19.8395 | 25.7695 | 23.01% | 1.0376 | 4.4757 | 14.8181 | 24.3808 | 27.1529 | 27.1529 | 27.1529 | 27.1529 | 1.0376 | 4.4757 | 13.9007 | 22.1751 | 25.7695 | 25.7695 | 25.7695 | 25.7695 | No | Other | AMP7 carryover
| TMS | Pentonville Road? Trunk Main Replacement | K371.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-05-26 | 2021-11-24 | 2023-09-29 | 2024-07-23 | 2027-12-03 | 2027-12-02 |  | IM4 | 2021-05-26 | 2021-11-24 | 2023-09-29 | 2024-07-23 | 2027-08-13 | 2027-08-12 |  |  | 13.0019 | 27.1248 | 40.1267 | 32.4% | 3.5467 | 10.3892 | 24.8457 | 34.8121 | 38.4629 | 38.4629 | 38.4629 | 38.4629 | 3.5467 | 10.3894 | 23.7081 | 35.8439 | 40.1267 | 40.1267 | 40.1267 | 40.1267 | No | Other | AMP7 carryover
| TMS | K372 Fortis Green to Cockfosters Trunk M | K372.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2020-09-07 | 2021-11-11 | 2023-02-10 | 2023-06-26 | 2025-09-22 | 2025-04-17 |  | IM4 | 2020-09-07 | 2021-11-11 | 2023-02-10 | 2023-06-26 | 2025-10-07 | 2025-04-17 |  |  | 25.2679 | 0.45086 | 25.7188 | 98.25% | 8.9371 | 21.848 | 23.9608 | 23.9608 | 23.9608 | 23.9608 | 23.9608 | 23.9608 | 8.9371 | 21.848 | 25.7188 | 25.7188 | 25.7188 | 25.7188 | 25.7188 | 25.7188 | No | Other | AMP7 carryover
| TMS | Victoria Station 30in? Trunk Main | K374.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-05-26 | 2021-11-24 | 2023-08-30 | 2023-08-31 | 2025-04-10 | 2025-06-30 |  | IM4 | 2021-05-26 | 2021-11-24 | 2023-08-30 | 2023-08-31 | 2025-08-26 | 2025-06-30 |  |  | 8.966 | 0.26456 | 9.2306 | 97.13% | 3.751 | 8.9123 | 9.232 | 9.232 | 9.232 | 9.232 | 9.232 | 9.232 | 3.751 | 8.9123 | 9.2306 | 9.2306 | 9.2306 | 9.2306 | 9.2306 | 9.2306 | No | Other | AMP7 carryover
| TMS | Surbiton 30in no 1 & 3? Trunk Mains | K375.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-05-26 | 2021-10-26 | 2024-01-10 | 2024-03-28 | 2025-10-16 | 2025-07-30 |  | IM4 | 2021-05-26 | 2021-10-26 | 2024-01-10 | 2024-03-28 | 2026-01-27 | 2025-11-03 |  |  | 12.0752 | 3.8185 | 15.8937 | 75.97% | 2.7266 | 9.9837 | 15.291 | 15.291 | 15.291 | 15.291 | 15.291 | 15.291 | 2.7266 | 9.9868 | 15.8937 | 15.8937 | 15.8937 | 15.8937 | 15.8937 | 15.8937 | No | Other | AMP7 carryover
| TMS | Mile End Park & Station | K493.01 |  | LWICA | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  |  |  | 2021-08-25 | 2021-12-20 | 2023-09-25 | 2024-07-19 | 2027-04-26 | 2027-04-01 |  | IM4 | 2021-08-25 | 2021-12-20 | 2023-09-25 | 2024-07-19 | 2027-04-14 | 2027-03-18 |  |  | 11.3698 | 17.4203 | 28.7901 | 39.49% | 3.6524 | 9.8703 | 20.0087 | 27.382 | 28.9976 | 28.9976 | 28.9976 | 28.9976 | 3.6524 | 9.8703 | 19.4315 | 27.162 | 28.7901 | 28.7901 | 28.7901 | 28.7901 | No | Other | AMP7 carryover
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!
[29 empty] | 0 | #DIV/0!

## DPWW4
DPWW4
Scheme-level data - Wastewater - Enhanced engagement, Large gated and Critical High-profile schemes
| Company | Scheme name | Scheme ID | WINEP ID | Line description | PCD ref | Type of scheme (retained/dropped/added) | Name of the substituted scheme | Original regulatory date | Current regulatory date | Interim milestone completion dates - Baseline | [6 empty] | Current interim milestone | Interim milestone completion dates - Forecast | [6 empty] | Primary reson for delay where IM date moves more than 90 days later than baseline | Spend to date (£m) - cumulative | Forecast expenditure to complete scheme (£m) - cumulative | Forecast outturn cost (£m) | % Spend to date | Baseline expenditure profile (£m) - cumulative | [7 empty] | Forecast expenditure profile (£m) - cumulative | [8 empty] | Critical high profile (Yes/No) | Type of scheme (enhanced engagement, large gated, delivery mechanism, other) | AMP
[31 empty] | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9 | Pre- AMP8 |  | AMP8 |  |  |  |  | AMP9
[11 empty] | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 |  | IM1 | IM2 | IM3 | IM4 | IM5 | IM6 | IM7 | [5 empty] | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | Total
| TMS | Guildford STW Relocation Delivery | J009 | THM00529 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2026-03-31 | 2019-05-01 | 2019-05-01 | 2021-07-30 | 2022-10-26 | 2027-07-19 | 2026-11-30 |  | IM4 | 2019-05-01 | 2019-05-01 | 2021-07-30 | 2022-10-26 | 2028-05-06 | 2027-04-29 |  |  | 6.0277 | 2.2137 | 8.2413 | 73.14% | 3.0727 | 5.3731 | 6.733 | 8.0353 | 8.0363 | 8.0363 | 8.0363 | 8.0363 | 3.0727 | 5.3731 | 6.9051 | 8.2359 | 8.2413 | 8.2413 | 8.2413 | 8.2413 |  | Yes | Other | AMP7 carryover
| TMS | Guildford STW Relocation Delivery | J009 |  |  | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2026-03-31 | 2019-05-01 | 2019-05-01 | 2021-07-30 | 2022-10-26 | 2027-07-19 | 2026-11-30 |  | IM4 | 2019-05-01 | 2019-05-01 | 2021-07-30 | 2022-10-26 | 2028-05-06 | 2027-04-29 |  |  | 122.7689 | 45.0867 | 167.8555 | 73.14% | 62.5839 | 109.4367 | 137.1347 | 163.6601 | 163.679 | 163.679 | 163.679 | 163.679 | 62.5839 | 109.4367 | 140.6399 | 167.744 | 167.8555 | 167.8555 | 167.8555 | 167.8555 |  | Yes | Other | AMP7 carryover
| TMS | East Hyde AMP7 Growth | J568 | HNL00214 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-21 | 2021-03-24 | 2026-09-30 | 2026-09-30 | 2028-11-30 | 2029-04-28 |  | IM2 | 2020-02-21 | 2021-03-24 | 2026-01-30 | 2026-07-30 | 2029-02-28 | 2029-02-28 |  |  | 0.54905 | 13.7701 | 14.3191 | 3.834% | 0.32868 | 0.45799 | 1.3695 | 4.4534 | 9.4253 | 15.7515 | 15.7515 | 15.7515 | 0.32868 | 0.45799 | 1.3662 | 4.4389 | 9.3927 | 14.3191 | 14.3191 | 14.3191 |  | Yes | Other | AMP7 carryover
| TMS | East Hyde AMP7 Growth | J568 |  |  | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-21 | 2021-03-24 | 2026-09-30 | 2026-09-30 | 2028-11-30 | 2029-04-28 |  | IM2 | 2020-02-21 | 2021-03-24 | 2026-01-30 | 2026-07-30 | 2029-02-28 | 2029-02-28 |  |  | 3.1113 | 78.0305 | 81.1418 | 3.834% | 1.8625 | 2.5953 | 7.7604 | 25.2358 | 53.4098 | 89.2585 | 89.2585 | 89.2585 | 1.8625 | 2.5953 | 7.7415 | 25.1535 | 53.2254 | 81.1418 | 81.1418 | 81.1418 |  | Yes | Other | AMP7 carryover
| TMS | Kingston Bagpuize STW Growth and Quality | J971.01 | FLO01277 | Storm Tank | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-03-31 | 2024-12-22 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2026-08-16 |  | IM4 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2026-06-16 |  |  | 2.3722 | 3.8468 | 6.219 | 38.14% | 1.097 | 2.1709 | 4.8346 | 6.2199 | 6.2478 | 6.2478 | 6.2478 | 6.2478 | 1.097 | 2.1709 | 4.154 | 6.1316 | 6.219 | 6.219 | 6.219 | 6.219 |  | No | Other | AMP7 carryover
| TMS | Kingston Bagpuize STW Growth and Quality | J971.01 | THM00536 | Ammonia | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2027-07-28 |  | IM4 | 2019-06-18 | 2022-02-22 | 2023-06-16 | 2023-06-21 | 2027-08-20 | 2027-05-28 |  |  | 9.4889 | 15.3873 | 24.8762 | 38.14% | 4.388 | 8.6836 | 19.3382 | 24.8794 | 24.9912 | 24.9912 | 24.9912 | 24.9912 | 4.388 | 8.6836 | 16.6161 | 24.5265 | 24.8762 | 24.8762 | 24.8762 | 24.8762 |  | No | Other | AMP7 carryover
| TMS | Haslemere STW Early Procurement | J983.01 | THM00531 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-08-21 | 2021-11-24 | 2025-11-17 | 2026-01-19 | 2028-01-06 | 2028-01-09 |  | IM2 | 2019-08-21 | 2021-11-24 | 2025-11-17 | 2026-01-19 | 2028-01-06 | 2027-11-09 |  |  | 3.6211 | 21.5115 | 25.1326 | 14.41% | 1.115 | 3.3418 | 4.9119 | 20.5348 | 26.5252 | 27.3685 | 27.3685 | 27.3685 | 1.115 | 3.3418 | 5.1332 | 19.9003 | 25.1326 | 25.1326 | 25.1326 | 25.1326 |  | No | Other | AMP7 carryover
| TMS | Cranleigh STW Flow Compliance &P-Removal | J984.01 | THM00514 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-09-11 | 2028-09-14 | 2028-09-27 |  | IM2 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-09-11 | 2028-09-14 | 2028-07-27 |  |  | 0.93817 | 25.105 | 26.0432 | 3.602% | 0.57152 | 0.83409 | 1.6437 | 8.8481 | 22.3196 | 26.4894 | 27.2042 | 27.2042 | 0.57152 | 0.83409 | 1.6538 | 8.2819 | 18.6586 | 25.006 | 26.0432 | 26.0432 |  | No | Other | AMP7 carryover
| TMS | Cranleigh STW Flow Compliance &P-Removal | J984.01 | THM00659 | P - Green | This part of the AMP7 project is not PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-09-11 | 2028-09-14 | 2028-09-27 |  | IM2 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-09-11 | 2028-09-14 | 2028-07-27 |  |  | 0.71645 | 19.1719 | 19.8884 | 3.602% | 0.43645 | 0.63697 | 1.2552 | 6.757 | 17.0448 | 20.2291 | 20.775 | 20.775 | 0.43645 | 0.63697 | 1.263 | 6.3246 | 14.249 | 19.0963 | 19.8884 | 19.8884 |  | No | Other | AMP7 carryover
| TMS | Harpenden STW Flow compliance and Low P | J988 | HNL00215 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-09-09 | 2021-09-22 | 2025-08-01 | 2026-01-02 | 2028-06-30 | 2028-05-30 |  | IM2 | 2020-09-09 | 2021-09-22 | 2025-08-15 | 2026-01-02 | 2029-01-31 | 2028-08-31 |  |  | 1.4614 | 19.2296 | 20.6911 | 7.063% | 0.51988 | 1.1487 | 3.3329 | 10.7121 | 18.4605 | 20.7652 | 20.7652 | 20.7652 | 0.51988 | 1.1487 | 3.322 | 10.6745 | 18.3948 | 20.6911 | 20.6911 | 20.6911 |  | No | Other | AMP7 carryover
| TMS | Harpenden STW Flow compliance and Low P | J988 |  |  | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-09-09 | 2021-09-22 | 2025-08-01 | 2026-01-02 | 2028-06-30 | 2028-05-30 |  | IM2 | 2020-09-09 | 2021-09-22 | 2025-08-15 | 2026-01-02 | 2029-01-31 | 2028-08-31 |  |  | 2.8369 | 37.3281 | 40.165 | 7.063% | 1.0092 | 2.2298 | 6.4697 | 20.7941 | 35.8351 | 40.3088 | 40.3088 | 40.3088 | 1.0092 | 2.2298 | 6.4486 | 20.7211 | 35.7075 | 40.165 | 40.165 | 40.165 |  | No | Other | AMP7 carryover
| TMS | Burstow STW Growth & Flow Compliance | J991.01 | KSL00235 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-02-20 | 2021-04-21 | 2021-12-03 | 2022-07-21 | 2026-02-03 | 2026-01-11 |  | IM4 | 2019-02-20 | 2021-04-21 | 2021-12-03 | 2022-07-21 | 2026-02-03 | 2025-11-11 |  |  | 26.2657 | 5.9699 | 32.2356 | 81.48% | 14.8499 | 24.9506 | 29.608 | 29.608 | 29.608 | 29.608 | 29.608 | 29.608 | 14.8499 | 24.9506 | 32.2356 | 32.2356 | 32.2356 | 32.2356 | 32.2356 | 32.2356 |  | No | Other | AMP7 carryover
| TMS | Shutford STW - G2G Flow Compliance | K082.01 | THM00554 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-20 | 2022-09-21 | 2024-07-01 | 2024-08-12 | 2026-03-23 | 2026-03-06 |  | IM4 | 2020-02-20 | 2022-09-21 | 2024-07-01 | 2024-08-12 | 2026-03-23 | 2026-01-06 |  |  | 7.8548 | 4.8049 | 12.6596 | 62.05% | 1.1141 | 6.1621 | 12.5366 | 12.7038 | 12.7038 | 12.7038 | 12.7038 | 12.7038 | 1.1141 | 6.1621 | 12.3065 | 12.6596 | 12.6596 | 12.6596 | 12.6596 | 12.6596 |  | No | Other | AMP7 carryover
| TMS | Bordon Flow Compliance | K104.01 | THM00497 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-27 | 2021-12-03 | 2025-11-21 | 2025-12-22 | 2031-10-20 | 2028-09-28 |  | IM2 | 2020-02-27 | 2021-12-03 | 2025-11-20 | 2025-12-22 | 2031-10-20 | 2028-07-28 |  |  | 3.7848 | 59.748 | 63.5329 | 5.957% | 2.16 | 3.607 | 5.7065 | 13.0282 | 30.4227 | 47.7853 | 59.2638 | 63.2304 | 2.16 | 3.607 | 6.2176 | 13.5127 | 30.8442 | 48.1438 | 59.5807 | 63.5329 |  | No | Other | AMP7 carryover
| TMS | Maple Lodge STW Quality AMP7 New Permit | K298 | HNL00234 (7TW200123) | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2025-03-31 | 2024-12-22 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-12-31 | 2030-11-30 |  | IM2 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-12-31 | 2030-09-28 |  |  | 3.6631 | 259.9074 | 263.5705 | 1.39% | 0.73363 | 1.5186 | 3.2798 | 10.8929 | 36.7689 | 73.2689 | 109.4839 | 132.222 | 1.4673 | 3.0372 | 7.1403 | 21.995 | 73.5593 | 146.2945 | 218.4617 | 263.5705 |  | Yes | Other | AMP7 carryover
| TMS | Maple Lodge STW Quality AMP7 New Permit | K298 | HNL00192 (7TW200093) | Storm Tank | PCDWW35 | Retained |  | 2024-12-22 | 2025-03-31 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-12-31 | 2030-11-30 |  | IM2 | 2021-04-15 | 2025-01-31 | 2026-03-31 | 2027-06-30 | 2030-12-31 | 2030-09-28 |  |  | 1.8871 | 133.8917 | 135.7788 | 1.39% | 0.37793 | 0.78232 | 1.6896 | 5.6115 | 18.9416 | 37.7446 | 56.4008 | 68.1144 | 0.75586 | 1.5646 | 3.6783 | 11.3307 | 37.8942 | 75.3639 | 112.5409 | 135.7788 |  | Yes | Other | AMP7 carryover
| TMS | WWNI Alton STW P-removal | K444.01 | THM00575 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-06-17 | 2025-11-24 | 2026-07-20 | 2028-02-24 | 2028-02-20 |  | IM2 | 2021-01-26 | 2021-06-17 | 2025-11-24 | 2026-07-20 | 2028-02-24 | 2027-12-20 |  |  | 1.1097 | 10.9973 | 12.107 | 9.166% | 0.99719 | 1.0903 | 1.3811 | 5.8933 | 12.1094 | 12.1678 | 12.1741 | 12.1741 | 0.99719 | 1.0903 | 1.4221 | 5.9179 | 12.107 | 12.107 | 12.107 | 12.107 |  | No | Other | AMP7 carryover
| TMS | WWNI Fleet STW P-removal | K444.04 | THM00096 | FTFT | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-07-21 | 2026-09-01 | 2026-10-22 | 2030-11-01 | 2030-11-03 |  | IM2 | 2019-06-18 | 2021-07-21 | 2026-09-01 | 2026-10-22 | 2030-05-30 | 2030-03-26 |  |  | 1.9131 | 52.0606 | 53.9736 | 3.544% | 0.67178 | 1.7968 | 2.5919 | 3.2586 | 8.846 | 26.5872 | 45.7786 | 54.2318 | 0.67178 | 1.7968 | 2.2812 | 3.1036 | 10.5012 | 31.4343 | 49.085 | 53.9736 |  | No | Other | AMP7 carryover
| TMS | WWNI Fleet STW P-removal | K444.04 | THM00599 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-06-18 | 2021-07-21 | 2026-09-01 | 2026-10-22 | 2030-11-01 | 2030-11-03 |  | IM2 | 2019-06-18 | 2021-07-21 | 2026-09-01 | 2026-10-22 | 2030-05-30 | 2030-03-26 |  |  | 0.78443 | 21.3469 | 22.1313 | 3.544% | 0.27546 | 0.73675 | 1.0628 | 1.3362 | 3.6272 | 10.9018 | 18.771 | 22.2372 | 0.27546 | 0.73675 | 0.93539 | 1.2726 | 4.3059 | 12.8893 | 20.1268 | 22.1313 |  | No | Other | AMP7 carryover
| TMS | Blackbirds STW Quality AMP7 New Permit? | K537.01 | HNL00233 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-09-30 | 2025-10-23 | 2026-09-01 | 2027-04-14 | 2029-10-12 | 2029-09-27 |  | IM1 | 2021-09-30 | 2025-10-23 | 2026-09-01 | 2027-04-14 | 2029-10-12 | 2029-07-27 |  |  | 0 | 11.973 | 11.973 | 0% | 0 | 0 | 0.92294 | 2.3492 | 8.7269 | 11.9754 | 12.204 | 12.204 | 0 | 0 | 0.41655 | 1.1575 | 6.6721 | 11.6244 | 11.973 | 11.973 |  | No | Other | AMP7 carryover
| TMS | Brentwood STW WAAP and P-Removal | L477.01 | HNL00207 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2023-12-01 | 2025-01-23 | 2026-01-21 | 2026-05-13 | 2027-12-13 | 2027-08-12 |  | IM2 | 2020-11-30 | 2025-01-23 | 2026-01-21 | 2026-05-13 | 2027-12-13 | 2027-09-30 |  |  | 0.65847 | 17.3411 | 17.9996 | 3.658% | 0.64784 | 0.45843 | 3.1567 | 6.6653 | 8.1014 | 8.3889 | 8.3889 | 8.3889 | 0 | 0.025715 | 1.8251 | 12.5772 | 17.4926 | 17.9996 | 17.9996 | 17.9996 |  | No | Other | AMP7 carryover
| TMS | Farnham STW WAAP and P-Removal | L516.01 | THM00598 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-02-22 | 2024-04-17 | 2025-12-23 | 2026-01-26 | 2028-02-08 | 2028-02-01 |  | IM2 | 2022-02-22 | 2024-04-17 | 2026-03-26 | 2026-04-23 | 2028-06-08 | 2028-04-04 |  |  | 4.2559 | 20.904 | 25.1599 | 16.92% | 0 | 3.6592 | 6.454 | 17.9818 | 25.0097 | 25.1532 | 25.1561 | 25.1561 | 0 | 3.6592 | 6.0463 | 14.1362 | 24.6911 | 25.0985 | 25.1599 | 25.1599 |  | No | Other | AMP7 carryover
| TMS | WWNI Barkway STW P-removal | L742.01 | HNL00221 | P - Amber in Plan | PCDWW35 | Retained |  | N/A | 2024-12-22 | 2019-05-22 | 2021-06-01 | 2024-09-10 | 2024-12-23 | 2025-06-10 | 2025-06-28 |  | IM4 | 2019-05-22 | 2021-06-01 | 2024-09-10 | 2024-12-23 | 2025-09-04 | 2025-10-31 |  |  | 2.783 | 0 | 2.783 | 100% | 0 | 2.7127 | 2.7566 | 2.7566 | 2.7566 | 2.7566 | 2.7566 | 2.7566 | 0 | 2.7127 | 2.783 | 2.783 | 2.783 | 2.783 | 2.783 | 2.783 |  | No | Other | AMP7 carryover
| TMS | WWNI Ripley STW G2G and Low P | K672.01 | THM00550 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-08-31 | 2027-06-01 | 2027-09-06 | 2030-08-22 | 2030-08-27 |  | IM2 | 2021-01-26 | 2021-08-31 | 2027-06-01 | 2027-09-06 | 2030-05-30 | 2030-03-29 |  |  | 0.79321 | 27.5955 | 28.3887 | 2.794% | 0.71281 | 0.7802 | 1.3056 | 4.0288 | 5.3092 | 11.3709 | 22.9 | 28.1078 | 0.71281 | 0.7802 | 1.3767 | 3.2392 | 7.2659 | 23.7177 | 28.3887 | 28.3887 |  | No | Other | AMP7 carryover
| TMS | WWNI Woking STW Storm Tank & Low P | K677.01 | THM00572 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2025-03-31 | 2024-12-22 | 2019-06-18 | 2025-04-17 | 2026-02-25 | 2026-09-15 | 2028-08-17 | 2028-08-29 |  | IM2 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-10-12 | 2028-09-13 | 2028-07-26 |  |  | 1.63 | 55.8073 | 57.4372 | 2.838% | 1.1682 | 1.5629 | 2.9275 | 15.0309 | 46.6105 | 56.1092 | 57.2772 | 57.2772 | 1.1682 | 1.5629 | 2.7569 | 14.5478 | 31.852 | 48.7893 | 57.4372 | 57.4372 |  | No | Other | AMP7 carryover
| TMS | WWNI Woking STW Storm Tank & Low P | K677.01 | THM00109 | Storm Tank | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2025-03-31 | 2019-06-18 | 2025-04-17 | 2026-02-25 | 2026-09-15 | 2028-08-17 | 2028-08-29 |  | IM2 | 2019-06-18 | 2025-05-22 | 2026-03-25 | 2026-10-12 | 2028-09-13 | 2028-07-26 |  |  | 0.26909 | 9.2134 | 9.4825 | 2.838% | 0.19286 | 0.25803 | 0.48331 | 2.4815 | 7.6951 | 9.2633 | 9.4561 | 9.4561 | 0.19286 | 0.25803 | 0.45514 | 2.4018 | 5.2586 | 8.0548 | 9.4825 | 9.4825 |  | No | Other | AMP7 carryover
| TMS | WWNI Watlington STW FTFT & Low P | K759.01 | THM00567 | P - Amber in Plan | PCDWW35 | Retained |  | 2025-03-31 | 2024-12-22 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-04-22 | 2027-06-18 | 2027-03-29 |  | IM3 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-07-07 | 2027-05-13 | 2027-01-21 |  |  | 0.81875 | 3.8369 | 4.6557 | 17.59% | 0.16874 | 0.49298 | 2.0472 | 4.2807 | 4.4948 | 4.6556 | 4.6556 | 4.6556 | 0.16874 | 0.49298 | 2.5279 | 4.2536 | 4.5332 | 4.6557 | 4.6557 | 4.6557 |  | No | Other | AMP7 carryover
| TMS | WWNI Watlington STW FTFT & Low P | K759.01 | FLO01298 | FTFT | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2025-03-31 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-04-22 | 2027-06-18 | 2027-03-29 |  | IM3 | 2019-06-18 | 2022-03-03 | 2025-01-15 | 2025-07-07 | 2027-05-13 | 2027-01-21 |  |  | 1.3881 | 6.5052 | 7.8933 | 17.59% | 0.28608 | 0.8358 | 3.4709 | 7.2575 | 7.6206 | 7.8932 | 7.8932 | 7.8932 | 0.28608 | 0.8358 | 4.2859 | 7.2115 | 7.6857 | 7.8933 | 7.8933 | 7.8933 |  | No | Other | AMP7 carryover
| TMS | WWNI Thornwood STW G2G & P-removal | K831.01 | HNL00209 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2023-12-12 | 2026-02-02 | 2026-05-11 | 2027-11-17 | 2027-11-08 |  | IM2 | 2020-10-06 | 2023-12-12 | 2026-02-02 | 2026-05-11 | 2027-11-17 | 2027-09-08 |  |  | 0.81521 | 12.3423 | 13.1575 | 6.196% | 0.63992 | 0.72021 | 1.6697 | 6.7834 | 12.2121 | 13.2103 | 13.2103 | 13.2103 | 0.63992 | 0.72021 | 1.5425 | 6.2492 | 12.1629 | 13.1575 | 13.1575 | 13.1575 |  | No | Other | AMP7 carryover
| TMS | Stansted Mountfitchet STW Growth & Low P | K936.01 | HNL00225 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2019-10-17 | 2022-03-31 | 2025-10-06 | 2026-07-01 | 2028-03-27 | 2028-02-24 |  | IM2 | 2019-10-17 | 2022-03-31 | 2025-10-06 | 2026-07-01 | 2028-03-27 | 2027-12-24 |  |  | 2.2976 | 23.0019 | 25.2995 | 9.082% | 0.86162 | 2.2187 | 4.3912 | 11.7381 | 25.3252 | 33.688 | 48.9948 | 48.9948 | 0.86162 | 2.2187 | 4.3854 | 11.7056 | 25.2434 | 25.2633 | 25.2995 | 25.2995 |  | No | Other | AMP7 carryover
| TMS | WWNI Wingrave Compliance First & Low P | K984.01 | THM00570 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-02-22 | 2022-06-08 | 2024-01-31 | 2024-04-19 | 2026-01-13 | 2025-12-22 |  | IM4 | 2022-02-22 | 2022-06-08 | 2024-01-31 | 2024-04-19 | 2026-01-13 | 2025-10-22 |  |  | 8.5179 | 1.5374 | 10.0552 | 84.71% | 1.1748 | 6.7826 | 9.9564 | 10.0604 | 10.0604 | 10.0604 | 10.0604 | 10.0604 | 1.1748 | 6.7826 | 10.0521 | 10.0552 | 10.0552 | 10.0552 | 10.0552 | 10.0552 |  | No | Other | AMP7 carryover
| TMS | Theydon Bois STW WAAP and P-Removal | L470.01 | HNL00213 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-09-01 | 2023-11-23 | 2025-08-13 | 2025-11-05 | 2027-05-14 | 2027-05-03 |  | IM2 | 2022-09-01 | 2023-11-23 | 2025-10-14 | 2025-11-26 | 2027-06-08 | 2027-03-23 |  |  | 2.5993 | 14.1117 | 16.711 | 15.55% | 1.0093 | 2.4226 | 6.0581 | 15.4866 | 16.5314 | 16.7478 | 16.7478 | 16.7478 | 1.0093 | 2.4226 | 5.8432 | 15.5562 | 16.4548 | 16.711 | 16.711 | 16.711 |  | No | Other | AMP7 carryover
| TMS | Burghfield STW WAAP and P-Removal | L483.01 | THM00587 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2022-06-22 | 2025-10-27 | 2025-11-26 | 2027-07-13 | 2027-06-14 |  | IM2 | 2021-01-26 | 2022-06-22 | 2025-10-27 | 2026-01-06 | 2027-09-29 | 2027-05-12 |  |  | 2.2278 | 20.8312 | 23.059 | 9.661% | 0.37305 | 1.8872 | 4.8945 | 19.5316 | 22.9281 | 23.0751 | 23.0751 | 23.0751 | 0.37305 | 1.8872 | 3.9801 | 17.5972 | 22.9126 | 23.059 | 23.059 | 23.059 |  | No | Other | AMP7 carryover
| TMS | Waddesdon STW WAAP and P-Removal | L484.01 | THM00564 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-06-23 | 2025-04-17 | 2025-04-30 | 2026-12-09 | 2026-11-15 |  | IM4 | 2020-11-30 | 2021-06-23 | 2025-04-08 | 2025-04-30 | 2026-12-09 | 2026-09-15 |  |  | 2.0511 | 12.0874 | 14.1385 | 14.51% | 1.0074 | 1.7382 | 7.4806 | 13.5188 | 14.189 | 14.189 | 14.189 | 14.189 | 1.0074 | 1.7382 | 7.4544 | 13.4707 | 14.1385 | 14.1385 | 14.1385 | 14.1385 |  | No | Other | AMP7 carryover
| TMS | Shamley Green STW WAAP & P-Removal | L487.01 | THM00552 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2022-10-17 | 2024-02-01 | 2025-09-19 | 2026-01-02 | 2028-09-20 | 2028-08-29 |  | IM2 | 2022-10-17 | 2024-02-01 | 2025-09-19 | 2026-01-02 | 2028-09-20 | 2028-06-29 |  |  | 2.0145 | 16.2395 | 18.254 | 11.04% | 0.86505 | 2.2826 | 4.3774 | 11.2679 | 19.744 | 20.9933 | 21.0714 | 21.0714 | 0.86505 | 2.2826 | 4.3343 | 10.0375 | 17.1228 | 18.1761 | 18.254 | 18.254 |  | No | Other | AMP7 carryover
| TMS | North Weald STW PRemoval&Flow Compliance | L511.01 | HNL00208 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2023-12-01 | 2026-04-07 | 2026-06-09 | 2028-01-26 | 2028-01-29 |  | IM2 | 2020-11-30 | 2023-12-01 | 2026-06-09 | 2026-07-23 | 2028-03-08 | 2028-01-18 |  |  | 0.84647 | 28.8793 | 29.7258 | 2.848% | 0.1777 | 0.75095 | 1.8038 | 9.7648 | 27.3132 | 29.839 | 29.8402 | 29.8402 | 0.1777 | 0.75095 | 1.4951 | 9.2812 | 27.1963 | 29.6889 | 29.7258 | 29.7258 |  | No | Other | AMP7 carryover
| TMS | Wisley STW G2G and P-Removal | L514.01 | THM00571 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2025-01-23 | 2026-02-26 | 2026-06-30 | 2028-09-19 | 2028-09-06 |  | IM2 | 2021-01-26 | 2025-01-23 | 2026-02-26 | 2026-06-30 | 2028-09-19 | 2028-07-06 |  |  | 1.2181 | 42.756 | 43.9741 | 2.77% | 0 | 0.95462 | 4.4751 | 17.2536 | 37.4528 | 44.0721 | 44.152 | 44.152 | 0 | 0.95462 | 4.0078 | 17.1733 | 37.2992 | 43.8945 | 43.9741 | 43.9741 |  | No | Other | AMP7 carryover
| TMS | Weston on the Green STW Low P | L692.01 | THM00569 | P - Amber in Plan | PCDWW35 | Retained |  | N/A | 2024-12-22 | 2020-11-30 | 2021-08-31 | 2025-08-04 | 2025-11-04 | 2027-09-03 | 2027-05-31 |  | IM2 | 2020-11-30 | 2021-08-31 | 2025-09-30 | 2026-01-12 | 2027-09-03 | 2025-10-31 |  |  | 1.4375 | 9.9548 | 11.3923 | 12.62% | 0 | 1.2319 | 2.501 | 7.9669 | 10.3502 | 11.1374 | 11.1374 | 11.1374 | 0 | 1.2319 | 3.1177 | 7.9545 | 10.6079 | 11.3923 | 11.3923 | 11.3923 |  | No | Other | AMP7 carryover
| TMS | Blunsdon STW Low P | L694.01 | THM00585 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-11-24 | 2025-08-18 | 2025-09-23 | 2027-07-06 | 2027-03-18 |  | IM2 | 2020-11-30 | 2021-11-24 | 2025-08-18 | 2025-09-23 | 2027-07-06 | 2027-01-18 |  |  | 1.6836 | 5.391 | 7.0746 | 23.8% | 0 | 1.4749 | 2.8341 | 7.5306 | 8.6561 | 8.8424 | 8.8424 | 8.8424 | 0 | 1.4749 | 4.0963 | 6.7136 | 7.0746 | 7.0746 | 7.0746 | 7.0746 |  | No | Other | AMP7 carryover
| TMS | Barford St Michael STW Low P | L695.01 | THM00494 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-06-23 | 2024-09-02 | 2024-11-19 | 2025-10-22 | 2025-06-30 |  | IM4 | 2020-11-30 | 2021-06-23 | 2024-09-02 | 2024-11-19 | 2026-01-23 | 2025-10-31 |  |  | 1.6643 | 0.43366 | 2.098 | 79.33% | 0 | 1.6643 | 2.6068 | 2.7987 | 2.7987 | 2.7987 | 2.7987 | 2.7987 | 0 | 1.6643 | 2.098 | 2.098 | 2.098 | 2.098 | 2.098 | 2.098 |  | No | Other | AMP7 carryover
| TMS | Marsh Gibbon STW Low P | L696.01 | THM00543 | P - Amber in Plan | PCDWW35 | Retained |  | N/A | 2024-12-22 | 2020-11-30 | 2021-06-23 | 2024-08-05 | 2024-08-15 | 2025-04-30 | 2025-06-30 |  | IM4 | 2020-11-30 | 2021-06-23 | 2024-08-05 | 2024-08-15 | 2025-07-28 | 2025-10-31 |  |  | 0.704 | 2.0426 | 2.7466 | 25.63% | 0 | 0.704 | 2.5176 | 2.7695 | 2.7695 | 2.7695 | 2.7695 | 2.7695 | 0 | 0.704 | 1.8345 | 2.7466 | 2.7466 | 2.7466 | 2.7466 | 2.7466 |  | No | Other | AMP7 carryover
| TMS | Dorton STW Low P | L698.01 | THM00520 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2022-07-22 | 2025-08-18 | 2025-09-24 | 2027-06-24 | 2027-03-29 |  | IM2 | 2021-01-26 | 2022-07-22 | 2025-08-18 | 2025-09-24 | 2027-06-24 | 2027-01-29 |  |  | 1.528 | 4.6581 | 6.1861 | 24.7% | 0 | 1.2741 | 2.7921 | 6.1582 | 6.4041 | 6.4135 | 6.4135 | 6.4135 | 0 | 1.2741 | 3.689 | 5.8405 | 6.1861 | 6.1861 | 6.1861 | 6.1861 |  | No | Other | AMP7 carryover
| TMS | Tetsworth STW Low P | L699.01 | THM00562 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-09-22 | 2025-08-18 | 2025-09-30 | 2027-07-20 | 2027-06-15 |  | IM2 | 2020-11-30 | 2021-09-22 | 2025-09-19 | 2025-10-31 | 2028-01-13 | 2027-05-19 |  |  | 1.4461 | 5.1569 | 6.603 | 21.9% | 0 | 1.2625 | 2.6775 | 5.5686 | 5.9118 | 5.9327 | 5.9327 | 5.9327 | 0 | 1.2625 | 2.5784 | 5.2819 | 6.5319 | 6.603 | 6.603 | 6.603 |  | No | Other | AMP7 carryover
| TMS | South Leigh STW Low P | L700.01 | THM00558 | P - Amber in Plan | PCDWW35 | Retained |  | N/A | 2024-12-22 | 2020-11-30 | 2022-07-20 | 2024-10-02 | 2024-10-02 | 2025-09-10 | 2025-06-30 |  | IM4 | 2020-11-30 | 2022-07-20 | 2024-10-02 | 2024-10-02 | 2025-12-04 | 2025-10-31 |  |  | 0.69778 | 1.1537 | 1.8515 | 37.69% | 0 | 0.69778 | 1.6093 | 1.857 | 1.857 | 1.857 | 1.857 | 1.857 | 0 | 0.69778 | 1.5203 | 1.8515 | 1.8515 | 1.8515 | 1.8515 | 1.8515 |  | No | Other | AMP7 carryover
| TMS | Stanton Harcourt STW Low P | L701.01 | THM00561 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-07 | 2021-11-24 | 2024-09-16 | 2024-09-11 | 2025-09-11 | 2025-05-21 |  | IM4 | 2020-12-07 | 2021-11-24 | 2024-09-16 | 2024-09-16 | 2025-09-08 | 2025-10-31 |  |  | 0.83005 | 0.90596 | 1.736 | 47.81% | 0 | 0.83239 | 1.3103 | 1.7396 | 1.7396 | 1.7396 | 1.7396 | 1.7396 | 0 | 0.83239 | 1.3196 | 1.736 | 1.736 | 1.736 | 1.736 | 1.736 |  | No | Other | AMP7 carryover
| TMS | Weston (Herts) STW Low P | L702.01 | HNL00217 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2024-09-18 | 2026-03-05 | 2026-05-18 | 2028-05-17 | 2028-04-09 |  | IM2 | 2020-11-30 | 2024-09-18 | 2026-03-26 | 2026-05-18 | 2028-05-17 | 2028-02-09 |  |  | 1.5166 | 6.5566 | 8.0733 | 18.79% | 0 | 1.4261 | 2.5964 | 5.0232 | 9.3334 | 9.6315 | 9.6422 | 9.6422 | 0 | 1.4261 | 2.5135 | 4.4093 | 7.7741 | 8.0626 | 8.0733 | 8.0733 |  | No | Other | AMP7 carryover
| TMS | Bishops Stortford STW Low P | L703.01 | HNL00226 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2021-12-20 | 2026-02-05 | 2026-05-12 | 2028-08-15 | 2028-07-02 |  | IM2 | 2020-11-30 | 2021-12-20 | 2026-03-26 | 2026-06-16 | 2028-09-19 | 2028-06-06 |  |  | 2.8501 | 7.0232 | 9.8733 | 28.87% | 0 | 2.7882 | 3.7284 | 5.8298 | 11.5314 | 11.9655 | 12.1761 | 12.1761 | 0 | 2.7882 | 3.6689 | 4.8593 | 9.2084 | 9.6131 | 9.8733 | 9.8733 |  | No | Other | AMP7 carryover
| TMS | Hartley Wintney STW Low P | L704.01 | THM00602 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-06-23 | 2026-01-09 | 2026-05-12 | 2028-01-21 | 2027-11-29 |  | IM2 | 2021-01-26 | 2021-06-23 | 2026-03-26 | 2026-06-16 | 2028-02-24 | 2027-11-02 |  |  | 2.3996 | 4.7639 | 7.1635 | 33.5% | 0 | 2.3342 | 3.5253 | 6.9626 | 9.5545 | 9.7611 | 9.789 | 9.789 | 0 | 2.3342 | 3.5077 | 4.9855 | 6.9168 | 7.111 | 7.1635 | 7.1635 |  | No | Other | AMP7 carryover
| TMS | Godalming STW Low P | L705.01 | THM00525 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2021-06-23 | 2026-01-09 | 2026-04-13 | 2028-10-25 | 2028-09-12 |  | IM2 | 2021-01-26 | 2021-06-23 | 2025-11-25 | 2026-03-05 | 2028-09-20 | 2028-06-07 |  |  | 2.3166 | 9.8282 | 12.1448 | 19.07% | 0 | 2.1319 | 2.8794 | 5.4993 | 12.935 | 13.6416 | 13.948 | 13.948 | 0 | 2.1319 | 4.1796 | 6.5666 | 11.4858 | 11.8607 | 12.1448 | 12.1448 |  | No | Other | AMP7 carryover
| TMS | Hockford STW Low P | L706.01 | THM00754 | P - Amber NOT in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2021-01-26 | 2024-09-18 | 2026-04-08 | 2026-07-14 | 2028-10-24 | 2028-09-04 |  | IM2 | 2021-01-26 | 2024-09-18 | 2026-03-26 | 2026-07-14 | 2028-10-24 | 2028-07-04 |  |  | 0.78015 | 5.6495 | 6.4297 | 12.13% | 0 | 0.75416 | 1.3176 | 2.1967 | 6.7416 | 7.2535 | 7.4816 | 7.4816 | 0 | 0.75416 | 1.9854 | 2.6026 | 5.8202 | 6.2024 | 6.4297 | 6.4297 |  | No | Other | AMP7 carryover
| TMS | Merstham STW Low P | L707.01 | KSL00234 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-03-05 | 2026-07-14 | 2028-07-17 | 2028-06-05 |  | IM2 | 2020-10-06 | 2024-09-18 | 2026-03-26 | 2026-06-29 | 2028-06-30 | 2028-03-21 |  |  | 1.8266 | 5.0916 | 6.9182 | 26.4% | 0 | 1.5543 | 2.4411 | 3.9438 | 8.5288 | 8.6719 | 8.6793 | 8.6793 | 0 | 1.5543 | 2.4764 | 3.7215 | 6.8339 | 6.9118 | 6.9182 | 6.9182 |  | No | Other | AMP7 carryover
| TMS | Elstead STW Low P | L708.01 | THM00521 | P - Amber in Plan | PCDWW35 | Retained |  | N/A | 2024-12-22 | 2020-11-30 | 2021-06-17 | 2025-09-18 | 2026-01-07 | 2027-06-11 | 2027-04-16 |  | IM2 | 2020-11-30 | 2021-06-17 | 2025-12-12 | 2026-04-02 | 2027-09-07 | 2025-10-31 |  |  | 2.1633 | 7.4863 | 9.6496 | 22.42% | 0 | 2.1323 | 3.891 | 8.8036 | 9.6662 | 9.7326 | 9.7326 | 9.7326 | 0 | 2.1323 | 3.2256 | 7.8757 | 9.5057 | 9.6496 | 9.6496 | 9.6496 |  | No | Other | AMP7 carryover
| TMS | Stanford Rivers STW Low P | L709.01 | HNL00212 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2025-05-22 | 2026-07-31 | 2026-11-25 | 2029-06-19 | 2029-05-01 |  | IM2 | 2020-11-30 | 2025-06-19 | 2026-07-23 | 2027-03-02 | 2029-09-17 | 2029-06-04 |  |  | 0.13649 | 11.0941 | 11.2306 | 1.215% | 0 | 0.1349 | 0.48672 | 1.4039 | 7.0733 | 11.4759 | 11.6215 | 11.6424 | 0 | 0.1349 | 0.43126 | 1.2281 | 4.5727 | 10.8106 | 11.1829 | 11.2306 |  | No | Other | AMP7 carryover
| TMS | Standon STW Low P | L712.01 | HNL00222 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2024-09-18 | 2025-09-09 | 2026-04-07 | 2027-11-22 | 2027-10-04 |  | IM2 | 2020-11-30 | 2024-09-18 | 2026-01-06 | 2026-07-29 | 2028-03-20 | 2027-11-24 |  |  | 0.48142 | 8.8385 | 9.3199 | 5.166% | 0 | 0.46753 | 1.4383 | 7.6375 | 9.9942 | 10.3093 | 10.3093 | 10.3093 | 0 | 0.46753 | 0.51072 | 2.985 | 8.9422 | 9.2167 | 9.3199 | 9.3199 |  | No | Other | AMP7 carryover
| TMS | Epping (Fiddlers Hamlet) STW Low P | L713.01 | HNL00252 | P - Green | PCDWW35 | Retained |  | N/A | 2026-05-12 | 2020-10-06 | 2021-11-24 | 2026-04-08 | 2026-07-28 | 2029-02-21 | 2028-12-25 |  | IM2 | 2020-10-06 | 2021-11-24 | 2026-03-26 | 2026-07-28 | 2029-02-21 | 2025-10-31 |  |  | 2.3033 | 8.4149 | 10.7182 | 21.49% | 0 | 2.2409 | 3.1145 | 4.1756 | 11.0197 | 12.7694 | 12.8915 | 12.9229 | 0 | 2.2409 | 3.1797 | 4.0408 | 9.2351 | 10.5654 | 10.687 | 10.7182 | merge ok | No | Other | AMP7 carryover
| TMS | Epping (Fiddlers Hamlet) STW Low P | L713.01 | HNL00211 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2021-11-24 | 2026-04-08 | 2026-07-28 | 2029-02-21 | 2028-12-25 |  | IM2 | 2020-10-06 | 2021-11-24 | 2026-03-26 | 2026-07-28 | 2029-02-21 | 2025-10-31 |  |  |  |  | 0 | #DIV/0! | [16 empty] | merge ok | No | Other | AMP7 carryover
| TMS | Braughing STW Low P | L718.01 | HNL00220 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-30 | 2024-09-18 | 2026-01-09 | 2026-03-12 | 2028-03-22 | 2028-02-01 |  | IM2 | 2020-11-30 | 2024-09-18 | 2026-03-26 | 2026-05-19 | 2028-05-30 | 2028-02-10 |  |  | 1.9476 | 6.4637 | 8.4113 | 23.15% | 0 | 1.8837 | 2.5862 | 6.5879 | 9.9963 | 10.1959 | 10.2736 | 10.2736 | 0 | 1.8837 | 3.486 | 5.0613 | 8.0981 | 8.2842 | 8.4113 | 8.4113 |  | No | Other | AMP7 carryover
| TMS | Holmwood STW WAAP and P-Removal | L745.01 | KSL00233 | P - Amber in Plan | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2024-06-01 | 2024-05-31 | 2026-01-23 | 2026-03-20 | 2028-06-15 | 2028-05-30 |  | IM2 | 2024-06-01 | 2024-05-31 | 2026-05-28 | 2026-08-04 | 2028-10-25 | 2028-08-14 |  |  | 2.3164 | 15.7046 | 18.0211 | 12.85% | 0 | 2.1297 | 3.5227 | 9.9999 | 17.9597 | 18.1565 | 18.2204 | 18.2204 | 0 | 2.1297 | 2.94 | 6.2911 | 15.8613 | 17.9181 | 18.0211 | 18.0211 |  | No | Other | AMP7 carryover
| TMS | Bexley WTW – Alleviation of Low Flows (W | K035.01 | KSL00046 | Closure of the North Orpington abstraction to protect the environment in the river Cray. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-03-25 | 2021-05-26 | 2025-06-30 | 2026-01-05 | 2030-06-13 | 2030-05-29 |  | IM3 | 2020-03-25 | 2021-05-26 | 2025-05-16 | 2025-11-17 | 2030-06-04 | 2030-05-24 |  |  | 6.6223 | 78.2582 | 84.8805 | 7.802% | 5.5566 | 6.4673 | 10.786 | 44.971 | 71.7926 | 82.0305 | 83.9824 | 85.4069 | 5.5566 | 6.4673 | 10.7147 | 37.7638 | 66.2434 | 81.8288 | 83.7712 | 84.8805 | merge ok | No | Other | AMP7 carryover
| TMS | Bexley WTW – Alleviation of Low Flows (W | K035.01 | KSL00044 | River restoration to improve flow conditions in the lower Cray | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-03-25 | 2021-05-26 | 2025-06-30 | 2026-01-05 | 2030-06-13 | 2030-05-29 |  | IM3 | 2020-03-25 | 2021-05-26 | 2025-05-16 | 2025-11-17 | 2030-06-04 | 2030-05-24 |  |  |  |  | 0 | #DIV/0! | [16 empty] | merge ok |  |  | AMP7 carryover
| TMS | LF Mitigation TV - Continue the river restoration work from AMP7 for Farmoor (Oxford Water Course) | K560.01 | THM00759 | River restoration to improve environmental resiliance on the Oxford Watercourses. | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2025-10-24 | 2025-11-14 | 2027-02-08 | 2027-02-02 |  | IM3 | 2020-05-13 | 2022-03-16 | 2025-05-29 | 2025-07-21 | 2027-02-08 | 2026-12-02 |  |  | 1.4439 | 7.2275 | 8.6714 | 16.65% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.35444 | 0.32366 | 1.456 | 2.1378 | 2.1662 | 2.1678 | 2.1678 | 2.1678 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation TV - Continue the river restoration work from AMP7 for Pangbourne on the Sulham Brook | K560.02 | THM00758 | River restoration to improve environmental resiliance on the Sulham Brook. | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2025-04-01 | 2025-08-15 | 2026-06-19 | 2026-05-31 |  | IM4 | 2020-05-13 | 2022-03-16 | 2025-01-20 | 2025-04-14 | 2026-06-19 | 2026-03-31 |  |  | 1.4439 | 7.2275 | 8.6714 | 16.65% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.35444 | 0.32366 | 1.456 | 2.1378 | 2.1662 | 2.1678 | 2.1678 | 2.1678 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation TV - Continue the river restoration work from AMP7 for Pann Mill | K560.03 | THM00760 | River restoration to improve environmental resiliance on the river Wye | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2027-08-23 | 2028-01-10 | 2029-01-18 | 2028-12-26 |  | IM2 | 2020-05-13 | 2022-03-16 | 2027-10-27 | 2028-03-14 | 2029-03-23 | 2028-12-26 |  |  | 1.4439 | 7.2275 | 8.6714 | 16.65% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.17722 | 0.16183 | 0.72799 | 1.0689 | 1.0831 | 1.0839 | 1.0839 | 1.0839 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation TV - RIVER RESTORATION PROJECTS - CHESS | K560.04 | HNL00095 | River restoration to improve environmental resiliance on the river Chess | PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2020-05-13 | 2022-03-16 | 2022-03-16 | 2025-03-28 | 2026-06-19 | 2026-05-31 |  | IM4 | 2020-05-13 | 2022-03-16 | 2022-03-16 | 2025-03-28 | 2026-06-19 | 2026-03-31 |  |  | 1.4439 | 7.2275 | 8.6714 | 16.65% | 0.17722 | 0.16183 | 0.50763 | 1.0577 | 1.068 | 1.0686 | 1.0686 | 1.0686 | 0.17722 | 0.16183 | 0.72799 | 1.0689 | 1.0831 | 1.0839 | 1.0839 | 1.0839 |  | No | Other | AMP7 carryover
| TMS | Hawridge - Alleviation of Low Flows | K036.01 | HNL00092 | Closure of the abstraction at Hawridge in the Chess catchment | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-02-25 | 2021-05-27 | 2026-11-20 | 2027-08-12 | 2029-11-01 | 2029-11-10 |  | IM2 | 2020-02-25 | 2021-05-27 | 2026-11-20 | 2027-08-12 | 2029-11-01 | 2029-09-10 |  |  | 2.7947 | 50.0088 | 52.8035 | 5.293% | 2.3504 | 2.7251 | 4.8787 | 7.8833 | 15.0822 | 34.1807 | 52.9793 | 52.9793 | 2.3504 | 2.7251 | 4.7312 | 7.8711 | 15.0439 | 34.0732 | 52.8035 | 52.8035 |  | No | Other | AMP7 carryover
| TMS | Lower Lee River Improvements | K559.01 | HNL00096 | River restoration and improvements to fish passage in the Lower lee to improve environmental resilience | PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2021-05-04 | 2022-01-25 | 2026-10-07 | 2027-02-11 | 2029-04-27 | 2029-02-15 |  | IM2 | 2021-05-04 | 2022-01-25 | 2026-10-07 | 2027-02-11 | 2029-04-27 | 2028-12-15 |  |  | 0.59189 | 9.6528 | 10.2446 | 5.778% | 0.45493 | 0.46531 | 0.7329 | 1.3518 | 6.1089 | 10.1286 | 10.188 | 10.2071 | 0.45493 | 0.46531 | 1.5031 | 2.0104 | 6.4321 | 10.1684 | 10.2256 | 10.2446 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation London - Upper Cray Restoration | K561.01 | KSL00401 | River restoration to improve environmental resilience on the river Cray. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 1.1381 | 15.2994 | 16.4375 | 6.924% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.19759 | 0.20124 | 0.45564 | 0.6342 | 2.2876 | 3.2641 | 3.2837 | 3.2875 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation London - Upper Darent Restoration - SUNDRIDGE PUMPING STATION | K561.02 | KSL00045 | River restoration to improve environmental resilience on the river Darent. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 1.1381 | 15.2994 | 16.4375 | 6.924% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.19759 | 0.20124 | 0.45564 | 0.6342 | 2.2876 | 3.2641 | 3.2837 | 3.2875 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation London - Upper Darent Restoration - WESTERHAM HILL PS | K561.03 | KSL00049 | River restoration to improve environmental resilience on the river Darent. | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 1.1381 | 15.2994 | 16.4375 | 6.924% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.19759 | 0.20124 | 0.45564 | 0.6342 | 2.2876 | 3.2641 | 3.2837 | 3.2875 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation London - Wandle Restoration - BRANTWOOD ROAD, CROYDON | K561.04 | KSL00047 | River restoration to improve environmental resilience on the river Wandle | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 1.1381 | 15.2994 | 16.4375 | 6.924% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.19759 | 0.20124 | 0.45564 | 0.6342 | 2.2876 | 3.2641 | 3.2837 | 3.2875 |  | No | Other | AMP7 carryover
| TMS | LF Mitigation London - Wandle Restoration - WADDON PUMPING STATION - WELLS & BOREHOLES | K561.05 | KSL00048 | River restoration to improve environmental resilience on the river Wandle | This part of the AMP7 project is not PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-09-03 |  | IM2 | 2020-05-27 | 2022-02-22 | 2026-11-11 | 2027-02-26 | 2028-11-22 | 2028-07-03 |  |  | 1.1381 | 15.2994 | 16.4375 | 6.924% | 0.1066 | 0.10818 | 0.15995 | 0.23291 | 1.0048 | 1.2348 | 1.243 | 1.243 | 0.19759 | 0.20124 | 0.45564 | 0.6342 | 2.2876 | 3.2641 | 3.2837 | 3.2875 |  | No | Other | AMP7 carryover
| TMS | BENTLEY STW | K932.01 | THM00581 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2000-01-01 | 2021-04-21 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | IM6 | 2000-01-01 | 2021-04-21 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  |  | 0.089187 | 2.1644 | 2.2536 | 3.958% | 0.085236 | 0.089187 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 0.085236 | 0.089187 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 2.1644 | 2.1644 |  | No | Other | AMP7 carryover
| TMS | BRENTWOOD SEWAGE TREATMENT WORKS | K556.03 | HNL00253 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2026-05-12 | 2025-03-31 | 2000-01-01 | 2021-08-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | IM6 | 2000-01-01 | 2021-08-02 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  |  | 0.048449 | 0.048449 | 0.096899 | 50% | 0.23849 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.23849 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 | 0.048449 |  | No | Other | AMP7 carryover
| TMS | WINEP - Catchment Management | K360 | HNL00087 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 3.614 | 3.6843 | 7.2983 | 49.52% | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 |  | No | Other | AMP7 carryover
| TMS | WINEP - Catchment Management | K360 | HNL00088 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 3.614 | 3.6843 | 7.2983 | 49.52% | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 |  | No | Other | AMP7 carryover
| TMS | WINEP - Catchment Management | K360 | HNL00089 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 3.614 | 3.6843 | 7.2983 | 49.52% | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 |  | No | Other | AMP7 carryover
| TMS | WINEP - Catchment Management | K360 | HNL00090 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 3.614 | 3.6843 | 7.2983 | 49.52% | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 |  | No | Other | AMP7 carryover
| TMS | WINEP - Catchment Management | K360 | HNL00094 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  | IM6 | 2020-12-23 | 2021-07-01 | 2021-07-02 | 2024-12-22 | 2024-12-22 | 2024-12-22 |  |  | 3.614 | 3.6843 | 7.2983 | 49.52% | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.28725 | 0.72279 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 | 0.73686 |  | No | Other | AMP7 carryover
| TMS | Lewknor STW Low P | L697 | THM00538 | PR19 WINEP Carryover actions | PCDWW35 | Retained |  | 2024-12-22 | 2024-12-22 | 2000-01-01 | 2023-02-23 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  | IM6 | 2000-01-01 | 2023-02-23 | 2025-03-31 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  |  | 1.2123 | 5.501 | 6.7132 | 18.06% | 0 | 1.2123 | 3.2942 | 5.4546 | 5.501 | 5.501 | 5.501 | 5.501 | 0 | 1.2123 | 3.2942 | 5.4546 | 5.501 | 5.501 | 5.501 | 5.501 |  | No | Other | AMP7 carryover
| TMS | WWNI Mill Green STW G2G and Low P | K649.01 | HNL00216 | P - Amber NOT in Plan | PCDWW35 | Retained |  | N/A | 2024-12-22 | 2021-01-26 | 2021-08-26 | 2024-06-28 | 2025-04-22 | 2027-05-12 | 2027-05-19 |  | IM4 | 2021-01-26 | 2021-08-26 | 2024-06-28 | 2025-03-31 | 2025-03-31 | 2025-03-31 |  |  | 9.5373 | 1.1428 | 10.6801 | 89.3% | 1.1428 | 4.9906 | 14.004 | 19.1132 | 19.1182 | 19.1182 | 19.1182 | 19.1182 | 1.1428 | 4.9906 | 12.0181 | 15.3154 | 15.5217 | 15.5217 | 15.5217 | 15.5217 |  | No | Other | AMP7 carryover
| TMS | Abbess Roding STW Phos Dosing TT + Alkal | UBA8.SEW.S38981 | 08TW100967a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-11-20 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 4.8334 | 4.8334 | 0% | 0 | 0 | 0 | 0 | 0.20017 | 0.72695 | 1.74 | 4.8334 | 0 | 0 | 0 | 0 | 0.20017 | 0.72695 | 1.74 | 4.8334 |  | No | Delivery Mechanism | AMP8
| TMS | Aldershot STW Phos Dosing TT + Alkalini | UBA8.SEW.S38954 | 08TW100862a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-07-06 | 2028-10-14 | 2029-05-01 | 2031-03-09 | 2032-03-31 |  |  | 2024-10-16 | 2027-07-06 | 2028-10-14 | 2029-05-01 | 2031-03-09 | 2032-03-31 |  |  | 0 | 12.7817 | 12.7817 | 0% | 0 | 0 | 0 | 0 | 0.52565 | 1.8328 | 4.1999 | 12.7817 | 0 | 0 | 0 | 0 | 0.52565 | 1.8328 | 4.1999 | 12.7817 |  | No | Delivery Mechanism | AMP8
| TMS | Andoversford STW - AMP8 Growth | UBA8.SEW.S40433 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2025-07-16 | 2026-05-18 | 2026-12-07 | 2028-11-15 | 2030-03-31 |  |  | 2024-10-16 | 2025-07-16 | 2026-05-18 | 2026-12-07 | 2028-11-15 | 2030-03-31 |  |  | 0 | 5.7598 | 5.7598 | 0% | 0 | 0 | 0 | 0.42451 | 1.3644 | 3.2303 | 5.6492 | 5.7598 | 0 | 0 | 0 | 0.42451 | 1.3644 | 3.2303 | 5.6492 | 5.7598 |  | No | Other | AMP8
| TMS | Appleton STW Phosphorus Dosing and TT | UBA8.SEW.S39552 | 08TW100863a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-10-16 | 2025-12-23 | 2026-12-27 | 2027-07-28 | 2030-10-28 | 2032-03-31 |  |  | 2024-10-16 | 2025-12-23 | 2026-12-27 | 2027-07-28 | 2030-10-28 | 2032-03-31 |  |  | 0 | 7.067 | 7.067 | 0% | 0 | 0 | 0 | 0 | 0.42376 | 1.5073 | 3.5161 | 7.067 | 0 | 0 | 0 | 0 | 0.42376 | 1.5073 | 3.5161 | 7.067 |  | No | Delivery Mechanism | AMP8
| TMS | Arborfield STW - AMP8 Growth | UBA8.SEW.S38253 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2026-03-10 | 2027-04-25 | 2027-10-30 | 2029-12-11 | 2031-03-31 |  |  | 2024-10-16 | 2026-03-10 | 2027-04-25 | 2027-10-30 | 2029-12-11 | 2031-03-31 |  |  | 0 | 43.5312 | 43.5312 | 0% | 0 | 0 | 2.3846 | 6.8297 | 10.9268 | 26.033 | 42.2986 | 43.5312 | 0 | 0 | 2.3846 | 6.8297 | 10.9268 | 26.033 | 42.2986 | 43.5312 |  | No | Other | AMP8
| TMS | Arborfield STW Cypermethrin - IMP & ND | UBA8.SEW.S40667 | 08TW101448a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2028-12-22 | 2030-02-14 | 2030-08-17 | 2032-11-15 | 2034-03-31 |  |  | 2024-10-16 | 2028-12-22 | 2030-02-14 | 2030-08-17 | 2032-11-15 | 2034-03-31 |  |  | 0 | 18.3279 | 18.3279 | 0% | 0 | 0 | 0 | 0.029304 | 2.8237 | 4.9386 | 12.6782 | 18.3279 | 0 | 0 | 0 | 0.029304 | 2.8237 | 4.9386 | 12.6782 | 18.3279 |  | No | Delivery Mechanism | AMP8
| TMS | Arborfield STW Phos Dosing TT + Alkalin | UBA8.SEW.S39006 | 08TW100864a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-03-10 | 2026-04-25 | 2026-10-30 | 2028-12-11 | 2030-03-31 |  |  | 2024-10-16 | 2025-03-10 | 2026-04-25 | 2026-10-30 | 2028-12-11 | 2030-03-31 |  |  | 0 | 11.9786 | 11.9786 | 0% | 0 | 0 | 0.66968 | 1.9337 | 3.7402 | 9.274 | 11.8264 | 11.9786 | 0 | 0 | 0.66968 | 1.9337 | 3.7402 | 9.274 | 11.8264 | 11.9786 |  | No | Other | AMP8
| TMS | Ascot STW Phosphorus Dosing and TT | UBA8.SEW.S39004 | 08TW100865a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-05-13 | 2028-04-17 | 2028-10-30 | 2029-12-12 | 2031-03-31 |  |  | 2024-10-16 | 2027-05-13 | 2028-04-17 | 2028-10-30 | 2029-12-12 | 2031-03-31 |  |  | 0 | 13.4404 | 13.4404 | 0% | 0 | 0 | 0 | 0 | 0.81712 | 2.188 | 5.4784 | 13.4404 | 0 | 0 | 0 | 0 | 0.81712 | 2.188 | 5.4784 | 13.4404 |  | No | Delivery Mechanism | AMP8
| TMS | Ash Vale STW Phosphorus Dosing TT + PST | UBA8.SEW.S39056 | 08TW100866a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-10-06 | 2029-01-14 | 2029-08-01 | 2031-03-10 | 2032-03-31 |  |  | 2024-10-16 | 2027-10-06 | 2029-01-14 | 2029-08-01 | 2031-03-10 | 2032-03-31 |  |  | 0 | 10.988 | 10.988 | 0% | 0 | 0 | 0 | 0 | 0.10115 | 1.6127 | 3.6397 | 10.988 | 0 | 0 | 0 | 0 | 0.10115 | 1.6127 | 3.6397 | 10.988 |  | No | Delivery Mechanism | AMP8
| TMS | Ashendon STW - Phosphorus - Dosing Only | UBA8.SEW.S39551 | 08TW100953a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-11-29 | 2025-06-16 | 2026-01-09 | 2027-11-18 | 2029-03-31 |  |  | 2024-10-16 | 2024-11-29 | 2025-06-16 | 2026-01-09 | 2027-11-18 | 2029-03-31 |  |  | 0 | 1.6768 | 1.6768 | 0% | 0 | 0 | 0.015548 | 0.29297 | 0.74207 | 1.6349 | 1.6674 | 1.6768 | 0 | 0 | 0.015548 | 0.29297 | 0.74207 | 1.6349 | 1.6674 | 1.6768 |  | No | Other | AMP8
| TMS | Aston Le Walls STW Phosphorus Dosing | UBA8.SEW.S39031 | 08TW100960a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-05-19 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 2024-10-16 | 2027-05-19 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 0 | 2.3863 | 2.3863 | 0% | 0 | 0 | 0 | 0 | 0.09886 | 0.40908 | 1.0508 | 2.3863 | 0 | 0 | 0 | 0 | 0.09886 | 0.40908 | 1.0508 | 2.3863 |  | No | Delivery Mechanism | AMP8
| TMS | Banbury STW - Phosphorus - Bio-P and TT | UBA8.SEW.S38967 | 08TW100869a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-05-04 | 2029-11-29 | 2030-02-05 | 2033-01-27 | 2034-03-31 |  |  | 2024-10-16 | 2029-05-04 | 2029-11-29 | 2030-02-05 | 2033-01-27 | 2034-03-31 |  |  | 0 | 27.4266 | 27.4266 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1.1942 | 27.4266 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1942 | 27.4266 |  | No | Delivery Mechanism | AMP8
| TMS | BASILDON PARK STW | UBA8.SEW.S41639 | 08TW101402a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-04-22 | 2027-02-08 | 2027-08-23 | 2028-12-13 | 2030-03-31 |  |  | 2025-04-01 | 2026-04-22 | 2027-02-08 | 2027-08-23 | 2028-12-13 | 2030-03-31 |  |  | 0 | 1.3853 | 1.3853 | 0% | 0 | 0 | 0.20569 | 0.38176 | 0.71707 | 1.1472 | 1.36 | 1.3853 | 0 | 0 | 0.20569 | 0.38176 | 0.71707 | 1.1472 | 1.36 | 1.3853 |  | No | Other | AMP8
| TMS | Basingstoke STW Phos TT + Alkalinity | UBA8.SEW.S38948 | 09TW100022a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-04-04 | 2030-02-22 | 2030-08-21 | 2032-11-24 | 2034-03-31 |  |  | 2024-10-16 | 2029-04-04 | 2030-02-22 | 2030-08-21 | 2032-11-24 | 2034-03-31 |  |  | 0 | 21.547 | 21.547 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.9394 | 21.547 | 0 | 0 | 0 | 0 | 0 | 0 | 0.9394 | 21.547 |  | No | Delivery Mechanism | AMP8
| TMS | Beckton STW Upgraded THP - SAS only | UBA8.SEW.S39830 |  | Gated scheme - NO PCD | Gated scheme - NO PCD | Retained |  |  |  | 2025-09-08 | 2029-01-11 | 2031-03-31 | 2032-07-01 | 2035-06-30 | 2036-03-31 |  |  | 2025-09-08 | 2029-01-11 | 2031-03-31 | 2032-07-01 | 2035-06-30 | 2036-03-31 |  |  | 0 | 218.0874 | 218.0874 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 1.5446 | 218.0874 | 0 | 0 | 0 | 0 | 0 | 0 | 1.5446 | 218.0874 |  | No | Large gated | AMP8
| TMS | Berkhamstead STW - Phosphorus - New TT | UBA8.SEW.S38965 | 09TW100023a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2029-08-29 | 2030-09-13 | 2031-03-15 | 2032-11-20 | 2034-03-31 |  |  | 2024-11-20 | 2029-08-29 | 2030-09-13 | 2031-03-15 | 2032-11-20 | 2034-03-31 |  |  | 0 | 8.794 | 8.794 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.36165 | 8.794 | 0 | 0 | 0 | 0 | 0 | 0 | 0.36165 | 8.794 |  | No | Delivery Mechanism | AMP8
| TMS | Bicester STW - AMP8 Growth | UBA8.SEW.S40437 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2029-11-13 | 2030-07-06 | 2030-10-02 | 2032-03-31 | 2033-03-31 |  |  | 2024-10-16 | 2029-11-13 | 2030-07-06 | 2030-10-02 | 2032-03-31 | 2033-03-31 |  |  | 0 | 92.0895 | 92.0895 | 0% | 0 | 0 | 0 | 0 | 4.4523 | 15.8167 | 39.9032 | 92.0895 | 0 | 0 | 0 | 0 | 4.4523 | 15.8167 | 39.9032 | 92.0895 |  | No | Other | AMP8
| TMS | Bicester STW Phos Dosing TT + Alkalinity | UBA8.SEW.S38939 | 08TW100872a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-28 | 2029-02-22 | 2029-08-19 | 2031-11-23 | 2033-03-31 |  |  | 2024-10-16 | 2028-08-28 | 2029-02-22 | 2029-08-19 | 2031-11-23 | 2033-03-31 |  |  | 0 | 20.012 | 20.012 | 0% | 0 | 0 | 0 | 0 | 0.65025 | 2.2424 | 4.8095 | 20.012 | 0 | 0 | 0 | 0 | 0.65025 | 2.2424 | 4.8095 | 20.012 |  | No | Delivery Mechanism | AMP8
| TMS | Bledington STW Phosphorus Dosing Only | UBA8.SEW.S39023 | 08TW100873a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2025-06-15 | 2026-01-09 | 2027-11-16 | 2029-03-31 |  |  | 2024-10-16 | 2024-10-16 | 2025-06-15 | 2026-01-09 | 2027-11-16 | 2029-03-31 |  |  | 0 | 2.0331 | 2.0331 | 0% | 0 | 0 | 0.12828 | 0.49692 | 1.2687 | 2.0082 | 2.0254 | 2.0331 | 0 | 0 | 0.12828 | 0.49692 | 1.2687 | 2.0082 | 2.0254 | 2.0331 |  | No | Other | AMP8
| TMS | Bletchingdon STW Phosphorus Stretch Targ | UBA8.SEW.S41885 | 08TW100874a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-10-18 | 2028-04-10 | 2028-10-02 | 2030-12-11 | 2032-03-31 |  |  | 2024-10-16 | 2027-10-18 | 2028-04-10 | 2028-10-02 | 2030-12-11 | 2032-03-31 |  |  | 0 | 8.9596 | 8.9596 | 0% | 0 | 0 | 0 | 0 | 0.083241 | 1.3335 | 2.6643 | 8.9596 | 0 | 0 | 0 | 0 | 0.083241 | 1.3335 | 2.6643 | 8.9596 |  | No | Delivery Mechanism | AMP8
| TMS | Bloxham STW Phosphorus Dosing TT + Alkal | UBA8.SEW.S41908 | 08TW100875a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 6.6835 | 6.6835 | 0% | 0 | 0 | 0.40076 | 1.4255 | 3.3253 | 6.4998 | 6.6344 | 6.6835 | 0 | 0 | 0.40076 | 1.4255 | 3.3253 | 6.4998 | 6.6344 | 6.6835 |  | No | Other | AMP8
| TMS | Blunsdon STW - AMP8 Growth | UBA8.SEW.S38261 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2026-03-07 | 2027-02-11 | 2027-08-25 | 2028-12-15 | 2030-03-31 |  |  | 2024-10-16 | 2026-03-07 | 2027-02-11 | 2027-08-25 | 2028-12-15 | 2030-03-31 |  |  | 0 | 10.7345 | 10.7345 | 0% | 0 | 0 | 0.45022 | 1.5224 | 2.6785 | 6.5562 | 10.4728 | 10.7345 | 0 | 0 | 0.45022 | 1.5224 | 2.6785 | 6.5562 | 10.4728 | 10.7345 |  | No | Other | AMP8
| TMS | Bourton on the Water STW Low P & TT | L956 | 08TW100877a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-10-16 | 2026-02-11 | 2026-12-07 | 2027-05-13 | 2030-03-07 | 2031-03-31 |  |  | 2024-10-16 | 2026-02-11 | 2026-12-07 | 2027-05-13 | 2030-03-07 | 2031-03-31 |  |  | 0.013552 | 6.6497 | 6.6633 | 0.2034% | 0 | 0.013552 | 0.16088 | 1.2595 | 3.2942 | 5.9721 | 6.6022 | 6.6497 | 0 | 0.013552 | 0.16088 | 1.2595 | 3.2942 | 5.9721 | 6.6022 | 6.6497 |  | No | Other | AMP8
| TMS | Bracknell STW AMP8 Low P BOD and Chem | L842 | 09TW100015a, 08TW100878a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  |  | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  |  | 0 | 26.8074 | 26.8074 | 0% | 0 | 0 | 0.77 | 7.1498 | 12.1465 | 16.0617 | 18.7218 | 26.8074 | 0 | 0 | 0.77 | 7.1498 | 12.1465 | 16.0617 | 18.7218 | 26.8074 |  | Yes | Delivery Mechanism | AMP8
| TMS | Bracknell STW AMP8 Low P BOD and Chem | L842 | 08TW101449a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  |  | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  |  | 0 | 46.2197 | 46.2197 | 0% | 0 | 0 | 1.3276 | 12.3272 | 20.9423 | 27.6926 | 32.279 | 46.2197 | 0 | 0 | 1.3276 | 12.3272 | 20.9423 | 27.6926 | 32.279 | 46.2197 |  | Yes | Delivery Mechanism | AMP8
| TMS | Bracknell STW AMP8 Low P BOD and Chem | L842 | 08TW101384a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  |  | 2023-06-02 | 2023-06-03 | 2023-08-18 | 2023-09-27 | 2031-11-20 | 2033-03-31 |  |  | 0 | 19.4123 | 19.4123 | 0% | 0 | 0 | 0.55758 | 5.1774 | 8.7958 | 11.6309 | 13.5572 | 19.4123 | 0 | 0 | 0.55758 | 5.1774 | 8.7958 | 11.6309 | 13.5572 | 19.4123 |  | Yes | Other | AMP8
| TMS | Broadwell STW Phosphorus Stretch Target | UBA8.SEW.S41886 | 08TW100879a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-30 | 2028-09-13 | 2029-03-15 | 2030-11-21 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-30 | 2028-09-13 | 2029-03-15 | 2030-11-21 | 2032-03-31 |  |  | 0 | 10.7842 | 10.7842 | 0% | 0 | 0 | 0 | 0 | 0.099271 | 1.5828 | 3.5722 | 10.7842 | 0 | 0 | 0 | 0 | 0.099271 | 1.5828 | 3.5722 | 10.7842 |  | No | Delivery Mechanism | AMP8
| TMS | Broughton STW - Phosphorus - Dosing Only | UBA8.SEW.S39728 | 09TW100025a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-06 | 2026-06-19 | 2027-01-17 | 2028-11-17 | 2030-03-31 |  |  | 2024-10-16 | 2025-07-06 | 2026-06-19 | 2027-01-17 | 2028-11-17 | 2030-03-31 |  |  | 0 | 2.094 | 2.094 | 0% | 0 | 0 | 0 | 0.12486 | 0.39854 | 0.96866 | 2.0318 | 2.094 | 0 | 0 | 0 | 0.12486 | 0.39854 | 0.96866 | 2.0318 | 2.094 |  | No | Other | AMP8
| TMS | Buckland STW Phosphorus Dosing and TT | UBA8.SEW.S38806 | 08TW100954a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-14 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 2024-10-16 | 2028-04-14 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 0 | 3.4453 | 3.4453 | 0% | 0 | 0 | 0 | 0 | 0.14932 | 0.49672 | 0.98886 | 3.4453 | 0 | 0 | 0 | 0 | 0.14932 | 0.49672 | 0.98886 | 3.4453 |  | No | Delivery Mechanism | AMP8
| TMS | Burstow STW engineered reed beds | UBA8.SEW.S38363 | 08TW101113a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  |  | 2024-10-16 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  |  | 0 | 17.3764 | 17.3764 | 0% | 0 | 0 | 0 | 0 | 0.56143 | 3.3005 | 7.8492 | 17.3764 | 0 | 0 | 0 | 0 | 0.56143 | 3.3005 | 7.8492 | 17.3764 |  | No | Delivery Mechanism | AMP8
| TMS | Burstow STW engineered reed beds | UBA8.SEW.S38363 | 08TW101113a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  |  | 2024-10-16 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  |  | 0 | 10.2052 | 10.2052 | 0% | 0 | 0 | 0 | 0 | 0.32973 | 1.9384 | 4.6099 | 10.2052 | 0 | 0 | 0 | 0 | 0.32973 | 1.9384 | 4.6099 | 10.2052 |  | No | Delivery Mechanism | AMP8
| TMS | Byfield STW Phosphorus Dosing and TT | UBA8.SEW.S38843 | 08TW100880a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-24 | 2028-05-17 | 2028-12-05 | 2030-11-14 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-24 | 2028-05-17 | 2028-12-05 | 2030-11-14 | 2032-03-31 |  |  | 0 | 5.7479 | 5.7479 | 0% | 0 | 0 | 0 | 0 | 0.24907 | 0.86353 | 2.0673 | 5.7479 | 0 | 0 | 0 | 0 | 0.24907 | 0.86353 | 2.0673 | 5.7479 |  | No | Delivery Mechanism | AMP8
| TMS | Camberley STW Phosphorus Dosing and TT | UBA8.SEW.S39052 | 08TW100881a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-04 | 2028-02-09 | 2028-08-25 | 2029-12-14 | 2031-03-31 |  |  | 2024-10-16 | 2027-03-04 | 2028-02-09 | 2028-08-25 | 2029-12-14 | 2031-03-31 |  |  | 0 | 30.5409 | 30.5409 | 0% | 0 | 0 | 0 | 1.409 | 4.4087 | 9.8371 | 24.6211 | 30.5409 | 0 | 0 | 0 | 1.409 | 4.4087 | 9.8371 | 24.6211 | 30.5409 |  | No | Delivery Mechanism | AMP8
| TMS | Cassington STW - AMP8 Growth | UBA8.SEW.S40428 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2028-03-10 | 2029-01-17 | 2029-08-01 | 2031-03-07 | 2032-03-31 |  |  | 2024-10-16 | 2028-03-10 | 2029-01-17 | 2029-08-01 | 2031-03-07 | 2032-03-31 |  |  | 0 | 20.5832 | 20.5832 | 0% | 0 | 0 | 0 | 0 | 1.1707 | 3.6894 | 8.5945 | 20.5832 | 0 | 0 | 0 | 0 | 1.1707 | 3.6894 | 8.5945 | 20.5832 |  | Yes | Other | AMP8
| TMS | Chacombe STW Phosphorus Dosing TT + FST | UBA8.SEW.S38841 | 08TW100882a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-18 | 2029-02-11 | 2029-08-25 | 2030-12-16 | 2032-03-31 |  |  | 2024-10-16 | 2028-04-18 | 2029-02-11 | 2029-08-25 | 2030-12-16 | 2032-03-31 |  |  | 0 | 5.3169 | 5.3169 | 0% | 0 | 0 | 0 | 0 | 0.23043 | 0.76656 | 1.5261 | 5.3169 | 0 | 0 | 0 | 0 | 0.23043 | 0.76656 | 1.5261 | 5.3169 |  | No | Delivery Mechanism | AMP8
| TMS | Chadlington STW Phosphorus Dosing & TT | UBA8.SEW.S39016 | 08TW100883a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-22 | 2029-05-16 | 2029-12-11 | 2031-11-20 | 2033-03-31 |  |  | 2024-10-16 | 2028-08-22 | 2029-05-16 | 2029-12-11 | 2031-11-20 | 2033-03-31 |  |  | 0 | 3.6212 | 3.6212 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.14997 | 3.6212 | 0 | 0 | 0 | 0 | 0 | 0 | 0.14997 | 3.6212 |  | No | Delivery Mechanism | AMP8
| TMS | Chalgrove STW - AMP8 Growth | L838 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  |  | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  |  | 0.00021146 | 27.1218 | 27.122 | 0.0007797% | 0 | 0.00021146 | -0.043602 | 1.2169 | 3.7057 | 16.0056 | 26.5289 | 27.1218 | 0 | 0.00021146 | -0.043602 | 1.2169 | 3.7057 | 16.0056 | 26.5289 | 27.1218 |  | No | Other | AMP8
| TMS | Chalgrove STW - AMP8 Growth | L838 | 08TW100884a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  |  | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  |  | 4.7749e-05 | 6.1243 | 6.1243 | 0.0007797% | 0 | 4.7749e-05 | -0.0098457 | 0.27478 | 0.83678 | 3.6142 | 5.9904 | 6.1243 | 0 | 4.7749e-05 | -0.0098457 | 0.27478 | 0.83678 | 3.6142 | 5.9904 | 6.1243 |  | No | Other | AMP8
| TMS | Chalgrove STW - AMP8 Growth | L838 | 08TW101387a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  |  | 2024-09-18 | 2025-05-21 | 2026-02-23 | 2026-09-10 | 2029-01-16 | 2030-03-31 |  |  | 8.1855e-05 | 10.4988 | 10.4988 | 0.0007797% | 0 | 8.1855e-05 | -0.016878 | 0.47106 | 1.4345 | 6.1957 | 10.2693 | 10.4988 | 0 | 8.1855e-05 | -0.016878 | 0.47106 | 1.4345 | 6.1957 | 10.2693 | 10.4988 |  | No | Other | AMP8
| TMS | Charlbury STW - Phosphorus - Dosing Only | UBA8.SEW.S39024 | 08TW100885a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2026-06-15 | 2027-01-09 | 2028-11-17 | 2030-03-31 |  |  | 2024-10-16 | 2024-10-16 | 2026-06-15 | 2027-01-09 | 2028-11-17 | 2030-03-31 |  |  | 0 | 2.1696 | 2.1696 | 0% | 0 | 0 | 0.00053337 | 0.34498 | 0.73189 | 1.946 | 2.1481 | 2.1696 | 0 | 0 | 0.00053337 | 0.34498 | 0.73189 | 1.946 | 2.1481 | 2.1696 |  | No | Other | AMP8
| TMS | Charlton-on-Otmoor STW Phos Dosing & TT | UBA8.SEW.S39049 | 08TW100861a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-08-22 | 2030-05-16 | 2030-12-11 | 2032-11-19 | 2034-03-31 |  |  | 2024-10-16 | 2029-08-22 | 2030-05-16 | 2030-12-11 | 2032-11-19 | 2034-03-31 |  |  | 0 | 3.8917 | 3.8917 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0.16117 | 3.8917 | 0 | 0 | 0 | 0 | 0 | 0 | 0.16117 | 3.8917 |  | No | Delivery Mechanism | AMP8
| TMS | Chertsey STW AMP8 WINEP Low P and Chem | L837 | 08TW100157a, 08TW100886a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-09-18 | 2024-09-18 | 2024-09-25 | 2024-11-09 | 2032-11-23 | 2034-03-31 |  |  | 2024-09-18 | 2024-09-18 | 2024-09-25 | 2024-11-09 | 2032-11-23 | 2034-03-31 |  |  | 0 | 28.9768 | 28.9768 | 0% | 0 | 0 | 0.47062 | 2.083 | 7.6538 | 14.6616 | 17.0494 | 28.9768 | 0 | 0 | 0.47062 | 2.083 | 7.6538 | 14.6616 | 17.0494 | 28.9768 |  | No | Delivery Mechanism | AMP8
| TMS | Chertsey STW AMP8 WINEP Low P and Chem | L837 | 08TW100474a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-09-18 | 2024-09-18 | 2024-09-25 | 2024-11-09 | 2032-11-23 | 2034-03-31 |  |  | 2024-09-18 | 2024-09-18 | 2024-09-25 | 2024-11-09 | 2032-11-23 | 2034-03-31 |  |  | 0 | 61.5758 | 61.5758 | 0% | 0 | 0 | 1.0001 | 4.4263 | 16.2643 | 31.1559 | 36.2301 | 61.5758 | 0 | 0 | 1.0001 | 4.4263 | 16.2643 | 31.1559 | 36.2301 | 61.5758 |  | No | Delivery Mechanism | AMP8
| TMS | Chinnor STW Phosphorus Dosing and TT | UBA8.SEW.S38991 | 08TW100887a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-04-18 | 2028-02-11 | 2028-08-24 | 2029-12-15 | 2031-03-31 |  |  | 2024-10-16 | 2027-04-18 | 2028-02-11 | 2028-08-24 | 2029-12-15 | 2031-03-31 |  |  | 0 | 7.5291 | 7.5291 | 0% | 0 | 0 | 0 | 0 | 0.45147 | 1.6059 | 3.746 | 7.5291 | 0 | 0 | 0 | 0 | 0.45147 | 1.6059 | 3.746 | 7.5291 |  | No | Other | AMP8
| TMS | Chipping Norton STW - AMP8 Growth | UBA8.SEW.S38259 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2025-07-04 | 2026-05-16 | 2026-12-13 | 2028-11-20 | 2030-03-31 |  |  | 2024-10-16 | 2025-07-04 | 2026-05-16 | 2026-12-13 | 2028-11-20 | 2030-03-31 |  |  | 0 | 8.809 | 8.809 | 0% | 0 | 0 | 0 | 0.79873 | 2.1712 | 5.3299 | 8.6908 | 8.809 | 0 | 0 | 0 | 0.79873 | 2.1712 | 5.3299 | 8.6908 | 8.809 |  | No | Other | AMP8
| TMS | Chipping Norton STW Phos Dosing TT & PST | UBA8.SEW.S38836 | 08TW100158a, 08TW100888a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2026-01-12 | 2026-11-21 | 2027-05-30 | 2029-03-06 | 2030-03-31 |  |  | 2024-10-16 | 2026-01-12 | 2026-11-21 | 2027-05-30 | 2029-03-06 | 2030-03-31 |  |  | 0 | 11.1559 | 11.1559 | 0% | 0 | 0 | 0.12578 | 0.36344 | 4.9528 | 8.9478 | 10.8128 | 11.1559 | 0 | 0 | 0.12578 | 0.36344 | 4.9528 | 8.9478 | 10.8128 | 11.1559 |  | No | Other | AMP8
| TMS | Chobham STW Low P & TT | L892 | 09TW100028a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-10-16 | 2027-07-13 | 2027-11-09 | 2028-01-03 | 2028-12-06 | 2030-03-31 |  |  | 2024-10-16 | 2027-07-13 | 2027-11-09 | 2028-01-03 | 2028-12-06 | 2030-03-31 |  |  | 0 | 8.7181 | 8.7181 | 0% | 0 | 0 | 2.0993 | 3.8445 | 6.2809 | 8.199 | 8.6432 | 8.7181 | 0 | 0 | 2.0993 | 3.8445 | 6.2809 | 8.199 | 8.6432 | 8.7181 |  | No | Other | AMP8
| TMS | Church Hanborough STW Phosphorus Stretch | UBA8.SEW.S41884 | 08TW100889a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-08-31 | 2026-02-21 | 2026-08-14 | 2028-11-19 | 2030-03-31 |  |  | 2024-10-16 | 2025-08-31 | 2026-02-21 | 2026-08-14 | 2028-11-19 | 2030-03-31 |  |  | 0 | 13.4569 | 13.4569 | 0% | 0 | 0 | 0.73289 | 2.1454 | 3.9314 | 9.8618 | 13.2776 | 13.4569 | 0 | 0 | 0.73289 | 2.1454 | 3.9314 | 9.8618 | 13.2776 | 13.4569 |  | No | Other | AMP8
| TMS | Cirencester STW Phosphorus Dosing and TT | UBA8.SEW.S38929 | 08TW100890a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-19 | 2029-07-27 | 2029-12-05 | 2030-12-11 | 2032-03-31 |  |  | 2024-10-16 | 2028-08-19 | 2029-07-27 | 2029-12-05 | 2030-12-11 | 2032-03-31 |  |  | 0 | 13.6948 | 13.6948 | 0% | 0 | 0 | 0 | 0 | 0.83259 | 2.2294 | 5.5822 | 13.6948 | 0 | 0 | 0 | 0 | 0.83259 | 2.2294 | 5.5822 | 13.6948 |  | No | Delivery Mechanism | AMP8
| TMS | CODICOTE CSO | UBA8.SEW.S41663 | 08TW101402j | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-19 | 2026-09-15 | 2029-03-18 | 2029-11-09 | 2032-11-22 | 2034-03-31 |  |  | 2024-11-19 | 2026-09-15 | 2029-03-18 | 2029-11-09 | 2032-11-22 | 2034-03-31 |  |  | 0 | 1.6957 | 1.6957 | 0% | 0 | 0 | 0 | 0 | 0.094369 | 0.19134 | 0.25272 | 1.6957 | 0 | 0 | 0 | 0 | 0.094369 | 0.19134 | 0.25272 | 1.6957 |  | No | Other | AMP8
| TMS | College Green Groundwater MD | UBA8.SEW.S38859 | 08TW100280a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 0.34115 | 0.34115 | 0% | 0 | 0 | 0.034117 | 0.27292 | 0.34115 | 0.34115 | 0.34115 | 0.34115 | 0 | 0 | 0.034117 | 0.27292 | 0.34115 | 0.34115 | 0.34115 | 0.34115 |  | No | Other | AMP8
| TMS | Continuos Water Quality Monitoring WCQM | L798 | 08TW101406a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-03-31 | 2023-04-03 | 2023-05-27 | 2023-05-31 | 2024-12-15 | 2030-03-31 |  |  | 2024-03-31 | 2023-04-03 | 2023-05-27 | 2023-05-31 | 2024-12-15 | 2030-03-31 |  |  | 0.18586 | 1.4652 | 1.651 | 11.26% | 0 | 0.18586 | 0.32256 | 0.46114 | 0.68908 | 1.1838 | 1.4652 | 1.4652 | 0 | 0.18586 | 0.32256 | 0.46114 | 0.68908 | 1.1838 | 1.4652 | 1.4652 |  | No | Other | AMP8
| TMS | Continuous Discharge Lower Thames MD | UBA8.SEW.S38862 | 08TW100280d | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  |  | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 0 | 0.87235 | 0.87235 | 0% | 0 | 0 | 0.34894 | 0.69788 | 0.78512 | 0.82874 | 0.87235 | 0.87235 | 0 | 0 | 0.34894 | 0.69788 | 0.78512 | 0.82874 | 0.87235 | 0.87235 |  | No | Other | AMP8
| TMS | Crawley STW Phosphorus Dosing and TT | UBA8.SEW.S38969 | 08TW100893a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-02-24 | 2026-02-21 | 2026-08-19 | 2028-11-21 | 2030-03-31 |  |  | 2024-10-16 | 2025-02-24 | 2026-02-21 | 2026-08-19 | 2028-11-21 | 2030-03-31 |  |  | 0 | 37.0499 | 37.0499 | 0% | 0 | 0 | 2.1034 | 6.0121 | 12.5549 | 29.9945 | 36.599 | 37.0499 | 0 | 0 | 2.1034 | 6.0121 | 12.5549 | 29.9945 | 36.599 | 37.0499 |  | No | Other | AMP8
| TMS | Cropredy STW Phosphorus Dosing and TT | UBA8.SEW.S39726 | 09TW100031a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 5.7683 | 5.7683 | 0% | 0 | 0 | 0.34588 | 1.2303 | 2.8699 | 5.6097 | 5.7259 | 5.7683 | 0 | 0 | 0.34588 | 1.2303 | 2.8699 | 5.6097 | 5.7259 | 5.7683 |  | No | Other | AMP8
| TMS | Cuddesdon STW Phosphorus Dosing and TT | UBA8.SEW.S39028 | 08TW100895a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-08-22 | 2027-05-16 | 2027-12-11 | 2029-11-19 | 2031-03-31 |  |  | 2024-10-16 | 2026-08-22 | 2027-05-16 | 2027-12-11 | 2029-11-19 | 2031-03-31 |  |  | 0 | 3.4662 | 3.4662 | 0% | 0 | 0 | 0 | 0 | 0.14355 | 0.52132 | 1.2478 | 3.4662 | 0 | 0 | 0 | 0 | 0.14355 | 0.52132 | 1.2478 | 3.4662 |  | No | Delivery Mechanism | AMP8
| TMS | Cuddington STW Phosphorus Dosing and TT | UBA8.SEW.S38990 | 08TW100896a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 4.97 | 4.97 | 0% | 0 | 0 | 0 | 0 | 0.20582 | 0.74749 | 1.7891 | 4.97 | 0 | 0 | 0 | 0 | 0.20582 | 0.74749 | 1.7891 | 4.97 |  | No | Delivery Mechanism | AMP8
| TMS | CULHAM STW | UBA8.SEW.S40712 | 08TW101393a, 08TW101392a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-09-18 | 2024-09-18 | 2024-09-24 | 2024-11-20 | 2026-03-22 | 2027-03-31 |  |  | 2024-09-18 | 2024-09-18 | 2024-09-24 | 2024-11-20 | 2026-03-22 | 2027-03-31 |  |  | 0 | 0 | 0 | #DIV/0! | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | No | Other | AMP8
| TMS | Culham STW - AMP8 Growth | UBA8.SEW.S40429 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-09-18 | 2029-09-18 | 2029-09-25 | 2029-11-21 | 2031-03-23 | 2032-03-31 |  |  | 2024-09-18 | 2029-09-18 | 2029-09-25 | 2029-11-21 | 2031-03-23 | 2032-03-31 |  |  | 0 | 27.2596 | 27.2596 | 0% | 0 | 0 | 0.049082 | 1.1553 | 2.1996 | 6.0072 | 15.5058 | 27.2596 | 0 | 0 | 0.049082 | 1.1553 | 2.1996 | 6.0072 | 15.5058 | 27.2596 |  | No | Other | AMP8
| TMS | Culham STW Phosphorus Dosing and TT | UBA8.SEW.S38909 | 08TW100897a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-09-18 | 2026-03-01 | 2026-12-24 | 2027-06-24 | 2029-03-23 | 2030-03-31 |  |  | 2024-09-18 | 2026-03-01 | 2026-12-24 | 2027-06-24 | 2029-03-23 | 2030-03-31 |  |  | 0 | 8.8761 | 8.8761 | 0% | 0 | 0 | 0.53224 | 1.8932 | 4.4162 | 8.6322 | 8.8109 | 8.8761 | 0 | 0 | 0.53224 | 1.8932 | 4.4162 | 8.6322 | 8.8109 | 8.8761 |  | No | Other | AMP8
| TMS | Culworth STW Phosphorus Dosing and TT | UBA8.SEW.S38978 | 08TW100898a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2030-08-22 | 2031-05-16 | 2031-12-11 | 2033-11-19 | 2035-03-31 |  |  | 2024-10-16 | 2030-08-22 | 2031-05-16 | 2031-12-11 | 2033-11-19 | 2035-03-31 |  |  | 0 | 3.2383 | 3.2383 | 0% | 0 | 0 | 0 | 0 | 7.606e-05 | 0.013764 | 0.080135 | 3.2383 | 0 | 0 | 0 | 0 | 7.606e-05 | 0.013764 | 0.080135 | 3.2383 |  | No | Delivery Mechanism | AMP8
| TMS | Cypermethrin Milton-Under-Wychwood STW | UBA8.SEW.S40203 | 08TW100489a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2025-11-08 | 2027-02-19 | 2027-08-15 | 2029-11-12 | 2031-03-31 |  |  | 2024-10-16 | 2025-11-08 | 2027-02-19 | 2027-08-15 | 2029-11-12 | 2031-03-31 |  |  | 0 | 9.9263 | 9.9263 | 0% | 0 | 0 | 0 | 0.5668 | 1.5983 | 2.9168 | 7.3133 | 9.9263 | 0 | 0 | 0 | 0.5668 | 1.5983 | 2.9168 | 7.3133 | 9.9263 |  | No | Delivery Mechanism | AMP8
| TMS | Didcot STW - AMP8 Growth | UBA8.SEW.S40439, J954, UBA8.SEW.S38256 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2028-08-30 | 2029-04-16 | 2030-04-04 | 2032-03-22 | 2033-03-31 |  |  | 2024-10-16 | 2028-08-30 | 2029-04-16 | 2030-04-04 | 2032-03-22 | 2033-03-31 |  |  | -0.0102 | 92.6593 | 92.6491 | -0.01101% | 0.003609 | -0.013809 | -0.013809 | 0.75285 | 4.1004 | 7.2539 | 10.8618 | 92.6593 | 0.003609 | -0.013809 | -0.013809 | 0.75285 | 4.1004 | 7.2539 | 10.8618 | 92.6593 |  | Yes | Enhanced engagement | AMP8
| TMS | Didcot STW Phosphorus Dosing and TT | UBA8.SEW.S38821 | 08TW100899a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-08-30 | 2029-04-16 | 2030-04-04 | 2032-03-22 | 2033-03-31 |  |  | 2024-10-16 | 2028-08-30 | 2029-04-16 | 2030-04-04 | 2032-03-22 | 2033-03-31 |  |  | 0 | 19.5996 | 19.5996 | 0% | 0 | 0 | 0 | 0 | 0.16234 | 0.35622 | 0.7502 | 19.5996 | 0 | 0 | 0 | 0 | 0.16234 | 0.35622 | 0.7502 | 19.5996 |  | No | Delivery Mechanism | AMP8
| TMS | Dollis Brook Leeside Crescent - Option 1 | UBA8.SEW.S38357 | 08TW101068a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-02-18 01:10 | 2026-10-01 12:09 | 2026-11-26 20:54 | 2027-07-19 | 2028-03-31 |  |  | 2024-11-20 | 2026-02-18 01:10 | 2026-10-01 12:09 | 2026-11-26 20:54 | 2027-07-19 | 2028-03-31 |  |  | 0 | 5.897 | 5.897 | 0% | 0 | 0 | 0.19638 | 3.9956 | 5.897 | 5.897 | 5.897 | 5.897 | 0 | 0 | 0.19638 | 3.9956 | 5.897 | 5.897 | 5.897 | 5.897 |  | No | Other | AMP8
| TMS | Dorking STW Phosphorus Dosing and TT | UBA8.SEW.S39050 | 08TW100900a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-04 | 2028-02-09 | 2028-08-25 | 2029-12-14 | 2031-03-31 |  |  | 2024-10-16 | 2027-03-04 | 2028-02-09 | 2028-08-25 | 2029-12-14 | 2031-03-31 |  |  | 0 | 12.3181 | 12.3181 | 0% | 0 | 0 | 0 | 0.74889 | 2.0053 | 5.021 | 11.9771 | 12.3181 | 0 | 0 | 0 | 0.74889 | 2.0053 | 5.021 | 11.9771 | 12.3181 |  | No | Other | AMP8
| TMS | Easthampstead Park STW P Removal (2 WINEP Actions) | UBA8.SEW.S38827 | 08TW100163a, 08TW100901a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2028-04-18 | 2029-02-11 | 2029-08-25 | 2030-12-16 | 2032-03-31 |  |  | 2024-10-16 | 2028-04-18 | 2029-02-11 | 2029-08-25 | 2030-12-16 | 2032-03-31 |  |  | 0 | 7.8286 | 7.8286 | 0% | 0 | 0 | 0 | 0 | 0.44455 | 1.2706 | 2.6301 | 7.8286 | 0 | 0 | 0 | 0 | 0.44455 | 1.2706 | 2.6301 | 7.8286 |  | No | Delivery Mechanism | AMP8
| TMS | Esher STW - Phosphorus - Bio-P and TT | UBA8.SEW.S39496 | 08TW100902a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-02-21 | 2028-02-03 | 2028-08-20 | 2029-12-08 | 2031-03-31 |  |  | 2024-10-16 | 2027-02-21 | 2028-02-03 | 2028-08-20 | 2029-12-08 | 2031-03-31 |  |  | 0 | 31.4007 | 31.4007 | 0% | 0 | 0 | 0 | 1.4487 | 4.5328 | 10.114 | 25.3142 | 31.4007 | 0 | 0 | 0 | 1.4487 | 4.5328 | 10.114 | 25.3142 | 31.4007 |  | No | Delivery Mechanism | AMP8
| TMS | F909_Streatham Vale Storm Relief CSO | UBA8.SEW.S38373 | 08TW101065a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-05-20 04:13 | 2028-05-18 04:13 | 2028-10-30 06:16 | 2030-09-16 | 2031-03-31 |  |  | 2024-11-06 | 2027-05-20 04:13 | 2028-05-18 04:13 | 2028-10-30 06:16 | 2030-09-16 | 2031-03-31 |  |  | 0 | 3.5307 | 3.5307 | 0% | 0 | 0 | 0 | 0.077138 | 1.2447 | 2.3148 | 3.1005 | 3.5307 | 0 | 0 | 0 | 0.077138 | 1.2447 | 2.3148 | 3.1005 | 3.5307 |  | No | Other | AMP8
| TMS | Farnborough STW Phosphorus Dosing Only | UBA8.SEW.S38976 | 08TW100955a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-08-22 | 2027-05-16 | 2027-12-11 | 2029-11-19 | 2031-03-31 |  |  | 2024-10-16 | 2026-08-22 | 2027-05-16 | 2027-12-11 | 2029-11-19 | 2031-03-31 |  |  | 0 | 3.3753 | 3.3753 | 0% | 0 | 0 | 0 | 0 | 0.13978 | 0.50765 | 1.2151 | 3.3753 | 0 | 0 | 0 | 0 | 0.13978 | 0.50765 | 1.2151 | 3.3753 |  | No | Delivery Mechanism | AMP8
| TMS | Farnham STW - No Build | S39086 | 08TW100174a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 | 2030-03-31 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | No | Other | AMP8
| TMS | Finstock STW Phosphorus Dosing & TT | UBA8.SEW.S39015 | 08TW100903a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-06 | 2026-05-22 | 2026-12-07 | 2028-11-17 | 2030-03-31 |  |  | 2024-10-16 | 2025-07-06 | 2026-05-22 | 2026-12-07 | 2028-11-17 | 2030-03-31 |  |  | 0 | 6.0032 |  |  | 0 | 0 | 0.35997 | 1.2804 | 2.9868 | 5.8383 | 5.9591 | 6.0032 | 0 | 0 | 0.35997 | 1.2804 | 2.9868 | 5.8383 | 5.9591 | 6.0032 |  | No | Other | AMP8
| TMS | Gerrards Cross STW Cypermethrin - IMP | UBA8.SEW.S40608 | 08TW100479a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-11-20 | 2026-01-01 | 2027-02-14 | 2027-08-17 | 2029-11-15 | 2031-03-31 |  |  | 2024-11-20 | 2026-01-01 | 2027-02-14 | 2027-08-17 | 2029-11-15 | 2031-03-31 |  |  | 0 | 12.3354 |  |  | 0 | 0 | 0 | 0.69402 | 1.9544 | 3.3651 | 8.5504 | 12.3354 | 0 | 0 | 0 | 0.69402 | 1.9544 | 3.3651 | 8.5504 | 12.3354 |  | No | Delivery Mechanism | AMP8
| TMS | Great Milton STW Phosphorus Dosing & TT | UBA8.SEW.S39029 | 08TW100905a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.579 |  |  | 0 | 0 | 0 | 0 | 0.14821 | 0.53828 | 1.2884 | 3.579 | 0 | 0 | 0 | 0 | 0.14821 | 0.53828 | 1.2884 | 3.579 |  | No | Delivery Mechanism | AMP8
| TMS | Great Rollright STW Phosphor Dosing & TT | UBA8.SEW.S39026 | 08TW100929a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.2742 |  |  | 0 | 0 | 0 | 0 | 0.1356 | 0.49245 | 1.1787 | 3.2742 | 0 | 0 | 0 | 0 | 0.1356 | 0.49245 | 1.1787 | 3.2742 |  | No | Delivery Mechanism | AMP8
| TMS | Greatworth STW Phosphorus Dosing & TT | UBA8.SEW.S38908 | 08TW100906a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-05-12 | 2027-02-06 | 2027-08-17 | 2028-12-11 | 2030-03-31 |  |  | 2024-10-16 | 2026-05-12 | 2027-02-06 | 2027-08-17 | 2028-12-11 | 2030-03-31 |  |  | 0 | 4.4931 |  |  | 0 | 0 | 0.15579 | 0.59885 | 1.1237 | 3.1395 | 4.4353 | 4.4931 | 0 | 0 | 0.15579 | 0.59885 | 1.1237 | 3.1395 | 4.4353 | 4.4931 |  | No | Other | AMP8
| TMS | Grendon Underwood STW Phosphorus Dosing | UBA8.SEW.S40987 | 08TW100218a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-04-18 | 2026-02-11 | 2026-08-25 | 2027-12-16 | 2029-03-31 |  |  | 2024-10-16 | 2025-04-18 | 2026-02-11 | 2026-08-25 | 2027-12-16 | 2029-03-31 |  |  | 0 | 2.2314 |  |  | 0 | 0 | 0.14079 | 0.54538 | 1.3925 | 2.2041 | 2.2229 | 2.2314 | 0 | 0 | 0.14079 | 0.54538 | 1.3925 | 2.2041 | 2.2229 | 2.2314 |  | No | Other | AMP8
| TMS | Haddenham STW Phos Dosing & TT + FST | UBA8.SEW.S38987 | 08TW100907a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  |  | 2024-10-16 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  |  | 0 | 8.6157 |  |  | 0 | 0 | 0 | 0 | 0.1701 | 0.69323 | 2.0277 | 8.6157 | 0 | 0 | 0 | 0 | 0.1701 | 0.69323 | 2.0277 | 8.6157 |  | No | Delivery Mechanism | AMP8
| TMS | HANNINGTON (HANTS) STW | UBA8.SEW.S41632 | 08TW101402b | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-05-19 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 2025-04-01 | 2026-05-19 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 4.3183 |  |  | 0 | 0 | 0.59362 | 1.2195 | 2.6805 | 4.1094 | 4.2769 | 4.3183 | 0 | 0 | 0.59362 | 1.2195 | 2.6805 | 4.1094 | 4.2769 | 4.3183 |  | No | Other | AMP8
| TMS | HANNINGTON (WILTS) STW | UBA8.SEW.S41633 | 08TW101402c | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-25 | 2028-03-01 | 2028-09-26 | 2028-12-26 | 2029-12-10 | 2031-03-31 |  |  | 2025-04-25 | 2028-03-01 | 2028-09-26 | 2028-12-26 | 2029-12-10 | 2031-03-31 |  |  | 0 | 3.2638 |  |  | 0 | 0 | 0.19125 | 0.5152 | 0.81617 | 1.6273 | 2.7701 | 3.2638 | 0 | 0 | 0.19125 | 0.5152 | 0.81617 | 1.6273 | 2.7701 | 3.2638 |  | No | Other | AMP8
| TMS | Hanwell STW Phosphorus Dosing and TT | UBA8.SEW.S38915 | 08TW100956a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.4531 |  |  | 0 | 0 | 0 | 0 | 0.031523 | 0.53008 | 1.2521 | 3.4531 | 0 | 0 | 0 | 0 | 0.031523 | 0.53008 | 1.2521 | 3.4531 |  | No | Delivery Mechanism | AMP8
| TMS | Hatfield Mill Green STW Phos Dosing & TT | UBA8.SEW.S39011 | 09TW100035a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  |  | 2024-11-20 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  |  | 0 | 9.6653 |  |  | 0 | 0 | 0 | 0 | 0.39749 | 1.3859 | 3.1759 | 9.6653 | 0 | 0 | 0 | 0 | 0.39749 | 1.3859 | 3.1759 | 9.6653 |  | No | Delivery Mechanism | AMP8
| TMS | HEADLEY STW (08TW100164a) | UBA8.SEW.S38438 | 08TW100164a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2024-10-16 | 2025-05-17 | 2025-12-12 | 2027-11-21 | 2029-03-31 |  |  | 2024-10-16 | 2024-10-16 | 2025-05-17 | 2025-12-12 | 2027-11-21 | 2029-03-31 |  |  | 0 | 6.7436 |  |  | 0 | 0 | 0.7578 | 1.7051 | 4.4694 | 6.6623 | 6.7198 | 6.7436 | 0 | 0 | 0.7578 | 1.7051 | 4.4694 | 6.6623 | 6.7198 | 6.7436 |  | No | Other | AMP8
| TMS | HEADLEY STW (08TW101402d) | UBA8.SEW.S41634 | 08TW101402d | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-02-27 | 2026-07-02 | 2026-11-04 | 2031-07-03 | 2031-03-31 |  |  | 2025-04-01 | 2026-02-27 | 2026-07-02 | 2026-11-04 | 2031-07-03 | 2031-03-31 |  |  | 0 | 1.3043 |  |  | 0 | 0 | 0.19239 | 0.34125 | 0.52146 | 0.82472 | 1.1131 | 1.3043 | 0 | 0 | 0.19239 | 0.34125 | 0.52146 | 0.82472 | 1.1131 | 1.3043 |  | No | Other | AMP8
| TMS | Henley STW Phosphorus Dosing and TT | UBA8.SEW.S38842 | 08TW100908a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-05-29 | 2028-12-10 | 2029-05-15 | 2029-12-08 | 2031-03-31 |  |  | 2024-10-16 | 2028-05-29 | 2028-12-10 | 2029-05-15 | 2029-12-08 | 2031-03-31 |  |  | 0 | 7.2008 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 2.1146 | 7.2008 | 0 | 0 | 0 | 0 | 0 | 0 | 2.1146 | 7.2008 |  | No | Delivery Mechanism | AMP8
| TMS | Heyford STW Phosphorus Dosing and TT | UBA8.SEW.S40986 | 08TW100217a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-05-06 | 2028-02-09 | 2028-08-18 | 2029-12-06 | 2031-03-31 |  |  | 2024-10-16 | 2027-05-06 | 2028-02-09 | 2028-08-18 | 2029-12-06 | 2031-03-31 |  |  | 0 | 5.8392 |  |  | 0 | 0 | 0 | 0 | 0.35014 | 1.2454 | 2.9052 | 5.8392 | 0 | 0 | 0 | 0 | 0.35014 | 1.2454 | 2.9052 | 5.8392 |  | No | Delivery Mechanism | AMP8
| TMS | HIGHWORTH EASTROP CSO | UBA8.SEW.S40798 | 08TW101402k | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-06-19 | 2025-07-08 | 2026-05-16 | 2026-12-09 | 2028-11-19 | 2030-03-31 |  |  | 2024-06-19 | 2025-07-08 | 2026-05-16 | 2026-12-09 | 2028-11-19 | 2030-03-31 |  |  | 0 | 2.0365 |  |  | 0 | 0 | 0.11242 | 0.33017 | 0.68389 | 1.7775 | 2.0152 | 2.0365 | 0 | 0 | 0.11242 | 0.33017 | 0.68389 | 1.7775 | 2.0152 | 2.0365 |  | No | Other | AMP8
| TMS | Highworth STW - AMP8 Growth | UBA8.SEW.S38245 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2028-02-29 | 2029-02-11 | 2029-08-26 | 2030-12-15 | 2032-03-31 |  |  | 2024-10-16 | 2028-02-29 | 2029-02-11 | 2029-08-26 | 2030-12-15 | 2032-03-31 |  |  | 0 | 11.1764 |  |  | 0 | 0 | 0 | 0 | 0.46875 | 1.585 | 2.7887 | 11.1764 | 0 | 0 | 0 | 0 | 0.46875 | 1.585 | 2.7887 | 11.1764 |  | No | Other | AMP8
| TMS | Highworth STW P Removal (2 WINEP Actions) | UBA8.SEW.S38984 | 08TW100162a, 08TW100909a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-10-16 | 2026-02-28 | 2027-02-11 | 2027-08-26 | 2028-12-14 | 2030-03-31 |  |  | 2024-10-16 | 2026-02-28 | 2027-02-11 | 2027-08-26 | 2028-12-14 | 2030-03-31 |  |  | 0 | 7.9014 |  |  | 0 | 0 | 0.47379 | 1.6853 | 3.9313 | 7.6843 | 7.8434 | 7.9014 | 0 | 0 | 0.47379 | 1.6853 | 3.9313 | 7.6843 | 7.8434 | 7.9014 |  | No | Other | AMP8
| TMS | Hogsmill STW P Removal (2 WINEP Actions) | UBA8.SEW.S38959 | 08TW100910a, 08TW100220 | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-27 | 2028-04-06 | 2028-08-16 | 2030-12-11 | 2032-03-31 |  |  | 2024-10-16 | 2027-03-27 | 2028-04-06 | 2028-08-16 | 2030-12-11 | 2032-03-31 |  |  | 0 | 66.99 |  |  | 0 | 0 | 0 | 0 | 0.7788 | 1.6008 | 19.4909 | 66.99 | 0 | 0 | 0 | 0 | 0.7788 | 1.6008 | 19.4909 | 66.99 |  | Yes | Delivery Mechanism | AMP8
| TMS | Horley STW Oxon Phosphorus Dosing and TT | UBA8.SEW.S39840 | 09TW100052a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-12-06 | 2028-06-28 | 2029-01-19 | 2030-12-11 | 2032-03-31 |  |  | 2024-10-16 | 2027-12-06 | 2028-06-28 | 2029-01-19 | 2030-12-11 | 2032-03-31 |  |  | 0 | 3.3904 |  |  | 0 | 0 | 0 | 0 | 0.031427 | 0.52137 | 1.2291 | 3.3904 | 0 | 0 | 0 | 0 | 0.031427 | 0.52137 | 1.2291 | 3.3904 |  | No | Delivery Mechanism | AMP8
| TMS | Horley STW Storm Overflow - Option 2 | UBA8.SEW.S38366 | 08TW101017a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  |  | 2024-10-16 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  |  | 0 | 16.0956 |  |  | 0 | 0 | 0 | 0 | 0.6732 | 1.8205 | 4.8534 | 16.0956 | 0 | 0 | 0 | 0 | 0.6732 | 1.8205 | 4.8534 | 16.0956 |  | No | Delivery Mechanism | AMP8
| TMS | Horley STW Surrey Phosphorus Dosing & TT | UBA8.SEW.S38945 | 08TW100911a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  |  | 2024-10-16 | 2028-02-22 | 2029-02-03 | 2029-08-21 | 2030-12-09 | 2032-03-31 |  |  | 0 | 14.3041 |  |  | 0 | 0 | 0 | 0 | 0.8114 | 2.2907 | 4.1811 | 14.3041 | 0 | 0 | 0 | 0 | 0.8114 | 2.2907 | 4.1811 | 14.3041 |  | No | Delivery Mechanism | AMP8
| TMS | IED - Aylesbury | UBA8.SEW.S42154, UBA8.SEW.S39555, UBA8.SEW.S42156, UBA8.SEW.S42155 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-03-30 | 2029-08-22 | 2030-04-22 | 2031-09-22 | 2032-03-31 |  |  | 2025-05-15 | 2026-03-30 | 2029-08-22 | 2030-04-22 | 2031-09-22 | 2032-03-31 |  |  | 0 | 22.8271 |  |  | 0 | 0 | 2.2955 | 5.2273 | 8.5328 | 12.951 | 18.0301 | 22.8271 | 0 | 0 | 2.2955 | 5.2273 | 8.5328 | 12.951 | 18.0301 | 22.8271 |  | No | Other | AMP8
| TMS | IED - Banbury | UBA8.SEW.S39557, UBA8.SEW.S42152, UBA8.SEW.S42150 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-04-29 | 2029-10-18 | 2030-06-18 | 2031-09-18 | 2032-03-31 |  |  | 2025-05-15 | 2026-04-29 | 2029-10-18 | 2030-06-18 | 2031-09-18 | 2032-03-31 |  |  | 0 | 15.8068 |  |  | 0 | 0 | 1.2904 | 2.986 | 4.6741 | 7.3898 | 11.1345 | 15.8068 | 0 | 0 | 1.2904 | 2.986 | 4.6741 | 7.3898 | 11.1345 | 15.8068 |  | No | Other | AMP8
| TMS | IED - Basingstoke | UBA8.SEW.S42146, UBA8.SEW.S39559, UBA8.SEW.S42147 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-07-15 | 2030-09-20 | 2030-12-03 | 2032-10-27 | 2033-03-31 |  |  | 2025-05-15 | 2030-07-15 | 2030-09-20 | 2030-12-03 | 2032-10-27 | 2033-03-31 |  |  | 0 | 23.9648 |  |  | 0 | 0 | 0.87478 | 2.1728 | 3.2801 | 5.3108 | 7.3415 | 23.9648 | 0 | 0 | 0.87478 | 2.1728 | 3.2801 | 5.3108 | 7.3415 | 23.9648 |  | No | Other | AMP8
| TMS | IED - Beckton | UBA8.SEW.S39604, UBA8.SEW.S42142 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-09-25 | 2029-12-03 | 2030-08-01 | 2032-01-01 | 2032-03-31 |  |  | 2025-05-15 | 2029-09-25 | 2029-12-03 | 2030-08-01 | 2032-01-01 | 2032-03-31 |  |  | 0 | 4.5428 |  |  | 0 | 0 | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 1.2033 | 4.5428 | 0 | 0 | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 1.2033 | 4.5428 |  | No | Other | AMP8
| TMS | IED - Beddington | UBA8.SEW.S42138, UBA8.SEW.S39561, UBA8.SEW.S42139 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-08-14 | 2030-10-22 | 2031-04-10 | 2032-09-09 | 2033-03-31 |  |  | 2025-05-15 | 2030-08-14 | 2030-10-22 | 2031-04-10 | 2032-09-09 | 2033-03-31 |  |  | 0 | 9.5166 |  |  | 0 | 0 | 1.1217 | 2.207 | 3.7231 | 5.1486 | 5.1486 | 9.5166 | 0 | 0 | 1.1217 | 2.207 | 3.7231 | 5.1486 | 5.1486 | 9.5166 |  | No | Other | AMP8
| TMS | IED - Bishops Stortford | UBA8.SEW.S42134, UBA8.SEW.S39563, UBA8.SEW.S42136, UBA8.SEW.S42135 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-03-30 | 2030-08-21 | 2031-04-21 | 2032-09-20 | 2033-03-31 |  |  | 2025-05-15 | 2026-03-30 | 2030-08-21 | 2031-04-21 | 2032-09-20 | 2033-03-31 |  |  | 0 | 16.0042 |  |  | 0 | 0 | 1.2873 | 2.9838 | 4.6689 | 7.4672 | 10.3887 | 16.0042 | 0 | 0 | 1.2873 | 2.9838 | 4.6689 | 7.4672 | 10.3887 | 16.0042 |  | No | Other | AMP8
| TMS | IED - Bracknell | UBA8.SEW.S42130, UBA8.SEW.S39565, UBA8.SEW.S42132, UBA8.SEW.S42131 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-12-24 | 2032-03-02 | 2032-09-02 | 2035-01-30 | 2035-03-31 |  |  | 2025-05-15 | 2031-12-24 | 2032-03-02 | 2032-09-02 | 2035-01-30 | 2035-03-31 |  |  | 0 | 15.5993 |  |  | 0 | 0 | 0.88527 | 1.2077 | 1.4894 | 1.7689 | 2.5915 | 15.5993 | 0 | 0 | 0.88527 | 1.2077 | 1.4894 | 1.7689 | 2.5915 | 15.5993 |  | No | Other | AMP8
| TMS | IED - Camberley | L902, UBA8.SEW.S42126 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2024-09-30 | 2026-05-30 | 2026-10-26 | 2027-04-28 | 2028-12-25 | 2032-03-31 |  |  | 2024-09-30 | 2026-05-30 | 2026-10-26 | 2027-04-28 | 2028-12-25 | 2032-03-31 |  |  | 0 | 18.1643 |  |  | 0 | 0 | 0.028042 | 0.12931 | 0.24542 | 0.43964 | 1.2953 | 18.1643 | 0 | 0 | 0.028042 | 0.12931 | 0.24542 | 0.43964 | 1.2953 | 18.1643 |  | No | Other | AMP8
| TMS | IED - Chertsey | UBA8.SEW.S42122, UBA8.SEW.S39569, UBA8.SEW.S42123 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-07-17 | 2030-09-24 | 2031-03-27 | 2033-08-23 | 2034-03-31 |  |  | 2025-05-15 | 2030-07-17 | 2030-09-24 | 2031-03-27 | 2033-08-23 | 2034-03-31 |  |  | 0 | 10.5605 |  |  | 0 | 0 | 0.21576 | 0.58469 | 0.58469 | 0.58469 | 1.559 | 10.5605 | 0 | 0 | 0.21576 | 0.58469 | 0.58469 | 0.58469 | 1.559 | 10.5605 |  | No | Other | AMP8
| TMS | IED - Crawley | UBA8.SEW.S39571, UBA8.SEW.S42119, UBA8.SEW.S42118 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-08-14 | 2029-10-22 | 2030-06-20 | 2031-08-22 | 2032-03-31 |  |  | 2025-05-15 | 2029-08-14 | 2029-10-22 | 2030-06-20 | 2031-08-22 | 2032-03-31 |  |  | 0 | 5.4643 |  |  | 0 | 0 | 0.68343 | 1.2291 | 1.7199 | 2.5867 | 3.802 | 5.4643 | 0 | 0 | 0.68343 | 1.2291 | 1.7199 | 2.5867 | 3.802 | 5.4643 |  | No | Other | AMP8
| TMS | IED - Crossness | UBA8.SEW.S42114, UBA8.SEW.S39606, UBA8.SEW.S42115 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-12-11 | 2030-02-18 | 2030-10-17 | 2036-07-15 | 2037-03-31 |  |  | 2025-05-15 | 2029-12-11 | 2030-02-18 | 2030-10-17 | 2036-07-15 | 2037-03-31 |  |  | 0 | 22.0744 |  |  | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 2.7649 | 22.0744 | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 2.7649 | 22.0744 |  | No | Other | AMP8
| TMS | IED - Deephams | UBA8.SEW.S42110, UBA8.SEW.S39573, UBA8.SEW.S42112, UBA8.SEW.S42111 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-03-30 | 2030-06-07 | 2030-11-07 | 2032-10-06 | 2033-03-31 |  |  | 2025-05-15 | 2030-03-30 | 2030-06-07 | 2030-11-07 | 2032-10-06 | 2033-03-31 |  |  | 0 | 26.986 |  |  | 0 | 0 | 4.0534 | 10.0069 | 15.5003 | 16.4544 | 17.3325 | 26.986 | 0 | 0 | 4.0534 | 10.0069 | 15.5003 | 16.4544 | 17.3325 | 26.986 |  | No | Other | AMP8
| TMS | IED - Didcot | UBA8.SEW.S39575, UBA8.SEW.S42108, UBA8.SEW.S42107, UBA8.SEW.S42106 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-09-24 | 2031-12-02 | 2032-06-03 | 2034-10-31 | 2035-03-31 |  |  | 2025-05-15 | 2031-09-24 | 2031-12-02 | 2032-06-03 | 2034-10-31 | 2035-03-31 |  |  | 0 | 18.3508 |  |  | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.7985 | 18.3508 | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.7985 | 18.3508 |  | No | Other | AMP8
| TMS | IED - East Hyde | UBA8.SEW.S42102 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2028-01-12 | 2028-03-21 | 2028-11-17 | 2030-01-21 | 2030-03-31 |  |  | 2025-05-15 | 2028-01-12 | 2028-03-21 | 2028-11-17 | 2030-01-21 | 2030-03-31 |  |  | 0 | 16.9986 |  |  | 0 | 0 | 2.3273 | 4.9479 | 8.5022 | 13.1421 | 16.7627 | 16.9986 | 0 | 0 | 2.3273 | 4.9479 | 8.5022 | 13.1421 | 16.7627 | 16.9986 |  | No | Other | AMP8
| TMS | IED - Hogsmill | UBA8.SEW.S42098, UBA8.SEW.S39579, UBA8.SEW.S42099 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-08-13 | 2030-10-21 | 2031-06-20 | 2032-09-20 | 2033-03-31 |  |  | 2025-05-15 | 2030-08-13 | 2030-10-21 | 2031-06-20 | 2032-09-20 | 2033-03-31 |  |  | 0 | 9.3866 |  |  | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.1648 | 9.3866 | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.1648 | 9.3866 |  | No | Other | AMP8
| TMS | IED - Long Reach | UBA8.SEW.S42094, UBA8.SEW.S39581 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-09-30 | 2030-12-06 | 2031-08-06 | 2032-10-07 | 2033-03-31 |  |  | 2025-05-15 | 2030-09-30 | 2030-12-06 | 2031-08-06 | 2032-10-07 | 2033-03-31 |  |  | 0 | 3.2666 |  |  | 0 | 0 | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 0.57541 | 3.2666 | 0 | 0 | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 0.57541 | 3.2666 |  | No | Other | AMP8
| TMS | IED - Maple Lodge | UBA8.SEW.S42090, UBA8.SEW.S39584, UBA8.SEW.S42092, UBA8.SEW.S42091 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-10-21 | 2031-12-29 | 2032-06-30 | 2039-12-30 | 2040-03-31 |  |  | 2025-05-15 | 2031-10-21 | 2031-12-29 | 2032-06-30 | 2039-12-30 | 2040-03-31 |  |  | 0 | 41.3886 |  |  | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 2.0814 | 41.3886 | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 2.0814 | 41.3886 |  | No | Other | AMP8
| TMS | IED - Mogden | UBA8.SEW.S39587, UBA8.SEW.S42087, UBA8.SEW.S42086 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-12-13 | 2031-02-20 | 2031-10-21 | 2036-08-04 | 2037-03-31 |  |  | 2025-05-15 | 2030-12-13 | 2031-02-20 | 2031-10-21 | 2036-08-04 | 2037-03-31 |  |  | 0 | 10.9223 |  |  | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.2374 | 10.9223 | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.2374 | 10.9223 |  | No | Other | AMP8
| TMS | IED - Oxford | UBA8.SEW.S39589, UBA8.SEW.S42083, UBA8.SEW.S42082 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2029-12-13 | 2030-02-20 | 2030-10-21 | 2034-01-12 | 2034-03-31 |  |  | 2025-05-15 | 2029-12-13 | 2030-02-20 | 2030-10-21 | 2034-01-12 | 2034-03-31 |  |  | 0 | 14.6242 |  |  | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.7127 | 14.6242 | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 1.7127 | 14.6242 |  | No | Other | AMP8
| TMS | IED - Reading | UBA8.SEW.S42078, L903 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2024-09-30 | 2025-08-31 | 2025-11-11 | 2026-04-15 | 2027-03-04 | 2027-03-31 |  |  | 2024-09-30 | 2025-08-31 | 2025-11-11 | 2026-04-15 | 2027-03-04 | 2027-03-31 |  |  | 0 | 1.3721 |  |  | 0 | 0 | 0.70322 | 1.2082 | 1.3721 | 1.3721 | 1.3721 | 1.3721 | 0 | 0 | 0.70322 | 1.2082 | 1.3721 | 1.3721 | 1.3721 | 1.3721 |  | No | Other | AMP8
| TMS | IED - Riverside | UBA8.SEW.S42074, UBA8.SEW.S39594 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2030-04-12 | 2030-06-20 | 2031-02-18 | 2032-07-20 | 2033-03-31 |  |  | 2025-05-15 | 2030-04-12 | 2030-06-20 | 2031-02-18 | 2032-07-20 | 2033-03-31 |  |  | 0 | 3.9713 |  |  | 0 | 0 | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 0.69966 | 3.9713 | 0 | 0 | 0.45746 | 0.57541 | 0.57541 | 0.57541 | 0.69966 | 3.9713 |  | No | Other | AMP8
| TMS | IED - Rye Meads | UBA8.SEW.S42070, UBA8.SEW.S39596, UBA8.SEW.S42072, UBA8.SEW.S42071 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2034-06-02 | 2034-08-10 | 2035-02-12 | 2037-09-14 | 2038-03-31 |  |  | 2025-05-15 | 2034-06-02 | 2034-08-10 | 2035-02-12 | 2037-09-14 | 2038-03-31 |  |  | 0 | 40.6175 |  |  | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 0.58469 | 40.6175 | 0 | 0 | 0.46484 | 0.58469 | 0.58469 | 0.58469 | 0.58469 | 40.6175 |  | No | Other | AMP8
| TMS | IED - Slough | UBA8.SEW.S39598, UBA8.SEW.S42068, UBA8.SEW.S42067, UBA8.SEW.S42066 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2026-04-29 | 2031-01-22 | 2031-09-22 | 2033-08-20 | 2034-03-31 |  |  | 2025-05-15 | 2026-04-29 | 2031-01-22 | 2031-09-22 | 2033-08-20 | 2034-03-31 |  |  | 0 | 28.34 |  |  | 0 | 0 | 2.2799 | 5.2978 | 8.5224 | 13.5173 | 18.758 | 28.34 | 0 | 0 | 2.2799 | 5.2978 | 8.5224 | 13.5173 | 18.758 | 28.34 |  | No | Other | AMP8
| TMS | IED - Swindon | UBA8.SEW.S39600, UBA8.SEW.S42064, UBA8.SEW.S42062 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-03-31 | 2031-06-06 | 2032-02-04 | 2034-01-03 | 2034-03-31 |  |  | 2025-05-15 | 2031-03-31 | 2031-06-06 | 2032-02-04 | 2034-01-03 | 2034-03-31 |  |  | 0 | 22.2663 |  |  | 0 | 0 | 2.1822 | 4.0575 | 6.5478 | 9.5734 | 11.7379 | 22.2663 | 0 | 0 | 2.1822 | 4.0575 | 6.5478 | 9.5734 | 11.7379 | 22.2663 |  | No | Other | AMP8
| TMS | IED - Wargrave | UBA8.SEW.S42058, UBA8.SEW.S39602, UBA8.SEW.S42060, UBA8.SEW.S42059 |  | Bioresources - IED and Reg changes | PCDWW30 | Retained |  | 2025-03-31 | 2025-03-31 | 2025-05-15 | 2031-01-24 | 2031-04-03 | 2031-12-02 | 2033-05-03 | 2033-03-31 |  |  | 2025-05-15 | 2031-01-24 | 2031-04-03 | 2031-12-02 | 2033-05-03 | 2033-03-31 |  |  | 0 | 14.9872 |  |  | 0 | 0 | 1.1111 | 3.0821 | 5.0476 | 7.919 | 10.517 | 14.9872 | 0 | 0 | 1.1111 | 3.0821 | 5.0476 | 7.919 | 10.517 | 14.9872 |  | No | Other | AMP8
| TMS | INV4 Sites Storm Overflow Programme | UBA8.SEW.S39995, L620 | 08TW101108ft, 08TW101108ui, 08TW101108ni, 08TW101108uc, 08TW101108aa, 08TW101108it, 08TW101108es, 08TW101108ot, 08TW101108ac, 08TW101108nj, 08TW101108ad, 08TW101108do, 08TW101108nk, 08TW101108rm, 08TW101108nl, 08TW101108ta, 08TW101108uf, 08TW101108us, 08TW101108os, 08TW101108qa, 08TW101108ol, 08TW101108tt, 08TW101108ed, 08TW101108cv, 08TW101108tw, 08TW101108ae, 08TW101108pt, 08TW101108ag, 08TW101108pv, 08TW101108fv, 08TW101108rk, 08TW101108ah, 08TW101108tb, 08TW101108ai, 08TW101108tc, 08TW101108iv, 08TW101108om, 08TW101108nm, 08TW101108ix, 08TW101108iz, 08TW101108hd, 08TW101108ep, 08TW101108cb, 08TW101108ak, 08TW101108ja, 08TW101108no, 08TW101108gb, 08TW101108dp, 08TW101108nn, 08TW101108fw, 08TW101108al, 08TW101108fx, 08TW101108dx, 08TW101108pf, 08TW101108rb, 08TW101108pg, 08TW101108gr, 08TW101108am, 08TW101108td, 08TW101108np, 08TW101108an, 08TW101108ao, 08TW101108ap, 08TW101108jk, 08TW101108nc, 08TW101108nb, 08TW101108na, 08TW101108mz, 08TW101108my, 08TW101108mx, 08TW101108mw, 08TW101108mv, 08TW101108fk, 08TW101108aq, 08TW101108nq, 08TW101108uq, 08TW101108te, 08TW101108nr, 08TW101108fl, 08TW101108jo, 08TW101108jm, 08TW101108ar, 08TW101108gg, 08TW101108ou, 08TW101108rh, 08TW101108jq, 08TW101108at, 08TW101108gm, 08TW101108qe, 08TW101108jr, 08TW101108qz, 08TW101108js, 08TW101108ns, 08TW101108uk, 08TW101108ud, 08TW101108el, 08TW101108qf, 08TW101108ny, 08TW101108rc, 08TW101108au, 08TW101108fh, 08TW101108pi, 08TW101108hi, 08TW101108hj, 08TW101108fo, 08TW101108nt, 08TW101108ez, 08TW101108nu, 08TW101108gd, 08TW101108aw, 08TW101108tz, 08TW101108jx, 08TW101108jw, 08TW101108jy, 08TW101108dz, 08TW101108tf, 08TW101108gf, 08TW101108ba, 08TW101108kb, 08TW101108bd, 08TW101108ew, 08TW101108tg, 08TW101108ul, 08TW101108ut, 08TW101108uu, 08TW101108uv, 08TW101108uw, 08TW101108ux, 08TW101108uy, 08TW101108uz, 08TW101108dm, 08TW101108ke, 08TW101108up, 08TW101108nw, 08TW101108ei, 08TW101108be, 08TW101108gj, 08TW101108cc, 08TW101108bf, 08TW101108uh, 08TW101108kf, 08TW101108th, 08TW101108qg, 08TW101108kj, 08TW101108et, 08TW101108nx, 08TW101108kk, 08TW101108tu, 08TW101108bg, 08TW101108du, 08TW101108ey, 08TW101108pj, 08TW101108pk, 08TW101108bh, 08TW101108ue, 08TW101108ko, 08TW101108ti, 08TW101108re, 08TW101108gx, 08TW101108gh, 08TW101108bk, 08TW101108bl, 08TW101108ev, 08TW101108bm, 08TW101108bn, 08TW101108qi, 08TW101108gk, 08TW101108rf, 08TW101108of, 08TW101108ks, 08TW101108dn, 08TW101108or, 08TW101108fc, 08TW101108op, 08TW101108dl, 08TW101108ee, 08TW101108bo, 08TW101108fu, 08TW101108kt, 08TW101108fd, 08TW101108bp, 08TW101108bq, 08TW101108gu, 08TW101108hp, 08TW101108br, 08TW101108ku, 08TW101108bs, 08TW101108nz, 08TW101108oq, 08TW101108pn, 08TW101108po, 08TW101108pp, 08TW101108ex, 08TW101108dk, 08TW101108ri, 08TW101108on, 08TW101108dj, 08TW101108qk, 08TW101108oa, 08TW101108eg, 08TW101108pq, 08TW101108ky, 08TW101108ua, 08TW101108bu, 08TW101108di, 08TW101108lb, 08TW101108ff, 08TW101108tj, 08TW101108bv, 08TW101108bw, 08TW101108rg, 08TW101108rj, 08TW101108qs, 08TW101108ql, 08TW101108dh, 08TW101108va, 08TW101108dt, 08TW101108dg, 08TW101108dr, 08TW101108bb, 08TW101108fg, 08TW101108fp, 08TW101108ub, 08TW101108eh, 08TW101108bx, 08TW101108ds, 08TW101108by, 08TW101108ca, 08TW101108bz, 08TW101108ro, 08TW101108qw, 08TW101108qx, 08TW101108lf, 08TW101108lg, 08TW101108ps, 08TW101108li, 08TW101108de, 08TW101108lj, 08TW101108lk, 08TW101108nv, 08TW101108ug, 08TW101108gp, 08TW101108ab, 08TW101108ln, 08TW101108gq, 08TW101108cd, 08TW101108dc, 08TW101108lo, 08TW101108pw, 08TW101108rl, 08TW101108fi, 08TW101108eo, 08TW101108ob, 08TW101108tk, 08TW101108lq, 08TW101108lr, 08TW101108bc, 08TW101108lv, 08TW101108dv, 08TW101108un, 08TW101108fq, 08TW101108ek, 08TW101108da, 08TW101108gs, 08TW101108eq, 08TW101108tx, 08TW101108cz, 08TW101108hx, 08TW101108fm, 08TW101108ce, 08TW101108cy, 08TW101108oc, 08TW101108dq, 08TW101108gl, 08TW101108fs, 08TW101108ef, 08TW101108dw, 08TW101108ia, 08TW101108mb, 08TW101108ga, 08TW101108cf, 08TW101108az, 08TW101108cg, 08TW101108gv, 08TW101108gw, 08TW101108qn, 08TW101108od, 08TW101108ch, 08TW101108ic, 08TW101108mf, 08TW101108ty, 08TW101108tl, 08TW101108em, 08TW101108cx, 08TW101108gc, 08TW101108cw, 08TW101108ej, 08TW101108mi, 08TW101108mj, 08TW101108cj, 08TW101108ck, 08TW101108cm, 08TW101108ie, 08TW101108qo, 08TW101108df, 08TW101108ax, 08TW101108vb, 08TW101108gz, 08TW101108ih, 08TW101108ii, 08TW101108ij, 08TW101108ik, 08TW101108if, 08TW101108dy, 08TW101108ig, 08TW101108ea, 08TW101108fb, 08TW101108cn, 08TW101108qt, 08TW101108co, 08TW101108oe, 08TW101108cu, 08TW101108cp, 08TW101108cq, 08TW101108fj, 08TW101108cr, 08TW101108ml, 08TW101108mm, 08TW101108jl, 08TW101108fa, 08TW101108ra, 08TW101108ur, 08TW101108gn, 08TW101108tm, 08TW101108og, 08TW101108fz, 08TW101108rp, 08TW101108tn, 08TW101108oo, 08TW101108qp, 08TW101108mq, 08TW101108gi, 08TW101108tv, 08TW101108fn, 08TW101108to, 08TW101108ip, 08TW101108eb, 08TW101108oh, 08TW101108iq, 08TW101108qq, 08TW101108oi, 08TW101108cs, 08TW101108ct, 08TW101108tp, 08TW101108ms, 08TW101108mt, 08TW101108ci, 08TW101108tq, 08TW101108gy, 08TW101108qr, 08TW101108pz, 08TW101108tr, 08TW101108db, 08TW101108ts, 08TW101108ec, 08TW101108gt, MULTIPLE!! | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-06-03 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-03-31 |  |  | 2025-06-03 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-02-26 | 2027-03-31 |  |  | 9.7663 | 33.978 |  |  | 0 | 9.7663 | 24.3546 | 33.978 | 33.978 | 33.978 | 33.978 | 33.978 | 0 | 9.7663 | 24.3546 | 33.978 | 33.978 | 33.978 | 33.978 | 33.978 |  | No | Other | AMP8
| TMS | Iver North 2 P limit | UBA8.SEW.S38386 | 08TW100159a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-11-20 | 2027-04-14 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 2024-11-20 | 2027-04-14 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 0 | 2.2917 |  |  | 0 | 0 | 0 | 0 | 0.27137 | 0.59334 | 1.6745 | 2.2917 | 0 | 0 | 0 | 0 | 0.27137 | 0.59334 | 1.6745 | 2.2917 |  | No | Other | AMP8
| TMS | Kings Sutton STW Phosphorus Dosing & TT | UBA8.SEW.S38906 | 09TW100038a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-14 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 2024-10-16 | 2028-04-14 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 0 | 6.441 |  |  | 0 | 0 | 0 | 0 | 0.22333 | 0.85847 | 1.6109 | 6.441 | 0 | 0 | 0 | 0 | 0.22333 | 0.85847 | 1.6109 | 6.441 |  | No | Delivery Mechanism | AMP8
| TMS | Leaking sewers Investigation Epsom MD | UBA8.SEW.S38864 | 08TW100280f | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 0.75173 |  |  | 0 | 0 | 0.075176 | 0.60139 | 0.75173 | 0.75173 | 0.75173 | 0.75173 | 0 | 0 | 0.075176 | 0.60139 | 0.75173 | 0.75173 | 0.75173 | 0.75173 |  | No | Other | AMP8
| TMS | Leaking sewers Medway MD | UBA8.SEW.S38863 | 08TW100280g | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 0.74811 |  |  | 0 | 0 | 0.074812 | 0.59849 | 0.74811 | 0.74811 | 0.74811 | 0.74811 | 0 | 0 | 0.074812 | 0.59849 | 0.74811 | 0.74811 | 0.74811 | 0.74811 |  | No | Other | AMP8
| TMS | Leatherhead STW Phos Dosing TT + Alkalin | UBA8.SEW.S38970 | 08TW100914a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-02-26 | 2028-02-22 | 2028-08-19 | 2030-11-22 | 2032-03-31 |  |  | 2024-10-16 | 2027-02-26 | 2028-02-22 | 2028-08-19 | 2030-11-22 | 2032-03-31 |  |  | 0 | 18.513 |  |  | 0 | 0 | 0 | 0 | 1.051 | 3.0041 | 6.2734 | 18.513 | 0 | 0 | 0 | 0 | 1.051 | 3.0041 | 6.2734 | 18.513 |  | No | Delivery Mechanism | AMP8
| TMS | Leatherhead STW Storm Overflow | UBA8.SEW.S42167 | 10TW100025a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-12-17 22:39 | 2028-07-23 15:52 | 2028-12-16 11:20 | 2029-12-16 | 2030-03-31 |  |  | 2024-06-26 | 2027-12-17 22:39 | 2028-07-23 15:52 | 2028-12-16 11:20 | 2029-12-16 | 2030-03-31 |  |  | 0 | 12.7891 |  |  | 0 | 0 | 0 | 0 | 1.3804 | 6.784 | 12.7891 | 12.7891 | 0 | 0 | 0 | 0 | 1.3804 | 6.784 | 12.7891 | 12.7891 |  | No | Other | AMP8
| TMS | LECKHAMPSTEAD STW | UBA8.SEW.S41635 | 08TW101402e | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 2025-04-01 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 2.865 |  |  | 0 | 0 | 0.16973 | 0.45671 | 0.7639 | 2.2324 | 2.8311 | 2.865 | 0 | 0 | 0.16973 | 0.45671 | 0.7639 | 2.2324 | 2.8311 | 2.865 |  | No | Other | AMP8
| TMS | Lee Chalk continuous discharge MD | UBA8.SEW.S38861 | 08TW100280e | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 0.73827 |  |  | 0 | 0 | 0.073828 | 0.59062 | 0.73827 | 0.73827 | 0.73827 | 0.73827 | 0 | 0 | 0.073828 | 0.59062 | 0.73827 | 0.73827 | 0.73827 | 0.73827 |  | No | Other | AMP8
| TMS | Little Compton STW Phosphor Dosing & TT | UBA8.SEW.S39025 | 08TW100916a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-05-19 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 2024-10-16 | 2028-05-19 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 0 | 3.4244 |  |  | 0 | 0 | 0 | 0 | 0.14181 | 0.51503 | 1.2327 | 3.4244 | 0 | 0 | 0 | 0 | 0.14181 | 0.51503 | 1.2327 | 3.4244 |  | No | Delivery Mechanism | AMP8
| TMS | Little Marlow STW Phosphorus Dosing & TT | UBA8.SEW.S39715 | 09TW100040a, 08TW101485a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-31 | 2028-02-07 | 2028-08-15 | 2029-12-10 | 2031-03-31 |  |  | 2024-10-16 | 2027-03-31 | 2028-02-07 | 2028-08-15 | 2029-12-10 | 2031-03-31 |  |  | 0 | 31.4694 |  |  | 0 | 0 | 0 | 0.29237 | 4.6838 | 9.3578 | 24.9203 | 31.4694 | 0 | 0 | 0 | 0.29237 | 4.6838 | 9.3578 | 24.9203 | 31.4694 |  | No | Other | AMP8
| TMS | LITTLE MILTON STW- Phosphorus Dosing TT | UBA8.SEW.S38796 | 08TW100917a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-06-28 | 2028-05-17 | 2028-12-13 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-06-28 | 2028-05-17 | 2028-12-13 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.7511 |  |  | 0 | 0 | 0 | 0 | 0.16257 | 0.54081 | 1.0766 | 3.7511 | 0 | 0 | 0 | 0 | 0.16257 | 0.54081 | 1.0766 | 3.7511 |  | No | Delivery Mechanism | AMP8
| TMS | Longborough STW Phosphorus Dosing & TT | UBA8.SEW.S39027 | 08TW100918a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.481 |  |  | 0 | 0 | 0 | 0 | 0.14416 | 0.52354 | 1.2531 | 3.481 | 0 | 0 | 0 | 0 | 0.14416 | 0.52354 | 1.2531 | 3.481 |  | No | Delivery Mechanism | AMP8
| TMS | Lots Road SPS Electrical Upgrade | L883 |  | Climate change uplift | PCDWW32 | Retained |  |  |  | 2025-04-01 | 2026-08-19 | 2027-04-27 | 2027-08-24 | 2030-07-15 | 2030-04-25 |  |  | 2025-04-01 | 2026-08-19 | 2027-04-27 | 2027-08-24 | 2030-07-15 | 2030-04-25 |  |  | 0 | 28.6246 |  |  | 0 | 0 | 1.1328 | 3.7026 | 8.0883 | 19.0005 | 27.9044 | 28.6246 | 0 | 0 | 1.1328 | 3.7026 | 8.0883 | 19.0005 | 27.9044 | 28.6246 |  | No | Other | AMP8
| TMS | Lower Middleton Cheney Phos Dosing & TT | UBA8.SEW.S38975 | 08TW100919a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2026-06-28 | 2027-01-19 | 2028-12-10 | 2030-03-31 |  |  | 2024-10-16 | 2024-10-16 | 2026-06-28 | 2027-01-19 | 2028-12-10 | 2030-03-31 |  |  | 0 | 6.5985 |  |  | 0 | 0 | 0.27326 | 0.99242 | 2.3754 | 6.1163 | 6.545 | 6.5985 | 0 | 0 | 0.27326 | 0.99242 | 2.3754 | 6.1163 | 6.545 | 6.5985 |  | No | Other | AMP8
| TMS | MAIDENHEAD STW | UBA8.SEW.S37931 | 08TW100165a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2027-03-31 | 2027-03-31 | 2022-09-23 | 2022-09-24 | 2024-03-02 | 2024-09-12 | 2026-12-09 | 2028-03-31 |  |  | 2022-09-23 | 2022-09-24 | 2024-03-02 | 2024-09-12 | 2026-12-09 | 2028-03-31 |  |  | 0 | 2.0939 |  |  | 0 | 0 | 0.47046 | 1.8284 | 2.0786 | 2.0939 | 2.0939 | 2.0939 | 0 | 0 | 0.47046 | 1.8284 | 2.0786 | 2.0939 | 2.0939 | 2.0939 |  | No | Other | AMP8
| TMS | Maidenhead STW P Removal (2 WINEP Actions) | UBA8.SEW.S38931 | 08TW100160a, 08TW100921a | P-removal | PCDWW10 | Retained |  | 2030-05-13 | 2030-05-13 | 2024-09-18 | 2028-09-23 | 2030-03-02 | 2030-09-12 | 2032-12-08 | 2034-03-31 |  |  | 2024-09-18 | 2028-09-23 | 2030-03-02 | 2030-09-12 | 2032-12-08 | 2034-03-31 |  |  | 0 | 27.4465 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1.1967 | 27.4465 | 0 | 0 | 0 | 0 | 0 | 0 | 1.1967 | 27.4465 |  | No | Delivery Mechanism | AMP8
| TMS | Marsh Gibbon STW AMP8 Ammonia | L840 | 08TW101398a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2024-09-18 | 2024-09-18 | 2025-04-30 | 2025-06-20 | 2025-12-13 | 2027-03-31 |  |  | 2024-09-18 | 2024-09-18 | 2025-04-30 | 2025-06-20 | 2025-12-13 | 2027-03-31 |  |  | 9.193e-07 | 1.3648 |  |  | 0 | 9.193e-07 | 0.88119 | 1.3564 | 1.3648 | 1.3648 | 1.3648 | 1.3648 | 0 | 9.193e-07 | 0.88119 | 1.3564 | 1.3648 | 1.3648 | 1.3648 | 1.3648 |  | No | Other | AMP8
| TMS | Mid-Chiltern Continuous Discharge MD | UBA8.SEW.S38860 | 08TW100280c | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  |  | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 0.18344 |  |  | 0 | 0 | 0.018347 | 0.14675 | 0.18344 | 0.18344 | 0.18344 | 0.18344 | 0 | 0 | 0.018347 | 0.14675 | 0.18344 | 0.18344 | 0.18344 | 0.18344 |  | No | Other | AMP8
| TMS | Middleton Cheney STW Cypermethrin | UBA8.SEW.S40580 | 08TW101452a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2025-12-07 | 2027-02-22 | 2027-08-12 | 2029-11-19 | 2031-03-31 |  |  | 2024-10-16 | 2025-12-07 | 2027-02-22 | 2027-08-12 | 2029-11-19 | 2031-03-31 |  |  | 0 | 10.2528 |  |  | 0 | 0 | 0 | 0.58544 | 1.6509 | 3.0127 | 7.5539 | 10.2528 | 0 | 0 | 0 | 0.58544 | 1.6509 | 3.0127 | 7.5539 | 10.2528 |  | No | Delivery Mechanism | AMP8
| TMS | MiltonUnderWychwood STW Phos Dosing TT | UBA8.SEW.S38888 | 08TW100922a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-12 | 2026-05-07 | 2026-11-18 | 2028-12-14 | 2030-03-31 |  |  | 2024-10-16 | 2025-07-12 | 2026-05-07 | 2026-11-18 | 2028-12-14 | 2030-03-31 |  |  | 0 | 6.0184 |  |  | 0 | 0 | 0 | 0.47253 | 1.2119 | 4.0875 | 5.9359 | 6.0184 | 0 | 0 | 0 | 0.47253 | 1.2119 | 4.0875 | 5.9359 | 6.0184 |  | No | Other | AMP8
| TMS | Mollington STW Phosphorus Dosing and TT | UBA8.SEW.S38974 | 08TW100957a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.4453 |  |  | 0 | 0 | 0 | 0 | 0.14268 | 0.51818 | 1.2403 | 3.4453 | 0 | 0 | 0 | 0 | 0.14268 | 0.51818 | 1.2403 | 3.4453 |  | No | Delivery Mechanism | AMP8
| TMS | Moreton in Marsh STW - AMP8 Growth | UBA8.SEW.S39487 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2025-10-16 | 2026-05-16 | 2026-12-14 | 2028-11-24 | 2030-03-31 |  |  | 2024-10-16 | 2025-10-16 | 2026-05-16 | 2026-12-14 | 2028-11-24 | 2030-03-31 |  |  | 0 | 7.5002 |  |  | 0 | 0 | 0.094183 | 1.925 | 4.4442 | 7.1804 | 7.3679 | 7.5002 | 0 | 0 | 0.094183 | 1.925 | 4.4442 | 7.1804 | 7.3679 | 7.5002 |  | Yes | Other | AMP8
| TMS | Moreton-in-Marsh STW - Phos Dose TT+FST | UBA8.SEW.S41910 | 08TW100923a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-02-04 | 2027-01-10 | 2027-07-25 | 2028-12-13 | 2030-03-31 |  |  | 2024-10-16 | 2026-02-04 | 2027-01-10 | 2027-07-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 9.7012 |  |  | 0 | 0 | 0.58171 | 2.0691 | 4.8267 | 9.4346 | 9.6299 | 9.7012 | 0 | 0 | 0.58171 | 2.0691 | 4.8267 | 9.4346 | 9.6299 | 9.7012 |  | Yes | Other | AMP8
| TMS | Oxford STW AMP 7 | K245 | 08TW100924a | P-removal | PCDWW10 | Retained |  | 2024-03-31 | 2025-03-31 | 2021-04-30 | 2022-01-31 | 2025-12-31 | 2027-03-30 | 2032-03-30 | 2032-02-29 |  | IM2 | 2024-09-18 | 2024-10-03 | 2025-12-31 | 2027-03-30 | 2030-03-31 | 2030-03-31 |  |  | 0 | 39.258 |  |  |  |  | 3.2317 | 8.3389 | 17.2529 | 26.4051 | 35.7017 | 62.9271 |  |  | 2.79 | 5.8115 | 10.8105 | 16.0178 | 21.3139 | 39.258 |  | Yes | Delivery Mechanism | AMP8
| TMS | Oxford STW AMP 7 | K245 | 08TW100166a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2024-03-31 | 2025-03-31 | 2021-04-30 | 2022-01-31 | 2025-12-31 | 2027-03-30 | 2032-03-30 | 2032-02-29 |  | IM2 | 2021-04-30 | 2025-10-04 | 2027-01-01 | 2028-03-30 | 2031-04-01 | 2032-03-31 |  |  | 0 | 2.6043 |  |  |  |  | 0.21438 | 0.55319 | 1.1445 | 1.7517 | 2.3684 | 4.1745 |  |  | 0.18508 | 0.38552 | 0.71715 | 1.0626 | 1.4139 | 2.6043 |  | Yes | Other | AMP8
| TMS | PANGBOURNE STW | UBA8.SEW.S38523 | 08TW100176a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-04-18 | 2026-02-11 | 2026-08-25 | 2027-12-16 | 2029-03-31 |  |  | 2024-10-16 | 2025-04-18 | 2026-02-11 | 2026-08-25 | 2027-12-16 | 2029-03-31 |  |  | 0 | 2.1941 |  |  | 0 | 0 | 0.17756 | 0.54956 | 1.5018 | 2.169 | 2.1887 | 2.1941 | 0 | 0 | 0.17756 | 0.54956 | 1.5018 | 2.169 | 2.1887 | 2.1941 |  | No | Other | AMP8
| TMS | Phosphorus Investigations | UBA8.SEW.S39057 | 08TW100204a, 08TW100202a, 08TW100201a, 08TW100198a, 08TW100197a, 08TW100203a, 08TW100200a, 08TW100199a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 3.8597 |  |  | 0 | 0 | 0 | 1.4632 | 3.3919 | 3.8597 | 3.8597 | 3.8597 | 0 | 0 | 0 | 1.4632 | 3.3919 | 3.8597 | 3.8597 | 3.8597 |  | No | Other | AMP8
| TMS | PR24 WINEP Ammonia Investigations | UBA8.SEW.S38655 | 08TW100180a, 08TW100178a, 08TW100179a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 1.2132 |  |  | 0 | 0 | 0.40442 | 0.80883 | 1.2132 | 1.2132 | 1.2132 | 1.2132 | 0 | 0 | 0.40442 | 0.80883 | 1.2132 | 1.2132 | 1.2132 | 1.2132 |  | No | Other | AMP8
| TMS | PR24 WINEP DO | UBA8.SEW.S38654 | 08TW100193a, 08TW100189a, 08TW100188a, 08TW100185a, 08TW100184a, 08TW100183a, 08TW100182a, 08TW100196a, 08TW100195a, 08TW100191a, 08TW100190a, 08TW100187a, 08TW100186a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 2024-06-19 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 4.3015 |  |  | 0 | 0 | 1.4338 | 2.8677 | 4.3015 | 4.3015 | 4.3015 | 4.3015 | 0 | 0 | 1.4338 | 2.8677 | 4.3015 | 4.3015 | 4.3015 | 4.3015 |  | No | Other | AMP8
| TMS | PR24 WINEP Kennett DO Investigation | UBA8.SEW.S38661 | 08TW100152a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-07-17 | 2027-07-29 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 2024-07-17 | 2027-07-29 | 2028-03-31 | 2028-03-31 | 2028-03-31 | 2028-03-31 |  |  | 0 | 0.1206 |  |  | 0 | 0 | 0.040199 | 0.080399 | 0.1206 | 0.1206 | 0.1206 | 0.1206 | 0 | 0 | 0.040199 | 0.080399 | 0.1206 | 0.1206 | 0.1206 | 0.1206 |  | No | Other | AMP8
| TMS | PR24 WINEP Silk Stream Investigation | UBA8.SEW.S38569 | 08TW100149a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 2025-04-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 0 | 1.1626 |  |  | 0 | 0 | 1.1626 | 1.1626 | 1.1626 | 1.1626 | 1.1626 | 1.1626 | 0 | 0 | 1.1626 | 1.1626 | 1.1626 | 1.1626 | 1.1626 | 1.1626 |  | No | Other | AMP8
| TMS | PR24 WINEP UMON6d | UBA8.SEW.S40421B | 08TW100734d | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | PCDWW3 | Retained |  | 2030-03-31 | 2030-03-31 |  | 2030-05-12 | 2030-06-14 | 2031-01-13 | 2032-11-19 | 2034-03-31 |  |  |  | 2030-05-12 | 2030-06-14 | 2031-01-13 | 2032-11-19 | 2034-03-31 |  |  | 0 | 6.3935 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.3124 | 6.3935 | 0 | 0 | 0 | 0 | 0 | 0 | 0.3124 | 6.3935 |  | No | Other | AMP8
| TMS | Princes Risborough STW Phos Dosing & TT | UBA8.SEW.S38936 | 08TW100925a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-03-04 | 2029-02-09 | 2029-08-26 | 2030-12-15 | 2032-03-31 |  |  | 2024-10-16 | 2028-03-04 | 2029-02-09 | 2029-08-26 | 2030-12-15 | 2032-03-31 |  |  | 0 | 8.0857 |  |  | 0 | 0 | 0 | 0 | 0.33485 | 1.2161 | 2.9107 | 8.0857 | 0 | 0 | 0 | 0 | 0.33485 | 1.2161 | 2.9107 | 8.0857 |  | No | Delivery Mechanism | AMP8
| TMS | Priors Marston STW Phosphorus Wetlands | UBA8.SEW.S38896 | 08TW100926a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-10-25 | 2026-06-14 | 2027-01-17 | 2028-11-19 | 2030-03-31 |  |  | 2024-10-16 | 2025-10-25 | 2026-06-14 | 2027-01-17 | 2028-11-19 | 2030-03-31 |  |  | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | No | Other | AMP8
| TMS | Purton STW Phosphorus Dosing TT + FST | UBA8.SEW.S38928 | 08TW101887a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-02-21 | 2027-02-03 | 2027-08-21 | 2028-12-08 | 2030-03-31 |  |  | 2024-10-16 | 2026-02-21 | 2027-02-03 | 2027-08-21 | 2028-12-08 | 2030-03-31 |  |  | 0 | 8.3111 |  |  | 0 | 0 | 0 | 0.56977 | 1.9668 | 4.6599 | 8.1514 | 8.3111 | 0 | 0 | 0 | 0.56977 | 1.9668 | 4.6599 | 8.1514 | 8.3111 |  | No | Other | AMP8
| TMS | Reading STW Phos Dosing TT + Alkalinity | UBA8.SEW.S38971 | 08TW100928a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-02-27 | 2027-09-08 | 2028-10-15 | 2031-03-30 | 2032-03-31 |  |  | 2024-10-16 | 2027-02-27 | 2027-09-08 | 2028-10-15 | 2031-03-30 | 2032-03-31 |  |  | 0 | 53.2557 |  |  | 0 | 0 | 0 | 0.60826 | 1.3497 | 3.9717 | 22.5515 | 53.2557 | 0 | 0 | 0 | 0.60826 | 1.3497 | 3.9717 | 22.5515 | 53.2557 |  | No | Delivery Mechanism | AMP8
| TMS | Reigate STW Phosphorus Dosing and TT | UBA8.SEW.S39022 | 08TW101888a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2026-02-10 | 2026-08-21 | 2029-12-21 | 2031-03-31 |  |  | 2024-10-16 | 2024-10-16 | 2026-02-10 | 2026-08-21 | 2029-12-21 | 2031-03-31 |  |  | 0 | 20.1284 |  |  | 0 | 0 | 0 | 1.2237 | 3.2767 | 8.2045 | 19.5712 | 20.1284 | 0 | 0 | 0 | 1.2237 | 3.2767 | 8.2045 | 19.5712 | 20.1284 |  | No | Other | AMP8
| TMS | River Mole_Ironsbottom CSO_Option 2b | UBA8.SEW.S38557 | 08TW101021a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-04-21 10:31 | 2028-11-18 11:12 | 2029-01-13 11:12 | 2029-07-09 | 2030-03-31 |  |  | 2024-11-06 | 2028-04-21 10:31 | 2028-11-18 11:12 | 2029-01-13 11:12 | 2029-07-09 | 2030-03-31 |  |  | 0 | 3.9766 |  |  | 0 | 0 | 0 | 0 | 0.098989 | 3.2715 | 3.9766 | 3.9766 | 0 | 0 | 0 | 0 | 0.098989 | 3.2715 | 3.9766 | 3.9766 |  | No | Other | AMP8
| TMS | River Mole_Stonebridge CSO_Option 2 | UBA8.SEW.S38361 | 08TW101003a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-03-17 15:13 | 2028-08-14 12:27 | 2029-01-11 09:40 | 2030-09-26 | 2031-03-31 |  |  | 2024-10-23 | 2028-03-17 15:13 | 2028-08-14 12:27 | 2029-01-11 09:40 | 2030-09-26 | 2031-03-31 |  |  | 0 | 6.2667 |  |  | 0 | 0 | 0 | 0 | 0.17063 | 2.4773 | 5.033 | 6.2667 | 0 | 0 | 0 | 0 | 0.17063 | 2.4773 | 5.033 | 6.2667 |  | No | Other | AMP8
| TMS | River Wandle Streatham Relief CSO B | UBA8.SEW.S38550 | 08TW101064a 08TW101096a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-05-19 06:44 | 2029-05-18 06:44 | 2029-09-02 07:56 | 2030-11-21 | 2031-03-31 |  |  | 2024-11-20 | 2028-05-19 06:44 | 2029-05-18 06:44 | 2029-09-02 07:56 | 2030-11-21 | 2031-03-31 |  |  | 0 | 13.9998 |  |  | 0 | 0 | 0 | 0 | 0.31674 | 3.9327 | 8.4706 | 13.9998 | 0 | 0 | 0 | 0 | 0.31674 | 3.9327 | 8.4706 | 13.9998 |  | No | Other | AMP8
| TMS | River Wandle Streatham Relief CSO E | UBA8.SEW.S38372 | 08TW101097a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-05-20 10:57 | 2026-12-01 11:28 | 2027-01-26 11:28 | 2027-08-17 | 2028-03-31 |  |  | 2024-11-20 | 2026-05-20 10:57 | 2026-12-01 11:28 | 2027-01-26 11:28 | 2027-08-17 | 2028-03-31 |  |  | 0 | 4.3922 |  |  | 0 | 0 | 0.10147 | 2.6984 | 4.3922 | 4.3922 | 4.3922 | 4.3922 | 0 | 0 | 0.10147 | 2.6984 | 4.3922 | 4.3922 | 4.3922 | 4.3922 |  | No | Other | AMP8
| TMS | Rye Meads STW Phosphorus Bio-P and TT | UBA8.SEW.S39010 | 09TW100046a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-02-19 | 2027-07-07 | 2028-12-18 | 2032-03-09 | 2033-03-31 |  |  | 2024-11-20 | 2026-02-19 | 2027-07-07 | 2028-12-18 | 2032-03-09 | 2033-03-31 |  |  | 0 | 109.1367 |  |  | 0 | 0 | 0 | 0 | 6.1936 | 17.703 | 32.399 | 109.1367 | 0 | 0 | 0 | 0 | 6.1936 | 17.703 | 32.399 | 109.1367 |  | Yes | Enhanced engagement | AMP8
| TMS | Sandhurst STW Phosphorus Dosing and TT | UBA8.SEW.S39054 | 08TW100930a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2029-08-29 | 2030-09-13 | 2031-03-15 | 2032-11-20 | 2034-03-31 |  |  | 2024-10-16 | 2029-08-29 | 2030-09-13 | 2031-03-15 | 2032-11-20 | 2034-03-31 |  |  | 0 | 10.7445 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.098905 | 10.7445 | 0 | 0 | 0 | 0 | 0 | 0 | 0.098905 | 10.7445 |  | No | Delivery Mechanism | AMP8
| TMS | SHERBORNE ST JOHN STW Phos Dosing and TT | UBA8.SEW.S39053 | 08TW100932a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-08-03 | 2026-11-01 | 2027-05-17 | 2029-03-09 | 2030-03-31 |  |  | 2024-10-16 | 2025-08-03 | 2026-11-01 | 2027-05-17 | 2029-03-09 | 2030-03-31 |  |  | 0 | 3.4929 |  |  | 0 | 0 | 0.032377 | 0.53713 | 1.2663 | 3.2386 | 3.4647 | 3.4929 | 0 | 0 | 0.032377 | 0.53713 | 1.2663 | 3.2386 | 3.4647 | 3.4929 |  | No | Other | AMP8
| TMS | SHIRBURN STW | UBA8.SEW.S41636 | 08TW101402f | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2028-05-19 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 2025-04-01 | 2028-05-19 | 2029-02-09 | 2029-08-25 | 2030-12-14 | 2032-03-31 |  |  | 0 | 3.0859 |  |  | 0 | 0 | 0.16961 | 0.34121 | 0.45857 | 0.72701 | 1.4634 | 3.0859 | 0 | 0 | 0.16961 | 0.34121 | 0.45857 | 0.72701 | 1.4634 | 3.0859 |  | No | Other | AMP8
| TMS | Shrivenham STW - Phosphorus - Actiflo | UBA8.SEW.S41911 | 08TW100933a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-06-03 | 2028-05-08 | 2028-11-20 | 2029-12-10 | 2031-03-31 |  |  | 2024-10-16 | 2027-06-03 | 2028-05-08 | 2028-11-20 | 2029-12-10 | 2031-03-31 |  |  | 0 | 16.5008 |  |  | 0 | 0 | 0 | 0 | 1.0531 | 3.3371 | 9.2985 | 16.5008 | 0 | 0 | 0 | 0 | 1.0531 | 3.3371 | 9.2985 | 16.5008 |  | No | Delivery Mechanism | AMP8
| TMS | Silchester STW Phos Dosing and TT | UBA8.SEW.S38955 | 08TW100934a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-06-29 | 2027-01-10 | 2027-05-28 | 2029-01-07 | 2030-03-31 |  |  | 2024-10-16 | 2026-06-29 | 2027-01-10 | 2027-05-28 | 2029-01-07 | 2030-03-31 |  |  | 0 | 9.5261 |  |  | 0 | 0 | 0 | 0.82155 | 2.3491 | 5.7644 | 9.3982 | 9.5261 | 0 | 0 | 0 | 0.82155 | 2.3491 | 5.7644 | 9.3982 | 9.5261 |  | No | Other | AMP8
| TMS | Slough STW WW Quality AMP7 New Permit | K222 | 08TW100935a | P-removal | PCDWW10 | Retained |  | 2025-03-31 | 2025-03-31 | 2020-11-30 | 2024-02-28 | 2025-05-30 | 2026-04-30 | 2029-05-31 | 2029-06-30 |  | IM2 | 2020-11-30 | 2023-07-30 | 2025-01-28 | 2026-01-28 | 2029-03-01 | 2029-03-31 |  |  | 0 | 23.0678 |  |  |  |  | 3.6302 | 11.5772 | 22.0591 | 32.1961 | 32.5005 | 32.5005 |  |  | 3.2949 | 9.3381 | 16.4265 | 22.8563 | 23.0678 | 23.0678 |  | No | Other | AMP8
| TMS | SO A3 Roehampton Vale CSO | UBA8.SEW.S39096 | 08TW101063a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-03-31 18:20 | 2027-06-27 | 2027-08-22 | 2027-11-21 | 2028-03-31 |  |  | 2024-11-06 | 2027-03-31 18:20 | 2027-06-27 | 2027-08-22 | 2027-11-21 | 2028-03-31 |  |  | 0 | 3.8893 |  |  | 0 | 0 | 0 | 0.097233 | 3.8893 | 3.8893 | 3.8893 | 3.8893 | 0 | 0 | 0 | 0.097233 | 3.8893 | 3.8893 | 3.8893 | 3.8893 |  | No | Other | AMP8
| TMS | SO Abbess Roding STW | UBA8.SEW.S39087 | 08TW101072a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-02-18 20:30 | 2028-08-03 16:45 | 2028-11-22 22:15 | 2029-08-28 | 2030-03-31 |  |  | 2024-10-02 | 2028-02-18 20:30 | 2028-08-03 16:45 | 2028-11-22 22:15 | 2029-08-28 | 2030-03-31 |  |  | 0 | 2.8259 |  |  | 0 | 0 | 0 | 0 | 0.11634 | 2.0501 | 2.8259 | 2.8259 | 0 | 0 | 0 | 0 | 0.11634 | 2.0501 | 2.8259 | 2.8259 |  | No | Other | AMP8
| TMS | SO Abbess Roding STW | UBA8.SEW.S39087 | 08TW101072a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-02-18 20:30 | 2028-08-03 16:45 | 2028-11-22 22:15 | 2029-08-28 | 2030-03-31 |  |  | 2024-10-02 | 2028-02-18 20:30 | 2028-08-03 16:45 | 2028-11-22 22:15 | 2029-08-28 | 2030-03-31 |  |  | 0 | 2.8259 |  |  | 0 | 0 | 0 | 0 | 0.11634 | 2.0501 | 2.8259 | 2.8259 | 0 | 0 | 0 | 0 | 0.11634 | 2.0501 | 2.8259 | 2.8259 |  | No | Other | AMP8
| TMS | SO Alicia Avenue CSO Unpermitted CSO | UBA8.SEW.S39182 | 08TW101099a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2029-03-29 04:16 | 2029-09-14 06:31 | 2029-11-09 06:31 | 2030-03-02 | 2030-03-31 |  |  | 2024-10-02 | 2029-03-29 04:16 | 2029-09-14 06:31 | 2029-11-09 06:31 | 2030-03-02 | 2030-03-31 |  |  | 0 | 3.5069 |  |  | 0 | 0 | 0 | 0 | 0.081922 | 2.2197 | 3.5483 | 3.5069 | 0 | 0 | 0 | 0 | 0.081922 | 2.2197 | 3.5483 | 3.5069 |  | No | Other | AMP8
| TMS | SO Andoversford STW - Option 1 | UBA8.SEW.S39216 | 08TW100978a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2025-12-17 19:14 | 2026-06-15 13:27 | 2026-10-13 09:37 | 2027-08-09 | 2028-03-31 |  |  | 2024-07-31 | 2025-12-17 19:14 | 2026-06-15 13:27 | 2026-10-13 09:37 | 2027-08-09 | 2028-03-31 |  |  | 0 | 4.8219 |  |  | 0 | 0 | 0.24526 | 3.2528 | 4.8219 | 4.8219 | 4.8219 | 4.8219 | 0 | 0 | 0.24526 | 3.2528 | 4.8219 | 4.8219 | 4.8219 | 4.8219 |  | No | Other | AMP8
| TMS | SO Auckland Rd Storm Tk SPS | UBA8.SEW.S39100 | 08TW101059a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2029-03-30 06:36 | 2029-12-05 21:50 | 2030-01-30 21:50 | 2030-07-17 | 2031-03-31 |  |  | 2024-11-20 | 2029-03-30 06:36 | 2029-12-05 21:50 | 2030-01-30 21:50 | 2030-07-17 | 2031-03-31 |  |  | 0 | 3.3625 |  |  | 0 | 0 | 0 | 0 | 0.080915 | 1.7319 | 2.8266 | 3.3625 | 0 | 0 | 0 | 0 | 0.080915 | 1.7319 | 2.8266 | 3.3625 |  | No | Other | AMP8
| TMS | SO Beech Hall Crescent, Walthamstow CSO | UBA8.SEW.S39109 | 08TW101050a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2026-03-18 01:55 | 2027-03-17 01:55 | 2027-07-03 03:20 | 2028-09-24 | 2029-03-31 |  |  | 2024-08-28 | 2026-03-18 01:55 | 2027-03-17 01:55 | 2027-07-03 03:20 | 2028-09-24 | 2029-03-31 |  |  | 0 | 3.8313 |  |  | 0 | 0 | 0.092717 | 1.9365 | 3.0244 | 3.8313 | 3.8313 | 3.8313 | 0 | 0 | 0.092717 | 1.9365 | 3.0244 | 3.8313 | 3.8313 | 3.8313 |  | No | Other | AMP8
| TMS | SO Bentley STW - Option 1 Suds | UBA8.SEW.S39213 | 08TW100981a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2029-03-30 03:39 | 2029-09-10 11:03 | 2029-11-05 11:03 | 2030-02-23 | 2030-03-31 |  |  | 2024-08-28 | 2029-03-30 03:39 | 2029-09-10 11:03 | 2029-11-05 11:03 | 2030-02-23 | 2030-03-31 |  |  | 0 | 6.3116 |  |  | 0 | 0 | 0 | 0 | 0.14424 | 4.106 | 6.3116 | 6.3116 | 0 | 0 | 0 | 0 | 0.14424 | 4.106 | 6.3116 | 6.3116 |  | No | Other | AMP8
| TMS | SO Bentley STW - Option 1 Suds | UBA8.SEW.S39213 | 08TW100981a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2029-03-30 03:39 | 2029-09-10 11:03 | 2029-11-05 11:03 | 2030-02-23 | 2030-03-31 |  |  | 2024-08-28 | 2029-03-30 03:39 | 2029-09-10 11:03 | 2029-11-05 11:03 | 2030-02-23 | 2030-03-31 |  |  | 0 | 3.3985 |  |  | 0 | 0 | 0 | 0 | 0.077669 | 2.2109 | 3.3985 | 3.3985 | 0 | 0 | 0 | 0 | 0.077669 | 2.2109 | 3.3985 | 3.3985 |  | No | Other | AMP8
| TMS | SO Bledington STW - Option 1 | UBA8.SEW.S39212 | 08TW100982a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-03-23 | 2027-03-22 | 2027-12-13 | 2030-12-09 | 2031-03-31 |  |  | 2024-07-31 | 2026-03-23 | 2027-03-22 | 2027-12-13 | 2030-12-09 | 2031-03-31 |  |  | 0 | 3.784 |  |  | 0 | 0 | 0.10641 | 0.78894 | 1.4283 | 2.2897 | 3.1511 | 3.784 | 0 | 0 | 0.10641 | 0.78894 | 1.4283 | 2.2897 | 3.1511 | 3.784 |  | No | Other | AMP8
| TMS | SO Boddington STW - Option 1 | UBA8.SEW.S39199 | 08TW100985a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-12-17 14:25 | 2027-10-07 01:20 | 2028-06-29 01:20 | 2031-03-08 | 2031-03-31 |  |  | 2024-06-26 | 2026-12-17 14:25 | 2027-10-07 01:20 | 2028-06-29 01:20 | 2031-03-08 | 2031-03-31 |  |  | 0 | 5.1276 |  |  | 0 | 0 | 0 | 0.20891 | 1.1948 | 2.923 | 4.0602 | 5.1276 | 0 | 0 | 0 | 0.20891 | 1.1948 | 2.923 | 4.0602 | 5.1276 |  | No | Other | AMP8
| TMS | SO Brickendon STW - Option 1 | UBA8.SEW.S39177 | 08TW100987a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2026-03-31 18:20 | 2026-06-27 | 2026-08-22 | 2026-11-21 | 2027-03-31 |  |  | 2024-07-03 | 2026-03-31 18:20 | 2026-06-27 | 2026-08-22 | 2026-11-21 | 2027-03-31 |  |  | 0 | 1.4112 |  |  | 0 | 0 | 0.40358 | 1.4112 | 1.4112 | 1.4112 | 1.4112 | 1.4112 | 0 | 0 | 0.40358 | 1.4112 | 1.4112 | 1.4112 | 1.4112 | 1.4112 |  | No | Other | AMP8
| TMS | SO Brook Way Chigwell CSO | UBA8.SEW.S39099 | 08TW101060a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-05-20 18:38 | 2027-05-19 18:38 | 2027-08-18 19:40 | 2028-08-31 | 2029-03-31 |  |  | 2024-11-20 | 2026-05-20 18:38 | 2027-05-19 18:38 | 2027-08-18 19:40 | 2028-08-31 | 2029-03-31 |  |  | 0 | 3.5817 |  |  | 0 | 0 | 0.074995 | 1.5218 | 2.8607 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.074995 | 1.5218 | 2.8607 | 3.5817 | 3.5817 | 3.5817 |  | No | Other | AMP8
| TMS | SO Burghfield STW - Option 2 | UBA8.SEW.S39172 | 08TW100988a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 02:33 | 2029-01-19 02:33 | 2029-10-12 02:33 | 2032-09-09 | 2033-03-31 |  |  | 2024-06-26 | 2028-01-21 02:33 | 2029-01-19 02:33 | 2029-10-12 02:33 | 2032-09-09 | 2033-03-31 |  |  | 0 | 23.7955 |  |  | 0 | 0 | 0 | 0 | 1.1225 | 5.7479 | 12.2513 | 23.7955 | 0 | 0 | 0 | 0 | 1.1225 | 5.7479 | 12.2513 | 23.7955 |  | No | Delivery Mechanism | AMP8
| TMS | SO Burghfield STW - Option 2 | UBA8.SEW.S39172 | 08TW100988a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 02:33 | 2029-01-19 02:33 | 2029-10-12 02:33 | 2032-09-09 | 2033-03-31 |  |  | 2024-06-26 | 2028-01-21 02:33 | 2029-01-19 02:33 | 2029-10-12 02:33 | 2032-09-09 | 2033-03-31 |  |  | 0 | 4.1992 |  |  | 0 | 0 | 0 | 0 | 0.1981 | 1.0143 | 2.162 | 4.1992 | 0 | 0 | 0 | 0 | 0.1981 | 1.0143 | 2.162 | 4.1992 |  | No | Delivery Mechanism | AMP8
| TMS | SO Cassington STW - Option 1 | UBA8.SEW.S39194 | 08TW101087a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-10-22 18:53 | 2028-10-20 18:53 | 2029-03-08 16:55 | 2030-02-19 | 2030-03-31 |  |  | 2024-07-03 | 2027-10-22 18:53 | 2028-10-20 18:53 | 2029-03-08 16:55 | 2030-02-19 | 2030-03-31 |  |  | 0 | 16.2702 |  |  | 0 | 0 | 0 | 0 | 1.0045 | 9.376 | 16.2702 | 16.2702 | 0 | 0 | 0 | 0 | 1.0045 | 9.376 | 16.2702 | 16.2702 |  | No | Other | AMP8
| TMS | SO Cassington STW - Option 1 | UBA8.SEW.S39194 | 08TW101087a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-10-22 18:53 | 2028-10-20 18:53 | 2029-03-08 16:55 | 2030-02-19 | 2030-03-31 |  |  | 2024-07-03 | 2027-10-22 18:53 | 2028-10-20 18:53 | 2029-03-08 16:55 | 2030-02-19 | 2030-03-31 |  |  | 0 | 11.7819 |  |  | 0 | 0 | 0 | 0 | 0.72743 | 6.7895 | 11.7819 | 11.7819 | 0 | 0 | 0 | 0 | 0.72743 | 6.7895 | 11.7819 | 11.7819 |  | No | Other | AMP8
| TMS | SO Chadlington STW - Option 1 | UBA8.SEW.S39171 | 08TW100989a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2028-01-21 07:16 | 2028-07-10 05:05 | 2028-11-01 03:38 | 2029-08-13 | 2030-03-31 |  |  | 2024-08-28 | 2028-01-21 07:16 | 2028-07-10 05:05 | 2028-11-01 03:38 | 2029-08-13 | 2030-03-31 |  |  | 0 | 4.9618 |  |  | 0 | 0 | 0 | 0 | 0.26409 | 3.8854 | 4.9618 | 4.9618 | 0 | 0 | 0 | 0 | 0.26409 | 3.8854 | 4.9618 | 4.9618 |  | No | Other | AMP8
| TMS | SO Charlton-On-Otmoor STW - Option 2 | UBA8.SEW.S39168 | 08TW100992a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2026-01-21 23:11 | 2026-08-24 11:25 | 2027-01-14 11:35 | 2028-01-07 | 2028-03-31 |  |  | 2024-08-28 | 2026-01-21 23:11 | 2026-08-24 11:25 | 2027-01-14 11:35 | 2028-01-07 | 2028-03-31 |  |  | 0 | 8.5103 |  |  | 0 | 0 | 0.41133 | 4.778 | 8.5103 | 8.5103 | 8.5103 | 8.5103 | 0 | 0 | 0.41133 | 4.778 | 8.5103 | 8.5103 | 8.5103 | 8.5103 |  | No | Other | AMP8
| TMS | SO Charlton-On-Otmoor STW - Option 2 | UBA8.SEW.S39168 | 08TW100992a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2026-01-21 23:11 | 2026-08-24 11:25 | 2027-01-14 11:35 | 2028-01-07 | 2028-03-31 |  |  | 2024-08-28 | 2026-01-21 23:11 | 2026-08-24 11:25 | 2027-01-14 11:35 | 2028-01-07 | 2028-03-31 |  |  | 0 | 4.0048 |  |  | 0 | 0 | 0.19357 | 2.2485 | 4.0048 | 4.0048 | 4.0048 | 4.0048 | 0 | 0 | 0.19357 | 2.2485 | 4.0048 | 4.0048 | 4.0048 | 4.0048 |  | No | Other | AMP8
| TMS | SO Cobham Bridge, Adj Cobham PS CSO | UBA8.SEW.S39200 | 08TW101082a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2026-09-17 01:10 | 2027-04-30 12:09 | 2027-06-25 20:54 | 2028-02-15 | 2028-03-31 |  |  | 2024-10-23 | 2026-09-17 01:10 | 2027-04-30 12:09 | 2027-06-25 20:54 | 2028-02-15 | 2028-03-31 |  |  | 0 | 3.4142 |  |  | 0 | 0 | 0.06263 | 0.80033 | 3.4142 | 3.4142 | 3.4142 | 3.4142 | 0 | 0 | 0.06263 | 0.80033 | 3.4142 | 3.4142 | 3.4142 | 3.4142 |  | No | Other | AMP8
| TMS | SO Compton (Berks) STW - Option 1 | UBA8.SEW.S39162 | 08TW100998a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-11-20 | 2027-11-19 | 2028-08-11 | 2031-08-08 | 2032-03-31 |  |  | 2024-07-10 | 2026-11-20 | 2027-11-19 | 2028-08-11 | 2031-08-08 | 2032-03-31 |  |  | 0 | 4.3059 |  |  | 0 | 0 | 0 | 0.24855 | 0.89553 | 2.112 | 3.0975 | 4.3059 | 0 | 0 | 0 | 0.24855 | 0.89553 | 2.112 | 3.0975 | 4.3059 |  | No | Delivery Mechanism | AMP8
| TMS | SO Compton (Berks) STW - Option 1 | UBA8.SEW.S39162 | 08TW100998a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-11-20 | 2027-11-19 | 2028-08-11 | 2031-08-08 | 2032-03-31 |  |  | 2024-07-10 | 2026-11-20 | 2027-11-19 | 2028-08-11 | 2031-08-08 | 2032-03-31 |  |  | 0 | 8.7423 |  |  | 0 | 0 | 0 | 0.50463 | 1.8182 | 4.288 | 6.2889 | 8.7423 | 0 | 0 | 0 | 0.50463 | 1.8182 | 4.288 | 6.2889 | 8.7423 |  | No | Delivery Mechanism | AMP8
| TMS | SO Crofton Rd Sunnydale CSO | UBA8.SEW.S39093 | 08TW101066a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-02-18 00:53 | 2027-02-17 00:53 | 2027-06-24 02:52 | 2028-12-03 | 2029-03-31 |  |  | 2024-11-20 | 2026-02-18 00:53 | 2027-02-17 00:53 | 2027-06-24 02:52 | 2028-12-03 | 2029-03-31 |  |  | 0 | 3.5817 |  |  | 0 | 0 | 0.1112 | 0.86274 | 2.3139 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.1112 | 0.86274 | 2.3139 | 3.5817 | 3.5817 | 3.5817 |  | No | Other | AMP8
| TMS | SO Crondall STW - Option 1 | UBA8.SEW.S39160 | 08TW101000a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2026-08-19 21:45 | 2027-04-30 03:13 | 2027-10-15 22:52 | 2028-12-11 | 2029-03-31 |  |  | 2024-10-23 | 2026-08-19 21:45 | 2027-04-30 03:13 | 2027-10-15 22:52 | 2028-12-11 | 2029-03-31 |  |  | 0 | 4.0069 |  |  | 0 | 0 | 0.072958 | 0.7644 | 2.6465 | 4.0069 | 4.0069 | 4.0069 | 0 | 0 | 0.072958 | 0.7644 | 2.6465 | 4.0069 | 4.0069 | 4.0069 |  | No | Other | AMP8
| TMS | SO Crondall STW - Option 1 | UBA8.SEW.S39160 | 08TW101000a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2026-08-19 21:45 | 2027-04-30 03:13 | 2027-10-15 22:52 | 2028-12-11 | 2029-03-31 |  |  | 2024-10-23 | 2026-08-19 21:45 | 2027-04-30 03:13 | 2027-10-15 22:52 | 2028-12-11 | 2029-03-31 |  |  | 0 | 5.3115 |  |  | 0 | 0 | 0.096712 | 1.0133 | 3.5081 | 5.3115 | 5.3115 | 5.3115 | 0 | 0 | 0.096712 | 1.0133 | 3.5081 | 5.3115 | 5.3115 | 5.3115 |  | No | Other | AMP8
| TMS | SO Cropredy STW - Option 1 | UBA8.SEW.S39203 | 08TW101079a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2028-01-21 02:07 | 2028-10-02 08:41 | 2029-03-21 13:03 | 2030-05-21 | 2031-03-31 |  |  | 2024-07-31 | 2028-01-21 02:07 | 2028-10-02 08:41 | 2029-03-21 13:03 | 2030-05-21 | 2031-03-31 |  |  | 0 | 4.0878 |  |  | 0 | 0 | 0 | 0 | 0.15256 | 1.3796 | 3.7636 | 4.0878 | 0 | 0 | 0 | 0 | 0.15256 | 1.3796 | 3.7636 | 4.0878 |  | No | Other | AMP8
| TMS | SO Cuddington STW - Option 1 | UBA8.SEW.S39159 | 08TW101001a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2028-02-18 04:57 | 2028-10-11 13:04 | 2029-03-18 02:28 | 2030-04-16 | 2030-03-31 |  |  | 2024-07-10 | 2028-02-18 04:57 | 2028-10-11 13:04 | 2029-03-18 02:28 | 2030-04-16 | 2030-03-31 |  |  | 0 | 4.2731 |  |  | 0 | 0 | 0 | 0 | 0.15331 | 1.9631 | 4.1641 | 4.2731 | 0 | 0 | 0 | 0 | 0.15331 | 1.9631 | 4.1641 | 4.2731 |  | No | Other | AMP8
| TMS | SO Daintry Close CSO | UBA8.SEW.S39088 | 08TW101071a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2027-03-31 04:16 | 2027-09-16 06:31 | 2027-11-11 06:31 | 2028-03-03 | 2028-03-31 |  |  | 2024-11-20 | 2027-03-31 04:16 | 2027-09-16 06:31 | 2027-11-11 06:31 | 2028-03-03 | 2028-03-31 |  |  | 0 | 3.5729 |  |  | 0 | 0 | 0.10941 | 2.3956 | 3.615 | 3.5729 | 3.5729 | 3.5729 | 0 | 0 | 0.10941 | 2.3956 | 3.615 | 3.5729 | 3.5729 | 3.5729 |  | No | Other | AMP8
| TMS | SO East Garston SPS - Option 1 | UBA8.SEW.S39201 | 08TW101081a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2025-12-17 20:14 | 2026-10-30 17:04 | 2027-01-17 22:16 | 2027-10-10 | 2028-03-31 |  |  | 2024-10-23 | 2025-12-17 20:14 | 2026-10-30 17:04 | 2027-01-17 22:16 | 2027-10-10 | 2028-03-31 |  |  | 0 | 3.7174 |  |  | 0 | 0 | 0.31101 | 1.7435 | 3.7174 | 3.7174 | 3.7174 | 3.7174 | 0 | 0 | 0.31101 | 1.7435 | 3.7174 | 3.7174 | 3.7174 | 3.7174 |  | No | Other | AMP8
| TMS | SO East Grafton STW - Option 1 | UBA8.SEW.S39155 | 08TW101005a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-03-17 06:20 | 2028-07-20 14:02 | 2028-10-12 03:10 | 2029-05-09 | 2030-03-31 |  |  | 2024-10-23 | 2028-03-17 06:20 | 2028-07-20 14:02 | 2028-10-12 03:10 | 2029-05-09 | 2030-03-31 |  |  | 0 | 1.0735 |  |  | 0 | 0 | 0 | 0 | 0.027663 | 0.91562 | 1.0735 | 1.0735 | 0 | 0 | 0 | 0 | 0.027663 | 0.91562 | 1.0735 | 1.0735 |  | No | Other | AMP8
| TMS | SO East Shefford STW - Option 2 | UBA8.SEW.S39154 | 08TW101006a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  |  | 2024-10-23 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  |  | 0 | 13.7669 |  |  | 0 | 0 | 0 | 0 | 0.4556 | 1.6859 | 3.7493 | 13.7669 | 0 | 0 | 0 | 0 | 0.4556 | 1.6859 | 3.7493 | 13.7669 |  | No | Delivery Mechanism | AMP8
| TMS | SO East Shefford STW - Option 2 | UBA8.SEW.S39154 | 08TW101006a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  |  | 2024-10-23 | 2028-01-22 | 2029-01-20 | 2029-10-13 | 2032-10-09 | 2033-03-31 |  |  | 0 | 3.2293 |  |  | 0 | 0 | 0 | 0 | 0.10687 | 0.39545 | 0.87948 | 3.2293 | 0 | 0 | 0 | 0 | 0.10687 | 0.39545 | 0.87948 | 3.2293 |  | No | Delivery Mechanism | AMP8
| TMS | SO Fyfield (Wilts) STW - Option 1 | UBA8.SEW.S39152 | 08TW101008a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-08-21 | 2028-08-19 | 2029-05-12 | 2032-05-08 | 2033-03-31 |  |  | 2024-10-23 | 2027-08-21 | 2028-08-19 | 2029-05-12 | 2032-05-08 | 2033-03-31 |  |  | 0 | 4.0229 |  |  | 0 | 0 | 0 | 0 | 0.2154 | 0.61331 | 1.704 | 4.0229 | 0 | 0 | 0 | 0 | 0.2154 | 0.61331 | 1.704 | 4.0229 |  | No | Delivery Mechanism | AMP8
| TMS | SO Fyfield (Wilts) STW - Option 1 | UBA8.SEW.S39152 | 08TW101008a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-08-21 | 2028-08-19 | 2029-05-12 | 2032-05-08 | 2033-03-31 |  |  | 2024-10-23 | 2027-08-21 | 2028-08-19 | 2029-05-12 | 2032-05-08 | 2033-03-31 |  |  | 0 | 11.4498 |  |  | 0 | 0 | 0 | 0 | 0.61305 | 1.7456 | 4.8497 | 11.4498 | 0 | 0 | 0 | 0 | 0.61305 | 1.7456 | 4.8497 | 11.4498 |  | No | Delivery Mechanism | AMP8
| TMS | SO Gerrards Cross STW - Option 1 | UBA8.SEW.S39151 | 08TW101009a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2025-10-23 | 2026-10-22 | 2027-07-15 | 2030-07-11 | 2031-03-31 |  |  | 2024-07-10 | 2025-10-23 | 2026-10-22 | 2027-07-15 | 2030-07-11 | 2031-03-31 |  |  | 0 | 11.2893 |  |  | 0 | 0 | 0.75845 | 4.0602 | 6.4451 | 8.5358 | 10.6266 | 11.2893 | 0 | 0 | 0.75845 | 4.0602 | 6.4451 | 8.5358 | 10.6266 | 11.2893 |  | No | Other | AMP8
| TMS | SO Gerrards Cross STW - Option 1 | UBA8.SEW.S39151 | 08TW101009a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2025-10-23 | 2026-10-22 | 2027-07-15 | 2030-07-11 | 2031-03-31 |  |  | 2024-07-10 | 2025-10-23 | 2026-10-22 | 2027-07-15 | 2030-07-11 | 2031-03-31 |  |  | 0 | 14.3682 |  |  | 0 | 0 | 0.9653 | 5.1675 | 8.2029 | 10.8638 | 13.5248 | 14.3682 | 0 | 0 | 0.9653 | 5.1675 | 8.2029 | 10.8638 | 13.5248 | 14.3682 |  | No | Other | AMP8
| TMS | SO Hadham Mill SPS - Option 1 | UBA8.SEW.S39190 | 08TW101091a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-05-20 | 2028-07-15 | 2028-09-09 | 2028-12-09 | 2029-03-31 |  |  | 2024-11-06 | 2028-05-20 | 2028-07-15 | 2028-09-09 | 2028-12-09 | 2029-03-31 |  |  | 0 | 3.3072 |  |  | 0 | 0 | 0 | 0 | 0.075927 | 3.3072 | 3.3072 | 3.3072 | 0 | 0 | 0 | 0 | 0.075927 | 3.3072 | 3.3072 | 3.3072 |  | No | Other | AMP8
| TMS | SO Hampstead Norreys STW - Option 2 | UBA8.SEW.S39148 | 08TW101012a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-01-21 12:41 | 2027-01-20 12:41 | 2027-09-12 19:21 | 2029-04-23 | 2029-03-31 |  |  | 2024-07-10 | 2026-01-21 12:41 | 2027-01-20 12:41 | 2027-09-12 19:21 | 2029-04-23 | 2029-03-31 |  |  | 0 | 9.5598 |  |  | 0 | 0 | 0.36579 | 3.3929 | 6.6018 | 9.2733 | 9.5598 | 9.5598 | 0 | 0 | 0.36579 | 3.3929 | 6.6018 | 9.2733 | 9.5598 | 9.5598 |  | No | Other | AMP8
| TMS | SO Hampstead Norreys STW - Option 2 | UBA8.SEW.S39148 | 08TW101012a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2026-01-21 12:41 | 2027-01-20 12:41 | 2027-09-12 19:21 | 2029-04-23 | 2029-03-31 |  |  | 2024-07-10 | 2026-01-21 12:41 | 2027-01-20 12:41 | 2027-09-12 19:21 | 2029-04-23 | 2029-03-31 |  |  | 0 | 3.1866 |  |  | 0 | 0 | 0.12193 | 1.131 | 2.2006 | 3.0911 | 3.1866 | 3.1866 | 0 | 0 | 0.12193 | 1.131 | 2.2006 | 3.0911 | 3.1866 | 3.1866 |  | No | Other | AMP8
| TMS | SO Hamstead Marshall STW - Option 1 | UBA8.SEW.S39147 | 08TW101013a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2027-12-16 18:19 | 2028-02-29 11:27 | 2028-04-25 11:27 | 2028-08-28 | 2029-03-31 |  |  | 2024-07-31 | 2027-12-16 18:19 | 2028-02-29 11:27 | 2028-04-25 11:27 | 2028-08-28 | 2029-03-31 |  |  | 0 | 1.4685 |  |  | 0 | 0 | 0 | 0.025401 | 0.51087 | 1.4685 | 1.4685 | 1.4685 | 0 | 0 | 0 | 0.025401 | 0.51087 | 1.4685 | 1.4685 | 1.4685 |  | No | Other | AMP8
| TMS | SO High Road, Woodford CSO | UBA8.SEW.S39101 | 08TW101058a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-05-20 16:38 | 2028-05-18 16:38 | 2028-08-27 06:15 | 2029-10-19 | 2030-03-31 |  |  | 2024-10-23 | 2027-05-20 16:38 | 2028-05-18 16:38 | 2028-08-27 06:15 | 2029-10-19 | 2030-03-31 |  |  | 0 | 3.6323 |  |  | 0 | 0 | 0 | 0.076195 | 1.5268 | 2.8349 | 3.6323 | 3.6323 | 0 | 0 | 0 | 0.076195 | 1.5268 | 2.8349 | 3.6323 | 3.6323 |  | No | Other | AMP8
| TMS | SO Holybourne SPS - Option 1 | UBA8.SEW.S39209 | 08TW101073a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-03-30 03:40 | 2028-06-17 | 2028-08-12 | 2028-11-11 | 2029-03-31 |  |  | 2024-10-02 | 2028-03-30 03:40 | 2028-06-17 | 2028-08-12 | 2028-11-11 | 2029-03-31 |  |  | 0 | 3.5697 |  |  | 0 | 0 | 0 | 0 | 0.088604 | 3.5697 | 3.5697 | 3.5697 | 0 | 0 | 0 | 0 | 0.088604 | 3.5697 | 3.5697 | 3.5697 |  | No | Other | AMP8
| TMS | SO Honeypot Lane CSO | UBA8.SEW.S39090 | 08TW101069a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-03-31 03:40 | 2026-05-29 | 2026-07-24 | 2026-10-23 | 2027-03-31 |  |  | 2024-11-20 | 2026-03-31 03:40 | 2026-05-29 | 2026-07-24 | 2026-10-23 | 2027-03-31 |  |  | 0 | 3.7137 |  |  | 0 | 0 | 0.095472 | 3.7137 | 3.7137 | 3.7137 | 3.7137 | 3.7137 | 0 | 0 | 0.095472 | 3.7137 | 3.7137 | 3.7137 | 3.7137 | 3.7137 |  | No | Other | AMP8
| TMS | SO Horton-Cum-Studley STW - Option 1 | UBA8.SEW.S39141 | 08TW101019a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2027-01-21 23:39 | 2027-06-03 14:09 | 2027-08-30 23:50 | 2028-04-08 | 2028-03-31 |  |  | 2024-07-10 | 2027-01-21 23:39 | 2027-06-03 14:09 | 2027-08-30 23:50 | 2028-04-08 | 2028-03-31 |  |  | 0 | 3.2898 |  |  | 0 | 0 | 0 | 0.21088 | 3.2388 | 3.2898 | 3.2898 | 3.2898 | 0 | 0 | 0 | 0.21088 | 3.2388 | 3.2898 | 3.2898 | 3.2898 |  | No | Other | AMP8
| TMS | SO Hungerford STW - Option 1 | UBA8.SEW.S39140 | 08TW101020a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-17 12:12 | 2028-09-15 12:12 | 2029-06-08 12:12 | 2032-03-08 | 2032-03-31 |  |  | 2024-11-06 | 2027-09-17 12:12 | 2028-09-15 12:12 | 2029-06-08 12:12 | 2032-03-08 | 2032-03-31 |  |  | 0 | 1.9384 |  |  | 0 | 0 | 0 | 0.033326 | 0.27355 | 0.43567 | 0.86376 | 1.9384 | 0 | 0 | 0 | 0.033326 | 0.27355 | 0.43567 | 0.86376 | 1.9384 |  | No | Delivery Mechanism | AMP8
| TMS | SO Little Hallingbury STW - Option 1 | UBA8.SEW.S39135 | 08TW101024a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-12-16 07:13 | 2027-09-23 07:27 | 2028-03-28 15:37 | 2029-07-10 | 2030-03-31 |  |  | 2024-06-26 | 2026-12-16 07:13 | 2027-09-23 07:27 | 2028-03-28 15:37 | 2029-07-10 | 2030-03-31 |  |  | 0 | 6.5574 |  |  | 0 | 0 | 0.11296 | 2.0526 | 3.4955 | 5.875 | 6.5574 | 6.5574 | 0 | 0 | 0.11296 | 2.0526 | 3.4955 | 5.875 | 6.5574 | 6.5574 |  | No | Other | AMP8
| TMS | SO Longbridge Road CSO - Option 1 | UBA8.SEW.S39102 | 08TW101057a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2026-03-18 10:37 | 2027-03-17 10:37 | 2027-06-25 11:25 | 2028-08-14 | 2029-03-31 |  |  | 2024-11-20 | 2026-03-18 10:37 | 2027-03-17 10:37 | 2027-06-25 11:25 | 2028-08-14 | 2029-03-31 |  |  | 0 | 3.5817 |  |  | 0 | 0 | 0.086482 | 1.8292 | 2.9369 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.086482 | 1.8292 | 2.9369 | 3.5817 | 3.5817 | 3.5817 |  | No | Other | AMP8
| TMS | SO Markyate STW - Option 1 | UBA8.SEW.S39134 | 08TW101025a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-17 | 2026-07-22 07:31 | 2027-07-21 07:31 | 2028-04-12 07:31 | 2030-11-11 | 2031-03-31 |  |  | 2024-07-17 | 2026-07-22 07:31 | 2027-07-21 07:31 | 2028-04-12 07:31 | 2030-11-11 | 2031-03-31 |  |  | 0 | 14.3424 |  |  | 0 | 0 | 0.60043 | 1.8879 | 5.4113 | 9.0256 | 12.7772 | 14.3424 | 0 | 0 | 0.60043 | 1.8879 | 5.4113 | 9.0256 | 12.7772 | 14.3424 |  | No | Other | AMP8
| TMS | SO Mulberry Court, Hall Road CSO | UBA8.SEW.S39103 | 08TW101056a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 05:24 | 2027-12-06 21:21 | 2028-01-31 21:21 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 05:24 | 2027-12-06 21:21 | 2028-01-31 21:21 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.8734 |  |  | 0 | 0 | 0.093244 | 2.0623 | 3.4252 | 3.8734 | 3.8734 | 3.8734 | 0 | 0 | 0.093244 | 2.0623 | 3.4252 | 3.8734 | 3.8734 | 3.8734 |  | No | Other | AMP8
| TMS | SO Newmans Lane SPS - Option 1 | UBA8.SEW.S39218 | 08TW100976a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2026-03-31 18:20 | 2026-06-27 | 2026-08-22 | 2026-11-21 | 2027-03-31 |  |  | 2024-11-06 | 2026-03-31 18:20 | 2026-06-27 | 2026-08-22 | 2026-11-21 | 2027-03-31 |  |  | 0 | 1.6949 |  |  | 0 | 0 | 0.041273 | 1.6949 | 1.6949 | 1.6949 | 1.6949 | 1.6949 | 0 | 0 | 0.041273 | 1.6949 | 1.6949 | 1.6949 | 1.6949 | 1.6949 |  | No | Other | AMP8
| TMS | SO Prospect Rd Woodford Monkhams Ln CSO | UBA8.SEW.S39106 | 08TW101053a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2027-03-31 01:27 | 2027-12-06 19:47 | 2028-01-31 19:47 | 2028-07-17 | 2029-03-31 |  |  | 2024-11-20 | 2027-03-31 01:27 | 2027-12-06 19:47 | 2028-01-31 19:47 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.5817 |  |  | 0 | 0 | 0.086258 | 1.8509 | 3.0005 | 3.5817 | 3.5817 | 3.5817 | 0 | 0 | 0.086258 | 1.8509 | 3.0005 | 3.5817 | 3.5817 | 3.5817 |  | No | Other | AMP8
| TMS | SO Ray Lodge Road (Ray Park 1) CSO | UBA8.SEW.S39107 | 08TW101052a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 01:50 | 2028-09-14 01:50 | 2028-12-16 18:41 | 2030-01-10 | 2030-03-31 |  |  | 2024-11-06 | 2027-09-16 01:50 | 2028-09-14 01:50 | 2028-12-16 18:41 | 2030-01-10 | 2030-03-31 |  |  | 0 | 3.692 |  |  | 0 | 0 | 0 | 0.062866 | 0.77365 | 2.6378 | 3.692 | 3.692 | 0 | 0 | 0 | 0.062866 | 0.77365 | 2.6378 | 3.692 | 3.692 |  | No | Other | AMP8
| TMS | SO Redbridge Ln West Wanstead CSO | UBA8.SEW.S39098 | 08TW101061a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2026-05-20 13:51 | 2027-05-19 13:51 | 2027-09-01 05:48 | 2028-11-09 | 2029-03-31 |  |  | 2024-10-02 | 2026-05-20 13:51 | 2027-05-19 13:51 | 2027-09-01 05:48 | 2028-11-09 | 2029-03-31 |  |  | 0 | 3.5181 |  |  | 0 | 0 | 0.073855 | 1.4722 | 2.6663 | 3.5181 | 3.5181 | 3.5181 | 0 | 0 | 0.073855 | 1.4722 | 2.6663 | 3.5181 | 3.5181 | 3.5181 |  | No | Other | AMP8
| TMS | SO Selborne STW - Option 1 | UBA8.SEW.S39192 | 08TW101089a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2026-06-24 02:51 | 2026-12-05 11:36 | 2027-03-25 01:26 | 2027-12-24 | 2028-03-31 |  |  | 2024-06-19 | 2026-06-24 02:51 | 2026-12-05 11:36 | 2027-03-25 01:26 | 2027-12-24 | 2028-03-31 |  |  | 0 | 2.4661 |  |  | 0 | 0 | 0.049954 | 0.71292 | 2.4661 | 2.4661 | 2.4661 | 2.4661 | 0 | 0 | 0.049954 | 0.71292 | 2.4661 | 2.4661 | 2.4661 | 2.4661 |  | No | Other | AMP8
| TMS | SO Sevenhampton Village STW - Option 1 | UBA8.SEW.S39191 | 08TW101090a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2026-03-18 14:10 | 2026-11-25 13:01 | 2027-01-27 12:43 | 2027-07-04 | 2028-03-31 |  |  | 2024-10-02 | 2026-03-18 14:10 | 2026-11-25 13:01 | 2027-01-27 12:43 | 2027-07-04 | 2028-03-31 |  |  | 0 | 3.55 |  |  | 0 | 0 | 0.11367 | 2.562 | 3.55 | 3.55 | 3.55 | 3.55 | 0 | 0 | 0.11367 | 2.562 | 3.55 | 3.55 | 3.55 | 3.55 |  | No | Other | AMP8
| TMS | SO South Park, Ilford CSO - Option 1 | UBA8.SEW.S39108 | 08TW101051a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 05:25 | 2028-09-14 05:25 | 2028-12-20 04:44 | 2030-01-27 | 2030-03-31 |  |  | 2024-11-06 | 2027-09-16 05:25 | 2028-09-14 05:25 | 2028-12-20 04:44 | 2030-01-27 | 2030-03-31 |  |  | 0 | 3.891 |  |  | 0 | 0 | 0 | 0.066255 | 0.81627 | 2.7599 | 3.891 | 3.891 | 0 | 0 | 0 | 0.066255 | 0.81627 | 2.7599 | 3.891 | 3.891 |  | No | Other | AMP8
| TMS | SO Stewkley STW - Option 1 | UBA8.SEW.S39124 | 08TW101035a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 22:54 | 2028-11-04 23:14 | 2029-05-15 23:27 | 2030-09-08 | 2031-03-31 |  |  | 2024-06-26 | 2028-01-21 22:54 | 2028-11-04 23:14 | 2029-05-15 23:27 | 2030-09-08 | 2031-03-31 |  |  | 0 | 5.0252 |  |  | 0 | 0 | 0 | 0 | 0.19351 | 1.4774 | 3.752 | 5.0252 | 0 | 0 | 0 | 0 | 0.19351 | 1.4774 | 3.752 | 5.0252 |  | No | Other | AMP8
| TMS | SO Therfield STW - Option 1 | UBA8.SEW.S39121 | 08TW101038a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-01-21 00:41 | 2026-10-09 08:19 | 2026-12-13 16:14 | 2027-05-26 | 2028-03-31 |  |  | 2024-06-26 | 2026-01-21 00:41 | 2026-10-09 08:19 | 2026-12-13 16:14 | 2027-05-26 | 2028-03-31 |  |  | 0 | 6.9279 |  |  | 0 | 0 | 0.41036 | 5.5552 | 6.9279 | 6.9279 | 6.9279 | 6.9279 | 0 | 0 | 0.41036 | 5.5552 | 6.9279 | 6.9279 | 6.9279 | 6.9279 |  | No | Other | AMP8
| TMS | SO Thornwood STW - Option 1 | UBA8.SEW.S39119 | 08TW101040a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2028-03-30 18:20 | 2028-06-26 | 2028-08-21 | 2028-11-20 | 2029-03-31 |  |  | 2024-07-03 | 2028-03-30 18:20 | 2028-06-26 | 2028-08-21 | 2028-11-20 | 2029-03-31 |  |  | 0 | 4.2377 |  |  | 0 | 0 | 0 | 0 | 0.2924 | 4.2377 | 4.2377 | 4.2377 | 0 | 0 | 0 | 0 | 0.2924 | 4.2377 | 4.2377 | 4.2377 |  | No | Other | AMP8
| TMS | SO Wardington SPS - Option 1 | UBA8.SEW.S39205 | 08TW101077a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-03-17 17:07 | 2029-02-04 19:58 | 2029-04-26 20:41 | 2030-01-23 | 2030-03-31 |  |  | 2024-11-20 | 2028-03-17 17:07 | 2029-02-04 19:58 | 2029-04-26 20:41 | 2030-01-23 | 2030-03-31 |  |  | 0 | 3.7172 |  |  | 0 | 0 | 0 | 0 | 0.096152 | 1.3969 | 3.7172 | 3.7172 | 0 | 0 | 0 | 0 | 0.096152 | 1.3969 | 3.7172 | 3.7172 |  | No | Other | AMP8
| TMS | SO Wealdbridge, North Weald SPS | UBA8.SEW.S39195 | 08TW101086a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-02-18 13:47 | 2028-10-01 00:46 | 2028-11-26 09:30 | 2029-06-03 | 2030-03-31 |  |  | 2024-11-06 | 2028-02-18 13:47 | 2028-10-01 00:46 | 2028-11-26 09:30 | 2029-06-03 | 2030-03-31 |  |  | 0 | 3.3007 |  |  | 0 | 0 | 0 | 0 | 0.17139 | 2.6258 | 3.3007 | 3.3007 | 0 | 0 | 0 | 0 | 0.17139 | 2.6258 | 3.3007 | 3.3007 |  | No | Other | AMP8
| TMS | SO Wheatley STW - Option 1 | UBA8.SEW.S39114 | 08TW101045a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-01-03 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  |  | 2025-01-03 | 2028-02-19 | 2029-02-17 | 2029-11-10 | 2032-11-06 | 2033-03-31 |  |  | 0 | 11.5003 |  |  | 0 | 0 | 0 | 0 | 0.36514 | 1.4918 | 3.0773 | 11.5003 | 0 | 0 | 0 | 0 | 0.36514 | 1.4918 | 3.0773 | 11.5003 |  | No | Delivery Mechanism | AMP8
| TMS | SO Whitwell STW - Option 1 | UBA8.SEW.S39113 | 08TW101046a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2027-09-16 12:00 | 2028-04-19 22:48 | 2028-09-11 06:00 | 2029-09-07 | 2030-03-31 |  |  | 2024-07-10 | 2027-09-16 12:00 | 2028-04-19 22:48 | 2028-09-11 06:00 | 2029-09-07 | 2030-03-31 |  |  | 0 | 4.1654 |  |  | 0 | 0 | 0 | 0.07894 | 1.2654 | 3.4796 | 4.1654 | 4.1654 | 0 | 0 | 0 | 0.07894 | 1.2654 | 3.4796 | 4.1654 | 4.1654 |  | No | Other | AMP8
| TMS | SO Widford And Wareside STW - Option 1 | UBA8.SEW.S39112 | 08TW101047a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-02-18 09:29 | 2028-09-03 06:38 | 2029-01-13 04:45 | 2029-12-09 | 2030-03-31 |  |  | 2024-11-06 | 2028-02-18 09:29 | 2028-09-03 06:38 | 2029-01-13 04:45 | 2029-12-09 | 2030-03-31 |  |  | 0 | 3.3261 |  |  | 0 | 0 | 0 | 0 | 0.11839 | 1.3339 | 3.3261 | 3.3261 | 0 | 0 | 0 | 0 | 0.11839 | 1.3339 | 3.3261 | 3.3261 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 1 CSO | UBA8.SEW.S39181 | 08TW101100a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:07 | 2027-12-06 21:39 | 2028-01-31 21:39 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 06:07 | 2027-12-06 21:39 | 2028-01-31 21:39 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.6618 |  |  | 0 | 0 | 0.1583 | 1.9918 | 3.2285 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.1583 | 1.9918 | 3.2285 | 3.6618 | 3.6618 | 3.6618 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 2 CSO | UBA8.SEW.S39180 | 08TW101101a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 04:11 | 2027-12-06 20:53 | 2028-01-31 20:53 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 04:11 | 2027-12-06 20:53 | 2028-01-31 20:53 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.6618 |  |  | 0 | 0 | 0.15831 | 1.9909 | 3.2262 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.15831 | 1.9909 | 3.2262 | 3.6618 | 3.6618 | 3.6618 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 3 CSO | UBA8.SEW.S39179 | 08TW101102a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:22 | 2027-12-06 21:45 | 2028-01-31 21:45 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 06:22 | 2027-12-06 21:45 | 2028-01-31 21:45 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.6618 |  |  | 0 | 0 | 0.1583 | 1.9918 | 3.2285 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.1583 | 1.9918 | 3.2285 | 3.6618 | 3.6618 | 3.6618 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 4 CSO | UBA8.SEW.S39178 | 08TW101103a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 00:19 | 2027-12-06 19:20 | 2028-01-31 19:20 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 00:19 | 2027-12-06 19:20 | 2028-01-31 19:20 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.6618 |  |  | 0 | 0 | 0.15851 | 1.9845 | 3.2102 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.15851 | 1.9845 | 3.2102 | 3.6618 | 3.6618 | 3.6618 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 5 CSO | UBA8.SEW.S39176 | 08TW101104a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 00:19 | 2027-12-06 19:20 | 2028-01-31 19:20 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 00:19 | 2027-12-06 19:20 | 2028-01-31 19:20 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.6618 |  |  | 0 | 0 | 0.15851 | 1.9845 | 3.2102 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.15851 | 1.9845 | 3.2102 | 3.6618 | 3.6618 | 3.6618 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 6 CSO | UBA8.SEW.S39175 | 08TW101105a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:27 | 2027-12-06 21:47 | 2028-01-31 21:47 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 06:27 | 2027-12-06 21:47 | 2028-01-31 21:47 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.6618 |  |  | 0 | 0 | 0.1583 | 1.9917 | 3.2282 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.1583 | 1.9917 | 3.2282 | 3.6618 | 3.6618 | 3.6618 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 7 CSO | UBA8.SEW.S39174 | 08TW101106a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 05:43 | 2027-12-06 21:29 | 2028-01-31 21:29 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 05:43 | 2027-12-06 21:29 | 2028-01-31 21:29 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.6618 |  |  | 0 | 0 | 0.15833 | 1.9888 | 3.2214 | 3.6618 | 3.6618 | 3.6618 | 0 | 0 | 0.15833 | 1.9888 | 3.2214 | 3.6618 | 3.6618 | 3.6618 |  | No | Other | AMP8
| TMS | SO Winn Valley SPS LB Redbridge 8 CSO | UBA8.SEW.S39173 | 08TW101107a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2027-03-31 06:27 | 2027-12-06 21:47 | 2028-01-31 21:47 | 2028-07-17 | 2029-03-31 |  |  | 2024-10-02 | 2027-03-31 06:27 | 2027-12-06 21:47 | 2028-01-31 21:47 | 2028-07-17 | 2029-03-31 |  |  | 0 | 3.5342 |  |  | 0 | 0 | 0.15279 | 1.922 | 3.1151 | 3.5342 | 3.5342 | 3.5342 | 0 | 0 | 0.15279 | 1.922 | 3.1151 | 3.5342 | 3.5342 | 3.5342 |  | No | Other | AMP8
| TMS | SO Winterbourne STW - Option 1 | UBA8.SEW.S39189 | 08TW101092a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-09-16 13:03 | 2027-06-26 10:53 | 2027-09-05 04:21 | 2028-02-29 | 2028-03-31 |  |  | 2024-07-31 | 2026-09-16 13:03 | 2027-06-26 10:53 | 2027-09-05 04:21 | 2028-02-29 | 2028-03-31 |  |  | 0 | 1.5053 |  |  | 0 | 0 | 0.026316 | 0.38243 | 1.5053 | 1.5053 | 1.5053 | 1.5053 | 0 | 0 | 0.026316 | 0.38243 | 1.5053 | 1.5053 | 1.5053 | 1.5053 |  | No | Other | AMP8
| TMS | SO Worcester Crescent CSO - Option 1 | UBA8.SEW.S39105 | 08TW101054a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-04-01 | 2027-09-16 22:18 | 2028-09-14 22:18 | 2028-12-15 21:55 | 2030-01-02 | 2030-03-31 |  |  | 2025-04-01 | 2027-09-16 22:18 | 2028-09-14 22:18 | 2028-12-15 21:55 | 2030-01-02 | 2030-03-31 |  |  | 0 | 3.5985 |  |  | 0 | 0 | 0 | 0.060614 | 0.68831 | 2.5576 | 3.5985 | 3.5985 | 0 | 0 | 0 | 0.060614 | 0.68831 | 2.5576 | 3.5985 | 3.5985 |  | No | Other | AMP8
| TMS | Stansted Mountifitchet STW- AMP8 Growth | UBA8.SEW.S40435, UBA8.SEW.S38269 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-11-20 | 2030-03-04 | 2031-02-09 | 2031-08-26 | 2032-12-14 | 2034-03-31 |  |  | 2024-11-20 | 2030-03-04 | 2031-02-09 | 2031-08-26 | 2032-12-14 | 2034-03-31 |  |  | 0 | 25.8918 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.45598 | 25.8918 | 0 | 0 | 0 | 0 | 0 | 0 | 0.45598 | 25.8918 |  | No | Other | AMP8
| TMS | Storm OF Bucklebury (Briff Lane) STW | UBA8.SEW.S40747 | 08TW100980a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-08-19 09:17 | 2028-03-06 01:42 | 2028-07-17 04:39 | 2029-06-15 | 2030-03-31 |  |  | 2024-07-03 | 2027-08-19 09:17 | 2028-03-06 01:42 | 2028-07-17 04:39 | 2029-06-15 | 2030-03-31 |  |  | 0 | 3.4285 |  |  | 0 | 0 | 0 | 0.065296 | 1.0959 | 3.026 | 3.4285 | 3.4285 | 0 | 0 | 0 | 0.065296 | 1.0959 | 3.026 | 3.4285 | 3.4285 |  | No | Other | AMP8
| TMS | Storm OF Bucklebury (Briff Lane) STW | UBA8.SEW.S40747 | 08TW100980a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-08-19 09:17 | 2028-03-06 01:42 | 2028-07-17 04:39 | 2029-06-15 | 2030-03-31 |  |  | 2024-07-03 | 2027-08-19 09:17 | 2028-03-06 01:42 | 2028-07-17 04:39 | 2029-06-15 | 2030-03-31 |  |  | 0 | 3.1648 |  |  | 0 | 0 | 0 | 0.060273 | 1.0116 | 2.7932 | 3.1648 | 3.1648 | 0 | 0 | 0 | 0.060273 | 1.0116 | 2.7932 | 3.1648 | 3.1648 |  | No | Other | AMP8
| TMS | Storm OF Huckers Lane (Selbourne) SPS | UBA8.SEW.S40743 | 08TW101030a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-06-24 03:17 | 2028-06-22 03:17 | 2028-09-29 01:34 | 2029-11-14 | 2030-03-31 |  |  | 2024-11-06 | 2027-06-24 03:17 | 2028-06-22 03:17 | 2028-09-29 01:34 | 2029-11-14 | 2030-03-31 |  |  | 0 | 3.2967 |  |  | 0 | 0 | 0 | 0.067154 | 0.86881 | 2.5824 | 3.2967 | 3.2967 | 0 | 0 | 0 | 0.067154 | 0.86881 | 2.5824 | 3.2967 | 3.2967 |  | No | Other | AMP8
| TMS | Storm Over Cascade Rd Buckhurst Hill CSO | UBA8.SEW.S41156 | 11TW100190a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 17:45 | 2028-09-13 13:01 | 2028-12-13 05:50 | 2029-12-25 | 2030-03-31 |  |  | 2024-11-06 | 2027-09-16 17:45 | 2028-09-13 13:01 | 2028-12-13 05:50 | 2029-12-25 | 2030-03-31 |  |  | 0 | 4.4763 |  |  | 0 | 0 | 0 | 0.07698 | 1.0127 | 3.247 | 4.4763 | 4.4763 | 0 | 0 | 0 | 0.07698 | 1.0127 | 3.247 | 4.4763 | 4.4763 |  | No | Other | AMP8
| TMS | Storm Over Constable's Piece Beckley STW | UBA8.SEW.S41499 | 11TW100087a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2028-04-21 12:27 | 2028-11-09 06:19 | 2029-03-23 18:14 | 2030-02-23 | 2030-03-31 |  |  | 2024-10-23 | 2028-04-21 12:27 | 2028-11-09 06:19 | 2029-03-23 18:14 | 2030-02-23 | 2030-03-31 |  |  | 0 | 3.4692 |  |  | 0 | 0 | 0 | 0 | 0.082488 | 0.90461 | 3.4692 | 3.4692 | 0 | 0 | 0 | 0 | 0.082488 | 0.90461 | 3.4692 | 3.4692 |  | No | Other | AMP8
| TMS | Storm Overflow Snakes Lane | UBA8.SEW.S41337 | 09TW100081a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2027-09-16 00:49 | 2028-09-14 00:49 | 2028-12-16 22:30 | 2030-01-11 | 2030-03-31 |  |  | 2024-11-06 | 2027-09-16 00:49 | 2028-09-14 00:49 | 2028-12-16 22:30 | 2030-01-11 | 2030-03-31 |  |  | 0 | 3.887 |  |  | 0 | 0 | 0 | 0.066186 | 0.81457 | 2.7758 | 3.887 | 3.887 | 0 | 0 | 0 | 0.066186 | 0.81457 | 2.7758 | 3.887 | 3.887 |  | No | Other | AMP8
| TMS | Storm Overflows - Bampton STW | UBA8.SEW.S40740 | 11TW100004a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-11-20 | 2028-11-18 | 2029-08-11 | 2032-08-07 | 2033-03-31 |  |  | 2024-06-19 | 2027-11-20 | 2028-11-18 | 2029-08-11 | 2032-08-07 | 2033-03-31 |  |  | 0 | 7.8295 |  |  | 0 | 0 | 0 | 0 | 0.46157 | 1.8381 | 3.3397 | 7.8295 | 0 | 0 | 0 | 0 | 0.46157 | 1.8381 | 3.3397 | 7.8295 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Bampton STW | UBA8.SEW.S40740 | 11TW100004a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-11-20 | 2028-11-18 | 2029-08-11 | 2032-08-07 | 2033-03-31 |  |  | 2024-06-19 | 2027-11-20 | 2028-11-18 | 2029-08-11 | 2032-08-07 | 2033-03-31 |  |  | 0 | 5.4409 |  |  | 0 | 0 | 0 | 0 | 0.32075 | 1.2773 | 2.3208 | 5.4409 | 0 | 0 | 0 | 0 | 0.32075 | 1.2773 | 2.3208 | 5.4409 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Barkway STW - Option 1 | UBA8.SEW.S39214 | 11TW100011a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-12-17 12:34 | 2028-06-03 13:36 | 2028-09-24 06:17 | 2029-07-03 | 2030-03-31 |  |  | 2024-06-26 | 2027-12-17 12:34 | 2028-06-03 13:36 | 2028-09-24 06:17 | 2029-07-03 | 2030-03-31 |  |  | 0 | 1.7336 |  |  | 0 | 0 | 0 | 0 | 0.10884 | 1.3675 | 1.7336 | 1.7336 | 0 | 0 | 0 | 0 | 0.10884 | 1.3675 | 1.7336 | 1.7336 |  | No | Other | AMP8
| TMS | Storm Overflows - Charlbury STW | UBA8.SEW.S40746 | 08TW101016a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-08-28 | 2028-01-21 21:40 | 2029-01-19 21:40 | 2029-09-24 22:20 | 2031-06-07 | 2032-03-31 |  |  | 2024-08-28 | 2028-01-21 21:40 | 2029-01-19 21:40 | 2029-09-24 22:20 | 2031-06-07 | 2032-03-31 |  |  | 0 | 4.7654 |  |  | 0 | 0 | 0 | 0 | 0.18852 | 0.79148 | 2.8991 | 4.7654 | 0 | 0 | 0 | 0 | 0.18852 | 0.79148 | 2.8991 | 4.7654 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Chinnor STW - Option 1 | UBA8.SEW.S39167 | 08TW100993a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-12-17 18:21 | 2028-12-15 18:21 | 2029-09-07 18:21 | 2032-08-28 | 2033-03-31 |  |  | 2024-10-23 | 2027-12-17 18:21 | 2028-12-15 18:21 | 2029-09-07 18:21 | 2032-08-28 | 2033-03-31 |  |  | 0 | 9.7499 |  |  | 0 | 0 | 0 | 0 | 0.40962 | 1.8244 | 3.8608 | 9.7499 | 0 | 0 | 0 | 0 | 0.40962 | 1.8244 | 3.8608 | 9.7499 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Chinnor STW - Option 1 | UBA8.SEW.S39167 | 08TW100993a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-23 | 2027-12-17 18:21 | 2028-12-15 18:21 | 2029-09-07 18:21 | 2032-08-28 | 2033-03-31 |  |  | 2024-10-23 | 2027-12-17 18:21 | 2028-12-15 18:21 | 2029-09-07 18:21 | 2032-08-28 | 2033-03-31 |  |  | 0 | 11.4455 |  |  | 0 | 0 | 0 | 0 | 0.48086 | 2.1417 | 4.5323 | 11.4455 | 0 | 0 | 0 | 0 | 0.48086 | 2.1417 | 4.5323 | 11.4455 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Churt SPS - Option 1 | UBA8.SEW.S39188 | 08TW100986a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-11-19 10:45 | 2027-11-18 10:45 | 2028-07-01 09:44 | 2031-01-26 | 2031-03-31 |  |  | 2024-07-31 | 2026-11-19 10:45 | 2027-11-18 10:45 | 2028-07-01 09:44 | 2031-01-26 | 2031-03-31 |  |  | 0 | 7.3444 |  |  | 0 | 0 | 0 | 0.42722 | 2.7165 | 4.5111 | 6.0089 | 7.3444 | 0 | 0 | 0 | 0.42722 | 2.7165 | 4.5111 | 6.0089 | 7.3444 |  | No | Other | AMP8
| TMS | Storm Overflows - Combe STW - Option 1 | UBA8.SEW.S39163 | 08TW100997a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2026-10-21 15:41 | 2027-04-11 01:23 | 2027-08-03 07:50 | 2028-05-15 | 2029-03-31 |  |  | 2024-07-31 | 2026-10-21 15:41 | 2027-04-11 01:23 | 2027-08-03 07:50 | 2028-05-15 | 2029-03-31 |  |  | 0 | 2.5158 |  |  | 0 | 0 | 0.042323 | 0.41336 | 2.2718 | 2.5158 | 2.5158 | 2.5158 | 0 | 0 | 0.042323 | 0.41336 | 2.2718 | 2.5158 | 2.5158 | 2.5158 |  | No | Other | AMP8
| TMS | Storm Overflows - Eydon STW - Option 1 | UBA8.SEW.S39153 | 08TW101007a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-09-16 16:20 | 2028-01-23 04:14 | 2028-04-17 20:10 | 2028-11-18 | 2029-03-31 |  |  | 2024-07-03 | 2027-09-16 16:20 | 2028-01-23 04:14 | 2028-04-17 20:10 | 2028-11-18 | 2029-03-31 |  |  | 0 | 1.9345 |  |  | 0 | 0 | 0 | 0.037297 | 0.44515 | 1.9345 | 1.9345 | 1.9345 | 0 | 0 | 0 | 0.037297 | 0.44515 | 1.9345 | 1.9345 | 1.9345 |  | No | Other | AMP8
| TMS | Storm Overflows - Eydon STW - Option 1 | UBA8.SEW.S39153 | 08TW101007a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-09-16 16:20 | 2028-01-23 04:14 | 2028-04-17 20:10 | 2028-11-18 | 2029-03-31 |  |  | 2024-07-03 | 2027-09-16 16:20 | 2028-01-23 04:14 | 2028-04-17 20:10 | 2028-11-18 | 2029-03-31 |  |  | 0 | 1.52 |  |  | 0 | 0 | 0 | 0.029305 | 0.34976 | 1.52 | 1.52 | 1.52 | 0 | 0 | 0 | 0.029305 | 0.34976 | 1.52 | 1.52 | 1.52 |  | No | Other | AMP8
| TMS | Storm Overflows - Finstock STW | UBA8.SEW.S40745 | 08TW101018a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2028-02-18 23:58 | 2029-02-16 23:58 | 2029-11-09 23:58 | 2031-11-17 | 2032-03-31 |  |  | 2024-07-10 | 2028-02-18 23:58 | 2029-02-16 23:58 | 2029-11-09 23:58 | 2031-11-17 | 2032-03-31 |  |  | 0 | 2.656 |  |  | 0 | 0 | 0 | 0 | 0.079963 | 0.71524 | 1.3505 | 2.656 | 0 | 0 | 0 | 0 | 0.079963 | 0.71524 | 1.3505 | 2.656 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Hanwell STW - Option 1 | UBA8.SEW.S39146 | 08TW101014a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2028-02-18 09:09 | 2028-05-30 13:37 | 2028-08-06 16:35 | 2029-01-24 | 2029-03-31 |  |  | 2024-06-19 | 2028-02-18 09:09 | 2028-05-30 13:37 | 2028-08-06 16:35 | 2029-01-24 | 2029-03-31 |  |  | 0 | 5.1867 |  |  | 0 | 0 | 0 | 0 | 0.243 | 5.1867 | 5.1867 | 5.1867 | 0 | 0 | 0 | 0 | 0.243 | 5.1867 | 5.1867 | 5.1867 |  | No | Other | AMP8
| TMS | Storm Overflows - Newbury STW - Option 1 | UBA8.SEW.S39196 | 08TW101085a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2027-12-18 | 2028-12-16 | 2029-09-08 | 2032-09-04 | 2033-03-31 |  |  | 2024-07-10 | 2027-12-18 | 2028-12-16 | 2029-09-08 | 2032-09-04 | 2033-03-31 |  |  | 0 | 36.8261 |  |  | 0 | 0 | 0 | 0 | 1.6279 | 5.9592 | 12.5245 | 36.8261 | 0 | 0 | 0 | 0 | 1.6279 | 5.9592 | 12.5245 | 36.8261 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - North Weald STW | UBA8.SEW.S40742 | 10TW100031a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2026-01-21 10:12 | 2027-01-20 10:12 | 2027-10-13 10:12 | 2030-02-01 | 2030-03-31 |  |  | 2024-06-26 | 2026-01-21 10:12 | 2027-01-20 10:12 | 2027-10-13 10:12 | 2030-02-01 | 2030-03-31 |  |  | 0 | 9.0774 |  |  | 0 | 0 | 0.33967 | 1.4904 | 3.0883 | 6.2681 | 9.0774 | 9.0774 | 0 | 0 | 0.33967 | 1.4904 | 3.0883 | 6.2681 | 9.0774 | 9.0774 |  | No | Other | AMP8
| TMS | Storm Overflows - Rusper STW - Option 1 | UBA8.SEW.S39204 | 08TW101078a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-20 | 2028-03-17 04:01 | 2029-03-16 04:01 | 2029-07-06 06:49 | 2030-10-15 | 2031-03-31 |  |  | 2024-11-20 | 2028-03-17 04:01 | 2029-03-16 04:01 | 2029-07-06 06:49 | 2030-10-15 | 2031-03-31 |  |  | 0 | 3.4807 |  |  | 0 | 0 | 0 | 0 | 0.088315 | 1.3391 | 2.5131 | 3.4807 | 0 | 0 | 0 | 0 | 0.088315 | 1.3391 | 2.5131 | 3.4807 |  | No | Other | AMP8
| TMS | Storm Overflows - Stone STW - Option 1 | UBA8.SEW.S39123 | 08TW101036a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-08-19 02:26 | 2028-08-17 02:26 | 2029-05-10 02:26 | 2031-04-19 | 2031-03-31 |  |  | 2024-06-26 | 2027-08-19 02:26 | 2028-08-17 02:26 | 2029-05-10 02:26 | 2031-04-19 | 2031-03-31 |  |  | 0 | 6.9485 |  |  | 0 | 0 | 0 | 0.12531 | 0.4853 | 1.9007 | 4.3508 | 6.9485 | 0 | 0 | 0 | 0.12531 | 0.4853 | 1.9007 | 4.3508 | 6.9485 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Stone STW - Option 1 | UBA8.SEW.S39123 | 08TW101036a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2027-08-19 02:26 | 2028-08-17 02:26 | 2029-05-10 02:26 | 2031-04-19 | 2031-03-31 |  |  | 2024-06-26 | 2027-08-19 02:26 | 2028-08-17 02:26 | 2029-05-10 02:26 | 2031-04-19 | 2031-03-31 |  |  | 0 | 6.1619 |  |  | 0 | 0 | 0 | 0.11112 | 0.43036 | 1.6855 | 3.8583 | 6.1619 | 0 | 0 | 0 | 0.11112 | 0.43036 | 1.6855 | 3.8583 | 6.1619 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows - Takeley STW - Option 1 | UBA8.SEW.S39122 | 08TW101037a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-01-21 05:34 | 2028-11-15 13:30 | 2029-06-03 02:47 | 2030-10-15 | 2031-03-31 |  |  | 2024-06-26 | 2028-01-21 05:34 | 2028-11-15 13:30 | 2029-06-03 02:47 | 2030-10-15 | 2031-03-31 |  |  | 0 | 9.0413 |  |  | 0 | 0 | 0 | 0 | 0.42838 | 3.4066 | 6.5679 | 9.0413 | 0 | 0 | 0 | 0 | 0.42838 | 3.4066 | 6.5679 | 9.0413 |  | No | Other | AMP8
| TMS | Storm Overflows Benson STW | UBA8.SEW.S41609 | 11TW100007a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2025-09-17 10:55 | 2026-09-16 10:55 | 2027-06-09 10:55 | 2030-05-21 | 2031-03-31 |  |  | 2024-07-31 | 2025-09-17 10:55 | 2026-09-16 10:55 | 2027-06-09 10:55 | 2030-05-21 | 2031-03-31 |  |  | 0 | 10.5612 |  |  | 0 | 0 | 0.70329 | 2.0047 | 4.8874 | 7.8072 | 10.1705 | 10.5612 | 0 | 0 | 0.70329 | 2.0047 | 4.8874 | 7.8072 | 10.1705 | 10.5612 |  | No | Other | AMP8
| TMS | Storm Overflows Benson STW | UBA8.SEW.S41609 | 11TW100007a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-31 | 2025-09-17 10:55 | 2026-09-16 10:55 | 2027-06-09 10:55 | 2030-05-21 | 2031-03-31 |  |  | 2024-07-31 | 2025-09-17 10:55 | 2026-09-16 10:55 | 2027-06-09 10:55 | 2030-05-21 | 2031-03-31 |  |  | 0 | 17.2315 |  |  | 0 | 0 | 1.1475 | 3.2708 | 7.9742 | 12.738 | 16.5939 | 17.2315 | 0 | 0 | 1.1475 | 3.2708 | 7.9742 | 12.738 | 16.5939 | 17.2315 |  | No | Other | AMP8
| TMS | Storm Overflows Bletchingdon STW | UBA8.SEW.S39211 | 08TW100983a | Storm overflows | PCDWW5 | Retained |  | 2028-03-31 | 2028-03-31 | 2024-07-17 | 2025-10-22 00:04 | 2026-10-06 | 2027-06-29 | 2030-06-25 | 2031-03-31 |  |  | 2024-07-17 | 2025-10-22 00:04 | 2026-10-06 | 2027-06-29 | 2030-06-25 | 2031-03-31 |  |  | 0 | 4.0631 |  |  | 0 | 0 | 0.21504 | 1.0612 | 2.433 | 3.2681 | 3.9101 | 4.0631 | 0 | 0 | 0.21504 | 1.0612 | 2.433 | 3.2681 | 3.9101 | 4.0631 |  | No | Other | AMP8
| TMS | Storm Overflows Chapel Row (Berks) STW | UBA8.SEW.S39169 | 08TW100991a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-10-21 07:13 | 2028-02-09 05:03 | 2028-04-23 03:36 | 2028-10-25 | 2029-03-31 |  |  | 2024-06-19 | 2027-10-21 07:13 | 2028-02-09 05:03 | 2028-04-23 03:36 | 2028-10-25 | 2029-03-31 |  |  | 0 | 2.7209 |  |  | 0 | 0 | 0 | 0.048008 | 0.94665 | 2.7209 | 2.7209 | 2.7209 | 0 | 0 | 0 | 0.048008 | 0.94665 | 2.7209 | 2.7209 | 2.7209 |  | No | Other | AMP8
| TMS | Storm Overflows Farnham STW | UBA8.SEW.S41575 | 11TW100035a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-26 | 2028-06-24 | 2029-06-23 | 2030-03-16 | 2033-03-12 | 2033-03-31 |  |  | 2024-06-26 | 2028-06-24 | 2029-06-23 | 2030-03-16 | 2033-03-12 | 2033-03-31 |  |  | 0 | 3.7181 |  |  | 0 | 0 | 0 | 0 | 0.079275 | 0.48271 | 1.0172 | 3.7181 | 0 | 0 | 0 | 0 | 0.079275 | 0.48271 | 1.0172 | 3.7181 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows Grendon Underwood STW | UBA8.SEW.S39149 | 08TW101011a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2027-03-31 04:16 | 2027-09-16 06:31 | 2027-11-11 06:31 | 2028-03-03 | 2028-03-31 |  |  | 2024-07-03 | 2027-03-31 04:16 | 2027-09-16 06:31 | 2027-11-11 06:31 | 2028-03-03 | 2028-03-31 |  |  | 0 | 5.3072 |  |  | 0 | 0 | 0.15802 | 2.524 | 5.3423 | 5.3072 | 5.3072 | 5.3072 | 0 | 0 | 0.15802 | 2.524 | 5.3423 | 5.3072 | 5.3072 | 5.3072 |  | No | Other | AMP8
| TMS | Storm Overflows Hambleden STW | UBA8.SEW.S39197 | 08TW101084a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2028-10-20 09:40 | 2029-03-20 04:22 | 2029-06-28 16:50 | 2030-03-07 | 2030-03-31 |  |  | 2024-11-06 | 2028-10-20 09:40 | 2029-03-20 04:22 | 2029-06-28 16:50 | 2030-03-07 | 2030-03-31 |  |  | 0 | 2.5378 |  |  | 0 | 0 | 0 | 0 | 0.044646 | 0.66847 | 2.501 | 2.5378 | 0 | 0 | 0 | 0 | 0.044646 | 0.66847 | 2.501 | 2.5378 |  | No | Other | AMP8
| TMS | Storm Overflows Holmwood STW | UBA8.SEW.S41562 | 10TW100024a | Flow to Full Treatment | PCDWW4 | Retained |  | 2028-03-31 | 2028-03-31 | 2024-06-19 | 2026-04-23 | 2027-04-22 | 2028-01-13 | 2031-01-09 | 2031-03-31 |  |  | 2024-06-19 | 2026-04-23 | 2027-04-22 | 2028-01-13 | 2031-01-09 | 2031-03-31 |  |  | 0 | 9.3582 |  |  | 0 | 0 | 0.3116 | 1.5004 | 3.1828 | 5.6947 | 8.2066 | 9.3582 | 0 | 0 | 0.3116 | 1.5004 | 3.1828 | 5.6947 | 8.2066 | 9.3582 |  | No | Other | AMP8
| TMS | Storm Overflows Holmwood STW | UBA8.SEW.S41562 | 10TW100024a | Storm overflows | PCDWW5 | Retained |  | 2028-03-31 | 2028-03-31 | 2024-06-19 | 2026-04-23 | 2027-04-22 | 2028-01-13 | 2031-01-09 | 2031-03-31 |  |  | 2024-06-19 | 2026-04-23 | 2027-04-22 | 2028-01-13 | 2031-01-09 | 2031-03-31 |  |  | 0 | 9.3582 |  |  | 0 | 0 | 0.3116 | 1.5004 | 3.1828 | 5.6947 | 8.2066 | 9.3582 | 0 | 0 | 0.3116 | 1.5004 | 3.1828 | 5.6947 | 8.2066 | 9.3582 |  | No | Other | AMP8
| TMS | Storm Overflows Little Compton STW | UBA8.SEW.S39136 | 08TW101023a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-10 | 2029-03-29 22:05 | 2029-09-14 13:38 | 2029-11-09 13:38 | 2030-03-02 | 2030-03-31 |  |  | 2024-07-10 | 2029-03-29 22:05 | 2029-09-14 13:38 | 2029-11-09 13:38 | 2030-03-02 | 2030-03-31 |  |  | 0 | 2.941 |  |  | 0 | 0 | 0 | 0 | 0.092326 | 1.9525 | 2.9827 | 2.941 | 0 | 0 | 0 | 0 | 0.092326 | 1.9525 | 2.9827 | 2.941 |  | No | Other | AMP8
| TMS | Storm Overflows Little Milton STW | UBA8.SEW.S41490 | 12TW100070a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2026-07-22 08:11 | 2027-02-14 20:08 | 2027-07-03 04:06 | 2028-06-13 | 2029-03-31 |  |  | 2024-10-02 | 2026-07-22 08:11 | 2027-02-14 20:08 | 2027-07-03 04:06 | 2028-06-13 | 2029-03-31 |  |  | 0 | 3.5446 |  |  | 0 | 0 | 0.071288 | 0.89696 | 3.215 | 3.5446 | 3.5446 | 3.5446 | 0 | 0 | 0.071288 | 0.89696 | 3.215 | 3.5446 | 3.5446 | 3.5446 |  | No | Other | AMP8
| TMS | Storm Overflows South Leigh STW | UBA8.SEW.S39127 | 08TW101032a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2028-07-21 05:09 | 2029-03-07 23:12 | 2029-05-04 09:43 | 2029-09-25 | 2030-03-31 |  |  | 2024-06-19 | 2028-07-21 05:09 | 2029-03-07 23:12 | 2029-05-04 09:43 | 2029-09-25 | 2030-03-31 |  |  | 0 | 2.287 |  |  | 0 | 0 | 0 | 0 | 0.045295 | 1.0763 | 2.287 | 2.287 | 0 | 0 | 0 | 0 | 0.045295 | 1.0763 | 2.287 | 2.287 |  | No | Other | AMP8
| TMS | Storm Overflows Standlake STW - Option 2 | UBA8.SEW.S40422 | 08TW101033a | Storm Overflow - Wetland | PCDWW5b | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2025-12-18 | 2026-12-17 | 2027-09-09 | 2030-09-05 | 2031-03-31 |  |  | 2024-11-06 | 2025-12-18 | 2026-12-17 | 2027-09-09 | 2030-09-05 | 2031-03-31 |  |  | 0 | 3.4035 |  |  | 0 | 0 | 0.16904 | 0.85948 | 1.6493 | 2.3558 | 3.0624 | 3.4035 | 0 | 0 | 0.16904 | 0.85948 | 1.6493 | 2.3558 | 3.0624 | 3.4035 |  | No | Other | AMP8
| TMS | Storm Overflows Standlake STW - Option 2 | UBA8.SEW.S40422 | 08TW101033a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-06 | 2025-12-18 | 2026-12-17 | 2027-09-09 | 2030-09-05 | 2031-03-31 |  |  | 2024-11-06 | 2025-12-18 | 2026-12-17 | 2027-09-09 | 2030-09-05 | 2031-03-31 |  |  | 0 | 4.3317 |  |  | 0 | 0 | 0.21514 | 1.0939 | 2.0991 | 2.9983 | 3.8976 | 4.3317 | 0 | 0 | 0.21514 | 1.0939 | 2.0991 | 2.9983 | 3.8976 | 4.3317 |  | No | Other | AMP8
| TMS | Storm Overflows Waddesdon STW | UBA8.SEW.S39116 | 08TW101043a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2028-01-21 23:06 | 2029-01-19 23:06 | 2029-10-12 23:06 | 2031-09-01 | 2032-03-31 |  |  | 2024-06-19 | 2028-01-21 23:06 | 2029-01-19 23:06 | 2029-10-12 23:06 | 2031-09-01 | 2032-03-31 |  |  | 0 | 5.1494 |  |  | 0 | 0 | 0 | 0 | 0.20624 | 2.1825 | 3.0169 | 5.1494 | 0 | 0 | 0 | 0 | 0.20624 | 2.1825 | 3.0169 | 5.1494 |  | No | Delivery Mechanism | AMP8
| TMS | Storm Overflows Weston (Herts) STW | UBA8.SEW.S39115 | 08TW101044a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-06-19 | 2027-10-21 06:36 | 2028-05-15 04:37 | 2028-09-30 03:18 | 2029-09-10 | 2030-03-31 |  |  | 2024-06-19 | 2027-10-21 06:36 | 2028-05-15 04:37 | 2028-09-30 03:18 | 2029-09-10 | 2030-03-31 |  |  | 0 | 3.3989 |  |  | 0 | 0 | 0 | 0.058757 | 0.9706 | 2.2086 | 3.3989 | 3.3989 | 0 | 0 | 0 | 0.058757 | 0.9706 | 2.2086 | 3.3989 | 3.3989 |  | No | Other | AMP8
| TMS | Storm Overflows Willingale STW | UBA8.SEW.S39111 | 08TW101048a | Flow to Full Treatment | PCDWW4 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-01-20 01:25 | 2028-08-01 17:48 | 2028-12-09 12:43 | 2029-10-30 | 2030-03-31 |  |  | 2024-10-02 | 2028-01-20 01:25 | 2028-08-01 17:48 | 2028-12-09 12:43 | 2029-10-30 | 2030-03-31 |  |  | 0 | 3.4052 |  |  | 0 | 0 | 0 | 0 | 0.16132 | 1.8101 | 3.4052 | 3.4052 | 0 | 0 | 0 | 0 | 0.16132 | 1.8101 | 3.4052 | 3.4052 |  | No | Other | AMP8
| TMS | Storm Overflows Willingale STW | UBA8.SEW.S39111 | 08TW101048a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-02 | 2028-01-20 01:25 | 2028-08-01 17:48 | 2028-12-09 12:43 | 2029-10-30 | 2030-03-31 |  |  | 2024-10-02 | 2028-01-20 01:25 | 2028-08-01 17:48 | 2028-12-09 12:43 | 2029-10-30 | 2030-03-31 |  |  | 0 | 1.6024 |  |  | 0 | 0 | 0 | 0 | 0.075914 | 0.85182 | 1.6024 | 1.6024 | 0 | 0 | 0 | 0 | 0.075914 | 0.85182 | 1.6024 | 1.6024 |  | No | Other | AMP8
| TMS | Storm Overflows Wingrave STW | UBA8.SEW.S39110 | 08TW101049a | Storm overflows | PCDWW5 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-03 | 2026-07-22 09:20 | 2027-04-12 06:32 | 2027-10-05 04:40 | 2028-12-18 | 2029-03-31 |  |  | 2024-07-03 | 2026-07-22 09:20 | 2027-04-12 06:32 | 2027-10-05 04:40 | 2028-12-18 | 2029-03-31 |  |  | 0 | 4.025 |  |  | 0 | 0 | 0.083494 | 1.6293 | 2.5489 | 4.025 | 4.025 | 4.025 | 0 | 0 | 0.083494 | 1.6293 | 2.5489 | 4.025 | 4.025 | 4.025 |  | No | Other | AMP8
| TMS | Stratfield Mortimer STW Phos dosing + TT | UBA8.SEW.S40733 | 09TW100180a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 2024-10-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 6.75 |  |  | 0 | 0 | 0 | 0.58213 | 1.6645 | 4.0845 | 6.6593 | 6.75 | 0 | 0 | 0 | 0.58213 | 1.6645 | 4.0845 | 6.6593 | 6.75 |  | No | Other | AMP8
| TMS | Swindon STW Phos Dosing TT + Alkalinity | UBA8.SEW.S38926 | 08TW100939a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-09-03 | 2026-06-05 | 2027-03-07 | 2030-11-29 | 2032-03-31 |  |  | 2024-10-16 | 2025-09-03 | 2026-06-05 | 2027-03-07 | 2030-11-29 | 2032-03-31 |  |  | 0 | 51.7629 |  |  | 0 | 0 | 0.14602 | 0.42467 | 0.64438 | 8.672 | 27.4178 | 51.7629 | 0 | 0 | 0.14602 | 0.42467 | 0.64438 | 8.672 | 27.4178 | 51.7629 |  | Yes | Delivery Mechanism | AMP8
| TMS | TEMPLE GUITING STW | UBA8.SEW.S41637 | 08TW101402g | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2027-05-19 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 2025-04-01 | 2027-05-19 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 0 | 4.2987 |  |  | 0 | 0 | 0.27136 | 0.68577 | 1.0997 | 2.2819 | 3.7545 | 4.2987 | 0 | 0 | 0.27136 | 0.68577 | 1.0997 | 2.2819 | 3.7545 | 4.2987 |  | No | Other | AMP8
| TMS | Thame STW - AMP8 Growth | UBA8.SEW.S38270 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2029-04-01 | 2030-02-09 | 2030-08-22 | 2031-12-07 | 2033-03-31 |  |  | 2024-10-16 | 2029-04-01 | 2030-02-09 | 2030-08-22 | 2031-12-07 | 2033-03-31 |  |  | 0 | 34.617 |  |  | 0 | 0 | 0 | 0 | 0.10014 | 0.36109 | 13.3284 | 34.617 | 0 | 0 | 0 | 0 | 0.10014 | 0.36109 | 13.3284 | 34.617 |  | No | Other | AMP8
| TMS | Thame STW Phos Dosing TT + Alkalinity | UBA8.SEW.S38933 | 08TW101889a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2028-04-01 | 2029-02-09 | 2029-08-22 | 2030-12-07 | 2032-03-31 |  |  | 2024-10-16 | 2028-04-01 | 2029-02-09 | 2029-08-22 | 2030-12-07 | 2032-03-31 |  |  | 0 | 7.585 |  |  | 0 | 0 | 0 | 0 | 0.31412 | 1.1408 | 2.7305 | 7.585 | 0 | 0 | 0 | 0 | 0.31412 | 1.1408 | 2.7305 | 7.585 |  | No | Delivery Mechanism | AMP8
| TMS | TIDDINGTON STW Phosphorus Dosing and TT | UBA8.SEW.S38986 | 08TW100940a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.6237 |  |  | 0 | 0 | 0 | 0 | 0.15007 | 0.545 | 1.3045 | 3.6237 | 0 | 0 | 0 | 0 | 0.15007 | 0.545 | 1.3045 | 3.6237 |  | No | Delivery Mechanism | AMP8
| TMS | TOWERSEY STW Phosphorus Dosing and TT | UBA8.SEW.S39030 | 08TW100941a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.4565 |  |  | 0 | 0 | 0 | 0 | 0.14314 | 0.51986 | 1.2443 | 3.4565 | 0 | 0 | 0 | 0 | 0.14314 | 0.51986 | 1.2443 | 3.4565 |  | No | Delivery Mechanism | AMP8
| TMS | Tring STW Phos Dosing TT + Alkalinity | UBA8.SEW.S38932 | 08TW100942a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 6.725 |  |  | 0 | 0 | 0 | 0 | 0.2785 | 1.0114 | 2.4209 | 6.725 | 0 | 0 | 0 | 0 | 0.2785 | 1.0114 | 2.4209 | 6.725 |  | No | Delivery Mechanism | AMP8
| TMS | Wallingford Inland Bathing Water Invest | UBA8.SEW.S38660 | 08TW100264a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-11-19 | 2026-04-20 | 2027-09-28 | 2028-05-18 | 2031-06-04 | 2031-03-31 |  |  | 2024-11-19 | 2026-04-20 | 2027-09-28 | 2028-05-18 | 2031-06-04 | 2031-03-31 |  |  | 0 | 0.24307 |  |  | 0 | 0 | 0.014623 | 0.036441 | 0.063612 | 0.13601 | 0.22007 | 0.24307 | 0 | 0 | 0.014623 | 0.036441 | 0.063612 | 0.13601 | 0.22007 | 0.24307 |  | No | Other | AMP8
| TMS | Wantage STW - AMP8 Growth | UBA8.SEW.S40436, UBA8.SEW.S38271, UBA8.SEW.S41830 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2025-11-18 | 2027-06-20 | 2027-12-19 | 2029-11-17 | 2030-03-31 |  |  | 2024-10-16 | 2025-11-18 | 2027-06-20 | 2027-12-19 | 2029-11-17 | 2030-03-31 |  |  | 0 | 39.71 |  |  | 0 | 0 | 0.71864 | 1.3768 | 5.6892 | 29.5346 | 39.5557 | 39.71 | 0 | 0 | 0.71864 | 1.3768 | 5.6892 | 29.5346 | 39.5557 | 39.71 |  | No | Other | AMP8
| TMS | Wantage STW Phosphorus Dosing and TT | UBA8.SEW.S38997 | 09TW100048a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2026-08-29 | 2027-02-20 | 2027-08-14 | 2029-11-19 | 2031-03-31 |  |  | 2024-10-16 | 2026-08-29 | 2027-02-20 | 2027-08-14 | 2029-11-19 | 2031-03-31 |  |  | 0 | 12.779 |  |  | 0 | 0 | 0 | 0.44898 | 0.8626 | 2.3109 | 9.481 | 12.779 | 0 | 0 | 0 | 0.44898 | 0.8626 | 2.3109 | 9.481 | 12.779 |  | No | Delivery Mechanism | AMP8
| TMS | WARMINGTON STW Phosphorus Dosing and TT | UBA8.SEW.S38973 | 08TW100959a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 3.4225 |  |  | 0 | 0 | 0 | 0 | 0.14173 | 0.51474 | 1.232 | 3.4225 | 0 | 0 | 0 | 0 | 0.14173 | 0.51474 | 1.232 | 3.4225 |  | No | Delivery Mechanism | AMP8
| TMS | Wash Water STW Low P, TT & FST | L897 | 08TW100946a | P-removal | PCDWW10 | Retained |  | 2026-03-31 | 2026-03-31 | 2023-05-12 | 2023-05-13 | 2023-11-05 | 2024-05-08 | 2024-12-15 | 2026-03-31 |  |  | 2023-05-12 | 2023-05-13 | 2023-11-05 | 2024-05-08 | 2024-12-15 | 2026-03-31 |  |  | 0 | 9.9824 |  |  | 0 | 0 | 9.8874 | 9.9824 | 9.9824 | 9.9824 | 9.9824 | 9.9824 | 0 | 0 | 9.8874 | 9.9824 | 9.9824 | 9.9824 | 9.9824 | 9.9824 |  | No | Other | AMP8
| TMS | WATLINGTON STW | UBA8.SEW.S40809 | 08TW101401a | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-02-17 | 2025-02-17 | 2025-06-13 | 2026-01-16 | 2027-11-21 | 2029-03-31 |  |  | 2025-02-17 | 2025-02-17 | 2025-06-13 | 2026-01-16 | 2027-11-21 | 2029-03-31 |  |  | 0 | 8.44e-06 |  |  | 0 | 0 | 0 | 0 | 1.91e-06 | 8.44e-06 | 8.44e-06 | 8.44e-06 | 0 | 0 | 0 | 0 | 1.91e-06 | 8.44e-06 | 8.44e-06 | 8.44e-06 |  | No | Other | AMP8
| TMS | WELFORD STW | UBA8.SEW.S41638 | 08TW101402h | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2026-05-19 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 2025-04-01 | 2026-05-19 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 2.6226 |  |  | 0 | 0 | 0.16645 | 0.42065 | 0.77438 | 2.2632 | 2.5952 | 2.6226 | 0 | 0 | 0.16645 | 0.42065 | 0.77438 | 2.2632 | 2.5952 | 2.6226 |  | No | Other | AMP8
| TMS | Weybridge STW Phosphorus Dosing and TT | UBA8.SEW.S38921 | 09TW100049a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-07-06 | 2026-05-22 | 2026-12-07 | 2028-11-17 | 2030-03-31 |  |  | 2024-10-16 | 2025-07-06 | 2026-05-22 | 2026-12-07 | 2028-11-17 | 2030-03-31 |  |  | 0 | 10.3566 |  |  | 0 | 0 | 0.62101 | 2.2089 | 5.1528 | 10.072 | 10.2805 | 10.3566 | 0 | 0 | 0.62101 | 2.2089 | 5.1528 | 10.072 | 10.2805 | 10.3566 |  | No | Other | AMP8
| TMS | Wheatley STW - AMP8 Growth | UBA8.SEW.S40434 |  | Growth to Sewerage Treatment Works | PCDWW27 | Retained |  |  |  | 2024-10-16 | 2025-07-23 | 2026-05-17 | 2026-12-12 | 2028-11-20 | 2030-03-31 |  |  | 2024-10-16 | 2025-07-23 | 2026-05-17 | 2026-12-12 | 2028-11-20 | 2030-03-31 |  |  | 0 | 17.4037 |  |  | 0 | 0 | 0.9995 | 3.3341 | 7.8398 | 16.5647 | 17.2567 | 17.4037 | 0 | 0 | 0.9995 | 3.3341 | 7.8398 | 16.5647 | 17.2567 | 17.4037 |  | No | Other | AMP8
| TMS | White Waltham STW Phos Dosing and TT | UBA8.SEW.S39002 | 08TW100947a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 2024-10-16 | 2027-08-23 | 2028-05-16 | 2028-12-11 | 2030-11-20 | 2032-03-31 |  |  | 0 | 5.99 |  |  | 0 | 0 | 0 | 0 | 0.24806 | 0.9009 | 2.1563 | 5.99 | 0 | 0 | 0 | 0 | 0.24806 | 0.9009 | 2.1563 | 5.99 |  | No | Delivery Mechanism | AMP8
| TMS | Widford STW Phos Dosing TT + Alkalinity | UBA8.SEW.S38952 | 08TW100948a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-11-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 2024-11-16 | 2026-04-14 | 2027-02-09 | 2027-08-25 | 2028-12-13 | 2030-03-31 |  |  | 0 | 5.4572 |  |  | 0 | 0 | 0.32723 | 1.164 | 2.7152 | 5.3073 | 5.4171 | 5.4572 | 0 | 0 | 0.32723 | 1.164 | 2.7152 | 5.3073 | 5.4171 | 5.4572 |  | No | Other | AMP8
| TMS | WINEP Emergency Overflows monitoring | UBA8.SEW.S40131 | 08TW100733a | MCERTs monitoring at emergency sewage pumping station overflows (WINEP/NEP) | PCDWW3 | Retained |  | 2030-03-31 | 2030-03-31 | 2025-06-30 | 2029-10-29 | 2030-06-13 | 2031-01-11 | 2032-11-19 | 2034-03-31 |  |  | 2025-06-30 | 2029-10-29 | 2030-06-13 | 2031-01-11 | 2032-11-19 | 2034-03-31 |  |  | 0 | 4.355 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0.21279 | 4.355 | 0 | 0 | 0 | 0 | 0 | 0 | 0.21279 | 4.355 |  | No | Other | AMP8
| TMS | WINEP Groundwater Darent Leaking Sewers | UBA8.SEW.S38858 | 08TW100280h | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-07-17 | 2025-11-28 | 2026-04-02 | 2026-05-12 | 2027-08-27 | 2028-03-31 |  |  | 2024-07-17 | 2025-11-28 | 2026-04-02 | 2026-05-12 | 2027-08-27 | 2028-03-31 |  |  | 0 | 0.92516 |  |  | 0 | 0 | 0.092517 | 0.74013 | 0.92516 | 0.92516 | 0.92516 | 0.92516 | 0 | 0 | 0.092517 | 0.74013 | 0.92516 | 0.92516 | 0.92516 | 0.92516 |  | No | Other | AMP8
| TMS | WINEP Groundwater Needs Windmill Hill | UBA8.SEW.S38857 | 08TW100280b | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-08-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 2025-08-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 0 | 0.35939 |  |  | 0 | 0 | 0.35939 | 0.35939 | 0.35939 | 0.35939 | 0.35939 | 0.35939 | 0 | 0 | 0.35939 | 0.35939 | 0.35939 | 0.35939 | 0.35939 | 0.35939 |  | No | Other | AMP8
| TMS | WINEP Lambourn N and P TAL East Shefford | UBA8.SEW.S38508 | 08TW100860a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-07-17 | 2025-11-23 | 2026-06-21 | 2027-01-17 | 2028-11-22 | 2030-03-31 |  |  | 2024-07-17 | 2025-11-23 | 2026-06-21 | 2027-01-17 | 2028-11-22 | 2030-03-31 |  |  | 0 | 8.58e-07 |  |  | 0 | 0 | 0 | 0 | 8.58e-07 | 8.58e-07 | 8.58e-07 | 8.58e-07 | 0 | 0 | 0 | 0 | 8.58e-07 | 8.58e-07 | 8.58e-07 | 8.58e-07 |  | No | Other | AMP8
| TMS | WINEP Lambourn P & N TAL Chieveley STW | UBA8.SEW.S38072 | 08TW100859a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2024-10-16 | 2029-03-31 | 2029-03-31 | 2029-03-31 | 2029-03-31 |  |  | 2024-10-16 | 2024-10-16 | 2029-03-31 | 2029-03-31 | 2029-03-31 | 2029-03-31 |  |  | 0 | 3.9252 |  |  | 0 | 0 | 0.82971 | 3.7 | 3.9016 | 3.9252 | 3.9252 | 3.9252 | 0 | 0 | 0.82971 | 3.7 | 3.9016 | 3.9252 | 3.9252 | 3.9252 |  | No | Other | AMP8
| TMS | WINEP SSSI Roding Valley Meadows Invest | UBA8.SEW.S40785 | 08TW101463a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2025-08-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 2025-08-01 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 0 | 0.3245 |  |  | 0 | 0 | 0.3245 | 0.3245 | 0.3245 | 0.3245 | 0.3245 | 0.3245 | 0 | 0 | 0.3245 | 0.3245 | 0.3245 | 0.3245 | 0.3245 | 0.3245 |  | No | Other | AMP8
| TMS | WINEP SSSI Rye Meads Improve Units | UBA8.SEW.S40789 | 08TW101459a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 | 2024-07-17 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 2024-07-17 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 | 2026-03-31 |  |  | 0 | 0.16277 |  |  | 0 | 0 | 0.054267 | 0.10852 | 0.16277 | 0.16277 | 0.16277 | 0.16277 | 0 | 0 | 0.054267 | 0.10852 | 0.16277 | 0.16277 | 0.16277 | 0.16277 |  | No | Other | AMP8
| TMS | Witney STW Phosphorus Dosing and TT | UBA8.SEW.S38802 | 08TW100949a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2027-03-31 | 2028-02-07 | 2028-08-15 | 2029-12-10 | 2031-03-31 |  |  | 2024-10-16 | 2027-03-31 | 2028-02-07 | 2028-08-15 | 2029-12-10 | 2031-03-31 |  |  | 0 | 15.1279 |  |  | 0 | 0 | 0 | 0.093253 | 0.2497 | 7.9791 | 14.6332 | 15.1279 | 0 | 0 | 0 | 0.093253 | 0.2497 | 7.9791 | 14.6332 | 15.1279 |  | No | Delivery Mechanism | AMP8
| TMS | Wokingham Ash Ridge Phos Dosing TT + Alk | UBA8.SEW.S39007 | 08TW100950a | P-removal | PCDWW10 | Retained |  | 2030-03-31 | 2030-03-31 | 2024-10-16 | 2025-02-25 | 2026-02-21 | 2026-08-19 | 2028-11-21 | 2030-03-31 |  |  | 2024-10-16 | 2025-02-25 | 2026-02-21 | 2026-08-19 | 2028-11-21 | 2030-03-31 |  |  | 0 | 10.5728 |  |  | 0 | 0 | 0.60024 | 1.7156 | 3.5827 | 8.5594 | 10.4441 | 10.5728 | 0 | 0 | 0.60024 | 1.7156 | 3.5827 | 8.5594 | 10.4441 | 10.5728 |  | No | Other | AMP8
| TMS | Wokingham STW Cypermethrin - IMP & ND | UBA8.SEW.S40653 | 08TW100102a | Treatment for chemical removal (WINEP/NEP) | PCDWW7 | Retained |  | 2027-03-31 | 2027-03-31 | 2024-10-16 | 2026-11-29 | 2028-02-20 | 2028-08-15 | 2030-11-13 | 2032-03-31 |  |  | 2024-10-16 | 2026-11-29 | 2028-02-20 | 2028-08-15 | 2030-11-13 | 2032-03-31 |  |  | 0 | 17.7999 |  |  | 0 | 0 | 0 | 0.51808 | 2.5068 | 4.4523 | 10.925 | 17.7999 | 0 | 0 | 0 | 0.51808 | 2.5068 | 4.4523 | 10.925 | 17.7999 |  | No | Delivery Mechanism | AMP8
| TMS | Wolvercote Stream Bathing Water Invest | UBA8.SEW.S38659 | 08TW100262a | WINEP Investigations (wastewater) | PCDWW18 | Retained |  | 2027-04-30 | 2027-04-30 |  | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 |  |  |  | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 | 2027-03-31 |  |  | 0 | 0.27465 |  |  | 0 | 0 | 0.13733 | 0.27465 | 0.27465 | 0.27465 | 0.27465 | 0.27465 | 0 | 0 | 0.13733 | 0.27465 | 0.27465 | 0.27465 | 0.27465 | 0.27465 |  | No | Other | AMP8
| TMS | WOLVERTON COMMON STW | UBA8.SEW.S41640 | 08TW101402i | Treatment for tightening of sanitary parameters | PCDWW12 | Retained |  | 2026-03-31 | 2026-03-31 | 2025-04-01 | 2027-04-14 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 2025-04-01 | 2027-04-14 | 2028-02-09 | 2028-08-24 | 2029-12-13 | 2031-03-31 |  |  | 0 | 1.2567 |  |  | 0 | 0 | 0 | 0 | 0.074159 | 0.19954 | 0.37061 | 1.2567 | 0 | 0 | 0 | 0 | 0.074159 | 0.19954 | 0.37061 | 1.2567 |  | No | Other | AMP8
| TMS | Dorking STW Storm Compliance | J982.01 | FLO01261 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-08-21 | 2020-01-21 | 2023-03-17 | 2024-05-09 | 2025-12-23 | 2025-10-20 |  | IM4 | 2019-08-21 | 2020-01-21 | 2023-03-17 | 2024-05-09 | 2025-12-23 | 2025-08-20 |  |  | 8.424 | 1.2239 |  |  | 2.1319 | 7.4179 | 10.1379 | 10.1418 | 10.1418 | 10.1418 | 10.1418 | 10.1418 | 2.1319 | 7.4179 | 9.644 | 9.6479 | 9.6479 | 9.6479 | 9.6479 | 9.6479 |  | No | Other | AMP7 carryover
| TMS | Heath Lake SSSI Enhancements | J985.01 | THM00074 | Phosphorous | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-09-26 | 2020-01-21 | 2025-06-16 | 2025-08-22 | 2026-11-13 | 2026-12-08 |  | IM3 | 2019-09-26 | 2020-01-21 | 2025-04-30 | 2025-10-20 | 2026-10-16 | 2026-08-20 |  |  | 1.4225 | 5.9586 |  |  | 0.61877 | 0.88896 | 2.8243 | 8.4432 | 8.5892 | 8.5892 | 8.5892 | 8.5892 | 0.71615 | 0.98634 | 3.968 | 7.3473 | 7.3811 | 7.3811 | 7.3811 | 7.3811 |  | No | Other | AMP7 carryover
| TMS | WINEP FtFT Witney STW | K081.01 | FLO01303 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2020-09-30 | 2021-12-23 | 2023-04-21 | 2026-01-29 | 2025-11-23 |  | IM4 | 2019-06-18 | 2020-09-30 | 2021-12-23 | 2023-04-21 | 2026-01-29 | 2025-09-23 |  |  | 15.081 | 3.3546 |  |  | 6.6023 | 12.8604 | 17.9357 | 17.9357 | 17.9357 | 17.9357 | 17.9357 | 17.9357 | 6.6023 | 12.8604 | 18.4356 | 18.4356 | 18.4356 | 18.4356 | 18.4356 | 18.4356 |  | No | Other | AMP7 carryover
| TMS | Slough STW WW Quality AMP7 New Permit | K222 | THM00672 (7TW200833) THM00099 (7TW200261) | Ammonia FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2020-11-30 | 2024-02-28 | 2025-05-30 | 2026-04-30 | 2029-05-31 | 2029-06-30 |  | IM2 | 2020-11-30 | 2023-07-30 | 2025-01-28 | 2026-01-28 | 2029-03-01 | 2030-03-31 |  |  | 6.961 | 53.8248 |  |  | 3.0856 | 3.8754 | 8.4705 | 27.0134 | 51.4712 | 75.1243 | 75.8345 | 75.8345 | 3.0856 | 3.8754 | 7.6881 | 21.7889 | 38.3285 | 53.3315 | 53.8248 | 53.8248 |  | No | Other | AMP7 carryover
| TMS | Oxford STW AMP 7 | K245 | 7TW200883 7TW200912 | Ammonia FTFT | PCDWW35 | Retained |  | 2025-03-31 | 2025-03-31 | 2021-04-30 | 2022-01-31 | 2025-12-31 | 2027-03-30 | 2032-03-30 | 2032-02-29 |  | IM2 | 2024-09-18 | 2024-10-03 | 2025-12-31 | 2027-03-30 | 2030-03-31 | 2029-12-24 |  |  | 18.7404 | 176.2376 |  |  | 7.935 | 10.8054 | 14.5077 | 37.4351 | 77.4519 | 118.5384 | 160.2726 | 282.4933 | 7.935 | 10.8054 | 12.5248 | 26.089 | 48.5308 | 71.9076 | 95.6829 | 176.2376 |  | No | Other | AMP7 carryover
| TMS | Croughton STW P-Removal | K428.01 | THM00660 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | N/A | 2025-03-31 | 2021-01-21 | 2021-06-23 | 2025-09-30 | 2025-10-01 | 2026-10-22 | 2026-10-25 |  | IM2 | 2021-01-21 | 2021-06-23 | 2025-07-30 | 2025-07-31 | 2026-08-21 | 2026-09-14 |  |  | 1.2282 | 2.1057 |  |  | 0.69881 | 1.2221 | 2.5222 | 3.2881 | 3.3067 | 3.3113 | 3.3113 | 3.3113 | 0.69881 | 1.2221 | 3.0261 | 3.3127 | 3.333 | 3.3338 | 3.3338 | 3.3338 |  | No | Other | AMP7 carryover
| TMS | Banbury STW FTFT and Low P | K435.01 | THM00088 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-15 | 2026-03-20 | 2026-06-26 | 2029-04-03 | 2029-05-29 |  | IM1 | 2019-06-18 | 2025-10-23 | 2026-05-20 | 2026-07-27 | 2029-07-18 | 2029-03-29 |  |  | 0.80151 | 24.3724 |  |  | 0.6596 | 0.77096 | 1.5166 | 3.3602 | 7.1484 | 9.1462 | 9.2602 | 9.3217 | 0.6596 | 0.77096 | 1.9487 | 9.6508 | 18.0226 | 24.5147 | 25.0094 | 25.1739 |  | No | Other | AMP7 carryover
| TMS | Banbury STW FTFT and Low P | K435.01 | THM00078 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-15 | 2026-03-20 | 2026-06-26 | 2029-04-03 | 2029-05-29 |  | IM1 | 2019-06-18 | 2025-10-23 | 2026-05-20 | 2026-07-27 | 2029-07-18 | 2029-03-29 | [23 empty] | No | Other | AMP7 carryover
| TMS | WWNI Therfield STW Storm Tank & Low P | K440.01 | HNL00219 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2024-12-22 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-05-14 | 2027-05-22 |  | IM4 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-05-14 | 2027-03-22 |  |  | 4.8188 | 12.4086 |  |  | 1.5159 | 3.8484 | 10.6087 | 15.127 | 15.8579 | 15.8579 | 15.8579 | 15.8579 | 1.5159 | 3.8484 | 12.1187 | 16.4844 | 17.2274 | 17.2274 | 17.2274 | 17.2274 |  | No | Other | AMP7 carryover
| TMS | WWNI Therfield STW Storm Tank & Low P | K440.01 | FLO01297 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2025-03-31 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-05-14 | 2027-05-22 |  | IM4 | 2019-06-18 | 2021-05-25 | 2024-06-28 | 2024-09-19 | 2027-05-14 | 2027-03-22 | [23 empty] | No | Other | AMP7 carryover
| TMS | Bourton on the Water STW FTFT & St. Tank | K445.01 | FLO01241 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2026-06-01 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2026-11-12 | 2026-09-01 |  |  | 17.8056 | 9.5065 |  |  | 8.6974 | 16.9054 | 26.5415 | 27.3071 | 27.3071 | 27.3071 | 27.3071 | 27.3071 | 8.6974 | 16.9054 | 26.2564 | 27.2981 | 27.3121 | 27.3121 | 27.3121 | 27.3121 |  | No | Other | AMP7 carryover
| TMS | Bourton on the Water STW FTFT & St. Tank | K445.01 | FLO01242 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2026-06-01 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-12-20 | 2023-04-21 | 2023-08-16 | 2026-11-12 | 2026-09-01 | [23 empty] | No | Other | AMP7 carryover
| TMS | WWNI Bampton STW FTFT | K450.01 | FLO01235 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-06-30 | 2026-04-09 | 2026-04-23 | 2028-03-20 | 2028-03-17 |  | IM2 | 2019-06-18 | 2021-06-30 | 2026-04-09 | 2026-04-23 | 2028-03-20 | 2028-01-17 |  |  | 0.62547 | 4.9092 |  |  | 0.27335 | 0.52918 | 0.92041 | 3.2872 | 5.4674 | 5.5037 | 5.5037 | 5.5037 | 0.27335 | 0.52918 | 0.968 | 3.3262 | 5.4985 | 5.5347 | 5.5347 | 5.5347 |  | No | Other | AMP7 carryover
| TMS | WWNI Fairford STW FTFT | K452.01 | THM00095 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2023-04-20 | 2026-04-01 | 2026-04-16 | 2027-12-09 | 2028-01-17 |  | IM2 | 2019-06-18 | 2023-04-20 | 2026-04-01 | 2026-04-16 | 2027-12-09 | 2027-11-17 |  |  | 0.86613 | 11.3291 |  |  | 0.47775 | 0.67996 | 1.409 | 8.2911 | 12.1138 | 12.2216 | 12.2216 | 12.2216 | 0.47775 | 0.67996 | 1.4321 | 8.2789 | 12.0878 | 12.1952 | 12.1952 | 12.1952 |  | No | Other | AMP7 carryover
| TMS | WWNI Cricklade STW FTFT & Storm Tank | K455.01 | FLO01257 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2024-11-30 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-11-30 | 2026-11-30 |  | IM4 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-11-30 | 2026-09-30 |  |  | 3.556 | 3.0558 |  |  | 2.0403 | 3.2269 | 6.4141 | 6.4141 | 6.4141 | 6.4141 | 6.4141 | 6.4141 | 2.0403 | 3.2269 | 5.1914 | 6.6118 | 6.6118 | 6.6118 | 6.6118 | 6.6118 |  | No | Other | AMP7 carryover
| TMS | WWNI Cricklade STW FTFT & Storm Tank | K455.01 | FLO01256 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2024-11-30 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-11-30 | 2026-11-30 |  | IM4 | 2019-05-25 | 2019-07-21 | 2023-02-02 | 2024-10-18 | 2026-11-30 | 2026-09-30 | [23 empty] | No | Other | AMP7 carryover
| TMS | WWNI Milton Under Wychwood STW FTFT | K540.01 | FLO01283 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-25 | 2024-12-20 | 2025-01-29 | 2026-09-10 | 2026-09-08 |  | IM4 | 2019-06-18 | 2021-08-25 | 2024-12-20 | 2025-01-29 | 2027-07-16 | 2026-08-27 |  |  | 2.7086 | 7.5528 |  |  | 0.35489 | 1.6235 | 8.3004 | 9.2782 | 9.2782 | 9.2782 | 9.2782 | 9.2782 | 0.35489 | 1.6235 | 8.2683 | 10.0925 | 10.2614 | 10.2614 | 10.2614 | 10.2614 |  | No | Other | AMP7 carryover
| TMS | WWNI Drayton STW FTFT Storm Tank & G2G | K543.01 | THM00105 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2026-07-24 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2027-05-13 | 2027-01-15 |  |  | 7.3881 | 12.8574 |  |  | 2.4221 | 5.7593 | 16.337 | 16.9375 | 16.9375 | 16.9375 | 16.9375 | 16.9375 | 2.4221 | 5.7593 | 19.3653 | 20.2456 | 20.2456 | 20.2456 | 20.2456 | 20.2456 |  | No | Other | AMP7 carryover
| TMS | WWNI Drayton STW FTFT Storm Tank & G2G | K543.01 | THM00094 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2026-07-24 | 2026-05-31 |  | IM4 | 2019-06-18 | 2021-08-25 | 2024-02-01 | 2024-02-29 | 2027-05-13 | 2027-01-15 | [23 empty] | No | Other | AMP7 carryover
| TMS | WWNI Cirencester STW FtFT & Storm Tank | K552.01 | FLO01254 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2025-03-31 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2026-03-24 | 2026-04-27 |  | IM4 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2026-09-22 | 2026-09-01 |  |  | 19.8538 | 6.1747 |  |  | 11.7339 | 18.731 | 27.664 | 27.664 | 27.664 | 27.664 | 27.664 | 27.664 | 11.7339 | 18.731 | 24.2789 | 26.0285 | 26.0285 | 26.0285 | 26.0285 | 26.0285 |  | No | Other | AMP7 carryover
| TMS | WWNI Cirencester STW FtFT & Storm Tank | K552.01 | THM00093 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2026-03-24 | 2026-04-27 |  | IM4 | 2019-06-18 | 2021-09-22 | 2023-03-27 | 2023-09-28 | 2026-09-22 | 2026-09-01 | [23 empty] | No | Other | AMP7 carryover
| TMS | WWNI LITTLE HALLINGBURY STW P-removal | K556.08 | HNL00227 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2023-05-15 | 2021-10-26 | 2025-09-22 | 2025-10-10 | 2027-04-26 | 2027-04-15 |  | IM2 | 2023-05-15 | 2021-10-26 | 2025-11-18 | 2025-12-08 | 2027-04-26 | 2027-02-15 |  |  | 0.64597 | 4.5283 |  |  | 0.66337 | 0.024487 | 2.5236 | 5.266 | 5.4567 | 5.4697 | 5.4697 | 5.4697 | 0.66337 | 0.024487 | 1.7196 | 4.9529 | 5.1614 | 5.1743 | 5.1743 | 5.1743 |  | No | Other | AMP7 carryover
| TMS | WWNI Upper Heyford STW FTFT | K568.01 | FLO01272 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-08-31 | 2023-07-03 | 2023-09-04 | 2025-12-01 | 2025-12-24 |  | IM4 | 2019-06-18 | 2021-08-31 | 2023-07-03 | 2023-09-04 | 2026-03-03 | 2026-01-26 |  |  | 0.65972 | 0.63062 |  |  | 0.48303 | 0.60577 | 1.2767 | 1.2767 | 1.2767 | 1.2767 | 1.2767 | 1.2767 | 0.48303 | 0.60577 | 1.2903 | 1.2903 | 1.2903 | 1.2903 | 1.2903 | 1.2903 |  | No | Other | AMP7 carryover
| TMS | Takeley STW WAAP | K645.01 | HNL00228 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | N/A | 2024-12-22 | 2019-07-17 | 2024-04-17 | 2025-08-27 | 2025-09-29 | 2026-06-30 | 2026-05-31 |  | IM2 | 2019-07-17 | 2024-04-17 | 2025-08-27 | 2025-09-29 | 2026-06-30 | 2026-03-31 |  |  | 0.41154 | 2.3662 |  |  | 0.10754 | 0.35881 | 2.0795 | 2.6664 | 2.7295 | 2.7295 | 2.7295 | 2.7295 | 0.10754 | 0.35881 | 2.13 | 2.7148 | 2.7777 | 2.7777 | 2.7777 | 2.7777 |  | No | Other | AMP7 carryover
| TMS | WWNI Henley STW FTFT | K650.01 | FLO01271 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-10-26 | 2024-09-23 | 2024-11-29 | 2026-12-21 | 2026-11-30 |  | IM4 | 2019-06-18 | 2021-10-26 | 2024-09-23 | 2024-11-29 | 2026-12-21 | 2026-09-30 |  |  | 3.399 | 7.5226 |  |  | 0.49833 | 2.2467 | 6.6364 | 10.9205 | 10.9274 | 10.9274 | 10.9274 | 10.9274 | 0.49833 | 2.2467 | 8.6084 | 10.9146 | 10.9215 | 10.9215 | 10.9215 | 10.9215 |  | No | Other | AMP7 carryover
| TMS | WWNI Leatherhead STW FTFT | K676.01 | KSL00279 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2025-05-22 | 2026-03-26 | 2026-10-16 | 2028-09-11 | 2028-09-24 |  | IM1 | 2019-06-18 | 2025-07-17 | 2026-04-27 | 2026-11-13 | 2028-10-10 | 2028-08-21 |  |  | 1.5932 | 25.5503 |  |  | 1.0108 | 1.4754 | 2.72 | 8.0963 | 22.0738 | 26.6002 | 27.3439 | 27.3439 | 1.0108 | 1.4754 | 2.7014 | 7.9515 | 18.2972 | 25.1037 | 27.1435 | 27.1435 |  | No | Other | AMP7 carryover
| TMS | Moreton in Marsh STW G2G & Storm Tank | K758.01 | FLO01284 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2022-03-03 | 2026-06-22 | 2026-09-07 | 2029-04-06 | 2029-03-31 |  | IM2 | 2019-06-18 | 2022-03-03 | 2026-08-28 | 2026-11-13 | 2029-04-06 | 2029-01-31 |  |  | 0.56727 | 9.683 |  |  | 0.44262 | 0.52056 | 0.87961 | 2.5917 | 6.076 | 8.9395 | 10.2495 | 10.262 | 0.44262 | 0.52056 | 0.92546 | 2.9129 | 6.2852 | 8.8962 | 10.2377 | 10.2502 |  | No | Other | AMP7 carryover
| TMS | WWNI Hogsmill STW Storm Tank | K760.01 | FLO01273 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2025-04-17 | 2026-01-02 | 2026-06-22 | 2028-02-24 | 2028-03-06 |  | IM2 | 2019-06-18 | 2025-04-17 | 2026-04-29 | 2026-05-22 | 2028-02-21 | 2027-12-24 |  |  | 1.7728 | 62.8994 |  |  | 1.3482 | 1.8856 | 5.1258 | 30.9349 | 53.5305 | 55.4749 | 55.8855 | 55.8855 | 1.3482 | 1.8856 | 3.0278 | 16.305 | 35.7922 | 55.233 | 64.6722 | 64.6722 |  | No | Other | AMP7 carryover
| TMS | WWNI Earlswood (Reigate) STW FtFT | K934.01 | FLO01264 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2022-06-22 | 2024-08-06 | 2025-02-14 | 2028-06-16 | 2028-07-10 |  | IM4 | 2019-06-18 | 2022-06-22 | 2024-08-06 | 2025-02-14 | 2028-06-16 | 2028-05-10 |  |  | 8.224 | 4.1687 |  |  | 2.0765 | 6.7791 | 10.9032 | 12.8193 | 13.2451 | 13.2451 | 13.2451 | 13.2451 | 2.0765 | 6.7791 | 10.7665 | 11.9341 | 12.3684 | 12.3926 | 12.3926 | 12.3926 |  | No | Other | AMP7 carryover
| TMS | WWNI Chieveley STW Low P & DWF | K982.01 | THM00065 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2021-05-26 | 2023-06-15 | 2026-05-20 | 2026-06-02 | 2027-07-28 | 2027-07-27 |  | IM2 | 2021-05-26 | 2023-06-15 | 2026-05-20 | 2026-06-02 | 2027-07-28 | 2027-05-27 |  |  | 0.26859 | 11.2303 |  |  | 0.14588 | 0.16792 | 1.4098 | 9.2869 | 11.3127 | 11.5515 | 11.5515 | 11.5515 | 0.14588 | 0.16792 | 1.1352 | 9.2425 | 11.2609 | 11.4989 | 11.4989 | 11.4989 |  | No | Other | AMP7 carryover
| TMS | WWNI Chinnor STW Pollutions scope | L040.01 | FLO01251 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2023-03-31 | 2024-11-30 | 2022-02-22 | 2022-06-08 | 2025-07-18 | 2025-08-11 | 2026-05-29 | 2026-07-05 |  | IM2 | 2022-02-22 | 2022-06-08 | 2025-07-18 | 2025-08-22 | 2026-11-30 | 2026-05-05 |  |  | 1.295 | 3.9394 |  |  | 0.5386 | 0.89122 | 2.9042 | 5.4054 | 5.4054 | 5.4054 | 5.4054 | 5.4054 | 0.5386 | 0.89122 | 2.315 | 5.2344 | 5.2344 | 5.2344 | 5.2344 | 5.2344 |  | No | Other | AMP7 carryover
| TMS | Faringdon Storm and Siphon | L057.01 | FLO01267 | Storm Tank | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2025-03-31 | 2019-06-18 | 2022-09-23 | 2024-06-28 | 2025-05-02 | 2026-05-13 | 2026-05-06 |  | IM3 | 2019-06-18 | 2022-09-23 | 2024-06-28 | 2025-07-21 | 2026-07-14 | 2026-05-11 |  |  | 2.057 | 4.5602 |  |  | 0.57167 | 1.7141 | 6.1584 | 6.327 | 6.3293 | 6.3293 | 6.3293 | 6.3293 | 0.57167 | 1.7141 | 6.4223 | 6.6149 | 6.6172 | 6.6172 | 6.6172 | 6.6172 |  | No | Other | AMP7 carryover
| TMS | Hatfield Heath STW WAAP and P-Removal | L473.01 | HNL00229 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2021-10-26 | 2025-04-17 | 2025-09-11 | 2027-10-26 | 2027-10-16 |  | IM3 | 2020-10-06 | 2021-10-26 | 2025-05-22 | 2025-09-11 | 2027-10-26 | 2025-04-30 |  |  | 3.7919 | 11.7485 |  |  | 2.319 | 3.3629 | 8.8249 | 14.2199 | 17.7941 | 17.8886 | 17.8886 | 17.8886 | 2.319 | 3.3629 | 8.1159 | 12.6615 | 15.4687 | 15.5405 | 15.5405 | 15.5405 |  | No | Other | AMP7 carryover
| TMS | Boxford STW Low P | L693.01 | THM00064 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-06-18 | 2021-11-24 | 2025-08-18 | 2025-11-26 | 2028-02-07 | 2027-12-29 |  | IM2 | 2019-06-18 | 2021-11-24 | 2025-09-30 | 2026-02-11 | 2028-02-07 | 2027-10-29 |  |  | 1.5042 | 9.2498 |  |  | 0 | 1.2518 | 2.4369 | 7.7375 | 9.7091 | 10.0701 | 10.0701 | 10.0701 | 0 | 1.2518 | 3.2692 | 7.6672 | 10.3944 | 10.754 | 10.754 | 10.754 |  | No | Other | AMP7 carryover
| TMS | Manuden STW Low P | L710.01 | HNL00224 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-01-09 | 2026-02-03 | 2028-07-13 | 2028-05-27 |  | IM2 | 2020-10-06 | 2024-09-18 | 2025-12-23 | 2026-01-20 | 2028-06-29 | 2028-03-13 |  |  | 1.7266 | 7.8573 |  |  | 0 | 1.5648 | 2.8467 | 6.3543 | 10.7468 | 10.9817 | 11.1535 | 11.1535 | 0 | 1.5648 | 3.6293 | 6.3169 | 9.2357 | 9.4243 | 9.5839 | 9.5839 |  | No | Other | AMP7 carryover
| TMS | Moreton STW Low P | L711.01 | HNL00210 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-02-26 | 2026-06-11 | 2028-06-14 | 2028-05-03 |  | IM2 | 2020-10-06 | 2024-09-18 | 2026-03-26 | 2026-07-15 | 2028-07-18 | 2028-04-06 |  |  | 0.70134 | 4.3602 |  |  | 0 | 0.67295 | 1.672 | 2.8065 | 5.7047 | 5.8457 | 5.9479 | 5.9479 | 0 | 0.67295 | 1.527 | 2.2638 | 4.7833 | 4.9403 | 5.0616 | 5.0616 |  | No | Other | AMP7 carryover
| TMS | Clavering STW Low P | L719.01 | HNL00223 | P - Green | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-10-06 | 2024-09-18 | 2026-02-05 | 2026-05-12 | 2028-08-15 | 2028-07-02 |  | IM2 | 2020-10-06 | 2024-09-18 | 2026-01-27 | 2026-04-14 | 2028-07-19 | 2028-03-31 |  |  | 1.7244 | 6.9099 |  |  | 0 | 1.6471 | 2.4936 | 4.4242 | 9.661 | 9.9556 | 10.123 | 10.123 | 0 | 1.6471 | 3.1394 | 4.8763 | 8.2846 | 8.483 | 8.6343 | 8.6343 |  | No | Other | AMP7 carryover
| TMS | Cholsey - FtFT & ST | K098.01 | FLO01252 | FTFT | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-03-31 | 2023-03-31 | 2019-06-18 | 2020-11-25 | 2021-11-18 | 2022-03-30 | 2025-02-28 | 2025-07-30 |  | IM5 | 2019-06-18 | 2020-11-25 | 2021-11-18 | 2022-03-30 | 2025-02-28 | 2025-09-30 |  |  | 8.1886 | 0.046477 |  |  | 7.6259 | 8.1363 | 8.1873 | 8.1873 | 8.1873 | 8.1873 | 8.1873 | 8.1873 | 7.6259 | 8.1363 | 8.2351 | 8.2351 | 8.2351 | 8.2351 | 8.2351 | 8.2351 |  | No | Other | AMP7 carryover
| TMS | Fish passage at Fobney Turbine House | K558.01 | THM00690 | Improving fish passage on the river Kennet at the turbine house structure. | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-12-31 | 2025-12-31 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-10-24 | 2027-04-21 | 2027-05-31 |  | IM3 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2026-01-27 | 2027-04-21 | 2027-03-31 |  |  | 1.652 | 7.425 |  |  | 0.95533 | 1.5282 | 4.6307 | 9.1237 | 9.1237 | 9.1237 | 9.1237 | 9.1237 | 0.95533 | 1.5282 | 3.075 | 9.0775 | 9.0775 | 9.0775 | 9.0775 | 9.0775 | merge ok | No | Other | AMP7 carryover
| TMS | Fish passage at Glenfield Gate weir on the Cherwell d/s of Grimsbury Reservoir abstraction | K558.02 | THM00691 | Improving fish passage on the river Cherwell at Glenfield Gate | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2020-05-13 | 2023-06-01 | 2023-06-01 | 2025-08-14 | 2027-06-17 | 2027-05-31 |  | IM3 | 2020-05-13 | 2023-06-01 | 2023-06-01 | 2025-11-10 | 2027-06-17 | 2027-03-31
| TMS | Fish Passage at River Pang at Pangbourne WTW | K558.03 | THM00692 | Improving fish passage on the river Pang at Pang Water Treatment Works | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-08-14 | 2027-06-17 | 2027-05-31 |  | IM3 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-11-10 | 2027-06-17 | 2027-03-31 |  |  | 0 | 0
| TMS | Fish Passage on the River Thames at Tangier Mill | K558.04 | THM00694 | Improving fish passage on the river Thames at Tangier Mill | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-09-01 | 2027-06-17 | 2027-05-31 |  | IM3 | 2020-05-13 | 2022-03-16 | 2023-06-01 | 2025-11-10 | 2027-06-17 | 2027-03-31
| TMS | Hogsmill Biodiversity (WINEP) | L443.01 | KSL00092 | Improving habitat for water voles on riparian habitat around the Hogsmill STW discharge | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2025-03-31 | 2025-03-31 | 2019-09-26 | 2023-06-20 | 2024-12-06 | 2026-02-09 | 2027-01-20 | 2027-02-11 |  | IM3 | 2019-09-26 | 2023-06-20 | 2024-12-06 | 2026-04-27 | 2027-01-20 | 2026-12-11 |  |  | 0.61413 | 2.1947 |  |  | 0.12331 | 0.46117 | 1.0298 | 2.7626 | 2.7626 | 2.7626 | 2.7626 | 2.7626 | 0.12331 | 0.46117 | 1.321 | 2.8088 | 2.8088 | 2.8088 | 2.8088 | 2.8088 |  | No | Other | AMP7 carryover
| TMS | Nitrates Reduction Lee (Rye Meads) | K562.01 | HNL00262 | Reduction in nitrates in Rye Meads STW effluent discharge to improve water quality at lower Lee abstraction points | AMP7 Delivery Plan (no AMP8 PCD) | Retained |  | 2024-12-22 | 2024-12-22 | 2020-11-02 | 2023-03-22 | 2026-04-13 | 2027-01-29 | 2030-06-20 | 2030-07-01 |  | IM2 | 2020-11-02 | 2023-03-22 | 2026-04-13 | 2027-01-29 | 2030-06-20 | 2030-05-01 |  |  | 1.2175 | 23.0954 |  |  | 0.5656 | 1.0386 | 1.626 | 3.0789 | 7.0648 | 19.6442 | 23.832 | 24.2611 | 0.5656 | 1.0386 | 1.7324 | 3.2075 | 7.179 | 19.7128 | 23.8853 | 24.3129 |  | No | Other | AMP7 carryover

## DPB1
DPB1 | [39 empty] | Ofwat Bon Numbers
DPB
Base PCD outputs
Header | Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | PCD output (cumulative) - Target | [10 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP reference |  | PCD output (cumulative) - Target | [10 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Performance
[8 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Target) | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | PCD output by 2029-30 (Outturn & Forecast) | PCD Output by 2034-35 (Outturn & Forecast) | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%)
Start_Data | [7 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [7 empty] | Start_BON | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals in kilometres | km | 3 |  | 73.2344 | 170.8802 | 292.9374 | 390.5832 | 488.229 | [5 empty] | 488.229 | 0 |  | 80.891 | 183.972 | 295.236 | 391.599 | 488.23 | [5 empty] | 488.23 | 0 | 100% |  |  | Green | DPB1.1 |  | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE | PCD_DPB1_MRBASE_T | PCD_DPB1_MRBASE_T | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_O | PCD_DPB1_MRBASE_OT | PCD_DPB1_MRBASE_OT | PCD_DPB1_MRBASE_P | PCD_DPB1_MRBASE_P
|  |  | PCDB1b | Mains renewals - asset health adjustment | Base asset health adjustment renewals in kilometres | km | 3 |  | 9.1088 | 21.2538 | 36.4351 | 48.5801 | 60.7251 | [5 empty] | 60.7251 | 0 |  | 5.333 | 16.718 | 31.913 | 48.551 | 60.835 | [5 empty] | 60.835 | 0 | 100.2% |  |  | Green | DPB1.2 |  | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH | PCD_DPB1_MRAH_T | PCD_DPB1_MRAH_T | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_O | PCD_DPB1_MRAH_OT | PCD_DPB1_MRAH_OT | PCD_DPB1_MRAH_P | PCD_DPB1_MRAH_P
|  |  | PCDB1c | Mains renewals - enhancement leakage | Enhancement leakage renewals in kilometres | km | 3 |  | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  |  |  | DPB1.3 |  | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA | PCD_DPB1_MRENHLEA_T | PCD_DPB1_MRENHLEA_T | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_O | PCD_DPB1_MRENHLEA_OT | PCD_DPB1_MRENHLEA_OT | PCD_DPB1_MRENHLEA_P | PCD_DPB1_MRENHLEA_P

## TMS_DPB1_ADD
TMS_DPB1_ADD | [38 empty] | Ofwat Bon Numbers
TMS
Base PCD outputs
| Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | PCD output (cumulative) - Target | [10 empty] | PCD Output Target by 2029-30 | PCD Output Target by 2034-35 | PCD output (cumulative) - Outturn & Forecast | [10 empty] | PCD Output Outturn & Forecast by 2029-30 | PCD Output Outturn & Forecast by 2034-35 | Performance |  |  |  | DP reference | [11 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Outturn & Forecast) | [11 empty] | PCD output by 2029-30 (Target) | PCD Output by 2034-35 (Outturn & Forecast)
[8 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast delivery as a percentage of PCD output target in 2029-30 (%) | Forecast delivery as a percentage of PCD output target in 2034-35 (%) | RAG Rating - Assurer's view | RAG Rating - Company's own view |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 | AMP8 |  |  |  |  | AMP9
[8 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [7 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
|  | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals in kilometres - Thames Valley | km | 3 | AMP8 2025-26: 33.6878; AMP8 2026-27: 78.6049; AMP8 2027-28: 134.7512; AMP8 2028-29: 179.6683; AMP8 2029-30: 224.5854 | 224.5854 | 0 |  | 23.176 | 73.533 | 123.897 | 174.247 | 224.596 | [5 empty] | 224.596 | 0 | 100% |  |  | Green | DPB1.1
|  |  | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals in kilometres - London | km | 3 | AMP8 2025-26: 39.5466; AMP8 2026-27: 92.2753; AMP8 2027-28: 158.1862; AMP8 2028-29: 210.9149; AMP8 2029-30: 263.6437 | 263.6437 | 0 |  | 57.715 | 110.439 | 171.339 | 217.352 | 263.634 | [5 empty] | 263.634 | 0 | 100% |  |  | Green | DPB1.1

## DPB2
DPB2 | [40 empty] | Ofwat Bon Numbers
DPB
Base PCD expenditure
Header | Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance
[9 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  |  |  | Non delivery PCD payment (£m/Driver) in 2022-23 prices | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 |  |  |  |  | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%)
Start_Data | [8 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [6 empty] | Start_BON | 2025-30 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | 2029-30 | 2034-35 | 2029-30 | 2034-35
| TMS | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals expenditure | £m | 3 |  |  | 55.5668 | 129.656 | 222.2674 | 296.3565 | 370.4457 | [5 empty] | 370.4457 | 0 |  | 98.2473 | 224.8796 | 370.4588 | 489.7312 | 616.0568 | [5 empty] | 616.0568 | 0 | 166.3% |  | DPB2.1 |  |  | PCD_DPB2_MR_BASE_NP | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE | PCD_DPB2_MR_BASE_T | PCD_DPB2_MR_BASE_T | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_O | PCD_DPB2_MR_BASE_OT | PCD_DPB2_MR_BASE_OT | PCD_DPB2_MR_BASE_P | PCD_DPB2_MR_BASE_P
|  |  | PCDB1b | Mains renewals - asset health adjustment | Base asset health adjustment renewals expenditure | £m | 3 |  |  | 10.5203 | 24.5474 | 42.0812 | 56.1083 | 70.1354 | [5 empty] | 70.1354 | 0 |  | 6.7004 | 27.5305 | 52.2788 | 78.8509 | 100.3089 | [5 empty] | 100.3089 | 0 | 143% |  | DPB2.2 |  |  | PCD_DPB2_MR_AH_NP | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH | PCD_DPB2_MR_AH_T | PCD_DPB2_MR_AH_T | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_O | PCD_DPB2_MR_AH_OT | PCD_DPB2_MR_AH_OT | PCD_DPB2_MR_AH_P | PCD_DPB2_MR_AH_P
|  |  | PCDB1c | Mains renewals - enhancement leakage | Enhancement leakage renewals expenditure | £m | 3 | [6 empty] | 0 | [5 empty] | 0 | 0 | [11 empty] | 0 | 0 |  |  | DPB2.3 |  |  | PCD_DPB2_MR_ENHLEA_NP | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA | PCD_DPB2_MR_ENHLEA_T | PCD_DPB2_MR_ENHLEA_T | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_O | PCD_DPB2_MR_ENHLEA_OT | PCD_DPB2_MR_ENHLEA_OT | PCD_DPB2_MR_ENHLEA_P | PCD_DPB2_MR_ENHLEA_P
|  |  | PCDB3a | Water network reinforcement | Water network reinforcement expenditure | £m | 3 |  |  | 31.5204 | 62.7508 | 94.0153 | 125.1037 | 155.9137 | [5 empty] | 155.9137 | 0 |  | 44.5061 | 89.6657 | 119.3526 | 145.14 | 161.1974 | [5 empty] | 161.1974 | 0 | 103.4% |  | DPB2.4 |  |  | PCD_DPB2_WN_RFT_NP | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT | PCD_DPB2_WN_RFT_T | PCD_DPB2_WN_RFT_T | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_O | PCD_DPB2_WN_RFT_OT | PCD_DPB2_WN_RFT_OT | PCD_DPB2_WN_RFT_P | PCD_DPB2_WN_RFT_P
|  |  | PCDB3b | Wastewater network reinforcement | Wastewater network reinforcement expenditure | £m | 3 |  |  | 24.5146 | 48.9294 | 73.2562 | 97.5065 | 121.6776 | [5 empty] | 121.6776 | 0 |  | 20.3278 | 51.1941 | 66.3807 | 87.2963 | 123.9399 | [5 empty] | 123.9399 | 0 | 101.9% |  | DPB2.5 |  |  | PCD_DPB2_WWN_RFT_NP | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT | PCD_DPB2_WWN_RFT_T | PCD_DPB2_WWN_RFT_T | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_O | PCD_DPB2_WWN_RFT_OT | PCD_DPB2_WWN_RFT_OT | PCD_DPB2_WWN_RFT_P | PCD_DPB2_WWN_RFT_P
[38 empty] | End_Data | [30 empty] | End_BON

## TMS_DPB2_ADD
TMS_DPB2_ADD | [37 empty] | Ofwat Bon Numbers
TMS
Base PCD expenditure
| Company | PCD Model | PCD Ref | Line description | PCD Output Description | Units | DPs | Non delivery PCD payment (£m/Driver) in 2022-23 prices | PCD Total Expenditure (Cumulative) - Allowance (£m) | [10 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Allowance) | PCD Total Expenditure (Cumulative) - Outturn & Forecast (£m) | [10 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast) | Performance |  | DP reference | [11 empty] | Total Expenditure by 2029-30 (Allowance) | Total Expenditure by 2034-35 (Outturn & Forecast) | [11 empty] | Total Expenditure by 2029-30 (Outturn & Forecast) | Total Expenditure by 2034-35 (Outturn & Forecast)
[9 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre-AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Forecast total expenditure as a percentage of allowed total expenditure in 2029-30 (%) | Forecast total expenditure as a percentage of allowed total expenditure in 2034-35 (%) |  | Pre- AMP8 | AMP8 |  |  |  |  | AMP9 | [6 empty] | Pre- AMP8 | AMP8 |  |  |  |  | AMP9
[9 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 | [5 empty] | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35 |  |  | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | 2031-32 | 2032-33 | 2033-34 | 2034-35
|  | PR24CA105 Base PCDs | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals expenditure - Thames Valley | £m | 3 |  | AMP8 2029-30: 65.9462 | 65.9462 | 0 |  | 23.8908 | 66.8395 | 109.7195 | 152.5716 | 195.2028 | [5 empty] | 195.2028 | 0 | 296% |  | DPB2.1
|  |  | PCDB1a | Mains renewals - base | Base wholesale water model funded renewals expenditure - London | £m | 3 |  | AMP8 2029-30: 304.4995 | 304.4995 | 0 |  | 74.3566 | 158.0402 | 260.7393 | 337.1597 | 420.854 | [5 empty] | 420.854 | 0 | 138.2% |  | DPB2.1